## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block | TSM/006793 | SM/07426 | Retrofitting | 04/12/2020 | 1336 | 57.56 | Yes | 57.56 | 27/07/2023 | 02/08/2021 | 3 | 56.45 | MVS
2 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Khudiram Pally-I, khudiram Pally-II, Rail cly & Sree Colony Habitation of Dumriguri Piped W/S Supply Scheme ( Part-B ) at Naxalbari Block | TSM/006796 | SM/07427 | Retrofitting | 04/12/2020 | 1560 | 82.41 | Yes | 82.41 |  |  | 0 | 0 | MVS
3 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Matidhar Bijmillini T.E and Pathoria Habitation of Paschim Madati Piped water Supply Scheme (Part - A) | TSM/006169 | SM/07031 | Retrofitting | 25/09/2020 | 1649 | 85.56 | Yes | 85.56 |  | 18/12/2020 | 1 | 33.72 | MVS
4 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Dhakpara village of Budharugaon Piped water Supply Scheme | TSM/006144 | SM/07214 | Retrofitting | 25/09/2020 | 751 | 55.85 | Yes | 55.85 | 25/02/2025 | 24/04/2025 | 2 | 55.18 | MVS
5 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u | TSM/007269 | SM/08295 | Retrofitting | 10/02/2021 | 1690 | 85.65 | Yes | 85.65 |  | 19/12/2022 | 3 | 2.49 | MVS
6 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division | TSM/009298 | SM/10767 | Retrofitting | 27/01/2022 | 130 | 16.01 | Yes | 16.01 |  | 24/05/2022 | 2 | 14.84 | MVS
7 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village | TSM/009470 | SM/10771 | Retrofitting | 27/01/2022 | 23 | 14.21 | Yes | 14.21 |  | 24/05/2022 | 4 | 14.18 | MVS
8 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan mission / Jal sapno Programme from existing scheme at 3rd mile , Simkuna | TSM/011136 | SM/11380 | Retrofitting | 30/03/2022 | 45 | 10.66 | Yes | 10.66 |  | 12/07/2022 | 2 | 9.57 | MVS
9 | DARJEELING | Neorakhola W/S Mnt. Division | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | TSM/011135 | SM/11381 | Retrofitting | 30/03/2022 | 520 | 76.94 | Yes | 76.94 | 24/04/2023 | 12/07/2022 | 4 | 76.68 | MVS
10 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under Jal Jeewan Mission/ Jal Swapno Programme at New Fallodi Tea Garden ( Mandir Goan) | TSM/011140 | SM/11390 | Retrofitting | 30/03/2022 | 45 | 10.66 | Yes | 10.66 |  | 12/07/2022 | 1 | 9.11 | MVS
11 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | TSM/011216 | SM/11399 | New | 30/03/2022 | 446 | 562.88 | Yes | 562.88 |  | 04/05/2023 | 2 | 356.95 | MVS
12 | DARJEELING | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME | TSM/010340 | SM/11775 | New | 25/04/2022 | 350 | 157.45 | Yes | 157.45 | 07/12/2022 | 20/05/2022 | 6 | 117.34 | MVS
13 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA | TSM/009858 | SM/10800 | New | 17/02/2022 | 233 | 143.69 | Yes | 143.69 |  | 09/04/2025 | 3 | 106.71 | MVS
14 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA | TSM/009857 | SM/10801 | New | 17/02/2022 | 233 | 163.3 | Yes | 163.3 |  | 05/08/2022 | 2 | 100.88 | MVS
15 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, | TSM/009603 | SM/11316 | Retrofitting | 17/02/2022 | 51 | 7.68 | Yes | 7.68 |  | 30/06/2022 | 2 | 7.09 | MVS
16 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA | TSM/010595 | SM/11334 | Retrofitting | 17/02/2022 | 246 | 33.35 | Yes | 33.35 |  | 30/06/2022 | 2 | 28.17 | MVS
17 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | TSM/012578 | SM/11944 | New | 20/05/2022 | 818 | 923.75 | Yes | 923.75 |  | 16/08/2023 | 4 | 937.32 | MVS
18 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. | TSM/011221 | SM/12367 | New | 30/03/2022 | 1317 | 1786.06 | Yes | 1786.06 | 25/01/2024 | 06/02/2023 | 2 | 1750.73 | MVS
19 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011218 | SM/12368 | New | 30/03/2022 | 1738 | 2044.39 | Yes | 2044.39 | 26/09/2024 | 18/03/2024 | 5 | 2017.99 | MVS
20 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | TSM/012592 | SM/12799 | Augmentation | 22/08/2022 | 1334 | 484.93 | Yes | 484.93 | 26/12/2024 | 05/06/2023 | 8 | 74.11 | MVS
21 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009526 | SM/11350 | New | 16/03/2022 | 35 | 26.38 | Yes | 26.38 |  | 12/07/2022 | 3 | 25.8 | MVS
22 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | TSM/010338 | SM/11786 | New | 25/04/2022 | 1763 | 669.61 | Yes | 669.61 | 11/08/2023 | 08/08/2023 | 11 | 634.22 | MVS
23 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional Household tap connection from existing PWSS at Khaling dhura & Vah Tukbar( Bhutta Kheti) | TSM/011129 | SM/13352 | Retrofitting | 05/07/2022 | 249 | 62.01 | Yes | 62.01 |  | 03/11/2022 | 1 | 48.48 | MVS
24 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | TSM/012588 | SM/12773 | Augmentation | 22/08/2022 | 408 | 513.64 | Yes | 513.64 | 25/02/2025 | 24/04/2025 | 7 | 479.83 | MVS
25 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. | TSM/011930 | SM/13041 | New | 20/05/2022 | 850 | 1164.09 | Yes | 1164.09 |  | 21/10/2022 | 3 | 1168.73 | MVS
26 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | TSM/012882 | SM/13955 | New | 22/08/2022 | 241 | 237.69 | Yes | 237.69 |  | 09/12/2024 | 3 | 236.04 | MVS
27 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013039 | SM/13959 | New | 22/08/2022 | 165 | 228.01 | Yes | 228.01 |  | 14/12/2022 | 2 | 212.22 | MVS
28 | DARJEELING | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme | TSM/015203 | SM/13436 | New | 09/09/2022 | 415 | 216.92 | Yes | 216.92 | 29/08/2024 | 05/04/2023 | 7 | 177.03 | MVS
29 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012884 | SM/14148 | New | 22/08/2022 | 1583 | 1646.2 | Yes | 1646.2 | 30/11/2022 | 24/09/2024 | 8 | 1630.4 | MVS
30 | DARJEELING | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | TSM/010325 | SM/14150 | New | 09/09/2022 | 3674 | 1709.08 | Yes | 1709.08 | 07/12/2023 | 08/08/2023 | 12 | 1306.72 | MVS
31 | DARJEELING | Neorakhola W/S Mnt. Division | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/014897 | SM/16161 | New | 28/12/2022 | 393 | 322.85 | Yes | 322.85 | 08/02/2023 | 28/04/2023 | 3 | 314.46 | MVS
32 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | TSM/020167 | SM/15269 | Augmentation | 16/11/2022 | 0 | 189.49 | Yes | 189.49 | 27/02/2025 | 08/05/2023 | 6 | 135.92 | MVS
33 | DARJEELING | Kurseong Division | RANGMOHAN PIPED WATER SUPPLY SCHEME | TSM/017734 | SM/15880 | New | 28/12/2022 | 172 | 327.7 | Yes | 327.7 | 23/12/2022 | 25/09/2024 | 3 | 307.9 | MVS
34 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | TSM/010324 | SM/15926 | New | 16/11/2022 | 847 | 352.69 | Yes | 352.69 | 26/06/2023 | 19/12/2024 | 8 | 300.68 | MVS
35 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | TSM/010332 | SM/15927 | New | 16/11/2022 | 1622 | 455.46 | Yes | 455.46 | 29/01/2025 | 14/08/2023 | 6 | 389.66 | MVS
36 | DARJEELING | Neorakhola W/S Mnt. Division | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme | TSM/014826 | SM/16384 | New | 09/09/2022 | 384 | 557.87 | Yes | 557.87 | 12/03/2024 | 05/05/2025 | 2 | 15.24 | MVS
37 | DARJEELING | Neorakhola W/S Mnt. Division | BARA MUNGWA PIPED WATER SUPPLY SCHEME | TSM/016188 | SM/15893 | New | 28/12/2022 | 358 | 476.33 | Yes | 476.33 | 12/03/2024 | 18/06/2024 | 2 | 467.8 | MVS
38 | DARJEELING | Neorakhola W/S Mnt. Division | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | TSM/018134 | SM/15897 | New | 28/12/2022 | 563 | 560.14 | Yes | 560.14 | 16/02/2024 | 25/09/2024 | 4 | 535.28 | MVS
39 | DARJEELING | Neorakhola W/S Mnt. Division | LAMAGAON PIPED WATER SUPPLY SCHEME. | TSM/019222 | SM/15868 | New | 28/12/2022 | 628 | 752.32 | Yes | 752.32 | 12/03/2024 | 10/05/2023 | 4 | 749.69 | MVS
40 | DARJEELING | Neorakhola W/S Mnt. Division | CHEGRA KHASMAHAL Piped Water Supply Scheme | TSM/018127 | SM/16141 | New | 28/12/2022 | 237 | 335.44 | Yes | 335.44 | 08/02/2023 | 04/05/2023 | 3 | 324.89 | MVS
41 | DARJEELING | Neorakhola W/S Mnt. Division | RELLING PIPED WATER SUPPLY SCHEME. | TSM/017939 | SM/15879 | New | 28/12/2022 | 643 | 937.57 | Yes | 937.57 | 08/02/2023 | 06/06/2023 | 3 | 901.47 | MVS
42 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/016211 | SM/18634 | New | 26/09/2022 | 1128 | 1305.54 | Yes | 1305.54 | 02/03/2023 | 08/07/2024 | 3 | 1194.6 | MVS
43 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | TSM/009292 | SM/18637 | Augmentation | 22/08/2022 | 680 | 1581.9 | Yes | 1581.9 | 25/02/2025 | 16/08/2023 | 5 | 1393.88 | MVS
44 | DARJEELING | Darjeeling Division | Hatta Water Supply Scheme | TSM/008806 | SM/09449 | New | 08/10/2021 | 310 | 313.13 | Yes | 313.13 | 12/10/2023 | 21/02/2022 | 4 | 315.98 | MVS
45 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011830 | SM/18821 | New | 20/05/2022 | 869 | 1262.02 | Yes | 1262.02 | 01/09/2023 | 05/05/2025 | 2 | 1249.7 | MVS
46 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | TSM/011752 | SM/18822 | New | 20/05/2022 | 2031 | 3724.46 | Yes | 3724.46 | 22/02/2023 | 05/05/2025 | 4 | 3712.36 | MVS
47 | DARJEELING | Kurseong Division | AUGMENTATION OF GARIDHORA (M.BARI) TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/020477 | SM/18880 | Augmentation | 10/03/2023 | 190 | 197.84 | Yes | 197.84 | 18/06/2024 |  | 0 | 0 | MVS
48 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dangarvita Piped water Supply Scheme at Kharibari Block | TSM/006792 | SM/07424 | Retrofitting | 04/12/2020 | 1334 | 70.07 | Yes | 70.07 |  |  | 0 | 0 | MVS
49 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block | TSM/006794 | SM/07425 | Retrofitting | 04/12/2020 | 898 | 50.62 | Yes | 50.62 | 27/07/2023 | 08/03/2022 | 3 | 49.62 | MVS
50 | DARJEELING | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | TSM/006162 | SM/07046 | Retrofitting | 25/09/2020 | 1943 | 98.86 | Yes | 98.86 | 19/08/2021 | 01/11/2021 | 3 | 19.54 | MVS
51 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Chayan Sing and Bhogbhita village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-B) | TSM/006163 | SM/07048 | Retrofitting | 25/09/2020 | 744 | 42.44 | Yes | 42.44 | 18/06/2021 | 16/03/2023 | 2 | 1.74 | MVS
52 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Pelku (JL No-71) & Thiknikata (JL No.-74) Mouzas of Kawakhali Pipe water Supply Scheme | TSM/006142 | SM/07213 | Retrofitting | 25/09/2020 | 1372 | 99.9 | Yes | 99.9 |  | 10/08/2023 | 1 | 74.02 | MVS
53 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | TSM/006148 | SM/07215 | Retrofitting | 25/09/2020 | 872 | 59.78 | Yes | 59.78 | 18/06/2021 | 02/08/2021 | 3 | 32.7 | MVS
54 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | TSM/006151 | SM/07216 | Retrofitting | 25/09/2020 | 399 | 61.95 | Yes | 61.95 |  | 13/03/2024 | 7 | 32.99 | MVS
55 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme | TSM/006152 | SM/07217 | Retrofitting | 25/09/2020 | 1053 | 80.78 | Yes | 80.78 | 27/07/2023 | 11/12/2020 | 3 | 60.87 | MVS
56 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-II) Piped water Supply Scheme | TSM/006145 | SM/07035 | Retrofitting | 25/09/2020 | 1032 | 62.07 | Yes | 62.07 |  | 02/08/2021 | 3 | 70.89 | MVS
57 | DARJEELING | Darjeeling Division | LOHAGARH WATER SUPPLY SCHEME | TSM/008814 | SM/09426 | New | 29/09/2021 | 430 | 170.07 | Yes | 170.07 | 02/12/2021 | 15/02/2024 | 3 | 174.08 | MVS
58 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division | TSM/009296 | SM/10765 | Retrofitting | 27/01/2022 | 136 | 18 | Yes | 18 |  | 26/05/2022 | 3 | 18.59 | MVS
59 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield | TSM/009472 | SM/10772 | Retrofitting | 27/01/2022 | 96 | 15.76 | Yes | 15.76 |  | 24/05/2022 | 3 | 14.32 | MVS
60 | DARJEELING | Darjeeling Division | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. | TSM/006997 | SM/10261 | Retrofitting | 08/01/2021 | 328 | 34.5 | Yes | 34.5 |  | 20/05/2022 | 1 | 5.7 | MVS
61 | DARJEELING | Neorakhola W/S Mnt. Division | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | TSM/010473 | SM/10789 | New | 16/03/2022 | 105 | 100.65 | Yes | 100.65 |  | 27/07/2023 | 3 | 201.32 | MVS
62 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) | TSM/011138 | SM/11378 | Retrofitting | 30/03/2022 | 0 | 40.64 | Yes | 40.64 |  | 12/07/2022 | 3 | 36.64 | MVS
63 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) | TSM/011137 | SM/11379 | Retrofitting | 30/03/2022 | 78 | 23.39 | Yes | 23.39 |  | 12/07/2022 | 4 | 19.91 | MVS
64 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | TSM/011133 | SM/11389 | Retrofitting | 30/03/2022 | 63 | 15.54 | Yes | 15.54 |  | 12/07/2022 | 4 | 13.37 | MVS
65 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | TSM/009847 | SM/10825 | New | 17/02/2022 | 165 | 118.57 | Yes | 118.57 | 28/02/2023 | 30/06/2022 | 2 | 90.47 | MVS
66 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney ( North shibkhola habitation ) under Kurseong Sub-Division PHED, GTA. | TSM/009606 | SM/11314 | Retrofitting | 17/02/2022 | 125 | 10.67 | Yes | 10.67 |  | 30/06/2022 | 2 | 10.05 | MVS
67 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation)under Kurseong Sub-Division PHED, GTA. | TSM/009594 | SM/11325 | Retrofitting | 17/02/2022 | 120 | 10.69 | Yes | 10.69 |  | 30/06/2022 | 2 | 10.08 | MVS
68 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Malotar Tea Estate under Kurseong-Sub Division, PHED, GTA | TSM/010590 | SM/11329 | Retrofitting | 17/02/2022 | 156 | 19.72 | Yes | 19.72 |  | 30/06/2022 | 2 | 18.8 | MVS
69 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. | TSM/009302 | SM/11300 | Retrofitting | 27/01/2022 | 55 | 20.83 | Yes | 20.83 |  | 30/06/2022 | 2 | 19.29 | MVS
70 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Krishi kunj | TSM/009481 | SM/11308 | Retrofitting | 27/01/2022 | 27 | 5.7 | Yes | 5.7 |  | 30/06/2022 | 1 | 5.52 | MVS
71 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Chota Tingling | TSM/009480 | SM/11309 | Retrofitting | 27/01/2022 | 60 | 8.98 | Yes | 8.98 |  | 30/06/2022 | 1 | 7.72 | MVS
72 | DARJEELING | Neorakhola W/S Mnt. Division | Singla Tea Garden water supply scheme. | TSM/009506 | SM/11339 | New | 17/02/2022 | 746 | 384.26 | Yes | 384.26 |  | 09/04/2025 | 4 | 377.71 | MVS
73 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | TSM/012508 | SM/11889 | New | 20/05/2022 | 308 | 319.88 | Yes | 319.88 | 24/04/2023 | 24/09/2024 | 5 | 310.76 | MVS
74 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme | TSM/006150 | SM/07038 | Retrofitting | 25/09/2020 | 1583 | 89.15 | Yes | 89.15 | 19/08/2021 | 08/07/2024 | 3 | 39.2 | MVS
75 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | TSM/011533 | SM/12037 | Augmentation | 20/05/2022 | 439 | 125.17 | Yes | 125.17 | 25/02/2025 | 24/04/2025 | 5 | 97.2 | MVS
76 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011759 | SM/11953 | New | 20/05/2022 | 527 | 768.51 | Yes | 768.51 |  | 05/05/2025 | 5 | 766.68 | MVS
77 | DARJEELING | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme | TSM/015199 | SM/13429 | Augmentation | 09/09/2022 | 604 | 347.93 | Yes | 347.93 | 25/02/2025 | 05/05/2025 | 7 | 277.76 | MVS
78 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | TSM/020159 | SM/14834 | Augmentation | 16/11/2022 | 0 | 111.08 | Yes | 111.08 | 24/03/2023 | 15/06/2023 | 4 | 46.06 | MVS
79 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012883 | SM/13956 | New | 22/08/2022 | 455 | 517.62 | Yes | 517.62 | 02/12/2022 | 09/12/2024 | 5 | 517.33 | MVS
80 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/013035 | SM/14528 | New | 22/08/2022 | 790 | 1138.22 | Yes | 1138.22 | 30/11/2022 | 17/02/2024 | 3 | 1061.88 | MVS
81 | DARJEELING | Neorakhola W/S Mnt. Division | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME | TSM/016084 | SM/16159 | New | 28/12/2022 | 55 | 307.56 | Yes | 307.56 | 08/02/2023 | 05/06/2023 | 2 | 288.35 | MVS
82 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | TSM/020169 | SM/15270 | Augmentation | 16/11/2022 | 0 | 148.87 | Yes | 148.87 | 25/02/2025 | 24/04/2025 | 5 | 87.93 | MVS
83 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME | TSM/020164 | SM/15272 | Augmentation | 16/11/2022 | 0 | 106.93 | Yes | 106.93 | 29/08/2024 | 14/03/2024 | 4 | 79.37 | MVS
84 | DARJEELING | Neorakhola W/S Mnt. Division | RIMBICK Piped Water Supply Scheme | TSM/019197 | SM/16123 | New | 28/12/2022 | 450 | 716.55 | Yes | 716.55 | 08/02/2023 | 12/07/2023 | 2 | 702.35 | MVS
85 | DARJEELING | Neorakhola W/S Mnt. Division | CHAINPURAY PIPED WATER SUPPLY SCHEME | TSM/017539 | SM/15881 | New | 28/12/2022 | 105 | 82.28 | Yes | 82.28 | 08/02/2023 | 12/07/2023 | 2 | 81.11 | MVS
86 | DARJEELING | Neorakhola W/S Mnt. Division | MAJUA PIPED WATER SUPPLY SCHEME. | TSM/018191 | SM/15874 | New | 28/12/2022 | 175 | 301.04 | Yes | 301.04 | 08/02/2023 | 28/04/2023 | 3 | 285.02 | MVS
87 | DARJEELING | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013036 | SM/16533 | New | 22/08/2022 | 936 | 1182.41 | Yes | 1182.41 | 30/11/2022 | 28/04/2023 | 3 | 1179.72 | MVS
88 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) | TSM/014159 | SM/16386 | New | 30/09/2022 | 329 | 669.48 | Yes | 669.48 | 02/12/2022 | 03/03/2023 | 2 | 661.54 | MVS
89 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/017453 | SM/16145 | New | 28/12/2022 | 346 | 442.66 | Yes | 442.66 | 11/02/2023 | 09/06/2025 | 3 | 434.26 | MVS
90 | DARJEELING | Neorakhola W/S Mnt. Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | TSM/017747 | SM/15647 | New | 30/09/2022 | 1036 | 656.45 | Yes | 656.45 | 29/11/2023 | 08/07/2024 | 4 | 509.76 | MVS
91 | DARJEELING | Kurseong Division | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. | TSM/013420 | SM/18638 | New | 30/09/2022 | 637 | 1513.58 | Yes | 1513.58 | 23/12/2022 | 11/08/2023 | 2 | 1340 | MVS
92 | DARJEELING | Neorakhola W/S Mnt. Division | PESHOK TEA GARDEN PWSS | TSM/016194 | SM/18728 | New | 28/12/2022 | 1000 | 1054.98 | Yes | 1054.98 | 17/07/2023 | 05/05/2025 | 4 | 1050.24 | MVS
93 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | TSM/018460 | SM/18386 | Augmentation | 16/11/2022 | 951 | 1249.24 | Yes | 1249.24 | 27/09/2024 | 05/06/2023 | 9 | 990.16 | MVS
94 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection under JSP Programme for PWS scheme at Kataray forest Busty | TSM/009305 | SM/11302 | Retrofitting | 27/01/2022 | 56 | 9.52 | Yes | 9.52 |  | 30/06/2022 | 1 | 7.66 | MVS
95 | DARJEELING | Neorakhola W/S Mnt. Division | DARJEELING-PULBAZAR PUMPING-I PWSS | TSM/019601 | SM/18827 | New | 28/12/2022 | 3658 | 17368.24 | Yes | 17368.24 | 28/11/2023 | 03/09/2024 | 3 | 15904.63 | MVS
96 | DARJEELING | Kurseong Division | AUGMENTATION OF SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/020480 | SM/18878 | Augmentation | 10/03/2023 | 161 | 199.02 | Yes | 199.02 | 18/06/2024 | 21/01/2025 | 1 | 585.79 | MVS
97 | DARJEELING | Kurseong Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | TSM/014167 | SM/18651 | New | 30/09/2022 | 1170 | 1262.65 | Yes | 1262.65 | 23/12/2022 | 08/07/2024 | 5 | 1243.37 | MVS
98 | DARJEELING | Kurseong Division | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. | TSM/013418 | SM/18652 | New | 30/09/2022 | 998 | 1174.35 | Yes | 1174.35 | 23/12/2022 | 11/08/2023 | 2 | 964.56 | MVS
99 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | TSM/009466 | SM/10724 | Augmentation | 16/03/2022 | 982 | 1047.38 | Yes | 1047.38 | 16/03/2023 | 07/08/2023 | 8 | 996.24 | MVS
100 | DARJEELING | Kurseong Division | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA | TSM/021550 | SM/18917 | New | 10/03/2023 | 925 | 947.7 | Yes | 947.7 | 11/03/2024 | 19/09/2024 | 1 | 861.59 | MVS
101 | DARJEELING | Siliguri W/S Division | IMPLEMENTATION OF AFFORDABLE IOT SYSTEM AT PURBA MADATI WATER SUPPLY SCHEME IN PHANSIDEWA BLOCK UNDER DARJEELING DISTRICT. | TSM/019983 |  | IOT | 16/11/2022 | 0 | 145.75 | No | 0 |  |  | 0 | 0 | MVS
102 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for mahipal and Bandargachh village of Bandargachh Piped water Supply Scheme | TSM/006157 | SM/07042 | Retrofitting | 25/09/2020 | 1307 | 81.93 | Yes | 81.93 |  | 02/08/2024 | 1 | 0.98 | MVS
103 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | TSM/006160 | SM/07043 | Retrofitting | 25/09/2020 | 1370 | 71.82 | Yes | 71.82 |  | 13/03/2023 | 5 | 174.33 | MVS
104 | DARJEELING | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme in 5 Habitation ( Ghaiter Busrty, Gurira Zote , Nagar Zote, NDDP Busty , Taluk Zote ) at Village Guria of | TSM/008601 | SM/09203 | Augmentation | 08/09/2021 | 1200 | 66.16 | Yes | 66.16 |  |  | 0 | 0 | MVS
105 | DARJEELING | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND | TSM/010032 | SM/10470 | New | 16/03/2022 | 975 | 701.4 | Yes | 701.4 | 27/07/2023 | 29/09/2022 | 1 | 6.01 | MVS
106 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | TSM/009103 | SM/09829 | Augmentation | 22/11/2021 | 2467 | 843.24 | Yes | 843.24 | 23/02/2024 | 07/04/2022 | 16 | 825.07 | MVS
107 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal swapno programme for Mirjangla,Mirjnaglar Chhat, Birsing, Fakna Mouza of Birsing Piped W/S Scheme at Naxalbari Block under Siliguri Sub Division, P.H.E Dte. ( Phase-II ) | TSM/008604 | SM/09079 | Retrofitting | 08/09/2021 | 1125 | 57.6 | Yes | 57.6 | 19/08/2021 | 01/11/2021 | 1 | 14.99 | MVS
108 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | TSM/009124 | SM/10025 | Augmentation | 22/11/2021 | 5380 | 1506.6 | Yes | 1506.6 | 31/07/2024 | 20/02/2023 | 21 | 1507.75 | MVS
109 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | TSM/011214 | SM/11396 | New | 30/03/2022 | 106 | 234.66 | Yes | 234.66 |  | 09/04/2025 | 3 | 224.72 | MVS
110 | DARJEELING | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME | TSM/010342 | SM/11776 | New | 25/04/2022 | 1035 | 386.83 | Yes | 386.83 | 06/10/2023 | 20/05/2022 | 5 | 321.04 | MVS
111 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source of school (31 nos) under Mirik Block in the District of Darjeeling under Neorakhola water supply & Mtc Division, P.H.E Dte. | TSM/009893 | SM/10784 | School | 27/01/2022 | 0 | 102.1 | Yes | 102.1 |  | 26/05/2022 | 1 | 94.19 | MVS
112 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA | TSM/009846 | SM/10826 | New | 17/02/2022 | 448 | 178.67 | Yes | 178.67 |  | 05/08/2022 | 2 | 97.9 | MVS
113 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA | TSM/009845 | SM/10827 | New | 17/02/2022 | 283 | 213.75 | Yes | 213.75 | 28/02/2023 | 26/05/2022 | 2 | 126.58 | MVS
114 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Thulung Gaon | TSM/009512 | SM/10830 | New | 17/02/2022 | 107 | 78.67 | Yes | 78.67 |  | 26/05/2022 | 2 | 76.53 | MVS
115 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Pokhriabong Busty 5 No. | TSM/009510 | SM/10832 | New | 17/02/2022 | 85 | 98.99 | Yes | 98.99 |  | 26/05/2022 | 4 | 87.49 | MVS
116 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. | TSM/009604 | SM/11315 | Retrofitting | 17/02/2022 | 108 | 21.28 | Yes | 21.28 |  | 30/06/2022 | 2 | 20.51 | MVS
117 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Rajbari under Kurseong-Sub Division, PHED, GTA | TSM/010589 | SM/11328 | Retrofitting | 17/02/2022 | 220 | 27.54 | Yes | 27.54 |  | 30/06/2022 | 2 | 23.48 | MVS
118 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012587 | SM/11942 | New | 20/05/2022 | 286 | 233.67 | Yes | 233.67 |  | 28/05/2025 | 3 | 230.5 | MVS
119 | DARJEELING | Neorakhola W/S Mnt. Division | Augmentation of source and provding FHTC at Bijanbari Bazaar | TSM/009478 | SM/11375 | Augmentation | 17/02/2022 | 50 | 42.06 | Yes | 42.06 | 24/04/2023 | 30/06/2022 | 1 | 35.85 | MVS
120 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Goethals Siding and Upper Kharay Busty with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009523 | SM/11352 | New | 16/03/2022 | 110 | 32.24 | Yes | 32.24 |  | 28/09/2022 | 1 | 31.04 | MVS
121 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Aganwadi Centers in Block- Mirik, under the District of Darjeeling ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/010192 | SM/11361 | Anganwadi | 16/03/2022 | 0 | 106.1 | Yes | 106.1 |  | 05/08/2022 | 1 | 97.78 | MVS
122 | DARJEELING | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme | TSM/015198 | SM/13428 | Augmentation | 09/09/2022 | 500 | 267.54 | Yes | 267.54 | 29/08/2024 | 15/06/2023 | 6 | 215.29 | MVS
123 | DARJEELING | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme | TSM/015194 | SM/13395 | Augmentation | 09/09/2022 | 348 | 271.14 | Yes | 271.14 | 27/02/2025 | 10/04/2023 | 7 | 220.06 | MVS
124 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | TSM/012040 | SM/14418 | New | 20/05/2022 | 1100 | 1660.67 | Yes | 1660.67 | 30/11/2022 | 29/04/2025 | 4 | 1645.75 | MVS
125 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012881 | SM/14530 | New | 22/08/2022 | 1488 | 1651.09 | Yes | 1651.09 | 22/02/2023 | 05/05/2025 | 3 | 1632.57 | MVS
126 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS | TSM/012043 | SM/15224 | New | 20/05/2022 | 910 | 2098.08 | Yes | 2098.08 | 26/04/2023 | 12/07/2023 | 2 | 2052.67 | MVS
127 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | TSM/020165 | SM/15274 | Augmentation | 16/11/2022 | 0 | 194.82 | Yes | 194.82 | 23/12/2024 | 03/10/2023 | 9 | 167.36 | MVS
128 | DARJEELING | Neorakhola W/S Mnt. Division | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) | TSM/016192 | SM/15892 | New | 28/12/2022 | 133 | 161.01 | Yes | 161.01 | 08/02/2023 | 28/04/2023 | 2 | 156.08 | MVS
129 | DARJEELING | Neorakhola W/S Mnt. Division | DANGIA PIPED WATER SUPPLY SCHEME | TSM/018175 | SM/15896 | New | 28/12/2022 | 484 | 524.85 | Yes | 524.85 | 08/02/2023 | 04/05/2023 | 5 | 508.53 | MVS
130 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018497 | SM/15630 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
131 | DARJEELING | Kurseong Division | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | TSM/013419 | SM/15650 | New | 30/09/2022 | 229 | 210.61 | Yes | 210.61 | 23/12/2022 | 10/03/2023 | 1 | 1.44 | MVS
132 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | TSM/009084 | SM/09827 | Augmentation | 22/11/2021 | 2315 | 870.41 | Yes | 870.41 | 25/02/2025 | 24/04/2025 | 16 | 753.37 | MVS
133 | DARJEELING | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | TSM/010326 | SM/15929 | New | 16/11/2022 | 1966 | 741.26 | Yes | 741.26 | 11/08/2023 | 08/08/2023 | 8 | 608.25 | MVS
134 | DARJEELING | Neorakhola W/S Mnt. Division | MAHANADI FOREST PIPED WATER SUPPLY SCHEME. | TSM/018153 | SM/15875 | New | 28/12/2022 | 158 | 217.84 | Yes | 217.84 | 19/06/2024 |  | 0 | 0 | MVS
135 | DARJEELING | Neorakhola W/S Mnt. Division | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/018126 | SM/15876 | New | 28/12/2022 | 1198 | 790.03 | Yes | 790.03 | 12/03/2024 | 18/06/2024 | 3 | 757.82 | MVS
136 | DARJEELING | Neorakhola W/S Mnt. Division | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | TSM/018101 | SM/15877 | New | 28/12/2022 | 35 | 150.95 | Yes | 150.95 | 08/02/2023 | 15/05/2023 | 3 | 133.5 | MVS
137 | DARJEELING | Neorakhola W/S Mnt. Division | BARBATIA KHASMAHAL PWSS | TSM/018689 | SM/18189 | New | 28/12/2022 | 147 | 404.81 | Yes | 404.81 | 11/02/2023 | 04/05/2023 | 2 | 195.53 | MVS
138 | DARJEELING | Kurseong Division | PWS Scheme for Toryak Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011217 | SM/19033 | New | 30/03/2022 | 1117 | 1424.7 | Yes | 1424.7 | 28/10/2022 | 03/11/2023 | 1 | 1230.38 | MVS
139 | DARJEELING | Neorakhola W/S Mnt. Division | GINGLAM & GIELIE TEA GARDEN PWSS | TSM/018144 | SM/18721 | New | 28/12/2022 | 908 | 1070.75 | Yes | 1070.75 | 12/03/2024 | 18/06/2024 | 3 | 1069.21 | MVS
140 | DARJEELING | Neorakhola W/S Mnt. Division | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/010228 | SM/10817 | New | 16/03/2022 | 989 | 379.09 | Yes | 379.09 |  | 02/11/2023 | 4 | 724.02 | MVS
141 | DARJEELING | Neorakhola W/S Mnt. Division | RONGCHONG AND LABDA PWSS | TSM/018103 | SM/18729 | New | 28/12/2022 | 594 | 1302.23 | Yes | 1302.23 | 27/04/2023 | 08/07/2024 | 3 | 1298.98 | MVS
142 | DARJEELING | Kurseong Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | TSM/014155 | SM/18730 | New | 28/12/2022 | 3257 | 3390 | Yes | 3390 | 27/04/2023 | 10/10/2023 | 4 | 3141.92 | MVS
143 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra | TSM/009299 | SM/10561 | Retrofitting | 27/01/2022 | 111 | 16.73 | Yes | 16.73 |  | 10/05/2022 | 2 | 14.47 | MVS
144 | DARJEELING | Neorakhola W/S Mnt. Division | SITTONG KHASMAHAL PWSS | TSM/016146 | SM/18336 | New | 28/12/2022 | 635 | 1082.47 | Yes | 1082.47 | 17/05/2023 | 28/05/2025 | 2 | 1044.2 | MVS
145 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | TSM/009555 | SM/18421 | Augmentation | 27/01/2022 | 921 | 1259.04 | Yes | 1259.04 | 31/07/2024 | 21/07/2022 | 14 | 1095.41 | MVS
146 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Gitangay under Kurseong-Sub Division, PHED, GTA | TSM/010598 | SM/11337 | Retrofitting | 17/02/2022 | 72 | 14.29 | Yes | 14.29 |  | 30/06/2022 | 2 | 12.31 | MVS
147 | DARJEELING | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. | TSM/003869 | SM/18784 | New | 04/12/2020 | 1541 | 623.79 | Yes | 623.79 | 11/07/2023 | 03/10/2023 | 6 | 560.99 | MVS
148 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/012605 | SM/12749 | Augmentation | 22/08/2022 | 838 | 335.45 | Yes | 335.45 | 29/08/2024 | 05/06/2023 | 6 | 251.92 | MVS
149 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Ghusuru Piped water Supply Scheme at Naxalbari Block | TSM/006798 | SM/07423 | Retrofitting | 04/12/2020 | 758 | 38.97 | Yes | 38.97 | 19/08/2021 | 01/11/2021 | 1 | 36.04 | MVS
150 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | TSM/006143 | SM/07033 | Retrofitting | 25/09/2020 | 1524 | 75.17 | Yes | 75.17 | 19/08/2021 | 03/08/2021 | 6 | 50.57 | MVS
151 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Khopalasi village of Panchkolguri Piped water Supply Scheme | TSM/006146 | SM/07039 | Retrofitting | 25/09/2020 | 1194 | 78 | Yes | 78 |  |  | 0 | 0 | MVS
152 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME | TSM/009581 | SM/10469 | Augmentation | 16/03/2022 | 2165 | 647.25 | Yes | 647.25 | 31/07/2024 | 20/02/2023 | 9 | 689.42 | MVS
153 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | TSM/009575 | SM/10183 | Augmentation | 16/12/2021 | 8610 | 1681.3 | Yes | 1681.3 | 31/07/2024 | 18/01/2023 | 34 | 1513.92 | MVS
154 | DARJEELING | Neorakhola W/S Mnt. Division | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | TSM/009891 | SM/10687 | School | 27/01/2022 | 0 | 379.94 | Yes | 379.94 |  | 06/05/2022 | 4 | 540.21 | MVS
155 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | TSM/009507 | SM/10835 | New | 17/02/2022 | 242 | 218.24 | Yes | 218.24 | 24/04/2023 | 03/08/2023 | 5 | 208.69 | MVS
156 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II | TSM/011131 | SM/11383 | Retrofitting | 30/03/2022 | 315 | 65.26 | Yes | 65.26 |  | 28/09/2022 | 3 | 64.2 | MVS
157 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. | TSM/011128 | SM/11385 | Retrofitting | 30/03/2022 | 170 | 47.07 | Yes | 47.07 |  | 12/07/2022 | 3 | 42.2 | MVS
158 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | TSM/011127 | SM/11386 | Retrofitting | 30/03/2022 | 474 | 122.75 | Yes | 122.75 |  | 12/07/2022 | 4 | 123.12 | MVS
159 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | TSM/011126 | SM/11387 | Retrofitting | 30/03/2022 | 145 | 31.49 | Yes | 31.49 |  | 11/05/2023 | 2 | 30.32 | MVS
160 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | TSM/009856 | SM/10802 | New | 17/02/2022 | 3231 | 228.59 | Yes | 228.59 |  | 01/11/2023 | 3 | 354.6 | MVS
161 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | TSM/009890 | SM/10814 | School | 27/01/2022 | 0 | 263.53 | Yes | 263.53 |  | 01/08/2024 | 12 | 8.97 | MVS
162 | DARJEELING | Neorakhola W/S Mnt. Division | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | TSM/010227 | SM/10818 | New | 16/03/2022 | 684 | 299.8 | Yes | 299.8 |  | 02/11/2023 | 6 | 15.22 | MVS
163 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram Tea Estate ( Dilaram Bazar habitation ) under Kurseong Sub-Division PHED, GTA. | TSM/009601 | SM/11318 | Retrofitting | 17/02/2022 | 65 | 7.31 | Yes | 7.31 |  | 30/06/2022 | 2 | 6.36 | MVS
164 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. | TSM/009598 | SM/11321 | Retrofitting | 17/02/2022 | 193 | 17.13 | Yes | 17.13 |  | 30/06/2022 | 2 | 15.7 | MVS
165 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div | TSM/009596 | SM/11323 | Retrofitting | 17/02/2022 | 270 | 22.61 | Yes | 22.61 |  | 30/06/2022 | 2 | 21.71 | MVS
166 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA | TSM/010588 | SM/11327 | Retrofitting | 17/02/2022 | 135 | 15.46 | Yes | 15.46 |  | 30/06/2022 | 2 | 13.42 | MVS
167 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Bagmara Busty under Kurseong-Sub Division, PHED, GTA | TSM/010596 | SM/11335 | Retrofitting | 17/02/2022 | 58 | 12.77 | Yes | 12.77 |  | 05/08/2022 | 2 | 9.52 | MVS
168 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for 14th Mile and Pagla Jhora Busty under Kurseong-Sub Division, PHED, GTA | TSM/010597 | SM/11336 | Retrofitting | 17/02/2022 | 102 | 13.82 | Yes | 13.82 |  | 30/06/2022 | 2 | 11.49 | MVS
169 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011758 | SM/11954 | New | 20/05/2022 | 215 | 333.26 | Yes | 333.26 |  | 18/10/2022 | 3 | 321.5 | MVS
170 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009525 | SM/11351 | New | 16/03/2022 | 35 | 18.6 | Yes | 18.6 |  | 12/07/2022 | 3 | 19.78 | MVS
171 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | TSM/011757 | SM/12128 | New | 20/05/2022 | 759 | 990.4 | Yes | 990.4 |  | 30/03/2023 | 4 | 993.32 | MVS
172 | DARJEELING | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | TSM/011530 | SM/12036 | Augmentation | 20/05/2022 | 1162 | 272.84 | Yes | 272.84 | 09/03/2023 | 13/11/2024 | 7 | 268.31 | MVS
173 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 87 Nos of School under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong. | TSM/010272 | SM/11355 | School | 16/03/2022 | 202 | 273.3 | Yes | 273.3 |  | 12/07/2022 | 1 | 232.24 | MVS
174 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 101 Nos of Aganwadi under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, kalimpong PHE Directorate | TSM/010273 | SM/11360 | Anganwadi | 16/03/2022 | 0 | 397.94 | Yes | 397.94 |  | 12/07/2022 | 1 | 310.44 | MVS
175 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source for 16 Numbers of Aganwadi Centers in Block- Kurseong, under the District of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte,. | TSM/010189 | SM/11362 | Anganwadi | 16/03/2022 | 0 | 38.79 | Yes | 38.79 |  | 12/07/2022 | 1 | 37.03 | MVS
176 | DARJEELING | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/010337 | SM/12751 | New | 22/08/2022 | 1023 | 629.15 | Yes | 629.15 | 27/03/2023 | 26/05/2022 | 9 | 581.1 | MVS
177 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012887 | SM/13957 | New | 22/08/2022 | 175 | 451.2 | Yes | 451.2 | 02/12/2022 | 20/01/2023 | 2 | 391.94 | MVS
178 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013038 | SM/13958 | New | 22/08/2022 | 170 | 330.4 | Yes | 330.4 |  | 23/12/2022 | 2 | 307.43 | MVS
179 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | TSM/012820 | SM/12983 | New | 20/05/2022 | 1341 | 1217.59 | Yes | 1217.59 | 02/12/2022 | 08/07/2024 | 5 | 1222.2 | MVS
180 | DARJEELING | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | TSM/010327 | SM/13440 | New | 09/09/2022 | 536 | 240.06 | Yes | 240.06 | 08/02/2024 | 10/02/2023 | 8 | 199.17 | MVS
181 | DARJEELING | Siliguri W/S Division | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme | TSM/015190 | SM/13391 | Augmentation | 09/09/2022 | 803 | 417.78 | Yes | 417.78 | 29/08/2024 | 03/01/2024 | 12 | 530.36 | MVS
182 | DARJEELING | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | TSM/015195 | SM/13392 | Augmentation | 09/09/2022 | 332 | 294.72 | Yes | 294.72 | 29/08/2024 | 05/06/2023 | 8 | 306.75 | MVS
183 | DARJEELING | Neorakhola W/S Mnt. Division | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | TSM/017294 | SM/16157 | New | 28/12/2022 | 125 | 112.01 | Yes | 112.01 | 08/02/2023 | 24/09/2024 | 3 | 116.11 | MVS
184 | DARJEELING | Neorakhola W/S Mnt. Division | KOLBONG KHASMAHAL PWSS | TSM/014695 | SM/15840 | New | 09/09/2022 | 143 | 214.49 | Yes | 214.49 | 24/01/2023 | 04/05/2023 | 2 | 213.09 | MVS
185 | DARJEELING | Neorakhola W/S Mnt. Division | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. | TSM/016115 | SM/15909 | New | 28/12/2022 | 120 | 304.67 | Yes | 304.67 | 08/02/2023 | 05/06/2023 | 2 | 279.12 | MVS
186 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Maharani Tea Garden | TSM/012916 | SM/16474 | New | 30/09/2022 | 488 | 465.91 | Yes | 465.91 | 25/11/2022 | 05/05/2025 | 3 | 459.74 | MVS
187 | DARJEELING | Neorakhola W/S Mnt. Division | BIJANBARI PIPED WATER SUPPLY SCHEME. | TSM/019202 | SM/15869 | New | 28/12/2022 | 298 | 357.73 | Yes | 357.73 | 01/02/2023 | 27/04/2023 | 2 | 340.98 | MVS
188 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GUABARI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018503 | SM/15628 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
189 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018499 | SM/15626 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 | 29/08/2024 | 2 | 87.65 | MVS
190 | DARJEELING | Neorakhola W/S Mnt. Division | SINGALILA FOREST PWSS | TSM/019228 | SM/16771 | New | 28/12/2022 | 76 | 398.31 | Yes | 398.31 | 01/02/2023 | 27/04/2023 | 4 | 394.84 | MVS
191 | DARJEELING | Kurseong Division | PWS scheme for St. Mary's & Goethals | TSM/013415 | SM/15661 | New | 30/09/2022 | 675 | 338.76 | Yes | 338.76 | 23/12/2022 | 09/12/2024 | 3 | 307.47 | MVS
192 | DARJEELING | Kurseong Division | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | TSM/020430 | SM/18723 | New | 28/12/2022 | 3485 | 2936.38 | Yes | 2936.38 | 17/02/2023 | 09/06/2025 | 2 | 2856.54 | MVS
193 | DARJEELING | Neorakhola W/S Mnt. Division | HUM TUKDAH KHASMAHAL PWSS | TSM/018171 | SM/18316 | New | 28/12/2022 | 1616 | 1456.69 | Yes | 1456.69 | 11/02/2023 | 12/07/2023 | 3 | 1221.71 | MVS
194 | DARJEELING | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | TSM/010345 | SM/11774 | New | 25/04/2022 | 1086 | 452.96 | Yes | 452.96 | 26/06/2023 | 01/06/2022 | 6 | 419.7 | MVS
195 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Panchkolguri & Jhauguri village of Panchkolguri Piped water Supply Scheme | TSM/006154 | SM/07219 | Retrofitting | 25/09/2020 | 735 | 55.74 | Yes | 55.74 |  |  | 0 | 0 | MVS
196 | DARJEELING | Siliguri W/S Division | Extension of Piped Water Supply (PWS) to Anganwadi Centers (AWCs) located within the command area of PWSS under Siliguri W/S Division. | TSM/005350 | SM/07966 | Anganwadi | 05/11/2019 | 391 | 15.95 | Yes | 15.95 |  |  | 0 | 0 | MVS
197 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-I) Piped water Supply Scheme | TSM/006155 | SM/07034 | Retrofitting | 25/09/2020 | 1032 | 64.86 | Yes | 64.86 | 18/06/2021 | 04/10/2024 | 2 | 4.74 | MVS
198 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal Swpna Programme for Samar Nagar& Debidanga area of Kalkut Mouza, Uttar Palash and Dakshin Palash area of Palash Mouza and Kalabari Mouza ( Part ) of Kalkut Piped W/S Scheme at | TSM/007267 | SM/08296 | Retrofitting | 10/02/2021 | 1250 | 63.28 | Yes | 63.28 |  | 03/08/2021 | 1 | 19.62 | MVS
199 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth | TSM/009297 | SM/10766 | Retrofitting | 27/01/2022 | 35 | 7.21 | Yes | 7.21 |  | 25/05/2022 | 2 | 6.44 | MVS
200 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | TSM/009591 | SM/10097 | Augmentation | 16/12/2021 | 5725 | 913.6 | Yes | 913.6 | 31/07/2024 | 21/07/2022 | 12 | 1005.99 | MVS
201 | DARJEELING | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] | TSM/007006 | SM/10262 | Retrofitting | 08/01/2021 | 817 | 159.17 | Yes | 159.17 |  | 27/09/2023 | 10 | 88.8 | MVS
202 | DARJEELING | Neorakhola W/S Mnt. Division | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | TSM/010472 | SM/10788 | New | 16/03/2022 | 1310 | 244.94 | Yes | 244.94 |  | 08/07/2024 | 9 | 252.93 | MVS
203 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme For Jhepi & Gurdung. | TSM/009509 | SM/10833 | New | 17/02/2022 | 309 | 318.71 | Yes | 318.71 | 24/04/2023 | 30/06/2022 | 4 | 308.84 | MVS
204 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source to sourceless schools under different Blocks viz Mirik,Kurseong,Darjeeling-Pulbazar,Jorebunglow-Sukhiapokhri & Rangli-Rangliot in the District of Darjeeling Under Neorakhola Wate | TSM/009457 | SM/10239 | School | 16/12/2021 | 0 | 389.69 | Yes | 389.69 |  | 28/02/2022 | 2 | 229.2 | MVS
205 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar | TSM/011134 | SM/11382 | Retrofitting | 30/03/2022 | 250 | 54.99 | Yes | 54.99 |  | 12/07/2022 | 2 | 50.37 | MVS
206 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) | TSM/009473 | SM/10773 | Retrofitting | 27/01/2022 | 139 | 21.6 | Yes | 21.6 |  | 24/05/2022 | 3 | 19.92 | MVS
207 | DARJEELING | Neorakhola W/S Mnt. Division | Creation of gravity based provision of drinking water from spring water source of anganwadi(119 nos) centers under Darjeeling pulbazar block in the district of Darjeeling under Neorakhola water supply & maintenance division, P.H.E. Directorate | TSM/009892 | SM/10796 | Anganwadi | 27/01/2022 | 0 | 429.36 | Yes | 429.36 |  | 06/05/2022 | 1 | 334.99 | MVS
208 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA | TSM/009848 | SM/10810 | New | 17/02/2022 | 233 | 151.73 | Yes | 151.73 |  | 26/05/2022 | 1 | 83.04 | MVS
209 | DARJEELING | Neorakhola W/S Mnt. Division | Nipania Piped water Supply Scheme. | TSM/010842 | SM/10815 | New | 16/03/2022 | 1314 | 461.01 | Yes | 461.01 |  | 02/11/2023 | 5 | 1013.55 | MVS
210 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional household tap connection with pipeline retrofitting for PWS scheme at Lingsaybong, Lodhuma-II | TSM/009471 | SM/10822 | Retrofitting | 27/01/2022 | 28 | 19.74 | Yes | 19.74 |  | 26/05/2022 | 2 | 16.77 | MVS
211 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011754 | SM/12179 | New | 20/05/2022 | 447 | 663.63 | Yes | 663.63 |  | 05/05/2025 | 3 | 659.3 | MVS
212 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis | TSM/009597 | SM/11322 | Retrofitting | 17/02/2022 | 174 | 14.74 | Yes | 14.74 |  | 30/06/2022 | 2 | 13.04 | MVS
213 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Kalimati Busty under Kurseong-Sub Division, PHED, GTA | TSM/010591 | SM/11330 | Retrofitting | 17/02/2022 | 56 | 13.49 | Yes | 13.49 |  | 30/06/2022 | 2 | 12.48 | MVS
214 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional households Tap connection under JSP Programme for PWS Scheme Soureni Bazar | TSM/009309 | SM/11306 | Retrofitting | 27/01/2022 | 166 | 23.6 | Yes | 23.6 |  | 30/06/2022 | 1 | 22.21 | MVS
215 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution networks retrofitting under JSP Programme for PWS Scheme for Chowandhura | TSM/009303 | SM/11311 | Retrofitting | 27/01/2022 | 41 | 11.81 | Yes | 11.81 |  | 30/06/2022 | 1 | 11.04 | MVS
216 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | TSM/011927 | SM/11856 | New | 20/05/2022 | 100 | 290.75 | Yes | 290.75 | 26/05/2023 | 12/07/2023 | 3 | 287.72 | MVS
217 | DARJEELING | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME | TSM/010346 | SM/12750 | New | 22/08/2022 | 1794 | 754.32 | Yes | 754.32 | 11/08/2023 | 11/08/2023 | 9 | 676.27 | MVS
218 | DARJEELING | Neorakhola W/S Mnt. Division | Augmentation of source for lower Takbia | TSM/009479 | SM/11374 | Augmentation | 17/02/2022 | 0 | 28.05 | Yes | 28.05 |  | 30/08/2024 | 2 | 24.72 | MVS
219 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011831 | SM/11891 | New | 20/05/2022 | 759 | 865.61 | Yes | 865.61 |  | 29/09/2022 | 3 | 860.97 | MVS
220 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009535 | SM/11345 | New | 16/03/2022 | 52 | 24.77 | Yes | 24.77 |  | 12/07/2022 | 2 | 23.93 | MVS
221 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/012602 | SM/12748 | Augmentation | 22/08/2022 | 598 | 255.93 | Yes | 255.93 | 29/08/2024 | 05/06/2023 | 15 | 303.63 | MVS
222 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) | TSM/010331 | SM/13509 | New | 09/09/2022 | 920 | 608.67 | Yes | 608.67 | 30/08/2024 | 15/06/2023 | 14 | 514.01 | MVS
223 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME | TSM/015582 | SM/13467 | Augmentation | 09/09/2022 | 194 | 647.04 | Yes | 647.04 | 29/08/2024 | 15/06/2023 | 6 | 435.09 | MVS
224 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | TSM/010966 | SM/14517 | Augmentation | 16/03/2022 | 8332 | 2399.99 | Yes | 2399.99 | 29/08/2024 | 02/08/2023 | 7 | 2476.01 | MVS
225 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/015166 | SM/14529 | New | 22/08/2022 | 2710 | 2347.04 | Yes | 2347.04 | 02/01/2025 | 30/07/2024 | 6 | 2063.47 | MVS
226 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | TSM/014847 | SM/14532 | New | 22/08/2022 | 1060 | 1462.38 | Yes | 1462.38 | 24/02/2023 | 29/05/2023 | 3 | 1408.05 | MVS
227 | DARJEELING | Neorakhola W/S Mnt. Division | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME | TSM/014898 | SM/16160 | New | 28/12/2022 | 196 | 237.91 | Yes | 237.91 | 08/02/2023 | 28/04/2023 | 2 | 197.63 | MVS
228 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/017463 | SM/15884 | New | 28/12/2022 | 644 | 710.16 | Yes | 710.16 | 11/02/2023 | 29/04/2025 | 3 | 1025.89 | MVS
229 | DARJEELING | Neorakhola W/S Mnt. Division | GOKE PIPED WATER SUPPLY SCHEME. | TSM/018207 | SM/15873 | New | 28/12/2022 | 1083 | 932.73 | Yes | 932.73 | 26/09/2024 | 17/12/2024 | 3 | 912.65 | MVS
230 | DARJEELING | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | TSM/010335 | SM/15925 | New | 16/11/2022 | 1748 | 610.74 | Yes | 610.74 | 25/02/2025 | 22/08/2023 | 8 | 528.48 | MVS
231 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DEBURAM PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018510 | SM/15858 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 | 14/11/2024 | 1 | 0.01 | MVS
232 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT OMI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018506 | SM/15859 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
233 | DARJEELING | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013286 | SM/16534 | New | 22/08/2022 | 389 | 1531.5 | Yes | 1531.5 | 22/02/2023 | 09/04/2025 | 3 | 1555.56 | MVS
234 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | TSM/014857 | SM/16535 | New | 22/08/2022 | 1196 | 1055.89 | Yes | 1055.89 | 30/11/2022 | 27/04/2023 | 2 | 1047.97 | MVS
235 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA BANSGAON PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018502 | SM/15629 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
236 | DARJEELING | Neorakhola W/S Mnt. Division | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. | TSM/015037 | SM/16238 | New | 28/12/2022 | 43 | 133.16 | Yes | 133.16 | 08/02/2023 | 17/07/2023 | 2 | 129 | MVS
237 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT | TSM/016292 | SM/16627 | New | 26/09/2022 | 854 | 954.9 | Yes | 954.9 | 02/12/2022 | 29/04/2025 | 2 | 27.17 | MVS
238 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DANGARVITA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018504 | SM/15627 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 | 14/11/2024 | 1 | 0.01 | MVS
239 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018498 | SM/15631 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
240 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Budharugaon village of Budharugaon Piped water Supply Scheme | TSM/006156 | SM/07041 | Retrofitting | 25/09/2020 | 1546 | 91.98 | Yes | 91.98 | 18/06/2021 | 02/08/2021 | 1 | 41.87 | MVS
241 | DARJEELING | Neorakhola W/S Mnt. Division | MAHANADI FOREST PIPED WATER SUPPLY SCHEME | TSM/017745 | SM/15648 | New | 30/09/2022 | 191 | 230 | Yes | 230 | 25/04/2023 | 08/07/2024 | 2 | 173.05 | MVS
242 | DARJEELING | Neorakhola W/S Mnt. Division | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017741 | SM/15655 | New | 30/09/2022 | 697 | 743.37 | Yes | 743.37 | 23/12/2022 | 07/06/2024 | 3 | 733.47 | MVS
243 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | TSM/010330 | SM/18321 | New | 09/09/2022 | 3721 | 1713.48 | Yes | 1713.48 | 16/03/2023 | 07/08/2023 | 10 | 1253.2 | MVS
244 | DARJEELING | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | TSM/007004 | SM/10264 | Retrofitting | 08/01/2021 | 1124 | 108.57 | Yes | 108.57 |  | 11/04/2022 | 4 | 72.59 | MVS
245 | DARJEELING | Neorakhola W/S Mnt. Division | SAMALBONG PWSS | TSM/017243 | SM/18722 | New | 28/12/2022 | 544 | 1305.89 | Yes | 1305.89 | 09/02/2023 | 29/04/2025 | 3 | 1302.58 | MVS
246 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS | TSM/012053 | SM/11854 | New | 20/05/2022 | 716 | 942.58 | Yes | 942.58 |  | 29/09/2022 | 3 | 935.51 | MVS
247 | DARJEELING | Kurseong Division | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | TSM/014420 | SM/18588 | New | 30/09/2022 | 2153 | 3308.68 | Yes | 3308.68 | 22/02/2023 | 23/03/2024 | 5 | 2994.09 | MVS
248 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/018540 | SM/18601 | New | 28/12/2022 | 2294 | 2696.35 | Yes | 2696.35 | 26/09/2024 | 02/12/2024 | 3 | 2690.49 | MVS
249 | DARJEELING | Kurseong Division | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | TSM/012921 | SM/18640 | New | 30/09/2022 | 886 | 1208.42 | Yes | 1208.42 | 25/11/2022 | 21/08/2023 | 1 | 5.46 | MVS
250 | DARJEELING | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | TSM/010333 | SM/18614 | New | 22/08/2022 | 1748 | 1017.38 | Yes | 1017.38 | 06/10/2023 | 01/03/2024 | 5 | 752.22 | MVS
251 | DARJEELING | Neorakhola W/S Mnt. Division | DAWAIPANI & TUKDAH TEA GARDEN PWSS | TSM/018050 | SM/18752 | New | 28/12/2022 | 1324 | 1141.66 | Yes | 1141.66 | 08/02/2023 | 05/05/2025 | 3 | 1131.52 | MVS
252 | DARJEELING | Kurseong Division | Augmentation of Nipania Piped Water Supply Scheme. | TSM/020476 | SM/18881 | Augmentation | 10/03/2023 | 159 | 194.06 | Yes | 194.06 | 18/06/2024 |  | 0 | 0 | MVS
253 | DARJEELING | Siliguri W/S Division | IMPLEMENTATION OF AFFORDABLE IOT SYSTEM AT PASCHIM MADATI WATER SUPPLY SCHEME IN PHANSIDEWA BLOCK UNDER DARJEELING DISTRICT. | TSM/019981 |  | IOT | 16/11/2022 | 2596 | 106.85 | No | 0 |  |  | 0 | 0 | MVS
254 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) | TSM/006165 | SM/07047 | Retrofitting | 25/09/2020 | 1142 | 66.13 | Yes | 66.13 | 19/08/2021 | 11/12/2020 | 3 | 95.37 | MVS
255 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ranidanga & Shaibhita village of Ranidanga-Rangapani Piped water Supply Scheme | TSM/006149 | SM/07036 | Retrofitting | 25/09/2020 | 1470 | 79.26 | Yes | 79.26 |  | 23/02/2023 | 1 | 0.88 | MVS
256 | DARJEELING | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D | TSM/008599 | SM/09204 | Augmentation | 08/09/2021 | 450 | 21.41 | Yes | 21.41 | 19/08/2021 | 30/10/2024 | 1 | 49.08 | MVS
257 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retroffting for Piped water supply scheme at Ramam Forest Village | TSM/009295 | SM/10764 | Retrofitting | 27/01/2022 | 60 | 21.15 | Yes | 21.15 |  | 24/05/2022 | 2 | 20.72 | MVS
258 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta | TSM/009301 | SM/10768 | Retrofitting | 27/01/2022 | 127 | 25.05 | Yes | 25.05 |  | 24/05/2022 | 2 | 25.02 | MVS
259 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting for Piped water supply scheme at Upper Lamagoan | TSM/009097 | SM/10769 | Retrofitting | 27/01/2022 | 76 | 22.77 | Yes | 22.77 |  | 25/05/2022 | 2 | 19.02 | MVS
260 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village | TSM/009469 | SM/10770 | Retrofitting | 27/01/2022 | 39 | 21.64 | Yes | 21.64 |  | 24/05/2022 | 2 | 16.98 | MVS
261 | DARJEELING | Darjeeling Division | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | TSM/007001 | SM/10260 | Retrofitting | 08/01/2021 | 3812 | 269.79 | Yes | 269.79 |  | 11/04/2022 | 13 | 223.47 | MVS
262 | DARJEELING | Neorakhola W/S Mnt. Division | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. | TSM/010476 | SM/10790 | New | 16/03/2022 | 129 | 100.33 | Yes | 100.33 |  | 27/07/2023 | 2 | 1.9 | MVS
263 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Daragoan Lekharga. | TSM/009505 | SM/10836 | New | 17/02/2022 | 84 | 67.94 | Yes | 67.94 |  | 03/07/2025 | 4 | 66.02 | MVS
264 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal jeewan Mission/Jal swapno Mission for balance household at Fatingtar | TSM/011130 | SM/11384 | Retrofitting | 30/03/2022 | 95 | 27.28 | Yes | 27.28 |  | 27/07/2023 | 1 | 25.37 | MVS
265 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar | TSM/011124 | SM/11392 | Retrofitting | 30/03/2022 | 950 | 180.91 | Yes | 180.91 |  | 12/07/2022 | 3 | 162.31 | MVS
266 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011215 | SM/11395 | New | 30/03/2022 | 360 | 306.47 | Yes | 306.47 |  | 04/05/2023 | 2 | 268.66 | MVS
267 | DARJEELING | Kurseong Division | CONSTRUCTION OF SOURCE AND OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SONADA TO ACCOMODATE TWO MOUZAS MAINLY SONADA FOREST & SONADA KHASMAHAL UNDER SUKHIA POKHARI BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, PHED. | TSM/021463 | SM/19039 | New | 10/03/2023 | 2100 | 2250.46 | Yes | 2250.46 | 08/04/2025 |  | 0 | 0 | MVS
268 | DARJEELING | Neorakhola W/S Mnt. Division | Choongtoong & Lizahill Tea Garden water supply scheme | TSM/009503 | SM/12269 | New | 17/02/2022 | 2635 | 1242.31 | Yes | 1242.31 |  | 31/08/2023 | 4 | 1237.7 | MVS
269 | DARJEELING | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | TSM/010343 | SM/11773 | New | 25/04/2022 | 1213 | 449.92 | Yes | 449.92 | 17/12/2024 | 10/08/2023 | 6 | 430.88 | MVS
270 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA | TSM/009854 | SM/10804 | New | 17/02/2022 | 588 | 123.59 | Yes | 123.59 |  | 23/12/2022 | 2 | 76.49 | MVS
271 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA | TSM/009849 | SM/10809 | New | 17/02/2022 | 99 | 115.19 | Yes | 115.19 |  | 10/01/2023 | 2 | 67.61 | MVS
272 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Singbuli factory gaon | TSM/009511 | SM/10831 | New | 17/02/2022 | 211 | 77.24 | Yes | 77.24 |  | 26/05/2022 | 2 | 64.49 | MVS
273 | DARJEELING | Neorakhola W/S Mnt. Division | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | TSM/010207 | SM/10819 | New | 16/03/2022 | 298 | 150.71 | Yes | 150.71 |  | 27/07/2023 | 3 | 0.27 | MVS
274 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011755 | SM/12178 | New | 20/05/2022 | 285 | 595.74 | Yes | 595.74 |  | 14/10/2022 | 3 | 590.98 | MVS
275 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | TSM/009595 | SM/11324 | Retrofitting | 17/02/2022 | 425 | 36.13 | Yes | 36.13 |  | 30/06/2022 | 2 | 30.3 | MVS
276 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail | TSM/009308 | SM/11305 | Retrofitting | 27/01/2022 | 60 | 14.68 | Yes | 14.68 |  | 30/06/2022 | 2 | 13.58 | MVS
277 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Bada kothi | TSM/009482 | SM/11310 | Retrofitting | 27/01/2022 | 37 | 4.51 | Yes | 4.51 |  | 30/06/2022 | 1 | 3.78 | MVS
278 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA | TSM/010592 | SM/11331 | Retrofitting | 17/02/2022 | 310 | 31.31 | Yes | 31.31 |  | 30/06/2022 | 2 | 28.31 | MVS
279 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sivitar under Kurseong-Sub Division, PHED, GTA | TSM/010594 | SM/11333 | Retrofitting | 17/02/2022 | 110 | 26.69 | Yes | 26.69 |  | 30/06/2022 | 2 | 24.69 | MVS
280 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Singtam Tea Garden | TSM/009502 | SM/11338 | New | 17/02/2022 | 485 | 176.87 | Yes | 176.87 | 24/01/2023 | 19/07/2023 | 1 | 2.82 | MVS
281 | DARJEELING | Kurseong Division | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED | TSM/021459 | SM/19038 | New | 10/03/2023 | 4193 | 6918 | Yes | 6918 | 26/09/2024 | 19/12/2024 | 2 | 6769.16 | MVS
282 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme | TSM/006153 | SM/07218 | Retrofitting | 25/09/2020 | 1406 | 98.75 | Yes | 98.75 |  | 13/01/2022 | 3 | 70.21 | MVS
283 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | TSM/012597 | SM/12807 | Augmentation | 22/08/2022 | 630 | 649.84 | Yes | 649.84 | 29/08/2024 | 15/06/2023 | 8 | 520.67 | MVS
284 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | TSM/011531 | SM/12035 | Augmentation | 20/05/2022 | 538 | 117.92 | Yes | 117.92 | 02/12/2022 | 13/11/2024 | 5 | 84.08 | MVS
285 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009534 | SM/11346 | New | 16/03/2022 | 45 | 21.35 | Yes | 21.35 |  | 12/07/2022 | 2 | 20.32 | MVS
286 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009527 | SM/11349 | New | 16/03/2022 | 175 | 79.79 | Yes | 79.79 | 03/03/2022 | 23/08/2023 | 2 | 78.19 | MVS
287 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. | TSM/012507 | SM/11952 | New | 20/05/2022 | 898 | 884.34 | Yes | 884.34 |  | 03/11/2022 | 3 | 884.41 | MVS
288 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | TSM/010269 | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 16/03/2022 | 6 | 28.59 | Yes | 28.59 |  | 12/07/2022 | 6 | 23.59 | MVS
289 | DARJEELING | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | TSM/015200 | SM/13437 | New | 09/09/2022 | 175 | 187.01 | Yes | 187.01 | 29/08/2024 | 05/06/2023 | 8 | 43.81 | MVS
290 | DARJEELING | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | TSM/015189 | SM/13394 | Augmentation | 09/09/2022 | 631 | 319.83 | Yes | 319.83 | 25/02/2025 | 24/04/2025 | 8 | 304.92 | MVS
291 | DARJEELING | Neorakhola W/S Mnt. Division | PANTHABARI FOREST Piped Water Supply Scheme | TSM/018085 | SM/16143 | New | 28/12/2022 | 134 | 142.59 | Yes | 142.59 | 11/02/2023 | 12/01/2024 | 4 | 94.5 | MVS
292 | DARJEELING | Neorakhola W/S Mnt. Division | HATTA PIPED WATER SUPPLY SCHEME. | TSM/017468 | SM/15883 | New | 28/12/2022 | 134 | 329.63 | Yes | 329.63 | 08/02/2023 | 05/06/2023 | 2 | 279.65 | MVS
293 | DARJEELING | Neorakhola W/S Mnt. Division | MANEDARA PIPED WATER SUPPLY SCHEME. | TSM/017455 | SM/15885 | New | 28/12/2022 | 347 | 485.98 | Yes | 485.98 | 12/03/2024 | 18/06/2024 | 3 | 448.77 | MVS
294 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BIRSING PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018507 | SM/15856 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
295 | DARJEELING | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | TSM/010328 | SM/15908 | New | 28/12/2022 | 1612 | 758.56 | Yes | 758.56 | 24/03/2023 | 28/07/2022 | 7 | 64.97 | MVS
296 | DARJEELING | Neorakhola W/S Mnt. Division | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme | TSM/014789 | SM/16385 | New | 09/09/2022 | 445 | 556.38 | Yes | 556.38 | 16/02/2024 | 12/07/2023 | 2 | 533.79 | MVS
297 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/016235 | SM/16628 | New | 26/09/2022 | 643 | 870.77 | Yes | 870.77 | 02/12/2022 | 23/03/2024 | 3 | 852.87 | MVS
298 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT TARBANDHA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018501 | SM/15632 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
299 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (GUNAWAR) (PART) | TSM/014157 | SM/15649 | New | 30/09/2022 | 348 | 611 | Yes | 611 | 17/07/2023 | 17/10/2023 | 1 | 605.39 | MVS
300 | DARJEELING | Kurseong Division | PWS Scheme for Selim Hill Tea Garden | TSM/013284 | SM/15652 | New | 30/09/2022 | 384 | 967.91 | Yes | 967.91 | 23/12/2022 | 24/09/2024 | 3 | 915.81 | MVS
301 | DARJEELING | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | TSM/015201 | SM/13438 | New | 09/09/2022 | 209 | 184.33 | Yes | 184.33 | 12/03/2024 | 15/06/2023 | 8 | 159.56 | MVS
302 | DARJEELING | Neorakhola W/S Mnt. Division | BADAMTAM TEA GARDEN PWSS | TSM/018945 | SM/18725 | New | 28/12/2022 | 986 | 1124.76 | Yes | 1124.76 | 12/12/2023 | 05/06/2025 | 4 | 1123.59 | MVS
303 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/016215 | SM/18317 | New | 26/09/2022 | 955 | 1246.59 | Yes | 1246.59 | 26/09/2024 | 26/02/2024 | 5 | 1226.06 | MVS
304 | DARJEELING | Neorakhola W/S Mnt. Division | LEBONG & MINERAL TEA GARDEN PWSS | TSM/019193 | SM/18726 | New | 28/12/2022 | 1242 | 1123.93 | Yes | 1123.93 | 12/03/2024 | 18/06/2024 | 4 | 1122.53 | MVS
305 | DARJEELING | Kurseong Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD | TSM/014164 | SM/18727 | New | 28/12/2022 | 1682 | 1928.5 | Yes | 1928.5 | 11/02/2023 | 23/08/2023 | 2 | 1938.1 | MVS
306 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | TSM/009121 | SM/10026 | Augmentation | 22/11/2021 | 4923 | 1323.79 | Yes | 1323.79 | 11/08/2023 | 16/06/2022 | 15 | 1331.56 | MVS
307 | DARJEELING | Kurseong Division | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | TSM/014414 | SM/18639 | New | 30/09/2022 | 1896 | 1969.93 | Yes | 1969.93 | 31/12/2022 | 26/02/2024 | 5 | 1842.66 | MVS
308 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme | TSM/006168 | SM/07030 | Retrofitting | 25/09/2020 | 1597 | 93.81 | Yes | 93.81 |  | 28/03/2024 | 3 | 68.94 | MVS
309 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANGARJUNG TEA GARDEN & OTHER 3 VILLAGES PWSS(MVS),BLOCK: JORE BUNGALOW-SUKHIAPOKHRI,DISTRICT: DARJEELING | TSM/021465 | SM/19177 | New | 10/03/2023 | 6430 | 9214.38 | Yes | 9214.38 | 06/02/2024 | 09/09/2024 | 1 | 8505.63 | MVS
310 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block | TSM/006795 | SM/07422 | Retrofitting | 04/12/2020 | 286 | 18.5 | Yes | 18.5 | 19/08/2021 | 01/11/2021 | 2 | 47.96 | MVS
311 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Mangalsing Piped water Supply Scheme | TSM/006167 | SM/07029 | Retrofitting | 25/09/2020 | 1096 | 56.89 | Yes | 56.89 |  | 06/09/2021 | 1 | 4.3 | MVS
312 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Paschim Madati Mouza part of Purba Madati Piped water Supply Scheme (Part-A) | TSM/006161 | SM/07070 | Retrofitting | 25/09/2020 | 810 | 44.75 | Yes | 44.75 |  | 18/12/2020 | 1 | 35.92 | MVS
313 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | TSM/006164 | SM/07049 | Retrofitting | 25/09/2020 | 1825 | 98.65 | Yes | 98.65 |  | 05/06/2023 | 3 | 42.33 | MVS
314 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for kantivita,Dhamnagach, & Purba bansgaon kismath villages under Bandargachh Piped water Supply Scheme | TSM/006158 | SM/07220 | Retrofitting | 25/09/2020 | 1173 | 77.54 | Yes | 77.54 |  |  | 0 | 0 | MVS
315 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Rajajhar & Rangapani village of Ranidanga-Rangapani Piped water Supply Scheme | TSM/006166 | SM/07037 | Retrofitting | 25/09/2020 | 1403 | 76.12 | Yes | 76.12 |  | 28/07/2023 | 2 | 1.62 | MVS
316 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme | TSM/006159 | SM/07045 | Retrofitting | 25/09/2020 | 1800 | 92.52 | Yes | 92.52 | 18/06/2021 | 02/08/2021 | 3 | 100.19 | MVS
317 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. | TSM/009476 | SM/10774 | Retrofitting | 27/01/2022 | 59 | 18.12 | Yes | 18.12 |  | 26/05/2022 | 3 | 17.26 | MVS
318 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | TSM/009125 | SM/09828 | Augmentation | 22/11/2021 | 100 | 613.39 | Yes | 613.39 | 08/02/2024 | 22/04/2022 | 19 | 662.32 | MVS
319 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | TSM/009122 | SM/09830 | Augmentation | 22/11/2021 | 2131 | 566.48 | Yes | 566.48 | 25/07/2023 | 09/02/2023 | 18 | 587.21 | MVS
320 | DARJEELING | Darjeeling Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | TSM/007002 | SM/10259 | Retrofitting | 08/01/2021 | 1005 | 80.55 | Yes | 80.55 |  | 06/05/2022 | 11 | 50.82 | MVS
321 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | TSM/009592 | SM/10073 | Augmentation | 16/12/2021 | 4904 | 910.44 | Yes | 910.44 | 27/09/2024 | 19/10/2023 | 14 | 760.23 | MVS
322 | DARJEELING | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | TSM/007005 | SM/10263 | Retrofitting | 08/01/2021 | 312 | 39.28 | Yes | 39.28 |  | 20/04/2022 | 4 | 33.87 | MVS
323 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | TSM/009576 | SM/10107 | Augmentation | 16/12/2021 | 3590 | 641.16 | Yes | 641.16 | 31/07/2023 | 06/05/2022 | 14 | 731.6 | MVS
324 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | TSM/009588 | SM/10108 | Augmentation | 16/12/2021 | 3735 | 640.28 | Yes | 640.28 | 12/03/2024 | 20/02/2023 | 10 | 699 | MVS
325 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin | TSM/008607 | SM/09078 | Retrofitting | 08/09/2021 | 398 | 23.31 | Yes | 23.31 | 27/07/2023 | 25/11/2024 | 3 | 1.7 | MVS
326 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Kolbong | TSM/009508 | SM/10834 | New | 17/02/2022 | 107 | 104.23 | Yes | 104.23 | 12/10/2023 | 31/05/2023 | 6 | 84.53 | MVS
327 | DARJEELING | Neorakhola W/S Mnt. Division | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | TSM/010475 | SM/10622 | Disaster | 16/03/2022 | 0 | 480.8 | Yes | 480.8 |  | 13/04/2022 | 4 | 347.68 | MVS
328 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. | TSM/011122 | SM/11394 | Retrofitting | 30/03/2022 | 1395 | 199.28 | Yes | 199.28 |  | 12/07/2022 | 3 | 184.59 | MVS
329 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011222 | SM/12366 | New | 30/03/2022 | 1358 | 1129.94 | Yes | 1129.94 |  | 05/05/2025 | 5 | 1125 | MVS
330 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | TSM/009579 | SM/10477 | Augmentation | 27/01/2022 | 321 | 335.48 | Yes | 335.48 | 31/07/2024 | 20/02/2023 | 9 | 266.56 | MVS
331 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | TSM/009101 | SM/10476 | Augmentation | 27/01/2022 | 3189 | 807.68 | Yes | 807.68 | 25/02/2025 | 24/04/2025 | 9 | 717.42 | MVS
332 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | TSM/009860 | SM/10798 | New | 17/02/2022 | 233 | 226.19 | Yes | 226.19 |  | 05/08/2022 | 2 | 118.28 | MVS
333 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA | TSM/009853 | SM/10805 | New | 17/02/2022 | 588 | 123.11 | Yes | 123.11 |  | 25/11/2022 | 2 | 79.07 | MVS
334 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | TSM/009851 | SM/10807 | New | 17/02/2022 | 754 | 103.62 | Yes | 103.62 |  | 26/05/2022 | 3 | 64.48 | MVS
335 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | TSM/009855 | SM/10803 | New | 17/02/2022 | 588 | 91.97 | Yes | 91.97 |  | 26/05/2022 | 3 | 61.51 | MVS
336 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA | TSM/009844 | SM/10828 | New | 17/02/2022 | 303 | 117.73 | Yes | 117.73 |  | 30/06/2022 | 4 | 82.9 | MVS
337 | DARJEELING | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING | TSM/010030 | SM/10824 | New | 16/03/2022 | 794 | 542.09 | Yes | 542.09 |  | 29/09/2022 | 1 | 4.89 | MVS
338 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. | TSM/009602 | SM/11317 | Retrofitting | 17/02/2022 | 142 | 12.12 | Yes | 12.12 |  | 30/06/2022 | 2 | 10.99 | MVS
339 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS | TSM/012041 | SM/11855 | New | 20/05/2022 | 228 | 408.25 | Yes | 408.25 |  | 19/09/2023 | 2 | 372.52 | MVS
340 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012579 | SM/11943 | New | 20/05/2022 | 385 | 212.19 | Yes | 212.19 | 07/03/2024 | 18/06/2024 | 3 | 222.66 | MVS
341 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009536 | SM/11344 | New | 16/03/2022 | 120 | 32.23 | Yes | 32.23 |  | 20/01/2024 | 4 | 40.4 | MVS
342 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | TSM/011534 | SM/12034 | Augmentation | 20/05/2022 | 239 | 197.56 | Yes | 197.56 | 27/03/2023 | 18/08/2023 | 6 | 221.81 | MVS
343 | DARJEELING | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme | TSM/015192 | SM/13508 | New | 09/09/2022 | 1391 | 563.65 | Yes | 563.65 | 29/08/2024 | 12/07/2023 | 8 | 492.13 | MVS
344 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | TSM/011526 | SM/12038 | Augmentation | 20/05/2022 | 200 | 119.17 | Yes | 119.17 | 25/02/2025 | 24/04/2025 | 5 | 37 | MVS
345 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 192 numbers of school under Darjeeling Pulbazar Block in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte | TSM/010216 | SM/11356 | School | 16/03/2022 | 0 | 638.99 | Yes | 638.99 |  | 12/07/2022 | 1 | 620.25 | MVS
346 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | TSM/010271 | SM/11365 | Health Center | 16/03/2022 | 0 | 38.03 | Yes | 38.03 |  | 12/07/2022 | 7 | 23.69 | MVS
347 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Rohini Tea Garden | TSM/011593 | SM/11938 | New | 25/04/2022 | 614 | 408.51 | Yes | 408.51 | 29/12/2022 | 28/04/2023 | 3 | 334.16 | MVS
348 | DARJEELING | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | TSM/015191 | SM/13433 | Augmentation | 09/09/2022 | 1363 | 587.76 | Yes | 587.76 | 29/08/2024 | 15/12/2023 | 8 | 458.87 | MVS
349 | DARJEELING | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | TSM/015196 | SM/13393 | Augmentation | 09/09/2022 | 393 | 339.93 | Yes | 339.93 | 29/08/2024 | 08/05/2023 | 6 | 273.43 | MVS
350 | DARJEELING | Neorakhola W/S Mnt. Division | LATPANICHAR PIPED WATER SUPPLY SCHEME | TSM/018164 | SM/16162 | New | 28/12/2022 | 172 | 268.11 | Yes | 268.11 | 08/02/2023 | 24/09/2024 | 3 | 243.86 | MVS
351 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME | TSM/020168 | SM/15271 | Augmentation | 16/11/2022 | 0 | 148.34 | Yes | 148.34 | 26/12/2024 | 18/09/2024 | 6 | 83.37 | MVS
352 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | TSM/020161 | SM/15273 | Augmentation | 16/11/2022 | 0 | 188.14 | Yes | 188.14 | 29/08/2024 | 30/09/2023 | 4 | 19.44 | MVS
353 | DARJEELING | Neorakhola W/S Mnt. Division | LODHAMA PIPED WATER SUPPLY SCHEME. | TSM/018972 | SM/15872 | New | 28/12/2022 | 45 | 178.54 | Yes | 178.54 | 01/02/2023 | 27/04/2023 | 2 | 157.85 | MVS
354 | DARJEELING | Neorakhola W/S Mnt. Division | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme | TSM/018086 | SM/16142 | New | 28/12/2022 | 711 | 334.74 | Yes | 334.74 | 27/04/2023 | 19/07/2023 | 1 | 4.38 | MVS
355 | DARJEELING | Neorakhola W/S Mnt. Division | PANIGHATA Piped Water Supply Scheme | TSM/018071 | SM/16144 | New | 28/12/2022 | 1222 | 363.69 | Yes | 363.69 | 26/09/2024 | 28/01/2024 | 6 | 360.95 | MVS
356 | DARJEELING | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME | TSM/010336 | SM/15928 | New | 16/11/2022 | 867 | 368.86 | Yes | 368.86 | 17/12/2024 | 26/10/2023 | 6 | 315.86 | MVS
357 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DAMDAMA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018508 | SM/15857 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
358 | DARJEELING | Neorakhola W/S Mnt. Division | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME | TSM/016186 | SM/15894 | New | 28/12/2022 | 259 | 295.85 | Yes | 295.85 | 10/02/2023 | 28/04/2023 | 2 | 251.87 | MVS
359 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | TSM/020258 | SM/15895 | New | 28/12/2022 | 598 | 496.03 | Yes | 496.03 | 25/04/2023 | 03/09/2024 | 4 | 225.67 | MVS
360 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/015162 | SM/16352 | New | 22/08/2022 | 715 | 705.57 | Yes | 705.57 | 02/12/2022 | 28/04/2023 | 2 | 694.98 | MVS
361 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ALOOBARI PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012886 | SM/16629 | New | 26/09/2022 | 333 | 610.28 | Yes | 610.28 | 02/12/2022 | 28/04/2023 | 2 | 579.52 | MVS
362 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | TSM/018158 | SM/15924 | Augmentation | 16/11/2022 | 803 | 858.49 | Yes | 858.49 | 29/08/2024 | 09/01/2024 | 11 | 692.97 | MVS
363 | DARJEELING | Neorakhola W/S Mnt. Division | SUKNA PIPED WATER SUPPLY SCHEME | TSM/017746 | SM/15653 | New | 30/09/2022 | 402 | 304.63 | Yes | 304.63 | 29/12/2022 | 08/07/2024 | 3 | 258.41 | MVS
364 | DARJEELING | Neorakhola W/S Mnt. Division | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. | TSM/018033 | SM/15878 | New | 28/12/2022 | 384 | 277.07 | Yes | 277.07 | 08/02/2023 | 28/04/2023 | 4 | 268.22 | MVS
365 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013037 | SM/18282 | New | 22/08/2022 | 1124 | 1545.44 | Yes | 1545.44 | 22/02/2023 | 18/07/2023 | 2 | 1481.43 | MVS
366 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/016207 | SM/18633 | New | 26/09/2022 | 1243 | 1443.98 | Yes | 1443.98 | 02/12/2022 | 26/02/2024 | 5 | 1433.61 | MVS
367 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | TSM/016300 | SM/18635 | New | 26/09/2022 | 1938 | 1907.13 | Yes | 1907.13 | 30/11/2022 | 26/02/2024 | 4 | 1902.08 | MVS
368 | DARJEELING | Neorakhola W/S Mnt. Division | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS | TSM/016195 | SM/18724 | New | 28/12/2022 | 1347 | 1783.75 | Yes | 1783.75 | 27/04/2023 | 19/12/2024 | 3 | 1780.02 | MVS
369 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | TSM/018448 | SM/18385 | Augmentation | 16/11/2022 | 5785 | 2394.79 | Yes | 2394.79 | 25/02/2025 | 29/01/2024 | 43 | 2024.24 | MVS
370 | DARJEELING | Neorakhola W/S Mnt. Division | MAHAL DIRAM TEA GARDEN PWSS | TSM/011323 | SM/13623 | New | 22/08/2022 | 166 | 230.73 | Yes | 230.73 | 12/12/2022 | 28/02/2023 | 3 | 215.95 | MVS
371 | DARJEELING | Neorakhola W/S Mnt. Division | KANKIBONG PWSS | TSM/019208 | SM/18992 | New | 28/12/2022 | 672 | 836.23 | Yes | 836.23 | 01/02/2023 | 17/10/2023 | 1 | 785.44 | MVS
372 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | TSM/011753 | SM/18820 | New | 20/05/2022 | 1170 | 2125.19 | Yes | 2125.19 | 22/02/2023 | 05/05/2025 | 4 | 2116.86 | MVS
373 | DARJEELING | Neorakhola W/S Mnt. Division | DARJEELING PULBAZAR PUMPING-II PWSS | TSM/019546 | SM/18659 | New | 28/12/2022 | 2169 | 8823.99 | Yes | 8823.99 | 28/11/2023 | 01/08/2024 | 8 | 8213.92 | MVS
374 | DARJEELING | Neorakhola W/S Mnt. Division | DARJEELING PULBAZAR PUMPING-III PWSS | TSM/019593 | SM/18792 | New | 28/12/2022 | 1620 | 7379.87 | Yes | 7379.87 | 05/02/2024 | 11/09/2024 | 4 | 6756.47 | MVS
375 | DARJEELING | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | TSM/010323 | SM/18613 | New | 22/08/2022 | 3355 | 1079.19 | Yes | 1079.19 | 16/03/2023 | 18/08/2023 | 9 | 769.82 | MVS
376 | DARJEELING | Kurseong Division | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | TSM/014424 | SM/18647 | New | 30/09/2022 | 4639 | 3828.95 | Yes | 3828.95 | 29/12/2022 | 11/08/2023 | 4 | 3619 | MVS
377 | DARJEELING | Kurseong Division | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) | TSM/014421 | SM/18648 | New | 30/09/2022 | 1564 | 2338.45 | Yes | 2338.45 | 12/12/2023 | 11/08/2023 | 2 | 2171.44 | MVS
378 | DARJEELING | Kurseong Division | PWS Scheme for Tindharia & Nurbang Tea Garden | TSM/013280 | SM/18649 | New | 30/09/2022 | 843 | 1203.19 | Yes | 1203.19 | 23/12/2022 | 09/04/2025 | 3 | 1181.61 | MVS
379 | DARJEELING | Darjeeling Division | BHIRGAON DHARGAON PWSS | TSM/011777 | SM/18714 | New | 05/07/2022 | 149 | 162.75 | Yes | 162.75 | 12/12/2022 | 07/08/2023 | 1 | 152.77 | MVS
380 | DARJEELING | Kurseong Division | Piped Water supply scheme of Ambotia T.E., Saint Mary's - I, Spring side, Makaibari and Karbia T.E. by pumping water from Balasan river under PHED Kurseong Division, GTA | TSM/021464 |  | New | 10/03/2023 | 3571 | 13750 | No | 0 |  |  | 0 | 0 | MVS
381 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | TSM/006797 | SM/07428 | Retrofitting | 04/12/2020 | 1454 | 77.59 | Yes | 77.59 |  | 25/11/2024 | 3 | 11.9 | MVS
382 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | TSM/006170 | SM/07032 | Retrofitting | 25/09/2020 | 508 | 31.72 | Yes | 31.72 |  | 18/12/2020 | 3 | 132.12 | MVS
383 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bansgaon village of Purba Bansgaon Piped water Supply Scheme | TSM/006147 | SM/07040 | Retrofitting | 25/09/2020 | 1347 | 85.15 | Yes | 85.15 |  | 11/12/2020 | 1 | 37.26 | MVS
384 | DARJEELING | Darjeeling Division | RIMBICK WATER SUPPLY SCHEME | TSM/008813 | SM/09427 | New | 29/09/2021 | 1636 | 627.68 | Yes | 627.68 | 12/10/2023 | 04/04/2022 | 4 | 628.93 | MVS
385 | DARJEELING | Darjeeling Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] | TSM/007003 | SM/10258 | Retrofitting | 08/01/2021 | 1560 | 112.63 | Yes | 112.63 |  | 20/12/2022 | 5 | 199.78 | MVS
386 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | TSM/009499 | SM/10714 | Augmentation | 16/03/2022 | 381 | 849.31 | Yes | 849.31 | 25/02/2025 | 28/09/2023 | 11 | 721.41 | MVS
387 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay | TSM/009477 | SM/10780 | Retrofitting | 27/01/2022 | 28 | 17.18 | Yes | 17.18 |  | 26/05/2022 | 2 | 16.83 | MVS
388 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | TSM/009504 | SM/10837 | New | 17/02/2022 | 160 | 101.18 | Yes | 101.18 |  | 28/11/2024 | 3 | 93.64 | MVS
389 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection existing PWSS at Bunkulung | TSM/011139 | SM/11391 | Retrofitting | 30/03/2022 | 155 | 33.5 | Yes | 33.5 |  | 12/07/2022 | 1 | 27.91 | MVS
390 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam | TSM/011123 | SM/11393 | Retrofitting | 30/03/2022 | 1398 | 184.74 | Yes | 184.74 | 24/01/2023 | 12/07/2023 | 2 | 174.64 | MVS
391 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Lower Bish Acre, Ghayabari. | TSM/009513 | SM/11397 | New | 30/03/2022 | 80 | 69.47 | Yes | 69.47 |  | 23/12/2022 | 3 | 66.5 | MVS
392 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | TSM/011219 | SM/11398 | New | 30/03/2022 | 225 | 379.74 | Yes | 379.74 | 07/03/2024 | 04/07/2024 | 3 | 335.84 | MVS
393 | DARJEELING | Siliguri W/S Division | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME | TSM/010341 | SM/11777 | New | 25/04/2022 | 652 | 164.44 | Yes | 164.44 | 07/12/2022 | 20/05/2022 | 5 | 111.23 | MVS
394 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/009888 | SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 27/01/2022 | 6 | 18.42 | Yes | 18.42 |  | 12/07/2022 | 5 | 17.9 | MVS
395 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/009889 | SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 27/01/2022 | 6 | 13.32 | Yes | 13.32 |  | 12/07/2022 | 3 | 12.89 | MVS
396 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | TSM/009859 | SM/10799 | New | 17/02/2022 | 233 | 80.89 | Yes | 80.89 |  | 26/05/2022 | 2 | 47.64 | MVS
397 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | TSM/009852 | SM/10806 | New | 17/02/2022 | 588 | 122.1 | Yes | 122.1 |  | 26/05/2022 | 3 | 70.97 | MVS
398 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | TSM/009850 | SM/10808 | New | 17/02/2022 | 233 | 189.33 | Yes | 189.33 |  | 09/04/2025 | 3 | 175.93 | MVS
399 | DARJEELING | Neorakhola W/S Mnt. Division | BARA CHENGA PIPED WATER SUPPLY SCHEME | TSM/010843 | SM/10816 | New | 16/03/2022 | 584 | 422.1 | Yes | 422.1 |  | 03/01/2024 | 6 | 3.96 | MVS
400 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | TSM/009843 | SM/10829 | New | 17/02/2022 | 269 | 167.48 | Yes | 167.48 |  | 05/05/2025 | 2 | 22.61 | MVS
401 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. | TSM/009599 | SM/11320 | Retrofitting | 17/02/2022 | 234 | 19.74 | Yes | 19.74 |  | 30/06/2022 | 2 | 17.94 | MVS
402 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III | TSM/009304 | SM/11301 | Retrofitting | 27/01/2022 | 45 | 8.63 | Yes | 8.63 |  | 30/06/2022 | 2 | 7.86 | MVS
403 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon | TSM/009307 | SM/11304 | Retrofitting | 27/01/2022 | 44 | 23.72 | Yes | 23.72 |  | 30/06/2022 | 2 | 20.4 | MVS
404 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household Tap connection under JSP Programme for PWS Scheme Manju Dara Gaon | TSM/009483 | SM/11307 | Retrofitting | 27/01/2022 | 35 | 6.09 | Yes | 6.09 |  | 30/06/2022 | 1 | 5.33 | MVS
405 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA | TSM/010593 | SM/11332 | Retrofitting | 17/02/2022 | 244 | 26.39 | Yes | 26.39 |  | 30/06/2022 | 2 | 25.25 | MVS
406 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | TSM/011929 | SM/11890 | New | 20/05/2022 | 609 | 760.91 | Yes | 760.91 |  | 29/09/2022 | 3 | 754.83 | MVS
407 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011829 | SM/12736 | New | 20/05/2022 | 990 | 1292.66 | Yes | 1292.66 |  | 03/11/2022 | 3 | 1282.53 | MVS
408 | DARJEELING | Neorakhola W/S Mnt. Division | Providing household tap connection from existing scheme at Museykhola & Dokan Dhura | TSM/011125 | SM/11818 | Retrofitting | 25/04/2022 | 279 | 50.5 | Yes | 50.5 | 01/03/2023 | 31/10/2023 | 1 | 46.23 | MVS
409 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009533 | SM/11347 | New | 16/03/2022 | 96 | 39.89 | Yes | 39.89 |  | 12/07/2022 | 2 | 38.8 | MVS
410 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. | TSM/009264 | SM/11353 | New | 16/03/2022 | 200 | 72.84 | Yes | 72.84 |  | 12/07/2022 | 2 | 64.04 | MVS
411 | DARJEELING | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | TSM/010344 | SM/11785 | New | 25/04/2022 | 216 | 165.38 | Yes | 165.38 | 31/07/2024 | 20/05/2022 | 7 | 145.22 | MVS
412 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | TSM/012510 | SM/13571 | New | 20/05/2022 | 1344 | 1420.81 | Yes | 1420.81 | 30/11/2022 | 05/05/2025 | 3 | 1411.87 | MVS
413 | DARJEELING | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme | TSM/015197 | SM/13427 | Augmentation | 09/09/2022 | 396 | 244.41 | Yes | 244.41 | 29/08/2024 | 05/06/2023 | 7 | 215.47 | MVS
414 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011832 | SM/13042 | New | 20/05/2022 | 578 | 1047.9 | Yes | 1047.9 |  | 31/07/2024 | 4 | 1018.82 | MVS
415 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | TSM/020162 | SM/14835 | Augmentation | 16/11/2022 | 92 | 98.37 | Yes | 98.37 | 29/08/2024 | 10/08/2023 | 6 | 51.67 | MVS
416 | DARJEELING | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | TSM/010329 | SM/14846 | New | 16/11/2022 | 2363 | 847.7 | Yes | 847.7 | 11/08/2023 | 11/08/2023 | 8 | 743.43 | MVS
417 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013295 | SM/13960 | New | 22/08/2022 | 349 | 300.61 | Yes | 300.61 |  | 23/12/2022 | 2 | 280.55 | MVS
418 | DARJEELING | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | TSM/010339 | SM/13439 | New | 09/09/2022 | 153 | 92.86 | Yes | 92.86 | 24/03/2023 | 27/07/2023 | 6 | 79.4 | MVS
419 | DARJEELING | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012888 | SM/14149 | New | 22/08/2022 | 946 | 1893.19 | Yes | 1893.19 | 30/11/2022 | 05/05/2025 | 4 | 1841.84 | MVS
420 | DARJEELING | Neorakhola W/S Mnt. Division | BLOOMFIELD TEA GARDEN PWSS | TSM/014905 | SM/15910 | New | 28/12/2022 | 556 | 447.08 | Yes | 447.08 | 16/02/2024 | 14/06/2024 | 4 | 432.73 | MVS
421 | DARJEELING | Neorakhola W/S Mnt. Division | RESHOP BAZAR PIPED WATER SUPPLY SCHEME | TSM/017530 | SM/15882 | New | 28/12/2022 | 181 | 423.41 | Yes | 423.41 | 08/02/2023 | 28/04/2023 | 2 | 418.07 | MVS
422 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BAIRAGI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018505 | SM/15855 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 | 14/11/2024 | 1 | 0.01 | MVS
423 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/015164 | SM/16532 | New | 22/08/2022 | 1274 | 1658.37 | Yes | 1658.37 | 13/12/2022 | 01/08/2024 | 2 | 58.79 | MVS
424 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018509 | SM/15860 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
425 | DARJEELING | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | TSM/010334 | SM/16753 | New | 22/08/2022 | 2155 | 890.47 | Yes | 890.47 | 16/03/2023 | 09/08/2023 | 9 | 777.07 | MVS
426 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Sepoy Dhura Tea Garden | TSM/013289 | SM/15651 | New | 30/09/2022 | 378 | 525.04 | Yes | 525.04 | 23/12/2022 | 05/05/2025 | 4 | 513.68 | MVS
427 | DARJEELING | Neorakhola W/S Mnt. Division | MONGPOO CINKONA PLANTATION, ROLAK & LONKU KHASMAHAL PWSS | TSM/015045 | SM/17191 | New | 09/09/2022 | 1682 | 240.32 | Yes | 879.54 | 29/12/2022 | 28/04/2023 | 1 | 230.27 | MVS
428 | DARJEELING | Kurseong Division | PWS Scheme for Edenvale Tea Garden | TSM/013285 | SM/18710 | New | 30/09/2022 | 108 | 150.23 | Yes | 150.23 | 25/11/2022 | 07/08/2023 | 2 | 140.15 | MVS
429 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009530 | SM/11348 | New | 16/03/2022 | 150 | 27.68 | Yes | 27.68 |  | 25/11/2022 | 2 | 25.15 | MVS
430 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | TSM/014851 | SM/18636 | New | 22/08/2022 | 722 | 1046.24 | Yes | 1046.24 | 22/02/2023 | 05/05/2025 | 2 | 1039.55 | MVS
431 | DARJEELING | Kurseong Division | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | TSM/012926 | SM/18559 | New | 30/09/2022 | 768 | 1470.02 | Yes | 1470.02 | 23/12/2022 | 05/05/2025 | 3 | 1409.88 | MVS
432 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/015170 | SM/14147 | New | 22/08/2022 | 960 | 1120.63 | Yes | 1120.63 | 02/12/2022 | 26/02/2024 | 4 | 1119.78 | MVS
433 | DARJEELING | Kurseong Division | PWS Scheme for Mirik Khasmahal | TSM/014413 | SM/18650 | New | 30/09/2022 | 1306 | 1261.17 | Yes | 1261.17 | 23/12/2022 | 23/03/2024 | 3 | 1245.13 | MVS
434 | DARJEELING | Kurseong Division | AUGMENTATION OF PAIRIKUMARI PIPED WATER SUPPLY SCHEME | TSM/020479 | SM/18879 | Augmentation | 10/03/2023 | 80 | 93.17 | Yes | 93.17 | 18/06/2024 |  | 0 | 0 | MVS
435 | DARJEELING | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEM UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | TSM/018512 | SM/15854 | Solarisation | 16/11/2022 | 0 | 9.14 | Yes | 9.14 | 25/04/2023 |  | 0 | 0 | MVS
436 | DARJEELING | Kurseong Division | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | TSM/017228 | SM/18534 | New | 30/09/2022 | 6130 | 3073.44 | Yes | 3073.44 | 08/11/2023 | 09/06/2025 | 2 | 2991.04 | MVS
437 | DARJEELING | Kurseong Division | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. | TSM/011596 | SM/11729 | Support | 25/04/2022 | 0 | 12.17 | Yes | 12.17 |  | 17/01/2023 | 2 | 10.66 | MVS
438 | DARJEELING | Neorakhola W/S Mnt. Division | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA | TSM/012036 | SM/12737 | Support | 20/05/2022 | 0 | 8.66 | Yes | 8.66 |  | 19/04/2023 | 5 | 9.48 | MVS
439 | DARJEELING | Northern Mechanical Division | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . | TSM/016096 | SM/14065 | Support | 26/09/2022 | 0 | 19.05 | Yes | 19.05 |  | 01/06/2023 | 7 | 17.45 | MVS
440 | DARJEELING | Siliguri W/S Division | Operational Charges Of Darjeeling District Laboratory related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission 2023-24 | TSM/022388 | SM/19262 | Support | 09/03/2024 | 0 | 26.78 | Yes | 26.78 |  |  | 0 | 0 | MVS
441 | DARJEELING | Siliguri W/S Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Siliguri Mahakuma Parishad (SMP) Darjeeling District. | TSM/008153 | SM/09029 | Support | 19/08/2021 | 0 | 88 | Yes | 88 |  | 17/08/2022 | 1 | 85.07 | MVS
442 | DARJEELING | Neorakhola W/S Mnt. Division | Proposed Estimate for Construction of Sub - Divisional Water Testing Lab over the existing PHE Division Building at Kurseong | TSM/014318 | SM/14195 | Support | 22/08/2022 | 0 | 59.93 | Yes | 59.93 |  |  | 0 | 0 | MVS
443 | DARJEELING | Neorakhola W/S Mnt. Division | Setting up of District Project Management Unit (DPMU) for Darjeeling (Hills) District under Jal Jeevan Mission (JJM). | TSM/020473 | SM/18270 | Support | 10/03/2023 | 0 | 45.27 | Yes | 45.27 | 16/05/2023 | 27/07/2023 | 1 | 45.14 | MVS
444 | DARJEELING | Neorakhola W/S Mnt. Division | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co | TSM/022265 | SM/19010 | Support | 17/08/2023 | 0 | 699.39 | Yes | 699.39 |  | 10/07/2024 | 7 | 823.91 | MVS
445 | DARJEELING | Siliguri W/S Division | Operational Charges of Darjeeling District Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | TSM/023759 | SM/19317 | Support | 22/10/2024 | 0 | 31.29 | Yes | 31.29 |  | 06/05/2022 | 1 | 4.91 | MVS
446 | DARJEELING | Darjeeling Division | Setting up of water testing laboratory at Darjeeling: under Darjeeling Division: PHED:GTA | TSM/014976 |  | Support | 16/11/2022 | 0 | 74.62 | No | 0 |  |  | 0 | 0 | MVS
447 | DARJEELING | Neorakhola W/S Mnt. Division | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | TSM/010684 | SM/10732 | Support | 16/03/2022 | 0 | 910.35 | Yes | 910.35 |  | 30/06/2022 | 7 | 371.06 | MVS
448 | DARJEELING | Neorakhola W/S Mnt. Division | Collection of Drinking Water Samples from various spot sources, PWSS, Schools, Anganwadis, Health Centres and Springs under Darjeeling Hills for water testing at Sindhap sub-district laboratory Darjeeling managed by Neorakhola water supply and maintenance | TSM/013497 | SM/15668 | Support | 09/09/2022 | 0 | 13.71 | Yes | 13.71 |  | 03/03/2023 | 1 | 12.75 | MVS
449 | DARJEELING | Darjeeling Division | Setting up of water testing laboratory at Sukhiapokri under Darjeeling Division:PHED:GTA | TSM/014979 |  | Support | 16/11/2022 | 0 | 995.59 | No | 0 |  |  | 0 | 0 | MVS
450 | DARJEELING | Siliguri W/S Division | Regarding Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . | TSM/005377 | SM/06627 | Support | 05/11/2019 | 0 | 9.85 | Yes | 9.85 |  | 11/12/2024 | 4 | 13.16 | MVS
451 | DARJEELING | Siliguri W/S Division | ENGAGEMENT OF THIRD PARTY INSPECTION AGENCY (TPIA) FOR QUALITY AND QUANTITY MONITORING OF RURAL WATER SUPPLY SCHEMES UNDER JAL SWAPNA (JJM) PROJECT IN DARJEELING DISTRICT OF WEST BENGAL | TSM/015603 |  | Support | 09/09/2022 | 0 | 243.82 | No | 0 |  |  | 0 | 0 | MVS
452 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. | TSM/015406 | SM/17179 | Support | 09/09/2022 | 0 | 22.95 | Yes | 22.95 |  | 02/09/2024 | 6 | 12.55 | MVS
Total | [7 empty] | 361323 | 275498.31 |  | 260820.9 |  |  | 1719 | 232147.89