## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dhaldanga, Chak dhaldanga, | TSM/005982 | SM/07242 | Retrofitting | 25/09/2020 | 1138 | 79.81 | Yes | 79.81 |  | 31/12/2020 | 5 | 93.45 | MVS
2 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supp | TSM/005914 | SM/07365 | Retrofitting | 25/09/2020 | 757 | 65.48 | Yes | 65.48 |  | 18/01/2021 | 9 | 92.87 | MVS
3 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-A) | TSM/006020 | SM/07372 | Retrofitting | 25/09/2020 | 921 | 75.12 | Yes | 75.12 |  | 19/04/2022 | 2 | 72.5 | MVS
4 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Anchuri, Dhulkumari, Patha | TSM/005990 | SM/07249 | Retrofitting | 25/09/2020 | 920 | 85.75 | Yes | 85.75 |  | 19/02/2021 | 3 | 117.93 | MVS
5 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1)under S | TSM/005955 | SM/07765 | Retrofitting | 25/09/2020 | 17874 | 1524.36 | Yes | 1524.36 | 19/04/2023 | 03/05/2023 | 203 | 2009.85 | MVS
6 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | TSM/005926 | SM/07259 | Retrofitting | 25/09/2020 | 955 | 86.91 | Yes | 86.91 |  | 29/12/2020 | 2 | 93.29 | MVS
7 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bara Gajra (103), Asberya (104), Kaliahuta (105), Jadurbankata (106), Nischintapur (107), Kankata (127), Dharra Muli (128) & Bagaldhara (129) mouzas by retrofitting Zone-F (M | TSM/005906 | SM/07269 | Retrofitting | 25/09/2020 | 1043 | 89.36 | Yes | 89.36 |  | 27/07/2022 | 5 | 86.49 | MVS
8 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kundurka (43), Paira (44), Simlabandh (45), Bhedua (46) & Lutia (47) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at | TSM/005919 | SM/07337 | Retrofitting | 25/09/2020 | 721 | 56.54 | Yes | 56.54 |  | 18/01/2021 | 7 | 71.56 | MVS
9 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kendboni, Kantaboni, Mamur | TSM/005742 | SM/06815 | Retrofitting | 28/08/2020 | 1213 | 86.39 | Yes | 86.39 |  | 19/02/2021 | 12 | 230 | MVS
10 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 Nos. Mouzas (Malpara, Harokabedy, Mangalda, Palsora, Kalai, Amdiha, Parasi | TSM/005956 | SM/07324 | Retrofitting | 25/09/2020 | 1058 | 96.55 | Yes | 96.55 |  | 05/02/2021 | 3 | 72.22 | MVS
11 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh W | TSM/005896 | SM/07357 | Retrofitting | 25/09/2020 | 561 | 86.26 | Yes | 88.45 |  | 18/01/2021 | 6 | 56.45 | MVS
12 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | TSM/005897 | SM/07358 | Retrofitting | 25/09/2020 | 937 | 79.04 | Yes | 79.04 |  | 05/02/2021 | 3 | 42.87 | MVS
13 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas ( Baraleddya, Dhagoria, Ban | TSM/005969 | SM/07329 | Retrofitting | 25/09/2020 | 811 | 96.08 | Yes | 96.08 | 01/11/2022 | 03/01/2023 | 11 | 117.15 | MVS
14 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | TSM/007482 | SM/09315 | Retrofitting | 19/02/2021 | 3480 | 224.2 | Yes | 230.75 | 16/11/2022 | 11/11/2021 | 11 | 311.02 | MVS
15 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Birasimul-70, Shakrul-71, Suripuskarini-72 & D | TSM/007429 | SM/09318 | Retrofitting | 10/02/2021 | 1343 | 99.95 | Yes | 99.95 |  | 17/08/2022 | 10 | 146.06 | MVS
16 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | TSM/007466 | SM/09320 | Retrofitting | 19/02/2021 | 2035 | 146.29 | Yes | 146.29 |  | 17/12/2021 | 17 | 267.36 | MVS
17 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Layak Bandh - 13 & Chua Masina - 17) of | TSM/007468 | SM/09321 | Retrofitting | 19/02/2021 | 2202 | 210.06 | Yes | 210.06 |  | 31/12/2021 | 5 | 255.71 | MVS
18 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | TSM/007421 | SM/08293 | Retrofitting | 10/02/2021 | 886 | 73.3 | Yes | 73.3 |  | 11/11/2021 | 6 | 167.6 | MVS
19 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | TSM/007430 | SM/08299 | Retrofitting | 10/02/2021 | 1112 | 87.68 | Yes | 87.68 |  | 23/09/2021 | 5 | 100.9 | MVS
20 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | TSM/007405 | SM/09625 | Retrofitting | 10/02/2021 | 2610 | 184.53 | Yes | 184.53 |  | 01/02/2022 | 4 | 220.19 | MVS
21 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | TSM/007406 | SM/09626 | Retrofitting | 10/02/2021 | 2273 | 110.98 | Yes | 202.38 |  | 30/12/2021 | 31 | 279.96 | MVS
22 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gurighati (25), Penruabaid (26) & Parsola (28) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme ( | TSM/007282 | SM/09635 | Retrofitting | 10/02/2021 | 813 | 69.48 | Yes | 69.48 | 31/08/2023 | 23/09/2021 | 4 | 52.44 | MVS
23 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | TSM/008407 | SM/09499 | Retrofitting | 19/08/2021 | 2721 | 231.41 | Yes | 231.41 | 30/09/2021 | 31/12/2021 | 12 | 298.14 | MVS
24 | BANKURA | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | TSM/008409 | SM/09502 | Retrofitting | 19/08/2021 | 2274 | 198.36 | Yes | 198.36 | 19/04/2023 | 28/04/2023 | 17 | 199.72 | MVS
25 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by | TSM/008626 | SM/09530 | Retrofitting | 08/09/2021 | 3143 | 251.99 | Yes | 251.99 | 17/02/2023 | 03/03/2022 | 4 | 182.02 | MVS
26 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting | TSM/008629 | SM/09531 | Retrofitting | 08/09/2021 | 2017 | 170.99 | Yes | 170.99 |  | 22/02/2022 | 3 | 120.77 | MVS
27 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Handulia (1), Metyaldoba (2), Lakhyatapal (3), Budhadhara (4), Kharkhari (6), Kharjuria (7), Peripathar (8) & Ramgar (33) mouzas by retrofitting of Water Supply Scheme for Pa | TSM/008191 | SM/09476 | Retrofitting | 19/08/2021 | 569 | 56.84 | Yes | 56.84 |  | 15/06/2022 | 3 | 39.22 | MVS
28 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | TSM/008192 | SM/09477 | Retrofitting | 19/08/2021 | 2435 | 197.45 | Yes | 197.45 | 30/09/2021 | 30/12/2021 | 5 | 203.59 | MVS
29 | BANKURA | Bankura Division | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t | TSM/008038 | SM/09853 | Augmentation | 19/08/2021 | 7078 | 293.12 | Yes | 293.12 |  | 09/02/2022 | 3 | 237.73 | MVS
30 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-II) (Part-B) | TSM/006015 | SM/07369 | Retrofitting | 25/09/2020 | 994 | 94.58 | Yes | 94.58 | 10/08/2022 | 02/03/2022 | 8 | 17.17 | MVS
31 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012469 | SM/10987 | New | 20/05/2022 | 59 | 39.05 | Yes | 39.05 |  |  | 0 | 0 | MVS
32 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012470 | SM/10988 | New | 20/05/2022 | 69 | 41.37 | Yes | 41.37 |  | 13/02/2023 | 0 | 0.12 | MVS
33 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NUNIABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012471 | SM/10989 | New | 20/05/2022 | 82 | 41.69 | Yes | 41.69 |  | 15/03/2023 | 1 | 0.12 | MVS
34 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAMARADIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012135 | SM/10904 | New | 20/05/2022 | 0 | 43.06 | Yes | 43.06 |  | 06/05/2024 | 1 | 0.11 | MVS
35 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUDHIA DOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012335 | SM/11072 | New | 20/05/2022 | 65 | 40.44 | Yes | 40.44 | 24/12/2021 |  | 0 | 0 | MVS
36 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balaramp[ur, House Hold:49) | TSM/012254 | SM/11149 | New | 20/05/2022 | 591 | 39.69 | Yes | 39.69 |  | 31/01/2023 | 3 | 0.67 | MVS
37 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALAPATHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012276 | SM/11013 | New | 20/05/2022 | 95 | 44.23 | Yes | 44.23 | 18/02/2025 | 07/06/2023 | 1 | 0.12 | MVS
38 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHEJURBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012279 | SM/11016 | New | 20/05/2022 | 56 | 38.36 | Yes | 38.36 |  | 07/06/2023 | 1 | 0.12 | MVS
39 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MANHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012282 | SM/11019 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 |  | 07/06/2023 | 1 | 0.12 | MVS
40 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JARKA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012284 | SM/11021 | New | 20/05/2022 | 54 | 37.89 | Yes | 37.89 |  | 07/06/2023 | 1 | 0.12 | MVS
41 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARUNIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012293 | SM/11030 | New | 20/05/2022 | 42 | 35.71 | Yes | 35.71 | 18/02/2025 | 23/04/2024 | 1 | 0.23 | MVS
42 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PAINADA MODARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012355 | SM/11036 | New | 20/05/2022 | 35 | 34.45 | Yes | 34.45 | 18/02/2025 | 23/04/2024 | 1 | 0.12 | MVS
43 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RESIAGARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012356 | SM/11037 | New | 20/05/2022 | 26 | 32.03 | Yes | 32.03 | 24/12/2021 | 04/08/2023 | 2 | 0.23 | MVS
44 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAHARAGARYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012338 | SM/11075 | New | 20/05/2022 | 24 | 31.49 | Yes | 31.49 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
45 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARESNATH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012295 | SM/11032 | New | 20/05/2022 | 48 | 37.21 | Yes | 37.21 |  | 04/08/2023 | 1 | 0.11 | MVS
46 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MAHADEBSINAM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012296 | SM/11033 | New | 20/05/2022 | 45 | 36.46 | Yes | 36.46 |  | 04/08/2023 | 1 | 0.11 | MVS
47 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHENCHURYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012365 | SM/11046 | New | 20/05/2022 | 53 | 37.66 | Yes | 37.66 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
48 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PUNESA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012368 | SM/11049 | New | 20/05/2022 | 88 | 42.86 | Yes | 42.86 | 24/12/2021 | 16/06/2023 | 0 | 0.12 | MVS
49 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012143 | SM/10907 | New | 20/05/2022 | 57 | 38.59 | Yes | 38.59 |  | 02/06/2023 | 1 | 0.12 | MVS
50 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SURBHAGAB BAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012376 | SM/11057 | New | 20/05/2022 | 88 | 42.86 | Yes | 42.86 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
51 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHAKJAMBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012377 | SM/11058 | New | 20/05/2022 | 68 | 41.14 | Yes | 41.14 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
52 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BERUABAID VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012319 | SM/11131 | New | 20/05/2022 | 90 | 43.25 | Yes | 43.25 | 24/12/2021 |  | 0 | 0 | MVS
53 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Mohanchak, House Hold No.: 96) | TSM/012268 | SM/11135 | New | 20/05/2022 | 347 | 39.69 | Yes | 39.69 | 24/12/2021 |  | 0 | 0 | MVS
54 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KAMLABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012450 | SM/10893 | New | 20/05/2022 | 97 | 44.62 | Yes | 44.62 |  | 22/05/2024 | 1 | 0.12 | MVS
55 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Basuda, Rajprasadpur, Saldanga, Managram, Dewangrya, Numuigary | TSM/005989 | SM/07248 | Retrofitting | 25/09/2020 | 946 | 83.6 | Yes | 83.6 |  | 29/12/2020 | 9 | 127.04 | MVS
56 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JIRABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012073 | SM/10896 | New | 20/05/2022 | 29 | 32.83 | Yes | 32.83 |  | 06/05/2024 | 1 | 0.35 | MVS
57 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUPURDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012113 | SM/10899 | New | 20/05/2022 | 20 | 30.41 | Yes | 30.41 |  | 02/06/2023 | 1 | 0.12 | MVS
58 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RADHANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012462 | SM/10980 | New | 20/05/2022 | 77 | 40.72 | Yes | 40.72 |  | 22/05/2024 | 2 | 0.24 | MVS
59 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sri Rampur, House Hold:46) | TSM/012264 | SM/11139 | New | 20/05/2022 | 46 | 39.69 | Yes | 39.69 | 24/12/2021 | 02/02/2023 | 2 | 0.14 | MVS
60 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR LAKHYARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012399 | SM/10942 | New | 20/05/2022 | 175 | 42.86 | Yes | 42.86 |  | 12/03/2024 | 1 | 0.12 | MVS
61 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ramchandrapur, House Hold No.: 45) | TSM/012204 | SM/11191 | New | 20/05/2022 | 45 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 3 | 0.26 | MVS
62 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) (Part-A) | TSM/006012 | SM/07352 | Retrofitting | 25/09/2020 | 121 | 61.19 | Yes | 99.63 | 15/05/2023 | 10/02/2021 | 9 | 99.77 | MVS
63 | BANKURA | Bankura Division | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. | TSM/011121 | SM/12381 | Augmentation | 22/08/2022 | 607 | 206.2 | Yes | 206.2 | 08/01/2024 | 24/07/2023 | 3 | 273.66 | MVS
64 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHIBARAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012428 | SM/10871 | New | 20/05/2022 | 45 | 36.46 | Yes | 36.46 |  | 11/04/2023 | 1 | 0.12 | MVS
65 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANGRAM VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012429 | SM/10872 | New | 20/05/2022 | 35 | 34.45 | Yes | 34.45 |  | 15/03/2023 | 1 | 0.12 | MVS
66 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Brindabanpur, House Hold No.: 95) | TSM/012227 | SM/11180 | New | 20/05/2022 | 407 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
67 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RADHASHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012406 | SM/10849 | New | 20/05/2022 | 717 | 41.14 | Yes | 41.14 |  | 22/05/2024 | 2 | 403.08 | MVS
68 | BANKURA | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | TSM/008991 | SM/09926 | Augmentation | 22/11/2021 | 2525 | 532.09 | Yes | 532.09 | 21/06/2024 | 25/09/2024 | 12 | 516.3 | MVS
69 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TARKAJOR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012438 | SM/10881 | New | 20/05/2022 | 46 | 36.71 | Yes | 36.71 |  | 11/09/2023 | 0 | 0.12 | MVS
70 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHELEBAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012439 | SM/10882 | New | 20/05/2022 | 36 | 34.21 | Yes | 34.21 |  | 07/09/2023 | 1 | 0.12 | MVS
71 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Mahishabandi, House Hold No.: 93) | TSM/012221 | SM/11183 | New | 20/05/2022 | 399 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
72 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Tentulia, House Hold No.: 23) | TSM/012213 | SM/11187 | New | 20/05/2022 | 265 | 38.64 | Yes | 38.64 |  | 15/03/2023 | 1 | 0.12 | MVS
73 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Akharashal, House Hold No.: 35) | TSM/012206 | SM/11190 | New | 20/05/2022 | 259 | 38.64 | Yes | 38.64 |  |  | 0 | 0 | MVS
74 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Narayanpur, House Hold No.: 53) | TSM/012189 | SM/11672 | New | 20/05/2022 | 496 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 2 | 0.25 | MVS
75 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chakchuamasina, House Hold No.: 75) | TSM/012183 | SM/11675 | New | 20/05/2022 | 75 | 39.88 | Yes | 39.88 |  | 22/05/2024 | 1 | 0.13 | MVS
76 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Karajbani , House Hold:74 | TSM/012170 | SM/11452 | New | 20/05/2022 | 658 | 38.91 | Yes | 38.91 | 24/12/2021 | 26/06/2023 | 1 | 0.12 | MVS
77 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kulpat Bonkati, Gourangadi | TSM/005745 | SM/06810 | Retrofitting | 28/08/2020 | 1186 | 60.35 | Yes | 90.12 |  | 12/06/2023 | 14 | 185.54 | MVS
78 | BANKURA | Bankura Division | Telrui Piped Water Supply Scheme | TSM/015147 | SM/13711 | New | 09/09/2022 | 950 | 674.44 | Yes | 674.44 | 12/03/2025 | 27/11/2023 | 5 | 116.71 | MVS
79 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village name-Chakdhoyakure, household-36) | TSM/012124 | SM/11409 | New | 20/05/2022 | 36 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
80 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Amghata, Household-22) | TSM/012122 | SM/11410 | New | 20/05/2022 | 22 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
81 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name: Indkata, House Hold- 93) | TSM/012074 | SM/11427 | New | 20/05/2022 | 313 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
82 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Siltya(P), House Hold:22) | TSM/012244 | SM/11428 | New | 20/05/2022 | 345 | 38.91 | Yes | 38.91 |  | 12/03/2024 | 1 | 0.14 | MVS
83 | BANKURA | Bankura Division | Salkhara Piped Water Supply Scheme | TSM/015725 | SM/14003 | New | 26/09/2022 | 812 | 462.35 | Yes | 462.35 | 27/01/2023 | 01/08/2023 | 3 | 335.65 | MVS
84 | BANKURA | Bankura Division | Chandal Bandi Piped Water Supply Scheme | TSM/015424 | SM/13999 | New | 26/09/2022 | 1325 | 603.03 | Yes | 603.03 | 14/12/2022 | 26/07/2024 | 2 | 33.53 | MVS
85 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012128 | SM/13253 | New | 20/05/2022 | 60 | 39.29 | Yes | 39.29 |  |  | 0 | 0 | MVS
86 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PECHARAH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012160 | SM/13259 | New | 20/05/2022 | 517 | 40.88 | Yes | 40.88 |  | 16/05/2024 | 1 | 0.23 | MVS
87 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALYANSAER VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012197 | SM/13269 | New | 20/05/2022 | 29 | 35.71 | Yes | 35.71 |  | 07/06/2023 | 1 | 0.12 | MVS
88 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/B WATER SUPPLY SCHEME | TSM/016259 | SM/15002 | Augmentation | 26/09/2022 | 1004 | 447.46 | Yes | 447.46 | 18/01/2024 | 03/05/2023 | 7 | 226.53 | MVS
89 | BANKURA | Bankura Division | Mukundapur Piped Water Supply Scheme | TSM/015734 | SM/14006 | New | 26/09/2022 | 1297 | 696.82 | Yes | 696.82 | 31/01/2025 | 12/05/2023 | 3 | 47.84 | MVS
90 | BANKURA | Bankura Division | Nabasan Piped Water Supply Scheme | TSM/014758 | SM/13874 | New | 09/09/2022 | 1528 | 925.26 | Yes | 925.26 | 12/03/2025 | 06/01/2023 | 4 | 157.26 | MVS
91 | BANKURA | Bankura Division | Ranpur Piped Water Supply Scheme | TSM/014589 | SM/14519 | New | 22/08/2022 | 3789 | 1534.45 | Yes | 1534.45 | 12/03/2025 | 12/05/2023 | 4 | 141.92 | MVS
92 | BANKURA | Bankura Division | Danga Makarandapur Piped Water Supply Scheme | TSM/014201 | SM/14523 | New | 22/08/2022 | 2744 | 1199.48 | Yes | 1199.48 | 29/11/2024 | 24/07/2023 | 6 | 1009.06 | MVS
93 | BANKURA | Bankura Division | Khundanga Piped Water Supply Scheme | TSM/014843 | SM/14482 | New | 09/09/2022 | 1575 | 764.18 | Yes | 764.18 | 29/11/2024 | 14/08/2023 | 3 | 1327.7 | MVS
94 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | TSM/015535 | SM/14491 | Retrofitting | 30/09/2022 | 3768 | 483.88 | Yes | 483.88 | 30/11/2023 | 22/05/2023 | 4 | 309.79 | MVS
95 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | TSM/008656 | SM/09536 | Retrofitting | 08/09/2021 | 434 | 34.65 | Yes | 34.65 |  | 31/12/2021 | 4 | 36.27 | MVS
96 | BANKURA | Bankura Division | Kataban Piped Water Supply Scheme | TSM/014204 | SM/14526 | New | 22/08/2022 | 2234 | 1021.84 | Yes | 1021.84 | 12/03/2025 | 06/01/2023 | 5 | 114.33 | MVS
97 | BANKURA | Bankura Mechanical Division | Construction of Grid-connected Solar Photo-Voltaic system for IBS Uppargora pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | TSM/019282 | SM/15329 | Solarisation | 16/11/2022 | 0 | 366.53 | Yes | 366.53 | 10/02/2023 | 24/07/2024 | 2 | 88 | MVS
98 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mouzas (Bagapatal, Parasia bad, Ba | TSM/005744 | SM/06813 | Retrofitting | 28/08/2020 | 829 | 60.4 | Yes | 60.4 |  | 18/01/2021 | 21 | 231.69 | MVS
99 | BANKURA | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018966 | SM/16954 | Augmentation | 16/11/2022 | 900 | 127.61 | Yes | 127.61 | 07/06/2024 | 02/06/2023 | 7 | 73.15 | MVS
100 | BANKURA | Bankura Division | Kaktia Piped Water Supply Scheme. | TSM/018274 | SM/16701 | New | 28/12/2022 | 2145 | 964.45 | Yes | 964.45 | 05/02/2024 | 24/07/2023 | 3 | 777.81 | MVS
101 | BANKURA | Bankura Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018910 | SM/17236 | Augmentation | 16/11/2022 | 290 | 486.42 | Yes | 486.42 | 16/04/2025 | 13/07/2023 | 8 | 369.41 | MVS
102 | BANKURA | Bankura Division | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018957 | SM/17261 | Augmentation | 16/11/2022 | 710 | 436.89 | Yes | 439.33 | 22/02/2024 | 12/07/2024 | 6 | 317.1 | MVS
103 | BANKURA | Bankura Division | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | TSM/018961 | SM/17262 | Augmentation | 16/11/2022 | 260 | 347.29 | Yes | 348.2 | 13/07/2023 | 14/08/2023 | 4 | 256.81 | MVS
104 | BANKURA | Bankura Division | Augmentation of Sashpur Zone-A Water Supply Scheme | TSM/019166 | SM/18114 | Augmentation | 16/11/2022 | 340 | 360.95 | Yes | 361.86 | 21/06/2024 | 13/07/2023 | 5 | 294.87 | MVS
105 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | TSM/019235 | SM/17707 | Augmentation | 16/11/2022 | 320 | 675.82 | Yes | 675.82 | 09/04/2025 | 28/03/2023 | 7 | 326.14 | MVS
106 | BANKURA | Bankura Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019152 | SM/17730 | Augmentation | 16/11/2022 | 260 | 445.59 | Yes | 449.24 | 31/01/2025 | 24/08/2023 | 6 | 113.63 | MVS
107 | BANKURA | Bankura Division | Augmentation of Radhanagar Zone-II Water Supply Scheme | TSM/019169 | SM/17691 | Augmentation | 16/11/2022 | 165 | 219.61 | Yes | 219.61 | 05/02/2024 | 27/07/2023 | 6 | 202.68 | MVS
108 | BANKURA | Bankura Division | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018915 | SM/17695 | Augmentation | 16/11/2022 | 653 | 681.6 | Yes | 681.6 | 30/09/2024 | 14/08/2023 | 9 | 461.21 | MVS
109 | BANKURA | Bankura Division | Augmentation works for Lakshmanpur (Zone L) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018950 | SM/17313 | Augmentation | 16/11/2022 | 1025 | 330.23 | Yes | 347.79 | 30/09/2024 | 18/07/2023 | 5 | 166.49 | MVS
110 | BANKURA | Bankura Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019231 | SM/17283 | Augmentation | 16/11/2022 | 250 | 749.19 | Yes | 759.85 | 25/04/2025 | 17/06/2025 | 6 | 271.94 | MVS
111 | BANKURA | Bankura Division | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | TSM/019128 | SM/17301 | Augmentation | 16/11/2022 | 9820 | 995.79 | Yes | 995.79 | 01/03/2024 | 20/04/2023 | 6 | 917.27 | MVS
112 | BANKURA | Bankura Division | Bagdoba Piped Water Supply Scheme | TSM/014781 | SM/18305 | New | 09/09/2022 | 2315 | 1189.17 | Yes | 1189.17 | 29/11/2024 | 27/09/2024 | 4 | 221.37 | MVS
113 | BANKURA | Bankura Division | Augmentation of Karisunda Water Supply Scheme | TSM/019162 | SM/17419 | Augmentation | 16/11/2022 | 100 | 311.6 | Yes | 311.6 | 30/09/2024 | 24/07/2023 | 6 | 263.13 | MVS
114 | BANKURA | Bankura Division | Augmentation of Chakuparsole Zone-B Water Supply Scheme | TSM/019171 | SM/17426 | Augmentation | 16/11/2022 | 172 | 357.24 | Yes | 357.24 | 29/04/2025 | 14/08/2023 | 3 | 184.35 | MVS
115 | BANKURA | Bankura Division | Augmentation of Rol Zone-B Water Supply Scheme | TSM/019094 | SM/17683 | Augmentation | 16/11/2022 | 77 | 341.82 | Yes | 341.82 | 17/04/2023 | 19/07/2023 | 3 | 258.22 | MVS
116 | BANKURA | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019244 | SM/17429 | Augmentation | 16/11/2022 | 225 | 464.58 | Yes | 464.58 | 12/02/2025 | 28/09/2024 | 13 | 332.25 | MVS
117 | BANKURA | Bankura Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | TSM/019143 | SM/17281 | Augmentation | 16/11/2022 | 280 | 918.67 | Yes | 929.93 | 08/04/2025 | 25/04/2025 | 9 | 188.02 | MVS
118 | BANKURA | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | TSM/011428 | SM/18390 | Augmentation | 22/08/2022 | 6421 | 2538.24 | Yes | 2538.24 | 29/04/2025 | 04/04/2023 | 17 | 1812.63 | MVS
119 | BANKURA | Bankura Division | Chak Patrasaer Piped Water Supply Scheme | TSM/015946 | SM/18401 | New | 30/09/2022 | 3211 | 1280.02 | Yes | 1280.02 | 07/03/2025 | 26/04/2024 | 10 | 355.51 | MVS
120 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHATA-AM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012307 | SM/11119 | New | 20/05/2022 | 290 | 40.72 | Yes | 40.72 |  | 04/08/2023 | 1 | 0.11 | MVS
121 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Gaighata, House Hold No.: 84) | TSM/012216 | SM/11185 | New | 20/05/2022 | 84 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 2 | 0.24 | MVS
122 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NACHNA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012362 | SM/11043 | New | 20/05/2022 | 68 | 41.14 | Yes | 41.14 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
123 | BANKURA | Bankura Division | Basantapur Piped Water Supply Scheme | TSM/014203 | SM/12424 | New | 22/08/2022 | 2052 | 882.95 | Yes | 882.95 | 12/03/2025 | 06/01/2023 | 4 | 82.57 | MVS
124 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR ASAN CHUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012402 | SM/10945 | New | 20/05/2022 | 280 | 42.08 | Yes | 42.08 |  | 12/03/2024 | 1 | 0.12 | MVS
125 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KATAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012482 | SM/10950 | New | 20/05/2022 | 84 | 42.08 | Yes | 42.08 |  | 15/05/2023 | 1 | 0.12 | MVS
126 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BELARUMA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012474 | SM/10992 | New | 20/05/2022 | 97 | 44.62 | Yes | 44.62 |  | 22/05/2024 | 1 | 0.12 | MVS
127 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | TSM/008985 | SM/09553 | Retrofitting | 08/10/2021 | 3357 | 279 | Yes | 279 |  | 25/07/2022 | 5 | 169.92 | MVS
128 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PEDDAA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012375 | SM/11056 | New | 20/05/2022 | 95 | 44.23 | Yes | 44.23 | 24/12/2021 | 16/06/2023 | 0 | 0.12 | MVS
129 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KOLSULI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012345 | SM/11082 | New | 20/05/2022 | 45 | 36.46 | Yes | 36.46 | 24/12/2021 | 26/07/2023 | 0 | 0.12 | MVS
130 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012172 | SM/13262 | New | 20/05/2022 | 216 | 40.19 | Yes | 40.19 |  | 16/05/2024 | 1 | 0.23 | MVS
131 | BANKURA | Bankura Division | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | TSM/018929 | SM/16973 | Augmentation | 16/11/2022 | 590 | 416.22 | Yes | 417.13 | 19/06/2024 | 09/09/2024 | 7 | 151.35 | MVS
132 | BANKURA | Bankura Division | Water supply arrangement for 2459 Nos. Anganwadi Centers within the command area of PWSS providing solar power operated (not having electric power connection). | TSM/005347 |  | Anganwadi | 05/11/2019 | 0 | 3221.07 | No | 0 |  |  | 0 | 0 | MVS
133 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 02 Nos. Mouzas (Pinguri & Tentulpoha) of MALIARA (Zone - A) under Bankura - I, | TSM/006004 | SM/07308 | Retrofitting | 25/09/2020 | 999 | 85.15 | Yes | 85.15 |  | 05/02/2021 | 13 | 133.29 | MVS
134 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - I) of MALIARA (Zone - A) under Bankura - I, II | TSM/006003 | SM/07309 | Retrofitting | 25/09/2020 | 954 | 84.49 | Yes | 84.49 | 23/03/2023 | 23/09/2021 | 12 | 114.47 | MVS
135 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patpur (214), Maharadihi (215), Dharampur (216), Bara Gari (220), Data Rampur (221), Pitha Baid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Bara | TSM/005892 | SM/07265 | Retrofitting | 25/09/2020 | 874 | 75.82 | Yes | 75.82 |  | 27/07/2022 | 17 | 168 | MVS
136 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kasipur (230), Indkucha (231), Dhanara (234), Nekra Sonda (246), Sabudad (253), Dumuria (254), Dhargram (255), Sial Pahari (256) & Dhabani (257) mouzas by retrofitting Zone-H | TSM/005900 | SM/07361 | Retrofitting | 25/09/2020 | 1117 | 98.21 | Yes | 99.88 |  | 05/02/2021 | 6 | 80.37 | MVS
137 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | TSM/005912 | SM/07363 | Retrofitting | 25/09/2020 | 1178 | 97.27 | Yes | 97.85 |  | 19/04/2022 | 10 | 113.87 | MVS
138 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (6 | TSM/005913 | SM/07364 | Retrofitting | 25/09/2020 | 788 | 69.9 | Yes | 69.9 |  | 27/07/2022 | 10 | 87.58 | MVS
139 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) | TSM/006022 | SM/07374 | Retrofitting | 25/09/2020 | 1298 | 97.77 | Yes | 97.77 |  | 08/10/2021 | 0 | 9 | MVS
140 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurul Pahari (238), Sindurpeti (239), Baurisol (240), Tiring (244), Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas by retrofitting Z | TSM/005899 | SM/07360 | Retrofitting | 25/09/2020 | 1103 | 98.22 | Yes | 99.9 | 27/12/2022 | 05/02/2021 | 7 | 142.37 | MVS
141 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Shitla, Manjumara, Monoharbati & Pabaya) of Kanchanpur (Zone - | TSM/005925 | SM/07258 | Retrofitting | 25/09/2020 | 952 | 86.63 | Yes | 86.63 |  | 10/02/2021 | 11 | 120.37 | MVS
142 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | TSM/005908 | SM/07270 | Retrofitting | 25/09/2020 | 1265 | 100 | Yes | 100 |  | 10/02/2021 | 32 | 203.62 | MVS
143 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bamdhantur, Nabada, Sibara | TSM/005993 | SM/07316 | Retrofitting | 25/09/2020 | 931 | 99.71 | Yes | 99.71 |  | 07/06/2021 | 9 | 106.83 | MVS
144 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | TSM/005940 | SM/07319 | Retrofitting | 25/09/2020 | 992 | 77.62 | Yes | 77.62 |  | 19/01/2021 | 7 | 183.86 | MVS
145 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | TSM/005751 | SM/06797 | Retrofitting | 28/08/2020 | 343 | 77.86 | Yes | 77.86 |  | 09/12/2020 | 4 | 53.73 | MVS
146 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | TSM/005750 | SM/06798 | Retrofitting | 28/08/2020 | 336 | 91.53 | Yes | 91.53 | 04/03/2024 | 05/02/2021 | 8 | 156.26 | MVS
147 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pita Dungri (275) & Kuchiar Mahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | TSM/005893 | SM/07354 | Retrofitting | 25/09/2020 | 833 | 67.76 | Yes | 67.76 |  | 09/07/2021 | 5 | 159.59 | MVS
148 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | TSM/005747 | SM/06799 | Retrofitting | 28/08/2020 | 1532 | 91.99 | Yes | 91.99 |  | 09/10/2020 | 7 | 135.03 | MVS
149 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas ( Bhalukbasa, Hrtyasol, Kus | TSM/005967 | SM/07344 | Retrofitting | 25/09/2020 | 819 | 95.35 | Yes | 95.35 |  | 19/01/2021 | 2 | 73.23 | MVS
150 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Wa | TSM/005907 | SM/07331 | Retrofitting | 25/09/2020 | 1207 | 99.99 | Yes | 99.99 |  | 27/07/2022 | 31 | 126.98 | MVS
151 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur) of BARJORA Water Su | TSM/007457 | SM/09312 | Retrofitting | 19/02/2021 | 1949 | 200.5 | Yes | 206.86 | 08/01/2024 | 17/12/2021 | 26 | 245.71 | MVS
152 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Hariramp | TSM/007458 | SM/09313 | Retrofitting | 19/02/2021 | 938 | 205.01 | Yes | 262.33 |  | 01/02/2022 | 10 | 238.49 | MVS
153 | BANKURA | Bankura Division | Construction & commissioning d of FHTC by Retrofitting of completeand commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Kunjapur-112 & Bahalalpur-114) of Betanal | TSM/007422 | SM/09317 | Retrofitting | 10/02/2021 | 852 | 97.49 | Yes | 97.49 | 09/08/2023 | 26/11/2021 | 1 | 66.8 | MVS
154 | BANKURA | Bankura Division | & commissiConstruction oning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Dighalgram-126) of Betanal (Zone - B) under | TSM/007425 | SM/09322 | Retrofitting | 10/02/2021 | 751 | 98.43 | Yes | 98.43 |  | 16/11/2021 | 1 | 69.52 | MVS
155 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Shashpur-75, Narayanpur-82, Thakuranidighi | TSM/007471 | SM/09324 | Retrofitting | 19/02/2021 | 2264 | 187.99 | Yes | 187.99 |  | 03/03/2022 | 2 | 154.2 | MVS
156 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Ajodhya (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Sancha - 6,Patalpur -8, Loharara - 9, Ajodhya -10 | TSM/007473 | SM/09326 | Retrofitting | 19/02/2021 | 3096 | 291.93 | Yes | 291.93 |  | 12/05/2022 | 1 | 240.2 | MVS
157 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishn | TSM/007474 | SM/09327 | Retrofitting | 19/02/2021 | 2355 | 230.52 | Yes | 254.63 |  | 11/11/2021 | 18 | 314.52 | MVS
158 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | TSM/007313 | SM/09233 | Retrofitting | 10/02/2021 | 1000 | 99.93 | Yes | 99.93 | 27/12/2022 | 23/09/2021 | 10 | 157.51 | MVS
159 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | TSM/007319 | SM/09236 | Retrofitting | 10/02/2021 | 2199 | 236.67 | Yes | 271.55 | 30/09/2021 | 27/06/2022 | 7 | 382.93 | MVS
160 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Abantika- 88 , Belthya- 89 & Deuli- 91) of BENDA u | TSM/007416 | SM/09240 | Retrofitting | 10/02/2021 | 733 | 73.17 | Yes | 73.17 |  | 11/11/2021 | 7 | 216.52 | MVS
161 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Jamrepara (295), Debgram (296), Agaya (350), Ampata (351) & Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjo | TSM/007290 | SM/09642 | Retrofitting | 10/02/2021 | 1030 | 61.34 | Yes | 84.2 |  | 12/07/2022 | 12 | 62.84 | MVS
162 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gamidya (192), Amla Tara (196), Angaria (197), Madan Mohanpur (198), Kheruashol (199), Betajora (200), Bhaluk Khulya (201), Brindabanpur (202), Shirsha (203), Siara (204), Ku | TSM/008621 | SM/09528 | Retrofitting | 08/09/2021 | 1663 | 148.3 | Yes | 148.3 |  | 22/02/2022 | 3 | 104.4 | MVS
163 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | TSM/008976 | SM/09550 | Retrofitting | 08/10/2021 | 2280 | 234.05 | Yes | 234.05 |  | 13/04/2022 | 13 | 252.49 | MVS
164 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur | TSM/008624 | SM/09529 | Retrofitting | 08/09/2021 | 2872 | 227.27 | Yes | 228.15 | 16/12/2022 | 21/04/2022 | 7 | 180.33 | MVS
165 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (2 | TSM/008588 | SM/09522 | Retrofitting | 08/09/2021 | 1047 | 101.77 | Yes | 101.77 |  | 18/02/2022 | 3 | 77.6 | MVS
166 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | TSM/008343 | SM/09852 | Augmentation | 19/08/2021 | 0 | 580.47 | Yes | 580.47 | 10/01/2025 | 14/08/2023 | 15 | 401.34 | MVS
167 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Narasole, Radhaballavpur, Gopinathdihi, Taljhoria, Namabad, K | TSM/005973 | SM/07239 | Retrofitting | 25/09/2020 | 924 | 96.29 | Yes | 96.29 |  | 10/02/2021 | 18 | 398.46 | MVS
168 | BANKURA | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | TSM/008344 | SM/10296 | Augmentation | 19/08/2021 | 0 | 2502.19 | Yes | 2502.19 | 12/02/2025 | 03/07/2024 | 11 | 2409.68 | MVS
169 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR ASNASUNDARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012337 | SM/11074 | New | 20/05/2022 | 41 | 35.46 | Yes | 35.46 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
170 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAERBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012173 | SM/10920 | New | 20/05/2022 | 70 | 41.6 | Yes | 41.6 |  |  | 0 | 0 | MVS
171 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012301 | SM/11113 | New | 20/05/2022 | 84 | 42.08 | Yes | 42.08 |  | 04/08/2023 | 1 | 0.11 | MVS
172 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GOALMURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012306 | SM/11118 | New | 20/05/2022 | 56 | 38.36 | Yes | 38.36 |  | 04/08/2023 | 1 | 0.11 | MVS
173 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012310 | SM/11122 | New | 20/05/2022 | 198 | 36.96 | Yes | 36.96 |  | 07/09/2023 | 1 | 0.12 | MVS
174 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJPURA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012311 | SM/11123 | New | 20/05/2022 | 404 | 33.64 | Yes | 33.64 |  | 19/09/2023 | 1 | 0.12 | MVS
175 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHATURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012273 | SM/11010 | New | 20/05/2022 | 93 | 43.84 | Yes | 43.84 |  | 07/06/2023 | 2 | 0.24 | MVS
176 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KARAMARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012277 | SM/11014 | New | 20/05/2022 | 60 | 39.29 | Yes | 39.29 | 18/02/2025 | 07/06/2023 | 1 | 0.12 | MVS
177 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUKNI BASA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012291 | SM/11028 | New | 20/05/2022 | 48 | 37.21 | Yes | 37.21 |  |  | 0 | 0 | MVS
178 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SAHARGHATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012342 | SM/11079 | New | 20/05/2022 | 38 | 34.71 | Yes | 34.71 | 18/02/2025 | 15/06/2023 | 0 | 0.12 | MVS
179 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JEMUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012344 | SM/11081 | New | 20/05/2022 | 31 | 33.37 | Yes | 33.37 | 18/02/2025 | 23/04/2024 | 1 | 0.12 | MVS
180 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANKATI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012487 | SM/10955 | New | 20/05/2022 | 78 | 40.91 | Yes | 40.91 |  | 15/05/2023 | 1 | 0.12 | MVS
181 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NABASHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012494 | SM/10962 | New | 20/05/2022 | 49 | 37.46 | Yes | 37.46 |  |  | 0 | 0 | MVS
182 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MACHLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012367 | SM/11048 | New | 20/05/2022 | 95 | 44.23 | Yes | 44.23 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
183 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MARASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012370 | SM/11051 | New | 20/05/2022 | 64 | 40.21 | Yes | 40.21 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
184 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHARAKANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012445 | SM/10888 | New | 20/05/2022 | 51 | 37.2 | Yes | 37.2 |  |  | 0 | 0 | MVS
185 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NISCHINTAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012454 | SM/10972 | New | 20/05/2022 | 90 | 43.25 | Yes | 43.25 |  | 07/09/2023 | 2 | 0.24 | MVS
186 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NAMADUDHIA DOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012326 | SM/11063 | New | 20/05/2022 | 157 | 31.49 | Yes | 31.49 | 18/02/2025 | 13/09/2024 | 1 | 0.37 | MVS
187 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KORKHI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012327 | SM/11064 | New | 20/05/2022 | 52 | 37.43 | Yes | 37.43 | 24/12/2021 |  | 0 | 0 | MVS
188 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHADULDOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012328 | SM/11065 | New | 20/05/2022 | 53 | 37.66 | Yes | 37.66 | 24/12/2021 | 22/05/2024 | 2 | 0.24 | MVS
189 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHANDIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012391 | SM/10934 | New | 20/05/2022 | 97 | 34.46 | Yes | 34.46 |  | 15/03/2023 | 1 | 0.12 | MVS
190 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Shyampur, House Hold:42) | TSM/012265 | SM/11138 | New | 20/05/2022 | 42 | 39.69 | Yes | 39.69 | 24/12/2021 | 02/02/2023 | 2 | 0.14 | MVS
191 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Adwaitabati, House Hold No.: 50) | TSM/012087 | SM/11099 | New | 20/05/2022 | 50 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
192 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | TSM/011376 | SM/11823 | Retrofitting | 25/04/2022 | 8274 | 512.6 | Yes | 513.85 | 24/02/2025 | 24/07/2023 | 1 | 356.78 | MVS
193 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TUNAMARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012418 | SM/10861 | New | 20/05/2022 | 39 | 33.77 | Yes | 34.96 | 24/12/2021 | 04/04/2024 | 1 | 0.12 | MVS
194 | BANKURA | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | TSM/008990 | SM/09927 | Augmentation | 22/11/2021 | 1224 | 308.91 | Yes | 308.91 | 21/06/2024 | 12/05/2022 | 9 | 277.93 | MVS
195 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Parbatipur, House Hold No.: 50) | TSM/012215 | SM/11186 | New | 20/05/2022 | 50 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 2 | 0.14 | MVS
196 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chaknayan, House Hold No.: 29) | TSM/012209 | SM/11189 | New | 20/05/2022 | 29 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 2 | 0.14 | MVS
197 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Brindabanpur, House Hold:60 | TSM/012193 | SM/11445 | New | 20/05/2022 | 183 | 38.91 | Yes | 38.91 |  | 12/03/2024 | 1 | 0.44 | MVS
198 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Bhetia, House Hold:78 | TSM/012181 | SM/11449 | New | 20/05/2022 | 78 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
199 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAMBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012348 | SM/11200 | New | 20/05/2022 | 78 | 40.91 | Yes | 40.91 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
200 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Ramnagar, House Hold No.: 88) | TSM/012192 | SM/11671 | New | 20/05/2022 | 383 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
201 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Pirragara, House Hold No.: 75) | TSM/012188 | SM/11673 | New | 20/05/2022 | 76 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
202 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Thakurhati , House Hold: 74 | TSM/012175 | SM/11451 | New | 20/05/2022 | 74 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
203 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Hurhrjangar, House Hold:45) | TSM/012238 | SM/11431 | New | 20/05/2022 | 45 | 38.91 | Yes | 38.91 |  | 04/08/2023 | 1 | 0.12 | MVS
204 | BANKURA | Bankura Division | Rani Bandh Piped Water Supply Scheme | TSM/014587 | SM/12415 | New | 22/08/2022 | 1199 | 923.31 | Yes | 924.1 | 25/04/2025 | 24/07/2023 | 5 | 905.47 | MVS
205 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Radhakrishnapur, House Hold:22) | TSM/012235 | SM/11432 | New | 20/05/2022 | 271 | 38.91 | Yes | 38.91 |  |  | 0 | 0 | MVS
206 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Borajpota, House Hold No.: 33) | TSM/012167 | SM/11681 | New | 20/05/2022 | 33 | 39.88 | Yes | 39.88 |  | 22/05/2024 | 2 | 0.23 | MVS
207 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Parashe, House Hold No.: 90) | TSM/012136 | SM/11689 | New | 20/05/2022 | 90 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
208 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rupuisar, Household-85) | TSM/012120 | SM/11411 | New | 20/05/2022 | 85 | 39.11 | Yes | 39.11 |  | 12/03/2024 | 1 | 0.14 | MVS
209 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Salda, Household-77) | TSM/012119 | SM/11412 | New | 20/05/2022 | 77 | 39.11 | Yes | 39.11 |  | 06/05/2024 | 2 | 0.24 | MVS
210 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TOL CHANDRAKONA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012166 | SM/13261 | New | 20/05/2022 | 136 | 40.42 | Yes | 40.42 |  |  | 0 | 0 | MVS
211 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHATANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012199 | SM/13270 | New | 20/05/2022 | 43 | 32.83 | Yes | 32.83 |  |  | 0 | 0 | MVS
212 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | TSM/016303 | SM/15005 | Augmentation | 26/09/2022 | 2578 | 648.32 | Yes | 648.32 | 29/04/2025 | 13/08/2024 | 7 | 420.71 | MVS
213 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | TSM/016332 | SM/15009 | Augmentation | 26/09/2022 | 1428 | 450.15 | Yes | 450.15 | 16/01/2025 | 25/04/2025 | 10 | 282.65 | MVS
214 | BANKURA | Bankura Division | Jibta Piped Water Supply Scheme | TSM/015757 | SM/15018 | New | 26/09/2022 | 896 | 670.46 | Yes | 670.46 | 09/12/2022 | 26/07/2024 | 4 | 83.27 | MVS
215 | BANKURA | Bankura Division | Ramnagar Piped Water Supply Scheme | TSM/015728 | SM/14005 | New | 26/09/2022 | 2116 | 991.65 | Yes | 991.65 | 31/01/2025 | 18/07/2023 | 4 | 671.69 | MVS
216 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Pump House I of Moynapur PWS scheme Dist Bankura | TSM/018680 | SM/15328 | Solarisation | 16/11/2022 | 0 | 14.34 | Yes | 14.34 | 29/12/2022 | 23/03/2023 | 1 | 9.86 | MVS
217 | BANKURA | Bankura Mechanical Division | Implementation of affordable IoT-Enabled water service delivery measurement and monitoring sensing system for rural deployment in the proposed villages under Panchal water supply scheme in Sonamukhi Block under Bankura District. | TSM/020256 | SM/15333 | IOT | 16/11/2022 | 0 | 36.48 | Yes | 36.48 | 30/07/2024 |  | 0 | 0 | MVS
218 | BANKURA | Bankura Division | Chakai Piped Water Supply Scheme | TSM/015173 | SM/14245 | New | 09/09/2022 | 2771 | 1142.89 | Yes | 1142.89 | 25/04/2025 | 28/11/2024 | 7 | 191.66 | MVS
219 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VI WATER SUPPLY SCHEME | TSM/016333 | SM/16260 | Augmentation | 26/09/2022 | 1381 | 383.62 | Yes | 383.62 | 24/01/2025 | 30/04/2025 | 8 | 260.32 | MVS
220 | BANKURA | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018921 | SM/16968 | Augmentation | 16/11/2022 | 431 | 447.32 | Yes | 447.32 | 12/03/2025 | 15/07/2024 | 9 | 344.72 | MVS
221 | BANKURA | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | TSM/019123 | SM/16953 | Augmentation | 16/11/2022 | 770 | 183.46 | Yes | 183.46 | 08/01/2024 | 22/05/2023 | 11 | 170.08 | MVS
222 | BANKURA | Bankura Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018906 | SM/16955 | Augmentation | 16/11/2022 | 820 | 474.22 | Yes | 478.49 | 03/03/2025 | 27/07/2023 | 6 | 351.02 | MVS
223 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | TSM/007463 | SM/09319 | Retrofitting | 19/02/2021 | 2881 | 253.39 | Yes | 254.76 | 16/11/2022 | 31/12/2021 | 9 | 176.32 | MVS
224 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Nangalbhanga-18, Chwak Chuamosina-19, B | TSM/007419 | SM/09308 | Retrofitting | 10/02/2021 | 807 | 67.34 | Yes | 67.34 |  |  | 0 | 0 | MVS
225 | BANKURA | Bankura Division | Karajbani Piped Water Supply Scheme | TSM/018423 | SM/16702 | New | 28/12/2022 | 1086 | 505.78 | Yes | 505.78 | 05/02/2024 | 12/05/2023 | 2 | 74.52 | MVS
226 | BANKURA | Bankura Division | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019159 | SM/16984 | Augmentation | 16/11/2022 | 470 | 497.75 | Yes | 500.19 | 09/04/2025 | 13/07/2023 | 8 | 350.15 | MVS
227 | BANKURA | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019241 | SM/17251 | Augmentation | 16/11/2022 | 230 | 455.28 | Yes | 455.28 | 31/01/2025 | 28/09/2024 | 9 | 200.7 | MVS
228 | BANKURA | Bankura Division | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018951 | SM/17253 | Augmentation | 16/11/2022 | 780 | 439.51 | Yes | 441.03 | 12/03/2024 | 12/07/2024 | 5 | 121.79 | MVS
229 | BANKURA | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | TSM/018956 | SM/17259 | Augmentation | 16/11/2022 | 4059 | 999.07 | Yes | 999.07 | 16/04/2025 | 24/07/2023 | 6 | 812.34 | MVS
230 | BANKURA | Bankura Division | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019215 | SM/17260 | Augmentation | 16/11/2022 | 120 | 434.18 | Yes | 436.62 | 09/04/2025 | 07/05/2025 | 5 | 121.93 | MVS
231 | BANKURA | Bankura Division | Augmentation of Akui Zone-A Water Supply Scheme | TSM/018973 | SM/16943 | Augmentation | 16/11/2022 | 250 | 228.16 | Yes | 228.16 | 17/04/2023 | 18/07/2023 | 4 | 145.01 | MVS
232 | BANKURA | Bankura Division | Augmentation of Prakash Zone-B Water Supply Scheme | TSM/019177 | SM/16945 | Augmentation | 16/11/2022 | 210 | 188.68 | Yes | 188.68 | 19/01/2024 | 28/06/2023 | 2 | 38.12 | MVS
233 | BANKURA | Bankura Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018938 | SM/17702 | Augmentation | 16/11/2022 | 603 | 691.23 | Yes | 709.58 | 19/01/2024 | 21/09/2023 | 13 | 478.15 | MVS
234 | BANKURA | Bankura Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | TSM/017979 | SM/18039 | New | 28/12/2022 | 1400 | 624.98 | Yes | 624.98 | 07/11/2023 | 14/08/2023 | 6 | 351.66 | MVS
235 | BANKURA | Bankura Division | Mahaldanga Piped Water Supply Scheme | TSM/014764 | SM/18318 | New | 09/09/2022 | 2847 | 1541.49 | Yes | 1541.49 | 29/11/2024 | 14/08/2023 | 5 | 1205.27 | MVS
236 | BANKURA | Bankura Division | Augmentation of Chuamasina Zone-A Water Supply Scheme | TSM/019173 | SM/17696 | Augmentation | 16/11/2022 | 410 | 390.83 | Yes | 390.83 | 19/06/2024 | 24/07/2023 | 7 | 368.16 | MVS
237 | BANKURA | Bankura Division | Proposed sub surface water based Parashibana pipe water supply scheme under Bankura Division, Block Chhatna, District: Bankura. | TSM/018449 | SM/18043 | New | 28/12/2022 | 1508 | 672.83 | Yes | 672.83 | 07/06/2024 | 18/04/2024 | 12 | 524.98 | MVS
238 | BANKURA | Bankura Division | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | TSM/019129 | SM/17303 | Augmentation | 16/11/2022 | 480 | 282.33 | Yes | 285.68 | 17/07/2023 | 08/02/2024 | 4 | 53.14 | MVS
239 | BANKURA | Bankura Division | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | TSM/019122 | SM/17291 | Augmentation | 16/11/2022 | 340 | 244.22 | Yes | 244.22 | 19/06/2024 | 18/04/2023 | 6 | 157.21 | MVS
240 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019153 | SM/17292 | Augmentation | 16/11/2022 | 210 | 745.16 | Yes | 752.47 | 09/04/2025 | 18/06/2024 | 9 | 314.68 | MVS
241 | BANKURA | Bankura Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | TSM/019140 | SM/17725 | Augmentation | 16/11/2022 | 300 | 592.88 | Yes | 592.88 | 29/04/2025 | 17/06/2025 | 8 | 299.26 | MVS
242 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | TSM/019146 | SM/17682 | Augmentation | 16/11/2022 | 190 | 309.8 | Yes | 309.8 | 19/06/2024 | 21/09/2023 | 5 | 145.78 | MVS
243 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Purunia, sangrampur, Laxminarayanpur, Baharkhulia & Gangadarpu | TSM/005923 | SM/07256 | Retrofitting | 25/09/2020 | 700 | 98.92 | Yes | 98.92 |  | 19/02/2021 | 9 | 107.44 | MVS
244 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019151 | SM/17295 | Augmentation | 16/11/2022 | 325 | 783.18 | Yes | 790.33 | 16/01/2025 | 27/07/2023 | 5 | 305.32 | MVS
245 | BANKURA | Bankura Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019227 | SM/17714 | Augmentation | 16/11/2022 | 310 | 858.94 | Yes | 863.2 | 29/04/2025 | 17/06/2025 | 7 | 390.41 | MVS
246 | BANKURA | Bankura Division | Khiri Piped Water Supply Scheme | TSM/014798 | SM/18436 | New | 09/09/2022 | 1645 | 1118.52 | Yes | 1118.52 | 12/03/2025 | 06/01/2023 | 4 | 135.46 | MVS
247 | BANKURA | Bankura Division | Laugram Piped Water Supply Scheme | TSM/014861 | SM/18438 | New | 09/09/2022 | 2764 | 1392.19 | Yes | 1392.19 | 12/03/2025 | 27/09/2024 | 4 | 194.89 | MVS
248 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANPUKHURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012292 | SM/11029 | New | 20/05/2022 | 35 | 34.45 | Yes | 34.45 |  | 23/04/2024 | 1 | 0.23 | MVS
249 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANAGRAM VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012161 | SM/10915 | New | 20/05/2022 | 69 | 41.37 | Yes | 41.37 |  | 05/06/2023 | 2 | 0.14 | MVS
250 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | TSM/007464 | SM/09629 | Retrofitting | 19/02/2021 | 1984 | 159.63 | Yes | 159.63 |  | 15/06/2022 | 9 | 130.68 | MVS
251 | BANKURA | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | TSM/018937 | SM/18423 | Augmentation | 16/11/2022 | 3575 | 1215.26 | Yes | 1215.26 | 16/04/2025 | 18/06/2024 | 13 | 945.95 | MVS
252 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dashere, House Hold No.: 75) | TSM/012092 | SM/11096 | New | 20/05/2022 | 75 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
253 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chanpatala, House Hold No.: 63) | TSM/012229 | SM/11179 | New | 20/05/2022 | 63 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
254 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SABUDAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012486 | SM/10954 | New | 20/05/2022 | 88 | 42.86 | Yes | 42.86 |  | 29/04/2024 | 1 | 0.12 | MVS
255 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHINKENDBANA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012430 | SM/10873 | New | 20/05/2022 | 21 | 30.68 | Yes | 30.68 |  | 15/03/2023 | 1 | 0.12 | MVS
256 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Maheshpur , House Hold No.: 84) | TSM/012162 | SM/11682 | New | 20/05/2022 | 867 | 39.88 | Yes | 39.88 |  | 07/09/2023 | 1 | 0.12 | MVS
257 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 nos. Mouzas (Pakhnna, Kamalpur, Tajpur, Pakhanna Bharabpur, Gopalpur, Radhakantapur, Pakhanna Pratap pur, P | TSM/007475 | SM/09328 | Retrofitting | 19/02/2021 | 1891 | 199.8 | Yes | 236.78 | 03/02/2023 | 28/07/2022 | 27 | 330.36 | MVS
258 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR INDARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012498 | SM/10966 | New | 20/05/2022 | 54 | 37.89 | Yes | 37.89 |  |  | 0 | 0 | MVS
259 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | TSM/005924 | SM/07257 | Retrofitting | 25/09/2020 | 931 | 94.9 | Yes | 94.9 |  | 29/12/2020 | 17 | 154.33 | MVS
260 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | TSM/005961 | SM/07251 | Retrofitting | 25/09/2020 | 958 | 99.13 | Yes | 99.13 |  | 05/10/2021 | 8 | 102.77 | MVS
261 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Guniada (1), Chalka (2), Chatanibaid (3), Bangopalpur (4) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph | TSM/005902 | SM/07266 | Retrofitting | 25/09/2020 | 845 | 71.22 | Yes | 71.22 |  | 18/01/2021 | 2 | 28.41 | MVS
262 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | TSM/005748 | SM/06801 | Retrofitting | 28/08/2020 | 580 | 48.55 | Yes | 48.55 |  | 10/02/2021 | 3 | 80.84 | MVS
263 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mouzas (Bhangaria, Magra and Sonad | TSM/005743 | SM/06812 | Retrofitting | 28/08/2020 | 831 | 60.55 | Yes | 60.55 |  | 05/02/2021 | 12 | 181.25 | MVS
264 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dulaparar (231), Asarda (232), Chandpara (233), Luapara (269), Kemduadangri (273), Benasuli (275), Phulberia (278), Danara (279) mouzas by retrofitting of Piped Water Supply | TSM/005749 | SM/06791 | Retrofitting | 28/08/2020 | 580 | 72.78 | Yes | 85.04 |  | 09/10/2020 | 7 | 155.12 | MVS
265 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sinyajora (32), Bhelaidiha (36), Korkhi (37) , Shyampur (44), Jugidangra (47), Rasikpur (48) and Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for L | TSM/005756 | SM/06793 | Retrofitting | 28/08/2020 | 675 | 63.21 | Yes | 67.66 |  | 09/12/2020 | 13 | 360.26 | MVS
266 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gotkanali (45), Bankhola (54), Jarisa (89) & Harinyaguri (90) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | TSM/005757 | SM/06794 | Retrofitting | 28/08/2020 | 1100 | 86.48 | Yes | 86.48 |  | 09/10/2020 | 5 | 122.49 | MVS
267 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | TSM/005735 | SM/06807 | Retrofitting | 28/08/2020 | 1008 | 99.9 | Yes | 99.9 | 08/01/2024 | 08/10/2020 | 9 | 194.84 | MVS
268 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | TSM/005898 | SM/07359 | Retrofitting | 25/09/2020 | 1147 | 98.59 | Yes | 99.99 |  | 09/07/2021 | 6 | 82.8 | MVS
269 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Ramchandrapur, Paschim Brindabanpur, Palsana & Saluka) of Jo | TSM/005965 | SM/07328 | Retrofitting | 25/09/2020 | 923 | 95.32 | Yes | 95.32 |  | 17/06/2021 | 15 | 181.32 | MVS
270 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Paharapatpur (117), Bhaluka (120), Kadra (121), Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Raniban | TSM/005909 | SM/07332 | Retrofitting | 25/09/2020 | 957 | 85.79 | Yes | 86.55 | 01/11/2022 | 18/01/2021 | 6 | 89 | MVS
271 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Srikara-31, Padua-11, Adpara Kumrul-12, Srip | TSM/007470 | SM/09323 | Retrofitting | 19/02/2021 | 2465 | 206.18 | Yes | 206.18 |  | 15/12/2021 | 5 | 253.48 | MVS
272 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Khuliamuri-126, Harabati-127, Dhengasole-128, | TSM/007414 | SM/09238 | Retrofitting | 10/02/2021 | 495 | 80.74 | Yes | 80.74 | 27/12/2022 | 01/12/2021 | 2 | 103.76 | MVS
273 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | TSM/007417 | SM/08290 | Retrofitting | 10/02/2021 | 692 | 73.31 | Yes | 78.52 |  | 23/09/2021 | 16 | 122.53 | MVS
274 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Tentulara-20, Saluka-21, Dharampur-22, | TSM/007418 | SM/08291 | Retrofitting | 10/02/2021 | 867 | 78.23 | Yes | 78.23 |  | 23/09/2021 | 6 | 120.75 | MVS
275 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54 | TSM/007415 | SM/09239 | Retrofitting | 10/02/2021 | 735 | 76.06 | Yes | 76.06 |  | 26/10/2021 | 2 | 70.26 | MVS
276 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368), Deuli (369) & Majura (372) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF | TSM/007300 | SM/09230 | Retrofitting | 10/02/2021 | 1179 | 89 | Yes | 89 |  | 06/06/2022 | 16 | 406.18 | MVS
277 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | TSM/007407 | SM/09627 | Retrofitting | 10/02/2021 | 3761 | 280.67 | Yes | 280.67 |  | 22/08/2022 | 5 | 266.37 | MVS
278 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | TSM/008193 | SM/09496 | Retrofitting | 19/08/2021 | 0 | 234.6 | Yes | 234.6 | 30/09/2021 | 17/12/2021 | 7 | 321.26 | MVS
279 | BANKURA | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | TSM/008411 | SM/09504 | Retrofitting | 19/08/2021 | 977 | 80.23 | Yes | 80.23 |  | 01/12/2021 | 6 | 182.84 | MVS
280 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas by retrofitting Ratanpur and adjo | TSM/008634 | SM/09532 | Retrofitting | 08/09/2021 | 2080 | 177.6 | Yes | 177.6 | 13/01/2022 | 21/04/2022 | 5 | 113.75 | MVS
281 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | TSM/007402 | SM/09621 | Retrofitting | 10/02/2021 | 2822 | 211.82 | Yes | 211.82 |  | 15/12/2021 | 6 | 506.35 | MVS
282 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Jhiknara-119 & Kharsi-121, Narra-120, Ratra-1 | TSM/007403 | SM/09622 | Retrofitting | 10/02/2021 | 2522 | 193.98 | Yes | 193.98 |  | 15/12/2021 | 1 | 175.44 | MVS
283 | BANKURA | Bankura Division | New pipe line with Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas | TSM/007460 | SM/09632 | Retrofitting | 19/02/2021 | 1796 | 291.82 | Yes | 294.2 | 08/01/2024 | 12/04/2022 | 12 | 133.68 | MVS
284 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | TSM/008190 | SM/09475 | Retrofitting | 19/08/2021 | 0 | 57.03 | Yes | 57.03 | 27/12/2022 | 28/02/2022 | 4 | 43.37 | MVS
285 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | TSM/007288 | SM/09641 | Retrofitting | 10/02/2021 | 2304 | 237.71 | Yes | 237.71 |  | 14/12/2021 | 3 | 39.69 | MVS
286 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jaba Balarampur (68), Bagjata (78), Debagram (79), Baidyanathpur (80), Mankhamar (81), Bhatgram (82), Banamalipur (83), Mukundabati (84), Lodna (89) & Madanpur (90) mouzas by | TSM/008576 | SM/09481 | Retrofitting | 08/09/2021 | 2000 | 164.78 | Yes | 164.78 | 16/02/2023 | 11/04/2023 | 4 | 131.97 | MVS
287 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | TSM/005972 | SM/09305 | Retrofitting | 25/09/2020 | 917 | 95.96 | Yes | 95.96 | 19/04/2023 | 28/04/2023 | 14 | 73.76 | MVS
288 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rautara (41), Kawabasa (42), Panbaraj (43), Kiabati (44), Bhulanpur (45), Palash Bani (46), Gengari (47), Pratappur (48), Gopalpur (49), Dhabani (50), Metyala (51), Jamjuri ( | TSM/008582 | SM/09520 | Retrofitting | 08/09/2021 | 3005 | 266.81 | Yes | 266.81 | 01/11/2022 | 09/12/2022 | 4 | 230.58 | MVS
289 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | TSM/006009 | SM/07330 | Retrofitting | 25/09/2020 | 241 | 45.01 | Yes | 67.6 | 21/06/2024 | 25/06/2021 | 9 | 78.61 | MVS
290 | BANKURA | Bankura Mechanical Division | Construction of Grid- connection solar photo-voltaic system for Kanaipur pumping station of Panchal PWS scheme,Dist: Bankura. | TSM/009607 | SM/10271 | IOT | 16/12/2021 | 0 | 16.95 | Yes | 16.95 |  | 28/04/2022 | 1 | 16.5 | MVS
291 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | TSM/008339 | SM/10293 | Augmentation | 19/08/2021 | 15728 | 1980.57 | Yes | 1980.57 | 16/04/2025 | 01/09/2023 | 15 | 1766.91 | MVS
292 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMODARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012467 | SM/10985 | New | 20/05/2022 | 76 | 40.52 | Yes | 40.52 |  | 15/03/2023 | 2 | 0.14 | MVS
293 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PAHARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012472 | SM/10990 | New | 20/05/2022 | 86 | 42.47 | Yes | 42.47 |  | 15/03/2023 | 1 | 0.12 | MVS
294 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GHUGUJAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012131 | SM/10903 | New | 20/05/2022 | 0 | 37.43 | Yes | 37.43 |  | 19/04/2024 | 1 | 0.35 | MVS
295 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | TSM/012066 | SM/11108 | New | 20/05/2022 | 804 | 38.5 | Yes | 38.5 |  | 16/05/2024 | 3 | 0.47 | MVS
296 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAGDUBI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012298 | SM/11110 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 |  |  | 0 | 0 | MVS
297 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GOBINDAPURBAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012379 | SM/10922 | New | 20/05/2022 | 300 | 31.49 | Yes | 31.49 |  |  | 0 | 0 | MVS
298 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAVI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012309 | SM/11121 | New | 20/05/2022 | 0 | 43.65 | Yes | 43.65 |  | 04/08/2023 | 3 | 0.35 | MVS
299 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANKTOR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012339 | SM/11076 | New | 20/05/2022 | 44 | 36.21 | Yes | 36.21 | 24/12/2021 | 16/06/2023 | 0 | 0.12 | MVS
300 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMODARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012488 | SM/10956 | New | 20/05/2022 | 55 | 38.13 | Yes | 38.13 |  | 15/05/2023 | 1 | 0.12 | MVS
301 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHANDORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012493 | SM/10961 | New | 20/05/2022 | 27 | 32.3 | Yes | 32.3 |  |  | 0 | 0 | MVS
302 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHEDUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012360 | SM/11041 | New | 20/05/2022 | 79 | 41.11 | Yes | 41.11 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
303 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHANDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012373 | SM/11054 | New | 20/05/2022 | 76 | 40.52 | Yes | 40.52 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
304 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKBASA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012448 | SM/10891 | New | 20/05/2022 | 52 | 37.43 | Yes | 37.43 |  | 22/05/2024 | 1 | 0.12 | MVS
305 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NATSHALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012501 | SM/10969 | New | 20/05/2022 | 76 | 40.52 | Yes | 40.52 |  |  | 0 | 0 | MVS
306 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PAHARIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012107 | SM/10897 | New | 20/05/2022 | 223 | 36.46 | Yes | 36.46 |  | 02/06/2023 | 1 | 0.12 | MVS
307 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAGNADA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012322 | SM/11059 | New | 20/05/2022 | 48 | 34.46 | Yes | 34.46 | 24/12/2021 |  | 0 | 0 | MVS
308 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GANGPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012457 | SM/10975 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 |  | 28/11/2024 | 2 | 0.14 | MVS
309 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Jemo, House Hold No.: 54) | TSM/012266 | SM/11137 | New | 20/05/2022 | 215 | 39.69 | Yes | 39.69 | 24/12/2021 | 02/02/2023 | 1 | 0.12 | MVS
310 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKATHOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012392 | SM/10935 | New | 20/05/2022 | 167 | 41.84 | Yes | 41.84 |  |  | 0 | 0 | MVS
311 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Asude, House Hold No.: 35) | TSM/012083 | SM/11102 | New | 20/05/2022 | 35 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
312 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHAITANDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012414 | SM/10857 | New | 20/05/2022 | 400 | 33.64 | Yes | 33.64 |  | 29/04/2024 | 1 | 0.12 | MVS
313 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nachur, House Hold No.: 59) | TSM/012241 | SM/11172 | New | 20/05/2022 | 59 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
314 | BANKURA | Bankura Division | Bhat Pushkarini Piped Water Supply Scheme | TSM/014586 | SM/12416 | New | 22/08/2022 | 1434 | 948.04 | Yes | 948.65 | 09/12/2022 | 24/07/2023 | 5 | 793.25 | MVS
315 | BANKURA | Bankura Division | Karachmani Khayarsol Piped Water Supply Scheme | TSM/014581 | SM/12420 | New | 22/08/2022 | 410 | 412.94 | Yes | 417.62 | 04/03/2024 | 02/05/2023 | 5 | 322.01 | MVS
316 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Khamardihi, House Hold:92 | TSM/012201 | SM/11444 | New | 20/05/2022 | 217 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
317 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name : Radha Damodarpur, House Hold:79 | TSM/012191 | SM/11446 | New | 20/05/2022 | 299 | 38.91 | Yes | 38.91 |  |  | 0 | 0 | MVS
318 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Dumni, House Hold:67 | TSM/012187 | SM/11447 | New | 20/05/2022 | 67 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
319 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under Jal Jeevan Mission (JJM) for 04 nos, Kharigara (302), Dhonara (303), Chingragoalaso | TSM/010428 | SM/12839 | Retrofitting | 22/08/2022 | 698 | 114.28 | Yes | 115.16 | 04/01/2023 | 28/03/2023 | 1 | 97.78 | MVS
320 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Kushtara , House Hold No.: 21 ) | TSM/012169 | SM/11680 | New | 20/05/2022 | 418 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
321 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Dakshinsol, Household-36) | TSM/012137 | SM/11405 | New | 20/05/2022 | 36 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
322 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Madhurpur, House Hold No.: 93) | TSM/012127 | SM/11692 | New | 20/05/2022 | 93 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
323 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bhabanipur, House Hold No.: 60) | TSM/012121 | SM/11695 | New | 20/05/2022 | 150 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
324 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Samanta Bandi, Household-39) | TSM/012133 | SM/11406 | New | 20/05/2022 | 39 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
325 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Nischintapur, Household-81) | TSM/012111 | SM/11413 | New | 20/05/2022 | 249 | 39.11 | Yes | 39.11 |  |  | 0 | 0 | MVS
326 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Shibdanga, Household-82) | TSM/012105 | SM/11415 | New | 20/05/2022 | 82 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
327 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Tiura, Household-95) | TSM/012093 | SM/11420 | New | 20/05/2022 | 604 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
328 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Nachanhati, Household-84) | TSM/012079 | SM/11425 | New | 20/05/2022 | 84 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
329 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BENAGARYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012067 | SM/13251 | New | 20/05/2022 | 54 | 37.89 | Yes | 37.89 |  |  | 0 | 0 | MVS
330 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BERA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012190 | SM/13266 | New | 20/05/2022 | 45 | 43.58 | Yes | 43.58 |  | 07/06/2023 | 1 | 0.12 | MVS
331 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | TSM/016212 | SM/15001 | Augmentation | 26/09/2022 | 1025 | 395.06 | Yes | 395.06 | 19/02/2024 | 28/09/2024 | 12 | 313.54 | MVS
332 | BANKURA | Bankura Division | Jamkuri Piped Water Supply Scheme | TSM/015750 | SM/14007 | New | 26/09/2022 | 1905 | 950.14 | Yes | 950.14 | 31/01/2025 | 26/07/2024 | 4 | 88.54 | MVS
333 | BANKURA | Bankura Division | Makarandapur Piped Water Supply Scheme | TSM/014566 | SM/14520 | New | 22/08/2022 | 2105 | 1153.54 | Yes | 1153.54 | 12/03/2025 | 06/01/2023 | 4 | 207.78 | MVS
334 | BANKURA | Bankura Division | Banna Piped Water Supply Scheme | TSM/014200 | SM/14525 | New | 22/08/2022 | 3405 | 1424.34 | Yes | 1424.34 | 12/03/2025 | 06/01/2023 | 5 | 205.58 | MVS
335 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Ekteswar PWSS scheme Dist Bankura | TSM/018673 | SM/15312 | Solarisation | 16/11/2022 | 0 | 34.74 | Yes | 34.74 | 29/12/2022 | 24/07/2024 | 3 | 25.65 | MVS
336 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Nabakishor PWSS scheme Dist Bankura | TSM/018679 | SM/15316 | Solarisation | 16/11/2022 | 0 | 11.26 | Yes | 11.26 | 29/12/2022 | 23/03/2023 | 1 | 7.8 | MVS
337 | BANKURA | Bankura Division | Deshra Piped Water Supply Scheme | TSM/014824 | SM/14246 | New | 09/09/2022 | 3339 | 1591.82 | Yes | 1591.82 | 12/03/2025 | 27/09/2024 | 3 | 109.32 | MVS
338 | BANKURA | Bankura Mechanical Division | Construction of Grid-connected Solar Photo-Voltaic system for Katulpur pump house-I(OHR site) of Kotulpur PWSS scheme,Dist: Bankura | TSM/016444 | SM/16963 | Solarisation | 30/09/2022 | 0 | 11.12 | Yes | 11.12 | 15/12/2022 | 17/04/2023 | 1 | 7.8 | MVS
339 | BANKURA | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018919 | SM/16966 | Augmentation | 16/11/2022 | 743 | 478.54 | Yes | 478.54 | 07/06/2024 | 09/09/2024 | 10 | 366.16 | MVS
340 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | TSM/015536 | SM/16940 | Retrofitting | 16/11/2022 | 4478 | 659.22 | Yes | 659.22 | 25/04/2025 | 02/05/2023 | 9 | 578.22 | MVS
341 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | TSM/016243 | SM/16935 | Augmentation | 26/09/2022 | 3815 | 999.97 | Yes | 999.97 | 25/04/2025 | 17/06/2025 | 8 | 804.44 | MVS
342 | BANKURA | Bankura Division | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018963 | SM/16957 | Augmentation | 16/11/2022 | 416 | 293.59 | Yes | 293.59 | 07/06/2024 | 19/07/2023 | 4 | 216.03 | MVS
343 | BANKURA | Bankura Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018960 | SM/17235 | Augmentation | 16/11/2022 | 230 | 231.27 | Yes | 231.27 | 07/03/2025 | 13/07/2023 | 8 | 225.25 | MVS
344 | BANKURA | Bankura Division | Augmentation of Ajodhya Water Supply Scheme | TSM/019176 | SM/17246 | Augmentation | 16/11/2022 | 480 | 320.23 | Yes | 320.23 | 19/01/2024 | 22/03/2024 | 6 | 301 | MVS
345 | BANKURA | Bankura Division | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018942 | SM/17250 | Augmentation | 16/11/2022 | 245 | 173.9 | Yes | 177.09 | 31/08/2023 | 18/07/2023 | 4 | 124.77 | MVS
346 | BANKURA | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018953 | SM/17257 | Augmentation | 16/11/2022 | 420 | 492.36 | Yes | 492.36 | 24/01/2025 | 21/08/2024 | 13 | 413.23 | MVS
347 | BANKURA | Bankura Division | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018946 | SM/17705 | Augmentation | 16/11/2022 | 630 | 267.08 | Yes | 271.86 | 29/11/2024 | 27/07/2023 | 5 | 207.14 | MVS
348 | BANKURA | Bankura Division | Birsingpur Piped Water Supply Scheme. | TSM/018234 | SM/17223 | New | 16/11/2022 | 1968 | 892.93 | Yes | 898.01 | 29/04/2025 | 27/11/2023 | 6 | 678.37 | MVS
349 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | TSM/018014 | SM/17227 | New | 16/11/2022 | 2517 | 766.66 | Yes | 766.66 | 29/04/2025 | 31/10/2023 | 7 | 456.57 | MVS
350 | BANKURA | Bankura Division | Jamuna Band Pipe Water Supply Scheme | TSM/017801 | SM/18037 | New | 28/12/2022 | 945 | 563.85 | Yes | 563.85 | 08/01/2024 | 24/07/2023 | 5 | 521.1 | MVS
351 | BANKURA | Bankura Division | Augmentation of Sashpur Zone-B Water Supply Scheme | TSM/019015 | SM/17421 | Augmentation | 16/11/2022 | 318 | 344.8 | Yes | 344.8 | 21/06/2024 | 13/07/2023 | 6 | 282.3 | MVS
352 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | TSM/017961 | SM/18040 | New | 28/12/2022 | 804 | 357.67 | Yes | 357.67 | 10/01/2025 | 21/09/2023 | 11 | 333.93 | MVS
353 | BANKURA | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018970 | SM/17286 | Augmentation | 16/11/2022 | 480 | 261.74 | Yes | 262.47 | 30/09/2024 | 14/08/2023 | 6 | 202.93 | MVS
354 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019148 | SM/17434 | Augmentation | 16/11/2022 | 215 | 953.45 | Yes | 632.28 | 16/01/2025 | 27/07/2023 | 4 | 247.99 | MVS
355 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019188 | SM/17440 | Augmentation | 16/11/2022 | 850 | 985.52 | Yes | 985.52 | 09/04/2025 | 02/07/2025 | 12 | 701.74 | MVS
356 | BANKURA | Bankura Division | Augmentation of Indas Water Supply Scheme | TSM/019132 | SM/17684 | Augmentation | 16/11/2022 | 280 | 177.59 | Yes | 178.2 | 19/06/2024 | 21/09/2023 | 7 | 110.21 | MVS
357 | BANKURA | Bankura Division | Brindabanpur Piped Water Supply Scheme | TSM/015157 | SM/18437 | New | 09/09/2022 | 3614 | 1649.04 | Yes | 1649.04 | 31/01/2025 | 06/01/2023 | 4 | 238.52 | MVS
358 | BANKURA | Bankura Division | Ghora Danga Piped Water Supply Scheme | TSM/018446 | SM/18611 | New | 28/12/2022 | 2413 | 1085.31 | Yes | 1085.31 | 05/02/2024 | 14/08/2023 | 2 | 803.73 | MVS
359 | BANKURA | Bankura Division | Rampur Piped Water Supply Scheme | TSM/018166 | SM/18349 | New | 16/11/2022 | 3297 | 1338.73 | Yes | 1338.73 | 29/04/2025 | 07/07/2025 | 7 | 1025.49 | MVS
360 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALI MAHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012150 | SM/13257 | New | 20/05/2022 | 104 | 36.7 | Yes | 36.7 |  | 05/06/2024 | 1 | 0.11 | MVS
361 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | TSM/005936 | SM/07264 | Retrofitting | 25/09/2020 | 1086 | 83.94 | Yes | 83.94 | 16/12/2022 | 12/07/2022 | 5 | 67.81 | MVS
362 | BANKURA | Bankura Division | Water Supply arrangement at Eklavya Model Residential school (EMRS) at Mukutmanipur, Khatra Sub- Division by creating source, Laying Rising Main & Distribution pipeline and Constructing CWR & Pump House | TSM/020438 | SM/18862 | School | 10/03/2023 | 0 | 56.72 | Yes | 56.72 | 22/12/2023 | 17/03/2023 | 2 | 38.95 | MVS
363 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020339 | SM/18894 | Augmentation | 10/03/2023 | 350 | 770.48 | Yes | 770.48 | 25/04/2025 | 17/06/2025 | 7 | 217.77 | MVS
364 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Siringa, House Hold No.: 21) | TSM/012076 | SM/11106 | New | 20/05/2022 | 21 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
365 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KAWA TANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012297 | SM/11109 | New | 20/05/2022 | 49 | 37.46 | Yes | 37.46 |  | 04/08/2023 | 1 | 0.11 | MVS
366 | BANKURA | Bankura Division | Baragaria Piped Water Supply Scheme | TSM/018204 | SM/18789 | New | 16/11/2022 | 3303 | 1529 | Yes | 1529 | 21/03/2025 | 04/10/2023 | 5 | 1180.71 | MVS
367 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Mahammad, House Hold No.: 83) | TSM/012259 | SM/11144 | New | 20/05/2022 | 312 | 39.69 | Yes | 39.69 |  | 02/02/2023 | 1 | 0.12 | MVS
368 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SANKARARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012408 | SM/10851 | New | 20/05/2022 | 740 | 43.45 | Yes | 43.45 |  |  | 0 | 0 | MVS
369 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANSHKETYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012442 | SM/10885 | New | 20/05/2022 | 95 | 44.23 | Yes | 44.23 |  | 04/04/2024 | 1 | 0.12 | MVS
370 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Parashia, House Hold:71 | TSM/012205 | SM/11443 | New | 20/05/2022 | 71 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
371 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAUTKHANA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012203 | SM/13271 | New | 20/05/2022 | 20 | 35.96 | Yes | 35.96 |  | 07/06/2023 | 1 | 0.12 | MVS
372 | BANKURA | Bankura Division | Biur Piped Water Supply Scheme | TSM/017778 | SM/18754 | New | 16/11/2022 | 2976 | 1334.45 | Yes | 1334.45 | 05/02/2024 | 26/10/2023 | 4 | 948.33 | MVS
373 | BANKURA | Bankura Division | Nanda Mohanpur Piped Water Supply Scheme | TSM/015172 | SM/19178 | New | 09/09/2022 | 3377 | 1443.13 | Yes | 1443.13 | 12/03/2025 | 06/01/2023 | 2 | 262.59 | MVS
374 | BANKURA | Bankura Division | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019164 | SM/18403 | Augmentation | 16/11/2022 | 3000 | 2747.96 | Yes | 2747.96 | 09/04/2025 | 25/04/2025 | 45 | 2080.21 | MVS
375 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | TSM/006001 | SM/07306 | Retrofitting | 25/09/2020 | 1304 | 96.39 | Yes | 96.39 | 16/12/2022 | 18/04/2022 | 16 | 207.07 | MVS
376 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Talgaria (93), Itamara (94), Uganpathar (95), Benagaria (96), Pathardihi (97), Jambedya (98), Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangam | TSM/005903 | SM/07267 | Retrofitting | 25/09/2020 | 1056 | 96.51 | Yes | 96.51 |  | 27/07/2022 | 10 | 108.77 | MVS
377 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | TSM/005922 | SM/07255 | Retrofitting | 25/09/2020 | 665 | 98.39 | Yes | 98.39 |  | 29/12/2020 | 10 | 175.3 | MVS
378 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) | TSM/006017 | SM/07370 | Retrofitting | 25/09/2020 | 1419 | 98.13 | Yes | 98.13 | 27/12/2022 | 29/11/2022 | 4 | 108.61 | MVS
379 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Mouladanga, Mithila, Jagan | TSM/005995 | SM/07238 | Retrofitting | 25/09/2020 | 1035 | 76.09 | Yes | 76.09 |  | 05/02/2021 | 7 | 98.52 | MVS
380 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | TSM/005987 | SM/07246 | Retrofitting | 25/09/2020 | 797 | 96.56 | Yes | 96.56 |  | 31/12/2020 | 5 | 159.4 | MVS
381 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | TSM/005901 | SM/07766 | Retrofitting | 25/09/2020 | 14433 | 1310.43 | Yes | 1310.43 | 27/12/2022 | 05/12/2022 | 205 | 2118.63 | MVS
382 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-B) | TSM/006011 | SM/07351 | Retrofitting | 25/09/2020 | 869 | 61.18 | Yes | 61.18 | 10/08/2022 | 18/09/2020 | 13 | 138.81 | MVS
383 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorshal, Dhenga kend, Kushma, Golhati & Bonomadhavpur) of J | TSM/006000 | SM/07339 | Retrofitting | 25/09/2020 | 841 | 81.28 | Yes | 81.28 |  | 04/10/2021 | 8 | 142.65 | MVS
384 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gourangadihi, Ledadihi, Ra | TSM/005740 | SM/06818 | Retrofitting | 28/08/2020 | 872 | 78.36 | Yes | 78.36 |  | 08/10/2020 | 7 | 235.35 | MVS
385 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chakadoba (73), Balarampur (138), Kubasol (139), Ban Pukhuria (140), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas | TSM/005917 | SM/07335 | Retrofitting | 25/09/2020 | 1201 | 99.02 | Yes | 99.02 |  | 18/01/2021 | 7 | 61.61 | MVS
386 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Kenjera-129, Chattrakhanda-130 & Nagatentu | TSM/007426 | SM/09332 | Retrofitting | 10/02/2021 | 613 | 85.14 | Yes | 85.14 |  | 22/11/2021 | 1 | 57.88 | MVS
387 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | TSM/007322 | SM/09237 | Retrofitting | 10/02/2021 | 3263 | 224.82 | Yes | 299.8 | 12/05/2023 | 29/10/2021 | 8 | 65.55 | MVS
388 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | TSM/007427 | SM/08297 | Retrofitting | 10/02/2021 | 1421 | 84.54 | Yes | 84.54 |  | 23/09/2021 | 10 | 134.98 | MVS
389 | BANKURA | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | TSM/007339 | SM/08310 | Retrofitting | 10/02/2021 | 7200 | 59.96 | Yes | 295.5 |  | 28/10/2021 | 7 | 31.11 | MVS
390 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | TSM/007284 | SM/09639 | Retrofitting | 10/02/2021 | 888 | 74.39 | Yes | 74.39 | 29/08/2023 | 23/09/2021 | 4 | 58.72 | MVS
391 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | TSM/008981 | SM/09549 | Retrofitting | 08/10/2021 | 2480 | 286.81 | Yes | 286.81 | 12/05/2023 | 13/04/2022 | 16 | 294.36 | MVS
392 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Kumirdoha, Gairabad, Fulberia, Dhaban, Bhabanipur, Upargara) | TSM/005974 | SM/09306 | Retrofitting | 25/09/2020 | 914 | 97.18 | Yes | 97.18 |  | 12/07/2022 | 28 | 127.65 | MVS
393 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JOR | TSM/006007 | SM/07310 | Retrofitting | 25/09/2020 | 1185 | 90.97 | Yes | 90.97 | 19/04/2023 | 09/07/2021 | 20 | 145.09 | MVS
394 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Salapahari (5), Elora (7), Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirba | TSM/005904 | SM/07268 | Retrofitting | 25/09/2020 | 919 | 77.68 | Yes | 77.68 |  | 05/02/2021 | 11 | 76.16 | MVS
395 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DEUL BHIRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012468 | SM/10986 | New | 20/05/2022 | 89 | 43.06 | Yes | 43.06 |  | 15/03/2023 | 1 | 0.12 | MVS
396 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHANDRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012475 | SM/10993 | New | 20/05/2022 | 93 | 41.04 | Yes | 43.84 |  | 15/03/2023 | 2 | 0.14 | MVS
397 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SIBARAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012117 | SM/10901 | New | 20/05/2022 | 225 | 36.96 | Yes | 36.96 |  | 02/06/2023 | 1 | 0.12 | MVS
398 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALUDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012138 | SM/10905 | New | 20/05/2022 | 161 | 39.52 | Yes | 39.52 |  | 02/06/2023 | 1 | 0.12 | MVS
399 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PANCHPUKHURIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012165 | SM/10917 | New | 20/05/2022 | 85 | 42.28 | Yes | 42.28 |  | 05/06/2023 | 2 | 0.24 | MVS
400 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARAMANIK KUNRI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012382 | SM/10925 | New | 20/05/2022 | 92 | 33.37 | Yes | 33.37 |  |  | 0 | 0 | MVS
401 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BURISAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012305 | SM/11117 | New | 20/05/2022 | 63 | 39.98 | Yes | 39.98 |  | 04/08/2023 | 1 | 0.11 | MVS
402 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGANNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012283 | SM/11020 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 | 18/02/2025 | 07/06/2023 | 1 | 0.12 | MVS
403 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMSUNDARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012357 | SM/11038 | New | 20/05/2022 | 47 | 36.96 | Yes | 36.96 | 24/12/2021 | 04/08/2023 | 1 | 0.12 | MVS
404 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GOALKPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012359 | SM/11040 | New | 20/05/2022 | 67 | 40.91 | Yes | 40.91 | 18/02/2025 | 23/04/2024 | 1 | 0.12 | MVS
405 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Metelsair, House Hold No.: 93) | TSM/012250 | SM/11153 | New | 20/05/2022 | 384 | 39.69 | Yes | 39.69 |  |  | 0 | 0 | MVS
406 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHABANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012497 | SM/10965 | New | 20/05/2022 | 651 | 41.37 | Yes | 41.37 |  |  | 0 | 0 | MVS
407 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MANJURA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012145 | SM/10908 | New | 20/05/2022 | 68 | 41.14 | Yes | 41.14 |  | 02/06/2023 | 1 | 0.12 | MVS
408 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR THANA DUMAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012313 | SM/11125 | New | 20/05/2022 | 0 | 37.46 | Yes | 37.46 |  | 19/09/2023 | 1 | 0.12 | MVS
409 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Jaljala, House Hold No.: 84) | TSM/012112 | SM/11086 | New | 20/05/2022 | 84 | 38.5 | Yes | 38.5 | 24/12/2021 | 02/02/2023 | 1 | 0.12 | MVS
410 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dehuabani, House Hold No.: 61) | TSM/012106 | SM/11088 | New | 20/05/2022 | 61 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 1 | 0.12 | MVS
411 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Napukur, House Hold No.: 89) | TSM/012104 | SM/11089 | New | 20/05/2022 | 89 | 38.5 | Yes | 38.5 |  | 15/03/2023 | 2 | 0.14 | MVS
412 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATDEULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012444 | SM/10887 | New | 20/05/2022 | 80 | 41.3 | Yes | 41.3 |  | 07/09/2023 | 1 | 0.12 | MVS
413 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bramhanairi, House Hold No.: 67) | TSM/012099 | SM/11092 | New | 20/05/2022 | 67 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
414 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURUSTHALIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012453 | SM/10971 | New | 20/05/2022 | 85 | 42.28 | Yes | 42.28 |  | 07/09/2023 | 1 | 0.12 | MVS
415 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHALTORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012502 | SM/10970 | New | 20/05/2022 | 451 | 41.14 | Yes | 41.14 |  |  | 0 | 0 | MVS
416 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KELERA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012451 | SM/10894 | New | 20/05/2022 | 75 | 42.76 | Yes | 42.76 |  | 15/03/2023 | 1 | 0.12 | MVS
417 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BOTKULA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012452 | SM/10895 | New | 20/05/2022 | 86 | 42.47 | Yes | 42.47 |  | 11/04/2023 | 1 | 0.12 | MVS
418 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALIAPATHAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012458 | SM/10976 | New | 20/05/2022 | 68 | 41.14 | Yes | 41.14 |  | 28/11/2024 | 2 | 0.14 | MVS
419 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KELAI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012395 | SM/10938 | New | 20/05/2022 | 244 | 45.01 | Yes | 45.01 |  |  | 0 | 0 | MVS
420 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KENTHALYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012396 | SM/10939 | New | 20/05/2022 | 157 | 41.6 | Yes | 41.6 |  | 12/03/2024 | 1 | 0.12 | MVS
421 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Jamsala, House Hold:60) | TSM/012260 | SM/11143 | New | 20/05/2022 | 317 | 39.69 | Yes | 39.69 |  | 26/06/2023 | 1 | 0.12 | MVS
422 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Kachara , House Hold No.: 25) | TSM/012080 | SM/11104 | New | 20/05/2022 | 285 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 1 | 0.12 | MVS
423 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012441 | SM/10884 | New | 20/05/2022 | 28 | 32.56 | Yes | 32.56 |  | 15/03/2023 | 2 | 0.14 | MVS
424 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Piritchak, House Hold No.: 39) | TSM/012198 | SM/11194 | New | 20/05/2022 | 39 | 38.64 | Yes | 38.64 |  | 18/01/2023 | 1 | 0.36 | MVS
425 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I Project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos, Baramasia & Mukundapur (PIRRAGARI | TSM/010429 | SM/11822 | Retrofitting | 25/04/2022 | 81 | 32 | Yes | 33.27 | 16/12/2022 | 06/04/2023 | 3 | 27.22 | MVS
426 | BANKURA | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | TSM/005084 | SM/09878 | Augmentation | 19/02/2021 | 3612 | 822.71 | Yes | 822.71 | 29/04/2025 | 01/12/2023 | 19 | 495.46 | MVS
427 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMUNDIHA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012410 | SM/10853 | New | 20/05/2022 | 730 | 41.5 | Yes | 41.5 |  |  | 0 | 0 | MVS
428 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR HARISHCHANDRAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012424 | SM/10867 | New | 20/05/2022 | 33 | 33.91 | Yes | 33.91 | 03/10/2024 | 22/05/2024 | 1 | 0.12 | MVS
429 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SALGERYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012427 | SM/10870 | New | 20/05/2022 | 24 | 31.49 | Yes | 31.49 |  | 11/04/2023 | 1 | 0.12 | MVS
430 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Amlasol, House Hold No.: 69) | TSM/012239 | SM/11173 | New | 20/05/2022 | 69 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
431 | BANKURA | Bankura Division | Ghagara Piped Water Supply Scheme | TSM/014207 | SM/12426 | New | 22/08/2022 | 658 | 457.53 | Yes | 457.53 | 12/03/2025 | 06/01/2023 | 3 | 37.74 | MVS
432 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Shibdanga, House Hold No.: 74) | TSM/012218 | SM/11184 | New | 20/05/2022 | 74 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
433 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Jhero, House Hold No.: 21) | TSM/012210 | SM/11188 | New | 20/05/2022 | 21 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 1 | 0.12 | MVS
434 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DOMAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012351 | SM/11203 | New | 20/05/2022 | 60 | 39.29 | Yes | 39.29 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
435 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Dumohani, House Hold No.: 51) | TSM/012178 | SM/11677 | New | 20/05/2022 | 358 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
436 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Paschim Nabasan, House Hold:33) | TSM/012233 | SM/11433 | New | 20/05/2022 | 33 | 38.91 | Yes | 38.91 |  | 04/08/2023 | 1 | 0.12 | MVS
437 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Kamar Bera, House Hold:81) | TSM/012222 | SM/11437 | New | 20/05/2022 | 336 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 2 | 0.84 | MVS
438 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Dihilapur, House Hold:52) | TSM/012217 | SM/11439 | New | 20/05/2022 | 182 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
439 | BANKURA | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | TSM/014178 | SM/12840 | Augmentation | 22/08/2022 | 1946 | 997.56 | Yes | 997.56 | 16/04/2025 | 17/06/2025 | 10 | 964.65 | MVS
440 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012063 | SM/13250 | New | 20/05/2022 | 188 | 39.05 | Yes | 39.05 |  |  | 0 | 0 | MVS
441 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Kubir Bandh, Household-43) | TSM/012147 | SM/11403 | New | 20/05/2022 | 633 | 39.11 | Yes | 39.11 |  |  | 0 | 0 | MVS
442 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chhatina, House Hold No.: 80) | TSM/012125 | SM/11693 | New | 20/05/2022 | 80 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
443 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Chhota Narayanpur, Household-24) | TSM/012129 | SM/11407 | New | 20/05/2022 | 24 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
444 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Bara Naryanpur, Household-73) | TSM/012088 | SM/11422 | New | 20/05/2022 | 73 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
445 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Maitya, Household-74) | TSM/012085 | SM/11423 | New | 20/05/2022 | 74 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
446 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012220 | SM/13274 | New | 20/05/2022 | 52 | 41.69 | Yes | 41.69 |  | 29/04/2024 | 1 | 0.12 | MVS
447 | BANKURA | Bankura Division | Atra Piped Water Supply Scheme | TSM/015426 | SM/14000 | New | 26/09/2022 | 2127 | 913.15 | Yes | 913.15 | 31/01/2025 | 26/07/2024 | 3 | 78.59 | MVS
448 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR INDRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012225 | SM/13275 | New | 20/05/2022 | 130 | 37.43 | Yes | 37.43 |  |  | 0 | 0 | MVS
449 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012139 | SM/13255 | New | 20/05/2022 | 181 | 32.57 | Yes | 32.57 |  |  | 0 | 0 | MVS
450 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MOULESWAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012146 | SM/13256 | New | 20/05/2022 | 79 | 30.69 | Yes | 30.69 |  |  | 0 | 0 | MVS
451 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | TSM/016260 | SM/15003 | Augmentation | 26/09/2022 | 1800 | 656.7 | Yes | 656.7 | 18/01/2024 | 22/05/2023 | 9 | 437.75 | MVS
452 | BANKURA | Bankura Division | Kalyanpur Piped Water Supply Scheme | TSM/015704 | SM/14010 | New | 26/09/2022 | 654 | 594.62 | Yes | 594.62 | 14/12/2022 | 06/01/2023 | 3 | 96.39 | MVS
453 | BANKURA | Bankura Division | Jadabnagar Piped Water Supply Scheme | TSM/014206 | SM/14527 | New | 22/08/2022 | 2927 | 1225.04 | Yes | 1225.04 | 29/08/2023 | 12/05/2023 | 6 | 121.8 | MVS
454 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Radhanagar PWSS scheme Dist Bankura | TSM/018675 | SM/15314 | Solarisation | 16/11/2022 | 0 | 31.01 | Yes | 31.01 | 29/12/2022 | 24/07/2024 | 2 | 22.62 | MVS
455 | BANKURA | Bankura Division | Dhagaria Piped Water Supply Scheme | TSM/015425 | SM/15023 | New | 26/09/2022 | 1851 | 908 | Yes | 908 | 31/01/2025 | 18/07/2023 | 5 | 602.76 | MVS
456 | BANKURA | Bankura Division | Augmentation of Kotulpur Piped Water Supply Scheme. | TSM/005085 | SM/09981 | Augmentation | 19/02/2021 | 4060 | 842.25 | Yes | 842.25 | 29/11/2024 | 01/12/2023 | 17 | 656.69 | MVS
457 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Sarenga PWSS scheme Dist Bankura | TSM/018671 | SM/15317 | Solarisation | 16/11/2022 | 0 | 42.2 | Yes | 42.2 | 10/02/2023 | 17/04/2023 | 1 | 30.51 | MVS
458 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Sanabandh PWSS scheme Dist Bankura | TSM/018676 | SM/15318 | Solarisation | 16/11/2022 | 0 | 34.74 | Yes | 34.74 | 29/12/2022 | 24/07/2024 | 2 | 25.15 | MVS
459 | BANKURA | Bankura Mechanical Division | Construction of Grid-connected Solar Photo-Voltaic system for Kukrakuri intake pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | TSM/019281 | SM/15330 | Solarisation | 16/11/2022 | 0 | 366.53 | Yes | 366.53 | 25/04/2023 | 03/07/2024 | 2 | 87.39 | MVS
460 | BANKURA | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | TSM/018930 | SM/16974 | Augmentation | 16/11/2022 | 1080 | 737.61 | Yes | 738.82 | 11/02/2025 | 25/04/2025 | 10 | 522.05 | MVS
461 | BANKURA | Bankura Division | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019157 | SM/16980 | Augmentation | 16/11/2022 | 110 | 431.07 | Yes | 433.81 | 29/04/2025 | 17/06/2025 | 7 | 127.28 | MVS
462 | BANKURA | Bankura Division | Augmentation of Benda water supply scheme | TSM/019170 | SM/17244 | Augmentation | 16/11/2022 | 80 | 273.28 | Yes | 273.28 | 19/06/2024 | 19/07/2023 | 5 | 248.59 | MVS
463 | BANKURA | Bankura Division | Basudebpur Piped Water Supply Scheme. | TSM/018186 | SM/16944 | New | 16/11/2022 | 2156 | 880.29 | Yes | 880.89 | 30/01/2023 | 14/08/2023 | 3 | 695.21 | MVS
464 | BANKURA | Bankura Division | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018944 | SM/17704 | Augmentation | 16/11/2022 | 302 | 232.29 | Yes | 235.52 | 16/04/2025 | 02/06/2025 | 6 | 231.54 | MVS
465 | BANKURA | Bankura Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019211 | SM/17711 | Augmentation | 16/11/2022 | 245 | 462.59 | Yes | 464.57 | 31/01/2025 | 11/05/2023 | 5 | 105.24 | MVS
466 | BANKURA | Bankura Division | Augmentation of Betanal Zone-A Water Supply Scheme | TSM/019158 | SM/17692 | Augmentation | 16/11/2022 | 251 | 267.76 | Yes | 267.76 | 30/01/2025 | 14/08/2023 | 6 | 258.29 | MVS
467 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | TSM/017903 | SM/18042 | New | 28/12/2022 | 985 | 438.88 | Yes | 438.88 | 07/01/2025 | 26/06/2025 | 6 | 118.06 | MVS
468 | BANKURA | Bankura Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | TSM/011406 | SM/17578 | New | 28/12/2022 | 586 | 490.58 | Yes | 490.58 | 30/09/2024 | 14/08/2023 | 8 | 361.84 | MVS
469 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019224 | SM/17288 | Augmentation | 16/11/2022 | 780 | 976.27 | Yes | 976.27 | 12/02/2025 | 24/07/2023 | 9 | 588.44 | MVS
470 | BANKURA | Bankura Division | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019233 | SM/17435 | Augmentation | 16/11/2022 | 312 | 851.03 | Yes | 861.68 | 29/04/2025 | 17/06/2025 | 8 | 343.88 | MVS
471 | BANKURA | Bankura Division | Augmentation of Betanal Zone-B Water Supply Scheme | TSM/019149 | SM/17418 | Augmentation | 16/11/2022 | 222 | 385.21 | Yes | 386.52 | 19/06/2024 | 13/07/2023 | 7 | 305.63 | MVS
472 | BANKURA | Bankura Division | Augmentation of Chuamasina Zone-B Water Supply Scheme | TSM/019172 | SM/17427 | Augmentation | 16/11/2022 | 260 | 243.49 | Yes | 243.49 | 19/06/2024 | 24/07/2023 | 3 | 239.7 | MVS
473 | BANKURA | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | TSM/018969 | SM/17285 | Augmentation | 16/11/2022 | 3576 | 622.12 | Yes | 622.12 | 24/01/2025 | 26/04/2024 | 9 | 595.74 | MVS
474 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SIAKULDOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012316 | SM/11128 | New | 20/05/2022 | 65 | 40.44 | Yes | 40.44 |  | 07/09/2023 | 1 | 0.12 | MVS
475 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Goala Danga, House Hold:96) | TSM/012219 | SM/11438 | New | 20/05/2022 | 282 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
476 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Dharisyer, House Hold No.: 25) | TSM/012155 | SM/11684 | New | 20/05/2022 | 62 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
477 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SIARBADA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012110 | SM/10898 | New | 20/05/2022 | 32 | 33.64 | Yes | 33.64 |  | 02/06/2023 | 1 | 0.12 | MVS
478 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012118 | SM/10902 | New | 20/05/2022 | 51 | 33.64 | Yes | 33.64 |  | 26/04/2024 | 2 | 0.35 | MVS
479 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MALIN DASI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012156 | SM/10912 | New | 20/05/2022 | 69 | 41.37 | Yes | 41.37 |  | 02/06/2023 | 1 | 0.12 | MVS
480 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012320 | SM/11132 | New | 20/05/2022 | 93 | 43.84 | Yes | 43.84 | 24/12/2021 | 29/05/2024 | 1 | 0.12 | MVS
481 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAJORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012465 | SM/10983 | New | 20/05/2022 | 89 | 43.06 | Yes | 43.06 |  |  | 0 | 0 | MVS
482 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAKHARANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012272 | SM/11009 | New | 20/05/2022 | 91 | 43.45 | Yes | 43.45 | 18/02/2025 | 16/05/2024 | 2 | 0.36 | MVS
483 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHALUKA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012417 | SM/10860 | New | 20/05/2022 | 299 | 37.46 | Yes | 37.46 | 24/12/2021 | 04/04/2024 | 1 | 0.12 | MVS
484 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MEMOULI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012324 | SM/11061 | New | 20/05/2022 | 31 | 33.37 | Yes | 33.37 | 24/12/2021 | 22/05/2024 | 2 | 0.24 | MVS
485 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Goppdanga, House Hold:36) | TSM/012243 | SM/11429 | New | 20/05/2022 | 36 | 38.91 | Yes | 38.91 |  | 04/08/2023 | 1 | 0.12 | MVS
486 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:66) | TSM/012214 | SM/11440 | New | 20/05/2022 | 66 | 38.91 | Yes | 38.91 |  |  | 0 | 0 | MVS
487 | BANKURA | Bankura Division | Binod Nagar Piped Water Supply Scheme | TSM/015427 | SM/18340 | New | 30/09/2022 | 2682 | 1113.09 | Yes | 1113.09 | 31/01/2025 | 06/01/2023 | 2 | 46.65 | MVS
488 | BANKURA | Bankura Division | Community based PWSS by stand alone system along with all allied works including fitting fixing of water storage tanks and MS structure, FHTC etc. at 89 nos. pin point sites within 14 nos. blocks, 450 nos. Mark-II tubewell including repairing of existing | TSM/006537 |  | Others | 04/12/2020 | 0 | 1882.67 | No | 0 |  |  | 0 | 0 | MVS
489 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hare Krishnapur , Dadimukha , Gopbandh , Bankuradanga, Belut , | TSM/006002 | SM/07305 | Retrofitting | 25/09/2020 | 1303 | 96.08 | Yes | 96.08 |  | 29/12/2020 | 10 | 175.82 | MVS
490 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | TSM/005991 | SM/07250 | Retrofitting | 25/09/2020 | 918 | 88.19 | Yes | 88.19 | 05/01/2023 | 10/02/2021 | 7 | 111.01 | MVS
491 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (1 | TSM/005915 | SM/07366 | Retrofitting | 25/09/2020 | 945 | 79.75 | Yes | 79.75 |  | 09/07/2021 | 11 | 63.29 | MVS
492 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) | TSM/006018 | SM/07371 | Retrofitting | 25/09/2020 | 1094 | 78.33 | Yes | 78.33 |  | 01/12/2021 | 3 | 91.87 | MVS
493 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyalda | TSM/005975 | SM/07240 | Retrofitting | 25/09/2020 | 1131 | 83.76 | Yes | 83.76 |  | 09/07/2021 | 11 | 142.1 | MVS
494 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kusum Goria, Tajpur Rampur, Rajmadhavtir, Kotalpukur & Mahidar | TSM/005984 | SM/07243 | Retrofitting | 25/09/2020 | 963 | 77.66 | Yes | 77.66 | 08/01/2024 | 04/10/2021 | 10 | 209.44 | MVS
495 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dadhimukha, Jamboni,Jagdal | TSM/005986 | SM/07245 | Retrofitting | 25/09/2020 | 1185 | 81.76 | Yes | 81.76 | 01/11/2022 | 05/02/2021 | 4 | 152.8 | MVS
496 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas (Dhaboagram, Tantkanali, Ni | TSM/005988 | SM/07247 | Retrofitting | 25/09/2020 | 920 | 85.75 | Yes | 85.75 |  | 12/02/2021 | 5 | 118.28 | MVS
497 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouza (Bandarkoda, Bhairabdanga, Barkura, Radhakantapur, Kantabesa, Ni | TSM/005931 | SM/07263 | Retrofitting | 25/09/2020 | 1052 | 99.4 | Yes | 99.4 |  | 18/01/2021 | 10 | 160.49 | MVS
498 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bara Bendya, Joytunga, Kostia & Khemua) of Joytunga (Zone - | TSM/005998 | SM/07313 | Retrofitting | 25/09/2020 | 819 | 97.22 | Yes | 97.22 |  | 04/04/2023 | 26 | 325.79 | MVS
499 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Bandarkhola, Ramharipur, Katapesia, Kolaberia & Maitha Gopinat | TSM/005997 | SM/07314 | Retrofitting | 25/09/2020 | 853 | 91.63 | Yes | 91.63 |  | 18/01/2021 | 6 | 173.35 | MVS
500 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | TSM/005920 | SM/07338 | Retrofitting | 25/09/2020 | 955 | 89.1 | Yes | 89.1 |  | 01/08/2022 | 7 | 165.65 | MVS
501 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | TSM/005891 | SM/07353 | Retrofitting | 25/09/2020 | 828 | 66.76 | Yes | 66.76 |  | 23/09/2021 | 9 | 266.52 | MVS
502 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mouzas (Junbedia) of HARIALGORA (Z | TSM/005738 | SM/06817 | Retrofitting | 28/08/2020 | 881 | 78.79 | Yes | 78.79 |  | 08/10/2020 | 5 | 168.43 | MVS
503 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | TSM/005736 | SM/06808 | Retrofitting | 28/08/2020 | 1013 | 88 | Yes | 88 | 05/01/2023 | 10/02/2021 | 6 | 166.43 | MVS
504 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Schem | TSM/007456 | SM/09330 | Retrofitting | 19/02/2021 | 2161 | 209.34 | Yes | 211.32 |  | 06/04/2023 | 6 | 215.01 | MVS
505 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Mathurabihari-28, Ramchandrapur-30, Matukp | TSM/007420 | SM/08292 | Retrofitting | 10/02/2021 | 828 | 70.88 | Yes | 70.88 |  | 23/09/2021 | 15 | 134.57 | MVS
506 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Du | TSM/007428 | SM/08298 | Retrofitting | 10/02/2021 | 1240 | 75.69 | Yes | 75.69 |  | 26/10/2021 | 2 | 64.05 | MVS
507 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjo | TSM/007306 | SM/09231 | Retrofitting | 10/02/2021 | 375 | 76.92 | Yes | 99.3 |  | 23/09/2021 | 6 | 78.17 | MVS
508 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | TSM/008195 | SM/09498 | Retrofitting | 19/08/2021 | 2933 | 247.99 | Yes | 247.99 | 27/12/2022 | 01/02/2022 | 5 | 178.11 | MVS
509 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | TSM/007294 | SM/09643 | Retrofitting | 10/02/2021 | 1015 | 79.52 | Yes | 79.61 |  | 29/11/2021 | 8 | 70.35 | MVS
510 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Majuria-135) of CHAKUPARSOLE (Zone - A) | TSM/007409 | SM/09636 | Retrofitting | 10/02/2021 | 943 | 86.9 | Yes | 86.9 |  | 22/11/2021 | 1 | 77.95 | MVS
511 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Baramara-149 & Kulaijuri-134) of CHAK | TSM/007412 | SM/09638 | Retrofitting | 10/02/2021 | 793 | 78.32 | Yes | 78.32 |  | 29/11/2021 | 1 | 70.43 | MVS
512 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | TSM/008196 | SM/09500 | Retrofitting | 19/08/2021 | 2933 | 218.91 | Yes | 297.84 | 30/09/2021 | 03/01/2022 | 17 | 297.54 | MVS
513 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baradi Kalapathar (15), Baradi (16), Dalambhija (17), Balguma (18), Chuagara (19), Bhangadeuli (20), Shushunia (21), Maukura (22), Belatikri (23), Guniada (24), Panchur (25), | TSM/008410 | SM/09503 | Retrofitting | 19/08/2021 | 2356 | 239.83 | Yes | 239.83 | 30/09/2021 | 29/10/2021 | 6 | 192.68 | MVS
514 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | TSM/007411 | SM/09619 | Retrofitting | 10/02/2021 | 703 | 73.06 | Yes | 73.06 |  | 29/11/2021 | 4 | 102.23 | MVS
515 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | TSM/007320 | SM/09620 | Retrofitting | 10/02/2021 | 882 | 75.16 | Yes | 75.16 |  | 29/11/2021 | 6 | 63.87 | MVS
516 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | TSM/008636 | SM/09533 | Retrofitting | 08/09/2021 | 2270 | 198.8 | Yes | 198.8 | 13/01/2022 | 21/04/2022 | 5 | 139.07 | MVS
517 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Sanpura-57, Jagaldwip-58, Dasarathbati-61 | TSM/007404 | SM/09623 | Retrofitting | 10/02/2021 | 2653 | 190.01 | Yes | 190.01 |  | 19/04/2022 | 5 | 297.36 | MVS
518 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kadamara (9), Pukhuria (10), Baranimdiha (13), Rengurbandh (14) & Rajabandh (15) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas un | TSM/007286 | SM/09640 | Retrofitting | 10/02/2021 | 714 | 88.11 | Yes | 90.02 | 12/05/2023 | 15/06/2022 | 16 | 86.66 | MVS
519 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha , Napra, Bagulia) of MALIARA (Zone - A) under Bankur | TSM/006005 | SM/09304 | Retrofitting | 25/09/2020 | 974 | 85.58 | Yes | 85.58 |  | 29/07/2022 | 10 | 239.98 | MVS
520 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NEKRAKONDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012478 | SM/10946 | New | 20/05/2022 | 81 | 41.5 | Yes | 41.5 |  |  | 0 | 0 | MVS
521 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANDARKONDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012481 | SM/10949 | New | 20/05/2022 | 28 | 32.56 | Yes | 32.56 |  | 15/05/2023 | 1 | 0.12 | MVS
522 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SIMCHAKA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012484 | SM/10952 | New | 20/05/2022 | 82 | 41.69 | Yes | 41.69 | 18/02/2025 | 15/05/2023 | 1 | 0.12 | MVS
523 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala) of Nabagr | TSM/005939 | SM/07342 | Retrofitting | 25/09/2020 | 806 | 98.67 | Yes | 98.67 | 16/11/2022 | 14/03/2023 | 1 | 9.98 | MVS
524 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | TSM/005918 | SM/07336 | Retrofitting | 25/09/2020 | 617 | 63.54 | Yes | 63.54 |  | 18/01/2021 | 12 | 77.53 | MVS
525 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHIN KAMALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012476 | SM/10994 | New | 20/05/2022 | 52 | 37.43 | Yes | 37.43 |  | 13/02/2023 | 1 | 0.26 | MVS
526 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KARRASOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012157 | SM/10913 | New | 20/05/2022 | 194 | 32.3 | Yes | 32.3 |  | 26/04/2024 | 1 | 0.24 | MVS
527 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TENTUL BERIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012158 | SM/10914 | New | 20/05/2022 | 51 | 35.96 | Yes | 35.96 |  | 26/04/2024 | 1 | 0.23 | MVS
528 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BELARMARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012384 | SM/10927 | New | 20/05/2022 | 123 | 33.64 | Yes | 33.64 |  | 13/09/2024 | 1 | 0.12 | MVS
529 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MANDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012385 | SM/10928 | New | 20/05/2022 | 197 | 36.71 | Yes | 36.71 |  |  | 0 | 0 | MVS
530 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR LEDAPAKUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012304 | SM/11116 | New | 20/05/2022 | 65 | 40.44 | Yes | 40.44 |  | 04/08/2023 | 1 | 0.11 | MVS
531 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GORADIHI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012312 | SM/11124 | New | 20/05/2022 | 156 | 31.22 | Yes | 31.22 |  |  | 0 | 0 | MVS
532 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JALJURA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012275 | SM/11012 | New | 20/05/2022 | 55 | 38.13 | Yes | 38.13 |  |  | 0 | 0 | MVS
533 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012281 | SM/11018 | New | 20/05/2022 | 76 | 40.52 | Yes | 40.52 |  |  | 0 | 0 | MVS
534 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BUCHI BURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012289 | SM/11026 | New | 20/05/2022 | 49 | 37.46 | Yes | 37.46 |  |  | 0 | 0 | MVS
535 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PHULJHOR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012290 | SM/11027 | New | 20/05/2022 | 41 | 35.46 | Yes | 35.46 |  | 04/08/2023 | 1 | 0.11 | MVS
536 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TILABAI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012354 | SM/11035 | New | 20/05/2022 | 21 | 30.68 | Yes | 30.68 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
537 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012340 | SM/11077 | New | 20/05/2022 | 46 | 36.71 | Yes | 36.71 | 24/12/2021 | 16/06/2023 | 0 | 0.12 | MVS
538 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JIAKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012341 | SM/11078 | New | 20/05/2022 | 33 | 33.91 | Yes | 33.91 | 24/12/2021 | 26/07/2023 | 0 | 0.12 | MVS
539 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BANSNALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012489 | SM/10957 | New | 20/05/2022 | 73 | 42.3 | Yes | 42.3 |  | 15/05/2023 | 1 | 0.12 | MVS
540 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PURBATOR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012492 | SM/10960 | New | 20/05/2022 | 33 | 33.91 | Yes | 33.91 |  |  | 0 | 0 | MVS
541 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TALTALA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012363 | SM/11044 | New | 20/05/2022 | 72 | 42.07 | Yes | 42.07 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
542 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAMASIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012153 | SM/10911 | New | 20/05/2022 | 85 | 42.28 | Yes | 42.28 |  |  | 0 | 0 | MVS
543 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Kankara, House Hold No.: 69) | TSM/012102 | SM/11090 | New | 20/05/2022 | 69 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
544 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA GOALDANGRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012321 | SM/11133 | New | 20/05/2022 | 83 | 41.89 | Yes | 41.89 | 24/12/2021 |  | 0 | 0 | MVS
545 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GANDLUGARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012449 | SM/10892 | New | 20/05/2022 | 94 | 44.04 | Yes | 44.04 |  | 15/03/2023 | 2 | 0.14 | MVS
546 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Shimdal, House Hold No.: 50) | TSM/012098 | SM/11093 | New | 20/05/2022 | 50 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
547 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KENDUT VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012499 | SM/10967 | New | 20/05/2022 | 151 | 44.43 | Yes | 44.43 |  |  | 0 | 0 | MVS
548 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PATIJANARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012455 | SM/10973 | New | 20/05/2022 | 72 | 42.07 | Yes | 42.07 |  | 11/04/2023 | 1 | 0.12 | MVS
549 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNABATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012323 | SM/11060 | New | 20/05/2022 | 25 | 31.76 | Yes | 31.76 | 24/12/2021 | 22/05/2024 | 1 | 0.12 | MVS
550 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012329 | SM/11066 | New | 20/05/2022 | 69 | 41.37 | Yes | 41.37 | 18/02/2025 | 22/05/2024 | 2 | 0.24 | MVS
551 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Dhanjoga, House Hold No.: 56) | TSM/012263 | SM/11140 | New | 20/05/2022 | 280 | 39.69 | Yes | 39.69 | 24/12/2021 | 07/09/2023 | 1 | 0.12 | MVS
552 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Angazrasol, House Hold:42) | TSM/012262 | SM/11141 | New | 20/05/2022 | 42 | 39.69 | Yes | 39.69 | 24/12/2021 | 02/02/2023 | 1 | 0.12 | MVS
553 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GHUTIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012440 | SM/10883 | New | 20/05/2022 | 35 | 34.45 | Yes | 34.45 |  | 22/05/2024 | 1 | 0.12 | MVS
554 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012443 | SM/10886 | New | 20/05/2022 | 97 | 44.62 | Yes | 44.62 |  |  | 0 | 0 | MVS
555 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Bhelaighata, House Hold No.: 32) | TSM/012200 | SM/11193 | New | 20/05/2022 | 474 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 1 | 0.12 | MVS
556 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Bhalukgere, House Hold No.: 48) | TSM/012196 | SM/11195 | New | 20/05/2022 | 48 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 2 | 0.14 | MVS
557 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAJURI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012412 | SM/10855 | New | 20/05/2022 | 214 | 43.45 | Yes | 43.45 |  | 16/05/2024 | 2 | 0.34 | MVS
558 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTAKEEHANDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012423 | SM/10866 | New | 20/05/2022 | 49 | 37.46 | Yes | 37.46 |  | 11/04/2023 | 1 | 0.12 | MVS
559 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nutangram Radhamohanpur, House Hold No.: 88) | TSM/012237 | SM/11174 | New | 20/05/2022 | 661 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
560 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Kumardubi, House Hold No.: 50) | TSM/012234 | SM/11176 | New | 20/05/2022 | 50 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
561 | BANKURA | Bankura Division | Mathurabati Piped Water Supply Scheme | TSM/014588 | SM/12417 | New | 22/08/2022 | 1001 | 689.99 | Yes | 691.64 | 09/12/2022 | 26/07/2024 | 6 | 108.9 | MVS
562 | BANKURA | Bankura Division | Hetia Piped Water Supply Scheme | TSM/014202 | SM/12425 | New | 22/08/2022 | 2353 | 815.5 | Yes | 815.5 | 31/01/2025 | 06/01/2023 | 5 | 76.41 | MVS
563 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHIRINGI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012403 | SM/10846 | New | 20/05/2022 | 272 | 40.52 | Yes | 40.52 |  | 12/03/2024 | 2 | 15500.73 | MVS
564 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012434 | SM/10877 | New | 20/05/2022 | 21 | 30.68 | Yes | 30.68 |  | 15/03/2023 | 1 | 0.12 | MVS
565 | BANKURA | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | TSM/011427 | SM/11980 | Augmentation | 25/04/2022 | 3930 | 1043.82 | Yes | 1043.82 | 12/02/2025 | 11/12/2024 | 11 | 1122.92 | MVS
566 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TELANBANDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012352 | SM/11204 | New | 20/05/2022 | 53 | 37.66 | Yes | 37.66 | 24/12/2021 | 16/06/2023 | 0 | 0.12 | MVS
567 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bhandarya, House Hold No.: 72) | TSM/012174 | SM/11679 | New | 20/05/2022 | 332 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
568 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Shankarpur, House Hold:52) | TSM/012224 | SM/11436 | New | 20/05/2022 | 52 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
569 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Danga Makarandapur, House Hold No.: 90) | TSM/012151 | SM/11685 | New | 20/05/2022 | 90 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
570 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Narayanpur, House Hold No.: 60) | TSM/012134 | SM/11690 | New | 20/05/2022 | 60 | 39.88 | Yes | 39.88 |  |  | 0 | 0 | MVS
571 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Chaulya, Household-71) | TSM/012100 | SM/11417 | New | 20/05/2022 | 71 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
572 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Tulardihi, House Hold:21) | TSM/012240 | SM/11430 | New | 20/05/2022 | 158 | 38.91 | Yes | 38.91 |  | 11/08/2023 | 1 | 0.24 | MVS
573 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Mathurabati, Household-54) | TSM/012090 | SM/11421 | New | 20/05/2022 | 262 | 39.11 | Yes | 39.11 |  | 12/03/2024 | 1 | 3.01 | MVS
574 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name -Aligang, House Hold-91) | TSM/012077 | SM/11426 | New | 20/05/2022 | 91 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
575 | BANKURA | Bankura Division | Ground water based Diga pipe water supply scheme, under Bankura Division, Block -Onda, Dist - Bankura. | TSM/011392 | SM/11923 | New | 25/04/2022 | 1133 | 541.12 | Yes | 541.12 | 01/03/2024 | 22/03/2024 | 11 | 513.08 | MVS
576 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012176 | SM/13263 | New | 20/05/2022 | 227 | 40.26 | Yes | 40.26 |  | 16/05/2024 | 1 | 0.23 | MVS
577 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BIRUDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012194 | SM/13267 | New | 20/05/2022 | 45 | 36.46 | Yes | 36.46 |  | 16/05/2024 | 1 | 0.24 | MVS
578 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TURUBANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012207 | SM/13272 | New | 20/05/2022 | 36 | 30.41 | Yes | 30.41 |  | 07/06/2023 | 1 | 0.12 | MVS
579 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | TSM/016337 | SM/14650 | Augmentation | 26/09/2022 | 184 | 89 | Yes | 89 | 12/02/2025 | 24/05/2022 | 5 | 35.98 | MVS
580 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | TSM/016323 | SM/15006 | Augmentation | 26/09/2022 | 608 | 246.43 | Yes | 246.43 | 10/03/2025 | 26/06/2025 | 5 | 146.09 | MVS
581 | BANKURA | Bankura Division | Patrabandh Piped Water Supply Scheme | TSM/015915 | SM/14012 | New | 26/09/2022 | 1936 | 978.71 | Yes | 978.71 | 12/03/2025 | 06/01/2023 | 3 | 75.32 | MVS
582 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dahala (250) & Bahadurpur (251) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under | TSM/005895 | SM/07356 | Retrofitting | 25/09/2020 | 735 | 64.72 | Yes | 64.72 |  | 05/02/2021 | 3 | 59.13 | MVS
583 | BANKURA | Bankura Division | Madhab Bati Piped Water Supply Scheme | TSM/014209 | SM/14522 | New | 22/08/2022 | 2974 | 1157.88 | Yes | 1157.88 | 31/01/2025 | 06/01/2023 | 5 | 88.96 | MVS
584 | BANKURA | Bankura Division | Rautkhanda Piped Water Supply Scheme | TSM/014208 | SM/14524 | New | 22/08/2022 | 3461 | 1442.11 | Yes | 1442.11 | 12/03/2025 | 06/01/2023 | 5 | 120.42 | MVS
585 | BANKURA | Bankura Division | Karak Berya Piped Water Supply Scheme | TSM/014783 | SM/14247 | New | 09/09/2022 | 1922 | 1009.33 | Yes | 1009.33 | 12/03/2025 | 06/01/2023 | 4 | 120.26 | MVS
586 | BANKURA | Bankura Division | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018939 | SM/16976 | Augmentation | 16/11/2022 | 765 | 299.84 | Yes | 306.48 | 16/04/2025 | 17/06/2025 | 5 | 135.78 | MVS
587 | BANKURA | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018912 | SM/16961 | Augmentation | 16/11/2022 | 540 | 456.92 | Yes | 456.92 | 16/04/2025 | 18/06/2024 | 11 | 200.74 | MVS
588 | BANKURA | Bankura Mechanical Division | Construction of Grid-connected Solar Photo-Voltaic system for Rampur pump house-I of Rampur PWSS scheme,Dist: Bankura | TSM/016561 | SM/16965 | Solarisation | 30/09/2022 | 0 | 6.92 | Yes | 6.92 | 15/12/2022 | 17/04/2023 | 1 | 4.81 | MVS
589 | BANKURA | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018926 | SM/16971 | Augmentation | 16/11/2022 | 176 | 607.96 | Yes | 607.96 | 08/01/2024 | 09/10/2023 | 9 | 249.95 | MVS
590 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | TSM/016262 | SM/16936 | Augmentation | 26/09/2022 | 1106 | 466.25 | Yes | 466.25 | 30/09/2024 | 09/08/2024 | 7 | 257.53 | MVS
591 | BANKURA | Bankura Division | Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | TSM/013112 | SM/16695 | New | 28/12/2022 | 319 | 196.01 | Yes | 196.01 | 30/07/2024 | 01/08/2023 | 9 | 210.69 | MVS
592 | BANKURA | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018907 | SM/16956 | Augmentation | 16/11/2022 | 968 | 629.42 | Yes | 632.16 | 12/03/2024 | 12/07/2024 | 13 | 157.08 | MVS
593 | BANKURA | Bankura Division | Gopalpur Piped Water Supply Scheme. | TSM/018122 | SM/16698 | New | 28/12/2022 | 2105 | 945.93 | Yes | 945.93 | 07/03/2025 | 14/08/2023 | 4 | 740.81 | MVS
594 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Bamania-113) of Betanal (Zone - B) under In | TSM/007423 | SM/09331 | Retrofitting | 10/02/2021 | 753 | 92.06 | Yes | 92.06 |  | 16/11/2021 | 1 | 63.93 | MVS
595 | BANKURA | Bankura Division | Manik Bazar Piped Water Supply Scheme. | TSM/018138 | SM/16705 | New | 28/12/2022 | 1258 | 565.3 | Yes | 565.3 | 22/02/2023 | 12/05/2023 | 3 | 61.38 | MVS
596 | BANKURA | Bankura Division | Augmentation of Amrul Zone-A Water Supply Scheme | TSM/019154 | SM/17229 | Augmentation | 16/11/2022 | 75 | 297.35 | Yes | 297.35 | 19/06/2024 | 18/07/2023 | 5 | 233.55 | MVS
597 | BANKURA | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). | TSM/018931 | SM/17245 | Augmentation | 16/11/2022 | 430 | 636.27 | Yes | 639.01 | 07/06/2024 | 19/07/2023 | 8 | 540.24 | MVS
598 | BANKURA | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | TSM/018932 | SM/17247 | Augmentation | 16/11/2022 | 1295 | 586.37 | Yes | 586.37 | 08/01/2024 | 14/08/2023 | 6 | 350.47 | MVS
599 | BANKURA | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018940 | SM/17249 | Augmentation | 16/11/2022 | 757 | 220.71 | Yes | 220.71 | 12/12/2024 | 10/06/2024 | 6 | 107.13 | MVS
600 | BANKURA | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | TSM/018955 | SM/17258 | Augmentation | 16/11/2022 | 260 | 364.06 | Yes | 367.1 | 30/09/2024 | 27/07/2023 | 7 | 236.92 | MVS
601 | BANKURA | Bankura Division | Adwaitabati Piped Water Supply Scheme | TSM/018268 | SM/16942 | New | 16/11/2022 | 1539 | 973.82 | Yes | 999.06 | 24/01/2025 | 12/03/2025 | 4 | 192.38 | MVS
602 | BANKURA | Bankura Division | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | TSM/018958 | SM/17700 | Augmentation | 16/11/2022 | 310 | 262.44 | Yes | 262.44 | 07/06/2024 | 11/04/2023 | 8 | 131.91 | MVS
603 | BANKURA | Bankura Division | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018947 | SM/17706 | Augmentation | 16/11/2022 | 275 | 246.08 | Yes | 255.52 | 16/04/2025 | 17/06/2025 | 4 | 162.53 | MVS
604 | BANKURA | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | TSM/018954 | SM/17710 | Augmentation | 16/11/2022 | 950 | 631.55 | Yes | 631.55 | 11/02/2025 | 25/04/2025 | 7 | 470.04 | MVS
605 | BANKURA | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018965 | SM/17712 | Augmentation | 16/11/2022 | 520 | 345.18 | Yes | 347.13 | 07/06/2024 | 18/07/2023 | 7 | 289.47 | MVS
606 | BANKURA | Bankura Division | Augmentation of Akui Zone-B Water Supply Scheme | TSM/019010 | SM/17228 | Augmentation | 16/11/2022 | 143 | 330.77 | Yes | 332.35 | 10/03/2025 | 13/07/2023 | 5 | 284.62 | MVS
607 | BANKURA | Bankura Division | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | TSM/017264 | SM/18036 | Augmentation | 28/12/2022 | 1120 | 799.22 | Yes | 799.22 | 14/06/2024 | 01/06/2023 | 8 | 697.5 | MVS
608 | BANKURA | Bankura Division | Augmentation of Somsar Water Supply Scheme | TSM/019134 | SM/17422 | Augmentation | 16/11/2022 | 85 | 152.16 | Yes | 152.16 | 14/06/2024 | 28/03/2023 | 5 | 141.14 | MVS
609 | BANKURA | Bankura Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | TSM/018452 | SM/18041 | New | 28/12/2022 | 1118 | 497.65 | Yes | 497.65 | 26/11/2024 | 31/08/2023 | 8 | 434.97 | MVS
610 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | TSM/008187 | SM/09472 | Retrofitting | 19/08/2021 | 2785 | 278.21 | Yes | 278.21 |  | 12/05/2022 | 6 | 516.78 | MVS
611 | BANKURA | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | TSM/019155 | SM/17297 | Augmentation | 16/11/2022 | 350 | 862.21 | Yes | 869.82 | 25/04/2025 | 12/07/2024 | 9 | 398.04 | MVS
612 | BANKURA | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018964 | SM/17280 | Augmentation | 16/11/2022 | 390 | 326.88 | Yes | 327.8 | 16/04/2025 | 27/07/2023 | 7 | 289.64 | MVS
613 | BANKURA | Bankura Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019225 | SM/17438 | Augmentation | 16/11/2022 | 245 | 818.04 | Yes | 824.28 | 16/01/2025 | 25/04/2025 | 11 | 473.45 | MVS
614 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | TSM/005928 | SM/07261 | Retrofitting | 25/09/2020 | 1033 | 83.44 | Yes | 83.44 |  | 10/02/2021 | 19 | 184.32 | MVS
615 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & J | TSM/005960 | SM/07327 | Retrofitting | 25/09/2020 | 926 | 66.26 | Yes | 66.26 |  | 17/06/2021 | 18 | 162.66 | MVS
616 | BANKURA | Bankura Division | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018941 | SM/17703 | Augmentation | 16/11/2022 | 850 | 248.23 | Yes | 248.23 | 16/04/2025 | 11/09/2023 | 4 | 104.03 | MVS
617 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUDARSHANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012397 | SM/10940 | New | 20/05/2022 | 141 | 41.89 | Yes | 41.89 |  | 12/03/2024 | 1 | 0.12 | MVS
618 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Ekteswar (Part, 70%) & Sankarhati) of pipe water supply scheme for E | TSM/007478 | SM/09310 | Retrofitting | 19/02/2021 | 452 | 32.92 | Yes | 32.92 |  | 12/11/2021 | 11 | 71.44 | MVS
619 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Akargarya, House Hold No.: 94) | TSM/012245 | SM/11158 | New | 20/05/2022 | 94 | 39.69 | Yes | 39.69 |  | 02/02/2023 | 2 | 0.14 | MVS
620 | BANKURA | Bankura Division | Panahar Piped Water Supply Scheme | TSM/018129 | SM/18790 | New | 16/11/2022 | 2586 | 1324.42 | Yes | 1324.42 | 29/11/2024 | 04/10/2023 | 7 | 1147.93 | MVS
621 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAERBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012500 | SM/10968 | New | 20/05/2022 | 55 | 38.13 | Yes | 38.13 |  |  | 0 | 0 | MVS
622 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Mach Doba, Household-67) | TSM/012095 | SM/11419 | New | 20/05/2022 | 67 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
623 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JASHODANANDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012366 | SM/11047 | New | 20/05/2022 | 99 | 45.01 | Yes | 45.01 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
624 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Barakura, House Hold No.: 61) | TSM/012144 | SM/11687 | New | 20/05/2022 | 61 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
625 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas | TSM/005753 | SM/06800 | Retrofitting | 28/08/2020 | 697 | 60.74 | Yes | 60.74 |  | 18/01/2021 | 13 | 179.17 | MVS
626 | BANKURA | Bankura Division | Dhulai Piped Water Supply Scheme. | TSM/018195 | SM/18753 | New | 16/11/2022 | 3401 | 1452.39 | Yes | 1452.39 | 25/04/2025 | 04/10/2023 | 7 | 1200.78 | MVS
627 | BANKURA | Bankura Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018924 | SM/16970 | Augmentation | 16/11/2022 | 500 | 488.77 | Yes | 488.77 | 04/03/2024 | 13/07/2023 | 7 | 233.84 | MVS
628 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Ladna, Mathana, Kodalia) of Joytunga (Zone - H) under Banku | TSM/005999 | SM/07312 | Retrofitting | 25/09/2020 | 859 | 85.93 | Yes | 85.93 | 04/01/2023 | 29/12/2020 | 11 | 126.92 | MVS
629 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Nangla, Agaya, Gidhuria, Pachasimul, Mechabaid, Banjurya, Har | TSM/005971 | SM/07253 | Retrofitting | 25/09/2020 | 872 | 90.95 | Yes | 90.95 | 13/01/2023 | 27/07/2021 | 15 | 162.95 | MVS
630 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Dakaisini, Khandari, Bansol, Dhwajmonipur & Damodarpur) of | TSM/005927 | SM/07260 | Retrofitting | 25/09/2020 | 959 | 89.89 | Yes | 89.89 | 01/11/2022 | 19/02/2021 | 12 | 166.9 | MVS
631 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | TSM/005941 | SM/07320 | Retrofitting | 25/09/2020 | 990 | 77.52 | Yes | 77.52 | 16/11/2022 | 25/08/2021 | 7 | 178.28 | MVS
632 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Khejurbedia, Upardihi, Rad | TSM/005737 | SM/06809 | Retrofitting | 28/08/2020 | 1008 | 99.97 | Yes | 99.97 |  | 09/12/2020 | 5 | 149.64 | MVS
633 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-H | TSM/005894 | SM/07355 | Retrofitting | 25/09/2020 | 716 | 61.82 | Yes | 61.82 |  | 27/07/2022 | 24 | 79.11 | MVS
634 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | TSM/005937 | SM/07340 | Retrofitting | 25/09/2020 | 1104 | 88.31 | Yes | 88.31 | 19/04/2023 | 28/04/2023 | 7 | 138.74 | MVS
635 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | TSM/005739 | SM/06816 | Retrofitting | 28/08/2020 | 870 | 80.94 | Yes | 80.94 |  | 09/12/2020 | 10 | 95.24 | MVS
636 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Mobarakpur, Chaptara, Send | TSM/005731 | SM/06803 | Retrofitting | 28/08/2020 | 49304 | 94.04 | Yes | 94.04 |  | 09/12/2020 | 8 | 199.46 | MVS
637 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Taldanga, Upar Narrah, Khe | TSM/005733 | SM/06806 | Retrofitting | 28/08/2020 | 1057 | 78.26 | Yes | 78.26 |  | 05/02/2021 | 11 | 203.97 | MVS
638 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Dhobagram, Chila bakra, Na | TSM/005933 | SM/07347 | Retrofitting | 25/09/2020 | 1055 | 93.49 | Yes | 93.49 |  | 10/02/2021 | 2 | 96.54 | MVS
639 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha | TSM/005935 | SM/07349 | Retrofitting | 25/09/2020 | 1050 | 95.93 | Yes | 95.93 |  | 04/02/2021 | 4 | 107.9 | MVS
640 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Sc | TSM/005910 | SM/07333 | Retrofitting | 25/09/2020 | 664 | 61.29 | Yes | 61.29 |  | 18/01/2021 | 3 | 53.41 | MVS
641 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 nos. Mouzas (Kastara, Rangamati, Kendana, Sat-deuli) of pipe water supply sc | TSM/007479 | SM/09311 | Retrofitting | 19/02/2021 | 38 | 26.8 | Yes | 55.5 | 19/07/2023 | 12/11/2021 | 17 | 107.58 | MVS
642 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | TSM/007481 | SM/09314 | Retrofitting | 19/02/2021 | 1633 | 169.28 | Yes | 169.28 | 19/07/2023 | 06/06/2022 | 17 | 194.7 | MVS
643 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | TSM/007280 | SM/09227 | Retrofitting | 10/02/2021 | 327 | 44.32 | Yes | 51.96 |  | 23/09/2021 | 9 | 88.62 | MVS
644 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | TSM/007289 | SM/09228 | Retrofitting | 10/02/2021 | 2415 | 255.23 | Yes | 255.23 | 13/12/2023 | 12/05/2022 | 3 | 488.76 | MVS
645 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | TSM/008194 | SM/09497 | Retrofitting | 19/08/2021 | 3319 | 272.39 | Yes | 272.39 | 05/12/2023 | 03/01/2022 | 5 | 184.3 | MVS
646 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benjtabani (51), Benrebati (52), Tilbari (53), Sarasbakra (55), Pukhuria (56), Birsingpur (57), Bikrampur (58), Krishnapur (59), Kathjuria (60), Nuniabad (61), Harintuli (62) | TSM/008983 | SM/09551 | Retrofitting | 08/10/2021 | 3109 | 264.94 | Yes | 264.94 |  | 25/07/2022 | 5 | 165.54 | MVS
647 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jhumka (156) Nutangram (157), Ghaghrakhulia (169), Ekaria Jambani (170), Krishnabati (171), Chandpur (172), Putiadaha (173), Pithabakra (174), Bagnada (175) & Nekratapal (176 | TSM/008989 | SM/09554 | Retrofitting | 08/10/2021 | 1257 | 110.71 | Yes | 112.59 |  | 13/12/2021 | 2 | 81.61 | MVS
648 | BANKURA | Bankura Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Bl | TSM/007461 | SM/09633 | Retrofitting | 19/02/2021 | 1657 | 295.14 | Yes | 295.14 |  | 10/05/2022 | 3 | 373.02 | MVS
649 | BANKURA | Bankura Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora B | TSM/007462 | SM/09634 | Retrofitting | 19/02/2021 | 1650 | 294.27 | Yes | 294.27 | 29/04/2025 | 14/01/2022 | 1 | 0.55 | MVS
650 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | TSM/008189 | SM/09474 | Retrofitting | 19/08/2021 | 1927 | 208.88 | Yes | 208.88 | 30/09/2021 | 19/04/2022 | 2 | 196.35 | MVS
651 | BANKURA | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | TSM/008992 | SM/09454 | Augmentation | 08/10/2021 | 1564 | 493.81 | Yes | 510.5 | 29/02/2024 | 03/11/2023 | 22 | 509.85 | MVS
652 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply s | TSM/007477 | SM/09309 | Retrofitting | 19/02/2021 | 245 | 36.21 | Yes | 36.21 |  | 12/11/2021 | 7 | 147.16 | MVS
653 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Su | TSM/008619 | SM/09524 | Retrofitting | 08/09/2021 | 1759 | 142.09 | Yes | 142.09 |  | 31/12/2021 | 3 | 86.85 | MVS
654 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHALAIDIHA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012480 | SM/10948 | New | 20/05/2022 | 25 | 31.76 | Yes | 31.76 | 18/02/2025 | 15/05/2023 | 1 | 0.12 | MVS
655 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Nabagram, Vidyadharpur, Ai | TSM/005730 | SM/06804 | Retrofitting | 28/08/2020 | 1209 | 92.61 | Yes | 92.61 |  | 08/10/2020 | 5 | 172.98 | MVS
656 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | TSM/005752 | SM/06790 | Retrofitting | 28/08/2020 | 1015 | 86.99 | Yes | 86.99 |  | 09/10/2020 | 14 | 202.92 | MVS
657 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SIROMANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012473 | SM/10991 | New | 20/05/2022 | 91 | 43.45 | Yes | 43.45 |  |  | 0 | 0 | MVS
658 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BIRBHANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012299 | SM/11111 | New | 20/05/2022 | 53 | 37.66 | Yes | 37.66 |  | 04/08/2023 | 1 | 0.11 | MVS
659 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUDRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012380 | SM/10923 | New | 20/05/2022 | 358 | 37.46 | Yes | 37.46 |  |  | 0 | 0 | MVS
660 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMALA DIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012383 | SM/10926 | New | 20/05/2022 | 246 | 33.64 | Yes | 33.64 |  | 13/09/2024 | 1 | 0.12 | MVS
661 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR ATARYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012386 | SM/10929 | New | 20/05/2022 | 324 | 35.21 | Yes | 35.21 |  |  | 0 | 0 | MVS
662 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUSUM KHUNDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012302 | SM/11114 | New | 20/05/2022 | 84 | 42.08 | Yes | 42.08 |  | 23/04/2024 | 1 | 0.12 | MVS
663 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR LACHHIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012280 | SM/11017 | New | 20/05/2022 | 92 | 43.65 | Yes | 43.65 |  | 07/06/2023 | 1 | 0.12 | MVS
664 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHADLI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012287 | SM/11024 | New | 20/05/2022 | 86 | 42.47 | Yes | 42.47 |  | 10/11/2023 | 1 | 0.12 | MVS
665 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALI BANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012343 | SM/11080 | New | 20/05/2022 | 28 | 32.56 | Yes | 32.56 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
666 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MAHISHAKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012346 | SM/11083 | New | 20/05/2022 | 28 | 32.56 | Yes | 32.56 | 24/12/2021 |  | 0 | 0 | MVS
667 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BENATHOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME+B20:B21 | TSM/012496 | SM/10964 | New | 20/05/2022 | 355 | 43.45 | Yes | 43.45 |  |  | 0 | 0 | MVS
668 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR ASNASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012364 | SM/11045 | New | 20/05/2022 | 91 | 43.45 | Yes | 43.45 | 24/12/2021 | 23/04/2024 | 2 | 1.02 | MVS
669 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NABAGRAM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012371 | SM/11052 | New | 20/05/2022 | 77 | 40.72 | Yes | 40.72 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
670 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012148 | SM/10909 | New | 20/05/2022 | 310 | 42.28 | Yes | 42.28 |  | 26/04/2024 | 2 | 0.35 | MVS
671 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMNISHALA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012315 | SM/11127 | New | 20/05/2022 | 66 | 40.68 | Yes | 40.68 |  | 19/09/2023 | 1 | 0.12 | MVS
672 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHINGRAGOALASOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012152 | SM/10910 | New | 20/05/2022 | 84 | 32.83 | Yes | 32.83 |  |  | 0 | 0 | MVS
673 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dharapat, House Hold No.: 65) | TSM/012109 | SM/11087 | New | 20/05/2022 | 65 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 1 | 0.12 | MVS
674 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Fatepur, House Hold:88) | TSM/012269 | SM/11134 | New | 20/05/2022 | 451 | 39.69 | Yes | 39.69 | 24/12/2021 | 02/02/2023 | 1 | 0.12 | MVS
675 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR UPARGERYAKULA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012456 | SM/10974 | New | 20/05/2022 | 62 | 39.75 | Yes | 39.75 |  | 04/04/2024 | 1 | 0.12 | MVS
676 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUKNABAD VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012331 | SM/11068 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 | 24/12/2021 | 22/05/2024 | 1 | 0.24 | MVS
677 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SALUKDANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012463 | SM/10981 | New | 20/05/2022 | 56 | 38.36 | Yes | 38.36 |  |  | 0 | 0 | MVS
678 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chandipur, House Hold No.: 97) | TSM/012261 | SM/11142 | New | 20/05/2022 | 725 | 39.69 | Yes | 39.69 | 24/12/2021 |  | 0 | 0 | MVS
679 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Baragopinathpur, House Hold No.: 90) | TSM/012257 | SM/11146 | New | 20/05/2022 | 90 | 39.69 | Yes | 39.69 |  | 02/02/2023 | 2 | 0.14 | MVS
680 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Lalgara, House Hold No.: 34) | TSM/012081 | SM/11103 | New | 20/05/2022 | 194 | 38.5 | Yes | 38.5 |  |  | 0 | 0 | MVS
681 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAMSHALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012411 | SM/10854 | New | 20/05/2022 | 193 | 41.6 | Yes | 41.6 |  | 16/05/2024 | 1 | 0.23 | MVS
682 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012413 | SM/10856 | New | 20/05/2022 | 23 | 31.22 | Yes | 31.22 |  | 16/05/2024 | 2 | 0.35 | MVS
683 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHINASANBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012419 | SM/10862 | New | 20/05/2022 | 134 | 34.46 | Yes | 34.46 |  |  | 0 | 0 | MVS
684 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALACHANDPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012420 | SM/10863 | New | 20/05/2022 | 34 | 34.18 | Yes | 34.18 |  | 15/03/2023 | 1 | 0.12 | MVS
685 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Radhanagar, House Hold No.: 97) | TSM/012242 | SM/11171 | New | 20/05/2022 | 97 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 2 | 0.14 | MVS
686 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAPKATA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012426 | SM/10869 | New | 20/05/2022 | 887 | 36.46 | Yes | 36.46 |  |  | 0 | 0 | MVS
687 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Hajipur, House Hold No.: 87) | TSM/012232 | SM/11177 | New | 20/05/2022 | 87 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
688 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nutangram, House Hold No.: 81) | TSM/012223 | SM/11182 | New | 20/05/2022 | 501 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
689 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHARADIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012404 | SM/10847 | New | 20/05/2022 | 276 | 41.3 | Yes | 41.3 |  |  | 0 | 0 | MVS
690 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BENAGERIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012436 | SM/10879 | New | 20/05/2022 | 30 | 33.1 | Yes | 33.1 |  | 04/04/2024 | 1 | 0.12 | MVS
691 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHOBAGERE VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012437 | SM/10880 | New | 20/05/2022 | 262 | 36.46 | Yes | 36.46 |  |  | 0 | 0 | MVS
692 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANAIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012349 | SM/11201 | New | 20/05/2022 | 59 | 39.05 | Yes | 39.05 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
693 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUKUTIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012350 | SM/11202 | New | 20/05/2022 | 61 | 39.52 | Yes | 39.52 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
694 | BANKURA | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | TSM/011432 | SM/12380 | Augmentation | 22/08/2022 | 1259 | 664.39 | Yes | 664.39 | 25/04/2025 | 22/05/2023 | 9 | 630.31 | MVS
695 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Shalkota, House Hold:75) | TSM/012212 | SM/11441 | New | 20/05/2022 | 126 | 38.91 | Yes | 38.91 |  |  | 0 | 0 | MVS
696 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Adhakata, House Hold No.: 51) | TSM/012141 | SM/11688 | New | 20/05/2022 | 51 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
697 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Mohishkhoar, House Hold No.: 78) | TSM/012130 | SM/11691 | New | 20/05/2022 | 78 | 39.88 | Yes | 39.88 |  | 11/01/2023 | 0 | 0.12 | MVS
698 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TIKARPARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012211 | SM/13273 | New | 20/05/2022 | 82 | 34.21 | Yes | 34.21 | 24/12/2021 |  | 0 | 0 | MVS
699 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHAK KRISHNASINGHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012154 | SM/13258 | New | 20/05/2022 | 213 | 42.51 | Yes | 42.51 |  |  | 0 | 0 | MVS
700 | BANKURA | Bankura Division | Pathara Piped Water Supply Scheme | TSM/015700 | SM/14009 | New | 26/09/2022 | 721 | 510.54 | Yes | 510.54 | 14/12/2022 | 06/01/2023 | 4 | 79.2 | MVS
701 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | TSM/011369 | SM/14126 | Retrofitting | 25/04/2022 | 7983 | 551.14 | Yes | 551.14 | 12/02/2025 | 20/04/2023 | 7 | 512.11 | MVS
702 | BANKURA | Bankura Division | Dhula Danga Piped Water Supply Scheme | TSM/014770 | SM/14176 | New | 09/09/2022 | 2331 | 1163.2 | Yes | 1163.2 | 12/03/2025 | 27/09/2024 | 4 | 90.56 | MVS
703 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Beliatore PWSS scheme, Dist- Bankura | TSM/018667 | SM/15311 | Solarisation | 16/11/2022 | 0 | 21.98 | Yes | 21.98 | 29/12/2022 | 19/09/2024 | 3 | 15.83 | MVS
704 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Laxmisagar PWSS scheme Dist Bankura | TSM/018678 | SM/15315 | Solarisation | 16/11/2022 | 0 | 6.8 | Yes | 6.8 | 29/12/2022 | 25/07/2024 | 2 | 4.74 | MVS
705 | BANKURA | Bankura Division | Rautara Piped Water Supply Scheme | TSM/014579 | SM/14521 | New | 22/08/2022 | 2019 | 1022.54 | Yes | 1022.54 | 31/01/2025 | 06/01/2023 | 2 | 168.28 | MVS
706 | BANKURA | Bankura Division | Pratappur Piped Water Supply Scheme. | TSM/015766 | SM/15019 | New | 26/09/2022 | 1828 | 963.17 | Yes | 963.17 | 12/03/2025 | 28/11/2024 | 5 | 122.56 | MVS
707 | BANKURA | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018927 | SM/16972 | Augmentation | 16/11/2022 | 100 | 601.7 | Yes | 601.7 | 30/01/2025 | 11/04/2023 | 12 | 400.74 | MVS
708 | BANKURA | Bankura Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018918 | SM/16964 | Augmentation | 16/11/2022 | 748 | 694.01 | Yes | 694.01 | 31/01/2025 | 10/06/2024 | 8 | 308.18 | MVS
709 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | TSM/019126 | SM/16951 | Augmentation | 16/11/2022 | 180 | 110.96 | Yes | 110.96 | 08/01/2024 | 03/10/2023 | 3 | 34.48 | MVS
710 | BANKURA | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | TSM/013114 | SM/16696 | New | 28/12/2022 | 1459 | 621.66 | Yes | 621.66 | 22/01/2025 | 01/08/2023 | 8 | 530.77 | MVS
711 | BANKURA | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | TSM/013115 | SM/16697 | New | 28/12/2022 | 1277 | 598.58 | Yes | 598.58 | 30/07/2024 | 12/07/2024 | 9 | 512.25 | MVS
712 | BANKURA | Bankura Division | Bhubut Piped Water Supply Scheme | TSM/018244 | SM/16700 | New | 28/12/2022 | 1153 | 518.29 | Yes | 518.29 | 05/02/2024 | 26/10/2023 | 3 | 422.64 | MVS
713 | BANKURA | Bankura Division | Augmentation of Morar Zone-A Water Supply Scheme | TSM/019174 | SM/17237 | Augmentation | 16/11/2022 | 404 | 420.31 | Yes | 420.31 | 10/03/2025 | 24/07/2023 | 6 | 374.06 | MVS
714 | BANKURA | Bankura Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018928 | SM/17242 | Augmentation | 16/11/2022 | 100 | 503.31 | Yes | 503.31 | 14/06/2024 | 08/06/2023 | 8 | 241.76 | MVS
715 | BANKURA | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | TSM/018935 | SM/17248 | Augmentation | 16/11/2022 | 265 | 377.71 | Yes | 394.85 | 16/04/2025 | 17/06/2025 | 14 | 252.5 | MVS
716 | BANKURA | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018952 | SM/17708 | Augmentation | 16/11/2022 | 270 | 407.23 | Yes | 408.45 | 06/05/2025 | 03/04/2025 | 6 | 232.23 | MVS
717 | BANKURA | Bankura Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | TSM/018000 | SM/18038 | New | 28/12/2022 | 474 | 224.65 | Yes | 224.65 | 29/04/2025 | 17/06/2025 | 7 | 200.03 | MVS
718 | BANKURA | Bankura Division | Augmentation of Dhengasole Water Supply Scheme | TSM/019178 | SM/17699 | Augmentation | 16/11/2022 | 448 | 323.64 | Yes | 323.64 | 30/01/2025 | 24/07/2023 | 4 | 221.01 | MVS
719 | BANKURA | Bankura Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | TSM/019239 | SM/18044 | New | 28/12/2022 | 564 | 379.09 | Yes | 379.09 | 07/11/2023 | 27/07/2023 | 6 | 336.14 | MVS
720 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019183 | SM/17302 | Augmentation | 16/11/2022 | 305 | 955.07 | Yes | 966.49 | 25/04/2025 | 14/08/2023 | 13 | 774.13 | MVS
721 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I) (Part-B) | TSM/006013 | SM/07368 | Retrofitting | 25/09/2020 | 945 | 86.28 | Yes | 86.28 | 10/08/2022 | 18/08/2021 | 7 | 45.2 | MVS
722 | BANKURA | Bankura Division | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | TSM/018959 | SM/18119 | Augmentation | 16/11/2022 | 520 | 385.27 | Yes | 387.1 | 13/07/2023 | 27/07/2023 | 4 | 235.98 | MVS
723 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | TSM/019125 | SM/17441 | Augmentation | 16/11/2022 | 367 | 226.57 | Yes | 226.63 | 10/03/2025 | 11/07/2024 | 6 | 188.57 | MVS
724 | BANKURA | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018968 | SM/17284 | Augmentation | 16/11/2022 | 505 | 555.78 | Yes | 555.78 | 13/02/2023 | 02/06/2023 | 7 | 385.38 | MVS
725 | BANKURA | Bankura Division | Danna Piped Water Supply Scheme. | TSM/015928 | SM/18302 | New | 26/09/2022 | 3100 | 1305.29 | Yes | 1305.29 | 31/01/2025 | 14/08/2023 | 7 | 1039.07 | MVS
726 | BANKURA | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018967 | SM/17282 | Augmentation | 16/11/2022 | 797 | 551.35 | Yes | 551.35 | 16/04/2025 | 25/04/2025 | 8 | 344.13 | MVS
727 | BANKURA | Bankura Division | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | TSM/019240 | SM/18612 | Augmentation | 28/12/2022 | 0 | 5127.01 | Yes | 5127.01 | 12/02/2025 | 04/10/2023 | 6 | 5325.38 | MVS
728 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUSHUNIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012353 | SM/11034 | New | 20/05/2022 | 25 | 31.76 | Yes | 31.76 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
729 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHAK RANGA METYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012378 | SM/10921 | New | 20/05/2022 | 62 | 32.03 | Yes | 32.03 |  | 13/09/2024 | 1 | 0.12 | MVS
730 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BRINDABANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012387 | SM/10930 | New | 20/05/2022 | 163 | 32.83 | Yes | 32.83 |  |  | 0 | 0 | MVS
731 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Durgabati, House Hold No.: 20) | TSM/012202 | SM/11192 | New | 20/05/2022 | 565 | 38.64 | Yes | 38.64 |  | 02/02/2023 | 1 | 0.12 | MVS
732 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DANGARSAI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012288 | SM/11025 | New | 20/05/2022 | 96 | 44.43 | Yes | 44.43 |  | 07/06/2023 | 1 | 0.12 | MVS
733 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) | TSM/006021 | SM/07373 | Retrofitting | 25/09/2020 | 1284 | 96.11 | Yes | 96.11 |  | 11/04/2022 | 2 | 24.12 | MVS
734 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KENDBANADHAGRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012421 | SM/10864 | New | 20/05/2022 | 32 | 33.64 | Yes | 33.64 |  | 15/03/2023 | 2 | 0.14 | MVS
735 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NIYASA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012433 | SM/10876 | New | 20/05/2022 | 46 | 36.71 | Yes | 36.71 |  | 15/03/2023 | 1 | 0.12 | MVS
736 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHUAKAKI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012358 | SM/11039 | New | 20/05/2022 | 80 | 41.3 | Yes | 41.3 | 24/12/2021 | 03/07/2024 | 1 | 0.12 | MVS
737 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMUN PATHRI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012333 | SM/11070 | New | 20/05/2022 | 86 | 42.47 | Yes | 42.47 | 24/12/2021 | 22/05/2024 | 2 | 0.24 | MVS
738 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AULIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012336 | SM/11073 | New | 20/05/2022 | 37 | 34.46 | Yes | 34.46 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
739 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamda (38), Tilabani (39), Jhikri (40), Kusumkanali (41) , Baurisol (42) and Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its | TSM/005758 | SM/06795 | Retrofitting | 28/08/2020 | 1090 | 88.07 | Yes | 88.07 |  | 12/02/2021 | 12 | 233.74 | MVS
740 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | TSM/016254 | SM/18495 | Augmentation | 26/09/2022 | 3991 | 1126 | Yes | 1126 | 25/04/2025 | 17/06/2025 | 7 | 829.99 | MVS
741 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhanga Bandh (91), Bheduasol (92), Kamalpur (93), Sayer Bankra (99), Kotalpur (100), Ramnagar (101), Dhabani (102), Manipur (105), Guinandi (106), Itapanchira (107), Paharpur | TSM/008575 | SM/09480 | Retrofitting | 08/09/2021 | 2309 | 207.69 | Yes | 207.69 |  | 21/04/2022 | 7 | 152.53 | MVS
742 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Rangametya, Kuladabar, Burat, Deulberia, Murgathol, Ampahari, | TSM/006008 | SM/07311 | Retrofitting | 25/09/2020 | 1181 | 88.11 | Yes | 88.11 |  | 05/02/2021 | 7 | 113.44 | MVS
743 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) | TSM/006014 | SM/07271 | Retrofitting | 25/09/2020 | 1029 | 96.39 | Yes | 96.39 |  | 10/02/2021 | 7 | 441.74 | MVS
744 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kalipur, Housibad, Parulia, Biskodar, Joljolia Banshal) of K | TSM/005921 | SM/07254 | Retrofitting | 25/09/2020 | 873 | 74.43 | Yes | 74.43 |  | 05/02/2021 | 1 | 36.37 | MVS
745 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Arjunda (65), Tirsulia (66), Barkania (69), Dhairapara (70), Jamdahara (71), Tilabani (72), Dhanga Dungri (74), Mirgi (75), Basudebpur (79), Jhat Pukhuria (80) & Patasimul (1 | TSM/005916 | SM/07367 | Retrofitting | 25/09/2020 | 1201 | 99.39 | Yes | 99.39 |  | 27/07/2022 | 7 | 97.42 | MVS
746 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | TSM/005996 | SM/07237 | Retrofitting | 25/09/2020 | 1033 | 75.94 | Yes | 75.94 |  | 10/02/2021 | 10 | 163.77 | MVS
747 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap | TSM/005985 | SM/07244 | Retrofitting | 25/09/2020 | 806 | 77.31 | Yes | 77.31 | 16/12/2022 | 23/02/2023 | 3 | 48.93 | MVS
748 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | TSM/005994 | SM/07315 | Retrofitting | 25/09/2020 | 932 | 98.56 | Yes | 98.56 | 16/12/2022 | 14/04/2022 | 18 | 48.42 | MVS
749 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahirdya, Fulkusma, Jambede, Nabagram)of Nabagram (Zon - K) unde | TSM/005942 | SM/07321 | Retrofitting | 25/09/2020 | 802 | 97.45 | Yes | 97.45 |  | 25/08/2021 | 1 | 112.13 | MVS
750 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouza (Talanda, Cahndanpur, Swargabati, Harishpur, Gopinathpur, Brinda | TSM/005930 | SM/07345 | Retrofitting | 25/09/2020 | 1056 | 85.97 | Yes | 85.97 |  | 29/07/2022 | 10 | 123.2 | MVS
751 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | TSM/005932 | SM/07346 | Retrofitting | 25/09/2020 | 1056 | 99.61 | Yes | 99.61 | 04/01/2023 | 19/02/2021 | 9 | 137.65 | MVS
752 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | TSM/006010 | SM/07350 | Retrofitting | 25/09/2020 | 816 | 58.68 | Yes | 58.68 |  | 23/11/2021 | 2 | 15.23 | MVS
753 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | TSM/005741 | SM/06814 | Retrofitting | 28/08/2020 | 1212 | 86.25 | Yes | 86.25 |  | 06/06/2022 | 9 | 136.11 | MVS
754 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | TSM/005954 | SM/07323 | Retrofitting | 25/09/2020 | 751 | 88.26 | Yes | 89.87 |  | 10/02/2021 | 7 | 156.84 | MVS
755 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Brindajam, Kaminbedia, Sihikapahari, Hatjore, Simulbedia, Moy | TSM/005958 | SM/07325 | Retrofitting | 25/09/2020 | 1108 | 88.06 | Yes | 88.06 |  | 09/07/2021 | 14 | 120.04 | MVS
756 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Chhendua, Chamkara, Fengab | TSM/005963 | SM/07343 | Retrofitting | 25/09/2020 | 994 | 99.07 | Yes | 99.07 |  | 19/01/2021 | 9 | 157.22 | MVS
757 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | TSM/005732 | SM/06802 | Retrofitting | 28/08/2020 | 1209 | 94.88 | Yes | 94.88 | 05/01/2023 | 08/10/2020 | 18 | 208.3 | MVS
758 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Patna Joykrishnapur, Kunja | TSM/005734 | SM/06805 | Retrofitting | 28/08/2020 | 1056 | 78.14 | Yes | 78.14 | 08/01/2024 | 10/02/2021 | 8 | 198.42 | MVS
759 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos mousas (Helna, Fagua kanali, Dumur | TSM/005934 | SM/07348 | Retrofitting | 25/09/2020 | 1018 | 92.5 | Yes | 93.87 |  | 10/02/2021 | 5 | 107.66 | MVS
760 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Banki-85, Chotogobindapur-86, Adilpur-87 & | TSM/007472 | SM/09325 | Retrofitting | 19/02/2021 | 2639 | 226.6 | Yes | 226.6 |  | 30/12/2021 | 4 | 255.7 | MVS
761 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B a | TSM/007311 | SM/09232 | Retrofitting | 10/02/2021 | 930 | 82.52 | Yes | 82.52 |  | 08/11/2021 | 10 | 78.49 | MVS
762 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | TSM/007413 | SM/09644 | Retrofitting | 10/02/2021 | 589 | 91.21 | Yes | 92.7 |  | 29/11/2021 | 7 | 108.67 | MVS
763 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Gangabati-32, Maurui-33, Bhagabanbati-34, Nu | TSM/007469 | SM/09628 | Retrofitting | 19/02/2021 | 2627 | 241.81 | Yes | 241.81 |  | 15/12/2021 | 7 | 374.52 | MVS
764 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | TSM/008569 | SM/09479 | Retrofitting | 08/09/2021 | 2267 | 181.27 | Yes | 181.27 | 16/02/2023 | 11/04/2023 | 4 | 140.4 | MVS
765 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina | TSM/008583 | SM/09521 | Retrofitting | 08/09/2021 | 1510 | 135.75 | Yes | 135.75 |  | 31/12/2021 | 3 | 85.01 | MVS
766 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retr | TSM/008597 | SM/09523 | Retrofitting | 08/09/2021 | 1422 | 137.57 | Yes | 137.57 | 14/05/2025 | 03/03/2022 | 3 | 98.84 | MVS
767 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | TSM/005944 | SM/07322 | Retrofitting | 25/09/2020 | 995 | 78.19 | Yes | 78.19 |  | 10/02/2021 | 7 | 99.98 | MVS
768 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Somsar (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos Mouza Bhagabatipur - 01, Palashdanga - 03, Kumna - 04 of | TSM/009450 | SM/10041 | Retrofitting | 16/12/2021 | 663 | 83.4 | Yes | 83.4 | 17/02/2023 | 02/06/2023 | 3 | 81.09 | MVS
769 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | TSM/008338 | SM/10292 | Augmentation | 19/08/2021 | 5831 | 3658.45 | Yes | 3658.45 | 15/01/2025 | 28/07/2022 | 28 | 1940.84 | MVS
770 | BANKURA | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | TSM/008341 | SM/10294 | Augmentation | 19/08/2021 | 3489 | 1011.34 | Yes | 1011.34 | 14/06/2024 | 28/08/2024 | 14 | 864.15 | MVS
771 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHATRABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012466 | SM/10984 | New | 20/05/2022 | 67 | 40.91 | Yes | 40.91 |  | 07/09/2023 | 1 | 0.12 | MVS
772 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MAKARKENDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012115 | SM/10900 | New | 20/05/2022 | 40 | 35.21 | Yes | 35.21 |  | 15/03/2023 | 0 | 0.12 | MVS
773 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Rohimchak, House Hold No.: 78) | TSM/012255 | SM/11148 | New | 20/05/2022 | 315 | 36.13 | Yes | 39.69 |  | 02/02/2023 | 2 | 0.24 | MVS
774 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Pal Puskarini, House Hold No.: 79) | TSM/012253 | SM/11150 | New | 20/05/2022 | 620 | 39.69 | Yes | 39.69 |  | 15/03/2023 | 1 | 0.12 | MVS
775 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR HARIDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012171 | SM/10919 | New | 20/05/2022 | 135 | 39.29 | Yes | 39.29 |  | 20/03/2024 | 1 | 0.13 | MVS
776 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Haldar Chak, House Hold No.: 40) | TSM/012075 | SM/11107 | New | 20/05/2022 | 156 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 1 | 0.12 | MVS
777 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NARAYANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012381 | SM/10924 | New | 20/05/2022 | 1128 | 32.3 | Yes | 32.3 |  |  | 0 | 0 | MVS
778 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PANKUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012388 | SM/10931 | New | 20/05/2022 | 441 | 34.96 | Yes | 34.96 |  | 13/09/2024 | 1 | 0.12 | MVS
779 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GUMKIHATA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012274 | SM/11011 | New | 20/05/2022 | 78 | 40.91 | Yes | 40.91 |  |  | 0 | 0 | MVS
780 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHALPARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012278 | SM/11015 | New | 20/05/2022 | 64 | 40.21 | Yes | 40.21 |  |  | 0 | 0 | MVS
781 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BENAKANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012490 | SM/10958 | New | 20/05/2022 | 44 | 36.21 | Yes | 36.21 |  |  | 0 | 0 | MVS
782 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BHULUI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012491 | SM/10959 | New | 20/05/2022 | 628 | 36.71 | Yes | 36.71 |  |  | 0 | 0 | MVS
783 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GHOLKURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012294 | SM/11031 | New | 20/05/2022 | 46 | 36.71 | Yes | 36.71 |  | 04/08/2023 | 1 | 0.11 | MVS
784 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kendgara, House Hold:27) | TSM/012251 | SM/11152 | New | 20/05/2022 | 225 | 39.69 | Yes | 39.69 |  | 26/06/2023 | 2 | 0.55 | MVS
785 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Enayet Chak, House Hold No.: 85) | TSM/012248 | SM/11155 | New | 20/05/2022 | 85 | 39.69 | Yes | 39.69 |  | 02/02/2023 | 2 | 0.14 | MVS
786 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012361 | SM/11042 | New | 20/05/2022 | 60 | 39.29 | Yes | 39.29 | 24/12/2021 | 15/06/2023 | 0 | 0.12 | MVS
787 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GHAGAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012369 | SM/11050 | New | 20/05/2022 | 77 | 40.72 | Yes | 40.72 | 24/12/2021 | 23/04/2024 | 1 | 0.12 | MVS
788 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALARAMPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012372 | SM/11053 | New | 20/05/2022 | 59 | 39.05 | Yes | 39.05 | 24/12/2021 | 03/07/2024 | 1 | 0.12 | MVS
789 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BRAHMANDHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012374 | SM/11055 | New | 20/05/2022 | 70 | 41.6 | Yes | 41.6 | 24/12/2021 | 16/06/2023 | 0 | 0.12 | MVS
790 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PAHARBERA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012314 | SM/11126 | New | 20/05/2022 | 925 | 44.04 | Yes | 44.04 |  | 07/09/2023 | 1 | 0.12 | MVS
791 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012317 | SM/11129 | New | 20/05/2022 | 44 | 36.21 | Yes | 36.21 | 18/02/2025 | 29/05/2024 | 3 | 0.68 | MVS
792 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NADUSENARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012447 | SM/10890 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 |  | 04/04/2024 | 1 | 0.12 | MVS
793 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SONAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012330 | SM/11067 | New | 20/05/2022 | 88 | 42.86 | Yes | 42.86 | 24/12/2021 |  | 0 | 0 | MVS
794 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TAPUBAID VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012332 | SM/11069 | New | 20/05/2022 | 92 | 43.65 | Yes | 43.65 | 24/12/2021 |  | 0 | 0 | MVS
795 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RENGURBANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012334 | SM/11071 | New | 20/05/2022 | 128 | 39.98 | Yes | 39.98 | 24/12/2021 |  | 0 | 0 | MVS
796 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Ram Bakhra, House Hold No.: 63) | TSM/012089 | SM/11098 | New | 20/05/2022 | 63 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 1 | 0.12 | MVS
797 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012393 | SM/10936 | New | 20/05/2022 | 238 | 43.84 | Yes | 43.84 |  | 12/03/2024 | 1 | 0.12 | MVS
798 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012394 | SM/10937 | New | 20/05/2022 | 242 | 44.62 | Yes | 44.62 |  | 12/03/2024 | 1 | 0.12 | MVS
799 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR ITA DANGRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012398 | SM/10941 | New | 20/05/2022 | 159 | 42.07 | Yes | 42.07 |  | 12/03/2024 | 1 | 0.12 | MVS
800 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MALLIKDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012400 | SM/10943 | New | 20/05/2022 | 293 | 44.62 | Yes | 44.62 |  |  | 0 | 0 | MVS
801 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR UTTAR KENDBANA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012464 | SM/10982 | New | 20/05/2022 | 74 | 42.53 | Yes | 42.53 |  | 04/04/2024 | 1 | 0.12 | MVS
802 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balananda, House Hold:42) | TSM/012256 | SM/11147 | New | 20/05/2022 | 508 | 39.69 | Yes | 39.69 |  | 29/04/2024 | 1 | 2.33 | MVS
803 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Rampur, House Hold No.:65) | TSM/012086 | SM/11100 | New | 20/05/2022 | 65 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
804 | BANKURA | Bankura Division | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | TSM/010931 | SM/12382 | Augmentation | 22/08/2022 | 1109 | 600.05 | Yes | 600.05 | 30/01/2025 | 14/11/2022 | 9 | 483.4 | MVS
805 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | TSM/005016 | SM/09877 | Augmentation | 10/02/2021 | 3690 | 557.61 | Yes | 656.27 | 05/04/2023 | 22/09/2022 | 8 | 685.25 | MVS
806 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | TSM/005017 | SM/09879 | Augmentation | 10/02/2021 | 1358 | 406.59 | Yes | 416.45 | 14/05/2025 | 17/04/2023 | 8 | 326.11 | MVS
807 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAMNAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012407 | SM/10850 | New | 20/05/2022 | 700 | 37.2 | Yes | 37.2 |  | 22/05/2024 | 1 | 5.08 | MVS
808 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR NISHCHINTAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012416 | SM/10859 | New | 20/05/2022 | 36 | 34.21 | Yes | 34.21 |  |  | 0 | 0 | MVS
809 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BINODPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012422 | SM/10865 | New | 20/05/2022 | 24 | 31.49 | Yes | 31.49 |  | 04/04/2024 | 1 | 0.12 | MVS
810 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUMIR PATHAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012432 | SM/10875 | New | 20/05/2022 | 47 | 36.96 | Yes | 36.96 |  | 04/04/2024 | 1 | 0.12 | MVS
811 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Digrya, House Hold No.: 64) | TSM/012231 | SM/11178 | New | 20/05/2022 | 64 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
812 | BANKURA | Bankura Division | Hirapur Piped Water Supply Scheme | TSM/014583 | SM/12418 | New | 22/08/2022 | 1423 | 902.58 | Yes | 902.58 | 12/03/2025 | 21/02/2023 | 4 | 161.79 | MVS
813 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KOT MADAN MOHANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012405 | SM/10848 | New | 20/05/2022 | 746 | 44.62 | Yes | 44.62 |  | 22/05/2024 | 1 | 0.12 | MVS
814 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMDANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012435 | SM/10878 | New | 20/05/2022 | 37 | 34.46 | Yes | 34.46 |  | 15/03/2023 | 1 | 0.12 | MVS
815 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Gosai Gram, House Hold:59 | TSM/012184 | SM/11448 | New | 20/05/2022 | 59 | 38.91 | Yes | 38.91 | 09/10/2023 | 26/06/2023 | 1 | 0.12 | MVS
816 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Haira bandh, House Hold:54 | TSM/012179 | SM/11450 | New | 20/05/2022 | 157 | 38.91 | Yes | 38.91 |  | 27/03/2024 | 1 | 0.12 | MVS
817 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Purba Nischintapur, House Hold No.: 81) | TSM/012185 | SM/11674 | New | 20/05/2022 | 649 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
818 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bagsara, House Hold No.: 25) | TSM/012159 | SM/11683 | New | 20/05/2022 | 25 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
819 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chandabil, House Hold No.: 93) | TSM/012149 | SM/11686 | New | 20/05/2022 | 93 | 39.88 | Yes | 39.88 |  | 31/01/2023 | 1 | 0.12 | MVS
820 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Jaypur, Household-22) | TSM/012142 | SM/11404 | New | 20/05/2022 | 583 | 39.11 | Yes | 39.11 |  |  | 0 | 0 | MVS
821 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Birampur, House Hold No.: 57) | TSM/012123 | SM/11694 | New | 20/05/2022 | 1479 | 39.88 | Yes | 39.88 |  |  | 0 | 0 | MVS
822 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TELLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012163 | SM/13260 | New | 20/05/2022 | 446 | 43.39 | Yes | 43.39 |  | 16/05/2024 | 1 | 0.23 | MVS
823 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PATRA HATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012186 | SM/13265 | New | 20/05/2022 | 157 | 39.95 | Yes | 39.95 |  |  | 0 | 0 | MVS
824 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHATURIKALAPATHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012195 | SM/13268 | New | 20/05/2022 | 42 | 36.46 | Yes | 36.46 |  |  | 0 | 0 | MVS
825 | BANKURA | Bankura Division | Patsol Piped Water Supply Scheme | TSM/015708 | SM/14011 | New | 26/09/2022 | 122 | 251.67 | Yes | 251.67 | 31/01/2025 | 06/01/2023 | 4 | 34.84 | MVS
826 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | TSM/016219 | SM/14091 | Augmentation | 26/09/2022 | 2305 | 816.64 | Yes | 816.64 | 12/02/2025 | 24/05/2022 | 9 | 470.75 | MVS
827 | BANKURA | Bankura Division | Goala Danga Piped Water Supply Scheme. | TSM/015440 | SM/14001 | New | 26/09/2022 | 713 | 478.88 | Yes | 478.88 | 31/01/2025 | 26/07/2024 | 6 | 51.7 | MVS
828 | BANKURA | Bankura Division | Kubir Bandh Piped Water Supply Scheme | TSM/015439 | SM/14008 | New | 26/09/2022 | 1052 | 724.55 | Yes | 724.55 | 25/04/2025 | 16/09/2025 | 6 | 1279.92 | MVS
829 | BANKURA | Bankura Division | Kushadwip Piped Water Supply Scheme | TSM/015399 | SM/15266 | New | 30/09/2022 | 1670 | 753.15 | Yes | 753.15 | 12/03/2025 | 08/09/2023 | 5 | 59.98 | MVS
830 | BANKURA | Bankura Division | Lankajol Piped Water Supply Scheme. | TSM/015918 | SM/15022 | New | 30/09/2022 | 2546 | 999.38 | Yes | 999.38 | 12/03/2025 | 24/12/2024 | 5 | 106.05 | MVS
831 | BANKURA | Bankura Division | Narayanpur Piped Water Supply Scheme | TSM/014854 | SM/14178 | New | 09/09/2022 | 1981 | 1043.85 | Yes | 1043.85 | 12/03/2025 | 27/09/2024 | 5 | 82.23 | MVS
832 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Mamudpur-124, Barabaikunthapur-125, Habish | TSM/007424 | SM/08294 | Retrofitting | 10/02/2021 | 549 | 80.95 | Yes | 80.95 | 10/05/2023 | 23/09/2021 | 10 | 106.37 | MVS
833 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | TSM/007297 | SM/09229 | Retrofitting | 10/02/2021 | 1188 | 89.49 | Yes | 89.49 |  | 08/11/2021 | 15 | 136.97 | MVS
834 | BANKURA | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | TSM/018936 | SM/16975 | Augmentation | 16/11/2022 | 475 | 282.39 | Yes | 282.39 | 21/06/2024 | 24/07/2023 | 15 | 230.1 | MVS
835 | BANKURA | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018949 | SM/16977 | Augmentation | 16/11/2022 | 350 | 230.91 | Yes | 234.93 | 30/09/2024 | 28/03/2023 | 5 | 107.54 | MVS
836 | BANKURA | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018911 | SM/16960 | Augmentation | 16/11/2022 | 730 | 676.41 | Yes | 678.24 | 11/02/2025 | 25/04/2025 | 10 | 495.9 | MVS
837 | BANKURA | Bankura Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018923 | SM/16969 | Augmentation | 16/11/2022 | 478 | 640.4 | Yes | 640.4 | 30/01/2025 | 24/07/2023 | 7 | 499.41 | MVS
838 | BANKURA | Bankura Division | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018962 | SM/16958 | Augmentation | 16/11/2022 | 280 | 289.59 | Yes | 289.59 | 14/05/2025 | 13/07/2023 | 4 | 217.24 | MVS
839 | BANKURA | Bankura Division | Dhan Simla Piped Water Supply Scheme. | TSM/018459 | SM/16706 | New | 28/12/2022 | 403 | 231.21 | Yes | 231.21 | 22/02/2023 | 22/05/2023 | 7 | 210.35 | MVS
840 | BANKURA | Bankura Division | Augmentation of Amrul Zone-B Water Supply Scheme | TSM/019147 | SM/17230 | Augmentation | 16/11/2022 | 50 | 314.92 | Yes | 314.92 | 19/06/2024 | 13/07/2023 | 5 | 262.21 | MVS
841 | BANKURA | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | TSM/018450 | SM/17231 | New | 16/11/2022 | 966 | 623.97 | Yes | 654.57 | 30/01/2025 | 21/09/2023 | 20 | 420.69 | MVS
842 | BANKURA | Bankura Division | Augmentation of Panchal Zone-I Water Supply Scheme | TSM/019138 | SM/17233 | Augmentation | 16/11/2022 | 6 | 23.84 | Yes | 23.84 | 08/01/2024 | 28/03/2023 | 1 | 22.93 | MVS
843 | BANKURA | Bankura Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018902 | SM/17234 | Augmentation | 16/11/2022 | 920 | 478.96 | Yes | 480.48 | 07/06/2024 | 09/09/2024 | 8 | 419.48 | MVS
844 | BANKURA | Bankura Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018922 | SM/17240 | Augmentation | 16/11/2022 | 344 | 547.7 | Yes | 547.7 | 07/06/2024 | 26/10/2023 | 8 | 460.67 | MVS
845 | BANKURA | Bankura Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018925 | SM/17241 | Augmentation | 16/11/2022 | 150 | 499.85 | Yes | 499.85 | 30/01/2025 | 24/07/2023 | 8 | 198.17 | MVS
846 | BANKURA | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | TSM/019179 | SM/17243 | Augmentation | 16/11/2022 | 128 | 439.27 | Yes | 439.27 | 10/03/2025 | 14/07/2025 | 8 | 353.28 | MVS
847 | BANKURA | Bankura Division | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018948 | SM/17252 | Augmentation | 16/11/2022 | 480 | 249.65 | Yes | 250.9 | 15/05/2025 | 25/09/2024 | 4 | 96.27 | MVS
848 | BANKURA | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | TSM/018934 | SM/17701 | Augmentation | 16/11/2022 | 260 | 337.51 | Yes | 339.34 | 30/09/2024 | 30/03/2023 | 10 | 264.4 | MVS
849 | BANKURA | Bankura Division | Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019163 | SM/17729 | Augmentation | 16/11/2022 | 600 | 458.65 | Yes | 459.25 | 31/01/2025 | 18/06/2024 | 6 | 152.36 | MVS
850 | BANKURA | Bankura Division | Dwarika Pipe Water Supply Scheme | TSM/018289 | SM/17224 | New | 16/11/2022 | 1443 | 711.56 | Yes | 733.57 | 11/01/2024 | 14/08/2023 | 5 | 706.82 | MVS
851 | BANKURA | Bankura Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019156 | SM/17731 | Augmentation | 16/11/2022 | 280 | 479.92 | Yes | 484.18 | 31/01/2025 | 17/03/2023 | 5 | 174.25 | MVS
852 | BANKURA | Bankura Division | Augmentation of Panchal Zone-II Water Supply Scheme | TSM/019144 | SM/17423 | Augmentation | 16/11/2022 | 34 | 236.43 | Yes | 236.43 | 05/03/2024 | 19/04/2024 | 4 | 58.2 | MVS
853 | BANKURA | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018908 | SM/17424 | Augmentation | 16/11/2022 | 281 | 389.74 | Yes | 392.78 | 30/09/2024 | 12/07/2024 | 9 | 158 | MVS
854 | BANKURA | Bankura Division | Augmentation of Chakuparsole Zone-A Water Supply Scheme | TSM/019175 | SM/17425 | Augmentation | 16/11/2022 | 360 | 423.84 | Yes | 423.84 | 09/04/2025 | 24/07/2023 | 5 | 346.34 | MVS
855 | BANKURA | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | TSM/018933 | SM/17428 | Augmentation | 16/11/2022 | 840 | 683.69 | Yes | 688.26 | 07/03/2025 | 09/11/2023 | 8 | 528.24 | MVS
856 | BANKURA | Bankura Division | Augmentation of Rol Zone-A Water Supply Scheme | TSM/019121 | SM/17693 | Augmentation | 16/11/2022 | 50 | 165.71 | Yes | 165.71 | 17/04/2023 | 27/07/2023 | 3 | 147.75 | MVS
857 | BANKURA | Bankura Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018913 | SM/17694 | Augmentation | 16/11/2022 | 680 | 473.04 | Yes | 473.96 | 12/03/2024 | 14/08/2023 | 6 | 317.82 | MVS
858 | BANKURA | Bankura Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | TSM/011399 | SM/17577 | New | 28/12/2022 | 254 | 468.23 | Yes | 468.23 | 05/03/2024 | 13/07/2023 | 10 | 277.83 | MVS
859 | BANKURA | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018971 | SM/17287 | Augmentation | 16/11/2022 | 490 | 259.86 | Yes | 260.78 | 30/09/2024 | 10/06/2024 | 10 | 84.59 | MVS
860 | BANKURA | Bankura Division | Augmentation of Radhanagar Zone-I Water Supply Scheme | TSM/019145 | SM/17690 | Augmentation | 16/11/2022 | 205 | 389.87 | Yes | 389.87 | 09/04/2025 | 19/08/2025 | 8 | 371.8 | MVS
861 | BANKURA | Bankura Division | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) | TSM/019189 | SM/17432 | Augmentation | 16/11/2022 | 180 | 433.16 | Yes | 436.2 | 31/01/2025 | 06/09/2024 | 4 | 69.28 | MVS
862 | BANKURA | Bankura Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019218 | SM/17433 | Augmentation | 16/11/2022 | 350 | 488.91 | Yes | 489.22 | 12/02/2025 | 22/05/2024 | 6 | 151.97 | MVS
863 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Basantapur, House Hold No.: 62) | TSM/012226 | SM/11181 | New | 20/05/2022 | 62 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
864 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020342 | SM/18892 | Augmentation | 10/03/2023 | 100 | 799.62 | Yes | 799.62 | 09/04/2025 | 08/07/2025 | 6 | 433.85 | MVS
865 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020340 | SM/18893 | Augmentation | 10/03/2023 | 60 | 464 | Yes | 464 | 25/04/2025 | 18/06/2024 | 5 | 291.58 | MVS
866 | BANKURA | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020341 | SM/18895 | Augmentation | 10/03/2023 | 50 | 882.2 | Yes | 882.2 | 10/03/2025 | 17/06/2025 | 4 | 401.55 | MVS
867 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA KUMIRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012401 | SM/10944 | New | 20/05/2022 | 291 | 44.23 | Yes | 44.23 |  |  | 0 | 0 | MVS
868 | BANKURA | Bankura Division | Water supply scheme for ASRAMSALA OF Ramkrishna Mission Sarada Vidyapith under Bishnupur Sub-Division of Bankura Division P.H.E. Dte. | TSM/011338 | SM/18851 | School | 10/03/2023 | 0 | 67.55 | Yes | 67.55 |  |  | 0 | 0 | MVS
869 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALIPAHARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012461 | SM/10979 | New | 20/05/2022 | 50 | 37.71 | Yes | 37.71 |  | 06/05/2024 | 1 | 0.12 | MVS
870 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Sapuradihi, household-25) | TSM/012126 | SM/11408 | New | 20/05/2022 | 25 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
871 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Mukha, House Hold No.: 93) | TSM/012096 | SM/11094 | New | 20/05/2022 | 93 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
872 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Barsi, Malbedya, Narasinghapur, Arrah, Barabanagram, Khudra b | TSM/005980 | SM/07241 | Retrofitting | 25/09/2020 | 1062 | 96.76 | Yes | 96.76 | 19/04/2023 | 09/07/2021 | 16 | 217.96 | MVS
873 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - II) of MALIARA (Zone - A) under Bankura - I,II & | TSM/006006 | SM/07307 | Retrofitting | 25/09/2020 | 954 | 84.49 | Yes | 84.49 | 08/01/2024 | 23/09/2021 | 6 | 108.73 | MVS
874 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Batikara (12), Nanda (15), Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Raniban | TSM/005905 | SM/07362 | Retrofitting | 25/09/2020 | 939 | 77.85 | Yes | 77.85 |  | 28/05/2024 | 12 | 193.72 | MVS
875 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jhunka, Shushunia parasibana, Paharbedia, Bharatpur, Kendua) | TSM/005970 | SM/07252 | Retrofitting | 25/09/2020 | 874 | 90.97 | Yes | 90.97 |  | 23/09/2021 | 10 | 128.72 | MVS
876 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 12 Nos. Mouzas (Enayetpur, Kaleberia, Namoghansara, Kururia Balarampur, Malkur | TSM/005929 | SM/07262 | Retrofitting | 25/09/2020 | 1032 | 80.43 | Yes | 80.43 |  | 10/02/2021 | 9 | 99.67 | MVS
877 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | TSM/005992 | SM/07317 | Retrofitting | 25/09/2020 | 972 | 85.51 | Yes | 85.51 |  | 26/07/2021 | 10 | 157.87 | MVS
878 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Aralbasi, Bansi, Patakola | TSM/005983 | SM/07318 | Retrofitting | 25/09/2020 | 1164 | 80.74 | Yes | 80.74 |  | 04/02/2021 | 7 | 104.91 | MVS
879 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | TSM/005754 | SM/06796 | Retrofitting | 28/08/2020 | 384 | 99.94 | Yes | 99.94 |  | 09/10/2020 | 8 | 168.86 | MVS
880 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria | TSM/005746 | SM/06811 | Retrofitting | 28/08/2020 | 1186 | 90.1 | Yes | 90.1 | 16/12/2022 | 18/04/2022 | 19 | 161.09 | MVS
881 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | TSM/005755 | SM/06792 | Retrofitting | 28/08/2020 | 981 | 74.89 | Yes | 74.89 |  | 09/10/2020 | 4 | 86.66 | MVS
882 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam | TSM/005959 | SM/07326 | Retrofitting | 25/09/2020 | 998 | 72.12 | Yes | 72.12 |  | 10/02/2021 | 5 | 147.91 | MVS
883 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis | TSM/005911 | SM/07334 | Retrofitting | 25/09/2020 | 1254 | 99.12 | Yes | 99.12 |  | 19/04/2022 | 18 | 188.31 | MVS
884 | BANKURA | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District | TSM/007338 | SM/08311 | Retrofitting | 10/02/2021 | 7093 | 298.3 | Yes | 298.3 | 11/01/2024 | 12/05/2022 | 3 | 219.07 | MVS
885 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | TSM/007459 | SM/09316 | Retrofitting | 19/02/2021 | 3242 | 237.85 | Yes | 272.68 | 16/10/2023 | 11/11/2021 | 44 | 357.88 | MVS
886 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S | TSM/007476 | SM/09329 | Retrofitting | 19/02/2021 | 1144 | 143.74 | Yes | 160.36 |  | 11/11/2021 | 17 | 142.5 | MVS
887 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by | TSM/007317 | SM/09235 | Retrofitting | 10/02/2021 | 885 | 79.85 | Yes | 79.85 |  | 08/11/2021 | 3 | 45.34 | MVS
888 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | TSM/007465 | SM/09630 | Retrofitting | 19/02/2021 | 1960 | 184.06 | Yes | 184.06 | 16/11/2022 | 01/06/2023 | 4 | 103.4 | MVS
889 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, | TSM/007408 | SM/09631 | Retrofitting | 10/02/2021 | 3315 | 425.14 | Yes | 427.7 |  | 29/11/2023 | 41 | 335.77 | MVS
890 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Dhabani-136, Chitrang-137, Baliguma-1 | TSM/007410 | SM/09637 | Retrofitting | 10/02/2021 | 949 | 86.89 | Yes | 86.89 |  | 29/11/2021 | 1 | 61.96 | MVS
891 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | TSM/008197 | SM/09501 | Retrofitting | 19/08/2021 | 2442 | 57.51 | Yes | 92.18 |  | 13/11/2020 | 31 | 142.3 | MVS
892 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | TSM/008984 | SM/09552 | Retrofitting | 08/10/2021 | 1926 | 161.82 | Yes | 161.82 |  | 15/06/2022 | 5 | 109.31 | MVS
893 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and | TSM/007303 | SM/09618 | Retrofitting | 10/02/2021 | 1119 | 99.94 | Yes | 99.94 |  | 23/09/2021 | 4 | 100.94 | MVS
894 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, | TSM/007467 | SM/09624 | Retrofitting | 19/02/2021 | 1461 | 139.57 | Yes | 139.57 |  | 03/03/2022 | 2 | 115.95 | MVS
895 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | TSM/008188 | SM/09473 | Retrofitting | 19/08/2021 | 1806 | 189.75 | Yes | 189.75 | 30/09/2021 | 29/09/2022 | 1 | 3.85 | MVS
896 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | TSM/008452 | SM/09478 | Retrofitting | 08/09/2021 | 2536 | 212.48 | Yes | 212.48 |  | 22/02/2022 | 5 | 317.24 | MVS
897 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma | TSM/008648 | SM/09534 | Retrofitting | 08/09/2021 | 2339 | 197.45 | Yes | 197.45 |  | 10/05/2022 | 3 | 137.37 | MVS
898 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza | TSM/008654 | SM/09535 | Retrofitting | 08/09/2021 | 1713 | 152.7 | Yes | 152.7 |  | 03/03/2022 | 3 | 111.75 | MVS
899 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012479 | SM/10947 | New | 20/05/2022 | 98 | 44.82 | Yes | 44.82 |  |  | 0 | 0 | MVS
900 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012483 | SM/10951 | New | 20/05/2022 | 72 | 42.07 | Yes | 42.07 |  | 15/05/2023 | 1 | 0.12 | MVS
901 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) | TSM/008523 | SM/08983 | Augmentation | 08/09/2021 | 2939 | 672.25 | Yes | 672.25 | 07/03/2025 | 25/05/2022 | 6 | 618.44 | MVS
902 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | TSM/008518 | SM/10290 | Augmentation | 29/09/2021 | 4030 | 1004.54 | Yes | 1004.54 | 29/11/2024 | 13/12/2023 | 10 | 986.91 | MVS
903 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012140 | SM/10906 | New | 20/05/2022 | 76 | 40.52 | Yes | 40.52 |  | 02/06/2023 | 1 | 0.08 | MVS
904 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012164 | SM/10916 | New | 20/05/2022 | 93 | 43.84 | Yes | 43.84 |  | 05/06/2023 | 1 | 0.12 | MVS
905 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012168 | SM/10918 | New | 20/05/2022 | 283 | 43.65 | Yes | 43.65 |  | 26/04/2024 | 1 | 0.23 | MVS
906 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOLA BAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012389 | SM/10932 | New | 20/05/2022 | 143 | 34.46 | Yes | 34.46 |  | 13/09/2024 | 1 | 1.2 | MVS
907 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012300 | SM/11112 | New | 20/05/2022 | 51 | 37.2 | Yes | 37.2 | 18/02/2025 | 04/08/2023 | 1 | 0.11 | MVS
908 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012303 | SM/11115 | New | 20/05/2022 | 70 | 41.6 | Yes | 41.6 | 18/02/2025 | 10/03/2025 | 1 | 0.9 | MVS
909 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012285 | SM/11022 | New | 20/05/2022 | 96 | 44.43 | Yes | 44.43 | 24/12/2021 | 07/06/2023 | 1 | 0.12 | MVS
910 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012286 | SM/11023 | New | 20/05/2022 | 95 | 44.23 | Yes | 44.23 |  | 07/06/2023 | 1 | 0.12 | MVS
911 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) | TSM/012116 | SM/11084 | New | 20/05/2022 | 50 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 1 | 0.12 | MVS
912 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012485 | SM/10953 | New | 20/05/2022 | 82 | 41.69 | Yes | 41.69 |  | 15/05/2023 | 1 | 0.12 | MVS
913 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) | TSM/012252 | SM/11151 | New | 20/05/2022 | 244 | 39.69 | Yes | 39.69 |  | 26/06/2023 | 1 | 0.12 | MVS
914 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) | TSM/012249 | SM/11154 | New | 20/05/2022 | 325 | 39.69 | Yes | 39.69 |  | 26/06/2023 | 1 | 0.12 | MVS
915 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) | TSM/012246 | SM/11157 | New | 20/05/2022 | 81 | 39.69 | Yes | 39.69 |  | 02/02/2023 | 2 | 0.14 | MVS
916 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012318 | SM/11130 | New | 20/05/2022 | 0 | 43.06 | Yes | 43.06 | 24/12/2021 | 29/05/2024 | 1 | 0.12 | MVS
917 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) | TSM/012101 | SM/11091 | New | 20/05/2022 | 55 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
918 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARISOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012325 | SM/11062 | New | 20/05/2022 | 121 | 37.21 | Yes | 37.21 | 24/12/2021 |  | 0 | 0 | MVS
919 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012459 | SM/10977 | New | 20/05/2022 | 94 | 44.04 | Yes | 44.04 |  | 22/05/2024 | 1 | 0.12 | MVS
920 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012460 | SM/10978 | New | 20/05/2022 | 63 | 39.98 | Yes | 39.98 |  | 15/03/2023 | 1 | 0.12 | MVS
921 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012390 | SM/10933 | New | 20/05/2022 | 78 | 34.96 | Yes | 34.96 |  | 28/05/2024 | 1 | 0.24 | MVS
922 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) | TSM/012267 | SM/11136 | New | 20/05/2022 | 96 | 39.69 | Yes | 39.69 | 24/12/2021 | 02/02/2023 | 2 | 0.14 | MVS
923 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) | TSM/012094 | SM/11095 | New | 20/05/2022 | 93 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
924 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) | TSM/012091 | SM/11097 | New | 20/05/2022 | 87 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
925 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) | TSM/012084 | SM/11101 | New | 20/05/2022 | 75 | 38.5 | Yes | 38.5 |  | 15/03/2023 | 2 | 0.14 | MVS
926 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) | TSM/012078 | SM/11105 | New | 20/05/2022 | 22 | 38.5 | Yes | 38.5 |  | 15/03/2023 | 2 | 0.14 | MVS
927 | BANKURA | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | TSM/014161 | SM/12379 | Augmentation | 22/08/2022 | 1107 | 590.96 | Yes | 590.96 | 07/12/2022 | 28/04/2023 | 6 | 433.03 | MVS
928 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | TSM/005083 | SM/09880 | Augmentation | 19/02/2021 | 1287 | 388.87 | Yes | 388.87 | 19/06/2024 | 01/12/2023 | 8 | 283.58 | MVS
929 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALIKHUN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012409 | SM/10852 | New | 20/05/2022 | 748 | 45.01 | Yes | 45.01 |  |  | 0 | 0 | MVS
930 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012415 | SM/10858 | New | 20/05/2022 | 36 | 34.21 | Yes | 34.21 |  |  | 0 | 0 | MVS
931 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012425 | SM/10868 | New | 20/05/2022 | 29 | 32.83 | Yes | 32.83 |  | 15/03/2023 | 3 | 0.38 | MVS
932 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012431 | SM/10874 | New | 20/05/2022 | 33 | 33.91 | Yes | 33.91 |  | 22/05/2024 | 2 | 0.36 | MVS
933 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) | TSM/012236 | SM/11175 | New | 20/05/2022 | 75 | 38.64 | Yes | 38.64 |  | 31/01/2023 | 1 | 0.12 | MVS
934 | BANKURA | Bankura Division | Harinashuli Piped Water Supply Scheme | TSM/014205 | SM/12422 | New | 22/08/2022 | 2340 | 946.83 | Yes | 946.83 | 09/12/2022 | 13/07/2023 | 7 | 1847.26 | MVS
935 | BANKURA | Bankura Division | Pankhai Piped Water Supply Scheme | TSM/014210 | SM/12427 | New | 22/08/2022 | 1742 | 825.44 | Yes | 825.44 | 12/03/2025 | 06/01/2023 | 4 | 78.54 | MVS
936 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Khanabari, House Hold No.: 53) | TSM/012180 | SM/11676 | New | 20/05/2022 | 700 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
937 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) | TSM/012177 | SM/11678 | New | 20/05/2022 | 236 | 39.88 | Yes | 39.88 |  | 29/04/2024 | 1 | 0.13 | MVS
938 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) | TSM/012230 | SM/11434 | New | 20/05/2022 | 71 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
939 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) | TSM/012228 | SM/11435 | New | 20/05/2022 | 208 | 38.91 | Yes | 38.91 |  | 26/06/2023 | 1 | 0.12 | MVS
940 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Barika Bhanupur, House Hold:53 | TSM/012208 | SM/11442 | New | 20/05/2022 | 53 | 38.91 | Yes | 38.91 |  |  | 0 | 0 | MVS
941 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) | TSM/012103 | SM/11416 | New | 20/05/2022 | 92 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
942 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) | TSM/012097 | SM/11418 | New | 20/05/2022 | 79 | 39.11 | Yes | 39.11 |  | 04/08/2023 | 1 | 0.12 | MVS
943 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) | TSM/012082 | SM/11424 | New | 20/05/2022 | 571 | 39.11 | Yes | 39.11 |  | 12/03/2024 | 1 | 2.63 | MVS
944 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKUNDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012072 | SM/13252 | New | 20/05/2022 | 97 | 44.62 | Yes | 44.62 |  |  | 0 | 0 | MVS
945 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAMRA MADHABPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012182 | SM/13264 | New | 20/05/2022 | 159 | 43.19 | Yes | 43.19 |  |  | 0 | 0 | MVS
946 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME | TSM/016326 | SM/15007 | Augmentation | 26/09/2022 | 565 | 362.07 | Yes | 362.07 | 10/01/2025 | 28/04/2023 | 7 | 191.76 | MVS
947 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | TSM/016329 | SM/15008 | Augmentation | 26/09/2022 | 957 | 454.11 | Yes | 454.11 | 12/02/2025 | 28/04/2023 | 7 | 237.05 | MVS
948 | BANKURA | Bankura Division | Lego Piped Water Supply Scheme | TSM/014855 | SM/14177 | New | 09/09/2022 | 1951 | 1049.01 | Yes | 1049.01 | 12/03/2025 | 28/11/2024 | 4 | 99.6 | MVS
949 | BANKURA | Bankura Division | Naruala Piped Water Supply Scheme | TSM/015168 | SM/13789 | New | 09/09/2022 | 1049 | 633.32 | Yes | 633.32 | 12/03/2025 | 28/11/2024 | 5 | 39.5 | MVS
950 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Patrasayer PWSS scheme Dist Bankura | TSM/018674 | SM/15313 | Solarisation | 16/11/2022 | 0 | 8.35 | Yes | 8.35 | 29/12/2022 | 23/03/2023 | 1 | 5.95 | MVS
951 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | TSM/016343 | SM/16261 | Augmentation | 26/09/2022 | 1415 | 509.65 | Yes | 509.65 | 10/01/2025 | 09/08/2024 | 7 | 304.11 | MVS
952 | BANKURA | Bankura Mechanical Division | Implementation of affordable IoT-Enabled water service delivery measurement and monitoring sensing system for rural deployment in the proposed villages under Indus water supply scheme in Indus Block under Bankura District. | TSM/020267 | SM/15332 | IOT | 16/11/2022 | 0 | 26.27 | Yes | 26.27 | 30/07/2024 |  | 0 | 0 | MVS
953 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | TSM/006016 | SM/07272 | Retrofitting | 25/09/2020 | 1275 | 88.11 | Yes | 88.11 |  | 10/02/2021 | 6 | 49.88 | MVS
954 | BANKURA | Bankura Mechanical Division | Implementation of affordable IoT-Enabled water service delivery measurement and monitoring sensing system for rural deployment in the proposed villages under Somsar water supply scheme in Indus Block under Bankura District. | TSM/020268 | SM/15334 | IOT | 16/11/2022 | 0 | 18.19 | Yes | 18.19 | 30/07/2024 |  | 0 | 0 | MVS
955 | BANKURA | Bankura Division | Nandagram Piped Water Supply Scheme | TSM/014862 | SM/14248 | New | 09/09/2022 | 3132 | 1465.27 | Yes | 1465.27 | 12/03/2025 | 27/09/2024 | 6 | 220.38 | MVS
956 | BANKURA | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018909 | SM/16959 | Augmentation | 16/11/2022 | 290 | 375.25 | Yes | 376.93 | 30/09/2024 | 14/08/2023 | 5 | 294.57 | MVS
957 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018920 | SM/16967 | Augmentation | 16/11/2022 | 900 | 738.9 | Yes | 749.13 | 06/05/2025 | 11/07/2024 | 9 | 695.79 | MVS
958 | BANKURA | Bankura Mechanical Division | Construction of Grid-connected Solar Photo-Voltaic system for Joypur pump house-I of Joypur PWSS scheme,Dist: Bankura | TSM/016449 | SM/16932 | Solarisation | 30/09/2022 | 0 | 9.77 | Yes | 9.77 | 15/12/2022 | 17/04/2023 | 1 | 6.65 | MVS
959 | BANKURA | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | TSM/019127 | SM/16950 | Augmentation | 16/11/2022 | 80 | 246.4 | Yes | 246.4 | 24/03/2023 | 11/04/2023 | 5 | 93.41 | MVS
960 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. | TSM/013109 | SM/16694 | New | 28/12/2022 | 718 | 370.23 | Yes | 370.23 | 30/09/2024 | 01/08/2023 | 9 | 344.49 | MVS
961 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | TSM/019124 | SM/16952 | Augmentation | 16/11/2022 | 180 | 172.5 | Yes | 172.5 | 30/09/2024 | 20/09/2024 | 5 | 152.46 | MVS
962 | BANKURA | Bankura Division | Augmentation for Gouripur Water Supply Scheme. | TSM/019130 | SM/17120 | Augmentation | 28/12/2022 | 120 | 116.24 | Yes | 116.24 | 08/01/2024 | 11/04/2023 | 6 | 84.63 | MVS
963 | BANKURA | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019237 | SM/17123 | Augmentation | 28/12/2022 | 544 | 230.53 | Yes | 230.53 | 21/09/2023 | 14/08/2023 | 5 | 238.65 | MVS
964 | BANKURA | Bankura Mechanical Division | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. | TSM/019195 | SM/17238 | Solarisation | 28/12/2022 | 0 | 140.97 | Yes | 140.97 | 19/01/2024 | 21/06/2024 | 4 | 126.46 | MVS
965 | BANKURA | Bankura Mechanical Division | Construction of Grid-Connected solar photo -voltaic system for Chhoto Birbhanpur PWSS scheme Dist Bankura | TSM/018672 | SM/17239 | Solarisation | 28/12/2022 | 0 | 11.26 | Yes | 11.26 | 10/02/2023 | 17/04/2023 | 1 | 7.8 | MVS
966 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | TSM/019213 | SM/17254 | Augmentation | 16/11/2022 | 400 | 569.26 | Yes | 571.7 | 31/01/2025 | 19/06/2024 | 10 | 226.98 | MVS
967 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | TSM/019165 | SM/17420 | Augmentation | 16/11/2022 | 55 | 288.97 | Yes | 288.97 | 19/06/2024 | 21/09/2023 | 8 | 178.15 | MVS
968 | BANKURA | Bankura Division | Augmentation of Prakash Zone-A Water Supply Scheme | TSM/019131 | SM/17222 | Augmentation | 16/11/2022 | 700 | 185.96 | Yes | 185.96 | 21/06/2024 | 18/07/2023 | 2 | 184.57 | MVS
969 | BANKURA | Bankura Division | Nandur Piped Water Supply Scheme | TSM/015740 | SM/18252 | New | 30/09/2022 | 3247 | 1462.49 | Yes | 1462.49 | 31/01/2025 | 06/01/2023 | 2 | 175.7 | MVS
970 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018916 | SM/17697 | Augmentation | 16/11/2022 | 538 | 579.05 | Yes | 579.05 | 29/04/2025 | 26/04/2024 | 12 | 489.2 | MVS
971 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018917 | SM/17698 | Augmentation | 16/11/2022 | 545 | 443.04 | Yes | 443.04 | 29/04/2025 | 18/04/2024 | 8 | 361.38 | MVS
972 | BANKURA | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019161 | SM/17304 | Augmentation | 16/11/2022 | 260 | 480.79 | Yes | 485.66 | 31/01/2025 | 04/09/2024 | 6 | 112.3 | MVS
973 | BANKURA | Bankura Division | Augmentation of Somsar (BRGF) Water Supply Scheme | TSM/019167 | SM/17579 | Augmentation | 16/11/2022 | 320 | 104.34 | Yes | 104.34 | 07/06/2024 | 09/09/2024 | 2 | 44.4 | MVS
974 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S | TSM/007315 | SM/09234 | Retrofitting | 10/02/2021 | 967 | 82.8 | Yes | 82.8 | 27/12/2022 | 23/09/2021 | 6 | 110.65 | MVS
975 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019150 | SM/17713 | Augmentation | 16/11/2022 | 230 | 736.39 | Yes | 743.39 | 12/02/2025 | 07/04/2025 | 22 | 541.84 | MVS
976 | BANKURA | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | TSM/019206 | SM/17430 | Augmentation | 16/11/2022 | 310 | 457.56 | Yes | 457.56 | 31/01/2025 | 04/09/2024 | 6 | 152.66 | MVS
977 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | TSM/008342 | SM/10295 | Augmentation | 19/08/2021 | 2522 | 1828.18 | Yes | 1828.18 | 18/06/2024 | 30/11/2022 | 25 | 1472.94 | MVS
978 | BANKURA | Bankura Division | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019204 | SM/18231 | Augmentation | 28/12/2022 | 310 | 153.99 | Yes | 153.99 | 16/01/2025 | 17/03/2023 | 2 | 21.54 | MVS
979 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012446 | SM/10889 | New | 20/05/2022 | 95 | 44.23 | Yes | 44.23 |  | 07/09/2023 | 1 | 0.12 | MVS
980 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012347 | SM/11199 | New | 20/05/2022 | 89 | 43.06 | Yes | 43.06 | 24/12/2021 | 18/01/2023 | 1 | 0.24 | MVS
981 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) | TSM/012108 | SM/11414 | New | 20/05/2022 | 201 | 39.11 | Yes | 39.11 |  | 07/09/2023 | 1 | 0.12 | MVS
982 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | TSM/019230 | SM/18424 | Augmentation | 16/11/2022 | 330 | 1092.92 | Yes | 1092.92 | 29/04/2025 | 18/06/2024 | 10 | 448.97 | MVS
983 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012308 | SM/11120 | New | 20/05/2022 | 72 | 42.07 | Yes | 42.07 |  | 04/08/2023 | 1 | 0.11 | MVS
984 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) | TSM/012247 | SM/11156 | New | 20/05/2022 | 20 | 39.69 | Yes | 39.69 |  |  | 0 | 0 | MVS
985 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMODAR MOHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012495 | SM/10963 | New | 20/05/2022 | 377 | 37.46 | Yes | 37.46 |  |  | 0 | 0 | MVS
986 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) | TSM/012114 | SM/11085 | New | 20/05/2022 | 89 | 38.5 | Yes | 38.5 |  | 02/02/2023 | 2 | 0.14 | MVS
987 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR HATIBAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012270 | SM/13254 | New | 20/05/2022 | 186 | 33.92 | Yes | 33.92 |  |  | 0 | 0 | MVS
988 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | TSM/005938 | SM/07341 | Retrofitting | 25/09/2020 | 1066 | 83.47 | Yes | 85.33 | 13/01/2023 | 05/02/2021 | 9 | 76.87 | MVS
989 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) | TSM/012258 | SM/11145 | New | 20/05/2022 | 46 | 39.69 | Yes | 39.69 |  | 26/06/2023 | 1 | 0.12 | MVS
990 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas | TSM/005019 | SM/09924 | Augmentation | 19/02/2021 | 3432 | 817.05 | Yes | 874.28 | 16/04/2025 | 28/08/2024 | 18 | 864.83 | MVS
991 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | TSM/015534 | SM/15260 | Support | 26/09/2022 | 0 | 168.45 | Yes | 168.45 | 07/06/2024 | 09/02/2024 | 27 | 174.89 | MVS
992 | BANKURA | Bankura Division | Operational charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | TSM/023203 | SM/19264 | Support | 09/03/2024 | 0 | 134.66 | Yes | 134.66 | 04/12/2024 | 25/06/2025 | 3 | 27.5 | MVS
993 | BANKURA | Bankura Mechanical Division | Arrangement for double tank Chlorine dosing system at different PWSS under different Blocks of Bankura District | TSM/023042 | SM/19296 | Support | 09/03/2024 | 0 | 47.11 | Yes | 47.11 |  |  | 0 | 0 | MVS
994 | BANKURA | Bankura Mechanical Division | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura | TSM/009959 | SM/10348 | Support | 27/01/2022 | 0 | 11.44 | Yes | 11.44 |  | 20/04/2022 | 9 | 21.41 | MVS
995 | BANKURA | Bankura Division | Proposal of Engagement of Additional Manpower as Project Management & Monitoring Specialist, Data Analytics and MIS Specialist at DPMU of Bankura District under, Jal Jeevan Mission (JJM) | TSM/023345 | SM/19351 | Support | 22/10/2024 | 0 | 38.4 | Yes | 38.4 |  |  | 0 | 0 | MVS
996 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. | TSM/005373 | SM/06634 | Support | 05/11/2019 | 0 | 104.55 | Yes | 104.55 | 24/03/2023 | 28/04/2023 | 43 | 117.85 | MVS
997 | BANKURA | Bankura Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. | TSM/008152 | SM/08977 | Support | 19/08/2021 | 0 | 481.61 | Yes | 481.61 |  | 20/05/2022 | 2 | 427.96 | MVS
998 | BANKURA | Bankura Division | Survey & collection of data through mobile app regarding availability of drinking water, sanitation facilities & other parameters in primary, upper primary schools anganwadi centers within Bankura District for the financial year 2020-2021 | TSM/009452 | SM/09928 | Support | 22/11/2021 | 0 | 11.7 | Yes | 11.7 |  | 10/01/2022 | 3 | 11.32 | MVS
999 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll) & uploading charges for the same related to Water Quality Monitoring & SurveillanceProgramme Under Jal Jeevan Mission | TSM/021614 | SM/19084 | Support | 17/08/2023 | 0 | 85.6 | Yes | 85.6 | 05/12/2023 | 06/02/2024 | 4 | 10.85 | MVS
1000 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE | TSM/015702 | SM/18829 | Support | 26/09/2022 | 0 | 55.09 | Yes | 55.09 |  | 05/10/2024 | 13 | 57.65 | MVS
1001 | BANKURA | Bankura Division | Mass Awareness Generation / IEC Activities for sensitization of rural community on WASH at 18 Blocks consisting of 149 GPs of Bankura District under Jal Jeevan Mission (JJM) Support Activities. | TSM/022797 |  | Support | 22/10/2024 | 0 | 122.33 | No | 0 |  |  | 0 | 0 | MVS
1002 | BANKURA | Bankura Division | Survey & Collection of data through mobile app regarding availability of drinking water, sanitation facilities and other parameters in Primary, Upper Primary Schools, Anganwadi Centers under Bankura District. | TSM/011464 |  | Support | 25/04/2022 | 0 | 11.7 | No | 0 |  |  | 0 | 0 | MVS
1003 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | TSM/023204 | SM/19269 | Support | 09/03/2024 | 0 | 168.45 | Yes | 168.45 | 03/03/2025 | 28/06/2024 | 7 | 64.04 | MVS
1004 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | TSM/016446 | SM/15258 | Support | 26/09/2022 | 0 | 60.18 | Yes | 60.18 | 17/04/2023 | 08/06/2023 | 6 | 3.19 | MVS
1005 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | TSM/016370 | SM/15259 | Support | 26/09/2022 | 0 | 141.68 | Yes | 141.68 | 07/06/2023 | 02/06/2023 | 24 | 113.69 | MVS
1006 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | TSM/011650 | SM/17128 | Support | 16/11/2022 | 0 | 78.45 | Yes | 78.45 | 29/11/2024 | 02/07/2024 | 44 | 67.89 | MVS
1007 | BANKURA | Bankura Division | Infrastructure development for Taldangra Sub-District water Testing Laboratory regarding NABL accreditation under Bankura Division, PHE Dte. related to support activities under JJM | TSM/011463 | SM/17416 | Support | 25/04/2022 | 0 | 17.29 | Yes | 17.29 | 20/01/2023 | 04/04/2023 | 1 | 16.79 | MVS
Total | [7 empty] | 858679 | 246519.19 |  | 242458.72 |  |  | 5158 | 169100.05