## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block | TSM/006300 | SM/07465 | Retrofitting | 25/09/2020 | 1711 | 123.54 | Yes | 123.54 | 09/01/2023 | 31/05/2021 | 2 | 117.41 | MVS
2 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme | TSM/005657 | SM/06719 | Retrofitting | 28/08/2020 | 952 | 67.6 | Yes | 67.6 |  | 12/10/2020 | 6 | 139.73 | MVS
3 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | TSM/006297 | SM/07009 | Retrofitting | 25/09/2020 | 639 | 50.47 | Yes | 50.47 | 04/11/2024 | 06/05/2022 | 5 | 44.17 | MVS
4 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | TSM/006748 | SM/07882 | Retrofitting | 04/12/2020 | 2697 | 174.48 | Yes | 174.48 | 14/01/2025 | 06/04/2022 | 11 | 189.08 | MVS
5 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | TSM/005660 | SM/06774 | Retrofitting | 28/08/2020 | 1035 | 69.51 | Yes | 69.51 |  | 05/11/2020 | 9 | 116.86 | MVS
6 | HOWRAH | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | TSM/011009 | SM/12270 | New | 30/03/2022 | 4274 | 1234.15 | Yes | 1326.85 | 12/02/2025 | 22/07/2024 | 13 | 1177.05 | MVS
7 | HOWRAH | Howrah Division | Khorda Etarai Piped Water Supply Scheme | TSM/012017 | SM/11892 | New | 20/05/2022 | 733 | 303.93 | Yes | 323.64 | 13/09/2024 | 21/12/2023 | 13 | 302.41 | MVS
8 | HOWRAH | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | TSM/011933 | SM/11893 | New | 20/05/2022 | 2273 | 901.91 | Yes | 1018.55 | 20/08/2025 | 11/06/2024 | 15 | 820.26 | MVS
9 | HOWRAH | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | TSM/011292 | SM/11574 | New | 30/03/2022 | 2011 | 699.66 | Yes | 699.66 | 14/01/2025 | 09/04/2025 | 18 | 206.94 | MVS
10 | HOWRAH | Howrah Division | ICHAPUR PWSS | TSM/012520 | SM/13629 | New | 22/08/2022 | 1335 | 586.48 | Yes | 586.48 | 17/12/2024 | 19/04/2023 | 14 | 548.96 | MVS
11 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015610 | SM/13751 | New | 09/09/2022 | 3095 | 700.58 | Yes | 700.58 | 05/05/2025 | 13/01/2023 | 8 | 480.44 | MVS
12 | HOWRAH | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | TSM/015269 | SM/13749 | New | 09/09/2022 | 3486 | 975.18 | Yes | 975.18 | 29/03/2023 | 10/05/2023 | 6 | 2153.97 | MVS
13 | HOWRAH | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | TSM/014766 | SM/13768 | New | 22/08/2022 | 4347 | 716.22 | Yes | 716.22 | 13/09/2024 | 20/06/2024 | 9 | 319.7 | MVS
14 | HOWRAH | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | TSM/010279 | SM/14095 | Augmentation | 17/02/2022 | 27364 | 8211.71 | Yes | 8211.71 | 03/09/2025 | 26/04/2024 | 54 | 7820.16 | MVS
15 | HOWRAH | Electrical Division | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | TSM/017892 | SM/16446 | Solarisation | 16/11/2022 | 0 | 222.22 | Yes | 222.22 | 21/03/2023 | 17/07/2023 | 1 | 119.89 | MVS
16 | HOWRAH | Howrah Division | Chak Kadamtala Piped Water Supply scheme | TSM/016145 | SM/16557 | New | 30/09/2022 | 69 | 40.27 | Yes | 40.27 | 26/09/2023 |  | 0 | 0 | MVS
17 | HOWRAH | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | TSM/011290 | SM/16927 | New | 30/03/2022 | 2000 | 721.94 | Yes | 721.94 | 14/12/2024 | 23/11/2023 | 12 | 734.15 | MVS
18 | HOWRAH | Howrah Division | Shibgachhia Piped Water Supply Scheme | TSM/018487 | SM/18193 | New | 28/12/2022 | 761 | 507.75 | Yes | 507.75 | 13/09/2024 | 18/07/2023 | 9 | 342.19 | MVS
19 | HOWRAH | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | TSM/021366 | SM/18844 | Augmentation | 10/03/2023 | 0 | 152.8 | Yes | 152.8 | 22/07/2024 | 17/02/2022 | 4 | 70.03 | MVS
20 | HOWRAH | Howrah Division | Source Augmentation of Balichak Water Supply Scheme | TSM/021377 | SM/18885 | Augmentation | 10/03/2023 | 0 | 177.16 | Yes | 177.16 | 11/03/2024 | 24/06/2024 | 6 | 124.36 | MVS
21 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | TSM/005647 | SM/06785 | Retrofitting | 28/08/2020 | 1211 | 83.99 | Yes | 83.99 |  | 15/06/2022 | 10 | 128.44 | MVS
22 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) | TSM/006301 | SM/07074 | Retrofitting | 25/09/2020 | 1550 | 99.1 | Yes | 99.1 |  | 11/02/2021 | 5 | 176.35 | MVS
23 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | TSM/006292 | SM/07396 | Retrofitting | 25/09/2020 | 2234 | 139.91 | Yes | 139.91 | 17/12/2024 | 20/06/2022 | 8 | 141.84 | MVS
24 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) | TSM/006744 | SM/07885 | Retrofitting | 04/12/2020 | 1505 | 96.53 | Yes | 96.53 | 04/04/2025 | 02/05/2023 | 2 | 62.15 | MVS
25 | HOWRAH | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | TSM/008353 | SM/10145 | Augmentation | 19/08/2021 | 5786 | 1092.62 | Yes | 1092.62 | 31/07/2024 | 27/06/2023 | 15 | 1085.19 | MVS
26 | HOWRAH | Howrah Division | Augmentation of Khalatpur PWSS | TSM/008963 | SM/11271 | Augmentation | 16/03/2022 | 2484 | 881.64 | Yes | 985.37 | 12/03/2025 | 16/04/2025 | 30 | 611.81 | MVS
27 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) | TSM/005663 | SM/06777 | Retrofitting | 28/08/2020 | 1590 | 99.91 | Yes | 99.91 |  | 29/03/2023 | 14 | 88.84 | MVS
28 | HOWRAH | Howrah Division | Shyamchak Mini Piped water Supply Scheme | TSM/016331 | SM/15284 | New | 26/09/2022 | 41 | 40.6 | Yes | 40.6 | 13/09/2024 | 19/01/2024 | 1 | 0.09 | MVS
29 | HOWRAH | Howrah Division | Sankhali Piped Water Supply Scheme | TSM/015853 | SM/15289 | New | 26/09/2022 | 1058 | 372.64 | Yes | 372.64 | 13/09/2024 | 12/04/2023 | 9 | 344.36 | MVS
30 | HOWRAH | Howrah Division | Senpur Dwitiya Piped Water Supply Scheme | TSM/016151 | SM/15199 | New | 30/09/2022 | 67 | 43.09 | Yes | 43.09 | 13/09/2024 | 05/02/2024 | 1 | 0.71 | MVS
31 | HOWRAH | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | TSM/011570 | SM/11719 | New | 25/04/2022 | 3480 | 932.95 | Yes | 932.95 | 04/04/2025 | 23/06/2025 | 12 | 855.92 | MVS
32 | HOWRAH | Howrah Division | Source Augmentation of Nakubar Water Supply Scheme | TSM/021308 | SM/18847 | Augmentation | 10/03/2023 | 0 | 189.2 | Yes | 189.2 | 24/09/2024 | 22/07/2022 | 4 | 48.46 | MVS
33 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | TSM/017917 | SM/18561 | New | 30/09/2022 | 3383 | 1636.21 | Yes | 1636.21 | 06/05/2025 | 18/09/2024 | 14 | 1048.62 | MVS
34 | HOWRAH | Howrah Division | Source Augmentation of Sarda Water Supply Scheme | TSM/021378 | SM/18884 | Augmentation | 10/03/2023 | 0 | 138.99 | Yes | 138.99 | 11/03/2024 | 26/06/2024 | 6 | 76.45 | MVS
35 | HOWRAH | Howrah Division | Augmentation of Ground water PWSS for Islampur | TSM/008589 | SM/09428 | Augmentation | 29/09/2021 | 4465 | 754.25 | Yes | 754.25 | 17/06/2022 | 01/12/2021 | 10 | 756.35 | MVS
36 | HOWRAH | Howrah Division | Sherpur Piped Water Supply Scheme | TSM/018486 | SM/18426 | New | 16/11/2022 | 5601 | 2000.35 | Yes | 2000.35 | 04/04/2025 | 29/04/2025 | 7 | 133.06 | MVS
37 | HOWRAH | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | TSM/015623 | SM/13747 | New | 09/09/2022 | 1053 | 452.58 | Yes | 452.58 | 11/07/2024 | 24/07/2023 | 7 | 401.71 | MVS
38 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | TSM/006293 | SM/07395 | Retrofitting | 25/09/2020 | 2466 | 158.03 | Yes | 158.03 |  | 25/01/2022 | 9 | 156.15 | MVS
39 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | TSM/008622 | SM/09350 | Augmentation | 29/09/2021 | 1208 | 368.57 | Yes | 414.71 | 20/08/2025 | 27/06/2022 | 11 | 268.49 | MVS
40 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | TSM/005653 | SM/06714 | Retrofitting | 28/08/2020 | 1160 | 79.55 | Yes | 79.55 |  | 09/11/2020 | 12 | 121.82 | MVS
41 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme | TSM/005654 | SM/06715 | Retrofitting | 28/08/2020 | 1042 | 73.1 | Yes | 73.1 | 22/08/2024 | 06/05/2022 | 8 | 126.46 | MVS
42 | HOWRAH | Howrah Division | Aumentation of PWSS for Surikhali | TSM/008596 | SM/09429 | Augmentation | 29/09/2021 | 992 | 333.75 | Yes | 333.75 | 29/11/2024 | 11/04/2022 | 29 | 276.67 | MVS
43 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | TSM/008627 | SM/09349 | Augmentation | 29/09/2021 | 5518 | 993.4 | Yes | 993.4 | 13/09/2024 | 11/06/2024 | 14 | 1035.84 | MVS
44 | HOWRAH | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | TSM/008775 | SM/09002 | Disaster | 08/09/2021 | 0 | 170.57 | Yes | 170.57 |  | 28/06/2022 | 59 | 206.96 | MVS
45 | HOWRAH | Howrah Division | Augmentation of Maju piped water supply scheme. | TSM/008091 | SM/10035 | Augmentation | 29/09/2021 | 4749 | 1692.75 | Yes | 1692.75 | 13/09/2024 | 20/06/2024 | 13 | 1428.68 | MVS
46 | HOWRAH | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | TSM/008513 | SM/10021 | Augmentation | 29/09/2021 | 3664 | 1553.14 | Yes | 1553.14 | 04/04/2025 | 26/06/2024 | 34 | 888.16 | MVS
47 | HOWRAH | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | TSM/011760 | SM/11711 | New | 25/04/2022 | 3591 | 998.59 | Yes | 1072.81 | 31/12/2024 | 27/11/2024 | 13 | 884.67 | MVS
48 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | TSM/011678 | SM/11222 | New | 25/04/2022 | 1248 | 469.24 | Yes | 469.24 | 13/09/2024 | 05/11/2024 | 8 | 458.13 | MVS
49 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | TSM/011056 | SM/11641 | New | 25/04/2022 | 3060 | 997.11 | Yes | 997.11 | 06/02/2024 | 03/08/2023 | 7 | 1189.88 | MVS
50 | HOWRAH | Howrah Division | Jaynagar Piped Water Supply Scheme | TSM/018489 | SM/14865 | New | 16/11/2022 | 3079 | 761.37 | Yes | 761.37 | 09/04/2025 | 05/06/2025 | 7 | 659.85 | MVS
51 | HOWRAH | Howrah Division | Mollar Chak Piped Water Supplu scheme | TSM/016154 | SM/15288 | New | 26/09/2022 | 68 | 44.36 | Yes | 44.36 | 13/09/2024 | 07/02/2024 | 1 | 0.09 | MVS
52 | HOWRAH | Howrah Division | Sankardari Mini Piped Water Supply Scheme | TSM/016140 | SM/15189 | New | 30/09/2022 | 91 | 45.72 | Yes | 45.72 | 13/09/2024 | 07/06/2023 | 2 | 330.4 | MVS
53 | HOWRAH | Howrah Division | Chakur water supply scheme. | TSM/008182 | SM/08987 | New | 19/08/2021 | 800 | 292.32 | Yes | 292.32 | 02/08/2023 | 11/01/2022 | 13 | 314.34 | MVS
54 | HOWRAH | Howrah Division | Augmentation of Keshabpur Water supply scheme | TSM/010465 | SM/16947 | Augmentation | 16/03/2022 | 2824 | 857.9 | Yes | 857.9 | 18/12/2024 | 04/04/2023 | 8 | 533.16 | MVS
55 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | TSM/017876 | SM/18565 | Augmentation | 30/09/2022 | 3713 | 1175.93 | Yes | 1175.93 | 27/12/2022 | 07/08/2023 | 7 | 569.97 | MVS
56 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | TSM/017891 | SM/18567 | Augmentation | 30/09/2022 | 4781 | 1416.25 | Yes | 1416.25 | 08/03/2025 | 07/08/2023 | 15 | 1112.57 | MVS
57 | HOWRAH | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | TSM/021379 | SM/18883 | Augmentation | 10/03/2023 | 0 | 491.99 | Yes | 491.99 | 24/09/2024 | 09/07/2024 | 10 | 275.06 | MVS
58 | HOWRAH | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | TSM/019257 | SM/19187 | Augmentation | 16/11/2022 | 154792 | 33980.3 | Yes | 33980.3 | 12/07/2024 | 08/07/2024 | 29 | 29595.59 | MVS
59 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | TSM/005644 | SM/06784 | Retrofitting | 28/08/2020 | 1195 | 78.15 | Yes | 78.15 |  | 09/11/2020 | 8 | 142.18 | MVS
60 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) | TSM/005646 | SM/06787 | Retrofitting | 28/08/2020 | 2110 | 90.51 | Yes | 90.51 | 17/12/2024 | 05/03/2025 | 4 | 64.87 | MVS
61 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | TSM/005665 | SM/06779 | Retrofitting | 28/08/2020 | 1400 | 89.06 | Yes | 89.06 |  | 05/11/2020 | 10 | 138.27 | MVS
62 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | TSM/008640 | SM/09347 | Augmentation | 29/09/2021 | 2789 | 546.45 | Yes | 546.45 | 29/07/2024 | 02/05/2023 | 24 | 584.01 | MVS
63 | HOWRAH | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | TSM/008092 | SM/09720 | Augmentation | 19/08/2021 | 0 | 589.85 | Yes | 589.85 | 20/08/2025 | 29/03/2024 | 12 | 490.88 | MVS
64 | HOWRAH | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | TSM/008354 | SM/10020 | Augmentation | 19/08/2021 | 7281 | 1524.22 | Yes | 1524.22 | 20/08/2025 | 12/06/2024 | 24 | 1492.01 | MVS
65 | HOWRAH | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | TSM/011761 | SM/11718 | New | 25/04/2022 | 1793 | 706.38 | Yes | 706.38 | 30/01/2023 | 18/04/2023 | 6 | 512.77 | MVS
66 | HOWRAH | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | TSM/011532 | SM/11723 | Augmentation | 25/04/2022 | 3513 | 853.17 | Yes | 853.17 | 13/09/2024 | 27/04/2023 | 11 | 534.29 | MVS
67 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | TSM/008801 | SM/09930 | Augmentation | 22/11/2021 | 2475 | 679.04 | Yes | 679.04 | 29/01/2025 | 07/04/2022 | 21 | 282.71 | MVS
68 | HOWRAH | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | TSM/011548 | SM/11793 | New | 25/04/2022 | 3240 | 896.37 | Yes | 896.37 | 16/12/2024 | 14/08/2023 | 12 | 802.53 | MVS
69 | HOWRAH | Howrah Division | Sonatala Piped Water Supply Scheme | TSM/015612 | SM/14949 | New | 09/09/2022 | 2988 | 729.29 | Yes | 729.29 | 20/08/2025 | 07/05/2025 | 11 | 196.33 | MVS
70 | HOWRAH | Howrah Division | Dakshin Panchla Piped Water Supply Scheme | TSM/018488 | SM/17196 | New | 28/12/2022 | 808 | 236.59 | Yes | 236.59 | 04/02/2023 | 04/04/2023 | 6 | 235.59 | MVS
71 | HOWRAH | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | TSM/010806 | SM/18398 | Augmentation | 16/03/2022 | 8036 | 1887.15 | Yes | 1887.15 | 12/02/2025 | 26/07/2024 | 25 | 1854.73 | MVS
72 | HOWRAH | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme | TSM/021407 | SM/18841 | Augmentation | 10/03/2023 | 0 | 115.24 | Yes | 115.24 | 13/09/2024 | 11/03/2024 | 3 | 68.35 | MVS
73 | HOWRAH | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme | TSM/021363 | SM/18845 | Augmentation | 10/03/2023 | 0 | 155.14 | Yes | 155.14 | 22/07/2024 | 01/03/2024 | 5 | 80.13 | MVS
74 | HOWRAH | Howrah Division | Source Augmentation of Bauria Water Supply Scheme | TSM/021551 | SM/18850 | Augmentation | 10/03/2023 | 0 | 115.24 | Yes | 115.24 |  | 02/05/2023 | 5 | 104.26 | MVS
75 | HOWRAH | Howrah Division | Baniban Zone-I Piped Water Supply Scheme | TSM/017947 | SM/18566 | New | 30/09/2022 | 6036 | 1511.88 | Yes | 1511.88 | 02/02/2023 | 16/08/2023 | 2 | 1062.62 | MVS
76 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | TSM/004182 | SM/18914 | New | 04/12/2020 | 4232 | 989.51 | Yes | 1046.52 | 15/07/2023 | 16/10/2023 | 6 | 1026.05 | MVS
77 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | TSM/006302 | SM/07075 | Retrofitting | 25/09/2020 | 2600 | 99.1 | Yes | 99.1 |  | 17/02/2022 | 7 | 188.12 | MVS
78 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | TSM/006303 | SM/07076 | Retrofitting | 25/09/2020 | 1450 | 99.1 | Yes | 99.1 |  | 10/02/2021 | 1 | 92.36 | MVS
79 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | TSM/005668 | SM/06782 | Retrofitting | 28/08/2020 | 1035 | 68.15 | Yes | 68.15 |  | 05/11/2020 | 15 | 132.24 | MVS
80 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | TSM/005645 | SM/06786 | Retrofitting | 28/08/2020 | 1410 | 94.88 | Yes | 94.88 |  | 13/10/2020 | 11 | 239.98 | MVS
81 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme | TSM/005650 | SM/06717 | Retrofitting | 28/08/2020 | 1150 | 80.45 | Yes | 80.45 |  | 04/11/2020 | 6 | 157.52 | MVS
82 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | TSM/005656 | SM/06721 | Retrofitting | 28/08/2020 | 1051 | 72.52 | Yes | 72.52 | 22/08/2024 | 07/10/2021 | 7 | 23.85 | MVS
83 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006747 | SM/07881 | Retrofitting | 04/12/2020 | 1744 | 112.45 | Yes | 112.45 |  | 06/04/2022 | 2 | 190.97 | MVS
84 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | TSM/006742 | SM/07886 | Retrofitting | 04/12/2020 | 2721 | 173.76 | Yes | 173.76 |  | 30/08/2022 | 8 | 159.86 | MVS
85 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006743 | SM/07887 | Retrofitting | 04/12/2020 | 2275 | 147.18 | Yes | 147.18 | 16/01/2025 | 24/02/2025 | 2 | 110.72 | MVS
86 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) | TSM/005662 | SM/06776 | Retrofitting | 28/08/2020 | 1590 | 99.91 | Yes | 99.91 |  | 13/07/2021 | 14 | 167.17 | MVS
87 | HOWRAH | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | TSM/008961 | SM/09424 | Disaster | 29/09/2021 | 0 | 105.31 | Yes | 105.31 |  | 27/12/2021 | 17 | 212.36 | MVS
88 | HOWRAH | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | TSM/008960 | SM/09353 | Disaster | 29/09/2021 | 0 | 23.17 | Yes | 23.17 |  | 31/01/2022 | 2 | 35.25 | MVS
89 | HOWRAH | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | TSM/011766 | SM/11717 | New | 25/04/2022 | 1398 | 475.19 | Yes | 475.19 | 14/01/2025 | 25/04/2023 | 6 | 417.64 | MVS
90 | HOWRAH | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | TSM/011550 | SM/11720 | New | 25/04/2022 | 1232 | 640.07 | Yes | 640.07 | 27/02/2023 | 24/07/2023 | 12 | 520.83 | MVS
91 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015621 | SM/13752 | New | 09/09/2022 | 11570 | 849.66 | Yes | 927.57 | 05/05/2025 | 12/08/2022 | 15 | 612.8 | MVS
92 | HOWRAH | Howrah Division | Patinan Piped Water Supply Scheme | TSM/015627 | SM/13848 | New | 09/09/2022 | 956 | 430.85 | Yes | 430.85 | 13/09/2024 | 05/04/2023 | 9 | 355.49 | MVS
93 | HOWRAH | Howrah Division | Purbba Gazipur Piped Water Supply Scheme | TSM/016144 | SM/15287 | New | 26/09/2022 | 91 | 45.5 | Yes | 45.5 | 13/09/2024 | 25/01/2024 | 1 | 0.08 | MVS
94 | HOWRAH | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | TSM/011062 | SM/15186 | New | 16/11/2022 | 3206 | 826.95 | Yes | 826.95 | 15/07/2023 | 16/08/2022 | 5 | 127.39 | MVS
95 | HOWRAH | Howrah Division | Manirampur Piped Water Supply Scheme | TSM/016149 | SM/15200 | New | 30/09/2022 | 75 | 43.19 | Yes | 43.19 | 13/09/2024 | 10/01/2024 | 1 | 0.08 | MVS
96 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pulgustia | TSM/008637 | SM/10143 | Augmentation | 16/12/2021 | 3842 | 708.72 | Yes | 708.72 | 05/02/2024 | 10/05/2023 | 11 | 699.35 | MVS
97 | HOWRAH | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | TSM/011301 | SM/16760 | New | 30/03/2022 | 3395 | 999.07 | Yes | 999.07 | 31/07/2024 | 12/04/2023 | 14 | 789.36 | MVS
98 | HOWRAH | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | TSM/005366 | SM/08966 | Augmentation | 17/07/2020 | 9981 | 2300.91 | Yes | 2511.74 | 20/08/2025 | 08/04/2024 | 16 | 2704.38 | MVS
99 | HOWRAH | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme | TSM/021553 | SM/18848 | Augmentation | 10/03/2023 | 0 | 115.24 | Yes | 115.24 | 16/01/2025 | 16/12/2022 | 4 | 31.18 | MVS
100 | HOWRAH | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | TSM/010977 | SM/11572 | New | 30/03/2022 | 3092 | 820.21 | Yes | 920.9 | 20/03/2025 | 23/09/2024 | 15 | 365.55 | MVS
101 | HOWRAH | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | TSM/019280 | SM/19186 | Augmentation | 16/11/2022 | 205921 | 55319.55 | Yes | 55319.55 | 20/08/2025 | 17/04/2025 | 71 | 9244 | MVS
102 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | TSM/006299 | SM/07466 | Retrofitting | 25/09/2020 | 2464 | 167.14 | Yes | 167.14 | 13/01/2023 | 23/12/2021 | 8 | 151.67 | MVS
103 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | TSM/008620 | SM/09351 | Augmentation | 29/09/2021 | 2781 | 618.61 | Yes | 618.61 | 13/09/2024 | 24/07/2023 | 16 | 682.1 | MVS
104 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | TSM/005652 | SM/06788 | Retrofitting | 28/08/2020 | 1494 | 97.34 | Yes | 97.34 |  | 12/10/2020 | 8 | 170.04 | MVS
105 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | TSM/005658 | SM/06718 | Retrofitting | 28/08/2020 | 1460 | 94.59 | Yes | 94.59 |  | 12/10/2020 | 10 | 173.15 | MVS
106 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme | TSM/005655 | SM/06720 | Retrofitting | 28/08/2020 | 1413 | 92.54 | Yes | 92.54 |  | 12/10/2020 | 9 | 208.52 | MVS
107 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | TSM/006746 | SM/07883 | Retrofitting | 04/12/2020 | 2184 | 140.91 | Yes | 140.91 | 27/06/2024 | 13/09/2024 | 9 | 144.2 | MVS
108 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | TSM/006745 | SM/07884 | Retrofitting | 04/12/2020 | 2203 | 135.21 | Yes | 135.21 | 20/08/2025 | 30/05/2025 | 6 | 170.22 | MVS
109 | HOWRAH | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | TSM/008595 | SM/09586 | Augmentation | 08/10/2021 | 3440 | 600.2 | Yes | 600.2 | 21/10/2024 | 27/11/2024 | 18 | 510.01 | MVS
110 | HOWRAH | Howrah Division | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS. | TSM/008212 | SM/09105 | Retrofitting | 19/08/2021 | 1033 | 94.09 | Yes | 94.09 |  | 07/12/2022 | 1 | 4.7 | MVS
111 | HOWRAH | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | TSM/011420 | SM/11007 | New | 25/04/2022 | 1774 | 697.67 | Yes | 697.67 | 17/12/2024 | 10/06/2024 | 14 | 598.94 | MVS
112 | HOWRAH | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | TSM/011584 | SM/12562 | New | 25/04/2022 | 5151 | 1842.31 | Yes | 1842.31 | 09/04/2025 | 02/06/2025 | 10 | 1721.07 | MVS
113 | HOWRAH | Howrah Division | Baniara PWSS with provision of FHTC connection | TSM/010919 | SM/11722 | New | 25/04/2022 | 1976 | 684 | Yes | 803.44 | 13/09/2022 | 12/08/2022 | 10 | 730.25 | MVS
114 | HOWRAH | Howrah Division | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | TSM/011491 | SM/11853 | New | 20/05/2022 | 3518 | 999.39 | Yes | 1056.32 | 24/02/2025 | 21/06/2024 | 13 | 885.36 | MVS
115 | HOWRAH | Howrah Division | Rampur PWSS | TSM/008769 | SM/11168 | Augmentation | 16/03/2022 | 1965 | 579.86 | Yes | 614.27 | 15/03/2024 | 03/05/2023 | 12 | 365.19 | MVS
116 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme | TSM/005649 | SM/06716 | Retrofitting | 28/08/2020 | 1375 | 93.35 | Yes | 93.35 |  | 04/11/2020 | 8 | 191.61 | MVS
117 | HOWRAH | Howrah Division | Sealdanga Piped Water Supply Scheme | TSM/018484 | SM/14866 | New | 16/11/2022 | 1709 | 689.76 | Yes | 689.76 | 05/05/2025 | 04/04/2023 | 10 | 566.21 | MVS
118 | HOWRAH | Howrah Division | Charkata Pukuria Piped Water Supply Scheme | TSM/016153 | SM/15290 | New | 26/09/2022 | 54 | 42.1 | Yes | 42.1 | 26/09/2023 |  | 0 | 0 | MVS
119 | HOWRAH | Howrah Division | Bhandardah PWSS with provision of FHTC connection | TSM/010904 | SM/14197 | New | 16/03/2022 | 3527 | 999.92 | Yes | 1149.77 |  | 27/11/2024 | 7 | 922.52 | MVS
120 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | TSM/006298 | SM/07467 | Retrofitting | 25/09/2020 | 3453 | 232.33 | Yes | 232.33 |  | 17/09/2021 | 20 | 319.94 | MVS
121 | HOWRAH | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | TSM/011909 | SM/17175 | New | 20/05/2022 | 3610 | 986.69 | Yes | 986.69 | 17/12/2024 | 02/05/2023 | 8 | 877.35 | MVS
122 | HOWRAH | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | TSM/021371 | SM/18842 | Augmentation | 10/03/2023 | 0 | 222.01 | Yes | 222.01 | 17/12/2024 | 26/06/2024 | 7 | 195.82 | MVS
123 | HOWRAH | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | TSM/021367 | SM/18843 | Augmentation | 10/03/2023 | 0 | 145.28 | Yes | 145.28 | 09/04/2025 | 26/06/2024 | 9 | 150.79 | MVS
124 | HOWRAH | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme | TSM/021380 | SM/18882 | Augmentation | 10/03/2023 | 0 | 251.54 | Yes | 251.54 | 17/02/2024 | 24/06/2024 | 7 | 148.69 | MVS
125 | HOWRAH | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | TSM/015233 | SM/18747 | New | 09/09/2022 | 3464 | 1102.79 | Yes | 1102.79 | 08/03/2025 | 16/08/2022 | 9 | 1783.16 | MVS
126 | HOWRAH | Howrah Division | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. | TSM/015619 | SM/18748 | New | 09/09/2022 | 5855 | 1400.74 | Yes | 1400.74 | 21/03/2023 | 16/08/2022 | 2 | 49.29 | MVS
127 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II | TSM/006294 | SM/07464 | Retrofitting | 25/09/2020 | 2472 | 164.03 | Yes | 164.03 | 17/12/2024 | 05/01/2021 | 4 | 98.76 | MVS
128 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | TSM/005351 | SM/07931 | Anganwadi | 05/11/2019 | 94793 | 278.52 | Yes | 278.52 | 29/07/2024 | 29/02/2024 | 6 | 26.23 | MVS
129 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | TSM/005643 | SM/06783 | Retrofitting | 28/08/2020 | 1340 | 83.47 | Yes | 83.47 |  | 09/11/2020 | 7 | 173.02 | MVS
130 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | TSM/005648 | SM/06713 | Retrofitting | 28/08/2020 | 846 | 63.09 | Yes | 63.09 |  | 04/11/2020 | 6 | 155.31 | MVS
131 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | TSM/006295 | SM/07010 | Retrofitting | 25/09/2020 | 1457 | 99.28 | Yes | 99.28 |  | 27/11/2020 | 8 | 162.81 | MVS
132 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | TSM/005666 | SM/06780 | Retrofitting | 28/08/2020 | 1200 | 77.58 | Yes | 77.58 |  | 13/07/2021 | 22 | 161.1 | MVS
133 | HOWRAH | Howrah Division | Sinking of Eight (08) Nos DWP ( Mark-II) Hand Tube Wells 100 mm x 40 mm dia 230 mtr deep within Sankrail Panchayat Samity under Howrah Division, PHE Dte in connection with super cyclone YAAS | TSM/008962 | SM/09352 | Disaster | 29/09/2021 | 0 | 15.87 | Yes | 15.87 |  | 31/01/2022 | 3 | 42.64 | MVS
134 | HOWRAH | Howrah Division | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | TSM/005659 | SM/08582 | Retrofitting | 28/08/2020 | 45330 | 3304.1 | Yes | 3304.1 | 20/08/2025 | 20/01/2023 | 184 | 3454.33 | MVS
135 | HOWRAH | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | TSM/011600 | SM/11000 | New | 25/04/2022 | 3323 | 965.98 | Yes | 965.98 | 13/09/2024 | 04/09/2023 | 22 | 951.89 | MVS
136 | HOWRAH | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | TSM/010688 | SM/11159 | Augmentation | 16/03/2022 | 3297 | 996.91 | Yes | 1084.15 | 12/02/2025 | 07/05/2024 | 24 | 987.13 | MVS
137 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | TSM/011679 | SM/11221 | New | 25/04/2022 | 1985 | 564.56 | Yes | 612.7 | 13/09/2024 | 08/05/2023 | 17 | 539.17 | MVS
138 | HOWRAH | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | TSM/011001 | SM/11573 | New | 30/03/2022 | 2942 | 767.48 | Yes | 808.74 | 24/02/2025 | 22/04/2025 | 21 | 364.92 | MVS
139 | HOWRAH | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | TSM/015228 | SM/13750 | New | 09/09/2022 | 1101 | 524.14 | Yes | 524.14 | 14/01/2025 | 20/04/2023 | 10 | 482.11 | MVS
140 | HOWRAH | Howrah Division | Sibpur Piped Water Supply Scheme. | TSM/014685 | SM/13769 | New | 22/08/2022 | 1174 | 597.87 | Yes | 597.87 | 13/09/2024 | 18/04/2023 | 9 | 458.64 | MVS
141 | HOWRAH | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | TSM/012056 | SM/13770 | New | 22/08/2022 | 1774 | 792.12 | Yes | 792.12 | 05/05/2025 | 21/04/2023 | 14 | 411.26 | MVS
142 | HOWRAH | Howrah Division | Khadinan Piped Water Supply Scheme | TSM/015626 | SM/13847 | New | 09/09/2022 | 2051 | 791.35 | Yes | 791.35 | 31/07/2024 | 27/04/2023 | 8 | 452.41 | MVS
143 | HOWRAH | Howrah Division | Matinala Piped Water Supply Scheme | TSM/016162 | SM/15285 | New | 26/09/2022 | 4568 | 797.05 | Yes | 797.05 | 20/08/2025 | 09/09/2024 | 15 | 712.85 | MVS
144 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006749 | SM/07880 | Retrofitting | 04/12/2020 | 2452 | 157.59 | Yes | 157.59 | 29/03/2023 | 10/05/2023 | 6 | 271.31 | MVS
145 | HOWRAH | Howrah Division | Ghuteghari Piped Water Supply Scheme | TSM/018482 | SM/17198 | New | 28/12/2022 | 77 | 55.7 | Yes | 55.7 | 13/09/2024 | 21/07/2022 | 2 | 3.47 | MVS
146 | HOWRAH | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | TSM/011637 | SM/18562 | New | 22/08/2022 | 3924 | 1384.19 | Yes | 1384.19 | 20/08/2025 | 06/11/2024 | 19 | 814.29 | MVS
147 | HOWRAH | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | TSM/012815 | SM/18490 | New | 22/08/2022 | 1254 | 497.17 | Yes | 497.17 | 05/05/2025 | 22/04/2025 | 7 | 437.64 | MVS
148 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | TSM/006296 | SM/07008 | Retrofitting | 25/09/2020 | 1500 | 98.14 | Yes | 98.14 | 17/12/2024 | 06/05/2022 | 8 | 98.51 | MVS
149 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | TSM/005667 | SM/06781 | Retrofitting | 28/08/2020 | 1050 | 69.04 | Yes | 69.04 |  | 05/11/2020 | 8 | 88.39 | MVS
150 | HOWRAH | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | TSM/005651 | SM/06789 | Retrofitting | 28/08/2020 | 777 | 59.15 | Yes | 59.15 |  | 15/06/2022 | 13 | 112.65 | MVS
151 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | TSM/005661 | SM/06775 | Retrofitting | 28/08/2020 | 1593 | 99.82 | Yes | 99.82 |  | 25/08/2020 | 49 | 226.12 | MVS
152 | HOWRAH | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | TSM/005664 | SM/06778 | Retrofitting | 28/08/2020 | 1590 | 99.91 | Yes | 99.91 |  | 16/10/2020 | 21 | 117.37 | MVS
153 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Pancharul | TSM/008635 | SM/09348 | Augmentation | 29/09/2021 | 3479 | 669.08 | Yes | 762.1 | 13/09/2024 | 07/06/2024 | 16 | 679.18 | MVS
154 | HOWRAH | Howrah Division | Rudrapur PWSS with provision of FHTC connection. | TSM/010920 | SM/11515 | New | 30/03/2022 | 2762 | 798.43 | Yes | 914.73 | 17/12/2024 | 25/04/2023 | 16 | 792.89 | MVS
155 | HOWRAH | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | TSM/011688 | SM/11458 | New | 25/04/2022 | 3079 | 1083.63 | Yes | 1187.53 | 17/12/2024 | 08/04/2025 | 40 | 1196.55 | MVS
156 | HOWRAH | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | TSM/011932 | SM/11894 | New | 20/05/2022 | 1819 | 760.71 | Yes | 760.71 | 17/03/2025 | 04/04/2023 | 13 | 723.49 | MVS
157 | HOWRAH | Howrah Division | Gopalpur Piped Water Supply Scheme | TSM/015625 | SM/13748 | New | 09/09/2022 | 1519 | 539.15 | Yes | 539.15 | 13/09/2024 | 08/05/2023 | 11 | 467.19 | MVS
158 | HOWRAH | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | TSM/011795 | SM/11790 | New | 25/04/2022 | 744 | 215.28 | Yes | 215.28 | 18/12/2024 | 10/05/2023 | 17 | 173.16 | MVS
159 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | TSM/012517 | SM/12874 | Augmentation | 20/05/2022 | 4238 | 1303.9 | Yes | 1303.9 | 08/03/2025 | 12/04/2023 | 26 | 1129.3 | MVS
160 | HOWRAH | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015622 | SM/14155 | New | 09/09/2022 | 4308 | 1025.18 | Yes | 1118.67 | 09/04/2025 | 07/05/2024 | 17 | 946.57 | MVS
161 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | TSM/015277 | SM/14154 | Augmentation | 09/09/2022 | 4372 | 1460.26 | Yes | 1460.26 | 05/05/2025 | 04/10/2024 | 20 | 1255.66 | MVS
162 | HOWRAH | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | TSM/006304 | SM/07077 | Retrofitting | 25/09/2020 | 1583 | 99.1 | Yes | 99.1 |  | 13/07/2021 | 12 | 152.47 | MVS
163 | HOWRAH | Howrah Division | Ground Water Based Raspur PWSS | TSM/017956 | SM/18719 | New | 30/09/2022 | 3327 | 1398.26 | Yes | 1398.26 | 06/05/2025 | 08/07/2025 | 9 | 1000.71 | MVS
164 | HOWRAH | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | TSM/021345 | SM/18846 | Augmentation | 10/03/2023 | 0 | 458.77 | Yes | 458.77 | 22/07/2024 | 10/02/2021 | 3 | 103.5 | MVS
165 | HOWRAH | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme | TSM/021552 | SM/18849 | Augmentation | 10/03/2023 | 0 | 115.24 | Yes | 115.24 | 14/01/2025 | 09/07/2024 | 6 | 100.68 | MVS
166 | HOWRAH | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | TSM/014806 | SM/18560 | Augmentation | 22/08/2022 | 5505 | 1424.21 | Yes | 1424.21 | 05/05/2025 | 07/08/2023 | 11 | 1122.63 | MVS
167 | HOWRAH | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | TSM/014879 | SM/18563 | New | 22/08/2022 | 6201 | 1342.84 | Yes | 1342.84 | 13/09/2024 | 20/06/2024 | 10 | 266.5 | MVS
168 | HOWRAH | Howrah Division | Baniban Zone-III Piped water Supply Scheme | TSM/018485 | SM/18564 | New | 28/12/2022 | 3716 | 1606.96 | Yes | 1606.96 | 06/05/2025 | 12/08/2025 | 5 | 1154.78 | MVS
169 | HOWRAH | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | TSM/008639 | SM/10146 | Augmentation | 29/09/2021 | 4553 | 1600.62 | Yes | 1600.62 | 13/09/2024 | 08/07/2024 | 16 | 1719.62 | MVS
170 | HOWRAH | Howrah Division | Enhanced Remuneration, festival Bonus and maintenance of five (05) nos laboratories in Howrah District | TSM/021996 | SM/19078 | Support | 17/08/2023 | 0 | 43.3 | Yes | 43.3 | 06/01/2025 | 13/08/2024 | 24 | 14.94 | MVS
171 | HOWRAH | Howrah Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper Primary Schools, Anganwadi Centers within Howrah District. | TSM/008052 | SM/08990 | Support | 19/08/2021 | 0 | 7.68 | Yes | 7.68 | 28/04/2023 | 12/05/2023 | 5 | 6.65 | MVS
172 | HOWRAH | Howrah Division | Operational Charges of PHED and NGO Managed Laboratories Related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission under Howrah Division, PHE Dte | TSM/013050 | SM/16933 | Support | 05/07/2022 | 0 | 30.12 | Yes | 30.12 | 15/12/2023 | 05/04/2024 | 54 | 29.73 | MVS
173 | HOWRAH | Howrah Division | Third Party Inspection job for Surface Water Based Piped Water Supply Scheme for Shyampur-I and II and Part of Bagnan-I and II and Uluberia -I Block | TSM/013051 | SM/15226 | Support | 05/07/2022 | 0 | 641.78 | Yes | 641.78 |  |  | 0 | 0 | MVS
174 | HOWRAH | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | TSM/005379 | SM/06614 | Support | 05/11/2019 | 0 | 34.05 | Yes | 34.05 | 30/07/2025 | 10/07/2024 | 11 | 44.04 | MVS
175 | HOWRAH | Howrah Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | TSM/008130 | SM/08988 | Support | 19/08/2021 | 0 | 23.7 | Yes | 23.7 |  |  | 0 | 0 | MVS
176 | HOWRAH | Howrah Division | Chemical Glassware and Instrument Requirement of Howrah District Laboratory for NABL Accreditation under Howrah Division PHE Dte. | TSM/007391 | SM/08684 | Support | 10/02/2021 | 0 | 20.59 | Yes | 20.59 | 30/07/2025 | 01/02/2023 | 7 | 7.33 | MVS
177 | HOWRAH | Howrah Division | Supply delivery and installation of Desktop Computer UPS Scanner Printer etc through Gem portal for the official use under offices of the Executive Engineer and all Sub Divisional office under Howrah Division, PHE Dte | TSM/022144 | SM/19114 | Support | 17/08/2023 | 0 | 71.48 | Yes | 71.48 |  | 07/05/2024 | 8 | 27.42 | MVS
178 | HOWRAH | Howrah Division | Remuneration, Festival Bonus and Maintenance of 5 nos Laboratories in Howrah District related to Water Quality Monitoring and Surveillance activities under Jal Jeevan Mission 2024-2025 | TSM/023406 | SM/19318 | Support | 22/10/2024 | 0 | 51.27 | Yes | 51.27 |  | 31/12/2024 | 2 | 1.55 | MVS
179 | HOWRAH | Howrah Division | Proposed New 9 Nos PHED managed Laboratories in Howrah District related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission 2024-2025 | TSM/023481 |  | Support | 22/10/2024 | 0 | 761.51 | No | 0 |  |  | 0 | 0 | MVS
180 | HOWRAH | Howrah Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Howrah District. | TSM/008144 | SM/08989 | Support | 19/08/2021 | 0 | 280.82 | Yes | 280.82 |  | 22/08/2022 | 1 | 271.44 | MVS
181 | HOWRAH | Howrah Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious and safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Howrah District under Howrah Division, PHE Dte | TSM/022014 | SM/19091 | Support | 17/08/2023 | 0 | 227.03 | Yes | 227.03 | 09/09/2025 | 20/02/2024 | 1 | 57.27 | MVS
182 | HOWRAH | Howrah Division | Regular Upkeepment, upgradation and Day to Day Activities of Mobile Laboratory Van (MLV) | TSM/023260 | SM/19281 | Support | 09/03/2024 | 0 | 37.26 | Yes | 37.26 |  |  | 0 | 0 | MVS
183 | HOWRAH | Howrah Division | Drinking Water sample collection and testing through field Test Kits (FTKs) and uploading charges for the same related to water quality Monitoring and surveillance programme under Jal Jeevan Mission, Howrah Division, PHE Dte | TSM/020591 | SM/18274 | Support | 10/03/2023 | 0 | 125.26 | Yes | 125.26 |  | 15/01/2024 | 1 | 25.16 | MVS
184 | HOWRAH | Howrah Division | Procurement of Mobile Laboratory Van(MLV) under Water Quality Monitoring and Surveillance Programme related to Jal Jeevan Mission, Howrah Division, PHE Dte | TSM/015331 |  | Support | 09/09/2022 | 0 | 78.13 | No | 0 |  |  | 0 | 0 | MVS
Total | [7 empty] | 893795 | 193940.52 |  | 194944.43 |  |  | 2252 | 126467.71