## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S | TSM/006805 | SM/07411 | Retrofitting | 04/12/2020 | 2943 | 92.29 | Yes | 92.29 |  | 07/07/2021 | 2 | 404.54 | MVS
2 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | TSM/006858 | SM/07413 | Retrofitting | 04/12/2020 | 1957 | 82.02 | Yes | 82.02 |  | 14/10/2020 | 7 | 34.39 | MVS
3 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme incl | TSM/006803 | SM/07410 | Retrofitting | 04/12/2020 | 880 | 49.5 | Yes | 49.5 |  | 24/01/2024 | 1 | 5.42 | MVS
4 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | TSM/005828 | SM/08120 | Retrofitting | 25/09/2020 | 1666 | 389.87 | Yes | 389.87 |  | 24/02/2021 | 6 | 401.94 | MVS
5 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | TSM/005829 | SM/08122 | Retrofitting | 25/09/2020 | 1203 | 357.03 | Yes | 357.03 |  | 12/05/2021 | 3 | 362.53 | MVS
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection for Betuabati W/S Scheme under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur | TSM/006116 | SM/07052 | Retrofitting | 25/09/2020 | 1090 | 68.39 | Yes | 68.39 |  | 21/12/2020 | 3 | 153.89 | MVS
7 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | TSM/006869 | SM/07629 | Retrofitting | 04/12/2020 | 3199 | 272.76 | Yes | 272.76 | 10/12/2024 | 12/05/2022 | 37 | 246.23 | MVS
8 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o | TSM/006863 | SM/07591 | Retrofitting | 04/12/2020 | 1075 | 66.06 | Yes | 66.06 |  | 17/03/2022 | 2 | 17.97 | MVS
9 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | TSM/006875 | SM/07592 | Retrofitting | 04/12/2020 | 1675 | 95.32 | Yes | 95.32 |  | 18/02/2021 | 3 | 147.3 | MVS
10 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | TSM/008679 | SM/09425 | Retrofitting | 29/09/2021 | 5866 | 286.94 | Yes | 286.94 |  | 07/04/2022 | 6 | 448.62 | MVS
11 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007690 | SM/08793 | Retrofitting | 19/02/2021 | 1753 | 66.55 | Yes | 66.55 |  | 25/07/2025 | 3 | 22.44 | MVS
12 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | TSM/007688 | SM/08794 | Retrofitting | 19/02/2021 | 3972 | 208.29 | Yes | 208.29 | 26/09/2024 | 24/08/2021 | 11 | 73.29 | MVS
13 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/009099 | SM/09555 | Retrofitting | 08/10/2021 | 2196 | 175.13 | Yes | 175.13 | 04/03/2024 | 18/12/2023 | 6 | 167.1 | MVS
14 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | TSM/008288 | SM/09471 | Retrofitting | 19/08/2021 | 2421 | 162.44 | Yes | 162.44 |  | 07/07/2021 | 7 | 41.45 | MVS
15 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | TSM/008304 | SM/09512 | Retrofitting | 19/08/2021 | 1957 | 102.7 | Yes | 102.7 | 20/01/2023 | 22/11/2021 | 6 | 109.6 | MVS
16 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | TSM/008305 | SM/09513 | Retrofitting | 19/08/2021 | 1573 | 106.53 | Yes | 106.53 | 29/09/2023 | 16/09/2021 | 6 | 132.01 | MVS
17 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | TSM/008307 | SM/09515 | Retrofitting | 19/08/2021 | 2491 | 125.82 | Yes | 125.82 |  | 13/07/2022 | 14 | 164.88 | MVS
18 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/009100 | SM/09556 | Retrofitting | 08/10/2021 | 252 | 21.75 | Yes | 21.75 | 09/01/2025 | 29/12/2023 | 6 | 40.25 | MVS
19 | SOUTH 24 PARGANAS | Alipore Division | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | TSM/009241 | SM/10534 | Augmentation | 27/01/2022 | 1769 | 208.5 | Yes | 208.5 | 06/08/2024 | 29/09/2023 | 5 | 224.42 | MVS
20 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | TSM/009341 | SM/10116 | School | 16/12/2021 | 0 | 879.72 | Yes | 879.72 |  | 12/07/2022 | 57 | 801 | MVS
21 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including | TSM/008428 | SM/09076 | Retrofitting | 08/09/2021 | 1169 | 120.65 | Yes | 120.65 |  | 23/03/2022 | 2 | 123.18 | MVS
22 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | TSM/009338 | SM/10119 | School | 16/12/2021 | 0 | 546.43 | Yes | 546.43 |  | 15/02/2022 | 12 | 503.16 | MVS
23 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008296 | SM/09952 | Retrofitting | 19/08/2021 | 200 | 65.43 | Yes | 65.43 | 21/12/2022 | 25/10/2021 | 3 | 84.85 | MVS
24 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | TSM/008684 | SM/09095 | Retrofitting | 08/09/2021 | 4630 | 261.46 | Yes | 261.46 |  | 11/02/2023 | 4 | 398.28 | MVS
25 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009237 | SM/10092 | Augmentation | 22/11/2021 | 4770 | 1160.08 | Yes | 1160.08 | 21/10/2024 | 13/07/2023 | 17 | 970.95 | MVS
26 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011196 | SM/11503 | New | 30/03/2022 | 924 | 467.26 | Yes | 467.26 | 23/02/2024 | 18/09/2023 | 16 | 364.59 | MVS
27 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | TSM/009222 | SM/09974 | Retrofitting | 22/11/2021 | 2745 | 164.33 | Yes | 164.33 |  | 31/10/2023 | 5 | 26.75 | MVS
Total | [7 empty] | 54376 | 6603.23 |  | 6603.23 |  |  | 250 | 6471.03