## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | JALPAIGURI | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | TSM/005789 | SM/06837 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 1080 | 61.53 | Yes | 61.53 | 05/01/2024 | 18/11/2020 | 10 | 109.04 | 127.39 | MVS
2 | JALPAIGURI | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | TSM/005790 | SM/06838 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 1664 | 92.26 | Yes | 92.26 | 13/10/2023 | 15/10/2020 | 7 | 82.81 | 94.17 | MVS
3 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | TSM/005792 | SM/06839 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 1671 | 99.99 | Yes | 99.99 | 22/02/2024 | 05/07/2021 | 9 | 81.88 | 149.5 | MVS
4 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | TSM/005793 | SM/06840 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 1362 | 74.02 | Yes | 74.02 | 13/10/2023 | 18/11/2020 | 11 | 93.34 | 142.26 | MVS
5 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme | TSM/005795 | SM/06841 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 1671 | 89.57 | Yes | 89.57 | 22/02/2024 | 15/10/2020 | 7 | 61.61 | 152.55 | MVS
6 | JALPAIGURI | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme | TSM/005797 | SM/06842 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/08/2020 | 873 | 48.73 | Yes | 48.73 | 12/10/2023 | 02/11/2020 | 2 | 48.19 | 20.56 | MVS
7 | JALPAIGURI | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme | TSM/005798 | SM/06843 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 28/08/2020 | 925 | 52.3 | Yes | 52.3 | 12/10/2023 | 23/11/2020 | 1 | 39.75 | 15.72 | MVS
8 | JALPAIGURI | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/005799 | SM/06844 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/08/2020 | 1082 | 57.04 | Yes | 57.04 | 12/10/2023 | 18/11/2020 | 6 | 90.2 | 111.59 | MVS
9 | JALPAIGURI | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | TSM/005800 | SM/06845 | Retrofitting |  |  |  | 28/08/2020 | 1118 | 60.77 | Yes | 60.77 | 22/02/2024 | 14/07/2022 | 4 | 29.44 | 123.03 | MVS
10 | JALPAIGURI | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | TSM/005801 | SM/06846 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/08/2020 | 632 | 37.11 | Yes | 37.11 | 12/10/2023 | 13/04/2021 | 8 | 44.51 | 80.29 | MVS
11 | JALPAIGURI | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme | TSM/005802 | SM/06847 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/08/2020 | 1019 | 56.03 | Yes | 56.03 | 12/10/2023 | 18/11/2020 | 2 | 60.62 | 89.99 | MVS
12 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | TSM/005796 | SM/06936 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 2332 | 126.48 | Yes | 126.48 | 13/10/2023 | 13/07/2023 | 10 | 157.5 | 185.61 | MVS
13 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | TSM/005794 | SM/06937 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 2431 | 129.58 | Yes | 129.58 | 22/02/2024 | 15/10/2020 | 11 | 134.35 | 144.65 | MVS
14 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | TSM/005791 | SM/06938 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/08/2020 | 1976 | 106.41 | Yes | 106.41 | 22/02/2024 | 15/10/2020 | 12 | 121.47 | 110.32 | MVS
15 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006195 | SM/06952 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 1257 | 65.98 | Yes | 65.98 | 12/10/2023 | 31/12/2020 | 3 | 39.93 | 130.74 | MVS
16 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | TSM/006201 | SM/06953 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 917 | 48.9 | Yes | 48.9 | 12/10/2023 | 12/04/2023 | 4 | 92.38 | 95.76 | MVS
17 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006193 | SM/06954 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 607 | 34.5 | Yes | 34.5 | 12/10/2023 | 01/09/2022 | 2 | 32.1 | 116.82 | MVS
18 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006191 | SM/06955 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 1205 | 62.52 | Yes | 62.52 | 12/10/2023 | 31/12/2020 | 4 | 59.2 | 143.6 | MVS
19 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006190 | SM/06956 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 1225 | 64.77 | Yes | 64.77 | 12/08/2024 | 13/05/2021 | 5 | 70.65 | 128.99 | MVS
20 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | TSM/006203 | SM/06957 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 640 | 36 | Yes | 36 | 08/02/2024 | 19/01/2022 | 3 | 27.63 | 71.25 | MVS
21 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | TSM/006192 | SM/06958 | Retrofitting |  |  |  | 25/09/2020 | 1745 | 99.31 | Yes | 99.31 | 13/10/2023 | 06/01/2021 | 6 | 116.9 | 234.21 | MVS
22 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | TSM/006211 | SM/06959 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 25/09/2020 | 914 | 57.13 | Yes | 57.13 | 13/10/2023 | 18/11/2020 | 5 | 70.38 | 237.44 | MVS
23 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme | TSM/006214 | SM/06960 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 25/09/2020 | 1692 | 99.43 | Yes | 99.43 | 13/10/2023 | 04/10/2021 | 3 | 8.94 | 10.51 | MVS
24 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme | TSM/006215 | SM/06961 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 25/09/2020 | 1259 | 75.45 | Yes | 75.45 | 13/10/2023 | 31/12/2020 | 2 | 25.75 | 70.26 | MVS
25 | JALPAIGURI | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme | TSM/006355 | SM/07028 | Retrofitting | Siliguri Sub-Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | 25/09/2020 | 1531 | 96.79 | Yes | 96.79 |  | 11/11/2024 | 2 | 1 | 100.07 | MVS
26 | JALPAIGURI | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Porjhar Piped water Supply Scheme. | TSM/006354 | SM/07044 | Retrofitting | Siliguri Sub-Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | 25/09/2020 | 1540 | 93.9 | Yes | 93.9 | 18/06/2021 | 16/12/2023 | 1 | 1.03 | 0.48 | MVS
27 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | TSM/006198 | SM/07301 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 240 | 30.18 | Yes | 30.18 | 12/10/2023 | 12/05/2021 | 5 | 11 | 60.24 | MVS
28 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | TSM/006213 | SM/07303 | Retrofitting |  |  |  | 25/09/2020 | 1296 | 89.78 | Yes | 89.78 | 13/10/2023 | 06/01/2021 | 7 | 122.11 | 206.83 | MVS
29 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme | TSM/006216 | SM/07304 | Retrofitting |  |  |  | 25/09/2020 | 447 | 36.39 | Yes | 36.39 | 13/10/2023 | 22/12/2020 | 3 | 43.13 | 143.73 | MVS
30 | JALPAIGURI | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | TSM/006751 | SM/07891 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 04/12/2020 | 4696 | 285.66 | Yes | 285.66 | 13/10/2023 | 02/07/2021 | 11 | 263.46 | 91.23 | MVS
31 | JALPAIGURI | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | TSM/006750 | SM/07892 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 04/12/2020 | 1950 | 131.79 | Yes | 131.79 | 13/10/2023 | 03/12/2021 | 8 | 134.54 | 96.72 | MVS
32 | JALPAIGURI | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | TSM/006752 | SM/07893 | Retrofitting |  |  |  | 04/12/2020 | 2191 | 133.21 | Yes | 133.21 | 26/03/2025 | 14/06/2022 | 12 | 111.51 | 83.94 | MVS
33 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | TSM/006189 | SM/08035 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 25/09/2020 | 5856 | 320.18 | Yes | 320.18 | 09/11/2023 | 13/05/2021 | 9 | 198.25 | 133.34 | MVS
34 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | TSM/006194 | SM/08036 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 25/09/2020 | 6704 | 349.29 | Yes | 349.29 | 13/12/2023 | 13/05/2021 | 24 | 341.92 | 313.76 | MVS
35 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | TSM/006196 | SM/08037 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 25/09/2020 | 6385 | 348.32 | Yes | 348.32 | 13/10/2023 | 21/10/2022 | 15 | 246.35 | 315.75 | MVS
36 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | TSM/006206 | SM/08038 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 25/09/2020 | 6473 | 396.46 | Yes | 396.46 | 13/10/2023 | 02/07/2021 | 43 | 614.28 | 407.81 | MVS
37 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | TSM/007024 | SM/08077 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 08/01/2021 | 1080 | 62.08 | Yes | 62.08 | 22/02/2024 | 13/03/2023 | 6 | 114.89 | 81.54 | MVS
38 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block | TSM/007025 | SM/08078 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/01/2021 | 2090 | 136.18 | Yes | 136.18 | 26/03/2025 | 13/05/2021 | 9 | 117.2 | 41.79 | MVS
39 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | TSM/006197 | SM/08284 | Retrofitting | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 25/09/2020 | 2315 | 137.5 | Yes | 137.5 | 12/10/2023 | 22/07/2022 | 10 | 37.79 | 19.02 | MVS
40 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | TSM/006199 | SM/08285 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 25/09/2020 | 5069 | 268.15 | Yes | 268.15 | 07/11/2023 | 13/05/2021 | 28 | 368.82 | 291.94 | MVS
41 | JALPAIGURI | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | TSM/006529 | SM/08578 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 04/12/2020 | 285 | 150.29 | Yes | 150.29 | 12/08/2024 | 24/09/2024 | 6 | 31.99 | 42.87 | MVS
42 | JALPAIGURI | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | TSM/006528 | SM/08579 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 04/12/2020 | 238 | 137.33 | Yes | 137.33 | 02/02/2024 | 05/09/2024 | 8 | 113.29 | 73.63 | MVS
43 | JALPAIGURI | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | TSM/006979 | SM/08581 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/01/2021 | 562 | 172.9 | Yes | 172.9 | 04/09/2024 | 19/12/2024 | 6 | 119.78 | 45.12 | MVS
44 | JALPAIGURI | Ghasmari Piped Water Supply Scheme. | TSM/003951 | SM/08868 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 19/02/2021 | 779 | 293.24 | Yes | 293.24 | 13/03/2024 | 06/02/2023 | 24 | 260.2 | 160.05 | MVS
45 | JALPAIGURI | Indong Tea Garden Area Piped Water Supply Scheme. | TSM/005102 | SM/08873 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 19/02/2021 | 1236 | 311.47 | Yes | 311.47 | 12/08/2024 | 16/06/2022 | 18 | 302.16 | 234.64 | MVS
46 | JALPAIGURI | Bagrakote Tea Garden Area Piped Water Supply Scheme. | TSM/003942 | SM/08874 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/02/2021 | 4594 | 518.37 | Yes | 518.37 | 11/11/2024 | 30/11/2021 | 20 | 526.22 | 239.88 | MVS
47 | JALPAIGURI | Kumlai Tea Garden Area Piped Water Supply Scheme. | TSM/003937 | SM/08875 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/02/2021 | 991 | 303.84 | Yes | 303.84 | 30/07/2024 | 18/08/2023 | 22 | 347.28 | 246.72 | MVS
48 | JALPAIGURI | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | TSM/005491 | SM/08876 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/02/2021 | 3422 | 1136.39 | Yes | 1136.39 | 28/03/2025 | 30/08/2024 | 48 | 1020.47 | 701.33 | MVS
49 | JALPAIGURI | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | TSM/007485 | SM/09099 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/02/2021 | 1369 | 163.94 | Yes | 163.94 | 22/02/2024 | 28/04/2022 | 9 | 159.15 | 113.68 | MVS
50 | JALPAIGURI | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | TSM/007026 | SM/09100 | Retrofitting | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/01/2021 | 4346 | 382.83 | Yes | 382.83 | 13/10/2023 | 05/04/2022 | 9 | 499.88 | 247.22 | MVS
51 | JALPAIGURI | Augmentation of Binnaguri Piped Water Supply Scheme | TSM/008442 | SM/09344 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/09/2021 | 2082 | 871.08 | Yes | 871.08 | 21/02/2025 | 15/03/2023 | 23 | 742.04 | 376.11 | MVS
52 | JALPAIGURI | Augmentation of Domohani Piped Water Supply Scheme | TSM/008382 | SM/09345 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/09/2021 | 2548 | 855.56 | Yes | 855.56 | 30/07/2024 | 20/04/2022 | 24 | 752.85 | 617.79 | MVS
53 | JALPAIGURI | Rejuvenation of Goralbari Piped Water Supply Scheme | TSM/008375 | SM/09390 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 08/09/2021 | 0 | 337.55 | Yes | 337.55 | 06/02/2025 | 26/05/2022 | 34 | 429.63 | 334.94 | MVS
54 | JALPAIGURI | Rejuvenation of Sajnapara Piped Water Supply Scheme | TSM/008378 | SM/09391 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/09/2021 | 0 | 92.36 | Yes | 92.36 | 12/10/2023 | 14/09/2022 | 13 | 49.42 | 30.72 | MVS
55 | JALPAIGURI | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | TSM/008374 | SM/09392 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/09/2021 | 1462 | 290.82 | Yes | 290.82 | 29/07/2024 | 14/06/2022 | 18 | 227.43 | 169.98 | MVS
56 | JALPAIGURI | Rejuvenation of Madhabdanga piped water supply scheme. | TSM/008102 | SM/09456 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 125.38 | Yes | 125.38 | 17/12/2024 | 10/04/2023 | 22 | 110.51 | 107.18 | MVS
57 | JALPAIGURI | Rejuvenation of Kajaldighi piped water supply scheme. | TSM/008110 | SM/09457 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 116.9 | Yes | 116.9 | 25/02/2025 | 06/04/2023 | 12 | 92.71 | 66.48 | MVS
58 | JALPAIGURI | Rejuvenation of Charerbari piped water supply scheme. | TSM/008106 | SM/09458 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 115.93 | Yes | 115.93 | 03/09/2024 | 25/04/2023 | 18 | 122.79 | 97.98 | MVS
59 | JALPAIGURI | Rejuvenation of Dwarikamari piped water supply scheme. | TSM/008109 | SM/09459 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 121.4 | Yes | 121.4 | 06/03/2025 | 20/07/2022 | 25 | 157.86 | 126.98 | MVS
60 | JALPAIGURI | Rejuvenation of Basilardanga piped water supply scheme. | TSM/008103 | SM/09460 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 115.16 | Yes | 115.16 | 22/02/2024 | 18/08/2022 | 20 | 122.63 | 105.01 | MVS
61 | JALPAIGURI | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | TSM/008155 | SM/09461 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 930 | 70.07 | Yes | 70.07 | 11/11/2024 | 03/02/2022 | 10 | 88.87 | 88.91 | MVS
62 | JALPAIGURI | Rejuvenation of Boalmari piped water supply scheme. | TSM/008104 | SM/09462 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 113.6 | Yes | 113.6 | 13/10/2023 | 02/06/2022 | 11 | 108.25 | 108.26 | MVS
63 | JALPAIGURI | Rejuvenation of Porapara piped water supply scheme. | TSM/008108 | SM/09463 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 19/08/2021 | 0 | 121.26 | Yes | 121.26 | 02/02/2024 | 07/04/2022 | 19 | 113.55 | 103.81 | MVS
64 | JALPAIGURI | Rejuvenation of Chakiavita Piped Water Supply Scheme | TSM/008824 | SM/09482 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 119.98 | Yes | 119.98 | 04/09/2024 | 01/06/2023 | 19 | 114.72 | 110.12 | MVS
65 | JALPAIGURI | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | TSM/008993 | SM/09483 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 188.47 | Yes | 188.47 | 28/01/2025 | 18/05/2023 | 7 | 183.18 | 29.87 | MVS
66 | JALPAIGURI | Rejuvenation of Chauhaddi Piped Water Supply Scheme | TSM/009001 | SM/09484 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 226.32 | Yes | 226.32 | 13/10/2023 | 20/04/2022 | 17 | 232.27 | 166.16 | MVS
67 | JALPAIGURI | Rejuvenation of Mallicksova Piped water Supply Scheme | TSM/009006 | SM/09485 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 178.69 | Yes | 178.69 | 24/01/2025 | 28/04/2023 | 20 | 90.19 | 88.01 | MVS
68 | JALPAIGURI | Rejuvenation of Khalaigram Piped Water Supply Scheme | TSM/009016 | SM/09486 | Augmentation | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 66.14 | Yes | 66.14 | 24/01/2025 | 28/04/2023 | 9 | 33.35 | 35.86 | MVS
69 | JALPAIGURI | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | TSM/009024 | SM/09487 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 217.47 | Yes | 217.47 | 28/06/2024 | 20/06/2024 | 23 | 216.93 | 92.07 | MVS
70 | JALPAIGURI | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | TSM/008107 | SM/09518 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 114.34 | Yes | 114.34 | 13/10/2023 | 28/02/2023 | 17 | 112.72 | 78.85 | MVS
71 | JALPAIGURI | Rejuvenation of Mohitnagar piped water supply scheme. | TSM/008105 | SM/09519 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 0 | 122.19 | Yes | 122.19 | 13/10/2023 | 28/04/2022 | 31 | 187.71 | 99.83 | MVS
72 | JALPAIGURI | Augmentation of Purba Daukimari Piped Water Supply Scheme | TSM/008810 | SM/09560 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 1586 | 545.87 | Yes | 545.87 | 12/03/2024 | 08/06/2023 | 18 | 519.22 | 459.48 | MVS
73 | JALPAIGURI | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | TSM/008821 | SM/09561 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 08/10/2021 | 1793 | 681.79 | Yes | 681.79 | 23/12/2024 | 17/01/2023 | 21 | 582.89 | 383.49 | MVS
74 | JALPAIGURI | Augmentation of Shikarpur Piped Water Supply Scheme | TSM/008818 | SM/09562 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 3418 | 977.54 | Yes | 977.54 | 16/04/2025 | 25/01/2024 | 23 | 774 | 309.76 | MVS
75 | JALPAIGURI | Augmentation of Kathapara Piped Water Supply Scheme | TSM/008819 | SM/09563 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 2665 | 834.88 | Yes | 834.88 | 24/01/2025 | 21/07/2023 | 23 | 571.59 | 218.56 | MVS
76 | JALPAIGURI | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | TSM/008823 | SM/09564 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 139.18 | Yes | 139.18 | 13/10/2023 | 14/09/2022 | 16 | 87.9 | 65.56 | MVS
77 | JALPAIGURI | Rejuvenation of Mainatali Piped Water Supply Scheme | TSM/008825 | SM/09565 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/10/2021 | 0 | 104.11 | Yes | 104.11 | 12/03/2024 | 18/05/2023 | 12 | 83.78 | 51.18 | MVS
78 | JALPAIGURI | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/009023 | SM/09858 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/11/2021 | 0 | 171.5 | Yes | 171.5 | 12/10/2023 | 04/04/2022 | 10 | 124.96 | 99.67 | MVS
79 | JALPAIGURI | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | TSM/009021 | SM/09859 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/11/2021 | 0 | 114.69 | Yes | 114.69 | 26/03/2025 | 01/06/2023 | 20 | 101.9 | 55.81 | MVS
80 | JALPAIGURI | Augmentation of Gairkata Piped Water Supply Scheme | TSM/008816 | SM/09860 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/11/2021 | 1787 | 480.53 | Yes | 480.53 | 24/01/2025 | 28/04/2023 | 13 | 404.65 | 100.58 | MVS
81 | JALPAIGURI | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | TSM/008817 | SM/09861 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/11/2021 | 2219 | 696.59 | Yes | 696.59 | 03/09/2024 | 05/04/2022 | 16 | 635.83 | 561.48 | MVS
82 | JALPAIGURI | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | TSM/009019 | SM/09862 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/11/2021 | 0 | 105.33 | Yes | 105.33 | 26/03/2025 | 25/07/2022 | 12 | 77.19 | 83.78 | MVS
83 | JALPAIGURI | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | TSM/009020 | SM/09863 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/11/2021 | 0 | 172.79 | Yes | 172.79 | 24/01/2025 | 29/04/2022 | 21 | 158.44 | 117.92 | MVS
84 | JALPAIGURI | Augmentation of Purbba Batabari Piped Water Supply Scheme | TSM/009026 | SM/09864 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/11/2021 | 1795 | 810.11 | Yes | 810.11 | 10/07/2025 | 04/04/2022 | 33 | 450.11 | 487.21 | MVS
85 | JALPAIGURI | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | TSM/009018 | SM/09865 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/11/2021 | 0 | 110.47 | Yes | 110.47 | 26/03/2025 | 31/05/2022 | 19 | 114.69 | 94.93 | MVS
86 | JALPAIGURI | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | TSM/003950 | SM/09975 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/02/2021 | 1906 | 385.01 | Yes | 385.01 | 29/07/2024 | 13/06/2024 | 32 | 327.75 | 229.28 | MVS
87 | JALPAIGURI | Augmentation of Kranti Piped water supply Scheme | TSM/008381 | SM/09994 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 08/09/2021 | 5563 | 1755.8 | Yes | 1755.8 | 26/03/2025 | 23/02/2023 | 34 | 1546.31 | 1000.63 | MVS
88 | JALPAIGURI | Augmentation of Sukani Piped Water Supply Scheme | TSM/008383 | SM/09995 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/09/2021 | 14294 | 4370.14 | Yes | 4370.14 | 26/03/2025 | 12/06/2024 | 99 | 4303.52 | 2615.13 | MVS
89 | JALPAIGURI | Augmentation of Sannyasikata Piped Water Supply Scheme | TSM/008408 | SM/09996 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 08/09/2021 | 6379 | 2105.11 | Yes | 2105.11 | 28/06/2024 | 28/08/2024 | 43 | 1771.51 | 1474.23 | MVS
90 | JALPAIGURI | Augmentation of Madhya Khagrabari Water Supply Scheme. | TSM/006969 | SM/10028 | Augmentation | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 19/08/2021 | 3594 | 986.41 | Yes | 986.41 | 30/08/2024 | 25/03/2023 | 34 | 837.88 | 744.26 | MVS
91 | JALPAIGURI | Augmentation of Ramsai Water Supply Scheme. | TSM/006970 | SM/10033 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 3250 | 976.19 | Yes | 976.19 | 30/07/2024 | 01/11/2022 | 21 | 879.23 | 753.72 | MVS
92 | JALPAIGURI | Augmentation of Maynaguri Piped Water Supply Scheme. | TSM/006968 | SM/10042 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 19/08/2021 | 7191 | 978.7 | Yes | 978.7 | 15/01/2025 | 17/05/2023 | 49 | 905.04 | 564.17 | MVS
93 | JALPAIGURI | Augmentation of Jalapara Piped Water Supply Scheme | TSM/009324 | SM/10043 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/12/2021 | 1573 | 620.86 | Yes | 620.86 | 03/09/2024 | 28/04/2023 | 9 | 580.02 | 350.68 | MVS
94 | JALPAIGURI | Augmentation of Banerhat Bazar Piped Water Supply Scheme | TSM/009726 | SM/10044 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/12/2021 | 3913 | 671.77 | Yes | 671.77 | 29/01/2025 | 12/06/2024 | 27 | 583.69 | 439.69 | MVS
95 | JALPAIGURI | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | TSM/009749 | SM/10069 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/12/2021 | 0 | 243.7 | Yes | 243.7 | 28/03/2025 | 07/03/2024 | 15 | 236.73 | 171.25 | MVS
96 | JALPAIGURI | Rejuvenation of Hila Tea Garden area piped water supply scheme | TSM/009745 | SM/10070 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/12/2021 | 0 | 208.35 | Yes | 208.35 | 28/03/2025 | 10/05/2023 | 24 | 198.1 | 151.33 | MVS
97 | JALPAIGURI | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | TSM/009317 | SM/10071 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/12/2021 | 1235 | 521.15 | Yes | 521.15 | 28/03/2025 | 05/04/2022 | 15 | 446.28 | 296.98 | MVS
98 | JALPAIGURI | Augmentation of Dakshin Berubari Water Supply Scheme. | TSM/006972 | SM/10086 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 4905 | 1574.27 | Yes | 1574.27 | 06/03/2025 | 19/09/2023 | 27 | 1221.17 | 842.17 | MVS
99 | JALPAIGURI | Augmentation of Mondalghat Water Supply Scheme. | TSM/006973 | SM/10087 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 3793 | 1095.64 | Yes | 1095.64 | 13/10/2023 | 25/04/2023 | 20 | 712.97 | 689.74 | MVS
100 | JALPAIGURI | Augmentation of Kharija-Berubari Water Supply Scheme. | TSM/006967 | SM/10088 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 5781 | 2064.37 | Yes | 2064.37 | 11/11/2024 | 13/09/2023 | 26 | 1793.7 | 1264.19 | MVS
101 | JALPAIGURI | Augmentation of Baikur Piped Water Supply Scheme. | TSM/006971 | SM/10089 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 7173 | 1763.64 | Yes | 1763.64 | 30/07/2024 | 10/10/2023 | 42 | 1597.76 | 1258.88 | MVS
102 | JALPAIGURI | Augmentation of Barnes Water Supply Scheme. | TSM/006966 | SM/10090 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 19/08/2021 | 4046 | 1115.54 | Yes | 1115.54 | 30/08/2024 | 17/05/2023 | 39 | 1199 | 968.14 | MVS
103 | JALPAIGURI | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | TSM/009977 | SM/10775 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/03/2022 | 783 | 536.12 | Yes | 536.12 |  | 01/06/2022 | 1 | 355.27 | 74.74 | MVS
104 | JALPAIGURI | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/009995 | SM/11812 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 27/01/2022 | 1206 | 94.73 | Yes | 94.73 | 14/08/2024 | 20/07/2022 | 10 | 84.26 | 44.74 | MVS
105 | JALPAIGURI | REJUVENATION OF METELIBAZAR PWSS | TSM/009996 | SM/11813 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 27/01/2022 | 1904 | 721.07 | Yes | 721.07 | 16/04/2025 | 06/04/2023 | 24 | 395.13 | 206.11 | MVS
106 | JALPAIGURI | AUGMENTATION OF LUKSAN BAZAR PWSS | TSM/009997 | SM/11814 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 27/01/2022 | 1895 | 616.25 | Yes | 616.25 | 26/03/2025 | 17/05/2023 | 37 | 381.65 | 203.51 | MVS
107 | JALPAIGURI | Augmentation of Bhatipara Water Supply Scheme | TSM/009740 | SM/13277 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/12/2021 | 5116 | 1483.83 | Yes | 1483.83 | 16/04/2025 | 08/05/2023 | 33 | 1285.86 | 716.59 | MVS
108 | JALPAIGURI | Augmentation of Lataguri Piped Water Supply Scheme | TSM/009331 | SM/13278 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/12/2021 | 4977 | 1834.7 | Yes | 1834.7 | 28/03/2025 | 10/08/2023 | 59 | 1413.99 | 1313.97 | MVS
109 | JALPAIGURI | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | TSM/015307 | SM/13681 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 2185 | 807.25 | Yes | 807.25 | 24/01/2025 | 16/01/2025 | 10 | 156.33 | 234.05 | MVS
110 | JALPAIGURI | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015312 | SM/13682 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 1332 | 544.59 | Yes | 544.59 | 18/02/2025 | 18/09/2025 | 7 | 412.84 | 46.29 | MVS
111 | JALPAIGURI | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | TSM/015421 | SM/13700 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 09/09/2022 | 1413 | 661.12 | Yes | 661.12 | 17/12/2024 | 03/04/2024 | 12 | 216.74 | 345.41 | MVS
112 | JALPAIGURI | GAURGRAM PIPED WATER SUPPLY SCHEME | TSM/015420 | SM/13701 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 09/09/2022 | 1472 | 594.88 | Yes | 594.88 | 17/12/2024 | 03/04/2024 | 15 | 540.56 | 386.73 | MVS
113 | JALPAIGURI | MAHANBHITA PIPED WATER SUPPLY SCHEME | TSM/015639 | SM/13702 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 2113 | 868.48 | Yes | 868.48 | 29/07/2024 | 26/05/2023 | 16 | 747.87 | 367.03 | MVS
114 | JALPAIGURI | BARA DIGHI PIPED WATER SUPPLY SCHEME | TSM/015677 | SM/13703 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 09/09/2022 | 210 | 156.26 | Yes | 156.26 | 29/08/2024 | 01/08/2024 | 6 | 119.13 | 89.79 | MVS
115 | JALPAIGURI | SHAKATI PIPED WATER SUPPLY SCHEME | TSM/015419 | SM/13704 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 09/09/2022 | 2042 | 557.7 | Yes | 557.7 | 25/02/2025 | 03/04/2024 | 14 | 470.05 | 314.76 | MVS
116 | JALPAIGURI | BRAHMAPUR PIPED WATER SUPPLY SCHEME | TSM/015422 | SM/13705 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 09/09/2022 | 2545 | 988.14 | Yes | 988.14 | 11/03/2025 | 07/08/2024 | 15 | 912.92 | 320.51 | MVS
117 | JALPAIGURI | AMGURI PIPED WATER SUPPLY SCHEME | TSM/015418 | SM/13706 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 09/09/2022 | 2373 | 891.35 | Yes | 891.35 | 26/03/2025 | 14/08/2024 | 14 | 279.59 | 514.78 | MVS
118 | JALPAIGURI | Augmentation of Odlabari Piped Water Supply Scheme | TSM/009742 | SM/13790 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 27/01/2022 | 3348 | 1003.52 | Yes | 1003.52 | 28/03/2025 | 05/04/2022 | 30 | 890.95 | 573.1 | MVS
119 | JALPAIGURI | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | TSM/015372 | SM/13898 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 1809 | 906.72 | Yes | 906.72 | 24/01/2025 | 10/04/2023 | 15 | 1033.91 | 723.56 | MVS
120 | JALPAIGURI | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | TSM/015326 | SM/13899 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 1798 | 772.86 | Yes | 772.86 | 06/03/2025 | 24/05/2023 | 14 | 696.04 | 532.15 | MVS
121 | JALPAIGURI | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | TSM/015391 | SM/13900 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 09/09/2022 | 1527 | 738.1 | Yes | 738.1 | 29/08/2024 | 07/03/2024 | 22 | 674.41 | 315.26 | MVS
122 | JALPAIGURI | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | TSM/015382 | SM/13901 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 09/09/2022 | 462 | 236.73 | Yes | 236.73 | 29/08/2024 | 28/04/2023 | 10 | 213.35 | 113.69 | MVS
123 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | TSM/013298 | SM/13987 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/08/2022 | 2286 | 756.71 | Yes | 756.71 | 28/03/2025 | 14/08/2024 | 21 | 632.11 | 263.83 | MVS
124 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | TSM/013277 | SM/13988 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/08/2022 | 1157 | 355.6 | Yes | 355.6 | 20/01/2025 | 07/03/2024 | 17 | 334.9 | 262.55 | MVS
125 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | TSM/013276 | SM/13989 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/08/2022 | 360 | 143.56 | Yes | 143.56 | 29/08/2024 | 16/03/2023 | 9 | 117.91 | 96.91 | MVS
126 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR TANDU | TSM/013281 | SM/13990 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/08/2022 | 396 | 177.66 | Yes | 177.66 | 29/08/2024 | 07/03/2024 | 10 | 158.2 | 88.51 | MVS
127 | JALPAIGURI | NIRANJANPAT WATER SUPPLY SCHEME | TSM/013267 | SM/13991 | New |  |  |  | 22/08/2022 | 866 | 543.63 | Yes | 543.63 | 24/01/2025 | 06/06/2023 | 13 | 331.45 | 142.25 | MVS
128 | JALPAIGURI | BINNAGURI PIPED WATER SUPPLY SCHEME | TSM/016357 | SM/14198 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 30/09/2022 | 1553 | 409.19 | Yes | 409.19 | 29/08/2024 | 03/04/2024 | 13 | 344.89 | 205.6 | MVS
129 | JALPAIGURI | KAOAGAP PIPED WATER SUPPLY SCHEME | TSM/016139 | SM/14199 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 30/09/2022 | 984 | 647.34 | Yes | 647.34 | 11/03/2025 | 03/04/2024 | 16 | 614.93 | 300.77 | MVS
130 | JALPAIGURI | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | TSM/014950 | SM/14200 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 30/09/2022 | 2644 | 779.1 | Yes | 779.1 | 26/07/2024 | 04/12/2024 | 12 | 617.01 | 337.74 | MVS
131 | JALPAIGURI | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | TSM/016181 | SM/14224 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 26/09/2022 | 116 | 140.42 | Yes | 140.42 | 24/01/2025 | 08/06/2023 | 9 | 71.55 | 15.78 | MVS
132 | JALPAIGURI | SIMULGURI PIPED WATER SUPPLY SCHEME | TSM/015430 | SM/14240 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 2948 | 1172.27 | Yes | 1172.27 | 03/10/2024 | 30/03/2023 | 15 | 1072.45 | 775.32 | MVS
133 | JALPAIGURI | PANI KAURI PIPED WATER SUPPLY SCHEME | TSM/015429 | SM/14241 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 3891 | 1381.36 | Yes | 1381.36 | 17/04/2025 | 17/10/2025 | 24 | 1162.66 | 409.42 | MVS
134 | JALPAIGURI | CHHOTA FAPRI WATER SUPPLY SCHEME | TSM/011228 | SM/14494 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 25/04/2022 | 758 | 304.33 | Yes | 304.33 | 30/07/2024 | 03/05/2023 | 7 | 256.23 | 79.47 | MVS
135 | JALPAIGURI | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | TSM/016180 | SM/14660 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 26/09/2022 | 1074 | 520.46 | Yes | 520.46 | 03/09/2024 | 11/03/2025 | 9 | 67.12 | 208.11 | MVS
136 | JALPAIGURI | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | TSM/016178 | SM/14664 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 26/09/2022 | 2319 | 870.88 | Yes | 870.88 | 11/11/2024 | 23/08/2024 | 12 | 728.9 | 530.37 | MVS
137 | JALPAIGURI | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | TSM/016176 | SM/14665 | New |  |  |  | 26/09/2022 | 425 | 417.67 | Yes | 417.67 | 06/03/2025 | 27/03/2023 | 9 | 295.63 | 173.15 | MVS
138 | JALPAIGURI | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016174 | SM/14666 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 26/09/2022 | 2390 | 852.43 | Yes | 852.43 | 24/01/2025 | 23/08/2024 | 15 | 717.43 | 437.28 | MVS
139 | JALPAIGURI | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | TSM/016170 | SM/14667 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 26/09/2022 | 469 | 464.69 | Yes | 464.69 | 11/03/2025 | 03/04/2024 | 15 | 350.44 | 211.97 | MVS
140 | JALPAIGURI | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME | TSM/016064 | SM/14826 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 30/09/2022 | 1067 | 551.68 | Yes | 551.68 | 11/03/2025 | 07/12/2023 | 15 | 448.84 | 224.61 | MVS
141 | JALPAIGURI | PATKATA ZONE-III PIPED WATER SUPPLY | TSM/017407 | SM/14878 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 2535 | 727.68 | Yes | 727.68 | 25/02/2025 | 03/04/2024 | 11 | 589.59 | 260.09 | MVS
142 | JALPAIGURI | KANTADIGHI KUMARPARA TEA GARDEN | TSM/017840 | SM/14879 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 2481 | 841.22 | Yes | 841.22 | 29/08/2024 | 07/03/2024 | 15 | 205.36 | 458.73 | MVS
143 | JALPAIGURI | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017838 | SM/14880 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 2050 | 732.1 | Yes | 732.1 | 12/08/2024 | 07/03/2024 | 13 | 507.9 | 111.46 | MVS
144 | JALPAIGURI | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | TSM/017836 | SM/14881 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 2106 | 681.26 | Yes | 681.26 | 25/02/2025 | 24/05/2023 | 14 | 561.79 | 159.99 | MVS
145 | JALPAIGURI | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015977 | SM/14882 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 30/09/2022 | 1110 | 558.05 | Yes | 558.05 | 11/03/2025 | 03/04/2024 | 14 | 437.62 | 199.48 | MVS
146 | JALPAIGURI | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | TSM/016364 | SM/14883 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 1611 | 544.31 | Yes | 544.31 | 26/03/2025 | 10/05/2023 | 15 | 476.34 | 117.11 | MVS
147 | JALPAIGURI | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016363 | SM/14884 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 2397 | 710.56 | Yes | 710.56 | 19/02/2025 | 17/10/2025 | 7 | 547.09 | 2.04 | MVS
148 | JALPAIGURI | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016190 | SM/14885 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 2665 | 913.53 | Yes | 913.53 | 11/11/2024 | 07/03/2024 | 19 | 849.2 | 724.08 | MVS
149 | JALPAIGURI | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016191 | SM/14886 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 1312 | 525.39 | Yes | 525.39 | 30/08/2024 | 07/08/2024 | 12 | 389.33 | 53.69 | MVS
150 | JALPAIGURI | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017494 | SM/14887 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 1619 | 641.1 | Yes | 641.1 | 11/03/2025 | 03/04/2024 | 14 | 549.67 | 294.96 | MVS
151 | JALPAIGURI | KHAS JANGAL PIPED WATER SUPPLY SCHEME | TSM/016691 | SM/14907 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 30/09/2022 | 456 | 245.77 | Yes | 245.77 | 08/01/2025 | 08/08/2023 | 6 | 176.1 | 13.04 | MVS
152 | JALPAIGURI | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | TSM/016642 | SM/14908 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 30/09/2022 | 428 | 248.15 | Yes | 248.15 | 23/12/2024 | 24/03/2023 | 11 | 202.3 | 95.22 | MVS
153 | JALPAIGURI | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016620 | SM/14911 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 30/09/2022 | 590 | 274.41 | Yes | 274.41 | 23/12/2024 | 23/08/2024 | 11 | 87.86 | 107.09 | MVS
154 | JALPAIGURI | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | TSM/015975 | SM/14914 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 30/09/2022 | 2374 | 478.22 | Yes | 478.22 | 11/03/2025 | 03/04/2024 | 14 | 399.52 | 239.08 | MVS
155 | JALPAIGURI | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | TSM/015976 | SM/14919 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 30/09/2022 | 2306 | 366.08 | Yes | 366.08 | 29/07/2024 | 03/04/2024 | 13 | 271.69 | 170.09 | MVS
156 | JALPAIGURI | REJUVENATION OF ARJI GARALBARI PWSS | TSM/018283 | SM/15030 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 172.44 | Yes | 172.44 | 12/03/2024 | 25/04/2023 | 15 | 138.36 | 83.32 | MVS
157 | JALPAIGURI | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | TSM/018224 | SM/15031 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 161.99 | Yes | 161.99 | 12/03/2024 | 01/06/2023 | 9 | 137.26 | 102.58 | MVS
158 | JALPAIGURI | Rejuvenation of Bhangarhat Piped Water Supply Scheme | TSM/018110 | SM/15032 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 178.3 | Yes | 178.3 | 26/07/2024 | 24/05/2023 | 8 | 136 | 37.96 | MVS
159 | JALPAIGURI | Rejuvenation of Chauhaddi Piped Water Supply Scheme | TSM/018108 | SM/15033 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 198.79 | Yes | 198.79 | 28/03/2025 | 30/05/2025 | 6 | 94.82 | 59.42 | MVS
160 | JALPAIGURI | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | TSM/018100 | SM/15059 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 127.24 | Yes | 127.24 | 12/03/2024 | 09/03/2023 | 10 | 68.26 | 62.04 | MVS
161 | JALPAIGURI | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/018112 | SM/15060 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 285.02 | Yes | 285.02 | 26/03/2025 | 09/02/2024 | 8 | 118.88 | 90.77 | MVS
162 | JALPAIGURI | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | TSM/018310 | SM/15068 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 70.86 | Yes | 70.86 | 12/03/2024 | 26/10/2023 | 7 | 59.72 | 37.19 | MVS
163 | JALPAIGURI | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | TSM/018227 | SM/15071 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 1015 | 177.04 | Yes | 177.04 | 12/03/2024 | 01/06/2023 | 5 | 72.27 | 53.99 | MVS
164 | JALPAIGURI | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | TSM/018016 | SM/15075 | Augmentation | RWS Jalpaiguri Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 0 | 158.29 | Yes | 158.29 | 14/08/2024 | 07/06/2023 | 10 | 94.27 | 48.19 | MVS
165 | JALPAIGURI | REJUVENATION OF PASCHIM SALBARI PWSS | TSM/018057 | SM/15076 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 16/11/2022 | 2840 | 399.4 | Yes | 399.4 | 17/12/2024 | 28/04/2023 | 11 | 176.02 | 46.34 | MVS
166 | JALPAIGURI | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/017647 | SM/15077 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 1068 | 180.27 | Yes | 180.27 | 11/11/2024 | 14/08/2024 | 14 | 118.08 | 39.98 | MVS
167 | JALPAIGURI | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | TSM/018039 | SM/15078 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 157.06 | Yes | 157.06 | 30/08/2024 | 28/04/2023 | 11 | 97.81 | 25.79 | MVS
168 | JALPAIGURI | Rejuvenation for Manabari Tea Garden | TSM/018002 | SM/15082 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 229.62 | Yes | 229.62 | 23/12/2024 | 08/08/2023 | 11 | 174.59 | 49.24 | MVS
169 | JALPAIGURI | Rejuvenation for Patkidaha Piped Water Supply Scheme | TSM/017986 | SM/15085 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 145.15 | Yes | 145.15 | 11/03/2025 | 18/04/2022 | 13 | 110.9 | 66.9 | MVS
170 | JALPAIGURI | REJUVENATION OF DAKSHIN SALBARI PWSS | TSM/017943 | SM/15087 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 16/11/2022 | 2129 | 246.25 | Yes | 246.25 | 30/01/2024 | 27/06/2024 | 10 | 95.46 | 29.94 | MVS
171 | JALPAIGURI | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | TSM/017709 | SM/15089 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 151.59 | Yes | 151.59 | 30/08/2024 | 08/06/2023 | 5 | 122.89 | 33.4 | MVS
172 | JALPAIGURI | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | TSM/017590 | SM/15094 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 125.87 | Yes | 125.87 | 04/09/2024 | 12/06/2024 | 8 | 105.55 | 36.98 | MVS
173 | JALPAIGURI | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | TSM/017589 | SM/15096 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 119.1 | Yes | 119.1 | 14/08/2024 | 01/06/2023 | 7 | 85.81 | 24.12 | MVS
174 | JALPAIGURI | Rejuvenation of Mathachulka Piped Water Supply Scheme | TSM/011305 | SM/15098 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 175.2 | Yes | 175.2 | 28/03/2025 | 22/07/2022 | 11 | 159.42 | 90.65 | MVS
175 | JALPAIGURI | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | TSM/018018 | SM/15099 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 150.59 | Yes | 150.59 | 03/09/2024 | 31/03/2022 | 5 | 45.58 | 38.96 | MVS
176 | JALPAIGURI | REJUVENATION OF PORA PARA PWSS | TSM/017999 | SM/15101 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer 2 | 16/11/2022 | 3934 | 424.27 | Yes | 424.27 | 25/02/2025 | 14/11/2024 | 11 | 243.29 | 84.9 | MVS
177 | JALPAIGURI | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | TSM/017971 | SM/15103 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 149.74 | Yes | 149.74 | 04/09/2024 | 30/05/2023 | 7 | 169.07 | 77.07 | MVS
178 | JALPAIGURI | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | TSM/017864 | SM/15109 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 182.13 | Yes | 182.13 | 22/02/2024 | 05/10/2023 | 8 | 137.05 | 48.72 | MVS
179 | JALPAIGURI | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | TSM/011303 | SM/15114 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 255.47 | Yes | 255.47 | 20/01/2025 | 16/06/2022 | 12 | 91.04 | 177.47 | MVS
180 | JALPAIGURI | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016185 | SM/15115 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 1368 | 560.37 | Yes | 560.37 | 26/03/2025 | 07/03/2024 | 13 | 462.35 | 303.54 | MVS
181 | JALPAIGURI | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | TSM/018613 | SM/15116 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 194.43 | Yes | 194.43 | 29/07/2024 | 25/05/2023 | 10 | 156.67 | 110.93 | MVS
182 | JALPAIGURI | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | TSM/011311 | SM/15117 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 196.67 | Yes | 196.67 | 12/08/2024 | 28/04/2023 | 10 | 179.35 | 162.46 | MVS
183 | JALPAIGURI | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | TSM/018042 | SM/15130 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 1315 | 182.74 | Yes | 182.74 | 04/09/2024 | 07/06/2023 | 11 | 128.17 | 46.18 | MVS
184 | JALPAIGURI | RETROFITTING OF MAHITNAGAR PWSS | TSM/018681 | SM/15131 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 180.43 | Yes | 180.43 | 13/10/2023 | 08/06/2023 | 2 | 116.29 | 75.34 | MVS
185 | JALPAIGURI | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | TSM/018659 | SM/15132 | Retrofitting | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 189.88 | Yes | 189.88 | 26/03/2025 | 08/06/2023 | 4 | 191.99 | 83.59 | MVS
186 | JALPAIGURI | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | TSM/014784 | SM/15261 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 22/08/2022 | 966 | 545.43 | Yes | 545.43 | 17/03/2025 | 23/08/2024 | 14 | 88.31 | 167.09 | MVS
187 | JALPAIGURI | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/013287 | SM/15262 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 22/08/2022 | 1408 | 635.17 | Yes | 635.17 | 24/01/2025 | 23/08/2024 | 13 | 79.63 | 285.29 | MVS
188 | JALPAIGURI | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | TSM/011227 | SM/15263 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 20/05/2022 | 1212 | 399.34 | Yes | 399.34 | 19/02/2025 | 10/05/2023 | 8 | 336.17 | 61.06 | MVS
189 | JALPAIGURI | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015385 | SM/15264 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 09/09/2022 | 1080 | 345.92 | Yes | 345.92 | 11/04/2025 | 10/04/2023 | 13 | 324.51 | 163.74 | MVS
190 | JALPAIGURI | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017834 | SM/15296 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 1832 | 604.63 | Yes | 604.63 | 28/03/2025 | 08/05/2023 | 12 | 489.65 | 265.76 | MVS
191 | JALPAIGURI | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016344 | SM/15297 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 1991 | 724.23 | Yes | 724.23 | 19/02/2025 | 22/11/2024 | 18 | 507.78 | 167.74 | MVS
192 | JALPAIGURI | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | TSM/011312 | SM/15298 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 241.44 | Yes | 241.44 | 28/03/2025 | 13/04/2023 | 5 | 167.36 | 149.23 | MVS
193 | JALPAIGURI | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | TSM/011308 | SM/15299 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 139.34 | Yes | 139.34 | 26/03/2025 | 28/06/2024 | 10 | 85.69 | 77.61 | MVS
194 | JALPAIGURI | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | TSM/011304 | SM/15300 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 159.96 | Yes | 159.96 | 24/01/2025 | 08/06/2023 | 12 | 156.06 | 140.78 | MVS
195 | JALPAIGURI | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | TSM/011306 | SM/15301 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 391.48 | Yes | 391.48 | 28/03/2025 | 24/11/2020 | 8 | 109.3 | 92.62 | MVS
196 | JALPAIGURI | Augmentation of Porjhar Pipe Water Supply Scheme | TSM/018097 | SM/15302 | Augmentation | Siliguri Sub-Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer(Civil) | Junior Engineer (Civil) | 16/11/2022 | 2564 | 597.01 | Yes | 597.01 | 29/08/2024 | 05/06/2023 | 6 | 424.77 | 167.01 | MVS
197 | JALPAIGURI | Rejuvenation of Purba Duramari Piped Water Supply Scheme | TSM/018104 | SM/15326 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 1409 | 206.58 | Yes | 206.58 | 11/03/2025 | 22/05/2023 | 6 | 85.5 | 51.4 | MVS
198 | JALPAIGURI | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | TSM/017841 | SM/15335 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 16/11/2022 | 2792 | 850.7 | Yes | 850.7 | 25/02/2025 | 23/08/2024 | 18 | 766.97 | 260.63 | MVS
199 | JALPAIGURI | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | TSM/019578 | SM/15338 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 121.26 | Yes | 121.26 | 08/02/2024 | 05/10/2023 | 5 | 93.44 | 77.57 | MVS
200 | JALPAIGURI | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017390 | SM/15339 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 4224 | 980.45 | Yes | 980.45 | 26/03/2025 | 03/04/2024 | 15 | 873.59 | 236.45 | MVS
201 | JALPAIGURI | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | TSM/014793 | SM/15742 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 22/08/2022 | 1391 | 678.84 | Yes | 678.84 | 24/01/2025 | 28/04/2023 | 11 | 436.75 | 205.35 | MVS
202 | JALPAIGURI | SONAKHULI PIPED WATER SUPPLY SCHEME | TSM/014183 | SM/15744 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD |  | 22/08/2022 | 732 | 446.23 | Yes | 446.23 | 24/01/2025 | 13/04/2023 | 13 | 287.11 | 79.48 | MVS
203 | JALPAIGURI | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | TSM/015316 | SM/15915 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 878 | 427.23 | Yes | 427.23 | 24/01/2025 | 08/05/2023 | 12 | 350.76 | 82.17 | MVS
204 | JALPAIGURI | KHUKLUNG PIPED WATER SUPPLY SCHEME | TSM/018691 | SM/15953 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 28/12/2022 | 118 | 119.09 | Yes | 119.09 | 12/03/2024 | 13/09/2023 | 3 | 70.06 | 34.97 | MVS
205 | JALPAIGURI | CHHAR TANDU PIPED WATER SUPPLY SCHEME | TSM/017828 | SM/15964 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 28/12/2022 | 573 | 330.17 | Yes | 330.17 | 26/03/2025 | 21/06/2024 | 9 | 99.22 | 64.4 | MVS
206 | JALPAIGURI | BARA GHARIA PIPED WATER SUPPLY SCHEME | TSM/018232 | SM/15967 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/12/2022 | 1304 | 703.7 | Yes | 703.7 | 30/07/2024 | 25/05/2023 | 15 | 625.67 | 271.68 | MVS
207 | JALPAIGURI | TESIMALA PIPED WATER SUPPLY SCHEME | TSM/016202 | SM/15970 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 28/12/2022 | 1140 | 391.74 | Yes | 391.74 | 26/07/2024 | 23/08/2024 | 7 | 81.5 | 146.55 | MVS
208 | JALPAIGURI | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017313 | SM/15971 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/12/2022 | 1963 | 846.82 | Yes | 846.82 | 10/07/2025 | 05/06/2024 | 24 | 627.29 | 181.16 | MVS
209 | JALPAIGURI | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016193 | SM/15978 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/12/2022 | 988 | 391.48 | Yes | 391.48 | 13/03/2025 | 23/05/2023 | 16 | 338.32 | 214.5 | MVS
210 | JALPAIGURI | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016184 | SM/15980 | New |  |  |  | 28/12/2022 | 694 | 350.2 | Yes | 350.2 | 30/08/2024 | 23/08/2024 | 12 | 295.68 | 66.56 | MVS
211 | JALPAIGURI | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016183 | SM/15990 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 28/12/2022 | 1096 | 406.46 | Yes | 406.46 | 12/03/2025 | 07/03/2024 | 14 | 339.79 | 178.72 | MVS
212 | JALPAIGURI | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015323 | SM/16040 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 774 | 386.02 | Yes | 386.02 | 29/08/2024 | 10/05/2023 | 10 | 294.86 | 205.08 | MVS
213 | JALPAIGURI | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017315 | SM/16041 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/12/2022 | 2356 | 918.46 | Yes | 918.46 | 17/04/2025 | 29/11/2024 | 19 | 820.46 | 325.63 | MVS
214 | JALPAIGURI | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | TSM/015374 | SM/16042 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD |  | 09/09/2022 | 1370 | 568.49 | Yes | 568.49 | 03/09/2024 | 08/05/2023 | 11 | 506.4 | 252.79 | MVS
215 | JALPAIGURI | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017495 | SM/16181 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/12/2022 | 1385 | 613.74 | Yes | 613.74 | 11/03/2025 | 03/04/2024 | 13 | 518.29 | 266.62 | MVS
216 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | TSM/013278 | SM/16492 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 22/08/2022 | 1078 | 461.81 | Yes | 461.81 | 24/01/2025 | 10/05/2023 | 7 | 417.97 | 65.98 | MVS
217 | JALPAIGURI | BHEMTIA PIPED WATER SUPPLY SCHEME | TSM/015327 | SM/16676 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 09/09/2022 | 667 | 414.83 | Yes | 414.83 | 11/03/2025 | 06/04/2023 | 8 | 262.77 | 56.77 | MVS
218 | JALPAIGURI | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | TSM/017935 | SM/16772 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 28/12/2022 | 1459 | 156.25 | Yes | 156.25 | 29/07/2024 | 28/11/2023 | 6 | 73.17 | 31.17 | MVS
219 | JALPAIGURI | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011283 | SM/16773 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/12/2022 | 527 | 171.57 | Yes | 171.57 | 26/03/2025 | 26/09/2023 | 6 | 166.7 | 98.44 | MVS
220 | JALPAIGURI | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | TSM/018684 | SM/16776 | New | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 28/12/2022 | 30 | 89.03 | Yes | 89.03 | 26/03/2025 | 08/08/2023 | 4 | 50.37 | 9.13 | MVS
221 | JALPAIGURI | Sisubari Tea Garden Piped Water Supply Scheme | TSM/018491 | SM/16778 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/12/2022 | 663 | 326.54 | Yes | 326.54 | 23/12/2024 | 07/03/2024 | 12 | 59.88 | 110.99 | MVS
222 | JALPAIGURI | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017319 | SM/16779 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 28/12/2022 | 2238 | 709.31 | Yes | 709.31 | 06/03/2025 | 28/04/2023 | 14 | 621.07 | 169.61 | MVS
223 | JALPAIGURI | HAIHAIPATHAR PWSS | TSM/016203 | SM/16852 | New | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 16/11/2022 | 2306 | 741.68 | Yes | 741.68 | 23/12/2024 | 23/08/2024 | 11 | 117.38 | 305.88 | MVS
224 | JALPAIGURI | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | TSM/018221 | SM/16937 | Augmentation | RWS Jalpaiguri Sub-Division |  | Junior Engineer | 16/11/2022 | 0 | 161.99 | Yes | 161.99 | 11/11/2024 | 06/06/2023 | 6 | 96.86 | 51.79 | MVS
225 | JALPAIGURI | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | TSM/011005 | SM/17181 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 30/03/2022 | 1317 | 201.66 | Yes | 201.66 | 06/03/2025 | 17/10/2025 | 3 | 41.27 | 7.59 | MVS
226 | JALPAIGURI | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | TSM/011016 | SM/17185 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 30/03/2022 | 940 | 180.04 | Yes | 180.04 | 28/03/2025 | 26/05/2023 | 7 | 126.77 | 107.71 | MVS
227 | JALPAIGURI | BARAGHARIA Piped Water Supply Scheme. | TSM/014917 | SM/17649 | New | Northern Mechanical Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 2063 | 613.18 | Yes | 613.18 | 26/03/2025 | 25/04/2023 | 8 | 531.4 | 273.28 | MVS
228 | JALPAIGURI | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011592 | SM/17681 | Augmentation | Jalpaiguri Sadar Sub-Division |  | Junior Engineer | 28/12/2022 | 240 | 116.16 | Yes | 116.16 | 26/03/2025 | 08/06/2023 | 6 | 108.18 | 70.27 | MVS
229 | JALPAIGURI | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II | TSM/011411 | SM/18094 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 16/11/2022 | 0 | 185.13 | Yes | 185.13 | 30/08/2024 | 06/06/2023 | 5 | 110.12 | 41.82 | MVS
230 | JALPAIGURI | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | TSM/010970 | SM/18283 | Augmentation | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 20/05/2022 | 19720 | 2862.78 | Yes | 2862.78 | 10/07/2025 | 17/05/2024 | 36 | 2185.8 | 629 | MVS
231 | JALPAIGURI | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | TSM/018407 | SM/18355 | Augmentation |  |  |  | 16/11/2022 | 5782 | 1573.93 | Yes | 1573.93 | 29/08/2024 | 05/06/2023 | 10 | 882.85 | 126.39 | MVS
232 | JALPAIGURI | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018253 | SM/18356 | New |  |  |  | 16/11/2022 | 2798 | 1140.38 | Yes | 1140.38 | 10/07/2025 | 14/05/2024 | 56 | 753.89 | 285.6 | MVS
233 | JALPAIGURI | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | TSM/017837 | SM/18357 | New |  |  |  | 16/11/2022 | 3403 | 1031.07 | Yes | 1031.07 | 23/12/2024 | 01/10/2024 | 27 | 785.65 | 567.25 | MVS
234 | JALPAIGURI | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | TSM/018490 | SM/18358 | New |  |  |  | 16/11/2022 | 3607 | 1399.31 | Yes | 1399.31 | 30/08/2024 | 23/08/2024 | 14 | 1170.64 | 523.62 | MVS
235 | JALPAIGURI | BASUSUBA PIPED WATER SUPPLY SCHEME | TSM/018240 | SM/18359 | New |  |  |  | 16/11/2022 | 2822 | 1257.66 | Yes | 1257.66 | 29/08/2024 | 03/04/2024 | 16 | 1021.32 | 314.16 | MVS
236 | JALPAIGURI | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017397 | SM/18360 | New |  |  |  | 16/11/2022 | 4224 | 1152.06 | Yes | 1152.06 | 06/03/2025 | 26/07/2024 | 12 | 947.09 | 322.96 | MVS
237 | JALPAIGURI | Kumarpara Piped Water Supply Scheme. | TSM/003957 | SM/18491 | New |  |  |  | 04/12/2020 | 2400 | 845.25 | Yes | 845.25 | 11/11/2024 | 03/04/2024 | 13 | 785.87 | 376.45 | MVS
238 | JALPAIGURI | Chapgar Piped Water Supply Scheme. | TSM/002874 | SM/18492 | New |  |  |  | 19/02/2021 | 0 | 757.75 | Yes | 757.75 | 11/11/2024 | 18/07/2024 | 19 | 572.19 | 128.76 | MVS
239 | JALPAIGURI | NOWAPARA PIPED WATER SUPPLY SCHEME | TSM/014951 | SM/18503 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 28/12/2022 | 3633 | 1060.21 | Yes | 1060.21 | 10/07/2025 | 31/05/2024 | 14 | 864.59 | 60.47 | MVS
240 | JALPAIGURI | SALUGARA PIPED WATER SUPPLY SCHEME | TSM/014952 | SM/18625 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 30/09/2022 | 5286 | 1182.82 | Yes | 1182.82 | 29/08/2024 | 03/10/2024 | 15 | 531.01 | 313.11 | MVS
241 | JALPAIGURI | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016182 | SM/18711 | New |  |  |  | 28/12/2022 | 1951 | 584.88 | Yes | 584.88 | 26/03/2025 | 07/03/2024 | 15 | 514.89 | 230.54 | MVS
242 | JALPAIGURI | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme | TSM/010092 | SM/18713 | Augmentation |  |  |  | 16/03/2022 | 1019 | 213.69 | Yes | 213.69 | 20/01/2025 | 13/09/2023 | 9 | 214.55 | 35.32 | MVS
243 | JALPAIGURI | Saptibari Piped Water Supply Scheme. | TSM/003947 | SM/18759 | New | RWS Jalpaiguri Sub-Division | Assistant Engineer | Junior Engineer | 04/12/2020 | 663 | 2026.68 | Yes | 2026.68 | 11/06/2024 | 08/07/2024 | 22 | 1476.73 | 997.18 | MVS
244 | JALPAIGURI | Satkhamar Piped Water Supply Scheme. | TSM/004973 | SM/18760 | New |  |  |  | 19/02/2021 | 7058 | 2137.78 | Yes | 2137.78 | 26/03/2025 | 13/09/2024 | 24 | 2041.72 | 592.33 | MVS
245 | JALPAIGURI | Singimari Piped Water Supply Scheme. | TSM/003948 | SM/18761 | New |  |  |  | 04/12/2020 | 2814 | 1138.97 | Yes | 1138.97 | 06/03/2025 | 14/08/2024 | 11 | 889.02 | 283.48 | MVS
246 | JALPAIGURI | Dakshin Jharalta Piped Water Supply Scheme. | TSM/005492 | SM/18835 | New | Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | 19/02/2021 | 3531 | 1190.83 | Yes | 1190.83 | 13/10/2023 | 07/08/2024 | 7 | 206.67 | 450.89 | MVS
247 | JALPAIGURI | Sikarpur Piped Water Supply Scheme. | TSM/003956 | SM/18836 | New |  |  |  | 19/02/2021 | 6574 | 1910.96 | Yes | 1910.96 | 26/12/2024 | 07/10/2024 | 33 | 801.08 | 616.95 | MVS
248 | JALPAIGURI | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017317 | SM/19097 | New |  |  |  | 28/12/2022 | 3357 | 1000.22 | Yes | 1000.22 | 26/03/2025 | 26/07/2024 | 12 | 852.96 | 265.39 | MVS
249 | JALPAIGURI | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018073 | SM/19175 | Augmentation |  |  |  | 28/12/2022 | 2814 | 1266.28 | Yes | 1266.28 | 28/06/2024 | 23/10/2024 | 3 | 1077.54 | 59.85 | MVS
Total | [9 empty] | 435009 | 125086.68 |  | 125086.68 |  |  | 3594 | 97506.65 | 58173.57