## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block | TSM/005677 | SM/06848 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | 28/08/2020 | 1733 | 85.66 | Yes | 85.66 |  | 14/10/2020 | 4 | 85.66 | 77.17 | MVS
2 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme | TSM/005676 | SM/06849 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 28/08/2020 | 1548 | 73.35 | Yes | 73.35 |  | 09/11/2020 | 3 | 60 | 54.24 | MVS
3 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme | TSM/005681 | SM/06850 | Retrofitting |  |  |  | 28/08/2020 | 1268 | 68.82 | Yes | 68.82 | 08/08/2024 | 16/09/2020 | 4 | 71.89 | 24.59 | MVS
4 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme | TSM/005679 | SM/06851 | Retrofitting | RWS Malda Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | 28/08/2020 | 1811 | 96.17 | Yes | 96.17 | 02/08/2024 | 10/11/2020 | 2 | 93.35 | 15.66 | MVS
5 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme | TSM/005680 | SM/06852 | Retrofitting |  |  |  | 28/08/2020 | 1707 | 102.95 | Yes | 102.95 | 21/01/2025 | 02/06/2025 | 5 | 105.81 | 42.33 | MVS
6 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme | TSM/005682 | SM/06853 | Retrofitting | Malda Sadar Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | 28/08/2020 | 1125 | 61.62 | Yes | 61.62 | 23/04/2025 | 27/05/2025 | 3 | 57.01 | 0 | MVS
7 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme | TSM/005683 | SM/06854 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer |  | 28/08/2020 | 1580 | 84.53 | Yes | 84.53 | 17/01/2025 | 10/11/2020 | 2 | 125.95 | 57.26 | MVS
8 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | TSM/005684 | SM/06855 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer |  | 28/08/2020 | 1366 | 73.75 | Yes | 73.75 | 12/07/2024 | 29/08/2025 | 4 | 72.1 | 29.08 | MVS
9 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | TSM/005685 | SM/06856 | Retrofitting | RWS Malda Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | 28/08/2020 | 1616 | 86.33 | Yes | 86.33 | 08/08/2024 | 28/05/2025 | 4 | 74.05 | 85.02 | MVS
10 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme | TSM/005686 | SM/06857 | Retrofitting | RWS Malda Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | 28/08/2020 | 1722 | 91.69 | Yes | 91.69 | 15/01/2025 | 21/05/2025 | 2 | 54.31 | 23.59 | MVS
11 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | TSM/005687 | SM/06858 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | 28/08/2020 | 1084 | 59.54 | Yes | 59.54 | 21/01/2025 | 11/12/2020 | 4 | 81.09 | 34.78 | MVS
12 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | TSM/005688 | SM/06859 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | 28/08/2020 | 1321 | 71.47 | Yes | 71.47 | 24/02/2025 | 10/11/2020 | 4 | 61.08 | 32.7 | MVS
13 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme | TSM/005689 | SM/06860 | Retrofitting | Malda Sadar Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | 28/08/2020 | 1749 | 93.04 | Yes | 93.04 | 23/02/2024 | 29/09/2020 | 2 | 71.62 | 48.7 | MVS
14 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | TSM/005690 | SM/06861 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Junior Engineer | 28/08/2020 | 1675 | 89.31 | Yes | 89.31 | 24/03/2025 | 17/06/2025 | 5 | 89.31 | 22.71 | MVS
15 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme | TSM/005691 | SM/06862 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | 28/08/2020 | 878 | 49.15 | Yes | 49.15 |  | 13/08/2021 | 2 | 37.29 | 0 | MVS
16 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | TSM/005692 | SM/06863 | Retrofitting | RWS Malda Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | 28/08/2020 | 991 | 54.86 | Yes | 54.86 | 16/07/2024 | 31/08/2020 | 7 | 36.7 | 15.66 | MVS
17 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme | TSM/005693 | SM/06864 | Retrofitting |  |  |  | 28/08/2020 | 1186 | 64.66 | Yes | 64.66 | 02/08/2024 | 31/08/2020 | 2 | 54.51 | 39 | MVS
18 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme | TSM/005694 | SM/06865 | Retrofitting |  |  |  | 28/08/2020 | 770 | 43.73 | Yes | 43.73 | 08/08/2024 | 31/08/2020 | 4 | 43.96 | 32.95 | MVS
19 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | TSM/005695 | SM/06866 | Retrofitting |  |  |  | 28/08/2020 | 1488 | 79.87 | Yes | 79.87 | 17/01/2025 | 10/11/2020 | 4 | 80.22 | 37.43 | MVS
20 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | TSM/005696 | SM/06867 | Retrofitting | RWS Malda Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | 28/08/2020 | 1748 | 92.99 | Yes | 92.99 | 15/01/2025 | 12/10/2020 | 6 | 120.39 | 28.64 | MVS
21 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme | TSM/005697 | SM/06868 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer |  | 28/08/2020 | 1122 | 61.47 | Yes | 61.47 | 24/03/2025 | 10/12/2020 | 2 | 87.69 | 0 | MVS
22 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme | TSM/005698 | SM/06869 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer |  | 28/08/2020 | 1642 | 87.63 | Yes | 87.63 | 24/04/2025 | 12/10/2020 | 2 | 66.89 | 30 | MVS
23 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme | TSM/005699 | SM/06870 | Retrofitting | Malda Sadar Sub-Division | Sri Biswadip Sengupta, Assistant Engineer |  | 28/08/2020 | 1735 | 92.34 | Yes | 92.34 | 21/04/2025 | 12/10/2020 | 2 | 87.95 | 45.91 | MVS
24 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | TSM/005700 | SM/06871 | Retrofitting | RWS Malda Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | 28/08/2020 | 975 | 54.06 | Yes | 54.06 | 08/08/2024 | 30/09/2020 | 6 | 50.94 | 8.19 | MVS
25 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | TSM/005701 | SM/06872 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | 28/08/2020 | 1639 | 87.48 | Yes | 87.48 | 17/01/2025 | 25/09/2024 | 5 | 25.96 | 43.95 | MVS
26 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | TSM/006275 | SM/06986 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 25/09/2020 | 790 | 35.94 | Yes | 35.94 |  | 24/08/2023 | 5 | 39.79 | 32.5 | MVS
27 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme | TSM/006277 | SM/07007 | Retrofitting |  |  |  | 25/09/2020 | 1583 | 86.07 | Yes | 86.07 | 21/01/2025 | 12/10/2020 | 4 | 70.15 | 29.67 | MVS
28 | MALDAH | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | TSM/006280 | SM/07972 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | 25/09/2020 | 47698 | 2518.77 | Yes | 2518.77 | 25/04/2025 | 22/05/2025 | 108 | 2111.87 | 345.33 | MVS
29 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | TSM/006282 | SM/07973 | Retrofitting | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | 25/09/2020 | 110880 | 5777.65 | Yes | 5777.65 | 05/05/2025 | 13/07/2023 | 175 | 3573.88 | 548.42 | MVS
30 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JOTE BASANTA, LAXMIGHAT Water Supply Scheme at English Bazar Block | TSM/005678 | SM/08283 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | 28/08/2020 | 9031 | 406.26 | Yes | 406.26 | 19/07/2024 | 11/05/2022 | 9 | 407.89 | 196.45 | MVS
31 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | TSM/007490 | SM/08760 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | 19/02/2021 | 2649 | 183.54 | Yes | 183.54 | 06/09/2022 | 26/09/2024 | 13 | 114.94 | 0 | MVS
32 | MALDAH | Augmentation of Bulbulchandi PWSS. | TSM/008161 | SM/09422 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | 29/09/2021 | 4929 | 981.06 | Yes | 981.06 | 21/04/2025 | 18/08/2023 | 13 | 910.71 | 0 | MVS
33 | MALDAH | Augmentation of Tilasan Piped water supply scheme | TSM/009047 | SM/09567 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | 08/10/2021 | 1568 | 331.85 | Yes | 331.85 | 16/02/2024 | 22/04/2022 | 14 | 254.11 | 0 | MVS
34 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | TSM/008223 | SM/09587 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | 19/08/2021 | 3660 | 154.36 | Yes | 154.36 | 27/02/2024 | 09/03/2023 | 15 | 154.57 | 0 | MVS
35 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc | TSM/008217 | SM/09588 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | 19/08/2021 | 8954 | 354.85 | Yes | 354.85 | 31/07/2024 | 11/05/2022 | 15 | 354.84 | 0 | MVS
36 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar | TSM/008376 | SM/09589 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 19/08/2021 | 1542 | 67.89 | Yes | 67.89 | 06/09/2022 | 14/08/2023 | 3 | 67.88 | 0 | MVS
37 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha | TSM/008219 | SM/09590 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 5193 | 235.98 | Yes | 235.98 | 27/08/2021 | 12/04/2022 | 16 | 237.58 | 0 | MVS
38 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | TSM/008224 | SM/09591 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | 19/08/2021 | 3174 | 145.97 | Yes | 145.97 | 16/02/2023 | 23/05/2023 | 10 | 145.96 | 0 | MVS
39 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- | TSM/008227 | SM/09592 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 19/08/2021 | 9584 | 464.42 | Yes | 464.42 | 27/02/2024 | 10/05/2022 | 10 | 440.79 | 0 | MVS
40 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl | TSM/008233 | SM/09593 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 12090 | 577.48 | Yes | 577.48 | 27/02/2024 | 11/05/2023 | 12 | 538.35 | 0 | MVS
41 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | TSM/008229 | SM/09646 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 19/08/2021 | 7024 | 394.52 | Yes | 394.52 | 21/03/2023 | 28/04/2022 | 14 | 351.93 | 0 | MVS
42 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | TSM/008236 | SM/09647 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 8220 | 363.53 | Yes | 363.53 | 12/10/2022 | 28/04/2022 | 12 | 388.32 | 0 | MVS
43 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | TSM/008228 | SM/09648 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 4934 | 242.47 | Yes | 242.47 | 20/04/2023 | 24/08/2023 | 23 | 245.71 | 0 | MVS
44 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar | TSM/008214 | SM/09649 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 19/08/2021 | 4560 | 213.41 | Yes | 213.41 | 19/01/2024 | 13/06/2022 | 8 | 213.4 | 0 | MVS
45 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | TSM/008222 | SM/09650 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 19/08/2021 | 12985 | 589.71 | Yes | 589.71 |  | 12/05/2022 | 3 | 589.7 | 0 | MVS
46 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl | TSM/008238 | SM/09651 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 3940 | 189.35 | Yes | 189.35 | 27/08/2021 | 11/05/2022 | 8 | 189.34 | 0 | MVS
47 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | TSM/008226 | SM/09652 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 19/08/2021 | 9700 | 450.25 | Yes | 450.25 | 21/03/2023 | 24/04/2023 | 16 | 450.24 | 0 | MVS
48 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | TSM/008230 | SM/09653 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | 19/08/2021 | 9815 | 445.56 | Yes | 445.56 | 27/02/2024 | 12/05/2022 | 23 | 445.55 | 0 | MVS
49 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | TSM/008401 | SM/09654 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 19/08/2021 | 1423 | 63.53 | Yes | 63.53 | 09/12/2022 | 11/05/2022 | 5 | 63.52 | 0 | MVS
50 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | TSM/008235 | SM/09655 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 22779 | 986.55 | Yes | 986.55 | 21/03/2023 | 27/04/2023 | 11 | 986.54 | 0 | MVS
51 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl | TSM/008234 | SM/09656 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 13790 | 598.68 | Yes | 598.68 | 09/12/2022 | 13/06/2022 | 6 | 598.67 | 0 | MVS
52 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | TSM/008220 | SM/09657 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 19/08/2021 | 8012 | 356.57 | Yes | 356.57 | 12/10/2022 | 28/04/2022 | 8 | 281.44 | 0 | MVS
53 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | TSM/008237 | SM/09658 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 11500 | 505.89 | Yes | 505.89 | 10/01/2023 | 12/05/2022 | 7 | 505.88 | 0 | MVS
54 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | TSM/008231 | SM/09659 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 5400 | 246.4 | Yes | 246.4 | 02/08/2023 | 12/05/2022 | 9 | 248.33 | 0 | MVS
55 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | TSM/008221 | SM/09660 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 19/08/2021 | 3600 | 161.36 | Yes | 161.36 | 06/09/2022 | 11/05/2023 | 9 | 154.91 | 0 | MVS
56 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | TSM/008232 | SM/09661 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 19/08/2021 | 20500 | 883.23 | Yes | 883.23 | 27/08/2021 | 28/04/2022 | 9 | 883.22 | 0 | MVS
57 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | TSM/008377 | SM/09662 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 19/08/2021 | 10136 | 470.57 | Yes | 470.57 | 19/01/2024 | 14/08/2023 | 14 | 451.91 | 0 | MVS
58 | MALDAH | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | TSM/008225 | SM/09663 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | 19/08/2021 | 12315 | 506.2 | Yes | 506.2 | 21/03/2023 | 03/05/2023 | 9 | 506.19 | 0 | MVS
59 | MALDAH | Augmentation of Deotala Water Supply Scheme | TSM/005108 | SM/09986 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/11/2021 | 2446 | 842.06 | Yes | 842.06 | 23/04/2025 | 08/04/2022 | 11 | 607.35 | 0 | MVS
60 | MALDAH | AUGMENTATION OF MALATIPUR PWSS | TSM/008173 | SM/09987 | Augmentation | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 22/11/2021 | 2301 | 699.42 | Yes | 699.42 | 24/03/2025 | 20/07/2023 | 17 | 742.78 | 0 | MVS
61 | MALDAH | Augmentation of Bhaluka Fatepur Piped water supply scheme | TSM/009046 | SM/10137 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 16/12/2021 | 4734 | 1077.25 | Yes | 1077.25 | 31/07/2024 | 09/03/2023 | 19 | 900.88 | 0 | MVS
62 | MALDAH | Augmentation of Bamongram piped water supply scheme. | TSM/008160 | SM/10138 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | 16/12/2021 | 3481 | 1038.64 | Yes | 1038.64 | 21/04/2025 | 31/01/2023 | 22 | 974.62 | 0 | MVS
63 | MALDAH | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | TSM/008180 | SM/10181 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 22/11/2021 | 7524 | 2126.39 | Yes | 2126.39 | 25/04/2025 | 09/03/2023 | 32 | 1445.94 | 0 | MVS
64 | MALDAH | Augmentation of Uttar Harishandropur piped water supply scheme. | TSM/008163 | SM/10291 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 29/09/2021 | 8400 | 2223.72 | Yes | 2223.72 | 25/04/2025 | 04/09/2023 | 26 | 1604.34 | 0 | MVS
65 | MALDAH | Augmentation of Mirzapur Piped Water Supply Scheme | TSM/009757 | SM/10317 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | 27/01/2022 | 4880 | 1029.67 | Yes | 1029.67 | 17/04/2025 | 16/03/2023 | 28 | 901.18 | 0 | MVS
66 | MALDAH | Augmentation of Khusida Piped Water Supply Scheme | TSM/008174 | SM/10397 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 16/12/2021 | 426 | 1222.99 | Yes | 1222.99 | 23/04/2025 | 10/04/2023 | 15 | 1057.3 | 0 | MVS
67 | MALDAH | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011061 | SM/10430 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 16/03/2022 | 12750 | 546.45 | Yes | 546.45 | 10/05/2023 | 12/05/2022 | 3 | 208.61 | 0 | MVS
68 | MALDAH | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011277 | SM/11587 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 30/03/2022 | 1523 | 582.14 | Yes | 582.14 | 25/04/2025 | 08/05/2023 | 11 | 394.46 | 0 | MVS
69 | MALDAH | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011278 | SM/11588 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | 30/03/2022 | 2912 | 904.9 | Yes | 904.9 | 23/04/2025 | 13/07/2023 | 6 | 567.07 | 0 | MVS
70 | MALDAH | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011264 | SM/11589 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 30/03/2022 | 2900 | 618.45 | Yes | 618.45 | 23/04/2025 | 16/05/2023 | 13 | 541.32 | 0 | MVS
71 | MALDAH | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011266 | SM/11590 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 30/03/2022 | 2789 | 609.28 | Yes | 609.28 | 21/04/2025 | 16/09/2022 | 12 | 372.45 | 0 | MVS
72 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011054 | SM/11911 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | 30/03/2022 | 15538 | 937.95 | Yes | 937.95 | 19/01/2024 | 14/08/2023 | 4 | 728.41 | 0 | MVS
73 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011051 | SM/11912 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 30/03/2022 | 5765 | 322.33 | Yes | 322.33 | 26/03/2025 | 14/08/2023 | 5 | 226.76 | 0 | MVS
74 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Panchanadapur and Hamidpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011050 | SM/11913 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 30/03/2022 | 6480 | 343.66 | Yes | 343.66 | 21/02/2023 | 14/08/2023 | 1 | 324.55 | 0 | MVS
75 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011053 | SM/11914 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | 30/03/2022 | 3749 | 211.54 | Yes | 211.54 | 01/02/2023 | 24/06/2024 | 2 | 181.1 | 0 | MVS
76 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011049 | SM/11915 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 30/03/2022 | 12637 | 685.6 | Yes | 685.6 | 10/05/2023 | 24/06/2024 | 4 | 240.26 | 0 | MVS
77 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | TSM/011047 | SM/11916 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | 30/03/2022 | 11515 | 496.83 | Yes | 496.83 | 24/03/2025 | 05/04/2023 | 13 | 462.01 | 0 | MVS
78 | MALDAH | Providing Functional Household Tap Connection (FHTC) under command area of Paramanandapur, Biswambhar Binodpur, Bishnupur Shrirampara, Kamalpur, Paschim Narayanpur, Enayetpur and Gouripurr Zone Water Supply Scheme at Manikchak Block under Malda Arsenic Ar | TSM/011052 | SM/11917 | Retrofitting | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | 30/03/2022 | 7515 | 521.52 | Yes | 521.52 | 10/05/2023 | 14/08/2023 | 1 | 176.47 | 0 | MVS
79 | MALDAH | Sahapur Piped Water Supply Scheme | TSM/010990 | SM/11968 | New | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 30/03/2022 | 7669 | 1135.04 | Yes | 1135.04 | 01/08/2024 | 02/02/2024 | 15 | 1106.94 | 0 | MVS
80 | MALDAH | Alal Zone-I Piped Water Supply Scheme | TSM/011887 | SM/12075 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 20/05/2022 | 1971 | 732.76 | Yes | 732.76 | 21/04/2025 | 17/05/2023 | 11 | 665.72 | 0 | MVS
81 | MALDAH | Choupaldanga pipe water Supply Scheme | TSM/011833 | SM/12076 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 20/05/2022 | 3482 | 902.87 | Yes | 902.87 | 24/04/2025 | 07/09/2023 | 18 | 837.14 | 0 | MVS
82 | MALDAH | WARI Piped Water Supply Scheme | TSM/011955 | SM/12077 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 20/05/2022 | 3903 | 1077.41 | Yes | 1077.41 | 01/08/2024 | 10/04/2023 | 18 | 993.34 | 0 | MVS
83 | MALDAH | Hatinda Piped Water Supply Scheme. | TSM/011729 | SM/12078 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 20/05/2022 | 4783 | 1095.36 | Yes | 1095.36 | 25/04/2025 | 27/05/2025 | 11 | 278.96 | 0 | MVS
84 | MALDAH | GAURIA Piped Water Supply Scheme. | TSM/011717 | SM/12079 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | 20/05/2022 | 4278 | 1006.53 | Yes | 1006.53 | 02/08/2024 | 22/09/2022 | 15 | 831.08 | 0 | MVS
85 | MALDAH | JIBJALSAR Piped Water Supply Scheme | TSM/013490 | SM/12182 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 05/07/2022 | 146 | 73.06 | Yes | 73.06 | 22/11/2024 | 20/03/2023 | 9 | 66.63 | 0 | MVS
86 | MALDAH | KHARANGAPUR JABRA Piped Water Supply Scheme | TSM/013445 | SM/12183 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 05/07/2022 | 1378 | 291.47 | Yes | 291.47 | 23/04/2025 | 30/07/2025 | 9 | 281.38 | 0 | MVS
87 | MALDAH | SERBABAR BALARAMPUR Piped Water Supply Scheme | TSM/013253 | SM/12184 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 05/07/2022 | 2967 | 834.65 | Yes | 834.65 | 31/07/2024 | 18/05/2023 | 8 | 772.52 | 0 | MVS
88 | MALDAH | SWARUPGANJ Piped Water Supply Scheme | TSM/013249 | SM/12185 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 05/07/2022 | 3192 | 761.39 | Yes | 761.39 | 30/07/2024 | 08/06/2023 | 10 | 711.41 | 0 | MVS
89 | MALDAH | DAKSHIN BHAKURIA Piped Water Supply Scheme | TSM/013248 | SM/12186 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 969 | 346.83 | Yes | 346.83 | 27/06/2024 | 14/07/2023 | 8 | 294.14 | 0 | MVS
90 | MALDAH | SAHAPUR Piped Water Supply Scheme | TSM/013245 | SM/12187 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 397 | 112.27 | Yes | 112.27 | 16/07/2024 | 17/02/2023 | 7 | 88.1 | 0 | MVS
91 | MALDAH | PASCHIM BHAGABANPUR Piped Water Supply Scheme | TSM/013216 | SM/12188 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 05/07/2022 | 2609 | 867.35 | Yes | 867.35 | 23/04/2025 | 17/05/2023 | 11 | 778.61 | 0 | MVS
92 | MALDAH | TALPUKUR Piped Water Supply Scheme | TSM/013199 | SM/12189 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 05/07/2022 | 2190 | 730.06 | Yes | 730.06 | 08/08/2024 | 10/05/2023 | 10 | 649.44 | 0 | MVS
93 | MALDAH | KISMAT BAROL Piped Water Supply Scheme | TSM/013044 | SM/12190 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 05/07/2022 | 2326 | 672 | Yes | 672 | 21/04/2025 | 06/06/2023 | 9 | 620.87 | 0 | MVS
94 | MALDAH | BETAHAL Piped Water Supply Scheme | TSM/013024 | SM/12191 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 1550 | 526.99 | Yes | 526.99 | 12/07/2024 | 11/07/2024 | 10 | 153.84 | 0 | MVS
95 | MALDAH | MALIOR PWSS | TSM/013022 | SM/12192 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 2789 | 718.85 | Yes | 718.85 | 12/07/2024 | 27/05/2025 | 12 | 696.08 | 0 | MVS
96 | MALDAH | BANGRUA PWSS | TSM/013018 | SM/12193 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 05/07/2022 | 900 | 300.09 | Yes | 300.09 | 21/04/2025 | 29/07/2025 | 10 | 254.58 | 0 | MVS
97 | MALDAH | PUTIA PWSS | TSM/013011 | SM/12194 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 132 | 82.16 | Yes | 82.16 | 12/07/2024 | 09/02/2023 | 7 | 70.28 | 0 | MVS
98 | MALDAH | PARO PWSS | TSM/012960 | SM/12195 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 05/07/2022 | 1995 | 510.75 | Yes | 510.75 | 24/04/2025 | 26/07/2023 | 8 | 387.65 | 0 | MVS
99 | MALDAH | SULTANNAGAR PWSS | TSM/012936 | SM/12196 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 1659 | 512.75 | Yes | 512.75 | 02/08/2024 | 02/05/2023 | 9 | 382.29 | 0 | MVS
100 | MALDAH | MABARAKPUR PWSS | TSM/012922 | SM/12197 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 05/07/2022 | 2608 | 704.22 | Yes | 704.22 | 30/07/2024 | 19/05/2023 | 13 | 699.32 | 0 | MVS
101 | MALDAH | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | TSM/012594 | SM/12267 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 05/07/2022 | 2534 | 753.45 | Yes | 753.45 | 23/04/2025 | 08/06/2023 | 7 | 622.77 | 0 | MVS
102 | MALDAH | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | TSM/013454 | SM/12304 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 15/07/2022 | 1823 | 602.34 | Yes | 602.34 | 21/04/2025 | 03/05/2023 | 8 | 506.43 | 0 | MVS
103 | MALDAH | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012802 | SM/12305 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | 15/07/2022 | 0 | 152.39 | Yes | 152.39 | 21/04/2025 | 28/09/2022 | 8 | 85.5 | 0 | MVS
104 | MALDAH | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012800 | SM/12311 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | 15/07/2022 | 1504 | 335.27 | Yes | 335.27 | 21/01/2025 | 26/05/2025 | 19 | 305.13 | 0 | MVS
105 | MALDAH | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012799 | SM/12312 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 15/07/2022 | 0 | 131.81 | Yes | 131.81 | 20/04/2025 | 03/11/2022 | 9 | 93.86 | 0 | MVS
106 | MALDAH | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012798 | SM/12313 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 15/07/2022 | 1008 | 145.33 | Yes | 145.33 | 23/02/2024 | 28/09/2022 | 6 | 95.2 | 0 | MVS
107 | MALDAH | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012797 | SM/12314 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 15/07/2022 | 0 | 135.51 | Yes | 135.51 | 23/02/2024 | 10/09/2024 | 9 | 114.17 | 0 | MVS
108 | MALDAH | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012801 | SM/12315 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | 15/07/2022 | 0 | 174.73 | Yes | 174.73 | 19/01/2024 | 28/09/2022 | 9 | 148.68 | 0 | MVS
109 | MALDAH | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014342 | SM/12316 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 15/07/2022 | 1748 | 167.81 | Yes | 167.81 | 21/01/2025 | 27/06/2024 | 10 | 152.81 | 0 | MVS
110 | MALDAH | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014339 | SM/12317 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 15/07/2022 | 1275 | 281.18 | Yes | 281.18 | 31/07/2024 | 03/11/2022 | 13 | 179.07 | 0 | MVS
111 | MALDAH | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014344 | SM/12323 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 15/07/2022 | 1906 | 180.45 | Yes | 180.45 | 23/04/2025 | 24/11/2022 | 7 | 118.95 | 0 | MVS
112 | MALDAH | Sanjail PWSS in Old Malda Block in District Malda | TSM/011706 | SM/12337 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | 25/04/2022 | 822 | 380.75 | Yes | 380.75 | 23/04/2025 | 18/04/2023 | 15 | 309.11 | 0 | MVS
113 | MALDAH | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | TSM/011680 | SM/12338 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | 25/04/2022 | 1607 | 710.64 | Yes | 710.64 | 24/04/2025 | 07/06/2024 | 11 | 385.22 | 0 | MVS
114 | MALDAH | Augmentation of Maheshpur piped water supply scheme | TSM/005106 | SM/12362 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | 19/08/2021 | 0 | 1566.03 | Yes | 1566.03 | 17/04/2025 | 27/05/2025 | 16 | 1036.27 | 0 | MVS
115 | MALDAH | Sharanpur Piped Water Supply Scheme | TSM/013210 | SM/12631 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 1080 | 383.2 | Yes | 383.2 | 24/04/2025 | 22/05/2025 | 13 | 366.93 | 0 | MVS
116 | MALDAH | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | TSM/012833 | SM/12632 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 05/07/2022 | 698 | 335.31 | Yes | 335.31 | 16/07/2024 | 13/06/2024 | 13 | 291.12 | 0 | MVS
117 | MALDAH | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | TSM/014767 | SM/12708 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 22/08/2022 | 1867 | 574.74 | Yes | 574.74 | 18/09/2024 | 06/06/2023 | 10 | 456.25 | 0 | MVS
118 | MALDAH | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | TSM/014888 | SM/12709 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 22/08/2022 | 2904 | 743.66 | Yes | 743.66 | 18/09/2024 | 06/04/2023 | 11 | 424.42 | 0 | MVS
119 | MALDAH | Augmentation of Jatradanga Piped water supply scheme | TSM/010498 | SM/12734 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | 16/03/2022 | 1133 | 390.21 | Yes | 390.21 | 23/04/2025 | 28/12/2020 | 8 | 289.44 | 0 | MVS
120 | MALDAH | BAIRAT Piped Water Supply Scheme | TSM/014439 | SM/12743 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 22/08/2022 | 3235 | 939.2 | Yes | 939.2 | 21/04/2025 | 09/02/2023 | 7 | 839.49 | 0 | MVS
121 | MALDAH | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015035 | SM/12760 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | 22/08/2022 | 0 | 220.11 | Yes | 220.11 | 21/04/2025 | 07/12/2022 | 7 | 133.52 | 0 | MVS
122 | MALDAH | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014744 | SM/12761 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 22/08/2022 | 364 | 295.68 | Yes | 295.68 | 21/04/2025 | 17/05/2023 | 11 | 235.84 | 0 | MVS
123 | MALDAH | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | TSM/014864 | SM/12762 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | 22/08/2022 | 736 | 149.78 | Yes | 149.78 | 23/04/2025 | 02/06/2025 | 10 | 127.19 | 0 | MVS
124 | MALDAH | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014459 | SM/12763 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 22/08/2022 | 750 | 369.49 | Yes | 369.49 | 23/04/2025 | 17/05/2023 | 14 | 246.54 | 0 | MVS
125 | MALDAH | SRI CHANDRAPUR Piped Water Supply Scheme | TSM/014411 | SM/12764 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 22/08/2022 | 2782 | 703.14 | Yes | 703.14 | 21/04/2025 | 27/05/2025 | 11 | 677.03 | 0 | MVS
126 | MALDAH | Uttar Mahinagar Piped Water Supply Scheme | TSM/014266 | SM/12765 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 919 | 403.76 | Yes | 403.76 | 24/03/2025 | 17/06/2025 | 10 | 394.06 | 0 | MVS
127 | MALDAH | SAIDPUR Piped Water Supply Scheme | TSM/014263 | SM/12766 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 2570 | 846.78 | Yes | 846.78 | 21/04/2025 | 08/06/2023 | 8 | 752.17 | 0 | MVS
128 | MALDAH | NABAGRAM Piped Water Supply Scheme | TSM/013452 | SM/12767 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 22/08/2022 | 3517 | 876.56 | Yes | 876.56 | 23/04/2025 | 04/06/2025 | 10 | 154.05 | 0 | MVS
129 | MALDAH | BHADAR Piped Water Supply Scheme | TSM/014278 | SM/12768 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 2200 | 660.39 | Yes | 660.39 | 01/03/2024 | 26/12/2023 | 10 | 574.86 | 0 | MVS
130 | MALDAH | MATIHARPUR Piped Water Supply Scheme | TSM/013447 | SM/12769 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 22/08/2022 | 3531 | 994.01 | Yes | 994.01 | 15/01/2025 | 04/06/2025 | 7 | 233.33 | 0 | MVS
131 | MALDAH | Alal Zone-II Piped Water Supply Scheme | TSM/011886 | SM/12877 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 20/05/2022 | 1413 | 596.19 | Yes | 596.19 | 21/04/2025 | 17/05/2023 | 9 | 480.47 | 0 | MVS
132 | MALDAH | JAMALPUR Piped Water Supply Scheme. | TSM/013493 | SM/12879 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 05/07/2022 | 4212 | 1047.18 | Yes | 1047.18 | 02/08/2024 | 04/04/2025 | 8 | 991.3 | 0 | MVS
133 | MALDAH | UTTAR BHAKURIA Piped Water Supply Scheme. | TSM/013230 | SM/12881 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 05/07/2022 | 215 | 86.24 | Yes | 86.24 | 24/04/2025 | 27/06/2024 | 5 | 67.73 | 0 | MVS
134 | MALDAH | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. | TSM/014262 | SM/13237 | Augmentation | Malda Mechanical Division | Assistant Engineer - II | Junior Engineer-04 | 22/08/2022 | 0 | 123.52 | Yes | 123.52 |  | 05/12/2022 | 2 | 128.63 | 0 | MVS
135 | MALDAH | JIGIN Piped Water Supply Scheme | TSM/015837 | SM/13430 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 09/09/2022 | 459 | 234.18 | Yes | 234.18 | 21/04/2025 | 29/05/2025 | 8 | 175.41 | 0 | MVS
136 | MALDAH | ALINAGAR Piped Water Supply Scheme | TSM/015847 | SM/13431 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 09/09/2022 | 2356 | 724.32 | Yes | 724.32 | 24/04/2025 | 07/06/2024 | 13 | 703.98 | 0 | MVS
137 | MALDAH | HORGOA Piped Water Supply Scheme | TSM/015215 | SM/13432 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 09/09/2022 | 1714 | 684.91 | Yes | 684.91 | 08/08/2024 | 13/06/2024 | 14 | 678.92 | 0 | MVS
138 | MALDAH | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | TSM/015617 | SM/13451 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 09/09/2022 | 2345 | 837.04 | Yes | 837.04 | 18/09/2024 | 03/05/2023 | 13 | 602.34 | 0 | MVS
139 | MALDAH | BISHANPUR PIPED WATER SUPPLY SCHEME | TSM/014466 | SM/13507 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 09/09/2022 | 2698 | 682.77 | Yes | 682.77 | 30/07/2024 | 11/05/2023 | 8 | 443.6 | 0 | MVS
140 | MALDAH | OLTARA PIPED WATER SUPPLY SCHEME. | TSM/013242 | SM/13718 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 05/07/2022 | 3535 | 1253.79 | Yes | 1253.79 | 31/07/2024 | 11/06/2024 | 9 | 1145.79 | 0 | MVS
141 | MALDAH | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | TSM/013215 | SM/13719 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 05/07/2022 | 2824 | 1149.66 | Yes | 1149.66 | 02/08/2024 | 10/09/2024 | 9 | 1006.13 | 0 | MVS
142 | MALDAH | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | TSM/014505 | SM/13720 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 3632 | 1484.54 | Yes | 1484.54 | 21/04/2025 | 13/03/2023 | 7 | 1331.62 | 0 | MVS
143 | MALDAH | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | TSM/014431 | SM/13721 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 2846 | 1128.57 | Yes | 1128.57 | 21/04/2025 | 11/08/2023 | 7 | 1006.21 | 0 | MVS
144 | MALDAH | Mahil Piped Water Supply Scheme | TSM/014388 | SM/13733 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 4895 | 1895.5 | Yes | 1895.5 | 21/04/2025 | 13/06/2024 | 10 | 1755.22 | 0 | MVS
145 | MALDAH | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | TSM/013468 | SM/13734 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 22/08/2022 | 3312 | 1389.03 | Yes | 1389.03 | 15/01/2025 | 17/05/2023 | 10 | 1284.53 | 0 | MVS
146 | MALDAH | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | TSM/013458 | SM/13746 | New | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 09/09/2022 | 2560 | 880.68 | Yes | 880.68 | 21/04/2025 | 13/09/2024 | 13 | 871.55 | 0 | MVS
147 | MALDAH | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | TSM/011884 | SM/13792 | Augmentation | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 20/05/2022 | 11149 | 2992.8 | Yes | 2992.8 | 02/08/2024 | 13/03/2023 | 10 | 1709.63 | 0 | MVS
148 | MALDAH | KHARBA PIPED WATER SUPPLY SCHEME. | TSM/011882 | SM/13793 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 20/05/2022 | 5400 | 1220.74 | Yes | 1220.74 | 24/03/2025 | 22/08/2023 | 15 | 1017.57 | 0 | MVS
149 | MALDAH | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011274 | SM/14097 | New | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | 20/05/2022 | 3524 | 1143.9 | Yes | 1143.9 | 15/01/2025 | 18/08/2023 | 12 | 729.24 | 0 | MVS
150 | MALDAH | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011269 | SM/14098 | New | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | 20/05/2022 | 4588 | 1578.1 | Yes | 1578.1 | 25/10/2024 | 10/08/2023 | 9 | 1063.39 | 0 | MVS
151 | MALDAH | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | TSM/011899 | SM/14099 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | 20/05/2022 | 5251 | 2200.14 | Yes | 2200.14 | 25/04/2025 | 09/08/2023 | 6 | 1323.24 | 0 | MVS
152 | MALDAH | Pukuria Piped Water Supply Scheme | TSM/011879 | SM/14100 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 20/05/2022 | 5771 | 1884.19 | Yes | 1884.19 | 25/04/2025 | 18/05/2023 | 11 | 1270.5 | 0 | MVS
153 | MALDAH | FATEPUR Piped Water Supply Scheme | TSM/015785 | SM/14173 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 09/09/2022 | 4277 | 1581.73 | Yes | 1581.73 | 21/04/2025 | 28/06/2024 | 7 | 1382.79 | 0 | MVS
154 | MALDAH | RAHIMPUR Piped Water Supply Scheme | TSM/015255 | SM/14174 | New | Malda Mechanical Division | Assistant Engineer - II | Junior Engineer-07 | 09/09/2022 | 2638 | 1077.41 | Yes | 1077.41 | 21/04/2025 | 10/04/2023 | 10 | 1019.57 | 0 | MVS
155 | MALDAH | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | TSM/008179 | SM/14190 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | 16/03/2022 | 1245 | 546.57 | Yes | 546.57 | 23/04/2025 | 11/06/2024 | 11 | 290.01 | 0 | MVS
156 | MALDAH | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015034 | SM/14420 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | 22/08/2022 | 0 | 172.98 | Yes | 172.98 | 21/01/2025 | 02/02/2023 | 8 | 139.12 | 0 | MVS
157 | MALDAH | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | TSM/013552 | SM/14461 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 30/09/2022 | 1274 | 447.97 | Yes | 447.97 | 21/04/2025 | 28/06/2024 | 10 | 389.12 | 0 | MVS
158 | MALDAH | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017203 | SM/15057 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | 16/11/2022 | 0 | 64.27 | Yes | 64.27 | 15/02/2023 | 17/02/2023 | 4 | 29.04 | 0 | MVS
159 | MALDAH | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016552 | SM/15062 | Augmentation | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 16/11/2022 | 0 | 93.1 | Yes | 93.1 | 24/03/2025 | 17/06/2025 | 7 | 87.78 | 0 | MVS
160 | MALDAH | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016220 | SM/15063 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 16/11/2022 | 250 | 124.6 | Yes | 124.6 | 21/04/2025 | 21/05/2025 | 9 | 100.1 | 0 | MVS
161 | MALDAH | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016724 | SM/15065 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 16/11/2022 | 0 | 216.09 | Yes | 216.09 | 24/03/2025 | 17/02/2023 | 6 | 172.62 | 0 | MVS
162 | MALDAH | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016694 | SM/15073 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 16/11/2022 | 0 | 96.31 | Yes | 96.31 | 29/07/2024 | 17/02/2023 | 6 | 60.82 | 0 | MVS
163 | MALDAH | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016722 | SM/15074 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 16/11/2022 | 0 | 83.83 | Yes | 83.83 | 23/02/2024 | 17/02/2023 | 7 | 78.55 | 0 | MVS
164 | MALDAH | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016720 | SM/15079 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | 16/11/2022 | 350 | 166.09 | Yes | 166.09 | 12/12/2024 | 21/03/2023 | 14 | 159.88 | 0 | MVS
165 | MALDAH | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016719 | SM/15080 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | 16/11/2022 | 0 | 213.72 | Yes | 213.72 | 10/01/2024 | 08/05/2025 | 11 | 165.9 | 0 | MVS
166 | MALDAH | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016679 | SM/15083 | Augmentation | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 16/11/2022 | 0 | 75.97 | Yes | 75.97 | 23/04/2025 | 27/05/2025 | 6 | 67.72 | 0 | MVS
167 | MALDAH | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | TSM/017205 | SM/15086 | Augmentation | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | 16/11/2022 | 0 | 116.57 | Yes | 116.57 | 22/11/2024 | 17/02/2023 | 5 | 93.75 | 0 | MVS
168 | MALDAH | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017129 | SM/15090 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 16/11/2022 | 0 | 102.52 | Yes | 102.52 | 21/01/2025 | 10/06/2024 | 10 | 87.85 | 0 | MVS
169 | MALDAH | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017125 | SM/15091 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 16/11/2022 | 0 | 84.27 | Yes | 84.27 | 23/02/2024 | 07/06/2024 | 7 | 85.46 | 0 | MVS
170 | MALDAH | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016347 | SM/15093 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | 16/11/2022 | 950 | 196.91 | Yes | 196.91 | 21/04/2025 | 09/12/2024 | 13 | 173.1 | 0 | MVS
171 | MALDAH | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016470 | SM/15102 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | 16/11/2022 | 0 | 104.31 | Yes | 104.31 | 22/11/2024 | 26/05/2025 | 8 | 67.84 | 0 | MVS
172 | MALDAH | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016549 | SM/15105 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 16/11/2022 | 0 | 212.37 | Yes | 212.37 | 30/07/2024 | 17/02/2023 | 8 | 180.02 | 0 | MVS
173 | MALDAH | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016529 | SM/15106 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | 16/11/2022 | 1658 | 149.47 | Yes | 149.47 | 24/04/2025 | 28/06/2024 | 7 | 90.76 | 0 | MVS
174 | MALDAH | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016471 | SM/15108 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | 16/11/2022 | 150 | 100.43 | Yes | 100.43 | 22/11/2024 | 27/05/2025 | 8 | 90.94 | 0 | MVS
175 | MALDAH | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016354 | SM/15110 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | 16/11/2022 | 130 | 119.4 | Yes | 119.4 | 17/04/2025 | 21/03/2023 | 5 | 60.08 | 0 | MVS
176 | MALDAH | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016285 | SM/15111 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | 16/11/2022 | 869 | 272.73 | Yes | 272.73 | 23/04/2025 | 20/04/2023 | 8 | 147.84 | 0 | MVS
177 | MALDAH | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016501 | SM/15112 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | 16/11/2022 | 0 | 84.77 | Yes | 84.77 | 23/07/2024 | 07/06/2024 | 6 | 63.65 | 0 | MVS
178 | MALDAH | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015614 | SM/15113 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 16/11/2022 | 1251 | 261.08 | Yes | 261.08 | 24/03/2025 | 27/06/2024 | 14 | 253.71 | 0 | MVS
179 | MALDAH | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | TSM/018015 | SM/15140 | New | Malda Arsenic Area W/S Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | 16/11/2022 | 2662 | 768.6 | Yes | 768.6 | 24/03/2025 | 04/05/2023 | 13 | 550.7 | 0 | MVS
180 | MALDAH | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | TSM/017481 | SM/15141 | Augmentation | Malda Arsenic Area W/S Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | 16/11/2022 | 550 | 131.66 | Yes | 131.66 | 21/10/2024 | 23/05/2023 | 14 | 120.45 | 0 | MVS
181 | MALDAH | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | TSM/017446 | SM/15142 | Augmentation | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | 16/11/2022 | 0 | 622.76 | Yes | 622.76 | 24/01/2023 | 15/02/2023 | 17 | 509.33 | 0 | MVS
182 | MALDAH | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | TSM/018197 | SM/15143 | Augmentation | Malda Arsenic Area W/S Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | 16/11/2022 | 0 | 270.23 | Yes | 270.23 | 03/02/2023 | 21/01/2021 | 5 | 212.43 | 0 | MVS
183 | MALDAH | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | TSM/017480 | SM/15144 | Augmentation | Malda Arsenic Area W/S Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | 16/11/2022 | 600 | 144.97 | Yes | 144.97 | 18/09/2024 | 13/04/2023 | 10 | 106.1 | 0 | MVS
184 | MALDAH | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED | TSM/018215 | SM/15145 | Augmentation | Malda Arsenic Area W/S Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | 16/11/2022 | 0 | 31.42 | Yes | 31.42 | 01/02/2023 | 23/05/2023 | 2 | 23.31 | 0 | MVS
185 | MALDAH | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019388 | SM/15149 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | 16/11/2022 | 375 | 881.16 | Yes | 881.16 | 02/08/2024 | 14/07/2023 | 7 | 618.56 | 0 | MVS
186 | MALDAH | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017676 | SM/15155 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | 16/11/2022 | 1413 | 398.39 | Yes | 398.39 | 21/04/2025 | 02/05/2023 | 9 | 281.29 | 0 | MVS
187 | MALDAH | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017677 | SM/15188 | Augmentation | RWS Malda Sub-Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | 16/11/2022 | 2641 | 390.5 | Yes | 390.5 | 21/04/2025 | 13/09/2024 | 9 | 278.39 | 0 | MVS
188 | MALDAH | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016606 | SM/15190 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 16/11/2022 | 0 | 103.91 | Yes | 103.91 | 24/03/2025 | 10/06/2024 | 8 | 76.31 | 0 | MVS
189 | MALDAH | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019390 | SM/15193 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | 16/11/2022 | 420 | 988.47 | Yes | 988.47 | 24/03/2025 | 02/06/2023 | 8 | 779.45 | 0 | MVS
190 | MALDAH | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. | TSM/017379 | SM/15197 | Augmentation | Malda Sadar Sub-Division | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | 16/11/2022 | 0 | 164.65 | Yes | 164.65 | 24/03/2025 | 21/02/2023 | 3 | 163.41 | 0 | MVS
191 | MALDAH | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015613 | SM/15201 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | 16/11/2022 | 450 | 196.28 | Yes | 196.28 | 21/04/2025 | 13/09/2024 | 8 | 175.58 | 0 | MVS
192 | MALDAH | MEHERPUR PIPED WATER SUPPLY SCHEME | TSM/011828 | SM/15222 | New | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | 20/05/2022 | 4342 | 1264.51 | Yes | 1264.51 | 01/08/2024 | 07/06/2024 | 11 | 940.62 | 0 | MVS
193 | MALDAH | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011258 | SM/15223 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | 30/03/2022 | 8288 | 2486.52 | Yes | 2486.52 | 25/04/2025 | 11/05/2023 | 13 | 1846.48 | 0 | MVS
194 | MALDAH | MATHURAPUR PIPED WATER SUPPLY SCHEME | TSM/013453 | SM/15248 | New | Chanchal Sub-Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 30/09/2022 | 2416 | 576.55 | Yes | 576.55 | 15/01/2025 | 12/05/2023 | 9 | 546.07 | 0 | MVS
195 | MALDAH | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | TSM/017775 | SM/15275 | New | Malda Arsenic Area W/S Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | 16/11/2022 | 2458 | 994.39 | Yes | 994.39 | 18/09/2024 | 06/06/2023 | 14 | 871.19 | 0 | MVS
196 | MALDAH | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019389 | SM/15308 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | 16/11/2022 | 340 | 879.54 | Yes | 879.54 | 02/08/2024 | 03/05/2023 | 9 | 847.12 | 0 | MVS
197 | MALDAH | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | TSM/016030 | SM/15521 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 26/09/2022 | 4378 | 1310.98 | Yes | 1310.98 | 04/10/2024 | 04/05/2023 | 10 | 1063.63 | 0 | MVS
198 | MALDAH | DILALBATI Piped Water Supply Scheme. | TSM/014129 | SM/15903 | New | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 30/09/2022 | 521 | 292.15 | Yes | 292.15 | 21/04/2025 | 28/05/2025 | 10 | 231.89 | 0 | MVS
199 | MALDAH | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | TSM/017774 | SM/15944 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 28/12/2022 | 833 | 571.17 | Yes | 571.17 | 18/09/2024 | 01/08/2023 | 8 | 355.92 | 0 | MVS
200 | MALDAH | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | TSM/017773 | SM/15946 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 28/12/2022 | 858 | 507.92 | Yes | 507.92 | 28/04/2023 | 14/07/2023 | 2 | 387.57 | 0 | MVS
201 | MALDAH | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | TSM/018180 | SM/15947 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 28/12/2022 | 2472 | 875.39 | Yes | 875.39 | 18/09/2024 | 01/08/2023 | 9 | 664.18 | 0 | MVS
202 | MALDAH | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | TSM/017675 | SM/15948 | Augmentation | Chanchal Sub-Division | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | 28/12/2022 | 733 | 254.87 | Yes | 254.87 | 21/04/2025 | 11/07/2024 | 8 | 114.09 | 0 | MVS
203 | MALDAH | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | TSM/017551 | SM/15949 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 28/12/2022 | 2088 | 734.03 | Yes | 734.03 | 18/09/2024 | 06/04/2023 | 11 | 547.83 | 0 | MVS
204 | MALDAH | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | TSM/018013 | SM/15950 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 28/12/2022 | 850 | 491.4 | Yes | 491.4 | 18/09/2024 | 05/10/2023 | 8 | 382.86 | 0 | MVS
205 | MALDAH | Augmentation of Alal Zone-III Piped Water Supply Scheme | TSM/011885 | SM/15951 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | 28/12/2022 | 1052 | 425.25 | Yes | 425.25 | 21/04/2025 | 08/06/2023 | 10 | 395.13 | 0 | MVS
206 | MALDAH | Augmentation of Nasipur Piped Water Supply Scheme | TSM/011880 | SM/15952 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | 28/12/2022 | 2049 | 868.83 | Yes | 868.83 | 08/08/2024 | 21/05/2025 | 13 | 687.04 | 0 | MVS
207 | MALDAH | Augmentation of Adina Zone-II Piped Water Supply Scheme | TSM/011890 | SM/15956 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 28/12/2022 | 649 | 355.78 | Yes | 355.78 | 21/04/2025 | 02/05/2023 | 7 | 313.49 | 0 | MVS
208 | MALDAH | Augmentation of Adina Zone-I Piped Water Supply Scheme | TSM/011889 | SM/15958 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | 28/12/2022 | 972 | 543.44 | Yes | 543.44 | 23/04/2025 | 08/06/2023 | 7 | 445.44 | 0 | MVS
209 | MALDAH | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | TSM/017385 | SM/15960 | New | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | 28/12/2022 | 106 | 49.53 | Yes | 49.53 | 10/01/2024 | 30/03/2023 | 5 | 43.8 | 0 | MVS
210 | MALDAH | SUJAPUR PIPED WATER SUPPLY SCHEME | TSM/018437 | SM/15962 | New | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | 28/12/2022 | 1287 | 586.08 | Yes | 586.08 | 15/01/2025 | 07/06/2023 | 9 | 543.58 | 0 | MVS
211 | MALDAH | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019385 | SM/16053 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | 28/12/2022 | 125 | 620.93 | Yes | 620.93 | 02/08/2024 | 26/04/2023 | 8 | 462.92 | 0 | MVS
212 | MALDAH | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019387 | SM/16382 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | 16/11/2022 | 500 | 1030.99 | Yes | 1030.99 | 24/03/2025 | 10/06/2024 | 7 | 903.69 | 0 | MVS
213 | MALDAH | Augmentation of Mahishbathani Piped Water Supply Scheme | TSM/017802 | SM/16383 | Augmentation | Malda Mechanical Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | 16/11/2022 | 1587 | 328.05 | Yes | 328.05 | 01/08/2024 | 17/05/2023 | 6 | 139.23 | 0 | MVS
214 | MALDAH | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | TSM/015921 | SM/17177 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 09/09/2022 | 2406 | 967 | Yes | 967 | 18/09/2024 | 04/05/2023 | 9 | 724.31 | 0 | MVS
215 | MALDAH | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | TSM/015930 | SM/17178 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 09/09/2022 | 2134 | 855.71 | Yes | 855.71 | 18/09/2024 | 01/08/2023 | 9 | 493.61 | 0 | MVS
216 | MALDAH | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | TSM/017477 | SM/17201 | New | Malda Arsenic Area W/S Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | 28/12/2022 | 8677 | 714.72 | Yes | 714.72 | 18/09/2024 | 26/07/2023 | 10 | 600.58 | 0 | MVS
217 | MALDAH | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | TSM/018102 | SM/18232 | New |  |  |  | 28/12/2022 | 2545 | 1365.35 | Yes | 1365.35 | 04/02/2025 | 13/07/2023 | 16 | 1063.35 | 0 | MVS
218 | MALDAH | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED | TSM/017806 | SM/18418 | New |  |  |  | 16/11/2022 | 3327 | 1309.89 | Yes | 1309.89 | 06/03/2025 | 01/08/2023 | 14 | 694.32 | 0 | MVS
219 | MALDAH | PERAPUR PWSS | TSM/015903 | SM/18420 | New |  |  |  | 30/09/2022 | 3213 | 1213.51 | Yes | 1213.51 | 21/04/2025 | 30/04/2025 | 8 | 1135.64 | 0 | MVS
220 | MALDAH | KALUARI PWSS | TSM/018421 | SM/18427 | New |  |  |  | 16/11/2022 | 4894 | 1380.18 | Yes | 1380.18 | 29/07/2024 | 07/06/2024 | 13 | 1105.73 | 0 | MVS
221 | MALDAH | PARAIL PWSS | TSM/014391 | SM/18431 | New |  |  |  | 22/08/2022 | 3263 | 1276.14 | Yes | 1276.14 | 21/04/2025 | 07/08/2023 | 6 | 1134.69 | 0 | MVS
222 | MALDAH | PARAHAR PWSS | TSM/014116 | SM/18432 | New |  |  |  | 22/08/2022 | 2983 | 1356.09 | Yes | 1356.09 | 21/04/2025 | 10/06/2024 | 9 | 1246.45 | 0 | MVS
223 | MALDAH | BABUPUR PWSS | TSM/014434 | SM/18433 | New |  |  |  | 22/08/2022 | 5617 | 1697.39 | Yes | 1697.39 | 21/04/2025 | 09/08/2023 | 10 | 1520.24 | 0 | MVS
224 | MALDAH | Augmentation of Samsi PWSS. | TSM/008164 | SM/18447 | Augmentation |  |  |  | 16/03/2022 | 6805 | 2234.04 | Yes | 2234.04 | 25/04/2025 | 08/08/2023 | 12 | 1294.21 | 0 | MVS
225 | MALDAH | DAHIL Piped Water Supply Scheme. | TSM/015609 | SM/18461 | New |  |  |  | 09/09/2022 | 4422 | 1594.44 | Yes | 1594.44 | 21/04/2025 | 28/05/2025 | 7 | 1387.68 | 0 | MVS
226 | MALDAH | HATNAGAR PIPED WATER SUPPLY SCHEME | TSM/020336 | SM/18496 | New |  |  |  | 28/12/2022 | 2677 | 1232.77 | Yes | 1232.77 | 21/04/2025 | 04/08/2025 | 9 | 1071.07 | 0 | MVS
227 | MALDAH | MORGRAM PWSS | TSM/018419 | SM/18557 | New |  |  |  | 16/11/2022 | 3767 | 1098.97 | Yes | 1098.97 | 05/05/2025 | 02/02/2024 | 13 | 977.75 | 0 | MVS
228 | MALDAH | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017388 | SM/18558 | Augmentation |  |  |  | 16/11/2022 | 9132 | 3085.32 | Yes | 3085.32 | 28/04/2025 | 21/05/2025 | 20 | 2282.68 | 0 | MVS
229 | MALDAH | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | TSM/019386 | SM/18660 | Augmentation |  |  |  | 16/11/2022 | 0 | 80427.62 | Yes | 80427.62 | 28/01/2025 | 11/11/2024 | 30 | 35902.95 | 0 | MVS
230 | MALDAH | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | TSM/017908 | SM/18685 | New |  |  |  | 28/12/2022 | 12384 | 15363.32 | Yes | 15363.32 | 28/04/2023 | 23/09/2024 | 10 | 14470.48 | 0 | MVS
231 | MALDAH | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | TSM/018373 | SM/18686 | New | Chanchal Sub-Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | 28/12/2022 | 56048 | 68069.12 | Yes | 68069.12 | 25/04/2025 | 28/08/2024 | 12 | 32309.8 | 0 | MVS
232 | MALDAH | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/020578 | SM/18910 | Augmentation |  |  |  | 10/03/2023 | 0 | 133.47 | Yes | 133.47 | 08/08/2024 | 30/08/2024 | 1 | 131.79 | 0 | MVS
233 | MALDAH | SOURCE AUGMENTATION TROUGH INTRODUCING ROLLING TYPE BARGE FOR RAW WATER LIFTING FROM RIVER FULHAR AT INTAKE STATION OF BALUPUR WATER SUPPLY SCHEME UNDER RATUA-I BLOCK IN THE DISTRICT OF MALDA UNDER MALDA MECHANICAL DIVISION, PHE DTE. | TSM/021467 | SM/18911 | Augmentation |  |  |  | 10/03/2023 | 0 | 109.49 | Yes | 109.49 | 25/04/2025 | 07/03/2024 | 1 | 105.37 | 0 | MVS
234 | MALDAH | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | TSM/020265 | SM/19225 | Augmentation |  |  |  | 16/11/2022 | 0 | 2769.31 | Yes | 2769.31 | 04/04/2025 | 03/12/2024 | 6 | 1853.74 | 0 | MVS
Total | [9 empty] | 918158 | 308914.29 |  | 308914.29 |  |  | 2451 | 196861.98 | 1981.92