## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS | TSM/005619 | SM/06745 | Retrofitting |  |  |  | 28/08/2020 | 1563 | 78.36 | Yes | 78.36 | 05/04/2023 | 05/10/2024 | 5 | 78.18 | 78.18 | MVS
2 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS | TSM/005627 | SM/06746 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 28/08/2020 | 1075 | 72.6 | Yes | 72.6 | 29/02/2024 | 20/04/2022 | 4 | 72.37 | 97.26 | MVS
3 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | TSM/005628 | SM/06747 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 28/08/2020 | 567 | 39.12 | Yes | 39.12 | 05/05/2025 | 07/08/2020 | 6 | 34.07 | 20.42 | MVS
4 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | TSM/005622 | SM/06748 | Retrofitting |  |  |  | 28/08/2020 | 1827 | 99.68 | Yes | 99.68 |  | 04/08/2020 | 8 | 100.03 | 189.35 | MVS
5 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | TSM/005621 | SM/06749 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 28/08/2020 | 1484 | 93.49 | Yes | 93.49 | 24/04/2025 | 07/08/2020 | 5 | 85.25 | 88.02 | MVS
6 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS | TSM/005618 | SM/06750 | Retrofitting |  |  |  | 28/08/2020 | 1006 | 58.89 | Yes | 58.89 | 13/01/2023 | 08/06/2021 | 2 | 67.88 | 70.16 | MVS
7 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | TSM/005623 | SM/06751 | Retrofitting |  |  |  | 28/08/2020 | 1898 | 99.03 | Yes | 99.03 | 21/03/2025 | 09/12/2022 | 6 | 119.53 | 194.09 | MVS
8 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | TSM/005625 | SM/06752 | Retrofitting |  |  |  | 28/08/2020 | 1308 | 81.95 | Yes | 81.95 | 26/04/2023 | 01/06/2023 | 20 | 143.92 | 118 | MVS
9 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS | TSM/005626 | SM/06753 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 28/08/2020 | 917 | 53.37 | Yes | 53.37 |  | 04/08/2020 | 4 | 15 | 29.68 | MVS
10 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | TSM/005614 | SM/06768 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 28/08/2020 | 583 | 37.98 | Yes | 37.98 |  | 09/07/2020 | 9 | 32.09 | 39.62 | MVS
11 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | TSM/005615 | SM/06769 | Retrofitting |  |  |  | 28/08/2020 | 1732 | 89.62 | Yes | 89.62 |  | 03/11/2020 | 5 | 81.77 | 159.38 | MVS
12 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | TSM/005616 | SM/06770 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 28/08/2020 | 607 | 46.11 | Yes | 46.11 | 17/04/2025 | 24/04/2023 | 7 | 41.69 | 55.96 | MVS
13 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | TSM/005617 | SM/06771 | Retrofitting |  |  |  | 28/08/2020 | 1583 | 91.38 | Yes | 91.38 |  | 13/07/2021 | 9 | 148.9 | 167.47 | MVS
14 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS | TSM/005624 | SM/06772 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 28/08/2020 | 1157 | 74.63 | Yes | 74.63 | 25/04/2023 | 15/02/2022 | 3 | 56.75 | 75.23 | MVS
15 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | TSM/005620 | SM/06773 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 28/08/2020 | 1113 | 60.25 | Yes | 60.25 |  | 07/12/2020 | 6 | 60.22 | 117 | MVS
16 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme | TSM/006219 | SM/06962 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 25/09/2020 | 1829 | 99.94 | Yes | 99.94 | 22/09/2023 | 07/12/2020 | 4 | 76.88 | 135.55 | MVS
17 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | TSM/006209 | SM/06963 | Retrofitting |  |  |  | 25/09/2020 | 1751 | 99.85 | Yes | 99.85 | 01/03/2024 | 18/07/2023 | 16 | 95.58 | 169.87 | MVS
18 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | TSM/006204 | SM/06964 | Retrofitting |  |  |  | 25/09/2020 | 1798 | 99.26 | Yes | 99.26 | 07/11/2023 | 24/08/2023 | 11 | 91.65 | 159.64 | MVS
19 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | TSM/006200 | SM/06965 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 25/09/2020 | 1893 | 91.43 | Yes | 91.43 |  | 28/06/2021 | 8 | 91.4 | 77.97 | MVS
20 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme | TSM/006202 | SM/06966 | Retrofitting |  |  |  | 25/09/2020 | 1871 | 98.36 | Yes | 98.36 | 25/08/2022 | 04/08/2020 | 7 | 98.61 | 155.79 | MVS
21 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | TSM/006205 | SM/06967 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 25/09/2020 | 1490 | 81.42 | Yes | 81.42 |  | 21/06/2021 | 8 | 42.26 | 75.8 | MVS
22 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | TSM/006212 | SM/06968 | Retrofitting |  |  |  | 25/09/2020 | 1895 | 99.96 | Yes | 99.96 | 18/10/2023 | 10/08/2020 | 6 | 99.96 | 199.84 | MVS
23 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | TSM/006218 | SM/06969 | Retrofitting |  |  |  | 25/09/2020 | 1429 | 83.79 | Yes | 83.79 |  | 03/06/2021 | 16 | 85.45 | 151.15 | MVS
24 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | TSM/006220 | SM/06970 | Retrofitting |  |  |  | 25/09/2020 | 1184 | 70.91 | Yes | 70.91 | 12/03/2024 | 10/08/2020 | 8 | 63.2 | 119.07 | MVS
25 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | TSM/006221 | SM/06971 | Retrofitting |  |  |  | 25/09/2020 | 1937 | 99.89 | Yes | 99.89 | 05/09/2024 | 27/04/2022 | 18 | 99.84 | 93.97 | MVS
26 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | TSM/006224 | SM/06972 | Retrofitting |  |  |  | 25/09/2020 | 1996 | 99.97 | Yes | 99.97 |  | 07/08/2020 | 9 | 96.61 | 128.84 | MVS
27 | PURBA BARDHAMAN | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | TSM/006207 | SM/07201 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 25/09/2020 | 515 | 47.47 | Yes | 47.47 | 13/01/2023 | 13/09/2023 | 10 | 28.77 | 38.47 | MVS
28 | PURBA BARDHAMAN | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | TSM/006217 | SM/07202 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 25/09/2020 | 503 | 46.9 | Yes | 46.9 | 27/01/2025 | 27/02/2023 | 12 | 23.34 | 41.56 | MVS
29 | PURBA BARDHAMAN | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | TSM/006210 | SM/07203 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 25/09/2020 | 521 | 47.76 | Yes | 47.76 | 06/11/2024 | 28/03/2024 | 12 | 22.44 | 39.59 | MVS
30 | PURBA BARDHAMAN | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | TSM/006222 | SM/07204 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 25/09/2020 | 1976 | 99.8 | Yes | 99.8 | 09/04/2025 | 08/10/2020 | 6 | 58.89 | 99.89 | MVS
31 | PURBA BARDHAMAN | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | TSM/006223 | SM/07205 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 25/09/2020 | 576 | 39.16 | Yes | 39.16 | 24/04/2025 | 10/08/2020 | 9 | 24.76 | 41.13 | MVS
32 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | TSM/006620 | SM/07544 | Retrofitting |  |  |  | 04/12/2020 | 1551 | 73.32 | Yes | 73.32 | 11/05/2023 | 20/03/2023 | 8 | 83.92 | 99.82 | MVS
33 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | TSM/006611 | SM/07545 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1555 | 73.51 | Yes | 73.51 | 29/10/2024 | 01/06/2023 | 13 | 58.92 | 52.98 | MVS
34 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | TSM/006621 | SM/07546 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 04/12/2020 | 2028 | 95.87 | Yes | 95.87 | 20/07/2023 | 06/09/2021 | 6 | 120.64 | 67.22 | MVS
35 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme | TSM/006587 | SM/07547 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 880 | 41.6 | Yes | 41.6 | 13/04/2023 | 09/06/2021 | 3 | 45.12 | 41.6 | MVS
36 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | TSM/006589 | SM/07548 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 1903 | 89.96 | Yes | 89.96 | 16/03/2023 | 18/04/2023 | 7 | 70.08 | 70.03 | MVS
37 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | TSM/006597 | SM/07549 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. |  | 04/12/2020 | 1744 | 82.44 | Yes | 82.44 | 02/09/2024 | 22/01/2021 | 9 | 66.31 | 29.05 | MVS
38 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | TSM/006595 | SM/07550 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. |  | 04/12/2020 | 2000 | 94.55 | Yes | 94.55 | 12/07/2023 | 19/04/2022 | 10 | 95.65 | 93.95 | MVS
39 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | TSM/006612 | SM/07551 | Retrofitting |  |  |  | 04/12/2020 | 1452 | 57.39 | Yes | 57.39 | 17/01/2024 | 21/06/2021 | 9 | 91.61 | 88.73 | MVS
40 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | TSM/006605 | SM/07552 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 04/12/2020 | 1610 | 92.04 | Yes | 92.04 | 13/01/2023 | 07/02/2023 | 10 | 92.02 | 89.61 | MVS
41 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | TSM/006649 | SM/07553 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 1536 | 99.79 | Yes | 99.79 | 06/12/2024 | 23/05/2022 | 7 | 119.22 | 97.35 | MVS
42 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Chandutia Piped Water Supply Scheme | TSM/006650 | SM/07554 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 413 | 26.82 | Yes | 26.82 | 29/02/2024 | 04/01/2022 | 1 | 5 | 5 | MVS
43 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme | TSM/006653 | SM/07555 | Retrofitting |  |  |  | 04/12/2020 | 264 | 16.96 | Yes | 16.96 |  | 16/10/2020 | 3 | 18.06 | 18.61 | MVS
44 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | TSM/006660 | SM/07556 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 816 | 52.23 | Yes | 52.23 |  | 09/12/2022 | 11 | 56.84 | 57.94 | MVS
45 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | TSM/006657 | SM/07557 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1153 | 74.73 | Yes | 74.73 | 01/03/2024 | 22/05/2023 | 7 | 41.04 | 40.03 | MVS
46 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | TSM/006599 | SM/07775 | Retrofitting | Katwa Sub-Division | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | 04/12/2020 | 2550 | 120.55 | Yes | 120.55 | 26/07/2024 | 21/09/2021 | 15 | 119.55 | 68.48 | MVS
47 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | TSM/006602 | SM/07776 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 04/12/2020 | 2615 | 123.62 | Yes | 123.62 | 06/04/2023 | 05/01/2022 | 7 | 60.59 | 78.77 | MVS
48 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | TSM/006591 | SM/07777 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 2118 | 100.12 | Yes | 100.12 | 05/06/2025 | 23/09/2024 | 10 | 76.65 | 96.23 | MVS
49 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block | TSM/006609 | SM/07778 | Retrofitting |  |  |  | 04/12/2020 | 2395 | 113.22 | Yes | 113.22 | 29/02/2024 | 29/06/2021 | 2 | 89.64 | 89.64 | MVS
50 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | TSM/006590 | SM/07779 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 2517 | 142.32 | Yes | 142.32 | 05/09/2024 | 25/09/2024 | 12 | 128.91 | 78.95 | MVS
51 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | TSM/006671 | SM/07780 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 5098 | 297.21 | Yes | 297.21 | 05/05/2025 | 02/12/2022 | 15 | 159.61 | 166.8 | MVS
52 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | TSM/006685 | SM/07781 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 1810 | 103.35 | Yes | 103.35 | 22/08/2022 | 01/06/2023 | 8 | 59.42 | 90.85 | MVS
53 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | TSM/006692 | SM/07782 | Retrofitting |  |  |  | 04/12/2020 | 2001 | 117.85 | Yes | 117.85 | 23/05/2022 | 06/09/2021 | 6 | 151.96 | 204.85 | MVS
54 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | TSM/006593 | SM/07797 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 828 | 39.14 | Yes | 39.14 | 12/09/2024 | 10/06/2024 | 7 | 36.28 | 19.86 | MVS
55 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | TSM/006615 | SM/07798 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 1881 | 88.92 | Yes | 88.92 | 24/04/2025 | 15/02/2021 | 7 | 93.69 | 152.43 | MVS
56 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | TSM/006601 | SM/07799 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. |  | 04/12/2020 | 2007 | 67.65 | Yes | 67.65 | 22/10/2024 | 18/05/2023 | 2 | 16.66 | 16.66 | MVS
57 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | TSM/006622 | SM/07800 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 04/12/2020 | 1910 | 90.29 | Yes | 90.29 | 18/12/2025 | 27/10/2021 | 6 | 24.03 | 20.41 | MVS
58 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | TSM/006654 | SM/07801 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1538 | 96.93 | Yes | 96.93 |  | 19/04/2023 | 5 | 64.75 | 74.46 | MVS
59 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block | TSM/006661 | SM/07802 | Retrofitting |  |  |  | 04/12/2020 | 446 | 28.42 | Yes | 28.42 |  | 18/02/2021 | 4 | 39.5 | 30.81 | MVS
60 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | TSM/006663 | SM/07803 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1103 | 71.15 | Yes | 71.15 | 12/03/2024 | 03/12/2020 | 5 | 33.98 | 62.44 | MVS
61 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | TSM/006667 | SM/07804 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1262 | 79.59 | Yes | 79.59 | 01/02/2024 | 31/08/2021 | 13 | 63.02 | 82.66 | MVS
62 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | TSM/006666 | SM/07805 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 713 | 46.03 | Yes | 46.03 | 26/09/2022 | 16/10/2020 | 6 | 30.5 | 43.59 | MVS
63 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block | TSM/006665 | SM/07806 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 410 | 26.44 | Yes | 26.44 | 26/09/2022 | 05/08/2024 | 4 | 20.41 | 30.13 | MVS
64 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | TSM/006679 | SM/07807 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 1017 | 62.17 | Yes | 62.17 | 16/03/2023 | 30/06/2022 | 7 | 76.57 | 42.7 | MVS
65 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | TSM/006677 | SM/07808 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 1383 | 89.76 | Yes | 89.76 | 23/08/2023 | 06/06/2024 | 7 | 85.86 | 68.7 | MVS
66 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | TSM/006675 | SM/07809 | Retrofitting |  |  |  | 04/12/2020 | 1133 | 69.73 | Yes | 69.73 | 20/07/2023 | 18/04/2023 | 7 | 68.19 | 101.26 | MVS
67 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | TSM/006674 | SM/07810 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 1398 | 83.84 | Yes | 83.84 | 22/07/2024 | 03/12/2024 | 3 | 54.74 | 65.19 | MVS
68 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kasiara Piped Water Supply Scheme atMangolkote Block | TSM/006694 | SM/07811 | Retrofitting |  |  |  | 04/12/2020 | 1041 | 65.25 | Yes | 65.25 |  | 22/09/2020 | 3 | 100.96 | 130.49 | MVS
69 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | TSM/006613 | SM/07812 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 2474 | 116.95 | Yes | 116.95 | 01/02/2024 | 12/10/2023 | 16 | 116.41 | 94.21 | MVS
70 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | TSM/006607 | SM/07813 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 04/12/2020 | 2942 | 139.08 | Yes | 139.08 | 04/09/2024 | 11/10/2023 | 19 | 86.68 | 85.67 | MVS
71 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | TSM/006594 | SM/07814 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 4050 | 191.46 | Yes | 191.46 | 05/05/2025 | 23/09/2024 | 10 | 97.17 | 85 | MVS
72 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | TSM/006603 | SM/07815 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 3443 | 162.76 | Yes | 162.76 | 04/03/2024 | 23/05/2022 | 11 | 155.84 | 190.37 | MVS
73 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | TSM/006596 | SM/07816 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. |  | 04/12/2020 | 2571 | 109.06 | Yes | 109.06 | 12/09/2024 | 06/04/2022 | 17 | 126.82 | 86.04 | MVS
74 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | TSM/006588 | SM/07817 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 2806 | 132.65 | Yes | 132.65 | 16/02/2024 | 05/06/2024 | 5 | 130.57 | 75.52 | MVS
75 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | TSM/006598 | SM/07818 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. |  | 04/12/2020 | 2581 | 122.01 | Yes | 122.01 | 05/08/2024 | 19/04/2022 | 13 | 125.06 | 165.3 | MVS
76 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme | TSM/006647 | SM/07819 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 04/12/2020 | 3993 | 257.15 | Yes | 257.15 | 19/11/2024 | 01/02/2021 | 4 | 134.69 | 55.4 | MVS
77 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | TSM/006627 | SM/07820 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 2176 | 141.29 | Yes | 141.29 | 04/04/2025 | 24/08/2023 | 12 | 199.94 | 128.16 | MVS
78 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | TSM/006625 | SM/07821 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 04/12/2020 | 1654 | 105.81 | Yes | 105.81 | 24/04/2025 | 22/07/2021 | 7 | 86.42 | 77.93 | MVS
79 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | TSM/006624 | SM/07822 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 3222 | 205.82 | Yes | 205.82 | 06/03/2024 | 26/05/2023 | 8 | 217.06 | 171.93 | MVS
80 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | TSM/006626 | SM/07823 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 2579 | 151.83 | Yes | 151.83 | 23/05/2025 | 10/06/2024 | 16 | 68.63 | 64.35 | MVS
81 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | TSM/006672 | SM/07824 | Retrofitting |  |  |  | 04/12/2020 | 1830 | 117.09 | Yes | 117.09 |  | 23/08/2024 | 9 | 102.8 | 133.83 | MVS
82 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | TSM/006658 | SM/07825 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1867 | 121.31 | Yes | 121.31 | 26/09/2022 | 28/02/2023 | 11 | 174.96 | 142.8 | MVS
83 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block | TSM/006662 | SM/07826 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1637 | 104.89 | Yes | 104.89 | 21/03/2025 | 13/09/2024 | 5 | 69.57 | 72.14 | MVS
84 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | TSM/006664 | SM/07827 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 1969 | 126.36 | Yes | 126.36 | 14/01/2025 | 25/09/2024 | 5 | 126.35 | 117.15 | MVS
85 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | TSM/006687 | SM/07828 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 3257 | 261 | Yes | 261 | 14/01/2025 | 22/08/2022 | 13 | 169.48 | 179.81 | MVS
86 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | TSM/006680 | SM/07829 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 4100 | 239.55 | Yes | 239.55 | 16/02/2024 | 13/04/2023 | 20 | 118.22 | 107.6 | MVS
87 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | TSM/006673 | SM/07830 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 1922 | 121.39 | Yes | 121.39 | 24/09/2024 | 03/08/2022 | 14 | 35.26 | 31.31 | MVS
88 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | TSM/006616 | SM/07855 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 3912 | 184.84 | Yes | 184.84 | 24/09/2024 | 12/05/2022 | 18 | 205.76 | 264.92 | MVS
89 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | TSM/006608 | SM/07856 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 04/12/2020 | 2730 | 129.06 | Yes | 129.06 | 12/09/2024 | 20/04/2022 | 17 | 121.66 | 96.7 | MVS
90 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | TSM/006600 | SM/07857 | Retrofitting |  |  |  | 04/12/2020 | 2342 | 110.71 | Yes | 110.71 | 05/08/2024 | 20/05/2022 | 13 | 159.32 | 153.01 | MVS
91 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | TSM/006610 | SM/07858 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. |  | 04/12/2020 | 4349 | 205.59 | Yes | 205.59 | 31/01/2025 | 06/04/2022 | 25 | 196.22 | 218.04 | MVS
92 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | TSM/006606 | SM/07859 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 04/12/2020 | 2550 | 134.62 | Yes | 134.62 | 25/08/2022 | 11/12/2023 | 8 | 141.13 | 128.92 | MVS
93 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | TSM/006641 | SM/07860 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 1853 | 115.29 | Yes | 115.29 | 12/03/2024 | 10/06/2024 | 6 | 8.95 | 14.63 | MVS
94 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | TSM/006629 | SM/07861 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 04/12/2020 | 3926 | 253.82 | Yes | 253.82 | 23/02/2024 | 07/06/2024 | 15 | 177.65 | 303.67 | MVS
95 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | TSM/006623 | SM/07862 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 04/12/2020 | 2107 | 136.5 | Yes | 136.5 | 17/04/2025 | 19/04/2022 | 22 | 101.71 | 134.17 | MVS
96 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | TSM/006643 | SM/07863 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 3454 | 125.64 | Yes | 125.64 | 24/04/2025 | 06/06/2024 | 10 | 124.07 | 94.12 | MVS
97 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | TSM/006652 | SM/07864 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 2535 | 148.07 | Yes | 148.07 | 05/05/2025 | 25/07/2023 | 15 | 143.38 | 148.61 | MVS
98 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | TSM/006651 | SM/07865 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 1651 | 106.28 | Yes | 106.28 | 14/05/2025 | 04/08/2022 | 14 | 69.33 | 48.72 | MVS
99 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | TSM/006659 | SM/07866 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 4796 | 283.41 | Yes | 283.41 | 14/01/2025 | 11/10/2023 | 17 | 283.4 | 353.72 | MVS
100 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | TSM/006668 | SM/07867 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 2784 | 168.95 | Yes | 168.95 | 21/01/2025 | 02/07/2021 | 22 | 151.09 | 144.94 | MVS
101 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | TSM/006689 | SM/07868 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 3050 | 249.54 | Yes | 249.54 | 03/04/2025 | 02/06/2021 | 15 | 59.52 | 84.5 | MVS
102 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | TSM/006683 | SM/07869 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 1976 | 109.48 | Yes | 109.48 | 23/10/2024 | 06/06/2024 | 7 | 95.03 | 31.2 | MVS
103 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block | TSM/006682 | SM/07870 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 2688 | 157.93 | Yes | 157.93 | 22/07/2024 | 05/04/2023 | 3 | 113.9 | 43.43 | MVS
104 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | TSM/006700 | SM/07871 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 3125 | 255.84 | Yes | 255.84 | 02/06/2025 | 05/10/2023 | 16 | 233.6 | 60.19 | MVS
105 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAMKRISHNAPUR Piped Water Supply Scheme at Raina-I Block | TSM/006614 | SM/07873 | Retrofitting |  |  |  | 04/12/2020 | 1096 | 47.08 | Yes | 47.08 |  | 16/08/2021 | 3 | 73.47 | 35.45 | MVS
106 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | TSM/006592 | SM/08030 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 35132 | 1902.4 | Yes | 1902.4 | 27/06/2024 | 02/06/2021 | 21 | 1872.4 | 2183.26 | MVS
107 | PURBA BARDHAMAN | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme | TSM/006628 | SM/08031 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 04/12/2020 | 5077 | 301.39 | Yes | 301.39 | 12/03/2024 | 25/08/2022 | 9 | 301.39 | 430.7 | MVS
108 | PURBA BARDHAMAN | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | TSM/006696 | SM/08033 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 6580 | 1100.67 | Yes | 1100.67 | 02/06/2025 | 09/01/2023 | 37 | 481.66 | 499.63 | MVS
109 | PURBA BARDHAMAN | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | TSM/006698 | SM/08034 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 8364 | 1126.08 | Yes | 1126.08 | 22/07/2024 | 31/12/2024 | 41 | 1003.81 | 494.75 | MVS
110 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | TSM/006604 | SM/08101 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 04/12/2020 | 7097 | 402.29 | Yes | 402.29 | 26/07/2024 | 01/07/2024 | 6 | 286.62 | 279.16 | MVS
111 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | TSM/006645 | SM/08102 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 04/12/2020 | 8834 | 489.24 | Yes | 489.24 | 12/03/2024 | 22/04/2022 | 10 | 244.15 | 187.96 | MVS
112 | PURBA BARDHAMAN | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | TSM/006655 | SM/08103 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 5112 | 331.6 | Yes | 331.6 | 23/02/2024 | 25/09/2024 | 8 | 333.39 | 305.33 | MVS
113 | PURBA BARDHAMAN | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | TSM/006656 | SM/08104 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 04/12/2020 | 5704 | 365.23 | Yes | 365.23 | 03/04/2025 | 06/06/2023 | 15 | 363.49 | 238.56 | MVS
114 | PURBA BARDHAMAN | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | TSM/006669 | SM/08105 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 04/12/2020 | 5098 | 311.16 | Yes | 311.16 | 08/05/2025 | 30/06/2022 | 17 | 244.41 | 213.32 | MVS
115 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | TSM/007673 | SM/08699 | Retrofitting |  |  |  | 19/02/2021 | 3292 | 198.59 | Yes | 198.59 | 12/03/2024 | 26/04/2022 | 9 | 143.79 | 102.1 | MVS
116 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007669 | SM/08700 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 19/02/2021 | 858 | 63.32 | Yes | 63.32 | 20/07/2023 | 19/04/2023 | 6 | 49.09 | 49.02 | MVS
117 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007681 | SM/08701 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 19/02/2021 | 5237 | 505.33 | Yes | 505.33 | 17/04/2025 | 01/07/2024 | 14 | 422.47 | 123.01 | MVS
118 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007670 | SM/08702 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 759 | 60.29 | Yes | 60.29 | 07/06/2023 | 03/06/2021 | 8 | 60.36 | 59.24 | MVS
119 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007680 | SM/08703 | Retrofitting | Burdwan Division | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | 19/02/2021 | 3098 | 196.29 | Yes | 196.29 | 14/01/2025 | 20/04/2022 | 32 | 123.22 | 80.8 | MVS
120 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | TSM/007676 | SM/08704 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 19/02/2021 | 4909 | 267.25 | Yes | 267.25 | 24/04/2025 | 25/09/2024 | 14 | 123.62 | 135.32 | MVS
121 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007675 | SM/08705 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/02/2021 | 2137 | 119.29 | Yes | 119.29 | 16/02/2024 | 27/11/2024 | 5 | 126 | 57.73 | MVS
122 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | TSM/007677 | SM/08706 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 1552 | 99.81 | Yes | 99.81 | 24/04/2025 | 11/01/2022 | 3 | 29.58 | 43.14 | MVS
123 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007671 | SM/08707 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 19/02/2021 | 3140 | 181.66 | Yes | 181.66 | 07/01/2025 | 25/10/2024 | 13 | 79.63 | 67.19 | MVS
124 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007678 | SM/08708 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 1804 | 112.85 | Yes | 112.85 | 26/07/2024 | 02/05/2022 | 6 | 86.46 | 86.21 | MVS
125 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | TSM/007684 | SM/08709 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 5528 | 327.79 | Yes | 327.79 | 03/01/2025 | 22/04/2022 | 22 | 330.84 | 327.61 | MVS
126 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | TSM/007685 | SM/08710 | Retrofitting | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/02/2021 | 4223 | 268.29 | Yes | 268.29 | 16/02/2024 | 29/08/2024 | 23 | 240.07 | 192.97 | MVS
127 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | TSM/007683 | SM/08711 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 3285 | 211.86 | Yes | 211.86 | 30/07/2024 | 02/06/2021 | 11 | 208.51 | 341.49 | MVS
128 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio | TSM/007672 | SM/08712 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 19/02/2021 | 2643 | 147.7 | Yes | 147.7 | 26/09/2022 | 02/12/2020 | 5 | 138.73 | 120.17 | MVS
129 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | TSM/007679 | SM/08713 | Retrofitting |  |  |  | 19/02/2021 | 806 | 52.2 | Yes | 52.2 | 13/03/2025 | 26/09/2024 | 5 | 19.81 | 19.81 | MVS
130 | PURBA BARDHAMAN | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | TSM/007682 | SM/08714 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 19/02/2021 | 2879 | 177.72 | Yes | 177.72 | 14/05/2025 | 19/04/2022 | 11 | 117.61 | 131 | MVS
131 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007674 | SM/08715 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 19/02/2021 | 2156 | 143.24 | Yes | 143.24 | 13/07/2023 | 28/04/2022 | 7 | 100.66 | 76.7 | MVS
132 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007668 | SM/08716 | Retrofitting |  |  |  | 19/02/2021 | 1113 | 80.58 | Yes | 80.58 | 11/03/2025 | 22/04/2025 | 4 | 75.63 | 68.88 | MVS
133 | PURBA BARDHAMAN | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007667 | SM/08717 | Retrofitting |  |  |  | 19/02/2021 | 671 | 46.27 | Yes | 46.27 | 13/01/2023 | 13/04/2023 | 6 | 12.9 | 40.97 | MVS
134 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | TSM/008574 | SM/08998 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 15/09/2021 | 2744 | 497.47 | Yes | 497.47 | 24/04/2025 | 31/01/2022 | 9 | 532.48 | 477.05 | MVS
135 | PURBA BARDHAMAN | Rejuvenation of Bhalki Water Supply Scheme. | TSM/007380 | SM/09103 | Augmentation | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 10/02/2021 | 1000 | 293.35 | Yes | 293.35 | 27/05/2022 | 07/04/2022 | 4 | 349.41 | 280.08 | MVS
136 | PURBA BARDHAMAN | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | TSM/008315 | SM/09104 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 19/08/2021 | 4335 | 245.18 | Yes | 245.18 | 09/12/2022 | 25/06/2021 | 20 | 178.77 | 73.68 | MVS
137 | PURBA BARDHAMAN | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008580 | SM/09403 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 657 | 651.77 | Yes | 651.77 | 13/09/2024 | 30/10/2024 | 12 | 653.33 | 467.68 | MVS
138 | PURBA BARDHAMAN | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008529 | SM/09404 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 29/09/2021 | 4677 | 851.6 | Yes | 851.6 | 13/10/2023 | 23/07/2024 | 12 | 927.68 | 791.14 | MVS
139 | PURBA BARDHAMAN | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008579 | SM/09405 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 29/09/2021 | 1240 | 262.41 | Yes | 262.41 | 06/12/2024 | 31/01/2022 | 7 | 310.92 | 262.41 | MVS
140 | PURBA BARDHAMAN | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008534 | SM/09406 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 29/09/2021 | 2045 | 316.97 | Yes | 316.97 | 04/08/2022 | 02/05/2022 | 6 | 381.91 | 307.73 | MVS
141 | PURBA BARDHAMAN | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008445 | SM/09407 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 1813 | 159.5 | Yes | 159.5 | 16/02/2024 | 30/10/2024 | 16 | 159.96 | 152.09 | MVS
142 | PURBA BARDHAMAN | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | TSM/008525 | SM/09408 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 29/09/2021 | 2829 | 495.29 | Yes | 495.29 | 10/12/2024 | 31/01/2022 | 8 | 544.49 | 495.15 | MVS
143 | PURBA BARDHAMAN | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | TSM/008524 | SM/09409 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 3783 | 532.8 | Yes | 532.8 | 13/07/2023 | 20/12/2023 | 11 | 580.07 | 451.13 | MVS
144 | PURBA BARDHAMAN | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | TSM/008451 | SM/09410 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 3077 | 697.69 | Yes | 697.69 | 24/09/2024 | 11/04/2022 | 10 | 508.41 | 415.1 | MVS
145 | PURBA BARDHAMAN | Augmentation of Ganganandapur PWSS for providing FHTC. | TSM/008073 | SM/09411 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 2940 | 808.85 | Yes | 808.85 | 29/01/2025 | 21/08/2023 | 21 | 805.86 | 626.42 | MVS
146 | PURBA BARDHAMAN | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008535 | SM/09412 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 29/09/2021 | 4088 | 537.66 | Yes | 537.66 | 16/02/2024 | 18/04/2022 | 7 | 579.43 | 405.18 | MVS
147 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008533 | SM/09413 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 29/09/2021 | 2817 | 564.13 | Yes | 564.13 | 04/08/2022 | 25/04/2022 | 9 | 593.25 | 536.68 | MVS
148 | PURBA BARDHAMAN | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | TSM/008532 | SM/09414 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 2613 | 487.81 | Yes | 487.81 | 29/01/2025 | 20/12/2023 | 8 | 110.24 | 387.42 | MVS
149 | PURBA BARDHAMAN | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | TSM/008531 | SM/09415 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 1667 | 443 | Yes | 443 | 24/08/2023 | 23/07/2024 | 13 | 444.83 | 314.14 | MVS
150 | PURBA BARDHAMAN | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | TSM/008530 | SM/09416 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 29/09/2021 | 1935 | 563.41 | Yes | 563.41 | 22/02/2024 | 26/07/2024 | 13 | 552.72 | 443.98 | MVS
151 | PURBA BARDHAMAN | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008830 | SM/09488 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 08/10/2021 | 1789 | 344.93 | Yes | 344.93 | 14/05/2025 | 11/04/2022 | 7 | 370.12 | 248.72 | MVS
152 | PURBA BARDHAMAN | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008828 | SM/09489 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 08/10/2021 | 4192 | 599.17 | Yes | 599.17 | 12/09/2024 | 12/04/2022 | 13 | 640.38 | 586.52 | MVS
153 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008753 | SM/09492 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 08/10/2021 | 3020 | 586.55 | Yes | 586.55 | 01/03/2024 | 10/08/2022 | 8 | 609.05 | 575.81 | MVS
154 | PURBA BARDHAMAN | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008751 | SM/09493 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 08/10/2021 | 2087 | 371.84 | Yes | 371.84 | 12/02/2024 | 20/02/2024 | 12 | 445.4 | 353.99 | MVS
155 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008742 | SM/09494 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 08/10/2021 | 2007 | 354.12 | Yes | 354.12 | 02/01/2025 | 19/04/2022 | 9 | 354.11 | 313.45 | MVS
156 | PURBA BARDHAMAN | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008577 | SM/09495 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 08/10/2021 | 121 | 531.47 | Yes | 531.47 | 23/12/2022 | 10/08/2022 | 15 | 562.57 | 523.78 | MVS
157 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008526 | SM/09566 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 08/10/2021 | 3670 | 623.11 | Yes | 623.11 | 01/12/2022 | 05/04/2022 | 7 | 697.17 | 542.19 | MVS
158 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008750 | SM/09568 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 08/10/2021 | 2804 | 455.89 | Yes | 455.89 | 06/08/2024 | 13/04/2022 | 10 | 535.6 | 437.08 | MVS
159 | PURBA BARDHAMAN | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008747 | SM/09569 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 08/10/2021 | 3020 | 527.28 | Yes | 527.28 | 04/08/2022 | 10/12/2021 | 10 | 144.64 | 409.61 | MVS
160 | PURBA BARDHAMAN | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008332 | SM/09699 | Augmentation | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/08/2021 | 1185 | 323.86 | Yes | 323.86 | 23/08/2023 | 30/12/2022 | 22 | 358.42 | 305.34 | MVS
161 | PURBA BARDHAMAN | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | TSM/008425 | SM/09700 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 19/08/2021 | 2498 | 625.09 | Yes | 625.09 | 02/01/2025 | 27/02/2023 | 21 | 623.01 | 553.59 | MVS
162 | PURBA BARDHAMAN | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008333 | SM/09712 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/08/2021 | 4237 | 732.87 | Yes | 732.87 | 01/08/2024 | 25/03/2025 | 22 | 708.62 | 298.46 | MVS
163 | PURBA BARDHAMAN | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008334 | SM/09713 | Augmentation | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/08/2021 | 2306 | 594.6 | Yes | 594.6 | 16/02/2024 | 06/06/2024 | 14 | 582.37 | 505.16 | MVS
164 | PURBA BARDHAMAN | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008335 | SM/09714 | Augmentation | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 19/08/2021 | 2485 | 754.02 | Yes | 754.02 | 27/12/2023 | 13/05/2022 | 14 | 711.55 | 454.25 | MVS
165 | PURBA BARDHAMAN | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008426 | SM/09715 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 19/08/2021 | 1708 | 523.43 | Yes | 523.43 | 21/06/2024 | 18/07/2024 | 17 | 686.96 | 378.62 | MVS
166 | PURBA BARDHAMAN | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | TSM/008170 | SM/09716 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 19/08/2021 | 2772 | 652.1 | Yes | 652.1 | 22/02/2024 | 29/02/2024 | 18 | 600.63 | 163.06 | MVS
167 | PURBA BARDHAMAN | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | TSM/008336 | SM/09717 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 19/08/2021 | 1762 | 530.67 | Yes | 530.67 | 06/03/2025 | 27/08/2024 | 17 | 489.21 | 349.74 | MVS
168 | PURBA BARDHAMAN | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | TSM/008172 | SM/09718 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 19/08/2021 | 3845 | 802.22 | Yes | 802.22 | 16/02/2024 | 21/09/2023 | 17 | 763.38 | 652.13 | MVS
169 | PURBA BARDHAMAN | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | TSM/008337 | SM/09719 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 19/08/2021 | 2213 | 677.83 | Yes | 677.83 | 22/02/2024 | 13/06/2024 | 10 | 677.33 | 487.11 | MVS
170 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009224 | SM/09873 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 22/11/2021 | 3189 | 651.8 | Yes | 651.8 | 16/02/2024 | 10/08/2023 | 10 | 648.59 | 257.23 | MVS
171 | PURBA BARDHAMAN | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | TSM/008453 | SM/09921 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 29/09/2021 | 6396 | 1144.6 | Yes | 1144.6 | 25/07/2024 | 10/05/2022 | 19 | 1141.09 | 860.71 | MVS
172 | PURBA BARDHAMAN | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | TSM/008767 | SM/10032 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 08/10/2021 | 5865 | 1069.93 | Yes | 1069.93 | 31/01/2024 | 31/05/2023 | 21 | 958.37 | 797.94 | MVS
173 | PURBA BARDHAMAN | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | TSM/009277 | SM/10055 | Retrofitting | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 16/12/2021 | 1771 | 114.87 | Yes | 114.87 | 16/02/2024 | 06/06/2024 | 4 | 113.83 | 49.18 | MVS
174 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009463 | SM/10056 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/12/2021 | 2676 | 726.35 | Yes | 726.35 | 28/02/2024 | 29/12/2023 | 11 | 775.7 | 690.09 | MVS
175 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009461 | SM/10057 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/12/2021 | 3593 | 972.04 | Yes | 972.04 | 23/05/2025 | 12/06/2024 | 17 | 253.62 | 611.12 | MVS
176 | PURBA BARDHAMAN | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009137 | SM/10058 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 16/12/2021 | 1599 | 987.71 | Yes | 987.71 | 24/08/2023 | 17/11/2022 | 8 | 912.9 | 892.73 | MVS
177 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009464 | SM/10059 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/12/2021 | 559 | 79.18 | Yes | 79.18 | 12/02/2024 | 04/04/2022 | 7 | 117.42 | 61.07 | MVS
178 | PURBA BARDHAMAN | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009468 | SM/10060 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/12/2021 | 3207 | 489.63 | Yes | 489.63 | 10/07/2024 | 31/05/2023 | 8 | 469.48 | 435.31 | MVS
179 | PURBA BARDHAMAN | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009467 | SM/10061 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/12/2021 | 4019 | 693.56 | Yes | 693.56 | 23/12/2024 | 20/12/2023 | 6 | 145.95 | 467.66 | MVS
180 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008802 | SM/10085 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 22/11/2021 | 15363 | 3231.45 | Yes | 3231.45 | 04/04/2025 | 14/08/2024 | 23 | 2661.83 | 2022 | MVS
181 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008752 | SM/10123 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 08/10/2021 | 4801 | 1083.3 | Yes | 1083.3 | 04/04/2025 | 13/06/2023 | 10 | 464.35 | 558.19 | MVS
182 | PURBA BARDHAMAN | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008749 | SM/10130 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 22/11/2021 | 5728 | 1023.72 | Yes | 1023.72 | 23/05/2025 | 28/06/2023 | 13 | 932.7 | 916.73 | MVS
183 | PURBA BARDHAMAN | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009133 | SM/10270 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 16/12/2021 | 6540 | 1096.06 | Yes | 1096.06 | 23/10/2024 | 04/05/2023 | 18 | 940.63 | 781.43 | MVS
184 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009140 | SM/10337 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 16/12/2021 | 9066 | 1360.01 | Yes | 1360.01 | 22/10/2024 | 08/06/2023 | 18 | 1320.53 | 1083.35 | MVS
185 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | TSM/010056 | SM/10391 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 27/01/2022 | 4079 | 942.3 | Yes | 942.3 | 08/05/2025 | 18/05/2023 | 12 | 995.13 | 766.46 | MVS
186 | PURBA BARDHAMAN | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | TSM/009953 | SM/10481 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 17/02/2022 | 1951 | 749.99 | Yes | 749.99 | 23/05/2025 | 14/07/2022 | 15 | 490.3 | 394.5 | MVS
187 | PURBA BARDHAMAN | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | TSM/010910 | SM/11491 | New | Central Mechanical Sub-Division | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | 25/04/2022 | 1442 | 457.23 | Yes | 457.23 | 30/03/2023 | 23/12/2022 | 14 | 64.92 | 332.44 | MVS
188 | PURBA BARDHAMAN | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | TSM/010918 | SM/11492 | New | Central Mechanical Sub-Division | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | 25/04/2022 | 2015 | 666.43 | Yes | 666.43 | 05/05/2025 | 27/03/2024 | 29 | 96.72 | 372.87 | MVS
189 | PURBA BARDHAMAN | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | TSM/013345 | SM/12080 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 15/07/2022 | 414 | 26.74 | Yes | 26.74 | 27/01/2025 | 25/04/2022 | 7 | 26.57 | 17.18 | MVS
190 | PURBA BARDHAMAN | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | TSM/014286 | SM/12081 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 15/07/2022 | 1250 | 58.96 | Yes | 58.96 | 19/05/2023 | 03/11/2020 | 5 | 58.94 | 38.9 | MVS
191 | PURBA BARDHAMAN | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio | TSM/010125 | SM/12116 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 16/03/2022 | 900 | 73.22 | Yes | 73.22 |  | 18/04/2022 | 2 | 73.15 | 53.15 | MVS
192 | PURBA BARDHAMAN | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | TSM/010059 | SM/13043 | Retrofitting | Katwa Sub-Division | Assistant Engineer |  | 15/07/2022 | 1775 | 109.18 | Yes | 109.18 | 13/01/2023 | 13/04/2023 | 6 | 40.76 | 40.76 | MVS
193 | PURBA BARDHAMAN | Kusha Piped Water Supply Scheme | TSM/015303 | SM/13279 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 1059 | 548.58 | Yes | 548.58 | 23/05/2025 | 03/08/2023 | 11 | 360.86 | 340.22 | MVS
194 | PURBA BARDHAMAN | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | TSM/015238 | SM/13280 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 09/09/2022 | 1672 | 575.1 | Yes | 575.1 | 07/02/2025 | 12/06/2024 | 10 | 163.16 | 449.86 | MVS
195 | PURBA BARDHAMAN | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | TSM/015304 | SM/13281 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 1136 | 510.5 | Yes | 510.5 | 04/04/2025 | 18/07/2023 | 12 | 367.62 | 256.1 | MVS
196 | PURBA BARDHAMAN | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE | TSM/015240 | SM/13282 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 2248 | 837.17 | Yes | 837.17 | 30/04/2025 | 05/10/2023 | 7 | 793.53 | 281.71 | MVS
197 | PURBA BARDHAMAN | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | TSM/015241 | SM/13283 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 2296 | 922.78 | Yes | 922.78 | 30/04/2025 | 05/10/2023 | 8 | 803.17 | 331.32 | MVS
198 | PURBA BARDHAMAN | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE | TSM/015242 | SM/13291 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 2810 | 871.79 | Yes | 871.79 | 30/04/2025 | 05/11/2024 | 15 | 817.66 | 296.29 | MVS
199 | PURBA BARDHAMAN | HARIGRAM PIPED WATER SUPPLY SCHEME | TSM/015300 | SM/13292 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 1217 | 526.13 | Yes | 526.13 | 08/01/2025 | 08/02/2023 | 11 | 348.96 | 283.38 | MVS
200 | PURBA BARDHAMAN | BHOTA PIPED WATER SUPPLY SCHEME | TSM/015701 | SM/13293 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 799 | 378.17 | Yes | 378.17 | 01/03/2024 | 10/12/2024 | 10 | 315.53 | 158.33 | MVS
201 | PURBA BARDHAMAN | Baikunthapur Piped Water Supply Scheme | TSM/015296 | SM/13294 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 1926 | 881.8 | Yes | 881.8 | 03/10/2024 | 17/12/2024 | 11 | 609.96 | 256.84 | MVS
202 | PURBA BARDHAMAN | Gangua Piped Water Supply Scheme | TSM/015297 | SM/13295 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 1665 | 574.91 | Yes | 574.91 | 01/03/2024 | 28/07/2023 | 8 | 77.87 | 194.16 | MVS
203 | PURBA BARDHAMAN | Amra Piped Water Supply Scheme | TSM/015338 | SM/13296 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 896 | 405.32 | Yes | 405.32 | 01/03/2024 | 15/05/2023 | 9 | 298.11 | 136.8 | MVS
204 | PURBA BARDHAMAN | RUPSA PIPED WATER SUPPLY SCHEME | TSM/015756 | SM/13298 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 2439 | 947.38 | Yes | 947.38 | 30/04/2025 | 13/04/2023 | 11 | 615.93 | 276.84 | MVS
205 | PURBA BARDHAMAN | HARIPUR PIPED WATER SUPPLY SCHEME | TSM/015829 | SM/13315 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 09/09/2022 | 543 | 342.07 | Yes | 342.07 | 29/01/2025 | 13/06/2024 | 11 | 296.26 | 224.14 | MVS
206 | PURBA BARDHAMAN | MASGARIA PIPED WATER SUPPLY SCHEME | TSM/015830 | SM/13318 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 1233 | 553.22 | Yes | 553.22 | 03/10/2024 | 17/04/2023 | 14 | 407.69 | 251.33 | MVS
207 | PURBA BARDHAMAN | Samanti Piped Water Supply Scheme | TSM/015299 | SM/13319 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 2107 | 926 | Yes | 926 | 01/03/2024 | 14/05/2024 | 10 | 608.58 | 402.95 | MVS
208 | PURBA BARDHAMAN | BAGPUR PIPED WATER SUPPLY SCHEME | TSM/015834 | SM/13323 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 1390 | 572.79 | Yes | 572.79 | 01/03/2024 | 26/06/2024 | 9 | 566.3 | 39.41 | MVS
209 | PURBA BARDHAMAN | SONAIAIMA Purba Piped Water Supply Scheme | TSM/015270 | SM/13326 | New | Central Mechanical Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | 09/09/2022 | 1416 | 633.06 | Yes | 633.06 | 17/03/2025 | 22/01/2025 | 12 | 575.46 | 400.83 | MVS
210 | PURBA BARDHAMAN | MANGANPUR PIPED WATER SUPPLY SCHEME | TSM/015844 | SM/13327 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 1736 | 784.22 | Yes | 784.22 | 22/07/2024 | 27/06/2024 | 10 | 773.8 | 382.25 | MVS
211 | PURBA BARDHAMAN | CHHORA PIPED WATER SUPPLY SCHEME | TSM/015271 | SM/13328 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 3034 | 995.39 | Yes | 995.39 | 01/03/2024 | 29/05/2025 | 15 | 928.22 | 749.95 | MVS
212 | PURBA BARDHAMAN | UCHALAN PIPED WATER SUPPLY SCHEME | TSM/015321 | SM/13329 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 1924 | 733.45 | Yes | 733.45 | 04/04/2025 | 18/07/2023 | 11 | 475.24 | 275.53 | MVS
213 | PURBA BARDHAMAN | PICHKURI PIPED WATER SUPPLY SCHEME | TSM/015273 | SM/13330 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 1793 | 703.65 | Yes | 703.65 | 16/01/2025 | 19/03/2025 | 11 | 590.02 | 376.72 | MVS
214 | PURBA BARDHAMAN | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | TSM/015295 | SM/13331 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 2827 | 942.52 | Yes | 942.52 | 05/05/2025 | 22/10/2024 | 8 | 188.53 | 219.07 | MVS
215 | PURBA BARDHAMAN | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. | TSM/015291 | SM/13332 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 3201 | 996.22 | Yes | 996.22 | 04/04/2025 | 09/08/2023 | 8 | 1013.34 | 751.55 | MVS
216 | PURBA BARDHAMAN | Katnabil Piped Water Supply Scheme | TSM/015310 | SM/13338 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 1319 | 623.44 | Yes | 623.44 | 04/04/2025 | 19/07/2024 | 11 | 444.62 | 249.94 | MVS
217 | PURBA BARDHAMAN | GROUND WATER BASED KANDARSONA PWSS | TSM/015313 | SM/13339 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 1011 | 497.29 | Yes | 497.29 | 09/04/2025 | 02/07/2025 | 13 | 328.69 | 287.91 | MVS
218 | PURBA BARDHAMAN | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | TSM/015237 | SM/13340 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 1861 | 691.97 | Yes | 691.97 | 30/04/2025 | 30/07/2024 | 15 | 549.02 | 285.6 | MVS
219 | PURBA BARDHAMAN | Serpur Piped Water Supply Scheme | TSM/015315 | SM/13384 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 813 | 478.73 | Yes | 478.73 | 04/04/2025 | 18/07/2023 | 9 | 341.14 | 211.08 | MVS
220 | PURBA BARDHAMAN | KHANDARI PIPED WATER SUPPLY SCHEME | TSM/015263 | SM/13396 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 2173 | 977.81 | Yes | 977.81 | 17/03/2025 | 19/03/2025 | 10 | 965.79 | 783.51 | MVS
221 | PURBA BARDHAMAN | Karatia Piped Water Supply Scheme | TSM/015260 | SM/13397 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 2002 | 839.41 | Yes | 839.41 | 16/01/2025 | 19/03/2025 | 11 | 736.76 | 508.49 | MVS
222 | PURBA BARDHAMAN | DEBPUR PIPED WATER SUPPLY SCHEME | TSM/015262 | SM/13398 | New | Durgapur Sub-DIvision | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 1898 | 792.97 | Yes | 792.97 | 30/04/2025 | 13/04/2023 | 11 | 701.44 | 420.41 | MVS
223 | PURBA BARDHAMAN | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | TSM/015846 | SM/13413 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 09/09/2022 | 1316 | 653.36 | Yes | 653.36 | 05/11/2024 | 18/06/2024 | 11 | 189.8 | 429.24 | MVS
224 | PURBA BARDHAMAN | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | TSM/015795 | SM/13417 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 354 | 234.83 | Yes | 234.83 | 10/07/2024 | 12/04/2023 | 12 | 197.26 | 136.27 | MVS
225 | PURBA BARDHAMAN | KONRAPUR PIPED WATER SUPPLY SCHEME | TSM/015826 | SM/13419 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 1636 | 728.41 | Yes | 728.41 | 24/09/2024 | 17/04/2023 | 9 | 516.68 | 161.56 | MVS
226 | PURBA BARDHAMAN | BICHKHARA PIPED WATER SUPPLY SCHEME | TSM/015779 | SM/13422 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 382 | 287.39 | Yes | 287.39 | 04/04/2025 | 16/01/2023 | 10 | 205.97 | 173.59 | MVS
227 | PURBA BARDHAMAN | BARAPALASHAN PIPED WATER SUPPLY SCHEME | TSM/015767 | SM/13423 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 09/09/2022 | 1825 | 714.32 | Yes | 714.32 | 01/03/2024 | 19/05/2023 | 10 | 447.29 | 204.52 | MVS
228 | PURBA BARDHAMAN | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | TSM/015781 | SM/13424 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 2435 | 997.78 | Yes | 997.78 | 30/04/2025 | 30/04/2024 | 10 | 167.19 | 517.79 | MVS
229 | PURBA BARDHAMAN | SAHAPUR PIPED WATER SUPPLY SCHEME | TSM/015784 | SM/13425 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 1188 | 572.23 | Yes | 572.23 | 23/05/2025 | 27/06/2024 | 12 | 337.24 | 330.9 | MVS
230 | PURBA BARDHAMAN | BIJRA PIPED WATER SUPPLY SCHEME | TSM/015755 | SM/13426 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 1934 | 838.13 | Yes | 838.13 | 01/03/2024 | 30/11/2023 | 9 | 82.94 | 203.65 | MVS
231 | PURBA BARDHAMAN | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | TSM/015796 | SM/13450 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 800 | 450.26 | Yes | 450.26 | 30/04/2025 | 30/04/2024 | 12 | 354.65 | 199.65 | MVS
232 | PURBA BARDHAMAN | NOAHATI PIPED WATER SUPPLY SCHEME | TSM/015812 | SM/13452 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 1938 | 921.11 | Yes | 921.11 | 06/03/2024 | 03/04/2025 | 10 | 544.19 | 460.28 | MVS
233 | PURBA BARDHAMAN | KAMALPUR PIPED WATER SUPPLY SCHEME | TSM/015828 | SM/13453 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 695 | 335.66 | Yes | 335.66 | 30/04/2025 | 22/05/2023 | 6 | 302.06 | 115.3 | MVS
234 | PURBA BARDHAMAN | AMRA PIPED WATER SUPPLY SCHEME | TSM/015790 | SM/13454 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 1602 | 799.29 | Yes | 799.29 | 04/04/2025 | 13/04/2023 | 10 | 742.73 | 337.27 | MVS
235 | PURBA BARDHAMAN | TELUN PIPED WATER SUPPLY SCHEME | TSM/015787 | SM/13455 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 2128 | 908.7 | Yes | 908.7 | 30/04/2025 | 29/03/2023 | 10 | 613.65 | 124.1 | MVS
236 | PURBA BARDHAMAN | BALABATI PIPED WATER SUPPLY SCHEME | TSM/015789 | SM/13457 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 1364 | 678.2 | Yes | 678.2 | 30/04/2025 | 13/04/2023 | 9 | 502.83 | 331.53 | MVS
237 | PURBA BARDHAMAN | KUCHUT PIPED WATER SUPPLY SCHEME | TSM/015770 | SM/13464 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 2306 | 910.64 | Yes | 910.64 | 15/10/2025 | 03/04/2025 | 21 | 550.53 | 429.01 | MVS
238 | PURBA BARDHAMAN | KHUNDKURI PIPED WATER SUPPLY SCHEME | TSM/015772 | SM/13465 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 2692 | 992.74 | Yes | 992.74 | 09/04/2025 | 13/09/2023 | 12 | 625.49 | 506.87 | MVS
239 | PURBA BARDHAMAN | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | TSM/015699 | SM/13466 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 503 | 313.2 | Yes | 313.2 | 31/07/2024 | 26/09/2024 | 9 | 228.37 | 194.52 | MVS
240 | PURBA BARDHAMAN | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | TSM/015776 | SM/13491 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 2003 | 789.53 | Yes | 789.53 | 03/10/2024 | 31/05/2024 | 19 | 129.49 | 439.87 | MVS
241 | PURBA BARDHAMAN | SHIBADA PIPED WATER SUPPLY SCHEME | TSM/015707 | SM/13492 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 1282 | 617.18 | Yes | 617.18 | 16/01/2025 | 19/03/2025 | 14 | 566.09 | 263.45 | MVS
242 | PURBA BARDHAMAN | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | TSM/015833 | SM/13493 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 09/09/2022 | 182 | 146.5 | Yes | 146.5 | 22/07/2024 | 07/06/2024 | 11 | 138.92 | 76.25 | MVS
243 | PURBA BARDHAMAN | SATINANDI PIPED WATER SUPPLY SCHEME | TSM/015705 | SM/13494 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 1630 | 642.77 | Yes | 642.77 | 01/03/2024 | 26/11/2024 | 11 | 536.23 | 459.65 | MVS
244 | PURBA BARDHAMAN | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | TSM/015302 | SM/13495 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 320 | 213.85 | Yes | 213.85 | 24/04/2025 | 10/05/2023 | 9 | 129.43 | 87.9 | MVS
245 | PURBA BARDHAMAN | SIGHNALI PIPED WATER SUPPLY SCHEME. | TSM/015852 | SM/13496 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 2101 | 771.8 | Yes | 771.8 | 30/04/2025 | 09/08/2023 | 7 | 686.7 | 418.43 | MVS
246 | PURBA BARDHAMAN | KACHUA PIPED WATER SUPPLY SCHEME | TSM/015840 | SM/13497 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 09/09/2022 | 1137 | 520.29 | Yes | 520.29 | 18/11/2024 | 22/05/2023 | 10 | 508.48 | 309.6 | MVS
247 | PURBA BARDHAMAN | KARAIL PIPED WATER SUPPLY SCHEME | TSM/015838 | SM/13498 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 298 | 194.91 | Yes | 194.91 | 01/03/2024 | 01/11/2023 | 6 | 114.97 | 34.88 | MVS
248 | PURBA BARDHAMAN | BAHADURPUR PIPED WATER SUPPLY SCHEME | TSM/015696 | SM/13504 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 936 | 420.97 | Yes | 420.97 | 01/03/2024 | 02/01/2025 | 9 | 303.24 | 264.41 | MVS
249 | PURBA BARDHAMAN | UKHRID PIPED WATER SUPPLY SCHEME | TSM/015780 | SM/13505 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 2045 | 834.72 | Yes | 834.72 | 30/04/2025 | 13/04/2023 | 8 | 533.57 | 347 | MVS
250 | PURBA BARDHAMAN | DEHA PIPED WATER SUPPLY SCHEME | TSM/015761 | SM/13506 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 09/09/2022 | 1516 | 753.28 | Yes | 753.28 | 12/09/2024 | 30/08/2024 | 10 | 129.65 | 252.56 | MVS
251 | PURBA BARDHAMAN | KHURUL PIPED WATER SUPPLY SCHEME | TSM/015279 | SM/13549 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 09/09/2022 | 738 | 357.08 | Yes | 357.08 | 01/03/2024 | 13/12/2023 | 8 | 258.32 | 156.08 | MVS
252 | PURBA BARDHAMAN | SILUT PIPED WATER SUPPLY SCHEME | TSM/016560 | SM/13903 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2432 | 894.4 | Yes | 894.4 | 01/03/2024 | 02/08/2023 | 8 | 630.35 | 445.89 | MVS
253 | PURBA BARDHAMAN | BALSIDANGA PIPED WATER SUPPLY SCHEME | TSM/016551 | SM/13904 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 319 | 245.44 | Yes | 245.44 | 08/05/2025 | 24/07/2025 | 12 | 192.47 | 124.07 | MVS
254 | PURBA BARDHAMAN | GOPALBERA PIPED WATER SUPPLY SCHEME | TSM/016299 | SM/13905 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 26/09/2022 | 2144 | 986.75 | Yes | 986.75 | 05/05/2025 | 04/05/2023 | 9 | 745.32 | 495.17 | MVS
255 | PURBA BARDHAMAN | BARASAT PIPED WATER SUPPLY SCHEME | TSM/016234 | SM/13906 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2198 | 813.48 | Yes | 813.48 | 01/03/2024 | 08/08/2023 | 8 | 540.95 | 240.64 | MVS
256 | PURBA BARDHAMAN | CHOTKHANDA PIPED WATER SUPPLY SCHEME | TSM/016228 | SM/13907 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 26/09/2022 | 2846 | 995.08 | Yes | 995.08 | 12/09/2024 | 19/05/2023 | 10 | 620.84 | 418.75 | MVS
257 | PURBA BARDHAMAN | DIGHA PIPED WATER SUPPLY SCHEME | TSM/016527 | SM/13938 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1556 | 809.82 | Yes | 809.82 | 01/03/2024 | 21/11/2024 | 10 | 762.23 | 487.5 | MVS
258 | PURBA BARDHAMAN | KALYANPUR PIPED WATER SUPPLY SCHEME | TSM/016514 | SM/13939 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | 26/09/2022 | 2206 | 820.46 | Yes | 820.46 | 01/08/2024 | 16/10/2023 | 10 | 580.73 | 99.04 | MVS
259 | PURBA BARDHAMAN | KALIGRAM PIPED WATER SUPPLY SCHEME | TSM/016309 | SM/13940 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 1810 | 777.44 | Yes | 777.44 | 01/03/2024 | 10/08/2023 | 8 | 491.98 | 153.71 | MVS
260 | PURBA BARDHAMAN | CHAGRAM PIPED WATER SUPPLY SCHEME | TSM/016296 | SM/13941 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 26/09/2022 | 1984 | 846.16 | Yes | 846.16 | 30/04/2025 | 04/05/2023 | 9 | 596.96 | 414.36 | MVS
261 | PURBA BARDHAMAN | KAMALPUR PIPED WATER SUPPLY SCHEME | TSM/016214 | SM/13942 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 26/09/2022 | 2652 | 869.97 | Yes | 869.97 | 04/04/2025 | 04/05/2023 | 11 | 605.85 | 450.02 | MVS
262 | PURBA BARDHAMAN | KURMUN PIPED WATER SUPPLY SCHEME | TSM/016294 | SM/13943 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2937 | 978.48 | Yes | 978.48 | 24/09/2024 | 14/09/2023 | 11 | 728.27 | 180.85 | MVS
263 | PURBA BARDHAMAN | BAKALSA PIPED WATER SUPPLY SCHEME | TSM/016209 | SM/13944 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2409 | 916.69 | Yes | 916.69 | 01/03/2024 | 25/08/2023 | 10 | 607.24 | 200.89 | MVS
264 | PURBA BARDHAMAN | JAGADABAD PIPED WATER SUPPLY SCHEME | TSM/016230 | SM/13945 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2060 | 872.95 | Yes | 872.95 | 01/03/2024 | 08/08/2023 | 9 | 594.43 | 257.05 | MVS
265 | PURBA BARDHAMAN | KHAIDYA PIPED WATER SUPPLY SCHEME | TSM/016223 | SM/13946 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2342 | 976.89 | Yes | 976.89 | 01/03/2024 | 08/08/2023 | 8 | 643.39 | 204.22 | MVS
266 | PURBA BARDHAMAN | GHOSHPUR PIPED WATER SUPPLY SCHEME | TSM/016250 | SM/13947 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 26/09/2022 | 1952 | 851.51 | Yes | 851.51 | 17/03/2025 | 19/05/2023 | 9 | 532.25 | 189.05 | MVS
267 | PURBA BARDHAMAN | BHUYERA PIPED WATER SUPPLY SCHEME | TSM/016618 | SM/13948 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1330 | 678.07 | Yes | 678.07 | 01/03/2024 | 19/03/2025 | 7 | 127.14 | 317.18 | MVS
268 | PURBA BARDHAMAN | JADABGANJ PIPED WATER SUPPLY SCHEME | TSM/016543 | SM/13966 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1821 | 849.7 | Yes | 849.7 | 06/12/2024 | 02/08/2024 | 13 | 733.59 | 247.08 | MVS
269 | PURBA BARDHAMAN | AMARPUR PIPED WATER SUPPLY SCHEME | TSM/016575 | SM/13967 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1194 | 613.42 | Yes | 613.42 | 01/03/2024 | 06/09/2024 | 8 | 532.51 | 236.29 | MVS
270 | PURBA BARDHAMAN | EORA PIPED WATER SUPPLY SCHEME | TSM/016534 | SM/13968 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 287 | 247.48 | Yes | 247.48 | 14/03/2024 | 24/04/2023 | 9 | 163.58 | 109.96 | MVS
271 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | TSM/011595 | SM/14014 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 20/05/2022 | 13054 | 848.66 | Yes | 848.66 | 24/09/2024 | 05/08/2024 | 9 | 833.24 | 461.29 | MVS
272 | PURBA BARDHAMAN | CHHATINI PIPED WATER SUPPLY SCHEME | TSM/016557 | SM/14017 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 26/09/2022 | 2137 | 959.51 | Yes | 959.51 | 04/04/2025 | 15/05/2023 | 11 | 818.77 | 236.57 | MVS
273 | PURBA BARDHAMAN | BELGRAM PIPED WATER SUPPLY SCHEME | TSM/016265 | SM/14018 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2093 | 931.79 | Yes | 931.79 | 01/03/2024 | 21/05/2024 | 8 | 814.97 | 676.6 | MVS
274 | PURBA BARDHAMAN | NANDIARA PIPED WATER SUPPLY SCHEME | TSM/016288 | SM/14019 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 26/09/2022 | 1609 | 768.33 | Yes | 768.33 | 01/03/2024 | 10/08/2023 | 10 | 533.36 | 224.91 | MVS
275 | PURBA BARDHAMAN | MOUDANGA PIPED WATER SUPPLY SCHEME | TSM/016612 | SM/14020 | New | Central Mechanical Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | 26/09/2022 | 1630 | 786.6 | Yes | 786.6 | 01/03/2024 | 25/07/2024 | 9 | 673.01 | 132.93 | MVS
276 | PURBA BARDHAMAN | RAJAPUR PIPED WATER SUPPLY SCHEME | TSM/016664 | SM/14021 | New | Central Mechanical Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | 26/09/2022 | 576 | 270.24 | Yes | 270.24 | 26/09/2024 | 30/01/2023 | 11 | 157.06 | 207.17 | MVS
277 | PURBA BARDHAMAN | MANDARDIHI PIPED WATER SUPPLY SCHEME | TSM/017176 | SM/14052 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 317 | 251.9 | Yes | 251.9 | 30/04/2025 | 02/03/2023 | 12 | 148.44 | 116.09 | MVS
278 | PURBA BARDHAMAN | KALIKAPUR PIPED WATER SUPPLY SCHEME | TSM/017372 | SM/14053 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2794 | 989.35 | Yes | 989.35 | 24/04/2025 | 19/07/2024 | 9 | 765.83 | 415.84 | MVS
279 | PURBA BARDHAMAN | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | TSM/017351 | SM/14054 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2763 | 991.42 | Yes | 991.42 | 04/04/2025 | 19/07/2024 | 11 | 659.45 | 543.93 | MVS
280 | PURBA BARDHAMAN | SRIBATI PIPED WATER SUPPLY SCHEME | TSM/017368 | SM/14055 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2799 | 998.02 | Yes | 998.02 | 04/04/2025 | 22/05/2023 | 10 | 749.99 | 594.35 | MVS
281 | PURBA BARDHAMAN | DHARALA PIPED WATER SUPPLY SCHEME | TSM/017149 | SM/14056 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 713 | 347.99 | Yes | 347.99 | 01/03/2024 | 26/11/2024 | 10 | 251.73 | 151.14 | MVS
282 | PURBA BARDHAMAN | AKHRA PIPED WATER SUPPLY SCHEME | TSM/017343 | SM/14057 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1984 | 804.45 | Yes | 804.45 | 18/03/2025 | 13/04/2023 | 12 | 612.04 | 479.43 | MVS
283 | PURBA BARDHAMAN | MULGRAM PIPED WATER SUPPLY SCHEME | TSM/017344 | SM/14058 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2199 | 824.61 | Yes | 824.61 | 04/04/2025 | 17/03/2023 | 8 | 79.45 | 534.35 | MVS
284 | PURBA BARDHAMAN | NABASTA PIPED WATER SUPPLY SCHEME | TSM/017158 | SM/14059 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 1515 | 843.93 | Yes | 843.93 | 30/04/2025 | 31/10/2023 | 9 | 652.93 | 228.83 | MVS
285 | PURBA BARDHAMAN | PHANRIJANGALPIPED WATER SUPPLY SCHEME | TSM/017152 | SM/14060 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 1177 | 551.85 | Yes | 551.85 | 01/03/2024 | 17/02/2025 | 8 | 472.51 | 329.94 | MVS
286 | PURBA BARDHAMAN | POALKURA PIPED WATER SUPPLY SCHEME | TSM/017154 | SM/14061 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 30/09/2022 | 780 | 384.32 | Yes | 384.32 | 30/04/2025 | 31/10/2023 | 10 | 343.37 | 128.34 | MVS
287 | PURBA BARDHAMAN | KOTALGHOSH PIPED WATER SUPPLY SCHEME | TSM/017147 | SM/14062 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1423 | 659.18 | Yes | 659.18 | 04/04/2025 | 10/08/2023 | 10 | 389.95 | 318.06 | MVS
288 | PURBA BARDHAMAN | NRISINHAPUR PIPED WATER SUPPLY SCHEME | TSM/016584 | SM/14071 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1303 | 667.05 | Yes | 667.05 | 17/03/2025 | 25/11/2024 | 8 | 149.8 | 379.08 | MVS
289 | PURBA BARDHAMAN | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | TSM/016545 | SM/14072 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1821 | 962.8 | Yes | 962.8 | 01/03/2024 | 03/10/2024 | 13 | 942.57 | 392.28 | MVS
290 | PURBA BARDHAMAN | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | TSM/016555 | SM/14073 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2189 | 853.72 | Yes | 853.72 | 01/03/2024 | 10/01/2025 | 8 | 565.41 | 192.17 | MVS
291 | PURBA BARDHAMAN | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | TSM/016266 | SM/14074 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2233 | 908.14 | Yes | 908.14 | 05/09/2024 | 10/05/2023 | 7 | 692.66 | 454.62 | MVS
292 | PURBA BARDHAMAN | KASHIARA PIPED WATER SUPPLY SCHEME | TSM/016221 | SM/14075 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2622 | 989.54 | Yes | 989.54 | 01/03/2024 | 09/08/2023 | 8 | 667.81 | 282.75 | MVS
293 | PURBA BARDHAMAN | PALITPUR PIPED WATER SUPPLY SCHEME | TSM/016289 | SM/14076 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 1222 | 565.9 | Yes | 565.9 | 01/03/2024 | 10/08/2023 | 8 | 370.15 | 33.79 | MVS
294 | PURBA BARDHAMAN | UTRA PIPED WATER SUPPLY SCHEME | TSM/015854 | SM/14077 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 2024 | 752 | Yes | 752 | 31/12/2024 | 12/04/2023 | 13 | 630.15 | 531.8 | MVS
295 | PURBA BARDHAMAN | SARANGA PIPED WATER SUPPLY SCHEME | TSM/016233 | SM/14078 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 1147 | 552.88 | Yes | 552.88 | 30/04/2025 | 04/05/2023 | 13 | 491.53 | 295.4 | MVS
296 | PURBA BARDHAMAN | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | TSM/017339 | SM/14079 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2461 | 951.8 | Yes | 951.8 | 04/04/2025 | 25/04/2025 | 11 | 699.34 | 533.28 | MVS
297 | PURBA BARDHAMAN | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | TSM/016225 | SM/14080 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 604 | 321.81 | Yes | 321.81 | 24/04/2025 | 24/04/2023 | 9 | 192.73 | 150.88 | MVS
298 | PURBA BARDHAMAN | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | TSM/011154 | SM/14132 | New | Burdwan Sadar Sub-Division | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | 30/03/2022 | 11115 | 5905.97 | Yes | 5905.97 | 14/05/2025 | 21/08/2025 | 5 | 4271.37 | 1253.86 | MVS
299 | PURBA BARDHAMAN | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | TSM/015285 | SM/14425 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 09/09/2022 | 2717 | 926.18 | Yes | 926.18 | 12/09/2024 | 05/04/2023 | 11 | 777.95 | 480.04 | MVS
300 | PURBA BARDHAMAN | DEARA PIPED WATER SUPPLY SCHEME | TSM/016793 | SM/14435 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 1692 | 695.72 | Yes | 695.72 | 08/07/2024 | 31/07/2024 | 18 | 516.11 | 371.54 | MVS
301 | PURBA BARDHAMAN | NIRALGACHHI PIPED WATER SUPPLY SCHEME | TSM/016790 | SM/14436 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 2227 | 835.48 | Yes | 835.48 | 18/11/2024 | 05/12/2024 | 7 | 105.96 | 141.57 | MVS
302 | PURBA BARDHAMAN | SHIKARPUR PIPED WATER SUPPLY SCHEME | TSM/016777 | SM/14437 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 2462 | 947.99 | Yes | 947.99 | 07/01/2025 | 31/07/2024 | 12 | 671.17 | 407.78 | MVS
303 | PURBA BARDHAMAN | SHUSHNA PIPED WATER SUPPLY SCHEME | TSM/016775 | SM/14438 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2000 | 824.06 | Yes | 824.06 | 30/04/2025 | 09/08/2023 | 12 | 662.08 | 375.91 | MVS
304 | PURBA BARDHAMAN | PATHARDANGA PIPED WATER SUPPLY SCHEME | TSM/016770 | SM/14440 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 2852 | 997.37 | Yes | 997.37 | 06/11/2024 | 31/07/2024 | 17 | 768.49 | 568.53 | MVS
305 | PURBA BARDHAMAN | TAIPARA Piped Water Supply Scheme. | TSM/016769 | SM/14442 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 2406 | 906.99 | Yes | 906.99 | 06/11/2024 | 31/07/2024 | 15 | 131.75 | 427.94 | MVS
306 | PURBA BARDHAMAN | NASIGRAM PIPED WATER SUPPLY SCHEME | TSM/017124 | SM/14443 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 30/09/2022 | 2924 | 993.43 | Yes | 993.43 | 07/03/2025 | 19/04/2023 | 13 | 953.34 | 633.31 | MVS
307 | PURBA BARDHAMAN | IBRAMBAD PIPED WATER SUPPLY SCHEME | TSM/016767 | SM/14444 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2085 | 801.33 | Yes | 801.33 | 04/04/2025 | 12/05/2023 | 8 | 111.97 | 358.93 | MVS
308 | PURBA BARDHAMAN | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | TSM/017120 | SM/14445 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1445 | 725.97 | Yes | 725.97 | 01/03/2024 | 09/08/2023 | 9 | 506.43 | 35.57 | MVS
309 | PURBA BARDHAMAN | GURPARA PIPED WATER SUPPLY SCHEME | TSM/017135 | SM/14447 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1680 | 773.39 | Yes | 773.39 | 04/04/2025 | 19/07/2024 | 8 | 149.58 | 303.41 | MVS
310 | PURBA BARDHAMAN | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | TSM/017139 | SM/14448 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2411 | 894.65 | Yes | 894.65 | 04/04/2025 | 26/04/2023 | 7 | 111.94 | 207.59 | MVS
311 | PURBA BARDHAMAN | TATARPUR PIPED WATER SUPPLY SCHEME | TSM/016791 | SM/14740 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 26/09/2022 | 1639 | 702.48 | Yes | 702.48 | 24/09/2024 | 06/06/2023 | 9 | 556.09 | 216.85 | MVS
312 | PURBA BARDHAMAN | BHEDIA PIPED WATER SUPPLY SCHEME | TSM/017145 | SM/14748 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 1543 | 699.32 | Yes | 699.32 | 01/03/2024 | 06/09/2024 | 9 | 676.65 | 251.01 | MVS
313 | PURBA BARDHAMAN | AUSGRAM PIPED WATER SUPPLY SCHEME | TSM/016287 | SM/14905 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2264 | 951.12 | Yes | 951.12 | 01/03/2024 | 08/08/2025 | 13 | 875.57 | 434.66 | MVS
314 | PURBA BARDHAMAN | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | TSM/016210 | SM/14906 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 673 | 309.75 | Yes | 309.75 | 09/04/2025 | 01/09/2025 | 11 | 193.78 | 109.36 | MVS
315 | PURBA BARDHAMAN | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | TSM/016257 | SM/14909 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1666 | 849.53 | Yes | 849.53 | 30/04/2025 | 24/08/2023 | 10 | 688.78 | 58.22 | MVS
316 | PURBA BARDHAMAN | GOHAGRAM PIPED WATER SUPPLY SCHEME | TSM/017131 | SM/14910 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1208 | 641.25 | Yes | 641.25 | 03/10/2024 | 17/02/2023 | 10 | 469.78 | 238.17 | MVS
317 | PURBA BARDHAMAN | NIGAN PIPE WATER SUPPLY SCHEME | TSM/017529 | SM/14912 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1886 | 722.46 | Yes | 722.46 | 04/04/2025 | 23/05/2023 | 8 | 482.41 | 71.35 | MVS
318 | PURBA BARDHAMAN | KUNDA PIPED WATER SUPPLY SCHEME | TSM/017498 | SM/14913 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 481 | 385.14 | Yes | 385.14 | 01/03/2024 | 16/05/2023 | 8 | 145.27 | 117.13 | MVS
319 | PURBA BARDHAMAN | SHRIGRAM PIPED WATER SUPPLY SCHEME | TSM/017500 | SM/14915 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1380 | 602.71 | Yes | 602.71 | 04/04/2025 | 23/05/2023 | 9 | 454.13 | 192.82 | MVS
320 | PURBA BARDHAMAN | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME | TSM/017150 | SM/14916 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1895 | 809.85 | Yes | 809.85 | 01/03/2024 | 09/08/2023 | 9 | 545.79 | 128.14 | MVS
321 | PURBA BARDHAMAN | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | TSM/016621 | SM/14917 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 392 | 232.57 | Yes | 232.57 | 22/07/2024 | 02/08/2024 | 8 | 231.73 | 103.23 | MVS
322 | PURBA BARDHAMAN | LAKHURIA PIPE WATER SUPPLY SCHEME | TSM/017538 | SM/14918 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1344 | 601.59 | Yes | 601.59 | 04/04/2025 | 16/04/2024 | 9 | 65.37 | 126.9 | MVS
323 | PURBA BARDHAMAN | BHANDARITURI PIPED WATER SUPPLY SCHEME | TSM/016595 | SM/14925 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 26/09/2022 | 457 | 190.41 | Yes | 190.41 | 02/01/2025 | 25/07/2024 | 9 | 184.19 | 94.44 | MVS
324 | PURBA BARDHAMAN | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | TSM/016537 | SM/14926 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 546 | 315.46 | Yes | 315.46 | 17/03/2025 | 26/11/2024 | 8 | 137.78 | 136.13 | MVS
325 | PURBA BARDHAMAN | ALIGRAM PIPED WATER SUPPLY SCHEME | TSM/016564 | SM/14927 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1088 | 503.42 | Yes | 503.42 | 01/03/2024 | 29/05/2025 | 18 | 289.82 | 250.55 | MVS
326 | PURBA BARDHAMAN | SAR PIPED WATER SUPPLY SCHEME | TSM/016522 | SM/14929 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 1131 | 395.09 | Yes | 395.09 | 31/07/2024 | 26/09/2024 | 11 | 326 | 260.7 | MVS
327 | PURBA BARDHAMAN | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | TSM/016302 | SM/14930 | New | RWS Burdwan Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 26/09/2022 | 2163 | 854.64 | Yes | 854.64 | 01/03/2024 | 13/11/2024 | 12 | 561.18 | 225.63 | MVS
328 | PURBA BARDHAMAN | MOSHRA PIPED WATER SUPPLY SCHEME | TSM/016307 | SM/14931 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 26/09/2022 | 1136 | 556.47 | Yes | 556.47 | 01/03/2024 | 30/04/2025 | 9 | 77.44 | 152.86 | MVS
329 | PURBA BARDHAMAN | KHEJURHATI PIPED WATER SUPPLY SCHEME | TSM/016813 | SM/14952 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 26/09/2022 | 687 | 408.16 | Yes | 408.16 | 04/04/2025 | 04/05/2023 | 9 | 371.92 | 257.28 | MVS
330 | PURBA BARDHAMAN | JALKANDAR PIPED WATER SUPPLY SCHEME | TSM/016585 | SM/14953 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2122 | 969.12 | Yes | 969.12 | 17/03/2025 | 19/03/2025 | 12 | 202.7 | 392.9 | MVS
331 | PURBA BARDHAMAN | KALAIJHUTI PIPED WATER SUPPLY SCHEME | TSM/016502 | SM/14954 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 491 | 294.41 | Yes | 294.41 | 01/03/2024 | 26/11/2024 | 7 | 199.22 | 155.99 | MVS
332 | PURBA BARDHAMAN | UDGARA PIPED WATER SUPPLY SCHEME | TSM/017636 | SM/14961 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 30/09/2022 | 1273 | 609.95 | Yes | 609.95 | 17/03/2025 | 30/04/2025 | 10 | 433.42 | 103.57 | MVS
333 | PURBA BARDHAMAN | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | TSM/017142 | SM/14962 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 30/09/2022 | 2126 | 939.99 | Yes | 939.99 | 30/04/2025 | 25/04/2023 | 8 | 115.59 | 550.35 | MVS
334 | PURBA BARDHAMAN | AMILIA PIPED WATER SUPPLY SCHEME | TSM/017634 | SM/14963 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 30/09/2022 | 894 | 415.83 | Yes | 415.83 | 09/12/2024 | 20/12/2024 | 11 | 348.07 | 281.95 | MVS
335 | PURBA BARDHAMAN | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | TSM/017127 | SM/14964 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2340 | 835.12 | Yes | 835.12 | 04/04/2025 | 12/05/2023 | 8 | 94.57 | 367.91 | MVS
336 | PURBA BARDHAMAN | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | TSM/017626 | SM/14965 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 30/09/2022 | 749 | 446.69 | Yes | 446.69 | 01/03/2024 | 10/05/2023 | 7 | 71.76 | 81.66 | MVS
337 | PURBA BARDHAMAN | CHARKHI PIPED WATER SUPPLY SCHEME | TSM/017458 | SM/14966 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1582 | 721.47 | Yes | 721.47 | 02/05/2025 | 18/04/2023 | 9 | 543.88 | 271.39 | MVS
338 | PURBA BARDHAMAN | MACHKHARA PIPED WATER SUPPLY SCHEME | TSM/017645 | SM/14967 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 30/09/2022 | 1886 | 878.93 | Yes | 878.93 | 17/03/2025 | 05/10/2023 | 8 | 588.34 | 306.73 | MVS
339 | PURBA BARDHAMAN | SAHAPUR PIPED WATER SUPPLY SCHEME | TSM/016623 | SM/14969 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 885 | 475.62 | Yes | 475.62 | 01/03/2024 | 23/08/2023 | 9 | 325.71 | 219.45 | MVS
340 | PURBA BARDHAMAN | MAHARUTBA PIPED WATER SUPPLY SCHEME | TSM/017501 | SM/14970 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1569 | 637.16 | Yes | 637.16 | 03/10/2024 | 02/08/2023 | 11 | 599.6 | 320.65 | MVS
341 | PURBA BARDHAMAN | SHIBLUN PIPE WATER SUPPLY SCHEME | TSM/017470 | SM/14972 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1394 | 663.56 | Yes | 663.56 | 02/05/2025 | 18/04/2023 | 10 | 537.64 | 302.2 | MVS
342 | PURBA BARDHAMAN | DEULIA PIPED WATER SUPPLY SCHEME | TSM/017118 | SM/14973 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1505 | 830.84 | Yes | 830.84 | 03/10/2024 | 09/08/2023 | 9 | 589.04 | 100.14 | MVS
343 | PURBA BARDHAMAN | SUATA PIPED WATER SUPPLY SCHEME | TSM/016604 | SM/14974 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 26/09/2022 | 2132 | 981.92 | Yes | 981.92 | 21/06/2024 | 06/06/2024 | 13 | 1036.79 | 576.97 | MVS
344 | PURBA BARDHAMAN | BHATPARA PIPE WATER SUPPLY SCHEME | TSM/017542 | SM/14975 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2183 | 820.95 | Yes | 820.95 | 04/04/2025 | 02/08/2023 | 9 | 548.89 | 415.54 | MVS
345 | PURBA BARDHAMAN | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | TSM/017577 | SM/14976 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 30/09/2022 | 1921 | 685.17 | Yes | 685.17 | 01/03/2024 | 19/05/2023 | 8 | 452.12 | 23.87 | MVS
346 | PURBA BARDHAMAN | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | TSM/017623 | SM/14977 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 30/09/2022 | 1708 | 841.52 | Yes | 841.52 | 17/03/2025 | 29/04/2024 | 9 | 582.97 | 267.26 | MVS
347 | PURBA BARDHAMAN | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | TSM/017618 | SM/14978 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 30/09/2022 | 786 | 462.5 | Yes | 462.5 | 10/12/2024 | 29/04/2024 | 9 | 334.31 | 268.79 | MVS
348 | PURBA BARDHAMAN | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME | TSM/017613 | SM/14979 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 30/09/2022 | 1921 | 576.58 | Yes | 576.58 | 02/02/2023 | 19/05/2023 | 5 | 378.75 | 32.76 | MVS
349 | PURBA BARDHAMAN | JABAGRAM PIPED WATER SUPPLY SCHEME | TSM/017140 | SM/14980 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2196 | 879.79 | Yes | 879.79 | 03/10/2024 | 17/02/2023 | 10 | 597.85 | 447.9 | MVS
350 | PURBA BARDHAMAN | UNIATATARPUR PIPED WATER SUPPLY SCHEME | TSM/017136 | SM/15133 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2232 | 698.43 | Yes | 698.43 | 04/04/2025 | 09/08/2023 | 9 | 626.8 | 198.38 | MVS
351 | PURBA BARDHAMAN | MALGRAM PIPED WATER SUPPLY SCHEME | TSM/017901 | SM/15150 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2056 | 636.08 | Yes | 636.08 | 04/04/2025 | 12/07/2024 | 10 | 447.19 | 268.88 | MVS
352 | PURBA BARDHAMAN | JAJIGRAM PIPE WATER SUPPLY SCHEME | TSM/017718 | SM/15151 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1588 | 709.72 | Yes | 709.72 | 12/11/2024 | 13/03/2023 | 11 | 496.4 | 371.66 | MVS
353 | PURBA BARDHAMAN | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | TSM/017554 | SM/15152 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 108 | 483.27 | Yes | 483.27 | 24/04/2025 | 29/08/2023 | 7 | 457.84 | 352.28 | MVS
354 | PURBA BARDHAMAN | MAKHALTOR PIPED WATER SUPPLY SCHEME | TSM/017600 | SM/15153 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1069 | 390.21 | Yes | 390.21 | 11/02/2025 | 10/03/2023 | 7 | 251.29 | 248.01 | MVS
355 | PURBA BARDHAMAN | KHATUNDI PIPED WATER SUPPLY SCHEME | TSM/017895 | SM/15154 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1112 | 469.62 | Yes | 469.62 | 04/04/2025 | 12/07/2024 | 10 | 385.68 | 257.39 | MVS
356 | PURBA BARDHAMAN | MURGRAM PIPED WATER SUPPLY SCHEME | TSM/017894 | SM/15156 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1763 | 537.11 | Yes | 537.11 | 02/05/2025 | 12/07/2024 | 15 | 426.96 | 313.98 | MVS
357 | PURBA BARDHAMAN | ANKHONA PIPED WATER SUPPLY SCHEME | TSM/017765 | SM/15157 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2087 | 782.97 | Yes | 782.97 | 04/04/2025 | 29/04/2025 | 11 | 559.2 | 298.66 | MVS
358 | PURBA BARDHAMAN | SRIPUR PIPE WATER SUPPLY SCHEME | TSM/017735 | SM/15158 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1608 | 571.6 | Yes | 571.6 | 02/05/2025 | 12/07/2024 | 11 | 407.57 | 182.7 | MVS
359 | PURBA BARDHAMAN | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | TSM/018160 | SM/15159 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 250 | 287.57 | Yes | 287.57 | 13/12/2024 | 13/04/2023 | 7 | 274.75 | 100.84 | MVS
360 | PURBA BARDHAMAN | PANDUGRAM PIPED WATER SUPPLY SCHEME | TSM/017748 | SM/15160 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1743 | 682.24 | Yes | 682.24 | 02/05/2025 | 12/07/2024 | 11 | 452.31 | 227.35 | MVS
361 | PURBA BARDHAMAN | SITAHATI PIPE WATER SUPPLY SCHEME | TSM/017646 | SM/15161 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 3022 | 784.13 | Yes | 784.13 | 01/03/2024 | 04/10/2023 | 10 | 494.49 | 305.24 | MVS
362 | PURBA BARDHAMAN | CHAKULIA PIPE WATER SUPPLY SCHEME | TSM/017644 | SM/15162 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2774 | 700.93 | Yes | 700.93 | 03/10/2024 | 08/08/2023 | 13 | 619.18 | 134.2 | MVS
363 | PURBA BARDHAMAN | MORGRAM PIPED WATER SUPPLY SCHEME | TSM/017883 | SM/15163 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1789 | 793.5 | Yes | 793.5 | 02/05/2025 | 29/04/2025 | 12 | 619.7 | 340.89 | MVS
364 | PURBA BARDHAMAN | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | TSM/017912 | SM/15165 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2568 | 810.54 | Yes | 810.54 | 24/04/2025 | 14/07/2023 | 10 | 633.39 | 443.4 | MVS
365 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | TSM/019278 | SM/15166 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/11/2022 | 0 | 226.46 | Yes | 226.46 | 17/04/2025 | 10/06/2024 | 15 | 192.31 | 86.82 | MVS
366 | PURBA BARDHAMAN | KULUTIA PIPED WATER SUPPLY SCHEME | TSM/017885 | SM/15167 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1631 | 685.87 | Yes | 685.87 | 04/04/2025 | 21/08/2023 | 9 | 499.54 | 175.76 | MVS
367 | PURBA BARDHAMAN | CHATKA PIPED WATER SUPPLY SCHEME | TSM/017915 | SM/15168 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2317 | 771.03 | Yes | 771.03 | 04/04/2025 | 11/07/2024 | 10 | 506.01 | 441.5 | MVS
368 | PURBA BARDHAMAN | CHINISPUR PIPED WATER SUPPLY SCHEME | TSM/017926 | SM/15170 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1794 | 584.6 | Yes | 584.6 | 04/04/2025 | 21/08/2023 | 10 | 403.41 | 148.49 | MVS
369 | PURBA BARDHAMAN | GOPKHANJI PIPED WATER SUPPLY SCHEME | TSM/017630 | SM/15171 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2054 | 914.1 | Yes | 914.1 | 04/04/2025 | 13/03/2023 | 7 | 556.84 | 304.45 | MVS
370 | PURBA BARDHAMAN | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | TSM/017544 | SM/15172 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 16/11/2022 | 1745 | 739.9 | Yes | 739.9 | 06/12/2024 | 01/10/2024 | 14 | 443.62 | 278.01 | MVS
371 | PURBA BARDHAMAN | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | TSM/019279 | SM/15173 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 0 | 287.77 | Yes | 287.77 | 06/08/2024 | 06/01/2025 | 5 | 120.12 | 0.96 | MVS
372 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | TSM/018188 | SM/15175 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 0 | 174.65 | Yes | 174.65 | 24/04/2025 | 13/04/2023 | 5 | 154.02 | 107.98 | MVS
373 | PURBA BARDHAMAN | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | TSM/019285 | SM/15176 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 16/11/2022 | 1200 | 217.82 | Yes | 217.82 | 06/08/2024 | 16/07/2024 | 5 | 175.37 | 60.27 | MVS
374 | PURBA BARDHAMAN | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | TSM/019265 | SM/15178 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 0 | 273.13 | Yes | 273.13 | 03/10/2024 | 06/06/2024 | 8 | 185.36 | 18.25 | MVS
375 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | TSM/018206 | SM/15179 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 450 | 145.55 | Yes | 145.55 | 24/09/2024 | 08/06/2023 | 10 | 105.5 | 3.25 | MVS
376 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | TSM/018216 | SM/15181 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | 16/11/2022 | 0 | 152.21 | Yes | 152.21 | 31/01/2025 | 28/04/2023 | 14 | 124.2 | 73.71 | MVS
377 | PURBA BARDHAMAN | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | TSM/019270 | SM/15182 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 0 | 279.58 | Yes | 279.58 | 02/09/2024 | 06/06/2024 | 6 | 175.05 | 6.03 | MVS
378 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | TSM/019275 | SM/15183 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 121 | 366.86 | Yes | 366.86 | 23/05/2025 | 10/06/2024 | 16 | 241.62 | 194.01 | MVS
379 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | TSM/019252 | SM/15184 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | 16/11/2022 | 544 | 220.43 | Yes | 220.43 | 17/04/2025 | 16/05/2023 | 11 | 107.47 | 69.67 | MVS
380 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | TSM/019254 | SM/15185 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | 16/11/2022 | 1500 | 397.16 | Yes | 397.16 | 04/09/2024 | 19/05/2023 | 6 | 119.55 | 75.74 | MVS
381 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | TSM/018185 | SM/15187 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 16/11/2022 | 562 | 144.12 | Yes | 144.12 | 05/05/2025 | 13/04/2023 | 8 | 78.83 | 53.63 | MVS
382 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | TSM/018125 | SM/15191 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 0 | 226.2 | Yes | 226.2 | 30/12/2024 | 08/05/2025 | 12 | 188.26 | 82.33 | MVS
383 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | TSM/018132 | SM/15192 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 1757 | 302.82 | Yes | 302.82 | 07/08/2024 | 03/05/2023 | 16 | 291.92 | 249.37 | MVS
384 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | TSM/017978 | SM/15194 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 16/11/2022 | 1684 | 341.33 | Yes | 341.33 | 02/01/2025 | 20/04/2023 | 12 | 230.89 | 92.29 | MVS
385 | PURBA BARDHAMAN | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | TSM/018214 | SM/15195 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 1983 | 107.27 | Yes | 107.27 | 12/02/2024 | 18/06/2024 | 2 | 98.13 | 64.64 | MVS
386 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | TSM/018026 | SM/15203 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 16/11/2022 | 350 | 153.66 | Yes | 153.66 | 17/04/2025 | 08/06/2023 | 8 | 119.38 | 63.24 | MVS
387 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA | TSM/018141 | SM/15205 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 0 | 80.39 | Yes | 80.39 | 05/05/2025 | 10/06/2024 | 2 | 1.74 | 0.77 | MVS
388 | PURBA BARDHAMAN | GOPALPUR PIPED WATER SUPPLY SCHEME | TSM/016822 | SM/15235 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 26/09/2022 | 1398 | 743.22 | Yes | 743.22 | 17/03/2025 | 20/12/2023 | 9 | 525.35 | 426.31 | MVS
389 | PURBA BARDHAMAN | RAJUR PIPED WATER SUPPLY SCHEME | TSM/017138 | SM/15238 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 2477 | 955.81 | Yes | 955.81 | 24/04/2025 | 12/04/2023 | 10 | 613.14 | 531.97 | MVS
390 | PURBA BARDHAMAN | PURULIA PIPED WATER SUPPLY SCHEME | TSM/017128 | SM/15239 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1004 | 459.29 | Yes | 459.29 | 04/04/2025 | 19/07/2024 | 9 | 142.45 | 179.53 | MVS
391 | PURBA BARDHAMAN | KHERUA PIPED WATER SUPPLY SCHEME | TSM/017126 | SM/15240 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1521 | 692.15 | Yes | 692.15 | 16/01/2025 | 17/02/2023 | 13 | 506.5 | 413.56 | MVS
392 | PURBA BARDHAMAN | BILLESWAR PIPED WATER SUPPLY SCHEME | TSM/017148 | SM/15241 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 1647 | 782.16 | Yes | 782.16 | 02/05/2025 | 19/07/2024 | 8 | 143.27 | 300.74 | MVS
393 | PURBA BARDHAMAN | MAHATA PIPED WATER SUPPLY SCHEME | TSM/017122 | SM/15242 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 30/09/2022 | 1751 | 766.68 | Yes | 766.68 | 30/04/2025 | 13/04/2023 | 11 | 682.74 | 416.28 | MVS
394 | PURBA BARDHAMAN | KARJJANA PIPED WATER SUPPLY SCHEME | TSM/017170 | SM/15244 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 309 | 235.19 | Yes | 235.19 | 05/05/2025 | 03/03/2023 | 11 | 131.38 | 104.95 | MVS
395 | PURBA BARDHAMAN | PASHALA PIPED WATER SUPPLY SCHEME | TSM/017155 | SM/15245 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 30/09/2022 | 476 | 280.13 | Yes | 280.13 | 30/04/2025 | 31/10/2023 | 8 | 230.85 | 33.54 | MVS
396 | PURBA BARDHAMAN | DHENRIA PIPED WATER SUPPLY SCHEME | TSM/017171 | SM/15246 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 30/09/2022 | 1267 | 703.67 | Yes | 703.67 | 01/03/2024 | 13/04/2023 | 11 | 648.99 | 361.85 | MVS
397 | PURBA BARDHAMAN | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | TSM/009941 | SM/15309 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 17/02/2022 | 1994 | 710.23 | Yes | 710.23 | 17/04/2025 | 08/06/2023 | 9 | 381.52 | 297.67 | MVS
398 | PURBA BARDHAMAN | HARISHNAPUR PIPED WATER SUPPLY SCHEME | TSM/016786 | SM/15319 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 26/09/2022 | 1867 | 714.61 | Yes | 714.61 | 01/03/2024 | 24/07/2023 | 8 | 463.71 | 68.77 | MVS
399 | PURBA BARDHAMAN | Narottambati Piped Water Supply Scheme | TSM/015319 | SM/15486 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 2297 | 1019.43 | Yes | 1019.43 | 01/03/2024 | 10/08/2023 | 10 | 670.33 | 198.54 | MVS
400 | PURBA BARDHAMAN | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | TSM/015306 | SM/15487 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 09/09/2022 | 3286 | 1236.06 | Yes | 1236.06 | 01/03/2024 | 24/08/2023 | 10 | 798.96 | 60.04 | MVS
401 | PURBA BARDHAMAN | Pipuldaha Piped Water Supply Scheme | TSM/015308 | SM/15488 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 2640 | 1182.3 | Yes | 1182.3 | 04/04/2025 | 28/05/2024 | 11 | 731.58 | 338.02 | MVS
402 | PURBA BARDHAMAN | Chaudanga Piped Water Supply Scheme | TSM/015305 | SM/15489 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 09/09/2022 | 2994 | 1143.73 | Yes | 1143.73 | 04/04/2025 | 27/07/2023 | 9 | 678.76 | 329.66 | MVS
403 | PURBA BARDHAMAN | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME | TSM/017550 | SM/15555 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 280 | 380.06 | Yes | 380.06 | 27/01/2025 | 13/12/2023 | 4 | 26.35 | 136.68 | MVS
404 | PURBA BARDHAMAN | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | TSM/018152 | SM/15556 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/11/2022 | 312 | 216.81 | Yes | 216.81 | 09/04/2025 | 26/11/2024 | 5 | 118.27 | 49.61 | MVS
405 | PURBA BARDHAMAN | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | TSM/017541 | SM/15557 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1000 | 722.06 | Yes | 722.06 | 12/03/2024 | 10/08/2023 | 7 | 719.17 | 271.4 | MVS
406 | PURBA BARDHAMAN | AUGMENTATION BHALKI Z-I & Z-II PWSS | TSM/019284 | SM/15560 | Augmentation | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 16/11/2022 | 600 | 466.54 | Yes | 466.54 | 01/08/2023 | 18/05/2023 | 6 | 244.67 | 35.81 | MVS
407 | PURBA BARDHAMAN | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME | TSM/018170 | SM/15562 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 16/11/2022 | 60 | 410.59 | Yes | 410.59 | 27/01/2025 | 13/04/2023 | 6 | 402.28 | 110.34 | MVS
408 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | TSM/018105 | SM/15565 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 16/11/2022 | 150 | 108.27 | Yes | 108.27 | 24/04/2025 | 04/05/2023 | 5 | 61.79 | 6.09 | MVS
409 | PURBA BARDHAMAN | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | TSM/017601 | SM/15568 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | 16/11/2022 | 594 | 583.85 | Yes | 583.85 | 09/08/2024 | 03/07/2024 | 7 | 485.57 | 151.74 | MVS
410 | PURBA BARDHAMAN | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | TSM/018386 | SM/15571 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 1414 | 904.68 | Yes | 904.68 | 22/01/2025 | 20/06/2024 | 7 | 291.8 | 273.94 | MVS
411 | PURBA BARDHAMAN | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME | TSM/017545 | SM/15573 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 16/11/2022 | 734 | 523.9 | Yes | 523.9 | 01/02/2024 | 20/08/2024 | 2 | 517.26 | 74.02 | MVS
412 | PURBA BARDHAMAN | MERA PIPE WATER SUPPLY SCHEME | TSM/017599 | SM/15575 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 1255 | 559.06 | Yes | 559.06 | 12/09/2024 | 31/05/2024 | 16 | 133.75 | 173.57 | MVS
413 | PURBA BARDHAMAN | MARO PIPED WATER SUPPLY SCHEME | TSM/017784 | SM/15579 | New | Durgapur Sub-DIvision | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | 28/12/2022 | 238 | 237.76 | Yes | 237.76 | 06/03/2024 | 01/06/2023 | 8 | 216.19 | 110.48 | MVS
414 | PURBA BARDHAMAN | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | TSM/017744 | SM/15581 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 892 | 500.08 | Yes | 500.08 | 12/03/2024 | 13/09/2024 | 8 | 369.09 | 192.94 | MVS
415 | PURBA BARDHAMAN | CHAKDAHA PIPED WATER SUPPLY SCHEME | TSM/017948 | SM/15582 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 293 | 207.53 | Yes | 207.53 | 12/03/2024 | 12/07/2024 | 7 | 54.47 | 86.28 | MVS
416 | PURBA BARDHAMAN | GOPALPUR PIPED WATER SUPPLY SCHEME | TSM/018235 | SM/15583 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | 28/12/2022 | 688 | 379.6 | Yes | 379.6 | 01/03/2024 | 19/05/2023 | 6 | 218.21 | 122.05 | MVS
417 | PURBA BARDHAMAN | SHYAMPUR PIPE WATER SUPPLY SCHEME | TSM/017557 | SM/15585 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 813 | 485.78 | Yes | 485.78 | 25/07/2024 | 07/08/2024 | 9 | 340.95 | 190.21 | MVS
418 | PURBA BARDHAMAN | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | TSM/017736 | SM/15586 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1614 | 711.87 | Yes | 711.87 | 25/02/2025 | 13/06/2024 | 10 | 688.22 | 325.39 | MVS
419 | PURBA BARDHAMAN | ANGARSON PIPED WATER SUPPLY SCHEME | TSM/017791 | SM/15587 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1560 | 692.97 | Yes | 692.97 | 19/03/2025 | 04/03/2024 | 8 | 202.37 | 263.72 | MVS
420 | PURBA BARDHAMAN | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | TSM/018388 | SM/15588 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 1000 | 793.59 | Yes | 793.59 | 18/01/2024 | 24/08/2023 | 6 | 784.39 | 33.64 | MVS
421 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | TSM/019256 | SM/15602 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 16/11/2022 | 500 | 700.54 | Yes | 700.54 | 21/06/2024 | 02/06/2021 | 4 | 517.18 | 235.78 | MVS
422 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | TSM/018161 | SM/15701 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 0 | 144.48 | Yes | 144.48 | 13/03/2025 | 31/05/2023 | 8 | 88.28 | 42.69 | MVS
423 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA | TSM/018150 | SM/15718 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 140 | 56.48 | Yes | 56.48 | 30/09/2024 | 28/02/2023 | 2 | 13.96 | 10.1 | MVS
424 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | TSM/017997 | SM/15722 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 16/11/2022 | 0 | 92.86 | Yes | 92.86 | 14/05/2025 | 17/07/2023 | 4 | 41.74 | 27.88 | MVS
425 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | TSM/017996 | SM/15723 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 16/11/2022 | 541 | 130.73 | Yes | 130.73 | 24/04/2025 | 04/04/2023 | 9 | 82.64 | 79.09 | MVS
426 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME | TSM/017966 | SM/15725 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 0 | 96.14 | Yes | 96.14 | 08/01/2025 | 12/07/2023 | 4 | 80.24 | 1.32 | MVS
427 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | TSM/018004 | SM/15753 | Augmentation | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 0 | 126.2 | Yes | 126.2 | 14/05/2025 | 10/06/2024 | 3 | 74.52 | 38.53 | MVS
428 | PURBA BARDHAMAN | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II | TSM/018387 | SM/16014 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 1000 | 979.43 | Yes | 979.43 | 23/02/2023 | 05/08/2024 | 4 | 962.07 | 28.16 | MVS
429 | PURBA BARDHAMAN | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME | TSM/017536 | SM/16016 | Augmentation | Katwa Sub-Division | Assistant Engineer |  | 28/12/2022 | 180 | 145.44 | Yes | 145.44 | 21/02/2023 | 19/05/2023 | 3 | 144.61 | 60.34 | MVS
430 | PURBA BARDHAMAN | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME | TSM/017528 | SM/16017 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 150 | 144.31 | Yes | 144.31 | 20/09/2023 | 14/07/2023 | 3 | 154.9 | 93.04 | MVS
431 | PURBA BARDHAMAN | KASIPUR PIPED WATER SUPPLY SCHEME | TSM/017742 | SM/16019 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1617 | 717.23 | Yes | 717.23 | 24/09/2024 | 24/08/2023 | 8 | 534.33 | 169.35 | MVS
432 | PURBA BARDHAMAN | MASARU PIPE WATER SUPPLY SCHEME | TSM/017655 | SM/16020 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 843 | 399.5 | Yes | 399.5 | 06/03/2025 | 12/05/2023 | 7 | 60.55 | 227.21 | MVS
433 | PURBA BARDHAMAN | SABIDPUR PIPED WATER SUPPLY SCHEME | TSM/017767 | SM/16021 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1769 | 783.85 | Yes | 783.85 | 01/03/2024 | 24/08/2023 | 9 | 600.94 | 209.75 | MVS
434 | PURBA BARDHAMAN | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME | TSM/017520 | SM/16022 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer,JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | 28/12/2022 | 130 | 145.22 | Yes | 145.22 | 14/05/2025 | 22/05/2023 | 3 | 141.41 | 131.2 | MVS
435 | PURBA BARDHAMAN | AMEGERIA PIPED WATER SUPPLY SCHEME | TSM/017927 | SM/16023 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 1863 | 649.63 | Yes | 649.63 | 04/04/2025 | 21/08/2023 | 8 | 450.43 | 180.43 | MVS
436 | PURBA BARDHAMAN | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | TSM/017750 | SM/16024 | New | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 1470 | 660.06 | Yes | 660.06 | 19/03/2025 | 27/06/2024 | 8 | 179.89 | 314.05 | MVS
437 | PURBA BARDHAMAN | MAHULA PIPED WATER SUPPLY SCHEME | TSM/017936 | SM/16025 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 946 | 423.81 | Yes | 423.81 | 12/03/2024 | 11/07/2024 | 10 | 388.2 | 188.83 | MVS
438 | PURBA BARDHAMAN | NAYAPARA PIPED WATER SUPPLY SCHEME | TSM/017639 | SM/16026 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 567 | 286.69 | Yes | 286.69 | 06/03/2025 | 23/11/2023 | 8 | 193.53 | 115.63 | MVS
439 | PURBA BARDHAMAN | DAFARPUR PIPED WATER SUPPLY SCHEME | TSM/017789 | SM/16028 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 720 | 417.08 | Yes | 417.08 | 19/03/2025 | 30/05/2025 | 14 | 109.56 | 156.61 | MVS
440 | PURBA BARDHAMAN | PATHAR GHATA PIPED WATER SUPPLY SCHEME | TSM/017727 | SM/16029 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1692 | 749.43 | Yes | 749.43 | 01/03/2024 | 24/08/2023 | 10 | 585.74 | 135.06 | MVS
441 | PURBA BARDHAMAN | BAKALSA PIPE WATER SUPPLY SCHEME | TSM/017743 | SM/16030 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 457 | 268.67 | Yes | 268.67 | 04/04/2025 | 12/07/2024 | 5 | 95.42 | 109.19 | MVS
442 | PURBA BARDHAMAN | KANKURHATI PIPED WATER SUPPLY SCHEME | TSM/018124 | SM/16031 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 466 | 251.87 | Yes | 251.87 | 04/04/2025 | 24/03/2023 | 8 | 187.83 | 130.57 | MVS
443 | PURBA BARDHAMAN | SHANKRA PIPE WATER SUPPLY SCHEME | TSM/017579 | SM/16032 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1047 | 470.45 | Yes | 470.45 | 22/07/2024 | 07/09/2023 | 7 | 300.01 | 8.59 | MVS
444 | PURBA BARDHAMAN | LOHARUNDI PIPED WATER SUPPLY SCHEME | TSM/017914 | SM/16033 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 284 | 256.48 | Yes | 256.48 | 12/03/2024 | 06/09/2024 | 9 | 140.81 | 99.15 | MVS
445 | PURBA BARDHAMAN | GHUNI PIPE WATER SUPPLY SCHEME | TSM/017555 | SM/16034 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1008 | 451.58 | Yes | 451.58 | 18/11/2024 | 10/08/2023 | 11 | 328.02 | 233.35 | MVS
446 | PURBA BARDHAMAN | KHARGAKUR PIPED WATER SUPPLY SCHEME | TSM/017797 | SM/16035 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1294 | 571.41 | Yes | 571.41 | 09/08/2024 | 28/08/2023 | 10 | 470.13 | 219.15 | MVS
447 | PURBA BARDHAMAN | KUSDANGA PIPED WATER SUPPLY SCHEME | TSM/017728 | SM/16036 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 865 | 493.57 | Yes | 493.57 | 29/10/2024 | 03/12/2024 | 9 | 164.91 | 177.75 | MVS
448 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | TSM/019358 | SM/16192 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 28/12/2022 | 1693 | 386.1 | Yes | 386.1 | 17/04/2025 | 29/05/2023 | 10 | 201.75 | 109.32 | MVS
449 | PURBA BARDHAMAN | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME | TSM/019603 | SM/16193 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 200 | 214.58 | Yes | 214.58 | 29/01/2025 | 28/07/2023 | 3 | 52.09 | 15.54 | MVS
450 | PURBA BARDHAMAN | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME | TSM/019606 | SM/16196 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 280 | 262.71 | Yes | 262.71 | 15/06/2023 | 17/10/2023 | 5 | 205.03 | 40.62 | MVS
451 | PURBA BARDHAMAN | RASUIKHANDA PIPED WATER SUPPLY SCHEME | TSM/016866 | SM/16253 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 26/09/2022 | 2353 | 996.62 | Yes | 996.62 | 17/03/2025 | 12/04/2023 | 9 | 713.42 | 681.2 | MVS
452 | PURBA BARDHAMAN | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | TSM/016815 | SM/16254 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 26/09/2022 | 446 | 254.97 | Yes | 254.97 | 14/05/2025 | 24/03/2023 | 10 | 143.94 | 100.43 | MVS
453 | PURBA BARDHAMAN | SHUKUR PIPED WATER SUPPLY SCHEME | TSM/016893 | SM/16255 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 26/09/2022 | 1849 | 889.84 | Yes | 889.84 | 01/03/2024 | 24/07/2023 | 9 | 567.36 | 120.57 | MVS
454 | PURBA BARDHAMAN | JHAMATPUR PIPED WATER SUPPLY SCHEME | TSM/017474 | SM/16256 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 30/09/2022 | 655 | 361.18 | Yes | 361.18 | 04/04/2025 | 23/05/2023 | 9 | 274.05 | 174.46 | MVS
455 | PURBA BARDHAMAN | DWARIATAN PIPED WATER SUPPLY SCHEME | TSM/017751 | SM/16285 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 1996 | 891.16 | Yes | 891.16 | 01/03/2024 | 13/06/2024 | 7 | 819.58 | 142.51 | MVS
456 | PURBA BARDHAMAN | BIRUHA PIPED WATER SUPPLY SCHEME | TSM/017756 | SM/16287 | New | RWS Burdwan Sub-Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | 28/12/2022 | 1813 | 813.4 | Yes | 813.4 | 06/11/2024 | 24/08/2023 | 10 | 673.23 | 231.62 | MVS
457 | PURBA BARDHAMAN | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C | TSM/019605 | SM/16289 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 200 | 94.64 | Yes | 94.64 | 04/03/2025 | 23/04/2025 | 4 | 69.45 | 35.74 | MVS
458 | PURBA BARDHAMAN | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | TSM/019604 | SM/16290 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 600 | 167.64 | Yes | 167.64 | 05/05/2025 | 01/06/2023 | 6 | 85.62 | 57.89 | MVS
459 | PURBA BARDHAMAN | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | TSM/020229 | SM/16293 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 300 | 252.07 | Yes | 252.07 | 01/02/2024 | 13/06/2024 | 5 | 233.27 | 98.63 | MVS
460 | PURBA BARDHAMAN | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | TSM/019618 | SM/16297 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 300 | 254.93 | Yes | 254.93 | 01/02/2024 | 13/06/2024 | 6 | 241.05 | 130.57 | MVS
461 | PURBA BARDHAMAN | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | TSM/019621 | SM/16298 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 0 | 379.1 | Yes | 379.1 | 25/07/2024 | 03/05/2023 | 8 | 341.57 | 23.58 | MVS
462 | PURBA BARDHAMAN | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME | TSM/019615 | SM/16299 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 200 | 205.59 | Yes | 205.59 | 01/02/2024 | 27/06/2024 | 4 | 193.28 | 124.73 | MVS
463 | PURBA BARDHAMAN | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | TSM/019614 | SM/16301 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 250 | 301.7 | Yes | 301.7 | 25/07/2024 | 04/07/2024 | 6 | 279.43 | 90.21 | MVS
464 | PURBA BARDHAMAN | GAHAK PIPE WATER SUPPLY SCHEME | TSM/017565 | SM/16303 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 924 | 414.78 | Yes | 414.78 | 25/07/2024 | 07/08/2024 | 9 | 305.36 | 110.15 | MVS
465 | PURBA BARDHAMAN | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME | TSM/019608 | SM/16304 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 200 | 286.45 | Yes | 286.45 | 11/11/2024 | 03/05/2023 | 5 | 76.76 | 43.51 | MVS
466 | PURBA BARDHAMAN | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME | TSM/019607 | SM/16306 | Augmentation | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 150 | 246 | Yes | 246 | 19/02/2024 | 10/05/2023 | 3 | 213.5 | 17.56 | MVS
467 | PURBA BARDHAMAN | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | TSM/018389 | SM/16307 | Augmentation | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 1000 | 965.63 | Yes | 965.63 | 18/01/2024 | 20/06/2024 | 6 | 430.08 | 128.3 | MVS
468 | PURBA BARDHAMAN | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | TSM/017731 | SM/16308 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 28/12/2022 | 401 | 179.63 | Yes | 179.63 | 18/11/2024 | 24/04/2023 | 11 | 154.69 | 128.57 | MVS
469 | PURBA BARDHAMAN | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | TSM/019630 | SM/16349 | Retrofitting | Kalna Sub-division | Assistant Engineer |  | 28/12/2022 | 500 | 126.77 | Yes | 126.77 | 13/09/2024 | 30/05/2023 | 5 | 128.39 | 85.81 | MVS
470 | PURBA BARDHAMAN | KHANJI PIPED WATER SUPPLY SCHEME | TSM/017942 | SM/16476 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2182 | 711.62 | Yes | 711.62 | 04/04/2025 | 12/07/2024 | 11 | 540.92 | 332.74 | MVS
471 | PURBA BARDHAMAN | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME | TSM/017651 | SM/16477 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1812 | 753.31 | Yes | 753.31 | 01/03/2024 | 04/10/2023 | 8 | 513.12 | 152.37 | MVS
472 | PURBA BARDHAMAN | BALINDAR PIPED WATER SUPPLY SCHEME | TSM/017777 | SM/16478 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 16/11/2022 | 2511 | 996.62 | Yes | 996.62 | 06/03/2025 | 23/04/2025 | 12 | 685.62 | 99.57 | MVS
473 | PURBA BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | TSM/018352 | SM/16479 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/11/2022 | 1946 | 433.76 | Yes | 433.76 | 09/04/2025 | 20/05/2025 | 13 | 214.08 | 108 | MVS
474 | PURBA BARDHAMAN | ARGUN PIPED WATER SUPPLY SCHEME | TSM/017907 | SM/16482 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1637 | 606.69 | Yes | 606.69 | 04/04/2025 | 21/08/2023 | 10 | 420.88 | 311.87 | MVS
475 | PURBA BARDHAMAN | BANKAPASI PIPE WATER SUPPLY SCHEME | TSM/017633 | SM/16484 | New | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2622 | 984.37 | Yes | 984.37 | 04/04/2025 | 16/04/2024 | 9 | 579.69 | 124.83 | MVS
476 | PURBA BARDHAMAN | AKALPAUSH PIPE WATER SUPPLY SCHEME | TSM/017758 | SM/16485 | New | RWS Burdwan Sub-Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | 16/11/2022 | 2094 | 921.29 | Yes | 921.29 | 01/03/2024 | 13/09/2024 | 13 | 670.12 | 326.2 | MVS
477 | PURBA BARDHAMAN | AUGMENTATION OF RAYAN (PART-II) PWSS | TSM/018136 | SM/16486 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/11/2022 | 4085 | 772.37 | Yes | 772.37 | 29/07/2024 | 25/06/2024 | 5 | 739.03 | 5.11 | MVS
478 | PURBA BARDHAMAN | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | TSM/018139 | SM/16487 | Augmentation | Central Mechanical Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 2200 | 857.85 | Yes | 857.85 | 25/07/2024 | 13/04/2023 | 5 | 52.05 | 16.53 | MVS
479 | PURBA BARDHAMAN | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MUGURA | TSM/017721 | SM/16488 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 606 | 39.97 | Yes | 39.97 | 06/03/2024 | 11/07/2024 | 3 | 38.83 | 19.33 | MVS
480 | PURBA BARDHAMAN | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL | TSM/017973 | SM/16489 | Retrofitting | Burdwan Sadar Sub-Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 16/11/2022 | 1075 | 57.12 | Yes | 57.12 | 23/05/2025 | 13/04/2023 | 3 | 42.23 | 27.95 | MVS
481 | PURBA BARDHAMAN | KHANPUR PIPED WATER SUPPLY SCHEME | TSM/016774 | SM/16540 | New | Kalna Sub-division | Assistant Engineer | JUNIOR ENGINEER | 26/09/2022 | 3321 | 1171.58 | Yes | 1171.58 | 30/04/2025 | 08/11/2023 | 8 | 843.33 | 83.44 | MVS
482 | PURBA BARDHAMAN | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME | TSM/018151 | SM/16548 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/11/2022 | 557 | 312.94 | Yes | 312.94 | 29/07/2024 | 19/05/2023 | 9 | 217.52 | 85.77 | MVS
483 | PURBA BARDHAMAN | NETRAKHANDA PIPED WATER SUPPLY SCHEME | TSM/016909 | SM/16616 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 26/09/2022 | 1424 | 663.07 | Yes | 663.07 | 01/03/2024 | 14/09/2023 | 8 | 421.23 | 41.41 | MVS
484 | PURBA BARDHAMAN | NERAGOHALIA PIPED WATER SUPPLY SCHEME | TSM/016948 | SM/16617 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 26/09/2022 | 2895 | 998.07 | Yes | 998.07 | 03/10/2024 | 09/08/2023 | 9 | 859.17 | 255.66 | MVS
485 | PURBA BARDHAMAN | SIPTA PIPED WATER SUPPLY SCHEME | TSM/016868 | SM/16618 | New | Central Mechanical Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | 26/09/2022 | 708 | 441.18 | Yes | 441.18 | 16/01/2025 | 18/05/2023 | 12 | 239.93 | 225.24 | MVS
486 | PURBA BARDHAMAN | BAJITPUR PIPED WATER SUPPLY SCHEME | TSM/016787 | SM/16619 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | 26/09/2022 | 1500 | 680.19 | Yes | 680.19 | 01/03/2024 | 24/07/2023 | 7 | 436.67 | 63.4 | MVS
487 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | TSM/019268 | SM/16774 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 16/11/2022 | 0 | 275.12 | Yes | 275.12 | 10/12/2024 | 06/06/2024 | 15 | 132.92 | 96.97 | MVS
488 | PURBA BARDHAMAN | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | TSM/019276 | SM/18112 | Augmentation | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | 10/03/2023 | 0 | 296.54 | Yes | 296.54 | 09/04/2025 | 21/03/2023 | 6 | 212.2 | 14.49 | MVS
489 | PURBA BARDHAMAN | AMADPUR PIPED WATER SUPPLY SCHEME | TSM/020484 | SM/18146 | New | Burdwan Sadar Sub-Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 10/03/2023 | 1499 | 571.48 | Yes | 571.48 | 01/03/2024 | 16/01/2024 | 4 | 39.7 | 113.87 | MVS
490 | PURBA BARDHAMAN | BARADOBA PIPED WATER SUPPLY SCHEME | TSM/017790 | SM/18230 | New | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | 28/12/2022 | 216 | 215.86 | Yes | 215.86 | 01/03/2024 | 26/11/2024 | 9 | 184.93 | 130.42 | MVS
491 | PURBA BARDHAMAN | MOHANPUR PIPED WATER SUPPLY SCHEME | TSM/016268 | SM/18242 | New | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 26/09/2022 | 2788 | 1333.72 | Yes | 1333.72 | 02/12/2024 | 08/01/2025 | 11 | 1459.79 | 833.07 | MVS
492 | PURBA BARDHAMAN | SASANGA PIPED WATER SUPPLY SCHEME | TSM/015804 | SM/18245 | New |  |  |  | 09/09/2022 | 3700 | 1466.25 | Yes | 1466.25 | 28/08/2024 | 07/08/2023 | 10 | 983.44 | 580.98 | MVS
493 | PURBA BARDHAMAN | ONARI PIPED WATER SUPPLY SCHEME | TSM/015802 | SM/18246 | New |  |  |  | 09/09/2022 | 2953 | 1194.73 | Yes | 1194.73 | 18/11/2024 | 07/08/2023 | 9 | 682.97 | 377.51 | MVS
494 | PURBA BARDHAMAN | NALA PIPED WATER SUPPLY SCHEME | TSM/016950 | SM/18256 | New |  |  |  | 26/09/2022 | 3779 | 1246.49 | Yes | 1246.49 | 04/09/2024 | 05/03/2025 | 8 | 268.84 | 314.81 | MVS
495 | PURBA BARDHAMAN | BANTIR PIPED WATER SUPPLY SCHEME | TSM/016817 | SM/18300 | New |  |  |  | 26/09/2022 | 2936 | 1286.37 | Yes | 1286.37 | 17/03/2025 | 19/07/2024 | 11 | 87.57 | 549.42 | MVS
496 | PURBA BARDHAMAN | KHANO PIPED WATER SUPPLY SCHEME | TSM/017813 | SM/18313 | New |  |  |  | 28/12/2022 | 4076 | 2374.1 | Yes | 2374.1 | 03/12/2024 | 21/04/2025 | 13 | 774.97 | 763.91 | MVS
497 | PURBA BARDHAMAN | JIUDHARA PWSS | TSM/017740 | SM/18314 | New |  |  |  | 28/12/2022 | 2709 | 1124.56 | Yes | 1124.56 | 12/09/2024 | 13/10/2023 | 9 | 980.66 | 217.05 | MVS
498 | PURBA BARDHAMAN | BALIDANGA PIPE WATER SUPPLY SCHEME | TSM/017725 | SM/18315 | New |  |  |  | 28/12/2022 | 3466 | 1116.5 | Yes | 1116.5 | 04/04/2025 | 08/08/2023 | 10 | 753.33 | 288.34 | MVS
499 | PURBA BARDHAMAN | LOAPUR PIPED WATER SUPPLY SCHEME | TSM/016509 | SM/18323 | New | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | 26/09/2022 | 3508 | 1466.39 | Yes | 1466.39 | 03/10/2024 | 25/11/2024 | 8 | 1176.05 | 414.84 | MVS
500 | PURBA BARDHAMAN | Balgana Piped Water Supply Scheme | TSM/015301 | SM/18326 | New |  |  |  | 09/09/2022 | 2564 | 1124.71 | Yes | 1124.71 | 07/08/2024 | 24/08/2023 | 10 | 777.88 | 146.08 | MVS
501 | PURBA BARDHAMAN | BAGHTONA PIPED WATER SUPPLY SCHEME | TSM/017608 | SM/18334 | New |  |  |  | 28/12/2022 | 1867 | 1031.05 | Yes | 1031.05 | 04/04/2025 | 24/07/2023 | 10 | 587.9 | 498.97 | MVS
502 | PURBA BARDHAMAN | BAINCHI PIPED WATER SUPPLY SCHEME | TSM/017649 | SM/18335 | New |  |  |  | 28/12/2022 | 2450 | 1089.2 | Yes | 1089.2 | 04/04/2025 | 10/08/2023 | 8 | 628.42 | 166.1 | MVS
503 | PURBA BARDHAMAN | SANKARPUR PIPED WATER SUPPLY SCHEME | TSM/016839 | SM/18337 | New |  |  |  | 26/09/2022 | 3257 | 1151.61 | Yes | 1151.61 | 17/03/2025 | 13/09/2024 | 8 | 69.91 | 365.39 | MVS
504 | PURBA BARDHAMAN | BELSHAR PIPED WATER SUPPLY SCHEME | TSM/016795 | SM/18338 | New |  |  |  | 26/09/2022 | 3434 | 1185.09 | Yes | 1185.09 | 17/03/2025 | 25/11/2024 | 8 | 93.37 | 589.22 | MVS
505 | PURBA BARDHAMAN | EHIAPUR PIPED WATER SUPPLY SCHEME | TSM/017933 | SM/18342 | New |  |  |  | 16/11/2022 | 3160 | 1201.07 | Yes | 1201.07 | 04/04/2025 | 12/07/2024 | 12 | 959.46 | 761.61 | MVS
506 | PURBA BARDHAMAN | HALIMPUR PIPE WATER SUPPLY SCHEME | TSM/017659 | SM/18343 | New |  |  |  | 16/11/2022 | 3829 | 1198.96 | Yes | 1198.96 | 03/10/2024 | 16/04/2024 | 11 | 1026.56 | 82.47 | MVS
507 | PURBA BARDHAMAN | SHILLA PIPED WATER SUPPLY SCHEME | TSM/017785 | SM/18344 | New |  |  |  | 16/11/2022 | 12334 | 4972.51 | Yes | 4972.51 | 03/12/2024 | 26/06/2024 | 15 | 2049.12 | 1221.38 | MVS
508 | PURBA BARDHAMAN | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | TSM/015283 | SM/18365 | New |  |  |  | 09/09/2022 | 4783 | 1436.61 | Yes | 1436.61 | 02/09/2024 | 26/06/2024 | 13 | 1395.29 | 825.49 | MVS
509 | PURBA BARDHAMAN | KASIGRAM PIPE WATER SUPPLY SCHEME | TSM/017607 | SM/18367 | New |  |  |  | 16/11/2022 | 3024 | 1354.92 | Yes | 1354.92 | 04/04/2025 | 24/07/2023 | 9 | 804.7 | 730.06 | MVS
510 | PURBA BARDHAMAN | Ichalabad Piped Water Supply Scheme | TSM/015311 | SM/18404 | New |  |  |  | 09/09/2022 | 2647 | 1170.91 | Yes | 1170.91 | 01/03/2024 | 31/07/2023 | 6 | 862.31 | 78.97 | MVS
511 | PURBA BARDHAMAN | SANTOSHPUR PIPED WATER SUPPLY SCHEME | TSM/015703 | SM/18405 | New | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 2995 | 1130.16 | Yes | 1130.16 | 30/04/2025 | 21/10/2024 | 9 | 206.19 | 358.8 | MVS
512 | PURBA BARDHAMAN | Bara Bainan Piped Water Supply Scheme | TSM/015314 | SM/18406 | New |  |  |  | 09/09/2022 | 2814 | 1077.31 | Yes | 1077.31 | 04/04/2025 | 27/07/2023 | 14 | 632.06 | 468.32 | MVS
513 | PURBA BARDHAMAN | Sanko Piped Water Supply Scheme | TSM/015698 | SM/18407 | New | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 09/09/2022 | 3620 | 1448.91 | Yes | 1448.91 | 01/10/2024 | 10/12/2024 | 8 | 270.93 | 525.98 | MVS
514 | PURBA BARDHAMAN | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | TSM/015738 | SM/18408 | New |  |  |  | 09/09/2022 | 3278 | 1068.22 | Yes | 1068.22 | 28/11/2024 | 11/02/2025 | 8 | 1039.3 | 292.6 | MVS
515 | PURBA BARDHAMAN | HATSIMUL PIPED WATER SUPPLY SCHEME | TSM/015309 | SM/18409 | New |  |  |  | 09/09/2022 | 2529 | 1338.5 | Yes | 1338.5 | 04/09/2024 | 31/07/2023 | 8 | 918.11 | 320.62 | MVS
516 | PURBA BARDHAMAN | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | TSM/015235 | SM/18422 | New | Durgapur Sub-DIvision | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | 09/09/2022 | 3196 | 1032.73 | Yes | 1032.73 | 05/05/2025 | 12/05/2023 | 10 | 263.99 | 823.34 | MVS
517 | PURBA BARDHAMAN | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | TSM/019289 | SM/18439 | Augmentation |  |  |  | 16/11/2022 | 9130 | 2281.19 | Yes | 2281.19 | 25/07/2024 | 21/05/2024 | 8 | 2259.18 | 1208.98 | MVS
518 | PURBA BARDHAMAN | KULSANA PIPE WATER SUPPLY SCHEME | TSM/017638 | SM/18440 | New |  |  |  | 16/11/2022 | 3613 | 1230.88 | Yes | 1230.88 | 03/10/2024 | 16/04/2024 | 12 | 1026.7 | 314.95 | MVS
519 | PURBA BARDHAMAN | GUSUMBA PIPED WATER SUPPLY SCHEME | TSM/017664 | SM/18441 | New |  |  |  | 16/11/2022 | 3423 | 1434.92 | Yes | 1434.92 | 12/03/2024 | 02/08/2023 | 9 | 986.32 | 424.56 | MVS
520 | PURBA BARDHAMAN | PANDUK PIPED WATER SUPPLY SCHEME | TSM/016569 | SM/18445 | New |  |  |  | 26/09/2022 | 3269 | 1188.77 | Yes | 1188.77 | 01/03/2024 | 26/11/2024 | 10 | 917.36 | 554.85 | MVS
521 | PURBA BARDHAMAN | PURANGAN PIPED WATER SUPPLY SCHEME | TSM/017795 | SM/18446 | New |  |  |  | 28/12/2022 | 5643 | 2589.76 | Yes | 2589.76 | 03/12/2024 | 02/08/2024 | 13 | 2314.1 | 589.95 | MVS
522 | PURBA BARDHAMAN | AURIA PIPED WATER SUPPLY SCHEME | TSM/017355 | SM/18455 | New |  |  |  | 30/09/2022 | 3373 | 1320.64 | Yes | 1320.64 | 04/04/2025 | 24/07/2023 | 10 | 858.59 | 774.69 | MVS
523 | PURBA BARDHAMAN | MEJHIARI PIPED WATER SUPPLY SCHEME | TSM/017341 | SM/18456 | New |  |  |  | 30/09/2022 | 2700 | 1088.2 | Yes | 1088.2 | 14/01/2025 | 31/07/2023 | 15 | 656.9 | 620.26 | MVS
524 | PURBA BARDHAMAN | LAKSHIMPUR PWSS | TSM/017132 | SM/18457 | New |  |  |  | 30/09/2022 | 2881 | 1048.15 | Yes | 1048.15 | 03/10/2024 | 04/10/2023 | 8 | 748.28 | 247.03 | MVS
525 | PURBA BARDHAMAN | AMUL PIPED WATER SUPPLY SCHEME | TSM/017361 | SM/18458 | New |  |  |  | 30/09/2022 | 3098 | 1267.14 | Yes | 1267.14 | 04/04/2025 | 24/07/2023 | 10 | 815.35 | 709.24 | MVS
526 | PURBA BARDHAMAN | SIMULIA PIPE WATER SUPPLY SCHEME | TSM/017517 | SM/18459 | New |  |  |  | 30/09/2022 | 2525 | 1023.66 | Yes | 1023.66 | 27/01/2025 | 04/10/2023 | 10 | 782.5 | 332.98 | MVS
527 | PURBA BARDHAMAN | KARUI PIPED WATER SUPPLY SCHEME | TSM/017346 | SM/18460 | New |  |  |  | 30/09/2022 | 3523 | 1346.35 | Yes | 1346.35 | 14/01/2025 | 31/07/2023 | 19 | 956.21 | 873.4 | MVS
528 | PURBA BARDHAMAN | TAHERPUR PIPED WATER SUPPLY SCHEME | TSM/017787 | SM/18478 | New |  |  |  | 16/11/2022 | 9074 | 4015.02 | Yes | 4015.02 | 03/12/2024 | 05/06/2024 | 13 | 1163.34 | 577.84 | MVS
529 | PURBA BARDHAMAN | NANAGAR PIPED WATER SUPPLY SCHEME | TSM/017621 | SM/18479 | New |  |  |  | 16/11/2022 | 2833 | 1161.5 | Yes | 1161.5 | 12/03/2024 | 21/10/2024 | 8 | 162.41 | 211.27 | MVS
530 | PURBA BARDHAMAN | BANDMURA PIPED WATER SUPPLY SCHEME | TSM/017663 | SM/18480 | New |  |  |  | 16/11/2022 | 3491 | 1451.41 | Yes | 1451.41 | 04/04/2025 | 24/04/2025 | 14 | 1082.23 | 300.26 | MVS
531 | PURBA BARDHAMAN | PALISGRAM PIPE WATER SUPPLY SCHEME | TSM/017661 | SM/18481 | New |  |  |  | 16/11/2022 | 3319 | 1222.8 | Yes | 1222.8 | 03/10/2024 | 04/10/2023 | 9 | 792.08 | 134.82 | MVS
532 | PURBA BARDHAMAN | DIGHRA PIPED WATER SUPPLY SCHEME | TSM/017954 | SM/18482 | New |  |  |  | 16/11/2022 | 2767 | 1127.12 | Yes | 1127.12 | 17/03/2025 | 10/08/2023 | 9 | 770.02 | 316.99 | MVS
533 | PURBA BARDHAMAN | KARAJGRAM PIPED WATER SUPPLY SCHEME | TSM/017658 | SM/18483 | New |  |  |  | 16/11/2022 | 2942 | 1319.23 | Yes | 1319.23 | 04/04/2025 | 24/04/2025 | 9 | 709.19 | 272 | MVS
534 | PURBA BARDHAMAN | KHAJURDIHI PIPE WATER SUPPLY SCHEME | TSM/017617 | SM/18484 | New |  |  |  | 16/11/2022 | 3132 | 1133.66 | Yes | 1133.66 | 11/12/2024 | 22/07/2024 | 11 | 1006.44 | 391.84 | MVS
535 | PURBA BARDHAMAN | GIDHGRAM PIPED WATER SUPPLY SCHEME | TSM/017652 | SM/18485 | New |  |  |  | 16/11/2022 | 3309 | 1409.11 | Yes | 1409.11 | 12/03/2024 | 07/08/2023 | 10 | 827.13 | 416.87 | MVS
536 | PURBA BARDHAMAN | REAN PIPED WATER SUPPLY SCHEME | TSM/016298 | SM/18504 | New |  |  |  | 26/09/2022 | 2477 | 1136.79 | Yes | 1136.79 | 17/03/2025 | 03/04/2025 | 7 | 135.55 | 583.67 | MVS
537 | PURBA BARDHAMAN | KHANDRA PIPED WATER SUPPLY SCHEME | TSM/016782 | SM/18505 | New |  |  |  | 26/09/2022 | 3199 | 1127.09 | Yes | 1127.09 | 30/04/2025 | 29/09/2023 | 9 | 234.53 | 271.34 | MVS
538 | PURBA BARDHAMAN | BIJUR PIPED WATER SUPPLY SCHEME | TSM/015773 | SM/18605 | New |  |  |  | 09/09/2022 | 2607 | 1119.15 | Yes | 1119.15 | 17/03/2025 | 03/04/2025 | 9 | 111.51 | 416.62 | MVS
539 | PURBA BARDHAMAN | BERUGRAM PIPED WATER SUPPLY SCHEME | TSM/015794 | SM/18606 | New |  |  |  | 09/09/2022 | 3294 | 1245.1 | Yes | 1245.1 | 03/10/2024 | 30/04/2025 | 14 | 1002.8 | 349.89 | MVS
540 | PURBA BARDHAMAN | SULTANPUR PIPED WATER SUPPLY SCHEME | TSM/015811 | SM/18607 | New |  |  |  | 09/09/2022 | 2849 | 1246.66 | Yes | 1246.66 | 03/10/2024 | 01/11/2023 | 9 | 987.44 | 349.83 | MVS
541 | PURBA BARDHAMAN | BISHNUPUR PIPED WATER SUPPLY SCHEME | TSM/015777 | SM/18608 | New |  |  |  | 09/09/2022 | 3799 | 1610.96 | Yes | 1610.96 | 17/03/2025 | 03/04/2025 | 12 | 1046.6 | 792.53 | MVS
542 | PURBA BARDHAMAN | CHANCHAL PIPED WATER SUPPLY SCHEME | TSM/015774 | SM/18609 | New |  |  |  | 09/09/2022 | 3013 | 1327.85 | Yes | 1327.85 | 01/03/2024 | 17/12/2024 | 10 | 903.88 | 287.87 | MVS
543 | PURBA BARDHAMAN | SANUI PIPED WATER SUPPLY SCHEME | TSM/015759 | SM/18610 | New |  |  |  | 09/09/2022 | 3764 | 1535.64 | Yes | 1535.64 | 03/10/2024 | 28/05/2024 | 11 | 1067.24 | 334.27 | MVS
544 | PURBA BARDHAMAN | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | TSM/021381 | SM/18679 | New |  |  |  | 10/03/2023 | 7647 | 4311.81 | Yes | 4311.81 | 03/12/2024 | 22/04/2024 | 14 | 1707.06 | 541.89 | MVS
545 | PURBA BARDHAMAN | NUDIPUR PIPED WATER SUPPLY SCHEME | TSM/015771 | SM/18834 | New |  |  |  | 09/09/2022 | 2769 | 1111.74 | Yes | 1111.74 | 12/09/2024 | 30/07/2024 | 11 | 736.56 | 100.57 | MVS
546 | PURBA BARDHAMAN | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. | TSM/019253 | SM/19113 | Augmentation |  |  |  | 10/03/2023 | 0 | 123.42 | Yes | 123.42 |  | 18/06/2024 | 4 | 118.01 | 1.85 | MVS
Total | [9 empty] | 1155377 | 323255.37 |  | 323255.37 |  |  | 5397 | 220618.65 | 139640.28