## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | HOOGHLY | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | TSM/005640 | SM/06754 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/08/2020 | 1236 | 73.81 | Yes | 73.81 |  | 17/12/2020 | 5 | 41.9 | 70.56 | MVS
2 | HOOGHLY | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | TSM/005629 | SM/06755 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) |  | 28/08/2020 | 1522 | 99.95 | Yes | 99.95 | 22/02/2024 | 26/02/2021 | 5 | 85.08 | 99.17 | MVS
3 | HOOGHLY | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) | TSM/005630 | SM/06756 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/08/2020 | 1286 | 99.92 | Yes | 99.92 |  | 24/11/2020 | 5 | 97.99 | 184.61 | MVS
4 | HOOGHLY | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 1374 nos Functional Household Tap Connection(FHTC) | TSM/005632 | SM/06757 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) |  | 28/08/2020 | 3925 | 99.73 | Yes | 99.73 | 02/03/2023 | 08/12/2020 | 1 | 4.98 | 12.55 | MVS
5 | HOOGHLY | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Rajarambati, Talandu, Taragun Mouza of Digsui-Heora (Zone-II) PWSS | TSM/005635 | SM/06758 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) |  | 28/08/2020 | 984 | 74.68 | Yes | 74.68 |  | 19/01/2022 | 1 | 29.43 | 29.43 | MVS
6 | HOOGHLY | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme | TSM/005638 | SM/06759 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/08/2020 | 511 | 40.46 | Yes | 40.46 | 03/11/2021 | 15/02/2021 | 2 | 24.19 | 77.81 | MVS
7 | HOOGHLY | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) | TSM/005633 | SM/06760 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/08/2020 | 1263 | 43.92 | Yes | 43.92 |  | 27/04/2022 | 2 | 13.77 | 13.77 | MVS
8 | HOOGHLY | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | TSM/005634 | SM/06761 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) |  | 28/08/2020 | 1065 | 83.39 | Yes | 83.39 |  | 19/01/2022 | 6 | 60.65 | 122.51 | MVS
9 | HOOGHLY | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | TSM/005637 | SM/06762 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/08/2020 | 1187 | 87.72 | Yes | 87.72 |  | 01/12/2021 | 3 | 58.51 | 85.51 | MVS
10 | HOOGHLY | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | TSM/005631 | SM/06763 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/08/2020 | 1342 | 99.47 | Yes | 99.47 |  | 26/04/2023 | 3 | 46.79 | 109.06 | MVS
11 | HOOGHLY | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | TSM/005636 | SM/06764 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/08/2020 | 976 | 70.7 | Yes | 70.7 | 03/10/2024 | 24/11/2020 | 6 | 78.16 | 77.5 | MVS
12 | HOOGHLY | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | TSM/005642 | SM/06765 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/08/2020 | 1089 | 89.54 | Yes | 89.54 | 03/10/2024 | 26/09/2022 | 8 | 75 | 96.23 | MVS
13 | HOOGHLY | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | TSM/005639 | SM/06766 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) |  | 28/08/2020 | 3814 | 93.4 | Yes | 93.4 | 12/02/2025 | 17/12/2020 | 8 | 157.17 | 99.51 | MVS
14 | HOOGHLY | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | TSM/005641 | SM/06767 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/08/2020 | 1190 | 99.51 | Yes | 99.51 |  | 24/11/2020 | 9 | 40.77 | 100.18 | MVS
15 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | TSM/006249 | SM/06987 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) |  | 25/09/2020 | 1435 | 92.65 | Yes | 92.65 |  | 03/02/2021 | 4 | 58.57 | 58.57 | MVS
16 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar Mouza of Borhol Zone-II Water Supply Scheme | TSM/006259 | SM/06988 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) |  | 25/09/2020 | 1189 | 75.19 | Yes | 75.19 |  | 17/12/2020 | 1 | 46.41 | 0 | MVS
17 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | TSM/006261 | SM/06989 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 2215 | 57.3 | Yes | 57.3 |  | 12/11/2021 | 3 | 97.6 | 20.6 | MVS
18 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme | TSM/006262 | SM/06990 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 2215 | 80.57 | Yes | 80.57 |  | 17/12/2020 | 3 | 157.56 | 160.04 | MVS
19 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | TSM/006273 | SM/06991 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 25/09/2020 | 1287 | 83.37 | Yes | 83.37 |  | 14/12/2021 | 5 | 77.28 | 120.94 | MVS
20 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | TSM/006263 | SM/06992 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 25/09/2020 | 1695 | 98.98 | Yes | 98.98 |  | 20/12/2021 | 8 | 194.92 | 75.4 | MVS
21 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | TSM/006266 | SM/06993 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 25/09/2020 | 1259 | 79.51 | Yes | 79.51 |  | 17/12/2020 | 5 | 53.03 | 55.66 | MVS
22 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio | TSM/006267 | SM/06994 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 2096 | 68.52 | Yes | 68.52 |  | 12/04/2021 | 3 | 88.7 | 136 | MVS
23 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme | TSM/006264 | SM/07149 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 1107 | 77.24 | Yes | 77.24 |  | 07/04/2022 | 4 | 65.25 | 95.84 | MVS
24 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under | TSM/006265 | SM/07150 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 803 | 56.16 | Yes | 56.16 |  | 02/02/2021 | 2 | 20.06 | 10.01 | MVS
25 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | TSM/006268 | SM/07151 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 2096 | 69.81 | Yes | 69.81 |  | 12/11/2021 | 6 | 81.28 | 74.65 | MVS
26 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | TSM/006678 | SM/07436 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 5421 | 288.46 | Yes | 288.46 | 31/01/2024 | 06/05/2022 | 16 | 285.95 | 313.56 | MVS
27 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. | TSM/006703 | SM/07437 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 4968 | 278.22 | Yes | 278.22 | 28/10/2024 | 19/04/2023 | 12 | 346.95 | 192.61 | MVS
28 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. | TSM/006702 | SM/07438 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) |  | 04/12/2020 | 2082 | 272.67 | Yes | 272.67 | 22/02/2023 | 26/11/2021 | 2 | 1.16 | 0.08 | MVS
29 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | TSM/006697 | SM/07439 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 04/12/2020 | 2472 | 157.36 | Yes | 157.36 |  | 10/03/2022 | 6 | 184.59 | 170.12 | MVS
30 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | TSM/006686 | SM/07440 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 3860 | 230.1 | Yes | 230.1 | 02/03/2023 | 10/05/2021 | 7 | 155.48 | 197.9 | MVS
31 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | TSM/006688 | SM/07441 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 2048 | 128.62 | Yes | 128.62 |  | 15/02/2021 | 6 | 155.25 | 106.45 | MVS
32 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | TSM/006691 | SM/07442 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 1961 | 123.87 | Yes | 123.87 |  | 14/12/2021 | 9 | 114.85 | 130.93 | MVS
33 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | TSM/006693 | SM/07443 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 1951 | 115.31 | Yes | 115.31 |  | 07/03/2022 | 10 | 110.18 | 174.03 | MVS
34 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | TSM/006272 | SM/07460 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 25/09/2020 | 2391 | 145.28 | Yes | 145.28 | 03/10/2024 | 21/07/2025 | 14 | 142 | 191.76 | MVS
35 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | TSM/006271 | SM/07461 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 1814 | 111.14 | Yes | 111.14 | 03/10/2024 | 02/11/2021 | 9 | 104.37 | 113.28 | MVS
36 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | TSM/006270 | SM/07462 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 25/09/2020 | 3233 | 184.15 | Yes | 184.15 | 20/11/2024 | 05/04/2023 | 10 | 177.85 | 106.59 | MVS
37 | HOOGHLY | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | TSM/006269 | SM/07463 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 25/09/2020 | 2123 | 130.74 | Yes | 130.74 |  | 07/04/2022 | 6 | 214.25 | 202.87 | MVS
38 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | TSM/006676 | SM/07534 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 04/12/2020 | 1112 | 72.23 | Yes | 72.23 |  | 01/12/2021 | 11 | 95.11 | 120.33 | MVS
39 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | TSM/006681 | SM/07535 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 04/12/2020 | 883 | 57.39 | Yes | 57.39 |  | 19/01/2022 | 7 | 52.5 | 80.01 | MVS
40 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | TSM/006708 | SM/07536 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 04/12/2020 | 1270 | 81.79 | Yes | 81.79 |  | 03/09/2021 | 7 | 133.12 | 114.43 | MVS
41 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | TSM/006707 | SM/07537 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 1515 | 95.57 | Yes | 95.57 |  | 15/02/2021 | 13 | 126.87 | 85.55 | MVS
42 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | TSM/006706 | SM/07538 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 502 | 32.62 | Yes | 32.62 |  | 15/02/2021 | 4 | 37.79 | 21.83 | MVS
43 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. | TSM/006705 | SM/07539 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 540 | 35.08 | Yes | 35.08 | 08/06/2023 | 10/05/2021 | 6 | 66.67 | 35.08 | MVS
44 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | TSM/006701 | SM/07540 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 1068 | 66.84 | Yes | 66.84 |  | 15/02/2021 | 7 | 83.16 | 55.44 | MVS
45 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME | TSM/006699 | SM/07541 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 04/12/2020 | 893 | 56.68 | Yes | 56.68 |  | 01/12/2021 | 5 | 52.15 | 96.09 | MVS
46 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | TSM/006695 | SM/07542 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 04/12/2020 | 1488 | 95.57 | Yes | 95.57 |  | 14/12/2021 | 4 | 110.24 | 105.42 | MVS
47 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | TSM/006684 | SM/07543 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 04/12/2020 | 1348 | 86.15 | Yes | 86.15 |  | 03/06/2022 | 4 | 74.78 | 93.13 | MVS
48 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | TSM/007125 | SM/07944 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 745 | 48.29 | Yes | 48.29 | 22/05/2023 | 10/04/2023 | 17 | 60.53 | 57.8 | MVS
49 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | TSM/007126 | SM/07945 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 08/01/2021 | 1203 | 74.37 | Yes | 74.37 | 11/04/2025 | 07/04/2022 | 7 | 75.48 | 119.73 | MVS
50 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. | TSM/007127 | SM/07946 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) |  | 08/01/2021 | 3076 | 97.35 | Yes | 97.35 |  | 22/10/2024 | 2 | 44.87 | 94.06 | MVS
51 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. | TSM/007128 | SM/07947 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 2555 | 83.61 | Yes | 83.61 |  | 01/12/2021 | 2 | 57.2 | 57.4 | MVS
52 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | TSM/007129 | SM/07948 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 4046 | 98.47 | Yes | 98.47 | 22/02/2023 | 11/02/2021 | 7 | 111 | 175.32 | MVS
53 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | TSM/007130 | SM/07949 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 2534 | 99.58 | Yes | 99.58 |  | 06/05/2022 | 10 | 110.27 | 118.48 | MVS
54 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | TSM/007131 | SM/07950 | Retrofitting |  |  |  | 08/01/2021 | 2559 | 99.37 | Yes | 99.37 |  | 03/02/2021 | 8 | 119.98 | 176.72 | MVS
55 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | TSM/007132 | SM/07951 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 4320 | 99.86 | Yes | 99.86 | 17/03/2025 | 17/12/2020 | 6 | 162.53 | 174.28 | MVS
56 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | TSM/007139 | SM/07952 | Retrofitting |  |  |  | 08/01/2021 | 3320 | 212.07 | Yes | 212.07 | 17/03/2025 | 06/05/2021 | 9 | 262.68 | 205.83 | MVS
57 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | TSM/007133 | SM/07953 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 2299 | 78.24 | Yes | 78.24 |  | 13/04/2022 | 7 | 74.38 | 110.92 | MVS
58 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | TSM/007134 | SM/07954 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 4296 | 247.47 | Yes | 247.47 |  | 09/07/2024 | 15 | 264.66 | 207.65 | MVS
59 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | TSM/007135 | SM/07955 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 2860 | 166.55 | Yes | 166.55 |  | 06/05/2021 | 5 | 170.04 | 141.43 | MVS
60 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | TSM/007136 | SM/07956 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 3727 | 203.01 | Yes | 203.01 |  | 22/07/2025 | 15 | 205.55 | 233.12 | MVS
61 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. | TSM/007137 | SM/07957 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 2936 | 163.57 | Yes | 163.57 |  | 31/08/2023 | 4 | 47.68 | 84.06 | MVS
62 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | TSM/007138 | SM/07958 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 2122 | 119.68 | Yes | 119.68 | 13/07/2023 | 06/05/2021 | 4 | 117.26 | 109.14 | MVS
63 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. | TSM/007385 | SM/08737 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 10/02/2021 | 2836 | 163.87 | Yes | 163.87 |  | 03/06/2022 | 7 | 78.66 | 66.97 | MVS
64 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | TSM/007386 | SM/08738 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 10/02/2021 | 2305 | 134.58 | Yes | 134.58 | 31/05/2023 | 06/05/2021 | 6 | 125.13 | 120.65 | MVS
65 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | TSM/007387 | SM/08739 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 10/02/2021 | 2939 | 197.26 | Yes | 197.26 |  | 06/05/2021 | 10 | 184.55 | 101.84 | MVS
66 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | TSM/007388 | SM/08740 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) |  | 10/02/2021 | 4056 | 230.84 | Yes | 230.84 |  | 13/04/2022 | 12 | 246.32 | 200.4 | MVS
67 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | TSM/007389 | SM/08741 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/02/2021 | 3700 | 214.13 | Yes | 214.13 | 20/03/2025 | 10/05/2021 | 19 | 208.72 | 130.34 | MVS
68 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | TSM/007390 | SM/08742 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 10/02/2021 | 3011 | 176.84 | Yes | 176.84 | 17/03/2023 | 07/04/2022 | 4 | 89.3 | 164.46 | MVS
69 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | TSM/007483 | SM/08743 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/02/2021 | 2754 | 147.07 | Yes | 147.07 | 03/10/2024 | 29/12/2023 | 8 | 134 | 58.28 | MVS
70 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BHANGAMORA WATER SUPPLY SCHEME. | TSM/007484 | SM/08744 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 19/02/2021 | 1135 | 80.9 | Yes | 80.9 |  | 15/12/2021 | 1 | 40.78 | 48.27 | MVS
71 | HOOGHLY | Chandanpur Piped Water Supply Scheme. | TSM/002250 | SM/08995 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 1105 | 486.65 | Yes | 486.65 | 13/07/2023 | 20/12/2022 | 20 | 554.8 | 395.26 | MVS
72 | HOOGHLY | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | TSM/008215 | SM/09066 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 19/08/2021 | 1625 | 97.91 | Yes | 97.91 |  | 27/10/2021 | 13 | 69.84 | 64.39 | MVS
73 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | TSM/008203 | SM/09067 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 19/08/2021 | 2144 | 131.23 | Yes | 131.23 |  | 03/06/2022 | 6 | 86.6 | 52.39 | MVS
74 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | TSM/008204 | SM/09068 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 19/08/2021 | 1287 | 80.21 | Yes | 80.21 |  | 12/11/2021 | 3 | 31.19 | 14.88 | MVS
75 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. | TSM/008206 | SM/09069 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 1553 | 95.2 | Yes | 95.2 | 17/03/2025 | 27/04/2022 | 2 | 8.42 | 26.71 | MVS
76 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | TSM/008207 | SM/09070 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 3870 | 136.85 | Yes | 136.85 | 02/03/2023 | 23/08/2022 | 9 | 179.33 | 132.86 | MVS
77 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. | TSM/008209 | SM/09071 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 800 | 50.04 | Yes | 50.04 |  | 30/06/2023 | 2 | 5.66 | 23.45 | MVS
78 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. | TSM/008211 | SM/09072 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 3956 | 42.14 | Yes | 42.14 |  | 14/12/2021 | 2 | 18.54 | 31.91 | MVS
79 | HOOGHLY | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008681 | SM/09207 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 15/09/2021 | 0 | 35.42 | Yes | 35.42 |  | 19/04/2023 | 4 | 31.42 | 31 | MVS
80 | HOOGHLY | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008680 | SM/09208 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 15/09/2021 | 0 | 35.42 | Yes | 35.42 | 09/11/2023 | 27/07/2023 | 8 | 29.56 | 6.15 | MVS
81 | HOOGHLY | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | TSM/008682 | SM/09423 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 29/09/2021 | 3352 | 43.82 | Yes | 43.82 | 11/11/2022 | 28/08/2025 | 12 | 56.49 | 34.01 | MVS
82 | HOOGHLY | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008674 | SM/09516 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/10/2021 | 0 | 43.94 | Yes | 43.94 | 08/12/2022 | 02/03/2023 | 12 | 26.06 | 16.67 | MVS
83 | HOOGHLY | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008677 | SM/09517 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 08/10/2021 | 0 | 43.94 | Yes | 43.94 | 08/12/2022 | 26/08/2022 | 10 | 36.52 | 28.53 | MVS
84 | HOOGHLY | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008678 | SM/09604 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 08/10/2021 | 0 | 43.94 | Yes | 43.94 | 12/04/2023 | 02/03/2023 | 5 | 14.42 | 14.42 | MVS
85 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | TSM/008326 | SM/09688 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 19/08/2021 | 1324 | 278.45 | Yes | 278.45 | 18/06/2024 | 25/03/2023 | 13 | 309.02 | 255.66 | MVS
86 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | TSM/008328 | SM/09689 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 1738 | 333.93 | Yes | 333.93 | 18/04/2022 | 17/04/2025 | 12 | 291.81 | 244.57 | MVS
87 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | TSM/008331 | SM/09690 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 1615 | 350.38 | Yes | 350.38 | 29/05/2023 | 20/04/2022 | 11 | 311.09 | 283.89 | MVS
88 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | TSM/008347 | SM/09691 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 2605 | 541.55 | Yes | 541.55 | 04/10/2024 | 20/04/2022 | 11 | 579.93 | 358.29 | MVS
89 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | TSM/008348 | SM/09692 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 19/08/2021 | 2553 | 444.24 | Yes | 444.24 | 03/10/2024 | 29/03/2023 | 15 | 470.47 | 313.26 | MVS
90 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | TSM/008322 | SM/09693 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 19/08/2021 | 3192 | 615.63 | Yes | 615.63 | 03/10/2024 | 18/05/2023 | 24 | 622.18 | 529.77 | MVS
91 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | TSM/008324 | SM/09694 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 19/08/2021 | 4298 | 772.01 | Yes | 772.01 | 11/04/2025 | 20/04/2022 | 27 | 674.64 | 582.16 | MVS
92 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | TSM/008327 | SM/09695 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 19/08/2021 | 3469 | 854.05 | Yes | 854.05 | 18/12/2024 | 17/04/2025 | 27 | 805.31 | 657.44 | MVS
93 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | TSM/008329 | SM/09698 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 2088 | 620.51 | Yes | 620.51 | 11/04/2025 | 02/06/2022 | 15 | 421.3 | 264.41 | MVS
94 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008316 | SM/09772 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 5146 | 337.05 | Yes | 337.05 | 17/03/2025 | 31/05/2022 | 24 | 226.89 | 285.06 | MVS
95 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008317 | SM/09773 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 1577 | 95.96 | Yes | 95.96 | 11/04/2025 | 19/09/2024 | 13 | 111.76 | 56.59 | MVS
96 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008318 | SM/09774 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 2826 | 166.04 | Yes | 166.04 | 01/03/2024 | 21/06/2024 | 3 | 72.4 | 9.65 | MVS
97 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008319 | SM/09775 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 4182 | 234.97 | Yes | 234.97 | 02/03/2023 | 06/05/2021 | 5 | 139.31 | 150.43 | MVS
98 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008320 | SM/09776 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 2181 | 130.24 | Yes | 130.24 |  | 21/09/2022 | 1 | 87.34 | 99.97 | MVS
99 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008321 | SM/09777 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 2123 | 131.1 | Yes | 131.1 |  | 31/05/2022 | 4 | 94.74 | 89.15 | MVS
100 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | TSM/008323 | SM/09790 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 2619 | 508.53 | Yes | 508.53 | 13/09/2024 | 06/11/2023 | 18 | 472.05 | 258.44 | MVS
101 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | TSM/009205 | SM/09791 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/11/2021 | 2698 | 885.42 | Yes | 885.42 | 18/06/2024 | 20/04/2022 | 29 | 871 | 626.01 | MVS
102 | HOOGHLY | Bilaspur Piped Water Supply Scheme. | TSM/004576 | SM/09825 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 08/01/2021 | 8919 | 2255.49 | Yes | 2255.49 | 11/04/2025 | 26/09/2024 | 59 | 1848.57 | 1373.49 | MVS
103 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | TSM/009212 | SM/09982 | Augmentation | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 22/11/2021 | 5180 | 1481.84 | Yes | 1481.84 | 18/12/2024 | 15/06/2023 | 43 | 1374.34 | 1130.93 | MVS
104 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | TSM/009209 | SM/09983 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/11/2021 | 4500 | 1263.17 | Yes | 1263.17 | 11/04/2025 | 26/09/2024 | 14 | 948.89 | 886.12 | MVS
105 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | TSM/009193 | SM/09984 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/11/2021 | 4914 | 1334.97 | Yes | 1334.97 | 07/03/2025 | 03/10/2024 | 40 | 1314.76 | 1219.21 | MVS
106 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | TSM/009196 | SM/10004 | Augmentation | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 22/11/2021 | 5595 | 1553.96 | Yes | 1553.96 | 31/07/2024 | 26/09/2024 | 19 | 1266.76 | 955.39 | MVS
107 | HOOGHLY | Augmentation of Champadanga Water Supply Scheme | TSM/009191 | SM/10005 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 22/11/2021 | 6374 | 1532.55 | Yes | 1532.55 | 17/10/2023 | 20/12/2022 | 42 | 1613.83 | 1157.37 | MVS
108 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | TSM/009210 | SM/10022 | Augmentation | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 22/11/2021 | 7976 | 2250.51 | Yes | 2250.51 | 11/04/2025 | 02/08/2024 | 47 | 2173.35 | 1833.62 | MVS
109 | HOOGHLY | Augmentation of Salepur-Duttapur Water Supply Scheme | TSM/009194 | SM/10023 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 22/11/2021 | 4593 | 1460.01 | Yes | 1460.01 | 12/02/2025 | 23/06/2022 | 24 | 1188.72 | 1091.19 | MVS
110 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME | TSM/009864 | SM/10131 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/12/2021 | 1061 | 83.52 | Yes | 83.52 | 17/03/2025 | 15/02/2021 | 2 | 54.34 | 52.06 | MVS
111 | HOOGHLY | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte | TSM/009779 | SM/10132 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/12/2021 | 2111 | 126.17 | Yes | 126.17 |  | 10/03/2022 | 2 | 84.89 | 80.4 | MVS
112 | HOOGHLY | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | TSM/009778 | SM/10133 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/12/2021 | 1702 | 99.96 | Yes | 99.96 |  | 28/10/2022 | 4 | 97.04 | 97.04 | MVS
113 | HOOGHLY | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | TSM/009772 | SM/10134 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/12/2021 | 1386 | 88.95 | Yes | 88.95 |  | 21/09/2022 | 4 | 60.64 | 57.55 | MVS
114 | HOOGHLY | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | TSM/009771 | SM/10135 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/12/2021 | 2163 | 137.19 | Yes | 137.19 |  | 16/08/2022 | 3 | 85.21 | 84.42 | MVS
115 | HOOGHLY | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | TSM/009766 | SM/10136 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/12/2021 | 1694 | 104.32 | Yes | 104.32 |  | 10/03/2022 | 4 | 76.63 | 48.85 | MVS
116 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | TSM/008325 | SM/10338 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 19/08/2021 | 10123 | 1306.66 | Yes | 1306.66 | 11/04/2025 | 03/10/2024 | 75 | 1193.4 | 767.35 | MVS
117 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | TSM/008330 | SM/10339 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 19/08/2021 | 5839 | 1352.9 | Yes | 1352.9 | 11/04/2025 | 31/07/2023 | 33 | 1498.94 | 611.31 | MVS
118 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | TSM/008349 | SM/10340 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 19/08/2021 | 9147 | 1822.88 | Yes | 1822.88 | 04/10/2024 | 19/04/2023 | 32 | 1688.07 | 1266.95 | MVS
119 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | TSM/008350 | SM/10341 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 0 | 1037.36 | Yes | 1037.36 | 17/02/2023 | 19/09/2023 | 27 | 922.5 | 700.09 | MVS
120 | HOOGHLY | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | TSM/004281 | SM/10357 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 19/08/2021 | 2878 | 777.8 | Yes | 777.8 |  | 01/04/2022 | 9 | 567.56 | 469.55 | MVS
121 | HOOGHLY | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | TSM/009987 | SM/10451 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 27/01/2022 | 3308 | 989.36 | Yes | 989.36 | 31/01/2024 | 31/07/2023 | 35 | 813.5 | 554.4 | MVS
122 | HOOGHLY | Augmentation of Chanparai Water Supply Scheme | TSM/009960 | SM/10467 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 27/01/2022 | 1711 | 414.46 | Yes | 414.46 | 08/06/2023 | 04/04/2025 | 11 | 298.37 | 290.53 | MVS
123 | HOOGHLY | Augmentation of Polba Water Supply Scheme | TSM/009961 | SM/10468 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 27/01/2022 | 4025 | 963.64 | Yes | 963.64 | 30/07/2024 | 26/09/2023 | 44 | 935.23 | 817.88 | MVS
124 | HOOGHLY | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010361 | SM/11001 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 16/03/2022 | 2289 | 128.04 | Yes | 128.04 |  | 19/10/2022 | 2 | 67.36 | 59.87 | MVS
125 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | TSM/009990 | SM/11002 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 16/03/2022 | 4068 | 371.11 | Yes | 371.11 | 08/06/2023 | 22/03/2023 | 6 | 637.32 | 145.59 | MVS
126 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010356 | SM/11003 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 16/03/2022 | 800 | 51.92 | Yes | 51.92 |  | 07/04/2022 | 3 | 31.88 | 14.75 | MVS
127 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | TSM/010297 | SM/11004 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/03/2022 | 4123 | 244.08 | Yes | 244.08 | 11/04/2025 | 12/08/2023 | 11 | 241.16 | 190.88 | MVS
128 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | TSM/009992 | SM/11005 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 16/03/2022 | 4206 | 270.62 | Yes | 270.62 |  | 02/05/2024 | 6 | 230.67 | 231.07 | MVS
129 | HOOGHLY | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010364 | SM/11006 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/03/2022 | 1224 | 77.49 | Yes | 77.49 |  | 13/04/2022 | 2 | 5.21 | 4.69 | MVS
130 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | TSM/009991 | SM/11165 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 16/03/2022 | 5831 | 264.04 | Yes | 264.04 |  | 07/04/2022 | 8 | 167.79 | 140.92 | MVS
131 | HOOGHLY | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | TSM/010115 | SM/11166 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 17/02/2022 | 3961 | 895.83 | Yes | 895.83 | 29/07/2024 | 15/12/2022 | 25 | 823.99 | 614.9 | MVS
132 | HOOGHLY | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | TSM/010116 | SM/11167 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 17/02/2022 | 1843 | 494.57 | Yes | 494.57 | 15/12/2022 | 06/04/2023 | 12 | 417.09 | 238.65 | MVS
133 | HOOGHLY | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010362 | SM/11225 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 16/03/2022 | 4588 | 271.91 | Yes | 271.91 |  | 23/06/2022 | 5 | 81 | 44.6 | MVS
134 | HOOGHLY | ASTARA PIPED WATER SUPPLY SCHEME | TSM/010469 | SM/11286 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/03/2022 | 1992 | 646.77 | Yes | 646.77 | 12/02/2025 | 22/06/2023 | 18 | 607.97 | 519.07 | MVS
135 | HOOGHLY | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | TSM/010839 | SM/11287 | New | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 16/03/2022 | 180 | 99.57 | Yes | 99.57 | 16/01/2024 | 21/08/2023 | 10 | 142.6 | 92.21 | MVS
136 | HOOGHLY | BHANJIPUR PIPED WATER SUPPLY SCHEME | TSM/010468 | SM/11288 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/03/2022 | 2533 | 759.23 | Yes | 759.23 | 21/08/2023 | 12/08/2023 | 14 | 643.45 | 397.29 | MVS
137 | HOOGHLY | GAURIBATI PIPED WATER SUPPLY SCHEME | TSM/010471 | SM/11289 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/03/2022 | 1387 | 464.35 | Yes | 464.35 | 22/08/2023 | 12/08/2023 | 14 | 468.65 | 345.63 | MVS
138 | HOOGHLY | HARAT PIPED WATER SUPPLY SCHEME | TSM/010834 | SM/11290 | New | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 16/03/2022 | 1913 | 668.44 | Yes | 668.44 | 16/05/2023 | 21/06/2023 | 15 | 727.49 | 376.66 | MVS
139 | HOOGHLY | NAITA PIPED WATER SUPPLY SCHEME | TSM/010835 | SM/11291 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/03/2022 | 2196 | 817.35 | Yes | 817.35 | 18/07/2023 | 12/08/2023 | 16 | 798.9 | 412.67 | MVS
140 | HOOGHLY | PANRRA PIPED WATER SUPPLY SCHEME | TSM/010824 | SM/11292 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/03/2022 | 2998 | 987.53 | Yes | 987.53 | 16/05/2023 | 04/04/2023 | 10 | 835.37 | 422.48 | MVS
141 | HOOGHLY | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | TSM/010827 | SM/11293 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/03/2022 | 881 | 385.02 | Yes | 385.02 | 18/07/2023 | 12/09/2024 | 16 | 441.01 | 307.06 | MVS
142 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011261 | SM/11461 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/03/2022 | 883 | 329.51 | Yes | 329.51 | 31/07/2024 | 18/05/2023 | 16 | 328.07 | 239.78 | MVS
143 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011280 | SM/11462 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/03/2022 | 2600 | 765.32 | Yes | 765.32 | 21/07/2023 | 22/08/2022 | 14 | 574.34 | 437.14 | MVS
144 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011273 | SM/11463 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/03/2022 | 3369 | 974.92 | Yes | 974.92 | 11/04/2025 | 21/02/2023 | 25 | 1091.81 | 630.92 | MVS
145 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011268 | SM/11464 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/03/2022 | 1500 | 369.78 | Yes | 369.78 | 11/04/2025 | 30/08/2022 | 15 | 283.49 | 153.18 | MVS
146 | HOOGHLY | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | TSM/011257 | SM/11465 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 30/03/2022 | 1770 | 307.35 | Yes | 307.35 | 30/07/2024 | 06/11/2023 | 18 | 263 | 218.66 | MVS
147 | HOOGHLY | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | TSM/011236 | SM/11466 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | 30/03/2022 | 2923 | 590.5 | Yes | 590.5 | 11/04/2025 | 15/12/2022 | 21 | 409.89 | 329.55 | MVS
148 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | TSM/011255 | SM/11467 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/03/2022 | 2350 | 552.74 | Yes | 552.74 | 18/07/2023 | 18/05/2023 | 19 | 662.94 | 381.03 | MVS
149 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011249 | SM/11468 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/03/2022 | 2800 | 709.16 | Yes | 709.16 | 11/04/2025 | 22/08/2023 | 24 | 660.94 | 467.31 | MVS
150 | HOOGHLY | SIRAZPUR PIPED WATER SUPPLY SCHEME | TSM/011542 | SM/11580 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 25/04/2022 | 2119 | 811.72 | Yes | 811.72 | 21/08/2023 | 11/08/2023 | 11 | 689.4 | 334.45 | MVS
151 | HOOGHLY | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | TSM/011547 | SM/11581 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 25/04/2022 | 1489 | 695.99 | Yes | 695.99 | 17/10/2023 | 26/04/2023 | 23 | 576.18 | 266.29 | MVS
152 | HOOGHLY | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | TSM/011485 | SM/11582 | New | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 25/04/2022 | 1724 | 681.54 | Yes | 681.54 | 31/07/2024 | 02/05/2023 | 9 | 664.64 | 390.04 | MVS
153 | HOOGHLY | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | TSM/011514 | SM/11583 | New | Hooghly Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | 25/04/2022 | 1656 | 997.69 | Yes | 997.69 |  | 27/12/2022 | 8 | 1131.8 | 695.18 | MVS
154 | HOOGHLY | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT | TSM/011523 | SM/11584 | New | Hooghly Division | Assistant Engineer(HQ) |  | 25/04/2022 | 1692 | 940.95 | Yes | 940.95 |  | 15/05/2023 | 5 | 2164.95 | 728.6 | MVS
155 | HOOGHLY | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT | TSM/011522 | SM/11621 | New | Hooghly Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | 25/04/2022 | 1850 | 996.92 | Yes | 996.92 | 24/05/2023 | 30/12/2022 | 5 | 1646.84 | 509.25 | MVS
156 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | TSM/011917 | SM/11866 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 20/05/2022 | 2063 | 689.8 | Yes | 689.8 | 01/03/2024 | 10/07/2024 | 21 | 630.31 | 529.86 | MVS
157 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | TSM/011916 | SM/11867 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 20/05/2022 | 1870 | 446.85 | Yes | 446.85 | 31/01/2024 | 14/06/2024 | 26 | 473.81 | 410.31 | MVS
158 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | TSM/011915 | SM/11868 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 20/05/2022 | 2962 | 837.42 | Yes | 837.42 | 03/02/2023 | 17/04/2023 | 16 | 635.19 | 519.57 | MVS
159 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | TSM/011627 | SM/11924 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 20/05/2022 | 2217 | 748.82 | Yes | 748.82 | 20/11/2024 | 21/02/2022 | 9 | 643.16 | 487.22 | MVS
160 | HOOGHLY | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | TSM/009988 | SM/11969 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 27/01/2022 | 4827 | 1096.03 | Yes | 1096.03 | 17/10/2023 | 14/06/2024 | 30 | 829.32 | 615.54 | MVS
161 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | TSM/011098 | SM/11990 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 5823 | 376.63 | Yes | 376.63 | 27/12/2024 | 16/12/2022 | 8 | 270.22 | 188.65 | MVS
162 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | TSM/011090 | SM/11997 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 05/07/2022 | 3456 | 213.94 | Yes | 213.94 | 02/03/2023 | 19/04/2023 | 3 | 90.3 | 73.26 | MVS
163 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME | TSM/010984 | SM/11998 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 2241 | 140.93 | Yes | 140.93 |  | 06/04/2023 | 2 | 25.49 | 25.49 | MVS
164 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BATANAL WATER SUPPLY SCHEME | TSM/011094 | SM/11999 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 3492 | 218.68 | Yes | 218.68 | 29/07/2024 | 29/04/2022 | 1 | 73.68 | 73.68 | MVS
165 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | TSM/011111 | SM/12000 | Retrofitting | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 05/07/2022 | 2300 | 148.75 | Yes | 148.75 | 22/02/2024 | 17/09/2024 | 12 | 156.63 | 40.78 | MVS
166 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME | TSM/010987 | SM/12001 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 1365 | 88.46 | Yes | 88.46 | 09/02/2023 | 23/08/2024 | 4 | 61.41 | 59.67 | MVS
167 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | TSM/010980 | SM/12002 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 3383 | 217.2 | Yes | 217.2 | 09/02/2023 | 20/04/2023 | 6 | 127.18 | 97.18 | MVS
168 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) | TSM/010979 | SM/12012 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 05/07/2022 | 735 | 47.77 | Yes | 47.77 |  | 21/09/2022 | 2 | 51.06 | 45.38 | MVS
169 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SRIPUR-BALAGARH WATER SUPPLY SCHEME | TSM/011088 | SM/12013 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 05/07/2022 | 3502 | 199.03 | Yes | 199.03 |  | 14/12/2021 | 1 | 30.15 | 30.15 | MVS
170 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | TSM/011091 | SM/12014 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 3119 | 197.98 | Yes | 197.98 | 27/03/2023 | 19/07/2023 | 1 | 94.38 | 0 | MVS
171 | HOOGHLY | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | TSM/010985 | SM/12015 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 05/07/2022 | 2620 | 163.75 | Yes | 163.75 | 07/01/2025 | 29/04/2022 | 5 | 156.41 | 117.86 | MVS
172 | HOOGHLY | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | TSM/014829 | SM/12228 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 22/08/2022 | 3126 | 741.99 | Yes | 741.99 | 29/07/2024 | 26/06/2024 | 11 | 529.16 | 298.86 | MVS
173 | HOOGHLY | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/015004 | SM/12229 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 3651 | 823.3 | Yes | 823.3 | 20/12/2022 | 17/08/2023 | 7 | 720.13 | 436.08 | MVS
174 | HOOGHLY | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014725 | SM/12232 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 22/08/2022 | 1752 | 762.35 | Yes | 762.35 | 31/07/2024 | 03/10/2024 | 8 | 604.93 | 121.74 | MVS
175 | HOOGHLY | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014722 | SM/12233 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 22/08/2022 | 2578 | 964.48 | Yes | 964.48 | 21/12/2022 | 19/10/2023 | 10 | 753.76 | 421.65 | MVS
176 | HOOGHLY | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014721 | SM/12235 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 22/08/2022 | 3207 | 981.16 | Yes | 981.16 | 29/07/2024 | 10/09/2024 | 11 | 836.77 | 342.11 | MVS
177 | HOOGHLY | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/015006 | SM/12238 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 2145 | 533.98 | Yes | 533.98 | 22/11/2022 | 30/03/2023 | 8 | 528.94 | 458.33 | MVS
178 | HOOGHLY | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | TSM/014163 | SM/12239 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 2266 | 649.37 | Yes | 649.37 | 08/02/2024 | 10/08/2023 | 6 | 640.36 | 180.36 | MVS
179 | HOOGHLY | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | TSM/014192 | SM/12242 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 472 | 286.66 | Yes | 286.66 | 20/01/2025 | 15/03/2023 | 9 | 289.43 | 189.58 | MVS
180 | HOOGHLY | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/015007 | SM/12243 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 1963 | 538.93 | Yes | 538.93 | 20/12/2022 | 17/08/2023 | 7 | 495.8 | 274.95 | MVS
181 | HOOGHLY | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014177 | SM/12245 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 2741 | 688.42 | Yes | 688.42 | 08/02/2024 | 10/08/2023 | 7 | 723 | 323.92 | MVS
182 | HOOGHLY | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014298 | SM/12246 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 3344 | 700.75 | Yes | 700.75 | 20/12/2022 | 12/08/2023 | 8 | 622.75 | 295.87 | MVS
183 | HOOGHLY | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/015005 | SM/12247 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 1847 | 553.34 | Yes | 553.34 | 22/11/2022 | 20/09/2024 | 8 | 536.92 | 388.49 | MVS
184 | HOOGHLY | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014197 | SM/12248 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 2935 | 671.18 | Yes | 671.18 | 11/04/2025 | 26/09/2024 | 10 | 733.05 | 499.72 | MVS
185 | HOOGHLY | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | TSM/014198 | SM/12249 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 2152 | 659.51 | Yes | 659.51 | 08/02/2024 | 31/07/2024 | 10 | 665.89 | 281.15 | MVS
186 | HOOGHLY | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014199 | SM/12250 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 2029 | 637.12 | Yes | 637.12 | 08/02/2024 | 31/07/2024 | 8 | 638.21 | 327.54 | MVS
187 | HOOGHLY | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014296 | SM/12251 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 2417 | 605.31 | Yes | 605.31 | 20/12/2022 | 17/08/2023 | 7 | 555.34 | 367.89 | MVS
188 | HOOGHLY | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014551 | SM/12252 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 1695 | 523.15 | Yes | 523.15 | 20/12/2022 | 17/08/2023 | 7 | 587.28 | 188.5 | MVS
189 | HOOGHLY | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014554 | SM/12253 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 1882 | 576.69 | Yes | 576.69 | 20/12/2022 | 17/08/2023 | 6 | 566.74 | 510.82 | MVS
190 | HOOGHLY | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014299 | SM/12254 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 2763 | 608.75 | Yes | 608.75 | 14/07/2023 | 17/07/2023 | 9 | 610.25 | 168.4 | MVS
191 | HOOGHLY | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | TSM/014302 | SM/12255 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 3145 | 689.12 | Yes | 689.12 | 22/11/2022 | 17/10/2023 | 9 | 644.07 | 509.56 | MVS
192 | HOOGHLY | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014307 | SM/12256 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 3235 | 908.93 | Yes | 908.93 | 20/12/2022 | 17/08/2023 | 8 | 712.21 | 462.83 | MVS
193 | HOOGHLY | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014304 | SM/12257 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 3762 | 811.45 | Yes | 811.45 | 20/12/2022 | 17/08/2023 | 8 | 726.68 | 409.54 | MVS
194 | HOOGHLY | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | TSM/014418 | SM/12258 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 837 | 390.37 | Yes | 390.37 | 22/11/2022 | 30/03/2023 | 6 | 312.19 | 201.7 | MVS
195 | HOOGHLY | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK | TSM/014410 | SM/12259 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 2185 | 563.79 | Yes | 563.79 | 22/11/2022 | 30/03/2023 | 6 | 506.96 | 375.03 | MVS
196 | HOOGHLY | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014409 | SM/12260 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 2969 | 653.17 | Yes | 653.17 | 20/12/2022 | 17/08/2023 | 6 | 427.88 | 328.27 | MVS
197 | HOOGHLY | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014395 | SM/12262 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 2542 | 749.81 | Yes | 749.81 | 20/12/2022 | 27/09/2024 | 8 | 618.62 | 368.06 | MVS
198 | HOOGHLY | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014425 | SM/12263 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 3116 | 831.48 | Yes | 831.48 | 14/07/2023 | 17/07/2023 | 9 | 612.45 | 366.57 | MVS
199 | HOOGHLY | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014552 | SM/12265 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 4371 | 948.04 | Yes | 948.04 | 20/12/2022 | 17/08/2023 | 14 | 793.61 | 449.59 | MVS
200 | HOOGHLY | BASUBATI PIPED WATER SUPPLY SCHEME | TSM/011423 | SM/12365 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 25/04/2022 | 3236 | 1115.75 | Yes | 1115.75 | 07/03/2025 | 22/06/2023 | 14 | 911.69 | 354.02 | MVS
201 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | TSM/009964 | SM/12369 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 17/02/2022 | 12977 | 3756.01 | Yes | 3756.01 | 07/03/2025 | 19/05/2025 | 38 | 2993.18 | 1242.6 | MVS
202 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | TSM/009198 | SM/12370 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/03/2022 | 4599 | 1268.51 | Yes | 1268.51 | 07/03/2025 | 19/05/2025 | 18 | 1118.56 | 832.6 | MVS
203 | HOOGHLY | NANDA PIPED WATER SUPPLY SCHEME | TSM/011424 | SM/12567 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 25/04/2022 | 2460 | 1120.63 | Yes | 1120.63 | 07/03/2025 | 08/04/2024 | 15 | 937.08 | 504.85 | MVS
204 | HOOGHLY | ATISARA PIPED WATER SUPPLY SCHEME | TSM/010832 | SM/12727 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/03/2022 | 3260 | 1322.35 | Yes | 1322.35 | 07/03/2025 | 26/09/2023 | 22 | 1135.79 | 839.35 | MVS
205 | HOOGHLY | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010507 | SM/12882 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 6938 | 409.9 | Yes | 409.9 | 13/07/2023 | 27/07/2023 | 3 | 80 | 80 | MVS
206 | HOOGHLY | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015532 | SM/13320 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 09/09/2022 | 2300 | 999.62 | Yes | 999.62 | 31/07/2024 | 18/03/2025 | 11 | 786.02 | 400 | MVS
207 | HOOGHLY | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/015540 | SM/13321 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 09/09/2022 | 3505 | 883.11 | Yes | 883.11 | 22/11/2022 | 30/03/2023 | 7 | 768.47 | 657.17 | MVS
208 | HOOGHLY | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015564 | SM/13322 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | 09/09/2022 | 1951 | 862.94 | Yes | 862.94 | 06/03/2023 | 19/10/2023 | 8 | 540.46 | 136.46 | MVS
209 | HOOGHLY | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015562 | SM/13324 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | 09/09/2022 | 2319 | 962.17 | Yes | 962.17 | 31/07/2024 | 19/10/2023 | 8 | 538.93 | 374.22 | MVS
210 | HOOGHLY | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015550 | SM/13325 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 09/09/2022 | 1356 | 647.04 | Yes | 647.04 | 06/03/2023 | 13/11/2024 | 14 | 498.19 | 127.15 | MVS
211 | HOOGHLY | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | TSM/015415 | SM/13333 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 09/09/2022 | 2064 | 928.84 | Yes | 928.84 | 18/06/2024 | 03/10/2024 | 13 | 714.41 | 142.28 | MVS
212 | HOOGHLY | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/015417 | SM/13334 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 09/09/2022 | 2537 | 942.99 | Yes | 942.99 | 31/07/2024 | 18/03/2025 | 15 | 761.77 | 626.28 | MVS
213 | HOOGHLY | PARJANA PIPED WATER SUPPLY SCHEME | TSM/015453 | SM/13335 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 09/09/2022 | 2350 | 950 | Yes | 950 | 29/11/2022 | 17/05/2023 | 9 | 762.75 | 551.32 | MVS
214 | HOOGHLY | BADE DIGARIA PIPED WATER SUPPLY SCHEME | TSM/015480 | SM/13336 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 09/09/2022 | 1666 | 657.34 | Yes | 657.34 | 07/09/2023 | 12/04/2023 | 12 | 522.39 | 347.22 | MVS
215 | HOOGHLY | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014698 | SM/13337 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 09/09/2022 | 2648 | 769.29 | Yes | 769.29 | 14/07/2023 | 26/09/2024 | 9 | 605.71 | 248.05 | MVS
216 | HOOGHLY | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/014990 | SM/13343 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 879 | 222.7 | Yes | 222.7 | 11/11/2022 | 09/08/2024 | 7 | 197.48 | 88.48 | MVS
217 | HOOGHLY | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/014984 | SM/13344 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 22/08/2022 | 511 | 235.69 | Yes | 235.69 | 21/08/2023 | 13/10/2023 | 6 | 241.18 | 171.63 | MVS
218 | HOOGHLY | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/014975 | SM/13345 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 511 | 225.59 | Yes | 225.59 | 03/10/2024 | 11/08/2023 | 11 | 255.86 | 196.8 | MVS
219 | HOOGHLY | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/014980 | SM/13346 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 22/08/2022 | 1868 | 214.65 | Yes | 214.65 | 20/11/2024 | 23/08/2022 | 8 | 181.73 | 133.38 | MVS
220 | HOOGHLY | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | TSM/014169 | SM/13347 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 1798 | 517.76 | Yes | 517.76 | 11/04/2025 | 31/07/2024 | 13 | 529.26 | 277.3 | MVS
221 | HOOGHLY | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | TSM/009962 | SM/13348 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | 17/02/2022 | 4545 | 1091.61 | Yes | 1091.61 | 09/01/2023 | 21/02/2023 | 14 | 964.5 | 820.64 | MVS
222 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | TSM/009963 | SM/13349 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 17/02/2022 | 3300 | 1335.08 | Yes | 1335.08 | 30/07/2024 | 16/08/2023 | 28 | 1055.26 | 622.88 | MVS
223 | HOOGHLY | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010508 | SM/13353 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 2936 | 186.31 | Yes | 186.31 | 15/02/2023 | 21/07/2025 | 14 | 176.76 | 117.26 | MVS
224 | HOOGHLY | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010506 | SM/13354 | Retrofitting | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 22/08/2022 | 4709 | 295.6 | Yes | 295.6 | 27/03/2023 | 19/07/2023 | 3 | 110.53 | 80.33 | MVS
225 | HOOGHLY | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010499 | SM/13355 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 2150 | 139.24 | Yes | 139.24 |  | 11/08/2023 | 2 | 5.8 | 0.7 | MVS
226 | HOOGHLY | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | TSM/010441 | SM/13356 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 1600 | 103.91 | Yes | 103.91 | 02/03/2023 | 19/04/2023 | 11 | 79.84 | 54.39 | MVS
227 | HOOGHLY | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | TSM/010438 | SM/13357 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 600 | 38.98 | Yes | 38.98 | 02/03/2023 | 19/04/2023 | 2 | 31.79 | 31.74 | MVS
228 | HOOGHLY | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | TSM/011471 | SM/13404 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 25/04/2022 | 3610 | 1616.96 | Yes | 1616.96 | 17/10/2023 | 08/06/2023 | 11 | 1140.37 | 990.55 | MVS
229 | HOOGHLY | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/015548 | SM/13409 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 09/09/2022 | 2689 | 201.57 | Yes | 201.57 | 20/11/2024 | 04/04/2025 | 17 | 142.94 | 102.75 | MVS
230 | HOOGHLY | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/015551 | SM/13410 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 09/09/2022 | 22 | 248.89 | Yes | 248.89 | 20/11/2024 | 04/04/2025 | 19 | 210.39 | 140.15 | MVS
231 | HOOGHLY | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/015549 | SM/13411 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 754 | 197.18 | Yes | 197.18 | 13/07/2023 | 11/05/2023 | 16 | 148.19 | 135.39 | MVS
232 | HOOGHLY | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015527 | SM/13414 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 09/09/2022 | 1759 | 737.21 | Yes | 737.21 | 06/12/2022 | 22/05/2023 | 9 | 708.43 | 435.96 | MVS
233 | HOOGHLY | Shyampur Mini Piped Water Supply Scheme | TSM/015675 | SM/13421 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 92 | 42.22 | Yes | 42.22 |  | 27/12/2022 | 5 | 104.59 | 40.99 | MVS
234 | HOOGHLY | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/015414 | SM/13501 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 09/09/2022 | 606 | 377.67 | Yes | 377.67 | 29/11/2022 | 03/03/2023 | 9 | 348.87 | 335.81 | MVS
235 | HOOGHLY | Barul mini pipe water supply scheme | TSM/015689 | SM/13548 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 74 | 41.13 | Yes | 41.13 |  | 02/08/2023 | 2 | 39.48 | 39.48 | MVS
236 | HOOGHLY | Chak Netara Mini Piped Water Supply Scheme | TSM/015684 | SM/13551 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 67 | 40.48 | Yes | 40.48 |  | 02/08/2023 | 3 | 39.3 | 39.3 | MVS
237 | HOOGHLY | Belun Mini Piped Water Supply Scheme | TSM/015669 | SM/13552 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 85 | 41.57 | Yes | 41.57 |  | 27/12/2022 | 5 | 102.71 | 40.36 | MVS
238 | HOOGHLY | Dwariapur Mini Piped Water Supply Scheme | TSM/015670 | SM/13553 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 73 | 40.17 | Yes | 40.17 |  | 27/12/2022 | 5 | 98.71 | 39 | MVS
239 | HOOGHLY | Kapsit Mini Piped Water Supply Scheme | TSM/015672 | SM/13554 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 53 | 38.3 | Yes | 38.3 |  | 27/12/2022 | 6 | 94.14 | 37.19 | MVS
240 | HOOGHLY | Jot Mahabhat Mini Piped Water Supply Scheme | TSM/015678 | SM/13555 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 59 | 39.7 | Yes | 39.7 |  | 02/08/2023 | 3 | 38.54 | 38.54 | MVS
241 | HOOGHLY | Par adra mini pipe water supply scheme | TSM/015601 | SM/13559 | New | Arambug Sub-Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | 09/09/2022 | 94 | 41.27 | Yes | 41.27 |  | 15/05/2023 | 1 | 0.58 | 0.58 | MVS
242 | HOOGHLY | Basantapur Mini Piped Water Supply Scheme | TSM/015632 | SM/13560 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 93 | 42.06 | Yes | 42.06 |  | 17/08/2023 | 8 | 181.02 | 74.14 | MVS
243 | HOOGHLY | Durlabhpur Mini Piped Water Supply Scheme | TSM/015635 | SM/13561 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | 09/09/2022 | 74 | 39.95 | Yes | 39.95 |  | 19/08/2023 | 3 | 46.82 | 38.33 | MVS
244 | HOOGHLY | Naopara Mini Piped Water Supply Scheme | TSM/015638 | SM/13562 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 77 | 40.56 | Yes | 40.56 |  | 19/08/2023 | 3 | 47.4 | 38.91 | MVS
245 | HOOGHLY | Rampur Mini Piped Water Supply Scheme | TSM/015640 | SM/13563 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 94 | 42.21 | Yes | 42.21 |  | 19/08/2023 | 3 | 48.9 | 40.41 | MVS
246 | HOOGHLY | Muragari Mini Piped Water Supply Scheme | TSM/015637 | SM/13564 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 55 | 38.17 | Yes | 38.17 |  | 19/08/2023 | 3 | 45.21 | 36.72 | MVS
247 | HOOGHLY | BINAGRAM PIPED WATER SUPPLY SCHEME | TSM/011414 | SM/13568 | New | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | 25/04/2022 | 2669 | 1145.89 | Yes | 1145.89 | 06/02/2023 | 01/08/2023 | 8 | 802 | 329.78 | MVS
248 | HOOGHLY | Dewanchak Mini Piped Water Supply Scheme | TSM/015683 | SM/13586 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 25 | 36.22 | Yes | 36.22 |  | 02/08/2023 | 2 | 35.01 | 35.01 | MVS
249 | HOOGHLY | Bhupatipur Mini Piped Water Supply Scheme | TSM/015661 | SM/13587 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) |  | 09/09/2022 | 16 | 33.76 | Yes | 33.76 |  | 15/05/2023 | 1 | 0.1 | 0 | MVS
250 | HOOGHLY | Adra mini pipe water supply scheme | TSM/015685 | SM/13589 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 91 | 43.03 | Yes | 43.03 |  | 02/08/2023 | 3 | 41.77 | 41.77 | MVS
251 | HOOGHLY | Chak mamrej mini pipe water supply scheme | TSM/015690 | SM/13590 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 88 | 42.75 | Yes | 42.75 |  | 02/08/2023 | 2 | 40.96 | 40.96 | MVS
252 | HOOGHLY | Dumurpara Mini Piped water Supply Scheme | TSM/015682 | SM/13591 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 70 | 40.73 | Yes | 40.73 |  | 02/08/2023 | 3 | 39.54 | 39.54 | MVS
253 | HOOGHLY | Bara Kumursa mini pipe water supply scheme | TSM/015686 | SM/13592 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 63 | 40.14 | Yes | 40.14 |  | 02/08/2023 | 3 | 38.97 | 38.97 | MVS
254 | HOOGHLY | Surjyapur Mini Piped Water Supply Scheme | TSM/015681 | SM/13594 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 79 | 41.97 | Yes | 41.97 |  | 02/08/2023 | 3 | 40.75 | 40.75 | MVS
255 | HOOGHLY | Ghosha Mini Piped Water Supply Scheme | TSM/015663 | SM/13595 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) |  | 09/09/2022 | 92 | 41.94 | Yes | 41.94 |  | 15/05/2023 | 1 | 0.57 | 0.57 | MVS
256 | HOOGHLY | Telinipara Mini Piped Water Supply Scheme | TSM/015641 | SM/13599 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 68 | 39.39 | Yes | 39.39 |  | 19/08/2023 | 3 | 46.31 | 37.82 | MVS
257 | HOOGHLY | Chak Behala mini pipe water supply scheme | TSM/015569 | SM/13656 | New | Arambug Sub-Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | 09/09/2022 | 37 | 35.41 | Yes | 35.41 |  | 15/05/2023 | 1 | 0.23 | 0.23 | MVS
258 | HOOGHLY | Char Sundalpur Mini Piped Water Supply Scheme | TSM/015633 | SM/13657 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 65 | 39.14 | Yes | 39.14 |  | 19/08/2023 | 3 | 46.09 | 37.6 | MVS
259 | HOOGHLY | Mamudpur Mini Piped Water Supply Scheme | TSM/015636 | SM/13658 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 60 | 38.7 | Yes | 38.7 |  | 19/08/2023 | 3 | 45.7 | 37.21 | MVS
260 | HOOGHLY | Palpukur Mini Piped Water Supply Scheme | TSM/015679 | SM/13659 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 29 | 36.56 | Yes | 36.56 |  | 02/08/2023 | 3 | 35.49 | 35.49 | MVS
261 | HOOGHLY | Arazi Krittibaspur Mini Piped Water Supply Scheme | TSM/015668 | SM/13660 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 19 | 34.7 | Yes | 34.7 |  | 27/12/2022 | 5 | 82.99 | 33.69 | MVS
262 | HOOGHLY | Sikil Beldiha Mini Piped Water Supply Scheme | TSM/015676 | SM/13661 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 65 | 39.43 | Yes | 39.43 |  | 27/12/2022 | 5 | 96.56 | 38.28 | MVS
263 | HOOGHLY | Naraharbati Mini Piped water Supply Scheme | TSM/015673 | SM/13662 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 60 | 38.96 | Yes | 38.96 |  | 27/12/2022 | 5 | 95.22 | 37.82 | MVS
264 | HOOGHLY | Uttar Hazipur Mini Piped Water Supply Scheme | TSM/015660 | SM/13663 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Chinsurah Block Junior Engineer (Civill) | 09/09/2022 | 68 | 39.26 | Yes | 39.26 |  | 27/12/2022 | 3 | 67.43 | 38.11 | MVS
265 | HOOGHLY | Jasapur mini pipe water supply scheme | TSM/015570 | SM/13664 | New | Arambug Sub-Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | 09/09/2022 | 96 | 41.46 | Yes | 41.46 |  | 25/09/2024 | 3 | 66.01 | 33.3 | MVS
266 | HOOGHLY | Dwaripara Mini Piped Water Supply Scheme | TSM/015671 | SM/13665 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 98 | 42.75 | Yes | 42.75 |  | 27/12/2022 | 5 | 106.11 | 41.51 | MVS
267 | HOOGHLY | Purba Chakla Mini Piped Water Supply Scheme | TSM/015674 | SM/13666 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 75 | 40.33 | Yes | 40.33 |  | 27/12/2022 | 5 | 99.16 | 39.16 | MVS
268 | HOOGHLY | Rautara Mini Piped Water Supply Scheme | TSM/015680 | SM/13667 | New | Arambug Sub-Division | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | 09/09/2022 | 94 | 43.31 | Yes | 43.31 |  | 02/08/2023 | 3 | 36.9 | 36.9 | MVS
269 | HOOGHLY | Digra Mini Piped Water Supply Scheme | TSM/015634 | SM/13670 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | 09/09/2022 | 53 | 38.05 | Yes | 38.05 |  | 19/08/2023 | 4 | 45.43 | 36.94 | MVS
270 | HOOGHLY | Jot ram mini pipe water supply scheme | TSM/015600 | SM/13672 | New | Arambug Sub-Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | 09/09/2022 | 76 | 39.59 | Yes | 39.59 |  | 15/05/2023 | 1 | 0.47 | 0.47 | MVS
271 | HOOGHLY | Bhabapur mini pipe water supply scheme | TSM/015568 | SM/13673 | New | Arambug Sub-Division | Assistant Engineer | Arambag Block Junior Engineer (Civill) | 09/09/2022 | 78 | 39.84 | Yes | 39.84 |  | 25/09/2024 | 3 | 61.28 | 30.18 | MVS
272 | HOOGHLY | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/014958 | SM/13677 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 222 | 295.58 | Yes | 295.58 | 17/02/2023 | 14/06/2024 | 18 | 157.3 | 135.79 | MVS
273 | HOOGHLY | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | TSM/015375 | SM/13762 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 09/09/2022 | 2092 | 977.91 | Yes | 977.91 | 06/03/2023 | 19/10/2023 | 12 | 762.67 | 384.31 | MVS
274 | HOOGHLY | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | TSM/011881 | SM/14040 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 20/05/2022 | 4472 | 1265.48 | Yes | 1265.48 | 09/12/2022 | 26/09/2024 | 26 | 1071.97 | 661.92 | MVS
275 | HOOGHLY | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017333 | SM/14116 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 30/09/2022 | 2013 | 920.66 | Yes | 920.66 | 22/03/2023 | 13/11/2024 | 8 | 581.68 | 349.61 | MVS
276 | HOOGHLY | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017320 | SM/14117 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 30/09/2022 | 1616 | 753.82 | Yes | 753.82 | 29/11/2022 | 22/03/2023 | 8 | 458.03 | 349.25 | MVS
277 | HOOGHLY | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017318 | SM/14118 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 30/09/2022 | 2117 | 958.51 | Yes | 958.51 | 11/04/2025 | 25/11/2024 | 16 | 687.95 | 301.1 | MVS
278 | HOOGHLY | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016500 | SM/14121 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 1852 | 511.47 | Yes | 511.47 | 22/11/2022 | 30/03/2023 | 7 | 484.56 | 301.27 | MVS
279 | HOOGHLY | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016261 | SM/14122 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 983 | 329.66 | Yes | 329.66 | 20/03/2025 | 02/06/2023 | 11 | 236.95 | 225.95 | MVS
280 | HOOGHLY | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016744 | SM/14467 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 2454 | 812.88 | Yes | 812.88 | 22/11/2022 | 26/09/2024 | 8 | 667.73 | 450.71 | MVS
281 | HOOGHLY | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014549 | SM/14531 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 22/08/2022 | 5064 | 1227.07 | Yes | 1227.07 | 14/07/2023 | 17/07/2023 | 12 | 1246.11 | 775.73 | MVS
282 | HOOGHLY | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016705 | SM/14684 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 806 | 494.21 | Yes | 494.21 | 22/03/2023 | 31/10/2023 | 8 | 305.44 | 143.23 | MVS
283 | HOOGHLY | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | TSM/015871 | SM/14685 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 2176 | 690.25 | Yes | 690.25 | 22/03/2023 | 31/10/2023 | 10 | 612.45 | 282.37 | MVS
284 | HOOGHLY | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | TSM/017627 | SM/14982 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 1829 | 886.42 | Yes | 886.42 | 31/07/2024 | 26/09/2024 | 13 | 720.1 | 445.09 | MVS
285 | HOOGHLY | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017581 | SM/14983 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 1322 | 605.65 | Yes | 605.65 | 09/01/2023 | 29/05/2023 | 7 | 415.11 | 253.68 | MVS
286 | HOOGHLY | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016236 | SM/15243 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 1459 | 482.37 | Yes | 482.37 | 20/03/2025 | 10/07/2024 | 11 | 357.08 | 275.18 | MVS
287 | HOOGHLY | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | TSM/017620 | SM/15247 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 1796 | 797.78 | Yes | 797.78 | 31/07/2024 | 01/06/2023 | 9 | 583.73 | 360.69 | MVS
288 | HOOGHLY | Ground Water Based Bighati (Zone -II) PWSS | TSM/017507 | SM/15249 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 1579 | 711.52 | Yes | 711.52 | 07/03/2025 | 12/04/2023 | 8 | 564.44 | 420.08 | MVS
289 | HOOGHLY | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/016533 | SM/15250 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 1095 | 345.51 | Yes | 345.51 | 29/11/2022 | 10/03/2023 | 8 | 326.43 | 237.52 | MVS
290 | HOOGHLY | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/016556 | SM/15251 | New | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 1570 | 336.9 | Yes | 336.9 | 29/11/2022 | 20/02/2024 | 5 | 277.23 | 209.44 | MVS
291 | HOOGHLY | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) | TSM/015867 | SM/15252 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 2352 | 726.99 | Yes | 726.99 | 22/03/2023 | 10/09/2024 | 11 | 658.88 | 343.61 | MVS
292 | HOOGHLY | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | TSM/020224 | SM/15787 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 16/11/2022 | 50 | 441.46 | Yes | 441.46 | 03/10/2024 | 17/04/2023 | 10 | 486.59 | 309.05 | MVS
293 | HOOGHLY | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | TSM/020227 | SM/15788 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/11/2022 | 50 | 308.8 | Yes | 308.8 | 18/04/2023 | 24/07/2023 | 6 | 464.79 | 0.31 | MVS
294 | HOOGHLY | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | TSM/018043 | SM/15789 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 2185 | 962.24 | Yes | 962.24 | 17/04/2023 | 18/07/2023 | 9 | 608.04 | 177.38 | MVS
295 | HOOGHLY | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | TSM/017830 | SM/15790 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 993 | 432.75 | Yes | 432.75 | 06/02/2023 | 02/06/2023 | 10 | 391.89 | 105.01 | MVS
296 | HOOGHLY | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | TSM/017827 | SM/15791 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 1671 | 742.77 | Yes | 742.77 | 08/08/2023 | 08/05/2023 | 9 | 501.27 | 242.73 | MVS
297 | HOOGHLY | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017805 | SM/15792 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/11/2022 | 1899 | 916.78 | Yes | 916.78 | 05/01/2023 | 03/08/2023 | 15 | 651.63 | 54.45 | MVS
298 | HOOGHLY | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | TSM/018794 | SM/15793 | Augmentation | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | 16/11/2022 | 610 | 52.29 | Yes | 52.29 | 17/02/2023 | 10/05/2023 | 4 | 41.04 | 9.68 | MVS
299 | HOOGHLY | Source Augmentation of Bamonjol PWSS | TSM/018694 | SM/15794 | Augmentation | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 16/11/2022 | 1233 | 55.16 | Yes | 55.16 | 03/10/2024 | 19/05/2023 | 4 | 32.54 | 22.96 | MVS
300 | HOOGHLY | Source Augmentation of Paschim Joykrishnapur PWSS | TSM/018693 | SM/15795 | Augmentation | Howrah Mechanical Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 16/11/2022 | 4230 | 110.32 | Yes | 110.32 | 20/11/2024 | 26/04/2023 | 10 | 97.41 | 87.11 | MVS
301 | HOOGHLY | Source Augmentation of Malia PWSS | TSM/018687 | SM/15796 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 1301 | 55.16 | Yes | 55.16 | 21/03/2023 | 26/04/2023 | 20 | 54.45 | 43.55 | MVS
302 | HOOGHLY | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/018201 | SM/15797 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 300 | 114.3 | Yes | 114.3 | 28/04/2023 | 02/06/2023 | 11 | 148.06 | 109.13 | MVS
303 | HOOGHLY | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/018380 | SM/15798 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 300 | 114.3 | Yes | 114.3 | 24/02/2023 | 17/04/2023 | 7 | 96.18 | 88.21 | MVS
304 | HOOGHLY | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016328 | SM/15799 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 2683 | 201.57 | Yes | 201.57 | 20/03/2025 | 14/06/2024 | 17 | 167.96 | 113.28 | MVS
305 | HOOGHLY | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/016351 | SM/15800 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 50 | 178.69 | Yes | 178.69 | 17/02/2023 | 09/08/2024 | 13 | 108.01 | 78.26 | MVS
306 | HOOGHLY | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK | TSM/016521 | SM/15801 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 613 | 178.69 | Yes | 178.69 | 28/04/2023 | 22/05/2023 | 7 | 206.1 | 112.84 | MVS
307 | HOOGHLY | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | TSM/020250 | SM/15802 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/11/2022 | 50 | 66.42 | Yes | 66.42 | 29/07/2024 | 17/05/2023 | 7 | 65.04 | 37.89 | MVS
308 | HOOGHLY | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | TSM/020252 | SM/15803 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 25 | 63.2 | Yes | 63.2 | 17/02/2023 | 22/05/2023 | 4 | 39.45 | 9.91 | MVS
309 | HOOGHLY | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | TSM/020251 | SM/15804 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/11/2022 | 50 | 115.21 | Yes | 115.21 | 17/02/2023 | 23/08/2024 | 5 | 30.01 | 19.52 | MVS
310 | HOOGHLY | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | TSM/020249 | SM/15805 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 25 | 64.09 | Yes | 64.09 | 31/07/2024 | 22/05/2023 | 5 | 36.85 | 31.89 | MVS
311 | HOOGHLY | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | TSM/020248 | SM/15806 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 25 | 65.81 | Yes | 65.81 | 17/02/2023 | 22/05/2023 | 5 | 51.41 | 11.24 | MVS
312 | HOOGHLY | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | TSM/020247 | SM/15807 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 50 | 128.96 | Yes | 128.96 | 17/02/2023 | 19/05/2023 | 6 | 85.71 | 46.27 | MVS
313 | HOOGHLY | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | TSM/020246 | SM/15808 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 25 | 77.79 | Yes | 77.79 | 11/04/2025 | 20/04/2023 | 10 | 68.42 | 14.67 | MVS
314 | HOOGHLY | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | TSM/020245 | SM/15809 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 50 | 153.03 | Yes | 153.03 | 31/07/2024 | 15/06/2023 | 8 | 95.67 | 28.73 | MVS
315 | HOOGHLY | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | TSM/020244 | SM/15810 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 50 | 64.36 | Yes | 64.36 | 31/07/2024 | 10/05/2023 | 5 | 53.45 | 44.3 | MVS
316 | HOOGHLY | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | TSM/020243 | SM/15811 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 25 | 65.58 | Yes | 65.58 | 31/07/2024 | 17/05/2023 | 5 | 51.22 | 0 | MVS
317 | HOOGHLY | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | TSM/020237 | SM/15812 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 50 | 75.87 | Yes | 75.87 | 12/02/2025 | 22/05/2023 | 10 | 48.27 | 9.76 | MVS
318 | HOOGHLY | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | TSM/020241 | SM/15813 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 16/11/2022 | 25 | 72.23 | Yes | 72.23 | 17/02/2023 | 18/05/2023 | 8 | 53.67 | 20.23 | MVS
319 | HOOGHLY | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | TSM/020242 | SM/15814 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 25 | 129.51 | Yes | 129.51 | 17/02/2023 | 17/05/2023 | 6 | 71.7 | 34.43 | MVS
320 | HOOGHLY | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | TSM/020228 | SM/15815 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 16/11/2022 | 25 | 67.86 | Yes | 67.86 | 17/02/2023 | 06/04/2023 | 5 | 26.95 | 5.06 | MVS
321 | HOOGHLY | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | TSM/018655 | SM/15886 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 1519 | 679.29 | Yes | 679.29 | 23/12/2024 | 26/09/2024 | 13 | 503.56 | 415.09 | MVS
322 | HOOGHLY | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/018068 | SM/15887 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 2293 | 920.25 | Yes | 920.25 | 29/07/2024 | 28/03/2025 | 14 | 702.65 | 249.15 | MVS
323 | HOOGHLY | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | TSM/018116 | SM/15888 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 1260 | 515.59 | Yes | 515.59 | 05/01/2023 | 08/02/2024 | 9 | 423.29 | 322.46 | MVS
324 | HOOGHLY | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | TSM/018131 | SM/15889 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 2516 | 884.94 | Yes | 884.94 | 07/03/2025 | 03/08/2023 | 14 | 674.75 | 261.51 | MVS
325 | HOOGHLY | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | TSM/018154 | SM/15890 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 16/11/2022 | 2876 | 995.46 | Yes | 995.46 | 11/04/2025 | 17/08/2023 | 11 | 1079.17 | 639.67 | MVS
326 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | TSM/011632 | SM/15891 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 2353 | 151.75 | Yes | 151.75 | 20/11/2024 | 19/04/2023 | 14 | 170.43 | 137.45 | MVS
327 | HOOGHLY | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | TSM/018701 | SM/15898 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 16/11/2022 | 200 | 71.13 | Yes | 71.13 | 22/02/2023 | 18/05/2023 | 6 | 41.82 | 42.78 | MVS
328 | HOOGHLY | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/018192 | SM/15899 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 300 | 114.3 | Yes | 114.3 | 17/02/2023 | 26/09/2023 | 9 | 90.22 | 83.3 | MVS
329 | HOOGHLY | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/018379 | SM/15900 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 16/11/2022 | 300 | 114.3 | Yes | 114.3 | 13/09/2024 | 10/05/2023 | 9 | 70.59 | 44.54 | MVS
330 | HOOGHLY | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK | TSM/020255 | SM/15901 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 0 | 219.96 | Yes | 219.96 | 28/10/2024 | 20/04/2023 | 2 | 109.95 | 81.58 | MVS
331 | HOOGHLY | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017588 | SM/15913 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 2200 | 907.78 | Yes | 907.78 | 22/03/2023 | 31/10/2023 | 8 | 585.63 | 245.92 | MVS
332 | HOOGHLY | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/020424 | SM/16119 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/12/2022 | 200 | 558.04 | Yes | 558.04 | 15/02/2023 | 19/04/2023 | 8 | 556.64 | 152.54 | MVS
333 | HOOGHLY | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | TSM/020412 | SM/16120 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/12/2022 | 435 | 417.91 | Yes | 417.91 | 04/10/2024 | 10/05/2023 | 7 | 324.11 | 207.34 | MVS
334 | HOOGHLY | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | TSM/020378 | SM/16121 | Augmentation | Arambug Sub-Division | Assistant Engineer | Khanakul 2 Block Junior Engineer | 28/12/2022 | 25 | 163.66 | Yes | 163.66 | 03/10/2024 | 18/05/2023 | 14 | 123.78 | 82.57 | MVS
335 | HOOGHLY | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | TSM/020384 | SM/16122 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | 28/12/2022 | 50 | 198.87 | Yes | 198.87 | 22/02/2023 | 18/05/2023 | 8 | 105.66 | 81.9 | MVS
336 | HOOGHLY | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | TSM/020386 | SM/16124 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 50 | 190.76 | Yes | 190.76 | 18/06/2024 | 18/05/2023 | 9 | 86.96 | 2.8 | MVS
337 | HOOGHLY | SAMANTA KHANDA WATER SUPPLY SCHEME | TSM/014936 | SM/16127 | New | Hooghly Division | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 2089 | 810.49 | Yes | 810.49 | 22/03/2023 | 10/09/2024 | 10 | 752.17 | 296.09 | MVS
338 | HOOGHLY | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | TSM/020404 | SM/16130 | Augmentation | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 25 | 178.48 | Yes | 178.48 | 03/10/2024 | 22/10/2024 | 12 | 60.57 | 34.19 | MVS
339 | HOOGHLY | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | TSM/020301 | SM/16136 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 540 | 231.55 | Yes | 231.55 | 13/02/2023 | 03/08/2023 | 6 | 209.96 | 192.35 | MVS
340 | HOOGHLY | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | TSM/018137 | SM/16138 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 611 | 271.36 | Yes | 271.36 | 13/02/2023 | 14/06/2024 | 12 | 260.66 | 178.76 | MVS
341 | HOOGHLY | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | TSM/016029 | SM/16236 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 26/09/2022 | 1850 | 851.51 | Yes | 851.51 |  | 21/02/2024 | 9 | 652.73 | 605.9 | MVS
342 | HOOGHLY | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/020222 | SM/16237 | New | Arambug Sub-Division | Assistant Engineer | Khanakul 2 Block Junior Engineer | 28/12/2022 | 124 | 55.7 | Yes | 55.7 | 15/02/2023 | 03/05/2023 | 5 | 33.38 | 33.93 | MVS
343 | HOOGHLY | Augmentation of Gobindapur Water Supply Scheme | TSM/014860 | SM/16351 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 22/08/2022 | 225 | 331.19 | Yes | 331.19 | 04/10/2024 | 03/05/2023 | 9 | 274.93 | 217.08 | MVS
344 | HOOGHLY | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | TSM/013254 | SM/16447 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 16/11/2022 | 1450 | 109.03 | Yes | 109.03 | 11/04/2025 | 20/04/2023 | 9 | 106.63 | 91.18 | MVS
345 | HOOGHLY | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | TSM/013029 | SM/16448 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 100 | 63.58 | Yes | 63.58 |  | 18/05/2023 | 8 | 50.59 | 47.39 | MVS
346 | HOOGHLY | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | TSM/013031 | SM/16449 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 16/11/2022 | 50 | 128.7 | Yes | 128.7 |  | 18/05/2023 | 11 | 108.19 | 67.53 | MVS
347 | HOOGHLY | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | TSM/013033 | SM/16450 | Augmentation | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 16/11/2022 | 100 | 136.17 | Yes | 136.17 | 11/04/2025 | 18/05/2023 | 7 | 103.11 | 99.42 | MVS
348 | HOOGHLY | Augmentation of Kulteghori Piped Water Supply Scheme | TSM/015885 | SM/16564 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 26/09/2022 | 2963 | 59.1 | Yes | 59.1 | 18/07/2023 | 26/06/2023 | 7 | 74.3 | 26.31 | MVS
349 | HOOGHLY | RETROFITTING FOR BANDIPUR WS SCHEME | TSM/020287 | SM/16648 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/12/2022 | 1550 | 99.14 | Yes | 99.14 | 17/03/2023 | 20/04/2023 | 12 | 81.25 | 39.43 | MVS
350 | HOOGHLY | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | TSM/020276 | SM/16651 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 1407 | 550.37 | Yes | 550.37 | 07/03/2025 | 19/05/2025 | 7 | 420.14 | 246.01 | MVS
351 | HOOGHLY | Gopalbati Piped Water Supply Scheme. | TSM/004249 | SM/16756 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 1059 | 421.19 | Yes | 421.19 | 31/07/2024 | 22/05/2023 | 9 | 430.38 | 114.33 | MVS
352 | HOOGHLY | Ramnagar Piped Water Supply Scheme. | TSM/004216 | SM/16757 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 19/08/2021 | 2549 | 755.39 | Yes | 755.39 | 31/07/2024 | 22/05/2023 | 13 | 751.57 | 669.81 | MVS
353 | HOOGHLY | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016255 | SM/16763 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 541 | 240.53 | Yes | 240.53 | 11/11/2022 | 09/08/2024 | 8 | 168.53 | 128.17 | MVS
354 | HOOGHLY | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | TSM/018155 | SM/16979 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 827 | 371.55 | Yes | 371.55 | 13/02/2023 | 16/06/2023 | 10 | 312.6 | 250.43 | MVS
355 | HOOGHLY | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | TSM/014174 | SM/17176 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 30/09/2022 | 793 | 277.86 | Yes | 277.86 | 23/11/2022 | 10/04/2023 | 8 | 261.56 | 139.95 | MVS
356 | HOOGHLY | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | TSM/016019 | SM/17289 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 26/09/2022 | 1715 | 787.21 | Yes | 787.21 | 07/03/2025 | 11/09/2025 | 9 | 555.88 | 480.66 | MVS
357 | HOOGHLY | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016129 | SM/17290 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 26/09/2022 | 706 | 400.4 | Yes | 400.4 | 29/07/2024 | 25/11/2024 | 6 | 294.84 | 102.41 | MVS
358 | HOOGHLY | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/020223 | SM/17625 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 1354 | 685.43 | Yes | 685.43 | 13/02/2023 | 08/06/2023 | 7 | 529.1 | 120.64 | MVS
359 | HOOGHLY | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/017991 | SM/17626 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 1341 | 663.19 | Yes | 663.19 | 29/07/2024 | 03/08/2023 | 9 | 476.41 | 104.6 | MVS
360 | HOOGHLY | GROUND BASED PWSS FOR NASIBPUR | TSM/013334 | SM/17627 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 2463 | 900.19 | Yes | 900.19 | 07/03/2025 | 08/06/2023 | 16 | 789.28 | 381.82 | MVS
361 | HOOGHLY | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | TSM/013329 | SM/17628 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 2306 | 764.21 | Yes | 764.21 | 07/03/2025 | 08/06/2023 | 8 | 546.52 | 269.49 | MVS
362 | HOOGHLY | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | TSM/018107 | SM/17629 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 28/12/2022 | 933 | 406.5 | Yes | 406.5 | 07/03/2025 | 05/11/2024 | 12 | 382.06 | 121.42 | MVS
363 | HOOGHLY | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014194 | SM/17632 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 22/08/2022 | 2018 | 637.99 | Yes | 637.99 | 08/02/2024 | 10/08/2023 | 7 | 655.55 | 72.55 | MVS
364 | HOOGHLY | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015825 | SM/17716 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 1985 | 728.51 | Yes | 728.51 | 18/06/2024 | 06/04/2023 | 7 | 483.44 | 138.06 | MVS
365 | HOOGHLY | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | TSM/015863 | SM/17719 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 907 | 398.66 | Yes | 398.66 | 22/03/2023 | 31/10/2023 | 10 | 373.6 | 196.77 | MVS
366 | HOOGHLY | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | TSM/015849 | SM/17721 | New | Arambug Sub-Division | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 30/09/2022 | 2838 | 861.33 | Yes | 861.33 | 22/03/2023 | 31/10/2023 | 9 | 825.72 | 312.73 | MVS
367 | HOOGHLY | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | TSM/020670 | SM/18095 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 477 | 274.98 | Yes | 274.98 | 17/10/2023 | 18/07/2023 | 9 | 207.28 | 172.59 | MVS
368 | HOOGHLY | BHANDARDAHA PIPED WATER SUPPLY SCHEME | TSM/020545 | SM/18096 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 368 | 214.91 | Yes | 214.91 | 15/03/2023 | 09/04/2024 | 7 | 128.79 | 114.22 | MVS
369 | HOOGHLY | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | TSM/020547 | SM/18097 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 934 | 362.38 | Yes | 362.38 | 13/06/2024 | 19/05/2025 | 11 | 241.72 | 164.51 | MVS
370 | HOOGHLY | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | TSM/020668 | SM/18098 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 740 | 237.95 | Yes | 237.95 | 15/03/2023 | 19/07/2023 | 6 | 128.69 | 87.78 | MVS
371 | HOOGHLY | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | TSM/020669 | SM/18099 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 522 | 241.67 | Yes | 241.67 | 15/03/2023 | 19/07/2023 | 6 | 141.38 | 46.08 | MVS
372 | HOOGHLY | KALACHHARA PIPED WATER SUPPLY SCHEME | TSM/020543 | SM/18100 | New | Chandannagar Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | 10/03/2023 | 292 | 190.75 | Yes | 190.75 | 16/03/2023 | 09/04/2024 | 9 | 110.76 | 99.07 | MVS
373 | HOOGHLY | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | TSM/020542 | SM/18101 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 328 | 224.39 | Yes | 224.39 | 15/03/2023 | 12/05/2023 | 6 | 130.34 | 117.92 | MVS
374 | HOOGHLY | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | TSM/020541 | SM/18102 | New | Chinsuria Sub-Division | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | 10/03/2023 | 96 | 45.54 | Yes | 45.54 | 15/03/2023 | 12/05/2023 | 5 | 40.9 | 43.27 | MVS
375 | HOOGHLY | SINHAL PATAN PIPED WATER SUPPLY SCHEME | TSM/020537 | SM/18103 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 230 | 183.43 | Yes | 183.43 | 16/03/2023 | 09/04/2024 | 7 | 97.97 | 19.66 | MVS
376 | HOOGHLY | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | TSM/020533 | SM/18104 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | 10/03/2023 | 891 | 554.56 | Yes | 554.56 | 16/03/2023 | 03/04/2025 | 11 | 439.72 | 190.08 | MVS
377 | HOOGHLY | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | TSM/020532 | SM/18105 | New | Srirampur Sub-Division | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | 10/03/2023 | 1287 | 673.9 | Yes | 673.9 | 16/03/2023 | 17/04/2025 | 13 | 517.28 | 250.91 | MVS
378 | HOOGHLY | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block | TSM/020539 | SM/18106 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 170 | 21.11 | Yes | 21.11 | 17/03/2023 | 29/02/2024 | 2 | 1.01 | 0.95 | MVS
379 | HOOGHLY | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block | TSM/020540 | SM/18107 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 180 | 21.7 | Yes | 21.7 | 17/03/2023 | 15/06/2023 | 1 | 11.42 | 0 | MVS
380 | HOOGHLY | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block | TSM/020535 | SM/18109 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 1874 | 41.33 | Yes | 41.33 | 17/03/2023 | 20/02/2024 | 3 | 36.16 | 6.03 | MVS
381 | HOOGHLY | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | TSM/020534 | SM/18110 | Retrofitting | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 1776 | 142.51 | Yes | 142.51 | 11/04/2025 | 23/07/2025 | 5 | 121.41 | 101.92 | MVS
382 | HOOGHLY | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Hasampur Water Supply Scheme Under Dhaniakhali Block | TSM/020538 | SM/18111 | Retrofitting | Chinsuria Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 10/03/2023 | 160 | 20.53 | Yes | 20.53 | 17/03/2023 | 28/10/2022 | 1 | 90.96 | 0 | MVS
383 | HOOGHLY | NAWPARA PIPED WATER SUPPLY SCHEME | TSM/011486 | SM/18241 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) |  | 16/11/2022 | 2929 | 1152.24 | Yes | 1152.24 | 31/07/2024 | 19/05/2025 | 11 | 955.79 | 705.28 | MVS
384 | HOOGHLY | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017493 | SM/18288 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 2787 | 1182.64 | Yes | 1182.64 | 18/06/2024 | 04/10/2024 | 11 | 764.68 | 368.96 | MVS
385 | HOOGHLY | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016111 | SM/18307 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 26/09/2022 | 2440 | 1089.72 | Yes | 1089.72 | 31/07/2024 | 04/10/2024 | 8 | 787.96 | 476.23 | MVS
386 | HOOGHLY | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016117 | SM/18308 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 26/09/2022 | 3198 | 1433.95 | Yes | 1433.95 | 30/07/2024 | 10/09/2024 | 12 | 899.02 | 294.54 | MVS
387 | HOOGHLY | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | TSM/017631 | SM/18309 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 2455 | 1026.73 | Yes | 1026.73 | 22/03/2023 | 23/08/2024 | 15 | 517.89 | 267.28 | MVS
388 | HOOGHLY | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | TSM/017614 | SM/18310 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 3156 | 1372.02 | Yes | 1372.02 | 18/06/2024 | 03/10/2024 | 10 | 850.33 | 330 | MVS
389 | HOOGHLY | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | TSM/018115 | SM/18320 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 16/11/2022 | 4389 | 1374.35 | Yes | 1374.35 | 08/02/2024 | 03/08/2023 | 9 | 1358.96 | 524.46 | MVS
390 | HOOGHLY | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | TSM/014834 | SM/18339 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 22/08/2022 | 4199 | 1052.22 | Yes | 1052.22 | 29/07/2024 | 10/09/2024 | 14 | 834.25 | 543.04 | MVS
391 | HOOGHLY | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | TSM/015413 | SM/18345 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | 09/09/2022 | 3124 | 1177.52 | Yes | 1177.52 | 06/03/2023 | 18/03/2025 | 9 | 799.56 | 461.6 | MVS
392 | HOOGHLY | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | TSM/015389 | SM/18346 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | 09/09/2022 | 2882 | 1006.17 | Yes | 1006.17 | 19/05/2023 | 26/09/2024 | 8 | 871.7 | 191.23 | MVS
393 | HOOGHLY | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | TSM/015380 | SM/18347 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 09/09/2022 | 4186 | 1047.32 | Yes | 1047.32 | 31/07/2024 | 03/08/2023 | 7 | 882.6 | 323.09 | MVS
394 | HOOGHLY | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | TSM/015371 | SM/18348 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 09/09/2022 | 2581 | 1091.61 | Yes | 1091.61 | 31/07/2024 | 12/07/2023 | 10 | 705.05 | 513.88 | MVS
395 | HOOGHLY | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | TSM/018133 | SM/18373 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | 16/11/2022 | 4229 | 1258.73 | Yes | 1258.73 | 11/04/2025 | 26/09/2024 | 11 | 1266.49 | 507.16 | MVS
396 | HOOGHLY | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | TSM/009649 | SM/18397 | Augmentation | Chandannagar Sub-Division | Assistant Engineer (Civil) |  | 16/03/2022 | 12225 | 4047.1 | Yes | 4047.1 | 03/10/2024 | 19/05/2025 | 64 | 3005.41 | 1229.86 | MVS
397 | HOOGHLY | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014739 | SM/18429 | New | Arambug Sub-Division | Assistant Engineer | Pursurah Block Junior Engineer | 22/08/2022 | 3194 | 1139.61 | Yes | 1139.61 | 18/12/2024 | 26/07/2023 | 11 | 881.18 | 22.47 | MVS
398 | HOOGHLY | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016693 | SM/18592 | New | Arambug Sub-Division | Assistant Engineer |  | 30/09/2022 | 2086 | 1147.47 | Yes | 1147.47 | 22/03/2023 | 18/03/2025 | 15 | 741.53 | 194.3 | MVS
399 | HOOGHLY | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | TSM/017604 | SM/18593 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 2432 | 1071.3 | Yes | 1071.3 | 31/07/2024 | 18/03/2025 | 10 | 799.69 | 438.69 | MVS
400 | HOOGHLY | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017484 | SM/18594 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 2500 | 1120.56 | Yes | 1120.56 | 12/02/2025 | 23/08/2024 | 11 | 728.02 | 143.46 | MVS
401 | HOOGHLY | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/017324 | SM/18595 | New |  |  |  | 30/09/2022 | 2659 | 1140.41 | Yes | 1140.41 | 22/03/2023 | 10/09/2024 | 10 | 664.07 | 398.55 | MVS
402 | HOOGHLY | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015822 | SM/18596 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 30/09/2022 | 2863 | 1182.91 | Yes | 1182.91 | 30/07/2024 | 04/10/2024 | 9 | 719.01 | 334.08 | MVS
403 | HOOGHLY | BENGAI WATER SUPPLY SCHEME | TSM/014934 | SM/18597 | New | Arambug Sub-Division | Assistant Engineer |  | 30/09/2022 | 3263 | 1076.77 | Yes | 1076.77 | 22/03/2023 | 31/10/2023 | 13 | 999.2 | 505.59 | MVS
404 | HOOGHLY | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | TSM/017299 | SM/18623 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 4209 | 1061.62 | Yes | 1061.62 | 31/07/2024 | 26/09/2024 | 26 | 1120.48 | 573.75 | MVS
405 | HOOGHLY | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | TSM/017292 | SM/18624 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 3725 | 1061.79 | Yes | 1061.79 | 07/05/2025 | 07/08/2023 | 27 | 1108.1 | 687.22 | MVS
406 | HOOGHLY | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017792 | SM/18642 | New | Arambug Sub-Division | Assistant Engineer |  | 16/11/2022 | 4990 | 1974.34 | Yes | 1974.34 | 31/07/2024 | 07/08/2023 | 11 | 950.44 | 14.09 | MVS
407 | HOOGHLY | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | TSM/017860 | SM/18643 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 16/11/2022 | 5168 | 1148.41 | Yes | 1148.41 | 31/07/2024 | 07/08/2023 | 7 | 906.06 | 244.11 | MVS
408 | HOOGHLY | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | TSM/019199 | SM/18644 | Augmentation |  |  |  | 16/11/2022 | 5011 | 2099.59 | Yes | 2099.59 | 08/06/2023 | 04/04/2025 | 18 | 264.76 | 124.48 | MVS
409 | HOOGHLY | Augmentation Of Piped Water Supply Scheme For KHANAKUL | TSM/017854 | SM/18645 | Augmentation |  |  |  | 16/11/2022 | 3930 | 1200.12 | Yes | 1200.12 | 12/02/2025 | 18/03/2025 | 13 | 912.23 | 132.56 | MVS
410 | HOOGHLY | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | TSM/018062 | SM/18646 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 16/11/2022 | 3142 | 1321.9 | Yes | 1321.9 | 29/07/2024 | 13/10/2025 | 13 | 815.5 | 47.41 | MVS
411 | HOOGHLY | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | TSM/020274 | SM/18657 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 28/12/2022 | 3347 | 1453.6 | Yes | 1453.6 | 07/03/2025 | 06/06/2024 | 9 | 923 | 705.3 | MVS
412 | HOOGHLY | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | TSM/017304 | SM/18666 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 3725 | 1136.8 | Yes | 1136.8 | 11/04/2025 | 07/08/2023 | 10 | 1212.96 | 670.22 | MVS
413 | HOOGHLY | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | TSM/017267 | SM/18667 | New | Srirampur Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 30/09/2022 | 5093 | 1548.7 | Yes | 1548.7 | 11/04/2025 | 04/08/2023 | 11 | 1630.66 | 521.26 | MVS
414 | HOOGHLY | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | TSM/018653 | SM/18668 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/12/2022 | 3101 | 1392.22 | Yes | 1392.22 | 31/07/2024 | 22/10/2024 | 15 | 889.16 | 521.25 | MVS
415 | HOOGHLY | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/014859 | SM/18670 | Augmentation | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 22/08/2022 | 4182 | 1132.16 | Yes | 1132.16 | 18/11/2022 | 07/08/2023 | 8 | 992.79 | 127.55 | MVS
416 | HOOGHLY | Baligari Piped Water Supply Scheme. | TSM/004358 | SM/18671 | New | Chandannagar Sub-Division | Assistant Engineer (Civil) | Junior Engineer (Civill) | 19/08/2021 | 3994 | 2067.16 | Yes | 2067.16 | 31/07/2024 | 19/05/2025 | 22 | 1270.04 | 779.3 | MVS
417 | HOOGHLY | Raghubati Piped Water Supply Scheme. | TSM/002251 | SM/18672 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 19/08/2021 | 5842 | 1129.16 | Yes | 1129.16 | 31/07/2024 | 04/10/2024 | 7 | 882.9 | 466.05 | MVS
418 | HOOGHLY | Augmentation of Balipur Water Supply Scheme | TSM/014800 | SM/18770 | Augmentation |  |  |  | 22/08/2022 | 4804 | 1152.8 | Yes | 1152.8 | 23/12/2024 | 20/05/2025 | 12 | 968 | 420.02 | MVS
419 | HOOGHLY | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | TSM/015416 | SM/18771 | New |  |  |  | 09/09/2022 | 2347 | 1074.94 | Yes | 1074.94 | 06/03/2023 | 19/10/2023 | 9 | 694.31 | 254.83 | MVS
420 | HOOGHLY | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015555 | SM/18772 | New |  |  |  | 09/09/2022 | 3575 | 1654.55 | Yes | 1654.55 | 31/07/2024 | 18/03/2025 | 16 | 881.29 | 284.86 | MVS
421 | HOOGHLY | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | TSM/015193 | SM/18778 | New |  |  |  | 30/09/2022 | 0 | 1107.03 | Yes | 1107.03 | 08/02/2024 | 29/08/2023 | 8 | 998.39 | 128.68 | MVS
422 | HOOGHLY | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | TSM/011639 | SM/18791 | Augmentation |  |  |  | 16/11/2022 | 3233 | 72.46 | Yes | 72.46 | 03/10/2024 | 05/11/2024 | 6 | 66.77 | 21.47 | MVS
423 | HOOGHLY | Mayapur Piped Water Supply Scheme. | TSM/004222 | SM/18833 | New |  |  |  | 04/12/2020 | 2505 | 1143.23 | Yes | 1143.23 | 31/07/2024 | 25/11/2024 | 11 | 572.43 | 122.31 | MVS
424 | HOOGHLY | Improvement of ¿MEGHSAR¿ Piped Water Supply Scheme by laying of HDPE Pipeline by HDD Process & Open cut method including restoration work at Mahanad Bandel Road within Meghsar PWSS under Chinsurah Sub Division. | TSM/020548 | SM/18926 | Augmentation |  |  |  | 10/03/2023 | 500 | 164.41 | Yes | 164.41 | 20/03/2025 | 14/03/2024 | 2 | 1.91 | 0.95 | MVS
425 | HOOGHLY | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | TSM/020494 | SM/18928 | Augmentation |  |  |  | 10/03/2023 | 0 | 162.48 | Yes | 162.48 | 17/10/2023 | 17/05/2023 | 7 | 134.82 | 20.43 | MVS
426 | HOOGHLY | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | TSM/020405 | SM/18929 | Augmentation |  |  |  | 10/03/2023 | 0 | 194.31 | Yes | 194.31 | 03/10/2024 | 14/12/2021 | 19 | 172.13 | 82.39 | MVS
427 | HOOGHLY | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | TSM/020453 | SM/18930 | Augmentation |  |  |  | 10/03/2023 | 0 | 55.3 | Yes | 55.3 |  | 07/02/2024 | 3 | 36.53 | 36.53 | MVS
428 | HOOGHLY | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | TSM/020469 | SM/18931 | Augmentation |  |  |  | 10/03/2023 | 0 | 83.25 | Yes | 83.25 |  | 13/10/2023 | 6 | 27.26 | 27.26 | MVS
429 | HOOGHLY | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020676 | SM/18932 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 | 13/09/2024 | 05/11/2024 | 5 | 85.24 | 15.84 | MVS
430 | HOOGHLY | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020675 | SM/18933 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 4 | 82.76 | 0.95 | MVS
431 | HOOGHLY | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020672 | SM/18934 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 7 | 101.54 | 42.14 | MVS
432 | HOOGHLY | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020671 | SM/18935 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 7 | 100.37 | 22.9 | MVS
433 | HOOGHLY | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020666 | SM/18936 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 7 | 96.38 | 34.7 | MVS
434 | HOOGHLY | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020642 | SM/18937 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 | 01/03/2024 | 19/06/2024 | 8 | 137.08 | 19.63 | MVS
435 | HOOGHLY | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020641 | SM/18938 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 10 | 117.27 | 55.32 | MVS
436 | HOOGHLY | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020640 | SM/18939 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 8 | 92.93 | 9.61 | MVS
437 | HOOGHLY | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020639 | SM/18940 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 8 | 100.91 | 43.18 | MVS
438 | HOOGHLY | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020552 | SM/18941 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 21/11/2023 | 8 | 89.25 | 25.12 | MVS
439 | HOOGHLY | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020551 | SM/18942 | Augmentation |  |  |  | 10/03/2023 | 1766 | 103.03 | Yes | 103.03 |  | 14/06/2024 | 12 | 62.99 | 41.73 | MVS
440 | HOOGHLY | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/020550 | SM/18943 | Augmentation |  |  |  | 10/03/2023 | 0 | 85.43 | Yes | 85.43 |  | 21/11/2023 | 6 | 56.77 | 33.32 | MVS
441 | HOOGHLY | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020549 | SM/18944 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 | 20/11/2024 | 23/12/2024 | 10 | 95.73 | 40.85 | MVS
442 | HOOGHLY | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020546 | SM/18945 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 11 | 98.02 | 10.93 | MVS
443 | HOOGHLY | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020544 | SM/18946 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 04/04/2025 | 15 | 123.93 | 8.12 | MVS
444 | HOOGHLY | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block | TSM/020492 | SM/18947 | Augmentation |  |  |  | 10/03/2023 | 0 | 140.91 | Yes | 140.91 |  | 10/09/2024 | 5 | 60.6 | 41.85 | MVS
445 | HOOGHLY | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | TSM/020478 | SM/18948 | Augmentation |  |  |  | 10/03/2023 | 0 | 153.27 | Yes | 153.27 | 23/12/2024 | 09/08/2024 | 8 | 99.36 | 36.77 | MVS
446 | HOOGHLY | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | TSM/020467 | SM/18949 | Augmentation |  |  |  | 10/03/2023 | 0 | 144.76 | Yes | 144.76 | 20/11/2024 | 06/11/2023 | 6 | 75.98 | 34.53 | MVS
447 | HOOGHLY | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | TSM/020465 | SM/18950 | Augmentation |  |  |  | 10/03/2023 | 0 | 153.27 | Yes | 153.27 |  | 31/10/2023 | 9 | 99.85 | 15.66 | MVS
448 | HOOGHLY | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | TSM/020464 | SM/18951 | Augmentation |  |  |  | 10/03/2023 | 0 | 153.27 | Yes | 153.27 | 27/12/2024 | 19/06/2024 | 7 | 101.55 | 21.64 | MVS
449 | HOOGHLY | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | TSM/020462 | SM/18952 | Augmentation |  |  |  | 10/03/2023 | 0 | 153.27 | Yes | 153.27 | 31/07/2024 | 10/07/2024 | 9 | 110.58 | 62.53 | MVS
450 | HOOGHLY | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | TSM/020461 | SM/18953 | Augmentation |  |  |  | 10/03/2023 | 0 | 67.84 | Yes | 67.84 | 31/07/2024 | 06/11/2023 | 6 | 70.75 | 41.36 | MVS
451 | HOOGHLY | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | TSM/020460 | SM/18954 | Augmentation |  |  |  | 10/03/2023 | 0 | 153.27 | Yes | 153.27 |  | 14/06/2024 | 14 | 125.28 | 66.08 | MVS
452 | HOOGHLY | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | TSM/020458 | SM/18955 | Augmentation |  |  |  | 10/03/2023 | 0 | 67.84 | Yes | 67.84 |  | 15/07/2024 | 5 | 45.76 | 5.81 | MVS
453 | HOOGHLY | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | TSM/020457 | SM/18956 | Augmentation |  |  |  | 10/03/2023 | 0 | 67.84 | Yes | 67.84 |  | 06/11/2023 | 6 | 49 | 17.74 | MVS
454 | HOOGHLY | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block | TSM/020456 | SM/18957 | Augmentation |  |  |  | 10/03/2023 | 0 | 146.07 | Yes | 146.07 |  | 08/11/2023 | 12 | 86.81 | 0 | MVS
455 | HOOGHLY | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | TSM/020455 | SM/18958 | Augmentation |  |  |  | 10/03/2023 | 0 | 155.79 | Yes | 155.79 | 23/12/2024 | 10/09/2024 | 9 | 65.05 | 9.55 | MVS
456 | HOOGHLY | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | TSM/020454 | SM/18959 | Augmentation |  |  |  | 10/03/2023 | 0 | 75.93 | Yes | 75.93 | 31/07/2024 | 25/11/2024 | 5 | 28.79 | 8.76 | MVS
457 | HOOGHLY | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | TSM/020452 | SM/18960 | Augmentation |  |  |  | 10/03/2023 | 0 | 172.88 | Yes | 172.88 |  | 23/08/2024 | 11 | 48.98 | 20.9 | MVS
458 | HOOGHLY | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | TSM/020451 | SM/18961 | Augmentation |  |  |  | 10/03/2023 | 0 | 174.48 | Yes | 174.48 | 12/02/2025 | 23/08/2024 | 6 | 83.19 | 39.95 | MVS
459 | HOOGHLY | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | TSM/020450 | SM/18962 | Augmentation |  |  |  | 10/03/2023 | 0 | 192.68 | Yes | 192.68 |  | 19/12/2024 | 6 | 95.1 | 17.72 | MVS
460 | HOOGHLY | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block | TSM/020449 | SM/18963 | Augmentation |  |  |  | 10/03/2023 | 0 | 63.33 | Yes | 63.33 | 17/10/2023 | 29/11/2023 | 3 | 46.27 | 28.53 | MVS
461 | HOOGHLY | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | TSM/020448 | SM/18964 | Augmentation |  |  |  | 10/03/2023 | 0 | 194.51 | Yes | 194.51 |  | 10/11/2023 | 8 | 84.47 | 0 | MVS
462 | HOOGHLY | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | TSM/020447 | SM/18965 | Augmentation |  |  |  | 10/03/2023 | 0 | 174.68 | Yes | 174.68 | 17/10/2023 | 19/12/2024 | 4 | 91.45 | 12.28 | MVS
463 | HOOGHLY | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | TSM/020442 | SM/18966 | Augmentation |  |  |  | 10/03/2023 | 0 | 408.03 | Yes | 408.03 | 11/04/2025 | 17/04/2025 | 19 | 301.17 | 91.25 | MVS
464 | HOOGHLY | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | TSM/020441 | SM/18967 | Augmentation |  |  |  | 10/03/2023 | 0 | 124.38 | Yes | 124.38 |  | 10/11/2023 | 5 | 108.9 | 60.09 | MVS
465 | HOOGHLY | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | TSM/020439 | SM/18968 | Augmentation |  |  |  | 10/03/2023 | 0 | 45.23 | Yes | 45.23 | 22/02/2024 | 05/11/2024 | 10 | 49.02 | 24.07 | MVS
466 | HOOGHLY | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020638 | SM/18969 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 8 | 107.88 | 56.96 | MVS
467 | HOOGHLY | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020637 | SM/18970 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 9 | 111.38 | 50.22 | MVS
468 | HOOGHLY | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020636 | SM/18971 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 6 | 91.32 | 22.9 | MVS
469 | HOOGHLY | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020635 | SM/18972 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 5 | 85 | 17.57 | MVS
470 | HOOGHLY | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020634 | SM/18973 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 14/06/2024 | 6 | 69.84 | 2.51 | MVS
471 | HOOGHLY | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020633 | SM/18974 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 23/12/2024 | 11 | 117.63 | 44.1 | MVS
472 | HOOGHLY | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/020632 | SM/18975 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 | 20/11/2024 | 06/11/2023 | 12 | 118.12 | 80.05 | MVS
473 | HOOGHLY | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020631 | SM/18976 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 06/11/2023 | 6 | 88.43 | 0.95 | MVS
474 | HOOGHLY | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020630 | SM/18977 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 14/06/2024 | 6 | 92.07 | 4.09 | MVS
475 | HOOGHLY | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020629 | SM/18978 | Augmentation |  |  |  | 10/03/2023 | 0 | 188.47 | Yes | 188.47 |  | 22/11/2023 | 7 | 111.22 | 57.25 | MVS
476 | HOOGHLY | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK | TSM/020555 | SM/18979 | Augmentation |  |  |  | 10/03/2023 | 0 | 103.03 | Yes | 103.03 | 17/10/2023 | 22/11/2023 | 2 | 28.61 | 0 | MVS
477 | HOOGHLY | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK | TSM/020554 | SM/18980 | Augmentation |  |  |  | 10/03/2023 | 0 | 103.03 | Yes | 103.03 |  | 22/11/2023 | 5 | 33.58 | 1.81 | MVS
478 | HOOGHLY | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020553 | SM/18981 | Augmentation |  |  |  | 10/03/2023 | 0 | 103.03 | Yes | 103.03 |  | 22/11/2023 | 6 | 56.65 | 9.56 | MVS
479 | HOOGHLY | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT ' | TSM/020220 | SM/19013 | New | Arambug Sub-Division | Assistant Engineer | Junior Engineer (Civill) | 28/12/2022 | 534 | 312.74 | Yes | 312.74 | 27/03/2023 | 30/10/2023 | 7 | 231.5 | 129.48 | MVS
480 | HOOGHLY | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly | TSM/018054 | SM/19014 | New |  |  |  | 28/12/2022 | 335 | 211.71 | Yes | 211.71 | 31/01/2023 | 30/10/2023 | 4 | 125.95 | 42.72 | MVS
481 | HOOGHLY | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT ' | TSM/020221 | SM/19015 | New |  |  |  | 28/12/2022 | 296 | 170.87 | Yes | 170.87 | 03/02/2023 | 30/10/2023 | 4 | 111.3 | 52.47 | MVS
482 | HOOGHLY | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | TSM/018539 | SM/19036 | Augmentation | Chinsuria Sub-Division | Assistant Engineer (Civil) |  | 28/12/2022 | 103628 | 25800.8 | Yes | 25800.8 | 20/01/2025 | 26/09/2024 | 24 | 31768.6 | 5600.68 | MVS
483 | HOOGHLY | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | TSM/011658 | SM/19161 | Augmentation |  |  |  | 16/11/2022 | 1522 | 51.21 | Yes | 51.21 | 03/10/2024 | 17/04/2025 | 4 | 22.66 | 20.32 | MVS
Total | [9 empty] | 979405 | 242178.38 |  | 242178.38 |  |  | 4723 | 208646.26 | 108183.98