## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | TSM/005648 | SM/06713 | Retrofitting |  |  |  | 28/08/2020 | 846 | 63.09 | Yes | 63.09 |  | 04/11/2020 | 6 | 120.95 | 63.09 | MVS
2 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | TSM/005653 | SM/06714 | Retrofitting |  |  |  | 28/08/2020 | 1160 | 79.55 | Yes | 79.55 |  | 09/11/2020 | 12 | 71.24 | 26.8 | MVS
3 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme | TSM/005654 | SM/06715 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 1042 | 73.1 | Yes | 73.1 | 22/08/2024 | 06/05/2022 | 8 | 28 | 0 | MVS
4 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme | TSM/005649 | SM/06716 | Retrofitting |  |  |  | 28/08/2020 | 1375 | 93.35 | Yes | 93.35 |  | 04/11/2020 | 8 | 180.04 | 90.54 | MVS
5 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme | TSM/005650 | SM/06717 | Retrofitting |  |  |  | 28/08/2020 | 1150 | 80.45 | Yes | 80.45 |  | 04/11/2020 | 9 | 154.67 | 61.85 | MVS
6 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | TSM/005658 | SM/06718 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE-USD | 28/08/2020 | 1460 | 94.59 | Yes | 94.59 |  | 12/10/2020 | 10 | 166.65 | 73.48 | MVS
7 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme | TSM/005657 | SM/06719 | Retrofitting |  |  |  | 28/08/2020 | 952 | 67.6 | Yes | 67.6 |  | 12/10/2020 | 6 | 100.59 | 67.5 | MVS
8 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme | TSM/005655 | SM/06720 | Retrofitting |  |  |  | 28/08/2020 | 1413 | 92.54 | Yes | 92.54 |  | 12/10/2020 | 11 | 227.52 | 91.09 | MVS
9 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | TSM/005656 | SM/06721 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 1051 | 72.52 | Yes | 72.52 | 22/08/2024 | 20/11/2024 | 8 | 23.67 | 24.65 | MVS
10 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | TSM/005660 | SM/06774 | Retrofitting | Howrah Sadar Sub-Division | AE/SADAR | JE Sadar | 28/08/2020 | 1035 | 69.51 | Yes | 69.51 |  | 05/11/2020 | 9 | 116.86 | 55.16 | MVS
11 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | TSM/005661 | SM/06775 | Retrofitting |  |  |  | 28/08/2020 | 1593 | 99.82 | Yes | 99.82 |  | 25/08/2020 | 50 | 221.07 | 98.35 | MVS
12 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) | TSM/005662 | SM/06776 | Retrofitting |  |  |  | 28/08/2020 | 1590 | 99.91 | Yes | 99.91 |  | 13/07/2021 | 16 | 155.53 | 99.91 | MVS
13 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) | TSM/005663 | SM/06777 | Retrofitting |  |  |  | 28/08/2020 | 1590 | 99.91 | Yes | 99.91 |  | 29/03/2023 | 16 | 99.35 | 78.72 | MVS
14 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | TSM/005664 | SM/06778 | Retrofitting |  |  |  | 28/08/2020 | 1590 | 99.91 | Yes | 99.91 |  | 16/10/2020 | 23 | 117.87 | 46.42 | MVS
15 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | TSM/005665 | SM/06779 | Retrofitting |  |  |  | 28/08/2020 | 1400 | 89.06 | Yes | 89.06 |  | 05/11/2020 | 10 | 127.48 | 89.06 | MVS
16 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | TSM/005666 | SM/06780 | Retrofitting |  |  |  | 28/08/2020 | 1200 | 77.58 | Yes | 77.58 |  | 13/07/2021 | 24 | 152 | 64.31 | MVS
17 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | TSM/005667 | SM/06781 | Retrofitting |  |  |  | 28/08/2020 | 1050 | 69.04 | Yes | 69.04 |  | 05/11/2020 | 11 | 105.26 | 20.87 | MVS
18 | HOWRAH | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | TSM/005668 | SM/06782 | Retrofitting |  |  |  | 28/08/2020 | 1035 | 68.15 | Yes | 68.15 |  | 05/11/2020 | 17 | 119.59 | 34.07 | MVS
19 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | TSM/005643 | SM/06783 | Retrofitting |  |  |  | 28/08/2020 | 1340 | 83.47 | Yes | 83.47 |  | 09/11/2020 | 7 | 161.1 | 83.47 | MVS
20 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | TSM/005644 | SM/06784 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 1195 | 78.15 | Yes | 78.15 |  | 09/11/2020 | 9 | 146.54 | 66.24 | MVS
21 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | TSM/005647 | SM/06785 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 1211 | 83.99 | Yes | 83.99 |  | 15/06/2022 | 14 | 156.23 | 63.11 | MVS
22 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | TSM/005645 | SM/06786 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 1410 | 94.88 | Yes | 94.88 |  | 13/10/2020 | 11 | 223.8 | 74.63 | MVS
23 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) | TSM/005646 | SM/06787 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 2110 | 90.51 | Yes | 90.51 | 17/12/2024 | 05/03/2025 | 7 | 80.76 | 65.92 | MVS
24 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | TSM/005652 | SM/06788 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 28/08/2020 | 1494 | 97.34 | Yes | 97.34 |  | 12/10/2020 | 8 | 152.93 | 62 | MVS
25 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | TSM/005651 | SM/06789 | Retrofitting | Ulberia Sub-Division | AE/Ulu |  | 28/08/2020 | 777 | 59.15 | Yes | 59.15 |  | 15/06/2022 | 14 | 108.81 | 0 | MVS
26 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | TSM/006296 | SM/07008 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 1500 | 98.14 | Yes | 98.14 | 17/12/2024 | 06/05/2022 | 8 | 97.64 | 78.3 | MVS
27 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | TSM/006297 | SM/07009 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 639 | 50.47 | Yes | 50.47 | 04/11/2024 | 06/05/2022 | 5 | 38.06 | 21.85 | MVS
28 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | TSM/006295 | SM/07010 | Retrofitting | Ulberia Sub-Division | AE/Ulu |  | 25/09/2020 | 1457 | 99.28 | Yes | 99.28 |  | 27/11/2020 | 8 | 162.81 | 82.18 | MVS
29 | HOWRAH | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) | TSM/006301 | SM/07074 | Retrofitting |  |  |  | 25/09/2020 | 1550 | 99.1 | Yes | 99.1 |  | 11/02/2021 | 6 | 150.18 | 65.37 | MVS
30 | HOWRAH | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | TSM/006302 | SM/07075 | Retrofitting |  |  |  | 25/09/2020 | 2600 | 99.1 | Yes | 99.1 |  | 17/02/2022 | 8 | 100.94 | 0 | MVS
31 | HOWRAH | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | TSM/006303 | SM/07076 | Retrofitting |  |  |  | 25/09/2020 | 1450 | 99.1 | Yes | 99.1 |  | 10/02/2021 | 4 | 191.46 | 0 | MVS
32 | HOWRAH | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | TSM/006304 | SM/07077 | Retrofitting |  |  |  | 25/09/2020 | 1583 | 99.1 | Yes | 99.1 |  | 13/07/2021 | 13 | 130.5 | 0 | MVS
33 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | TSM/006293 | SM/07395 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 2466 | 158.03 | Yes | 158.03 |  | 25/01/2022 | 12 | 137.92 | 105.48 | MVS
34 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | TSM/006292 | SM/07396 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 2234 | 139.91 | Yes | 139.91 | 17/12/2024 | 20/06/2022 | 8 | 131.63 | 37.2 | MVS
35 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II | TSM/006294 | SM/07464 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 2472 | 164.03 | Yes | 164.03 | 17/12/2024 | 05/01/2021 | 4 | 98.76 | 56.33 | MVS
36 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block | TSM/006300 | SM/07465 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 1711 | 123.54 | Yes | 123.54 | 09/01/2023 | 31/05/2021 | 2 | 117.7 | 0 | MVS
37 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | TSM/006299 | SM/07466 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 2464 | 167.14 | Yes | 167.14 | 13/01/2023 | 23/12/2021 | 9 | 151.3 | 109.37 | MVS
38 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | TSM/006298 | SM/07467 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 25/09/2020 | 3453 | 232.33 | Yes | 232.33 |  | 17/09/2021 | 23 | 272.11 | 198.98 | MVS
39 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006749 | SM/07880 | Retrofitting | Ulberia Sub-Division | AE/RWS | JE/USD | 04/12/2020 | 2452 | 157.59 | Yes | 157.59 | 29/03/2023 | 10/05/2023 | 6 | 270.36 | 0 | MVS
40 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006747 | SM/07881 | Retrofitting | RWS Howrah Sub-Division | AE/RWS | JE/RWS/Udaynaryanpur | 04/12/2020 | 1744 | 112.45 | Yes | 112.45 |  | 06/04/2022 | 2 | 186.12 | 0 | MVS
41 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | TSM/006748 | SM/07882 | Retrofitting | Ulberia Sub-Division | AE/Ulu |  | 04/12/2020 | 2697 | 174.48 | Yes | 174.48 | 14/01/2025 | 06/04/2022 | 11 | 158.03 | 0 | MVS
42 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | TSM/006746 | SM/07883 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 04/12/2020 | 2184 | 140.91 | Yes | 140.91 | 27/06/2024 | 13/09/2024 | 9 | 136.22 | 0 | MVS
43 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | TSM/006745 | SM/07884 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 04/12/2020 | 2203 | 135.21 | Yes | 135.21 | 20/08/2025 | 30/05/2025 | 6 | 129.19 | 0 | MVS
44 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) | TSM/006744 | SM/07885 | Retrofitting | Ulberia Sub-Division | AE/Ulu |  | 04/12/2020 | 1505 | 96.53 | Yes | 96.53 | 04/04/2025 | 02/05/2023 | 3 | 96.53 | 0 | MVS
45 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | TSM/006742 | SM/07886 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 04/12/2020 | 2721 | 173.76 | Yes | 173.76 |  | 30/08/2022 | 8 | 159.82 | 0 | MVS
46 | HOWRAH | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006743 | SM/07887 | Retrofitting | RWS Howrah Sub-Division | AE/RWS | JE/RWS/Udaynaryanpur | 04/12/2020 | 2275 | 147.18 | Yes | 147.18 | 16/01/2025 | 24/02/2025 | 2 | 111.88 | 0 | MVS
47 | HOWRAH | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | TSM/005659 | SM/08582 | Retrofitting |  |  |  | 28/08/2020 | 45330 | 3304.1 | Yes | 3304.1 | 20/08/2025 | 20/01/2023 | 188 | 2498.11 | 540.83 | MVS
48 | HOWRAH | Rejuvenation of Amta Piped water supply scheme. | TSM/005366 | SM/08966 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | 17/07/2020 | 9981 | 2511.74 | Yes | 2511.74 | 20/08/2025 | 08/04/2024 | 16 | 2235.61 | 0 | MVS
49 | HOWRAH | Chakur water supply scheme. | TSM/008182 | SM/08987 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 19/08/2021 | 800 | 292.32 | Yes | 292.32 | 02/08/2023 | 11/01/2022 | 15 | 244.08 | 0 | MVS
50 | HOWRAH | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS. | TSM/008212 | SM/09105 | Retrofitting | Ulberia Sub-Division | AE/Ulu | JE/USD | 19/08/2021 | 1033 | 94.09 | Yes | 94.09 |  | 07/12/2022 | 1 | 4.48 | 0 | MVS
51 | HOWRAH | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | TSM/008640 | SM/09347 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 29/09/2021 | 2789 | 546.45 | Yes | 546.45 | 29/07/2024 | 02/05/2023 | 26 | 591.54 | 0 | MVS
52 | HOWRAH | Augmentation of Ground water based PWSS Pancharul | TSM/008635 | SM/09348 | Augmentation | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 29/09/2021 | 3479 | 762.1 | Yes | 762.1 | 13/09/2024 | 07/06/2024 | 17 | 630.89 | 0 | MVS
53 | HOWRAH | Augmentation of Ground water based PWSS Mankur Deulgram | TSM/008627 | SM/09349 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 29/09/2021 | 5518 | 993.4 | Yes | 993.4 | 13/09/2024 | 11/06/2024 | 15 | 1071.43 | 0 | MVS
54 | HOWRAH | Augmentation of Ground water based PWSS Kanupat. | TSM/008622 | SM/09350 | Augmentation | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 29/09/2021 | 1208 | 414.71 | Yes | 414.71 | 20/08/2025 | 27/06/2022 | 12 | 274.81 | 0 | MVS
55 | HOWRAH | Augmentation of Ground water based PWSS Bhurshit Bamunpara | TSM/008620 | SM/09351 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 29/09/2021 | 2781 | 618.61 | Yes | 618.61 | 13/09/2024 | 24/07/2023 | 20 | 714.08 | 0 | MVS
56 | HOWRAH | Augmentation of Ground water PWSS for Islampur | TSM/008589 | SM/09428 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | 29/09/2021 | 4465 | 754.25 | Yes | 754.25 | 17/06/2022 | 01/12/2021 | 11 | 802.55 | 0 | MVS
57 | HOWRAH | Aumentation of PWSS for Surikhali | TSM/008596 | SM/09429 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | 29/09/2021 | 992 | 333.75 | Yes | 333.75 | 29/11/2024 | 11/04/2022 | 30 | 245.25 | 0 | MVS
58 | HOWRAH | Augmentation of Ground Water Based PWSS for Shekrahati | TSM/008595 | SM/09586 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 08/10/2021 | 3440 | 600.2 | Yes | 600.2 | 21/10/2024 | 27/11/2024 | 19 | 508.8 | 0 | MVS
59 | HOWRAH | Augmentation of Nischintapur piped water supply scheme. | TSM/008092 | SM/09720 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | 19/08/2021 | 0 | 589.85 | Yes | 589.85 | 20/08/2025 | 29/03/2024 | 13 | 494.42 | 0 | MVS
60 | HOWRAH | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | TSM/008801 | SM/09930 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | 22/11/2021 | 2475 | 679.04 | Yes | 679.04 | 29/01/2025 | 07/04/2022 | 22 | 313.31 | 0 | MVS
61 | HOWRAH | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | TSM/008354 | SM/10020 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 19/08/2021 | 7281 | 1524.22 | Yes | 1524.22 | 20/08/2025 | 12/06/2024 | 26 | 1428.62 | 0 | MVS
62 | HOWRAH | Augmentation of Kanpur Piped water supply scheme (Zone-II) | TSM/008513 | SM/10021 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | 29/09/2021 | 3664 | 1553.14 | Yes | 1553.14 | 04/04/2025 | 26/06/2024 | 39 | 864.61 | 0 | MVS
63 | HOWRAH | Augmentation of Maju piped water supply scheme. | TSM/008091 | SM/10035 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 29/09/2021 | 4749 | 1692.75 | Yes | 1692.75 | 13/09/2024 | 20/06/2024 | 15 | 1400.1 | 0 | MVS
64 | HOWRAH | Augmentation of Ground water based PWSS Pulgustia | TSM/008637 | SM/10143 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 16/12/2021 | 3842 | 708.72 | Yes | 708.72 | 05/02/2024 | 10/05/2023 | 12 | 713.25 | 0 | MVS
65 | HOWRAH | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | TSM/008353 | SM/10145 | Augmentation | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | 19/08/2021 | 5786 | 1092.62 | Yes | 1092.62 | 31/07/2024 | 27/06/2023 | 17 | 778.55 | 0 | MVS
66 | HOWRAH | Augmentation of Ground water based PWSS Jujarsah | TSM/008639 | SM/10146 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 29/09/2021 | 4553 | 1600.62 | Yes | 1600.62 | 13/09/2024 | 08/07/2024 | 17 | 1827.67 | 0 | MVS
67 | HOWRAH | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | TSM/011600 | SM/11000 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 25/04/2022 | 3323 | 965.98 | Yes | 965.98 | 13/09/2024 | 04/09/2023 | 23 | 921.77 | 0 | MVS
68 | HOWRAH | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | TSM/011420 | SM/11007 | New | RWS Howrah Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | 25/04/2022 | 1774 | 697.67 | Yes | 697.67 | 17/12/2024 | 10/06/2024 | 15 | 573.6 | 0 | MVS
69 | HOWRAH | Makardaha PWSS with provision of FHTC in connection of Domjur Block | TSM/010688 | SM/11159 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 16/03/2022 | 3297 | 1084.15 | Yes | 1084.15 | 12/02/2025 | 07/05/2024 | 25 | 986.96 | 0 | MVS
70 | HOWRAH | Rampur PWSS | TSM/008769 | SM/11168 | Augmentation | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 16/03/2022 | 1965 | 614.27 | Yes | 614.27 | 15/03/2024 | 03/05/2023 | 12 | 361.08 | 0 | MVS
71 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | TSM/011679 | SM/11221 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 25/04/2022 | 1985 | 612.7 | Yes | 612.7 | 13/09/2024 | 08/05/2023 | 18 | 513.76 | 0 | MVS
72 | HOWRAH | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | TSM/011678 | SM/11222 | New | RWS Howrah Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | 25/04/2022 | 1248 | 469.24 | Yes | 469.24 | 13/09/2024 | 05/11/2024 | 9 | 459.17 | 0 | MVS
73 | HOWRAH | Augmentation of Khalatpur PWSS | TSM/008963 | SM/11271 | Augmentation | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 16/03/2022 | 2484 | 985.37 | Yes | 985.37 | 12/03/2025 | 16/04/2025 | 30 | 586.9 | 0 | MVS
74 | HOWRAH | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | TSM/011688 | SM/11458 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | 25/04/2022 | 3079 | 1187.53 | Yes | 1187.53 | 17/12/2024 | 08/04/2025 | 41 | 1060.99 | 0 | MVS
75 | HOWRAH | Rudrapur PWSS with provision of FHTC connection. | TSM/010920 | SM/11515 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 30/03/2022 | 2762 | 914.73 | Yes | 914.73 | 17/12/2024 | 25/04/2023 | 17 | 802.43 | 0 | MVS
76 | HOWRAH | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | TSM/010977 | SM/11572 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | 30/03/2022 | 3092 | 920.9 | Yes | 920.9 | 20/03/2025 | 23/09/2024 | 16 | 302.38 | 0 | MVS
77 | HOWRAH | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | TSM/011001 | SM/11573 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 30/03/2022 | 2942 | 808.74 | Yes | 808.74 | 24/02/2025 | 22/04/2025 | 22 | 364.05 | 0 | MVS
78 | HOWRAH | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | TSM/011292 | SM/11574 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | 30/03/2022 | 2011 | 699.66 | Yes | 699.66 | 14/01/2025 | 09/04/2025 | 18 | 201.12 | 0 | MVS
79 | HOWRAH | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | TSM/011056 | SM/11641 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | 25/04/2022 | 3060 | 997.11 | Yes | 997.11 | 06/02/2024 | 03/08/2023 | 7 | 1189.84 | 0 | MVS
80 | HOWRAH | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | TSM/011760 | SM/11711 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 25/04/2022 | 3591 | 1072.81 | Yes | 1072.81 | 31/12/2024 | 27/11/2024 | 14 | 886.21 | 0 | MVS
81 | HOWRAH | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | TSM/011766 | SM/11717 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 25/04/2022 | 1398 | 475.19 | Yes | 475.19 | 14/01/2025 | 25/04/2023 | 6 | 417.64 | 0 | MVS
82 | HOWRAH | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | TSM/011761 | SM/11718 | New | RWS Howrah Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | 25/04/2022 | 1793 | 706.38 | Yes | 706.38 | 30/01/2023 | 18/04/2023 | 6 | 512.77 | 0 | MVS
83 | HOWRAH | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | TSM/011570 | SM/11719 | New | RWS Howrah Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | 25/04/2022 | 3480 | 932.95 | Yes | 932.95 | 04/04/2025 | 23/06/2025 | 13 | 800.96 | 0 | MVS
84 | HOWRAH | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | TSM/011550 | SM/11720 | New | RWS Howrah Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | 25/04/2022 | 1232 | 640.07 | Yes | 640.07 | 27/02/2023 | 24/07/2023 | 12 | 516.33 | 0 | MVS
85 | HOWRAH | Baniara PWSS with provision of FHTC connection | TSM/010919 | SM/11722 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | 25/04/2022 | 1976 | 803.44 | Yes | 803.44 | 13/09/2022 | 12/08/2022 | 10 | 732.74 | 0 | MVS
86 | HOWRAH | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | TSM/011532 | SM/11723 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 25/04/2022 | 3513 | 853.17 | Yes | 853.17 | 13/09/2024 | 27/04/2023 | 12 | 500.21 | 0 | MVS
87 | HOWRAH | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | TSM/011795 | SM/11790 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | 25/04/2022 | 744 | 215.28 | Yes | 215.28 | 18/12/2024 | 10/05/2023 | 18 | 169.99 | 0 | MVS
88 | HOWRAH | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | TSM/011548 | SM/11793 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | 25/04/2022 | 3240 | 896.37 | Yes | 896.37 | 16/12/2024 | 14/08/2023 | 13 | 827.35 | 0 | MVS
89 | HOWRAH | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | TSM/011491 | SM/11853 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 20/05/2022 | 3518 | 1056.32 | Yes | 1056.32 | 24/02/2025 | 21/06/2024 | 14 | 880.77 | 0 | MVS
90 | HOWRAH | Khorda Etarai Piped Water Supply Scheme | TSM/012017 | SM/11892 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | 20/05/2022 | 733 | 323.64 | Yes | 323.64 | 13/09/2024 | 19/11/2024 | 14 | 295.61 | 0 | MVS
91 | HOWRAH | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | TSM/011933 | SM/11893 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 20/05/2022 | 2273 | 1018.55 | Yes | 1018.55 | 20/08/2025 | 11/06/2024 | 16 | 818.61 | 0 | MVS
92 | HOWRAH | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | TSM/011932 | SM/11894 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 20/05/2022 | 1819 | 760.71 | Yes | 760.71 | 17/03/2025 | 04/04/2023 | 14 | 703.84 | 0 | MVS
93 | HOWRAH | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | TSM/011009 | SM/12270 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | 30/03/2022 | 4274 | 1326.85 | Yes | 1326.85 | 12/02/2025 | 22/07/2024 | 14 | 1170.07 | 0 | MVS
94 | HOWRAH | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | TSM/011584 | SM/12562 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 25/04/2022 | 5151 | 1842.31 | Yes | 1842.31 | 09/04/2025 | 02/06/2025 | 11 | 1723.56 | 0 | MVS
95 | HOWRAH | Augmentation of Bamunhati Water Supply Scheme | TSM/012517 | SM/12874 | Augmentation | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | 20/05/2022 | 4238 | 1303.9 | Yes | 1303.9 | 08/03/2025 | 12/04/2023 | 26 | 1068.68 | 0 | MVS
96 | HOWRAH | ICHAPUR PWSS | TSM/012520 | SM/13629 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 22/08/2022 | 1335 | 586.48 | Yes | 586.48 | 17/12/2024 | 19/04/2023 | 14 | 547.66 | 0 | MVS
97 | HOWRAH | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | TSM/015623 | SM/13747 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 09/09/2022 | 1053 | 452.58 | Yes | 452.58 | 11/07/2024 | 24/07/2023 | 7 | 435.93 | 0 | MVS
98 | HOWRAH | Gopalpur Piped Water Supply Scheme | TSM/015625 | SM/13748 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 09/09/2022 | 1519 | 539.15 | Yes | 539.15 | 13/09/2024 | 08/05/2023 | 12 | 439.37 | 0 | MVS
99 | HOWRAH | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | TSM/015269 | SM/13749 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 09/09/2022 | 3486 | 975.18 | Yes | 975.18 | 29/03/2023 | 10/05/2023 | 6 | 750.7 | 0 | MVS
100 | HOWRAH | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | TSM/015228 | SM/13750 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | 09/09/2022 | 1101 | 524.14 | Yes | 524.14 | 14/01/2025 | 20/04/2023 | 11 | 499.15 | 0 | MVS
101 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015610 | SM/13751 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 09/09/2022 | 3095 | 700.58 | Yes | 700.58 | 05/05/2025 | 19/11/2024 | 9 | 442.88 | 0 | MVS
102 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015621 | SM/13752 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 09/09/2022 | 11570 | 927.57 | Yes | 927.57 | 05/05/2025 | 12/08/2022 | 18 | 640.17 | 0 | MVS
103 | HOWRAH | Paschim Panchla Piped Water Supply Scheme. | TSM/014766 | SM/13768 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 22/08/2022 | 4347 | 716.22 | Yes | 716.22 | 13/09/2024 | 20/06/2024 | 11 | 725.79 | 0 | MVS
104 | HOWRAH | Sibpur Piped Water Supply Scheme. | TSM/014685 | SM/13769 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | 22/08/2022 | 1174 | 597.87 | Yes | 597.87 | 13/09/2024 | 18/04/2023 | 10 | 458.04 | 0 | MVS
105 | HOWRAH | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | TSM/012056 | SM/13770 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 22/08/2022 | 1774 | 792.12 | Yes | 792.12 | 05/05/2025 | 21/04/2023 | 15 | 411.4 | 0 | MVS
106 | HOWRAH | Khadinan Piped Water Supply Scheme | TSM/015626 | SM/13847 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 09/09/2022 | 2051 | 791.35 | Yes | 791.35 | 31/07/2024 | 27/04/2023 | 9 | 453 | 0 | MVS
107 | HOWRAH | Patinan Piped Water Supply Scheme | TSM/015627 | SM/13848 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | 09/09/2022 | 956 | 430.85 | Yes | 430.85 | 13/09/2024 | 05/04/2023 | 11 | 381.03 | 0 | MVS
108 | HOWRAH | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | TSM/010279 | SM/14095 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR | JE Sadar | 17/02/2022 | 27364 | 8211.71 | Yes | 8211.71 | 03/09/2025 | 26/04/2024 | 55 | 7817.46 | 0 | MVS
109 | HOWRAH | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | TSM/015277 | SM/14154 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 09/09/2022 | 4372 | 1460.26 | Yes | 1460.26 | 05/05/2025 | 04/10/2024 | 20 | 1222.83 | 0 | MVS
110 | HOWRAH | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015622 | SM/14155 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | 09/09/2022 | 4308 | 1118.67 | Yes | 1118.67 | 09/04/2025 | 07/05/2024 | 18 | 947.99 | 0 | MVS
111 | HOWRAH | Bhandardah PWSS with provision of FHTC connection | TSM/010904 | SM/14197 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 16/03/2022 | 3527 | 1149.77 | Yes | 1149.77 |  | 27/11/2024 | 7 | 922.52 | 0 | MVS
112 | HOWRAH | Jaynagar Piped Water Supply Scheme | TSM/018489 | SM/14865 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 16/11/2022 | 3079 | 761.37 | Yes | 761.37 | 09/04/2025 | 05/06/2025 | 8 | 694.25 | 0 | MVS
113 | HOWRAH | Sealdanga Piped Water Supply Scheme | TSM/018484 | SM/14866 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 16/11/2022 | 1709 | 689.76 | Yes | 689.76 | 05/05/2025 | 04/04/2023 | 10 | 565.61 | 0 | MVS
114 | HOWRAH | Sonatala Piped Water Supply Scheme | TSM/015612 | SM/14949 | New | RWS Howrah Sub-Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | 09/09/2022 | 2988 | 729.29 | Yes | 729.29 | 20/08/2025 | 07/05/2025 | 12 | 193.77 | 0 | MVS
115 | HOWRAH | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | TSM/011062 | SM/15186 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | 16/11/2022 | 3206 | 826.95 | Yes | 826.95 | 15/07/2023 | 16/08/2022 | 6 | 127.38 | 0 | MVS
116 | HOWRAH | Sankardari Mini Piped Water Supply Scheme | TSM/016140 | SM/15189 | New |  |  |  | 30/09/2022 | 91 | 45.72 | Yes | 45.72 | 13/09/2024 | 07/06/2023 | 2 | 36.79 | 0 | MVS
117 | HOWRAH | Senpur Dwitiya Piped Water Supply Scheme | TSM/016151 | SM/15199 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 30/09/2022 | 67 | 43.09 | Yes | 43.09 | 13/09/2024 | 07/06/2023 | 2 | 37.41 | 0 | MVS
118 | HOWRAH | Manirampur Piped Water Supply Scheme | TSM/016149 | SM/15200 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 30/09/2022 | 75 | 43.19 | Yes | 43.19 | 13/09/2024 | 07/06/2023 | 2 | 36.79 | 0 | MVS
119 | HOWRAH | Shyamchak Mini Piped water Supply Scheme | TSM/016331 | SM/15284 | New | Howrah Sadar Sub-Division | AE/SADAR |  | 26/09/2022 | 41 | 40.6 | Yes | 40.6 | 13/09/2024 | 07/06/2023 | 2 | 36.79 | 0 | MVS
120 | HOWRAH | Matinala Piped Water Supply Scheme | TSM/016162 | SM/15285 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 26/09/2022 | 4568 | 797.05 | Yes | 797.05 | 20/08/2025 | 09/09/2024 | 17 | 657.01 | 0 | MVS
121 | HOWRAH | Purbba Gazipur Piped Water Supply Scheme | TSM/016144 | SM/15287 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 26/09/2022 | 91 | 45.5 | Yes | 45.5 | 13/09/2024 | 07/06/2023 | 2 | 36.79 | 0 | MVS
122 | HOWRAH | Mollar Chak Piped Water Supplu scheme | TSM/016154 | SM/15288 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | 26/09/2022 | 68 | 44.36 | Yes | 44.36 | 13/09/2024 | 07/06/2023 | 2 | 36.79 | 0 | MVS
123 | HOWRAH | Sankhali Piped Water Supply Scheme | TSM/015853 | SM/15289 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 26/09/2022 | 1058 | 372.64 | Yes | 372.64 | 13/09/2024 | 12/04/2023 | 10 | 341.28 | 0 | MVS
124 | HOWRAH | Charkata Pukuria Piped Water Supply Scheme | TSM/016153 | SM/15290 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 26/09/2022 | 54 | 42.1 | Yes | 42.1 | 26/09/2023 | 07/06/2023 | 1 | 36.7 | 0 | MVS
125 | HOWRAH | Chak Kadamtala Piped Water Supply scheme | TSM/016145 | SM/16557 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 30/09/2022 | 69 | 40.27 | Yes | 40.27 | 26/09/2023 | 07/06/2023 | 1 | 36.7 | 0 | MVS
126 | HOWRAH | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | TSM/011301 | SM/16760 | New | Howrah Mechanical Sub-Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 30/03/2022 | 3395 | 999.07 | Yes | 999.07 | 31/07/2024 | 12/04/2023 | 14 | 788.98 | 0 | MVS
127 | HOWRAH | Kamina Piped Water Supply Scheme with provision of FHTC | TSM/011290 | SM/16927 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | 30/03/2022 | 2000 | 721.94 | Yes | 721.94 | 14/12/2024 | 23/11/2023 | 14 | 737.31 | 0 | MVS
128 | HOWRAH | Augmentation of Keshabpur Water supply scheme | TSM/010465 | SM/16947 | Augmentation | Howrah Sadar Sub-Division | AE/SADAR |  | 16/03/2022 | 2824 | 857.9 | Yes | 857.9 | 18/12/2024 | 04/04/2023 | 8 | 564.13 | 0 | MVS
129 | HOWRAH | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | TSM/011909 | SM/17175 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 20/05/2022 | 3610 | 986.69 | Yes | 986.69 | 17/12/2024 | 04/04/2023 | 9 | 905.04 | 0 | MVS
130 | HOWRAH | Dakshin Panchla Piped Water Supply Scheme | TSM/018488 | SM/17196 | New | Howrah Sadar Sub-Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | 28/12/2022 | 808 | 236.59 | Yes | 236.59 | 04/02/2023 | 04/04/2023 | 6 | 235.4 | 0 | MVS
131 | HOWRAH | Ghuteghari Piped Water Supply Scheme | TSM/018482 | SM/17198 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | 28/12/2022 | 77 | 55.7 | Yes | 55.7 | 13/09/2024 | 19/11/2024 | 3 | 3.53 | 0 | MVS
132 | HOWRAH | Shibgachhia Piped Water Supply Scheme | TSM/018487 | SM/18193 | New | Ulberia Sub-Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | 28/12/2022 | 761 | 507.75 | Yes | 507.75 | 13/09/2024 | 18/07/2023 | 10 | 342.82 | 0 | MVS
133 | HOWRAH | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | TSM/010806 | SM/18398 | Augmentation |  |  |  | 16/03/2022 | 8036 | 1887.15 | Yes | 1887.15 | 12/02/2025 | 26/07/2024 | 27 | 1856.35 | 0 | MVS
134 | HOWRAH | Sherpur Piped Water Supply Scheme | TSM/018486 | SM/18426 | New |  |  |  | 16/11/2022 | 5601 | 2000.35 | Yes | 2000.35 | 04/04/2025 | 29/04/2025 | 7 | 133.06 | 0 | MVS
135 | HOWRAH | Bedhi Chandrapur Piped Water Supply Scheme | TSM/012815 | SM/18490 | New | RWS Howrah Sub-Division | AE/RWS | JE/BLK/amta2 | 22/08/2022 | 1254 | 497.17 | Yes | 497.17 | 05/05/2025 | 22/04/2025 | 8 | 438.13 | 0 | MVS
136 | HOWRAH | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | TSM/014806 | SM/18560 | Augmentation |  |  |  | 22/08/2022 | 5505 | 1424.21 | Yes | 1424.21 | 05/05/2025 | 07/08/2023 | 14 | 1155.01 | 0 | MVS
137 | HOWRAH | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | TSM/017917 | SM/18561 | New |  |  |  | 30/09/2022 | 3383 | 1636.21 | Yes | 1636.21 | 06/05/2025 | 18/09/2024 | 15 | 1073.15 | 0 | MVS
138 | HOWRAH | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | TSM/011637 | SM/18562 | New |  |  |  | 22/08/2022 | 3924 | 1384.19 | Yes | 1384.19 | 20/08/2025 | 06/11/2024 | 20 | 824.46 | 0 | MVS
139 | HOWRAH | PANCHLA PIPED WATER SUPPLY SCHEME. | TSM/014879 | SM/18563 | New |  |  |  | 22/08/2022 | 6201 | 1342.84 | Yes | 1342.84 | 13/09/2024 | 20/06/2024 | 13 | 1268.48 | 0 | MVS
140 | HOWRAH | Baniban Zone-III Piped water Supply Scheme | TSM/018485 | SM/18564 | New | Ulberia Sub-Division | AE/Ulu | JE-USD | 28/12/2022 | 3716 | 1606.96 | Yes | 1606.96 | 06/05/2025 | 12/08/2025 | 5 | 1154.56 | 0 | MVS
141 | HOWRAH | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | TSM/017876 | SM/18565 | Augmentation |  |  |  | 30/09/2022 | 3713 | 1175.93 | Yes | 1175.93 | 27/12/2022 | 07/08/2023 | 8 | 610.13 | 0 | MVS
142 | HOWRAH | Baniban Zone-I Piped Water Supply Scheme | TSM/017947 | SM/18566 | New | Ulberia Sub-Division | AE/Ulu | JE-USD | 30/09/2022 | 6036 | 1511.88 | Yes | 1511.88 | 02/02/2023 | 16/08/2023 | 2 | 1062.62 | 0 | MVS
143 | HOWRAH | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | TSM/017891 | SM/18567 | Augmentation |  |  |  | 30/09/2022 | 4781 | 1416.25 | Yes | 1416.25 | 08/03/2025 | 07/08/2023 | 16 | 1111.59 | 0 | MVS
144 | HOWRAH | Ground Water Based Raspur PWSS | TSM/017956 | SM/18719 | New |  |  |  | 30/09/2022 | 3327 | 1398.26 | Yes | 1398.26 | 06/05/2025 | 08/07/2025 | 9 | 1000.71 | 0 | MVS
145 | HOWRAH | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | TSM/015233 | SM/18747 | New |  |  |  | 09/09/2022 | 3464 | 1102.79 | Yes | 1102.79 | 08/03/2025 | 16/08/2022 | 9 | 834.53 | 0 | MVS
146 | HOWRAH | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. | TSM/015619 | SM/18748 | New |  |  |  | 09/09/2022 | 5855 | 1400.74 | Yes | 1400.74 | 21/03/2023 | 16/08/2022 | 3 | 996.44 | 0 | MVS
147 | HOWRAH | Source Augmentation of Majhu Khetra Water Supply Scheme | TSM/021407 | SM/18841 | Augmentation |  |  |  | 10/03/2023 | 0 | 115.24 | Yes | 115.24 | 13/09/2024 | 11/03/2024 | 3 | 68.34 | 0 | MVS
148 | HOWRAH | Source Augmentation of Laskarpur Piped Water Supply Scheme | TSM/021371 | SM/18842 | Augmentation |  |  |  | 10/03/2023 | 0 | 222.01 | Yes | 222.01 | 17/12/2024 | 26/06/2024 | 7 | 195.79 | 0 | MVS
149 | HOWRAH | Source Augmentation of Gobindapur Piped Water Supply Scheme | TSM/021367 | SM/18843 | Augmentation |  |  |  | 10/03/2023 | 0 | 145.28 | Yes | 145.28 | 09/04/2025 | 26/06/2024 | 9 | 157.58 | 0 | MVS
150 | HOWRAH | Source Augmentation of Sahapur Piped Water Supply Scheme | TSM/021366 | SM/18844 | Augmentation |  |  |  | 10/03/2023 | 0 | 152.8 | Yes | 152.8 | 22/07/2024 | 17/02/2022 | 4 | 68.36 | 0 | MVS
151 | HOWRAH | Source Augmentation of Beldubi Water Supply Scheme | TSM/021363 | SM/18845 | Augmentation |  |  |  | 10/03/2023 | 0 | 155.14 | Yes | 155.14 | 22/07/2024 | 01/03/2024 | 5 | 75.86 | 0 | MVS
152 | HOWRAH | Source Augmentation of Bikihakola Water Supply Scheme | TSM/021345 | SM/18846 | Augmentation |  |  |  | 10/03/2023 | 0 | 458.77 | Yes | 458.77 | 22/07/2024 | 10/02/2021 | 7 | 74.38 | 0 | MVS
153 | HOWRAH | Source Augmentation of Nakubar Water Supply Scheme | TSM/021308 | SM/18847 | Augmentation |  |  |  | 10/03/2023 | 0 | 189.2 | Yes | 189.2 | 24/09/2024 | 22/07/2022 | 4 | 47.17 | 0 | MVS
154 | HOWRAH | Source Augmentation of Chitnan Water Supply Scheme | TSM/021553 | SM/18848 | Augmentation |  |  |  | 10/03/2023 | 0 | 115.24 | Yes | 115.24 | 16/01/2025 | 16/12/2022 | 4 | 28.78 | 0 | MVS
155 | HOWRAH | Source Augmentation of Garbhabanipur Water Supply Scheme | TSM/021552 | SM/18849 | Augmentation |  |  |  | 10/03/2023 | 0 | 115.24 | Yes | 115.24 | 14/01/2025 | 09/07/2024 | 6 | 100.43 | 0 | MVS
156 | HOWRAH | Source Augmentation of Bauria Water Supply Scheme | TSM/021551 | SM/18850 | Augmentation |  |  |  | 10/03/2023 | 0 | 115.24 | Yes | 115.24 |  | 02/05/2023 | 5 | 90.59 | 0 | MVS
157 | HOWRAH | Source Augmentaion of kulgacchi Water Supply Scheme | TSM/021380 | SM/18882 | Augmentation |  |  |  | 10/03/2023 | 0 | 251.54 | Yes | 251.54 | 17/02/2024 | 24/06/2024 | 7 | 145.75 | 0 | MVS
158 | HOWRAH | Source Augmentation of Amragari Water Supply Scheme | TSM/021379 | SM/18883 | Augmentation |  |  |  | 10/03/2023 | 0 | 491.99 | Yes | 491.99 | 24/09/2024 | 09/07/2024 | 10 | 245.4 | 0 | MVS
159 | HOWRAH | Source Augmentation of Sarda Water Supply Scheme | TSM/021378 | SM/18884 | Augmentation |  |  |  | 10/03/2023 | 0 | 138.99 | Yes | 138.99 | 11/03/2024 | 26/06/2024 | 6 | 75.43 | 0 | MVS
160 | HOWRAH | Source Augmentation of Balichak Water Supply Scheme | TSM/021377 | SM/18885 | Augmentation |  |  |  | 10/03/2023 | 0 | 177.16 | Yes | 177.16 | 11/03/2024 | 24/06/2024 | 6 | 122.11 | 0 | MVS
161 | HOWRAH | Uttar Manasri Piped Water Supply Scheme. | TSM/004182 | SM/18914 | New |  |  |  | 04/12/2020 | 4232 | 1046.52 | Yes | 1046.52 | 15/07/2023 | 16/04/2025 | 7 | 1032.59 | 0 | MVS
162 | HOWRAH | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | TSM/019280 | SM/19186 | Augmentation |  |  |  | 16/11/2022 | 205921 | 55319.55 | Yes | 55319.55 | 20/08/2025 | 17/04/2025 | 71 | 9239.36 | 0 | MVS
163 | HOWRAH | Augmentation of surface water based Sankrail Piped water supply scheme | TSM/019257 | SM/19187 | Augmentation |  |  |  | 16/11/2022 | 154792 | 33980.3 | Yes | 33980.3 | 12/07/2024 | 08/07/2024 | 29 | 29595.59 | 0 | MVS
Total | [9 empty] | 799002 | 192534.42 |  | 192534.42 |  |  | 2198 | 122769.19 | 2797.13