## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | PURBA MEDINIPUR | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | TSM/005473 | SM/06651 | New |  |  |  | 05/11/2019 | 74 | 28.92 | Yes | 28.92 |  | 05/05/2021 | 6 | 28.06 | 55.94 | MVS
2 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme | TSM/005766 | SM/06877 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 28/08/2020 | 2030 | 99.46 | Yes | 99.46 |  | 05/11/2020 | 2 | 152.56 | 144.14 | MVS
3 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | TSM/005767 | SM/06878 | Retrofitting |  |  |  | 28/08/2020 | 1574 | 77.32 | Yes | 77.32 |  | 05/11/2020 | 5 | 148.68 | 147.92 | MVS
4 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | TSM/005768 | SM/06879 | Retrofitting |  |  |  | 28/08/2020 | 745 | 38.01 | Yes | 38.01 |  | 18/12/2020 | 10 | 81.78 | 73.81 | MVS
5 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme | TSM/005769 | SM/06880 | Retrofitting |  |  |  | 28/08/2020 | 1656 | 81.66 | Yes | 81.66 | 16/02/2023 | 05/11/2020 | 3 | 155.99 | 153 | MVS
6 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme | TSM/005770 | SM/06881 | Retrofitting |  |  |  | 28/08/2020 | 1960 | 99.51 | Yes | 99.51 |  | 05/11/2020 | 4 | 95.82 | 150.61 | MVS
7 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme | TSM/005771 | SM/06882 | Retrofitting |  |  |  | 28/08/2020 | 1950 | 99.43 | Yes | 99.43 |  | 05/11/2020 | 2 | 99.22 | 188.57 | MVS
8 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme | TSM/005772 | SM/06883 | Retrofitting |  |  |  | 28/08/2020 | 2000 | 99.43 | Yes | 99.43 |  | 05/11/2020 | 4 | 190.31 | 189.44 | MVS
9 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | TSM/005773 | SM/06884 | Retrofitting |  |  |  | 28/08/2020 | 745 | 37.82 | Yes | 37.82 |  | 18/12/2020 | 8 | 71.98 | 70.86 | MVS
10 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Uttar Khasda W/S Scheme | TSM/005774 | SM/06885 | Retrofitting |  |  |  | 28/08/2020 | 1966 | 99.63 | Yes | 99.63 |  | 05/11/2020 | 2 | 183.73 | 174.55 | MVS
11 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme | TSM/005775 | SM/06886 | Retrofitting |  |  |  | 28/08/2020 | 2020 | 99.67 | Yes | 99.67 |  | 05/11/2020 | 3 | 96.26 | 165.83 | MVS
12 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | TSM/005764 | SM/06887 | Retrofitting |  |  |  | 28/08/2020 | 1995 | 99.71 | Yes | 99.71 |  | 05/11/2020 | 5 | 200.05 | 193.45 | MVS
13 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | TSM/005765 | SM/06888 | Retrofitting |  |  |  | 28/08/2020 | 1955 | 93.57 | Yes | 93.57 |  | 18/12/2020 | 9 | 181.57 | 181.57 | MVS
14 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | TSM/005759 | SM/06889 | Retrofitting |  |  |  | 28/08/2020 | 1114 | 57.01 | Yes | 57.01 |  | 18/12/2020 | 7 | 112.31 | 112.31 | MVS
15 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | TSM/005760 | SM/06890 | Retrofitting |  |  |  | 28/08/2020 | 1842 | 90.86 | Yes | 90.86 |  | 18/12/2020 | 9 | 88.17 | 173.44 | MVS
16 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | TSM/005761 | SM/06891 | Retrofitting |  |  |  | 28/08/2020 | 1698 | 83.27 | Yes | 83.27 |  | 18/12/2020 | 7 | 163.22 | 161.76 | MVS
17 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme | TSM/005762 | SM/06892 | Retrofitting |  |  |  | 28/08/2020 | 1791 | 90.8 | Yes | 90.8 |  | 05/11/2020 | 2 | 86.96 | 161.3 | MVS
18 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | TSM/005763 | SM/06893 | Retrofitting |  |  |  | 28/08/2020 | 1551 | 75.12 | Yes | 75.12 |  | 05/11/2020 | 5 | 135.42 | 144.45 | MVS
19 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme | TSM/006240 | SM/07093 | Retrofitting |  |  |  | 25/09/2020 | 1511 | 73.12 | Yes | 73.12 |  | 01/02/2021 | 2 | 106.46 | 106.45 | MVS
20 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | TSM/006241 | SM/07094 | Retrofitting |  |  |  | 25/09/2020 | 2010 | 99.43 | Yes | 99.43 |  | 09/02/2021 | 6 | 153.89 | 192.76 | MVS
21 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | TSM/006242 | SM/07095 | Retrofitting |  |  |  | 25/09/2020 | 1850 | 88.28 | Yes | 88.28 |  | 21/01/2021 | 10 | 142.57 | 112.42 | MVS
22 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | TSM/006243 | SM/07096 | Retrofitting |  |  |  | 25/09/2020 | 717 | 34.92 | Yes | 34.92 |  | 21/01/2021 | 7 | 33.44 | 63.41 | MVS
23 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla Piped Water Supply Scheme | TSM/006244 | SM/07097 | Retrofitting |  |  |  | 25/09/2020 | 1890 | 99.87 | Yes | 99.87 |  | 28/01/2021 | 5 | 196.07 | 198.21 | MVS
24 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | TSM/006245 | SM/07098 | Retrofitting | Digha Sub-Division |  | Junior Engineer | 25/09/2020 | 2000 | 99.86 | Yes | 99.86 |  | 21/01/2021 | 14 | 137.57 | 127.04 | MVS
25 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Bathuary Piped Water Supply Scheme | TSM/006246 | SM/07099 | Retrofitting | Digha Sub-Division |  | Junior Engineer | 25/09/2020 | 2025 | 99.16 | Yes | 99.16 |  | 11/01/2021 | 4 | 98.91 | 141.81 | MVS
26 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Basudevpur Piped Water Supply Scheme | TSM/006247 | SM/07100 | Retrofitting |  |  |  | 25/09/2020 | 1800 | 90.02 | Yes | 90.02 | 26/05/2025 | 05/01/2021 | 2 | 88.72 | 88.18 | MVS
27 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Chirulia Piped Water Supply Scheme | TSM/006248 | SM/07101 | Retrofitting |  |  |  | 25/09/2020 | 1167 | 58.04 | Yes | 58.04 |  | 28/01/2021 | 3 | 52.6 | 98.41 | MVS
28 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme | TSM/006250 | SM/07102 | Retrofitting |  |  |  | 25/09/2020 | 2000 | 99.76 | Yes | 99.76 |  | 05/01/2021 | 3 | 96.83 | 172.46 | MVS
29 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme | TSM/006251 | SM/07104 | Retrofitting |  |  |  | 25/09/2020 | 2000 | 97.26 | Yes | 97.26 | 28/02/2024 | 21/12/2020 | 3 | 179.06 | 169.42 | MVS
30 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme | TSM/006252 | SM/07105 | Retrofitting |  |  |  | 25/09/2020 | 2020 | 99.66 | Yes | 99.66 |  | 21/12/2020 | 4 | 99.33 | 190.89 | MVS
31 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme | TSM/006253 | SM/07106 | Retrofitting |  |  |  | 25/09/2020 | 2000 | 99.2 | Yes | 99.2 | 24/11/2023 | 11/01/2021 | 4 | 181.02 | 179.85 | MVS
32 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Mandarmani Piped Water Supply Scheme | TSM/006254 | SM/07107 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 25/09/2020 | 1258 | 62.75 | Yes | 62.75 |  | 20/01/2021 | 1 | 60.84 | 60.84 | MVS
33 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme | TSM/006255 | SM/07108 | Retrofitting |  |  |  | 25/09/2020 | 1900 | 97.82 | Yes | 97.82 |  | 05/01/2021 | 2 | 97.78 | 186.18 | MVS
34 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | TSM/006256 | SM/07109 | Retrofitting |  |  |  | 25/09/2020 | 2024 | 99.52 | Yes | 99.52 |  | 05/01/2021 | 5 | 99.19 | 192.25 | MVS
35 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kudi Piped Water Supply Scheme | TSM/006257 | SM/07110 | Retrofitting |  |  |  | 25/09/2020 | 1500 | 72.71 | Yes | 72.71 |  | 08/04/2022 | 4 | 134.47 | 94.58 | MVS
36 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VIA | TSM/006341 | SM/07111 | Retrofitting |  |  |  | 25/09/2020 | 1159 | 54.94 | Yes | 54.94 |  | 11/05/2021 | 1 | 51.1 | 51.1 | MVS
37 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX | TSM/006342 | SM/07112 | Retrofitting |  |  |  | 25/09/2020 | 1196 | 56.55 | Yes | 56.55 |  | 11/01/2021 | 3 | 54.91 | 109.6 | MVS
38 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IXA | TSM/006343 | SM/07113 | Retrofitting |  |  |  | 25/09/2020 | 2091 | 99.88 | Yes | 99.88 |  | 05/01/2021 | 1 | 96.85 | 193.4 | MVS
39 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II | TSM/006344 | SM/07114 | Retrofitting |  |  |  | 25/09/2020 | 1905 | 99.94 | Yes | 99.94 |  | 05/01/2021 | 1 | 96 | 192 | MVS
40 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI | TSM/006345 | SM/07115 | Retrofitting |  |  |  | 25/09/2020 | 1985 | 99.73 | Yes | 99.73 |  | 05/01/2021 | 2 | 97.15 | 194.27 | MVS
41 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII | TSM/006348 | SM/07116 | Retrofitting |  |  |  | 25/09/2020 | 1945 | 99.8 | Yes | 99.8 |  | 28/01/2021 | 4 | 193.43 | 193.46 | MVS
42 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-X | TSM/006347 | SM/07117 | Retrofitting |  |  |  | 25/09/2020 | 1905 | 99.53 | Yes | 99.53 |  | 23/12/2020 | 1 | 96.37 | 193.84 | MVS
43 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XIII | TSM/006349 | SM/07118 | Retrofitting |  |  |  | 25/09/2020 | 1985 | 99.86 | Yes | 99.86 |  | 05/01/2021 | 1 | 96.92 | 195.77 | MVS
44 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme | TSM/006258 | SM/07119 | Retrofitting |  |  |  | 25/09/2020 | 1517 | 78.45 | Yes | 78.45 |  | 23/12/2020 | 4 | 77.76 | 122 | MVS
45 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 2 Water Supply Scheme | TSM/006260 | SM/07120 | Retrofitting |  |  |  | 25/09/2020 | 1561 | 79 | Yes | 79 |  | 05/01/2021 | 5 | 153.36 | 153.35 | MVS
46 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | TSM/006637 | SM/07477 | Retrofitting |  |  |  | 04/12/2020 | 904 | 45.95 | Yes | 45.95 |  | 14/05/2025 | 7 | 81.63 | 80.67 | MVS
47 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Uttar Charaikhia W/S Scheme Under Contai-I Block | TSM/006632 | SM/07478 | Retrofitting |  |  |  | 04/12/2020 | 937 | 46.94 | Yes | 46.94 |  | 04/02/2021 | 4 | 135.53 | 90.49 | MVS
48 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block | TSM/006631 | SM/07479 | Retrofitting |  |  |  | 04/12/2020 | 1612 | 79.84 | Yes | 79.84 |  | 11/02/2021 | 3 | 132.12 | 132.12 | MVS
49 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | TSM/006648 | SM/07480 | Retrofitting |  |  |  | 04/12/2020 | 1724 | 87.9 | Yes | 87.9 |  | 27/01/2021 | 13 | 132.79 | 157.89 | MVS
50 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS under Nandakumar Block. | TSM/006640 | SM/07481 | Retrofitting |  |  |  | 04/12/2020 | 550 | 26.99 | Yes | 26.99 |  | 18/12/2020 | 7 | 12.73 | 7.75 | MVS
51 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | TSM/006646 | SM/07482 | Retrofitting |  |  |  | 04/12/2020 | 992 | 53.02 | Yes | 53.02 |  | 27/01/2021 | 7 | 120.44 | 102.5 | MVS
52 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | TSM/006639 | SM/07483 | Retrofitting |  |  |  | 04/12/2020 | 1571 | 76.83 | Yes | 76.83 |  | 27/01/2021 | 14 | 91.14 | 145.48 | MVS
53 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. | TSM/006644 | SM/07484 | Retrofitting |  |  |  | 04/12/2020 | 2070 | 99.86 | Yes | 99.86 |  | 05/02/2021 | 2 | 97.67 | 193.36 | MVS
54 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | TSM/006642 | SM/07485 | Retrofitting |  |  |  | 04/12/2020 | 2050 | 99.81 | Yes | 99.81 |  | 05/02/2021 | 17 | 137.2 | 183.61 | MVS
55 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Argoal W/S Scheme under Potashpur-II Block | TSM/006635 | SM/07652 | Retrofitting |  |  |  | 04/12/2020 | 2629 | 129.4 | Yes | 129.4 |  | 04/02/2021 | 4 | 173.53 | 213.55 | MVS
56 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. | TSM/006638 | SM/07653 | Retrofitting |  |  |  | 04/12/2020 | 2382 | 116.61 | Yes | 116.61 |  | 05/02/2021 | 4 | 328.7 | 228.71 | MVS
57 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block | TSM/006633 | SM/07654 | Retrofitting |  |  |  | 04/12/2020 | 2449 | 117.41 | Yes | 117.41 |  | 04/02/2021 | 3 | 86.8 | 128.68 | MVS
58 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. | TSM/006636 | SM/07655 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 04/12/2020 | 2288 | 114.11 | Yes | 114.11 |  | 04/02/2021 | 3 | 66.57 | 85.37 | MVS
59 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur | TSM/006617 | SM/07656 | Retrofitting |  |  |  | 04/12/2020 | 3451 | 164.81 | Yes | 164.81 | 11/08/2023 | 08/02/2021 | 3 | 172.02 | 260.23 | MVS
60 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | TSM/006618 | SM/07657 | Retrofitting | Haldia Sub-Division | Assistant Engineer | Junior Engineer | 04/12/2020 | 3634 | 177.82 | Yes | 177.82 |  | 05/02/2021 | 21 | 271.59 | 307.25 | MVS
61 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | TSM/006634 | SM/07658 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 04/12/2020 | 3662 | 178.36 | Yes | 178.36 |  | 17/05/2021 | 6 | 206.46 | 165.25 | MVS
62 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | TSM/006630 | SM/07659 | Retrofitting |  |  |  | 04/12/2020 | 4683 | 228.34 | Yes | 228.34 |  | 08/02/2021 | 6 | 640.2 | 445.49 | MVS
63 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | TSM/006619 | SM/07660 | Retrofitting | Haldia Sub-Division | Assistant Engineer | Junior Engineer | 04/12/2020 | 3545 | 169.11 | Yes | 169.11 |  | 25/02/2021 | 4 | 329.67 | 235.46 | MVS
64 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur | TSM/006704 | SM/07661 | Retrofitting |  |  |  | 04/12/2020 | 4231 | 201.91 | Yes | 201.91 |  | 05/02/2021 | 4 | 330.51 | 386.84 | MVS
65 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | TSM/006350 | SM/07976 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 25/09/2020 | 27063 | 1280.9 | Yes | 1280.9 |  | 29/01/2021 | 5 | 1222.87 | 2278.72 | MVS
66 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Amtalia W/S Scheme under Contai-II Deshopran Block(PHASE-II) | TSM/007092 | SM/08222 | Retrofitting |  |  |  | 08/01/2021 | 1215 | 92.76 | Yes | 92.76 |  | 11/05/2021 | 1 | 90.23 | 65.29 | MVS
67 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I | TSM/007098 | SM/08223 | Retrofitting |  |  |  | 08/01/2021 | 2832 | 203.44 | Yes | 203.44 |  | 25/02/2021 | 3 | 201.01 | 276.52 | MVS
68 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kanaidighi W/S Scheme under Contai-III Block (PHASE-II) | TSM/007097 | SM/08224 | Retrofitting |  |  |  | 08/01/2021 | 680 | 98.97 | Yes | 98.97 |  | 11/05/2021 | 3 | 97.56 | 113.92 | MVS
69 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Uttar Khasda W/S Scheme under Contai-I Block (PHASE-II) | TSM/007093 | SM/08225 | Retrofitting |  |  |  | 08/01/2021 | 300 | 27.04 | Yes | 27.04 |  | 22/02/2021 | 3 | 73.23 | 46.98 | MVS
70 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Bagmari W/S Scheme Potashpur-II Block (PHASE-II) | TSM/007096 | SM/08226 | Retrofitting |  |  |  | 08/01/2021 | 1220 | 91.23 | Yes | 91.23 |  | 11/05/2021 | 1 | 88.69 | 115.43 | MVS
71 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) | TSM/007095 | SM/08227 | Retrofitting |  |  |  | 08/01/2021 | 427 | 27.42 | Yes | 27.42 |  | 08/12/2021 | 4 | 47.87 | 45.63 | MVS
72 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Ranisai W/S Scheme (Phase - II) | TSM/007100 | SM/08228 | Retrofitting |  |  |  | 08/01/2021 | 310 | 37.55 | Yes | 37.55 |  | 22/02/2021 | 3 | 104.26 | 69.36 | MVS
73 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Barasubarnanagar W/S Scheme (PHASE-II) | TSM/007091 | SM/08229 | Retrofitting |  |  |  | 08/01/2021 | 206 | 31.23 | Yes | 31.23 |  | 08/06/2021 | 2 | 60.35 | 60.35 | MVS
74 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) | TSM/007094 | SM/08230 | Retrofitting |  |  |  | 08/01/2021 | 150 | 11.32 | Yes | 11.32 |  | 22/02/2021 | 3 | 32.2 | 21.26 | MVS
75 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) | TSM/007099 | SM/08231 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 08/01/2021 | 1389 | 176.93 | Yes | 176.93 |  | 23/06/2021 | 2 | 175.93 | 243.87 | MVS
76 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme | TSM/007101 | SM/08232 | Retrofitting |  |  |  | 08/01/2021 | 1375 | 102.22 | Yes | 102.22 | 19/06/2024 | 25/02/2021 | 2 | 97.26 | 122.13 | MVS
77 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block | TSM/007102 | SM/08233 | Retrofitting |  |  |  | 08/01/2021 | 2466 | 216.57 | Yes | 216.57 |  | 18/08/2022 | 2 | 228.78 | 172.89 | MVS
78 | PURBA MEDINIPUR | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | TSM/005356 | SM/08698 | New |  |  |  | 05/11/2019 | 0 | 746.17 | Yes | 746.17 |  | 14/06/2022 | 44 | 629.6 | 630.13 | MVS
79 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II | TSM/007265 | SM/08745 | Retrofitting |  |  |  | 10/02/2021 | 670 | 104.08 | Yes | 104.08 |  | 10/09/2021 | 4 | 106.14 | 101.34 | MVS
80 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK | TSM/007259 | SM/08746 | Retrofitting |  |  |  | 10/02/2021 | 1575 | 98.91 | Yes | 98.91 |  | 10/09/2021 | 2 | 95.93 | 129.99 | MVS
81 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II | TSM/007239 | SM/08747 | Retrofitting |  |  |  | 10/02/2021 | 250 | 23.05 | Yes | 23.05 |  | 10/09/2021 | 2 | 22.6 | 21.15 | MVS
82 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II | TSM/007238 | SM/08748 | Retrofitting |  |  |  | 10/02/2021 | 700 | 60.25 | Yes | 60.25 |  | 10/09/2021 | 4 | 65.74 | 56.26 | MVS
83 | PURBA MEDINIPUR | Rejuvenation to accommodate FHTC under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division PHE Dte Purba Medinipur Phase II | TSM/007261 | SM/08749 | Retrofitting |  |  |  | 10/02/2021 | 450 | 65.32 | Yes | 65.32 |  | 10/09/2021 | 1 | 63.43 | 124.51 | MVS
84 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK | TSM/007235 | SM/08750 | Retrofitting |  |  |  | 10/02/2021 | 1500 | 99.92 | Yes | 99.92 |  | 10/09/2021 | 2 | 123.3 | 170.64 | MVS
85 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | TSM/007237 | SM/08751 | Retrofitting |  |  |  | 10/02/2021 | 400 | 45.72 | Yes | 45.72 |  | 10/09/2021 | 5 | 57.11 | 44.38 | MVS
86 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II | TSM/007263 | SM/08752 | Retrofitting | Digha Sub-Division |  | Junior Engineer | 10/02/2021 | 1000 | 145.47 | Yes | 145.47 |  | 10/09/2021 | 3 | 145.47 | 143.26 | MVS
87 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK | TSM/007257 | SM/08753 | Retrofitting |  |  |  | 10/02/2021 | 1950 | 100.13 | Yes | 100.13 |  | 10/09/2021 | 2 | 97.49 | 134.86 | MVS
88 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Alinan Zone-I and II PWSS Balance Part Block Sahid Matangini under Tamluk Sub Division of Tamluk Division PHE Dte. Purba Medinipur. | TSM/007251 | SM/08754 | Retrofitting |  |  |  | 10/02/2021 | 1100 | 60.34 | Yes | 60.34 |  | 10/09/2021 | 2 | 115.31 | 113.46 | MVS
89 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in DONA Zone-I Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. | TSM/007248 | SM/08755 | Retrofitting |  |  |  | 10/02/2021 | 1897 | 91.37 | Yes | 91.37 |  | 10/09/2021 | 3 | 179.62 | 112.88 | MVS
90 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in DONA Zone-II Balance Work Water Supply Scheme Block Moyna in the District of Purba Medinipur. | TSM/007247 | SM/08756 | Retrofitting |  |  |  | 10/02/2021 | 899 | 42.75 | Yes | 42.75 |  | 10/09/2021 | 2 | 82.78 | 82.61 | MVS
91 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN HABICHAK PWSS BALANCE WORK BLOCK CHANDIPUR IN THE DISTRICT OF PURBA MEDINIPUR. | TSM/007234 | SM/08757 | Retrofitting |  |  |  | 10/02/2021 | 548 | 25.02 | Yes | 25.02 |  | 10/09/2021 | 2 | 48.29 | 48 | MVS
92 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN DAMUDARPUR PWSS UNDER CONTAI - I BLOCK PHASE II | TSM/007236 | SM/08758 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 10/02/2021 | 220 | 17.38 | Yes | 17.38 |  | 10/09/2021 | 1 | 16.62 | 15.68 | MVS
93 | PURBA MEDINIPUR | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | TSM/007254 | SM/08759 | Retrofitting |  |  |  | 10/02/2021 | 1600 | 471.12 | Yes | 471.12 |  | 25/04/2022 | 12 | 411.85 | 392.24 | MVS
94 | PURBA MEDINIPUR | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme under block Paskura-II in the district of Purba Medinipur Zone-VIII | TSM/006346 | SM/08790 | Retrofitting |  |  |  | 25/09/2020 | 7511 | 353.17 | Yes | 353.17 |  | 15/09/2021 | 2 | 342.75 | 684.43 | MVS
95 | PURBA MEDINIPUR | Shyampur Piped Water Supply Scheme. | TSM/004398 | SM/08878 | New |  |  |  | 28/08/2020 | 2571 | 800.17 | Yes | 800.17 | 04/09/2023 | 02/05/2022 | 23 | 728.68 | 602.16 | MVS
96 | PURBA MEDINIPUR | Baharampur Piped Water Supply Scheme. | TSM/005079 | SM/08879 | New |  |  |  | 28/08/2020 | 2296 | 688.64 | Yes | 688.64 |  | 17/11/2021 | 22 | 691.06 | 561.38 | MVS
97 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | TSM/008361 | SM/09034 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 3041 | 829.85 | Yes | 829.85 | 15/12/2022 | 29/07/2024 | 14 | 201.73 | 527.31 | MVS
98 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Uttar Charikhia PWSS under Contai I Block (Phase-II). | TSM/008269 | SM/09047 | Retrofitting |  |  |  | 19/08/2021 | 180 | 17.78 | Yes | 17.78 |  | 02/11/2021 | 1 | 17.26 | 17.26 | MVS
99 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). | TSM/008270 | SM/09048 | Retrofitting |  |  |  | 19/08/2021 | 0 | 37.06 | Yes | 37.06 |  | 02/11/2021 | 2 | 36.47 | 35.66 | MVS
100 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. | TSM/008271 | SM/09049 | Retrofitting |  |  |  | 19/08/2021 | 505 | 41.88 | Yes | 41.88 |  | 02/11/2021 | 2 | 40.65 | 40.65 | MVS
101 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone I (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-I) | TSM/008272 | SM/09050 | Retrofitting |  |  |  | 19/08/2021 | 1100 | 61.99 | Yes | 61.99 |  | 02/11/2021 | 1 | 59.87 | 59.87 | MVS
102 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Surface Water Based W/S Scheme for Zone X (Balance Work) Block Kolaghat in the district of Purba Medinipur under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-III) | TSM/008273 | SM/09051 | Retrofitting |  |  |  | 19/08/2021 | 1600 | 93.24 | Yes | 93.24 |  | 08/11/2021 | 1 | 84.01 | 84.01 | MVS
103 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block | TSM/008274 | SM/09052 | Retrofitting |  |  |  | 19/08/2021 | 76 | 76.42 | Yes | 76.42 |  | 02/11/2021 | 2 | 74.01 | 74 | MVS
104 | PURBA MEDINIPUR | Retorfitting to accommodate FHTC under JJM in Kudi PWSS under Egra I Block (Phase-II) | TSM/008275 | SM/09053 | Retrofitting |  |  |  | 19/08/2021 | 200 | 14.94 | Yes | 14.94 |  | 02/11/2021 | 1 | 12.22 | 12.22 | MVS
105 | PURBA MEDINIPUR | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) | TSM/008276 | SM/09054 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 19/08/2021 | 400 | 50.27 | Yes | 50.27 |  | 02/11/2021 | 2 | 47.75 | 46.55 | MVS
106 | PURBA MEDINIPUR | Retorfitting to accommodate FHTC under JJM in Basudevpur PWSS under Egra II Block (Phase-II) | TSM/008277 | SM/09055 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 19/08/2021 | 160 | 71.42 | Yes | 71.42 |  | 02/11/2021 | 1 | 69.11 | 67.16 | MVS
107 | PURBA MEDINIPUR | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | TSM/008278 | SM/09056 | Retrofitting |  |  |  | 19/08/2021 | 1600 | 88.01 | Yes | 88.01 |  | 02/11/2021 | 6 | 88.78 | 85.36 | MVS
108 | PURBA MEDINIPUR | Retorfitting to accommodate FHTC under JJM in Dulalpur PWSS. | TSM/008402 | SM/09057 | Retrofitting |  |  |  | 19/08/2021 | 1166 | 59.18 | Yes | 59.18 |  | 02/11/2021 | 1 | 57.42 | 57.41 | MVS
109 | PURBA MEDINIPUR | Balance work for Retrofitting to accommodate FHTC (907 Nos.) and laying of laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for | TSM/008314 | SM/09058 | Retrofitting |  |  |  | 19/08/2021 | 907 | 130.31 | Yes | 130.31 |  | 08/11/2021 | 1 | 115.86 | 115.86 | MVS
110 | PURBA MEDINIPUR | Balance Work for Retrofitting to Accommodate FHTC (300 nos) and Laying of Left-Out Portion UPVC Pipeline due to uncovered area of different Nodal point of Srirampur and its Adjoining Mouzas Water Supply Scheme under JJM within Tamluk Block under Tamluk S | TSM/008440 | SM/09073 | Retrofitting |  |  |  | 08/09/2021 | 300 | 21.74 | Yes | 21.74 |  | 22/11/2021 | 1 | 19.58 | 18.98 | MVS
111 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. | TSM/008355 | SM/09074 | Retrofitting |  |  |  | 08/09/2021 | 335 | 61.29 | Yes | 61.29 |  | 22/11/2021 | 2 | 38.92 | 28.56 | MVS
112 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008432 | SM/09272 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 2201 | 366.83 | Yes | 366.83 | 24/11/2022 | 31/05/2022 | 10 | 333.83 | 331.54 | MVS
113 | PURBA MEDINIPUR | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | TSM/008373 | SM/09273 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 1592 | 249.69 | Yes | 249.69 |  | 02/12/2021 | 5 | 17.99 | 69.05 | MVS
114 | PURBA MEDINIPUR | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | TSM/008439 | SM/09274 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 967 | 359.88 | Yes | 359.88 | 28/03/2023 | 09/08/2023 | 12 | 304.18 | 182.43 | MVS
115 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | TSM/008433 | SM/09275 | Augmentation | RWS Tamluk Sub-Division |  | Junior Engineer | 08/09/2021 | 1878 | 478.65 | Yes | 478.65 |  | 05/04/2022 | 8 | 462.32 | 449.54 | MVS
116 | PURBA MEDINIPUR | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme | TSM/008370 | SM/09276 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 909 | 340.42 | Yes | 340.42 | 28/11/2022 | 02/05/2022 | 11 | 309.37 | 167.18 | MVS
117 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008364 | SM/09277 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 1586 | 315.94 | Yes | 315.94 | 11/11/2022 | 27/05/2022 | 5 | 306.7 | 262.85 | MVS
118 | PURBA MEDINIPUR | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | TSM/008438 | SM/09278 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 3059 | 678.53 | Yes | 678.53 | 27/02/2025 | 11/04/2025 | 14 | 657.85 | 486.36 | MVS
119 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008366 | SM/09279 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 2139 | 366.62 | Yes | 366.62 | 20/12/2022 | 05/04/2022 | 6 | 360.65 | 349.09 | MVS
120 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | TSM/008365 | SM/09280 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 2013 | 445.45 | Yes | 445.45 |  | 05/04/2022 | 6 | 192.18 | 231.26 | MVS
121 | PURBA MEDINIPUR | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | TSM/008368 | SM/09281 | Augmentation | Haldia Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 2920 | 681.09 | Yes | 681.09 | 02/11/2022 | 14/06/2023 | 13 | 792.59 | 597.79 | MVS
122 | PURBA MEDINIPUR | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | TSM/008437 | SM/09282 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 4747 | 890.9 | Yes | 890.9 | 17/03/2023 | 13/04/2023 | 27 | 834.24 | 691.4 | MVS
123 | PURBA MEDINIPUR | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | TSM/008435 | SM/09283 | Augmentation | Haldia Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 3478 | 686.91 | Yes | 686.91 | 21/12/2023 | 20/01/2023 | 21 | 176.03 | 478.06 | MVS
124 | PURBA MEDINIPUR | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | TSM/008371 | SM/09284 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 2879 | 739.47 | Yes | 739.47 | 31/07/2024 | 05/04/2022 | 14 | 735.89 | 662.67 | MVS
125 | PURBA MEDINIPUR | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | TSM/008434 | SM/09285 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 4622 | 932.77 | Yes | 932.77 | 17/03/2023 | 14/06/2023 | 12 | 853.03 | 773.92 | MVS
126 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | TSM/008436 | SM/09286 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 08/09/2021 | 4335 | 764.17 | Yes | 764.17 | 03/08/2023 | 29/08/2023 | 12 | 709.42 | 661.27 | MVS
127 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | TSM/008358 | SM/09287 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 986 | 349.47 | Yes | 349.47 | 11/11/2022 | 13/04/2023 | 17 | 309.82 | 276.43 | MVS
128 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | TSM/008356 | SM/09288 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 3398 | 850.34 | Yes | 850.34 | 29/10/2024 | 01/12/2021 | 17 | 627.97 | 562.22 | MVS
129 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Supply Scheme for Anurai. | TSM/008497 | SM/09334 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 2536 | 704.29 | Yes | 704.29 |  | 27/05/2022 | 19 | 554.57 | 465.05 | MVS
130 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Supply Scheme for Majna | TSM/008493 | SM/09335 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 2501 | 556.85 | Yes | 556.85 | 22/05/2023 | 01/12/2021 | 15 | 439.6 | 372.89 | MVS
131 | PURBA MEDINIPUR | Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008492 | SM/09336 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 1784 | 556.34 | Yes | 556.34 | 14/02/2023 | 02/12/2021 | 24 | 394.8 | 382.76 | MVS
132 | PURBA MEDINIPUR | Augmentation of Ground Water Based Asadtalia PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008486 | SM/09337 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 1862 | 529.85 | Yes | 529.85 |  | 17/08/2023 | 20 | 478.64 | 406.33 | MVS
133 | PURBA MEDINIPUR | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-II Water Supply Scheme. | TSM/008474 | SM/09338 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 3736 | 685.69 | Yes | 685.69 |  | 22/06/2022 | 7 | 624.91 | 378.83 | MVS
134 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Haipur PWSS under Contai-I Block (Phase-II) | TSM/008499 | SM/09339 | Retrofitting |  |  |  | 29/09/2021 | 314 | 125.52 | Yes | 125.52 |  | 05/04/2022 | 10 | 133.06 | 122.73 | MVS
135 | PURBA MEDINIPUR | Narikeldaha Piped Water Supply Scheme. | TSM/004396 | SM/09342 | New |  |  |  | 25/09/2020 | 2272 | 848.91 | Yes | 848.91 |  | 30/11/2021 | 17 | 795.56 | 762.73 | MVS
136 | PURBA MEDINIPUR | Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008484 | SM/09402 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 2132 | 535.02 | Yes | 535.02 | 22/05/2023 | 01/10/2024 | 14 | 459.78 | 286.03 | MVS
137 | PURBA MEDINIPUR | Balance Work for Retrofitting to Accommodate FHTC (152 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of different nodal point of Dona Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk | TSM/009044 | SM/09443 | Retrofitting |  |  |  | 08/10/2021 | 152 | 48.34 | Yes | 48.34 |  | 13/12/2021 | 1 | 45.8 | 45.8 | MVS
138 | PURBA MEDINIPUR | Augmentation of Ground Water Based Dwariberya PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008974 | SM/09444 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 2915 | 726.52 | Yes | 726.52 |  | 19/04/2022 | 22 | 542.68 | 463.76 | MVS
139 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Talda | TSM/008950 | SM/09445 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 3171 | 822.22 | Yes | 822.22 | 14/02/2023 | 05/05/2022 | 27 | 641.67 | 560.08 | MVS
140 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai | TSM/008948 | SM/09446 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 2679 | 710.98 | Yes | 710.98 | 17/01/2025 | 06/08/2021 | 30 | 587.16 | 426.96 | MVS
141 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji | TSM/008927 | SM/09447 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 2940 | 663.05 | Yes | 663.05 | 28/11/2022 | 19/04/2022 | 12 | 521.57 | 320.98 | MVS
142 | PURBA MEDINIPUR | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme | TSM/008913 | SM/09448 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 4327 | 802.36 | Yes | 802.36 | 14/12/2022 | 05/04/2022 | 32 | 841.11 | 733.73 | MVS
143 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Gobra PWSS under Ramnagar-I Block. | TSM/009108 | SM/09800 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 22/11/2021 | 2550 | 149.22 | Yes | 149.22 |  | 19/01/2022 | 2 | 136.45 | 106.19 | MVS
144 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block. | TSM/009119 | SM/09801 | Retrofitting |  |  |  | 22/11/2021 | 2862 | 160.98 | Yes | 160.98 |  | 29/06/2022 | 3 | 144.09 | 144.09 | MVS
145 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC (2753) Nos. and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different nodal point under JJM in Uttar Dhalhara Zone-II of Sahid Matangini Block in this district of Purba Medinipur. | TSM/009117 | SM/09802 | Retrofitting |  |  |  | 22/11/2021 | 2753 | 164.09 | Yes | 164.09 |  | 19/01/2022 | 3 | 150.82 | 90.9 | MVS
146 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC (2633) Nos. of Chandibenia Zone-I and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division, PHE Dte. in the district of Purba Medinipur. | TSM/009116 | SM/09803 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 22/11/2021 | 2633 | 120.85 | Yes | 120.85 |  | 19/01/2022 | 2 | 104.66 | 104.47 | MVS
147 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Nagua PWSS under Egra-I Block. | TSM/009110 | SM/09804 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 22/11/2021 | 2783 | 166.66 | Yes | 166.66 |  | 19/01/2022 | 3 | 168.1 | 115.23 | MVS
148 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli | TSM/008360 | SM/09912 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 3862 | 1029.45 | Yes | 1029.45 | 28/11/2022 | 11/05/2022 | 20 | 811.42 | 718.16 | MVS
149 | PURBA MEDINIPUR | Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008359 | SM/09913 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 6158 | 1104.23 | Yes | 1104.23 | 20/12/2022 | 22/12/2022 | 25 | 1054.46 | 839.43 | MVS
150 | PURBA MEDINIPUR | Rejuvenation & Retrofitting of Ground Water Based Kulbari PWSS to Accommodate FHTC in Chandipur Block Under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008357 | SM/09914 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 4407 | 1060.63 | Yes | 1060.63 |  | 05/04/2022 | 16 | 882.21 | 864.95 | MVS
151 | PURBA MEDINIPUR | Augmentation of Suadighi piped water supply scheme. | TSM/005364 | SM/09919 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 6915 | 2222.11 | Yes | 2222.11 | 06/12/2022 | 14/06/2023 | 41 | 1667.59 | 1179.6 | MVS
152 | PURBA MEDINIPUR | Augmentation of Madhakhali piped water supply scheme. | TSM/005363 | SM/09920 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 7098 | 2333.22 | Yes | 2333.22 | 06/12/2022 | 19/04/2022 | 37 | 1729.58 | 1486.18 | MVS
153 | PURBA MEDINIPUR | Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme. | TSM/008362 | SM/09977 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 7229 | 1187.36 | Yes | 1187.36 | 18/08/2023 | 07/06/2023 | 36 | 1011.07 | 714.52 | MVS
154 | PURBA MEDINIPUR | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme. | TSM/008480 | SM/10030 | Augmentation | Haldia Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 707 | 1321.6 | Yes | 1321.6 | 02/11/2022 | 19/04/2022 | 20 | 1278.47 | 1038.59 | MVS
155 | PURBA MEDINIPUR | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme. | TSM/008466 | SM/10031 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 29/09/2021 | 5167 | 1041.15 | Yes | 1041.15 | 14/12/2022 | 07/11/2023 | 19 | 985.66 | 790.43 | MVS
156 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput. | TSM/009590 | SM/10072 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/12/2021 | 1833 | 581.76 | Yes | 581.76 | 28/03/2023 | 12/07/2022 | 9 | 464.44 | 306.15 | MVS
157 | PURBA MEDINIPUR | Balance Work for Retrofitting to Accommodate FHTC (750 Nos.) and Laying of left-out portion UPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-XI, Block-Kolaghat in this | TSM/009589 | SM/10095 | Retrofitting |  |  |  | 16/12/2021 | 750 | 95.4 | Yes | 95.4 |  | 08/02/2022 | 1 | 92.89 | 92.89 | MVS
158 | PURBA MEDINIPUR | Balance work for Retrofitting to Accommodate FHTC (951 Nos.) and laying of Left-out portion UPVC pipeline due to uncovered area of this Zone and Damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme under Zone-III | TSM/009577 | SM/10096 | Retrofitting |  |  |  | 16/12/2021 | 951 | 89.89 | Yes | 89.89 |  | 23/02/2022 | 1 | 77.04 | 77.04 | MVS
159 | PURBA MEDINIPUR | Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme. | TSM/008980 | SM/10120 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 7239 | 1515.48 | Yes | 1515.48 | 14/12/2022 | 27/06/2022 | 13 | 1198.17 | 1112.83 | MVS
160 | PURBA MEDINIPUR | Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008977 | SM/10121 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 9661 | 2314.83 | Yes | 2314.83 | 20/12/2022 | 28/02/2023 | 32 | 1510.08 | 1636.65 | MVS
161 | PURBA MEDINIPUR | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme | TSM/008952 | SM/10122 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/10/2021 | 6387 | 1492.39 | Yes | 1492.39 | 17/03/2023 | 05/04/2022 | 26 | 1255.76 | 1111.65 | MVS
162 | PURBA MEDINIPUR | Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) | TSM/009104 | SM/10125 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/11/2021 | 9676 | 2077.89 | Yes | 2077.89 | 06/12/2022 | 07/04/2025 | 29 | 1198.52 | 1410.88 | MVS
163 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti | TSM/009080 | SM/10126 | Augmentation | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/11/2021 | 3753 | 1145.17 | Yes | 1145.17 | 28/11/2022 | 17/06/2022 | 12 | 720.22 | 655.27 | MVS
164 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani | TSM/009079 | SM/10127 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/11/2021 | 5256 | 1418.64 | Yes | 1418.64 | 06/12/2022 | 27/06/2022 | 15 | 942.33 | 822.76 | MVS
165 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda | TSM/009078 | SM/10128 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/11/2021 | 5364 | 1634.61 | Yes | 1634.61 | 06/12/2022 | 29/04/2024 | 18 | 1012.15 | 622.3 | MVS
166 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Durmut | TSM/009492 | SM/10323 | Augmentation | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/12/2021 | 3895 | 1166.79 | Yes | 1166.79 |  | 23/05/2022 | 31 | 946.76 | 715.07 | MVS
167 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur | TSM/009493 | SM/10342 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 27/01/2022 | 2162 | 800.14 | Yes | 800.14 | 28/03/2023 | 23/06/2022 | 17 | 481.41 | 414.12 | MVS
168 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Kamarda | TSM/009494 | SM/10344 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 27/01/2022 | 3155 | 952 | Yes | 952 | 14/08/2023 | 24/04/2023 | 12 | 170.04 | 492.39 | MVS
169 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Paschim Kamarda (Phase-II) PWSS under Contai-III Block. | TSM/009922 | SM/10345 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 27/01/2022 | 13 | 43.75 | Yes | 43.75 |  | 12/07/2022 | 3 | 42.84 | 3.52 | MVS
170 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC (410) Nos. under JJM in Keshabpur Jalpai PWSS (Balance Part-Phase-II) under Mahishadal Dev. Block. | TSM/008953 | SM/10346 | Retrofitting |  |  |  | 27/01/2022 | 410 | 26.17 | Yes | 26.17 |  | 08/03/2022 | 1 | 19.06 | 19.06 | MVS
171 | PURBA MEDINIPUR | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | TSM/009767 | SM/10393 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 27/01/2022 | 2729 | 787.03 | Yes | 787.03 | 11/01/2024 | 30/08/2024 | 10 | 707.56 | 550.65 | MVS
172 | PURBA MEDINIPUR | Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. | TSM/009747 | SM/10396 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 27/01/2022 | 7163 | 1547.92 | Yes | 1547.92 | 28/03/2023 | 29/12/2023 | 13 | 360.93 | 1071.3 | MVS
173 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM un Baranalgeria (Zone-II) PWSS under Egra-II Block. | TSM/010148 | SM/10431 | Retrofitting | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 17/02/2022 | 1718 | 106.97 | Yes | 106.97 |  | 25/04/2022 | 4 | 122.28 | 121.57 | MVS
174 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in MUKUNDAPUR PWSS under Ramnagar-I Block | TSM/010126 | SM/10432 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 17/02/2022 | 2488 | 126.97 | Yes | 126.97 |  | 25/04/2022 | 2 | 125.78 | 0 | MVS
175 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) | TSM/008955 | SM/10433 | Retrofitting | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 17/02/2022 | 304 | 178.42 | Yes | 178.42 | 20/12/2022 | 18/08/2022 | 5 | 26.48 | 72.2 | MVS
176 | PURBA MEDINIPUR | Balance work for Retrofitting to Accommodate FHTC (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-VIII, | TSM/009921 | SM/10434 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 17/02/2022 | 200 | 82 | Yes | 82 | 04/09/2023 | 05/04/2022 | 2 | 79.61 | 79.61 | MVS
177 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC (Balance Work) (579 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-IV, Blo | TSM/009912 | SM/10435 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 17/02/2022 | 579 | 94.29 | Yes | 94.29 |  | 05/04/2022 | 1 | 91.47 | 65.2 | MVS
178 | PURBA MEDINIPUR | Balance work for Retrofitting to Accommodate FHTC (862 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-II, Bl | TSM/009911 | SM/10436 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 17/02/2022 | 862 | 99.32 | Yes | 99.32 |  | 21/06/2022 | 2 | 96.36 | 96.36 | MVS
179 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC (Balance Work) (200 Nos.) and laying of left-out portion UPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface Water Based Water Supply Scheme for Zone-V, Bloc | TSM/009910 | SM/10437 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 17/02/2022 | 200 | 19.89 | Yes | 19.89 |  | 05/04/2022 | 1 | 17.51 | 16.09 | MVS
180 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I,Potashpur-I & Potashpur-II Development Block under Purba Medinipur District. | TSM/010151 | SM/10585 | New |  |  |  | 16/03/2022 | 1356 | 969 | Yes | 969 | 06/03/2024 | 27/05/2024 | 2 | 40.04 | 850.94 | MVS
181 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II, Moyna, Nandakumar & Panskura-I Development Block under Purba Medinipur District. | TSM/010150 | SM/10586 | New |  |  |  | 16/03/2022 | 1311 | 992 | Yes | 992 | 06/03/2024 | 27/05/2024 | 2 | 22.62 | 763.96 | MVS
182 | PURBA MEDINIPUR | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2) | TSM/010123 | SM/10588 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 7796 | 999.73 | Yes | 999.73 | 06/12/2022 | 01/10/2024 | 20 | 1224.5 | 706.69 | MVS
183 | PURBA MEDINIPUR | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | TSM/010122 | SM/10589 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 0 | 980.6 | Yes | 980.6 | 28/11/2022 | 25/07/2023 | 35 | 911.73 | 503.58 | MVS
184 | PURBA MEDINIPUR | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | TSM/010121 | SM/10590 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 4830 | 585.68 | Yes | 585.68 | 06/12/2022 | 14/10/2022 | 6 | 725.69 | 337.98 | MVS
185 | PURBA MEDINIPUR | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | TSM/010120 | SM/10591 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 0 | 703.33 | Yes | 703.33 | 14/12/2022 | 14/06/2024 | 13 | 368.71 | 245.97 | MVS
186 | PURBA MEDINIPUR | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | TSM/010094 | SM/10592 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 0 | 903.71 | Yes | 903.71 |  | 22/11/2023 | 15 | 627.54 | 508.76 | MVS
187 | PURBA MEDINIPUR | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010114 | SM/10593 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 4937 | 995.98 | Yes | 995.98 | 14/08/2023 | 28/06/2022 | 40 | 1005.02 | 759.4 | MVS
188 | PURBA MEDINIPUR | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | TSM/010097 | SM/10594 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 2508 | 819.79 | Yes | 819.79 | 06/12/2022 | 17/06/2022 | 10 | 803.21 | 281.18 | MVS
189 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Ramnagar-II, Sahid Matangini & Sutahata Development Block within Purba Medinipur District. | TSM/010295 | SM/10617 | New |  |  |  | 16/03/2022 | 704 | 977.46 | Yes | 977.46 | 06/03/2024 | 27/05/2024 | 2 | 22.49 | 790.86 | MVS
190 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Panskura-I and Potashpur-I Development Block under Purba Medinipur District. | TSM/010147 | SM/10618 | New |  |  |  | 16/03/2022 | 1306 | 969 | Yes | 969 | 06/03/2024 | 27/05/2024 | 2 | 34.85 | 487.06 | MVS
191 | PURBA MEDINIPUR | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | TSM/010131 | SM/10619 | New |  |  |  | 16/03/2022 | 1080 | 974 | Yes | 974 | 06/03/2024 | 27/05/2024 | 2 | 25.19 | 484.2 | MVS
192 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Potashpur-II and Ramnagar-I Development Block Within Purba Medinipur District. | TSM/010128 | SM/10620 | New |  |  |  | 16/03/2022 | 1279 | 992 | Yes | 992 | 06/06/2022 | 27/05/2024 | 2 | 25.5 | 644.24 | MVS
193 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) at different locations under Ramnagar-I and Ramnagar-II Development Block Within Purba Medinipur District. | TSM/010127 | SM/10621 | New |  |  |  | 16/03/2022 | 1223 | 989 | Yes | 989 | 06/06/2022 | 27/05/2024 | 2 | 32.86 | 761.49 | MVS
194 | PURBA MEDINIPUR | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | TSM/010095 | SM/10647 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 5157 | 539.62 | Yes | 539.62 | 14/12/2022 | 12/07/2022 | 26 | 710.53 | 527.18 | MVS
195 | PURBA MEDINIPUR | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | TSM/010118 | SM/10664 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 0 | 599.83 | Yes | 599.83 |  | 17/08/2023 | 11 | 351.93 | 93.83 | MVS
196 | PURBA MEDINIPUR | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, CONTAI-I, DESHAPRAN & EGRA-I BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | TSM/010130 | SM/10666 | New |  |  |  | 16/03/2022 | 1451 | 980.83 | Yes | 980.83 | 06/06/2022 | 27/05/2024 | 2 | 26.07 | 557.42 | MVS
197 | PURBA MEDINIPUR | Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/008372 | SM/10681 | Augmentation | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 6101 | 1073.49 | Yes | 1073.49 | 14/12/2022 | 17/08/2023 | 13 | 917.81 | 573.44 | MVS
198 | PURBA MEDINIPUR | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | TSM/008369 | SM/10682 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 5547 | 1414.27 | Yes | 1414.27 | 14/12/2022 | 02/08/2023 | 14 | 1382.72 | 1118.22 | MVS
199 | PURBA MEDINIPUR | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | TSM/008367 | SM/10683 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 5528 | 1126.18 | Yes | 1126.18 | 11/12/2023 | 25/07/2023 | 11 | 1061.96 | 851.65 | MVS
200 | PURBA MEDINIPUR | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | TSM/008363 | SM/10684 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 08/09/2021 | 8284 | 1309.53 | Yes | 1309.53 | 14/02/2023 | 17/04/2023 | 21 | 1337.32 | 1162.7 | MVS
201 | PURBA MEDINIPUR | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR BHAGWANPUR-I & BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | TSM/010132 | SM/10689 | New |  |  |  | 16/03/2022 | 2537 | 963 | Yes | 963 | 06/06/2022 | 27/05/2024 | 2 | 34.27 | 859.82 | MVS
202 | PURBA MEDINIPUR | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I | TSM/010096 | SM/10725 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 3032 | 1006.09 | Yes | 1006.09 | 06/12/2022 | 07/06/2023 | 8 | 994.64 | 334.39 | MVS
203 | PURBA MEDINIPUR | Augmentation of Ground water Based Betkundu Water Supply Scheme | TSM/009994 | SM/11206 | Augmentation | Haldia Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 5997 | 1317.43 | Yes | 1317.43 | 27/02/2024 | 24/06/2024 | 11 | 1288.47 | 938.48 | MVS
204 | PURBA MEDINIPUR | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011102 | SM/11469 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 2587 | 570.27 | Yes | 570.27 | 28/11/2022 | 06/01/2022 | 14 | 206.26 | 363.48 | MVS
205 | PURBA MEDINIPUR | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010432 | SM/11470 | Augmentation | Haldia Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 8505 | 869.93 | Yes | 869.93 | 14/12/2022 | 05/04/2022 | 6 | 961.77 | 672.93 | MVS
206 | PURBA MEDINIPUR | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010403 | SM/11471 | Augmentation | Haldia Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 0 | 745.37 | Yes | 745.37 | 29/05/2023 | 08/06/2023 | 10 | 401.98 | 303.41 | MVS
207 | PURBA MEDINIPUR | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010402 | SM/11472 | Augmentation | Haldia Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 8206 | 834.19 | Yes | 834.19 | 11/08/2023 | 05/04/2022 | 9 | 1124.47 | 594.96 | MVS
208 | PURBA MEDINIPUR | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010401 | SM/11473 | Augmentation | Haldia Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 0 | 873.48 | Yes | 873.48 | 06/03/2024 | 23/04/2025 | 18 | 594.54 | 247.48 | MVS
209 | PURBA MEDINIPUR | Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010400 | SM/11474 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 6217 | 997.01 | Yes | 997.01 | 28/11/2022 | 24/03/2023 | 14 | 859.82 | 539.08 | MVS
210 | PURBA MEDINIPUR | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011087 | SM/11549 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 5686 | 850.53 | Yes | 850.53 | 28/11/2022 | 10/09/2024 | 14 | 857.08 | 602.2 | MVS
211 | PURBA MEDINIPUR | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | TSM/010673 | SM/11552 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 2646 | 617.59 | Yes | 617.59 | 09/07/2024 | 26/11/2024 | 11 | 96.47 | 351.49 | MVS
212 | PURBA MEDINIPUR | Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/010395 | SM/11553 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 4374 | 944.76 | Yes | 944.76 | 27/02/2024 | 23/04/2025 | 21 | 853.56 | 446.04 | MVS
213 | PURBA MEDINIPUR | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | TSM/011149 | SM/11554 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 5512 | 742.35 | Yes | 742.35 | 23/12/2022 | 02/11/2022 | 10 | 596.13 | 490.36 | MVS
214 | PURBA MEDINIPUR | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/010581 | SM/11612 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 0 | 69.8 | Yes | 69.8 | 28/11/2022 | 18/08/2022 | 6 | 83.84 | 38.3 | MVS
215 | PURBA MEDINIPUR | Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block. | TSM/010580 | SM/11613 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 0 | 68.66 | Yes | 68.66 | 28/11/2022 | 18/08/2022 | 3 | 36.66 | 0 | MVS
216 | PURBA MEDINIPUR | Augmentation of Moyna (Zone-I) PWSS | TSM/011492 | SM/11614 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 4527 | 998.4 | Yes | 998.4 | 11/04/2023 | 15/12/2023 | 17 | 873.46 | 549.95 | MVS
217 | PURBA MEDINIPUR | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | TSM/011150 | SM/11615 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 3857 | 915.35 | Yes | 915.35 | 28/11/2022 | 29/04/2024 | 10 | 911.78 | 201.79 | MVS
218 | PURBA MEDINIPUR | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-1) | TSM/011148 | SM/11616 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 25/04/2022 | 0 | 838.08 | Yes | 838.08 |  | 24/04/2023 | 7 | 841.13 | 711.24 | MVS
219 | PURBA MEDINIPUR | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | TSM/011146 | SM/11617 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 6291 | 843.08 | Yes | 843.08 | 28/11/2022 | 23/07/2024 | 13 | 705.29 | 415.97 | MVS
220 | PURBA MEDINIPUR | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) | TSM/011144 | SM/11618 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 25/04/2022 | 6291 | 806.74 | Yes | 806.74 | 23/12/2022 | 02/11/2022 | 3 | 829.26 | 788.49 | MVS
221 | PURBA MEDINIPUR | Augmentation of Moyna (Zone-II) PWSS | TSM/011493 | SM/11639 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 3745 | 990.17 | Yes | 990.17 | 11/04/2023 | 01/10/2024 | 14 | 890.01 | 719.39 | MVS
222 | PURBA MEDINIPUR | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/011780 | SM/11859 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 0 | 37.95 | Yes | 37.95 | 28/11/2022 | 18/08/2022 | 5 | 33.33 | 9.47 | MVS
223 | PURBA MEDINIPUR | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/011779 | SM/11860 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 0 | 106.95 | Yes | 106.95 | 14/02/2023 | 18/08/2022 | 5 | 87.48 | 44.03 | MVS
224 | PURBA MEDINIPUR | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/011778 | SM/11861 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 0 | 43.42 | Yes | 43.42 | 28/11/2022 | 18/08/2022 | 5 | 37.27 | 28.25 | MVS
225 | PURBA MEDINIPUR | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/010577 | SM/11862 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 0 | 69.86 | Yes | 69.86 | 04/05/2023 | 18/08/2022 | 8 | 69.08 | 60.6 | MVS
226 | PURBA MEDINIPUR | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | TSM/011827 | SM/11881 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 2526 | 595.37 | Yes | 595.37 | 29/11/2023 | 20/04/2023 | 12 | 540.37 | 293.65 | MVS
227 | PURBA MEDINIPUR | KURPAI AND ADJOINING MOUJAS PWSS | TSM/011814 | SM/11882 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 1684 | 498.52 | Yes | 498.52 | 12/01/2023 | 04/05/2023 | 5 | 452.23 | 85.13 | MVS
228 | PURBA MEDINIPUR | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | TSM/011811 | SM/11883 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 1643 | 428.89 | Yes | 428.89 | 16/03/2023 | 20/04/2023 | 8 | 275.13 | 137.27 | MVS
229 | PURBA MEDINIPUR | BARNAN AND ITS ADJOINING MOUJAS PWSS | TSM/011802 | SM/11884 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 0 | 404.59 | Yes | 404.59 | 12/01/2023 | 24/06/2024 | 6 | 45.34 | 94.47 | MVS
230 | PURBA MEDINIPUR | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/011790 | SM/11885 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 1306 | 410.86 | Yes | 410.86 | 14/02/2023 | 07/06/2024 | 5 | 369.64 | 110.61 | MVS
231 | PURBA MEDINIPUR | PUTPUTIA PWSS | TSM/011609 | SM/11886 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 1670 | 581.53 | Yes | 581.53 | 12/01/2023 | 06/02/2023 | 4 | 56.29 | 287.21 | MVS
232 | PURBA MEDINIPUR | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | TSM/010579 | SM/11887 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 0 | 57.27 | Yes | 57.27 | 13/02/2023 | 12/07/2023 | 6 | 43.83 | 37.18 | MVS
233 | PURBA MEDINIPUR | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/010576 | SM/11896 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 0 | 62.49 | Yes | 62.49 | 16/02/2023 | 12/07/2023 | 3 | 42.15 | 9.66 | MVS
234 | PURBA MEDINIPUR | Augmentation of Ground Water based Jalpai Water Supply Scheme. | TSM/011021 | SM/11920 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 7890 | 2009.45 | Yes | 2009.45 | 31/07/2024 | 14/06/2023 | 36 | 2002.4 | 1259.41 | MVS
235 | PURBA MEDINIPUR | KHARUI AND ADJOINING MOUZAS PWSS | TSM/011813 | SM/11945 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 2574 | 637.14 | Yes | 637.14 | 12/01/2023 | 24/06/2024 | 6 | 99.65 | 253.99 | MVS
236 | PURBA MEDINIPUR | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | TSM/011808 | SM/11946 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 4142 | 984.88 | Yes | 984.88 | 12/01/2023 | 15/07/2024 | 6 | 83.88 | 64.78 | MVS
237 | PURBA MEDINIPUR | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | TSM/011798 | SM/11947 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 3857 | 565.75 | Yes | 565.75 | 13/02/2023 | 14/06/2024 | 9 | 508.26 | 255.22 | MVS
238 | PURBA MEDINIPUR | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II) | TSM/010119 | SM/11948 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 4380 | 533.3 | Yes | 533.3 | 14/12/2022 | 16/08/2022 | 10 | 608.27 | 424 | MVS
239 | PURBA MEDINIPUR | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/010578 | SM/11949 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 0 | 71.08 | Yes | 71.08 | 22/05/2023 | 10/05/2023 | 6 | 52.86 | 11.77 | MVS
240 | PURBA MEDINIPUR | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | TSM/010437 | SM/11979 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 7010 | 1668.76 | Yes | 1668.76 | 06/03/2024 | 05/04/2022 | 10 | 2122.61 | 620.95 | MVS
241 | PURBA MEDINIPUR | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011103 | SM/11984 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 7156 | 1454.18 | Yes | 1454.18 | 28/11/2022 | 07/09/2022 | 11 | 1459.57 | 1206.8 | MVS
242 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | TSM/010583 | SM/12118 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 3903 | 1079.89 | Yes | 1079.89 | 19/12/2023 | 20/04/2023 | 17 | 632.58 | 667.39 | MVS
243 | PURBA MEDINIPUR | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | TSM/011904 | SM/12129 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2545 | 582.43 | Yes | 582.43 | 12/01/2023 | 06/02/2023 | 3 | 68.29 | 489.58 | MVS
244 | PURBA MEDINIPUR | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | TSM/011925 | SM/12130 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1566 | 411.46 | Yes | 411.46 | 12/01/2023 | 24/06/2024 | 9 | 60.61 | 104.11 | MVS
245 | PURBA MEDINIPUR | AGAR & ADJOINING MOUJAS PWSS | TSM/011926 | SM/12131 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 832 | 388.58 | Yes | 388.58 | 16/03/2023 | 24/06/2024 | 7 | 250.96 | 145.85 | MVS
246 | PURBA MEDINIPUR | AMARPUR & ADJOINING MOUZAS | TSM/013130 | SM/12132 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1297 | 537.37 | Yes | 537.37 | 25/05/2023 | 06/02/2023 | 4 | 55.87 | 218.2 | MVS
247 | PURBA MEDINIPUR | Tilkhoja & Adjoining mouzas | TSM/013132 | SM/12133 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2331 | 714.12 | Yes | 714.12 | 17/02/2023 | 10/01/2024 | 6 | 79.85 | 367.31 | MVS
248 | PURBA MEDINIPUR | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | TSM/013135 | SM/12134 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1988 | 706.44 | Yes | 706.44 | 07/01/2023 | 02/05/2023 | 6 | 626.99 | 78.15 | MVS
249 | PURBA MEDINIPUR | NAIPUR & ADJOINING MOUZAS | TSM/013138 | SM/12135 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1575 | 550.96 | Yes | 550.96 | 14/03/2023 | 16/01/2023 | 4 | 56.82 | 203.83 | MVS
250 | PURBA MEDINIPUR | KALABERIA & ADJOINING MOUZAS | TSM/013144 | SM/12136 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 3184 | 743.49 | Yes | 743.49 | 07/01/2023 | 16/01/2023 | 2 | 45.13 | 61.24 | MVS
251 | PURBA MEDINIPUR | JAMITTA & ADJOINING MOUZAS | TSM/013145 | SM/12137 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1163 | 373.67 | Yes | 373.67 | 29/11/2023 | 15/03/2023 | 10 | 293.56 | 188.94 | MVS
252 | PURBA MEDINIPUR | KAKRA & ADJOINING MOUZAS | TSM/013146 | SM/12138 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 3312 | 784.19 | Yes | 784.19 | 07/01/2023 | 04/05/2023 | 6 | 726.82 | 522.94 | MVS
253 | PURBA MEDINIPUR | EREKHALI AND ADJOINING MOUJAS PWSS | TSM/013147 | SM/12139 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1713 | 627.99 | Yes | 627.99 | 11/08/2023 | 11/05/2023 | 11 | 398.17 | 305.89 | MVS
254 | PURBA MEDINIPUR | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | TSM/013149 | SM/12140 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2038 | 582.1 | Yes | 582.1 | 06/01/2023 | 05/01/2024 | 4 | 58.03 | 358.01 | MVS
255 | PURBA MEDINIPUR | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013152 | SM/12141 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2407 | 894.23 | Yes | 894.23 | 28/02/2023 | 29/04/2024 | 3 | 78.22 | 275.7 | MVS
256 | PURBA MEDINIPUR | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | TSM/013154 | SM/12142 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1730 | 722.2 | Yes | 722.2 | 29/12/2022 | 10/04/2023 | 17 | 448.16 | 320.2 | MVS
257 | PURBA MEDINIPUR | BALGOBINDAPUR & ADJOINING MOUZAS | TSM/013159 | SM/12143 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2138 | 879.41 | Yes | 879.41 | 26/05/2023 | 05/09/2023 | 5 | 750.03 | 60.99 | MVS
258 | PURBA MEDINIPUR | BASANTA CHAK AND ADJOINING MOUJAS PWSS | TSM/013164 | SM/12144 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2072 | 564.98 | Yes | 564.98 | 17/02/2023 | 10/01/2024 | 6 | 67.27 | 390.26 | MVS
259 | PURBA MEDINIPUR | TANIA BILA AND ADJOINING MOUJAS PWSS | TSM/013166 | SM/12145 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1236 | 510.18 | Yes | 510.18 | 13/02/2023 | 25/07/2023 | 4 | 497.06 | 201.69 | MVS
260 | PURBA MEDINIPUR | BAKCHA AND ADJOINING MOUJAS PWSS | TSM/013173 | SM/12146 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2046 | 623.54 | Yes | 623.54 | 27/02/2025 | 10/01/2024 | 6 | 72.63 | 378.84 | MVS
261 | PURBA MEDINIPUR | RAMCHANDRAPUR AND ADJOINING MOUJAS | TSM/013184 | SM/12147 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2232 | 656.72 | Yes | 656.72 | 11/04/2023 | 11/05/2023 | 12 | 585.7 | 370.4 | MVS
262 | PURBA MEDINIPUR | BRINDABANPUR & ADJOINING MOUJAS PWSS | TSM/013186 | SM/12148 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1023 | 429.14 | Yes | 429.14 | 11/08/2023 | 20/02/2024 | 6 | 89.92 | 257.11 | MVS
263 | PURBA MEDINIPUR | GOBINDAPUR & ADJOINING MOUZAS | TSM/013193 | SM/12149 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 910 | 385.96 | Yes | 385.96 | 14/08/2023 | 05/01/2024 | 4 | 55.27 | 23.61 | MVS
264 | PURBA MEDINIPUR | HOGALBERYA AND ADJOINING MOUJAS PWSS | TSM/013195 | SM/12150 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2680 | 762.45 | Yes | 762.45 | 12/01/2023 | 05/01/2024 | 3 | 58.32 | 9.27 | MVS
265 | PURBA MEDINIPUR | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013196 | SM/12151 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2338 | 687.4 | Yes | 687.4 | 06/01/2023 | 10/12/2024 | 8 | 82.23 | 32.14 | MVS
266 | PURBA MEDINIPUR | HARINAN PWSS & ADJOINING MOUJAS | TSM/013202 | SM/12152 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2360 | 708.52 | Yes | 708.52 | 06/01/2023 | 05/01/2024 | 7 | 61.56 | 444.9 | MVS
267 | PURBA MEDINIPUR | MIRJAPUR AND ADJOINING MOUJAS PWSS | TSM/013480 | SM/12153 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2305 | 939.19 | Yes | 939.19 | 07/01/2023 | 04/05/2023 | 7 | 794.63 | 523.49 | MVS
268 | PURBA MEDINIPUR | PURBA RADHAPUR & ADJOINING MOUZAS | TSM/013212 | SM/12154 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1870 | 758.06 | Yes | 758.06 | 07/01/2023 | 08/06/2023 | 8 | 694.55 | 309.35 | MVS
269 | PURBA MEDINIPUR | GOYALDA & ADJOINING MOUZAS PWSS | TSM/013213 | SM/12155 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1582 | 579.91 | Yes | 579.91 | 07/01/2023 | 01/06/2023 | 5 | 524.07 | 249.05 | MVS
270 | PURBA MEDINIPUR | RADHABALLAV CHAK & ADJOINING MOUZAS | TSM/013217 | SM/12156 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2026 | 715.87 | Yes | 715.87 | 27/02/2025 | 10/01/2024 | 6 | 87.58 | 421.65 | MVS
271 | PURBA MEDINIPUR | BIJAYNAGAR & ADJOINING MOUJAS PWSS | TSM/013223 | SM/12157 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1750 | 695.66 | Yes | 695.66 | 11/08/2023 | 01/10/2024 | 10 | 679.36 | 321.74 | MVS
272 | PURBA MEDINIPUR | GOPINATHPUR & ADJOINING MOUZAS | TSM/013247 | SM/12158 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1851 | 727.42 | Yes | 727.42 | 27/01/2023 | 04/05/2023 | 6 | 666.86 | 460.51 | MVS
273 | PURBA MEDINIPUR | GAR BHERA & ADJOINING MOUZAS | TSM/013250 | SM/12159 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1275 | 596.45 | Yes | 596.45 | 07/01/2023 | 10/04/2023 | 6 | 523.62 | 366.16 | MVS
274 | PURBA MEDINIPUR | UTTAR CHANDRA CHAK AND ADJOINING MOUJAS PWSS | TSM/013252 | SM/12160 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2064 | 751.44 | Yes | 751.44 | 17/02/2023 | 10/01/2024 | 6 | 87.95 | 370.43 | MVS
275 | PURBA MEDINIPUR | GOBRADAN & ADJOINING MOUZAS | TSM/013255 | SM/12161 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1420 | 569.73 | Yes | 569.73 | 17/02/2023 | 10/01/2024 | 6 | 78.59 | 297.85 | MVS
276 | PURBA MEDINIPUR | ABAS BERYA & ADJOINING MOUZAS | TSM/013303 | SM/12162 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1576 | 620.61 | Yes | 620.61 | 16/03/2023 | 12/07/2023 | 7 | 535.27 | 146.4 | MVS
277 | PURBA MEDINIPUR | SATSATMAL & ADJOINING MOUJAS PWSS | TSM/013315 | SM/12163 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2638 | 975.7 | Yes | 975.7 | 13/02/2023 | 25/07/2023 | 6 | 869.06 | 366.27 | MVS
278 | PURBA MEDINIPUR | PATNA & ADJOINING MOUZAS | TSM/013343 | SM/12164 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2930 | 1065.08 | Yes | 1065.08 | 22/05/2023 | 03/06/2025 | 8 | 972.88 | 491.24 | MVS
279 | PURBA MEDINIPUR | GOKULNAGAR AND ADJOINING MOUJAS | TSM/013479 | SM/12165 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2421 | 821.18 | Yes | 821.18 | 17/02/2023 | 10/01/2024 | 6 | 60.63 | 422.89 | MVS
280 | PURBA MEDINIPUR | URURI AND ADJOINING MOUJAS PWSS | TSM/013484 | SM/12166 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2233 | 816.68 | Yes | 816.68 | 12/09/2024 | 10/03/2023 | 11 | 379.86 | 313.8 | MVS
281 | PURBA MEDINIPUR | KAYEMGERYA AND ADJOINING MOUJAS PWSS | TSM/013485 | SM/12167 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2055 | 744.93 | Yes | 744.93 | 11/08/2023 | 27/03/2023 | 7 | 140.6 | 333.41 | MVS
282 | PURBA MEDINIPUR | KEKAI & ADJOINING MOUJAS PWSS | TSM/013491 | SM/12168 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1793 | 742.03 | Yes | 742.03 | 14/03/2023 | 01/10/2024 | 8 | 86.79 | 186.85 | MVS
283 | PURBA MEDINIPUR | BAHADURPUR AND ADJOINING MOUJAS PWSS | TSM/013492 | SM/12169 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2470 | 915.42 | Yes | 915.42 | 16/03/2023 | 29/07/2024 | 9 | 466.26 | 443.06 | MVS
284 | PURBA MEDINIPUR | PANCHET AND ADJOINING MOUJAS PWSS | TSM/013494 | SM/12170 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1919 | 897.82 | Yes | 897.82 | 14/03/2023 | 09/07/2024 | 6 | 73.43 | 240.22 | MVS
285 | PURBA MEDINIPUR | MANIKJOR AND ADJOINING MOUJAS PWSS | TSM/013499 | SM/12171 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2206 | 927.42 | Yes | 927.42 | 16/03/2023 | 12/05/2023 | 8 | 590.96 | 227.91 | MVS
286 | PURBA MEDINIPUR | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | TSM/013500 | SM/12172 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1875 | 664.72 | Yes | 664.72 | 14/03/2023 | 24/06/2024 | 4 | 68.5 | 55.51 | MVS
287 | PURBA MEDINIPUR | PANCH BAJARI & ADJOINING MOUJAS PWSS | TSM/013501 | SM/12173 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1015 | 484.28 | Yes | 484.28 | 16/03/2023 | 10/04/2023 | 8 | 196.09 | 163.24 | MVS
288 | PURBA MEDINIPUR | AJAYA & ADJOINING MOUJAS PWSS | TSM/013505 | SM/12174 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 3771 | 817.13 | Yes | 817.13 | 16/03/2023 | 12/09/2024 | 5 | 69.28 | 504.54 | MVS
289 | PURBA MEDINIPUR | KHARAT KATBAR & ADJOINING MOUJAS PWSS | TSM/013509 | SM/12175 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1895 | 725.48 | Yes | 725.48 | 14/03/2023 | 09/07/2024 | 7 | 79.36 | 140.92 | MVS
290 | PURBA MEDINIPUR | RUKMINIPUR AND ADJOINING MOUJAS PWSS | TSM/013518 | SM/12176 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1588 | 739.06 | Yes | 739.06 | 10/01/2023 | 04/05/2023 | 4 | 525.5 | 256.88 | MVS
291 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | TSM/012057 | SM/12177 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 05/07/2022 | 2657 | 154.98 | Yes | 154.98 |  | 24/11/2022 | 3 | 141.99 | 81.24 | MVS
292 | PURBA MEDINIPUR | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | TSM/011155 | SM/12268 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 6014 | 1409.77 | Yes | 1409.77 | 28/11/2022 | 07/06/2024 | 9 | 1362.53 | 612.75 | MVS
293 | PURBA MEDINIPUR | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011906 | SM/12279 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 4912 | 1684.91 | Yes | 1684.91 | 28/11/2022 | 19/06/2025 | 11 | 1541.57 | 1236.67 | MVS
294 | PURBA MEDINIPUR | MAYACHAR AND ADJOINING MOUJAS PWSS | TSM/014303 | SM/12281 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1306 | 575.5 | Yes | 575.5 | 31/01/2023 | 24/06/2024 | 9 | 250.59 | 222.47 | MVS
295 | PURBA MEDINIPUR | MAKRAMPUR AND ADJOINING MOUJAS PWSS | TSM/014260 | SM/12282 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1422 | 752.28 | Yes | 752.28 | 14/03/2023 | 16/01/2023 | 4 | 61.77 | 83.52 | MVS
296 | PURBA MEDINIPUR | TALADIHA AND ADJOINING MOUJAS PWSS | TSM/014254 | SM/12283 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1324 | 496.8 | Yes | 496.8 | 14/01/2023 | 08/06/2023 | 4 | 454.14 | 131.69 | MVS
297 | PURBA MEDINIPUR | TAJPUR AND ADJOINING MOUJAS PWSS | TSM/014247 | SM/12284 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 2785 | 815.19 | Yes | 815.19 | 10/01/2023 | 22/04/2025 | 7 | 782.81 | 357.01 | MVS
298 | PURBA MEDINIPUR | DANGAR TULSI AND ADJOINING MOUJAS PWSS | TSM/014243 | SM/12285 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1347 | 712.76 | Yes | 712.76 | 14/03/2023 | 16/01/2023 | 4 | 64.58 | 229.55 | MVS
299 | PURBA MEDINIPUR | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | TSM/014238 | SM/12286 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 2130 | 776 | Yes | 776 | 01/03/2024 | 07/06/2024 | 12 | 635.13 | 396.23 | MVS
300 | PURBA MEDINIPUR | DEPAL AND ADJOINING MOUJAS PWSS | TSM/014228 | SM/12287 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1789 | 640.15 | Yes | 640.15 | 11/01/2023 | 29/08/2024 | 7 | 581.62 | 283.22 | MVS
301 | PURBA MEDINIPUR | TELAMI AND ADJOINING MOUJAS PWSS | TSM/014226 | SM/12288 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 724 | 462.76 | Yes | 462.76 | 14/03/2023 | 24/06/2024 | 5 | 70.94 | 155.17 | MVS
302 | PURBA MEDINIPUR | KANTHI BARI AND ADJOINING MOUJAS PWSS | TSM/014225 | SM/12289 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1276 | 795.33 | Yes | 795.33 | 16/03/2023 | 10/06/2024 | 6 | 655.41 | 445.53 | MVS
303 | PURBA MEDINIPUR | BAISPUR AND ADJOINING MOUJAS PWSS | TSM/014224 | SM/12290 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1251 | 495.84 | Yes | 495.84 | 14/03/2023 | 09/07/2024 | 3 | 45.08 | 224.07 | MVS
304 | PURBA MEDINIPUR | UTTAR DAIDPUR AND ADJOINING MOUJAS PWSS | TSM/014130 | SM/12291 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1648 | 717.02 | Yes | 717.02 | 15/03/2023 | 19/07/2023 | 5 | 583.07 | 321.97 | MVS
305 | PURBA MEDINIPUR | PACHAHRI & ADJOINING MOUJAS PWSS | TSM/014128 | SM/12292 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 2014 | 614.09 | Yes | 614.09 | 16/03/2023 | 01/10/2024 | 12 | 492.17 | 319.83 | MVS
306 | PURBA MEDINIPUR | DAKSHINPATHAR BERYA AND ADJOINING MOUJAS PWSS | TSM/014119 | SM/12293 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1638 | 665.46 | Yes | 665.46 | 16/03/2023 | 01/10/2024 | 6 | 533.28 | 210.21 | MVS
307 | PURBA MEDINIPUR | ILASHPUR AND ADJOINING MOUJAS PWSS | TSM/013993 | SM/12294 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 2038 | 847.64 | Yes | 847.64 | 07/01/2023 | 29/08/2024 | 7 | 729.48 | 423.18 | MVS
308 | PURBA MEDINIPUR | NAICHHANPUR AND ADJOINING MOUJAS PWSS | TSM/013987 | SM/12295 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1513 | 593.04 | Yes | 593.04 | 16/03/2023 | 02/05/2023 | 10 | 478.67 | 407.94 | MVS
309 | PURBA MEDINIPUR | SAHARA AND ADJOINING MOUJAS PWSS | TSM/013976 | SM/12296 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1155 | 500.78 | Yes | 500.78 | 14/03/2023 | 29/07/2024 | 5 | 49.26 | 210.05 | MVS
310 | PURBA MEDINIPUR | BASUDEVBERYA AND ADJOINING MOUJAS PWSS | TSM/013975 | SM/12297 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1064 | 541.09 | Yes | 541.09 | 16/03/2023 | 10/03/2023 | 12 | 198.35 | 207.24 | MVS
311 | PURBA MEDINIPUR | ERENDA AND ADJOINING MOUJAS PWSS | TSM/013974 | SM/12298 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1749 | 697.48 | Yes | 697.48 | 15/03/2023 | 21/07/2023 | 5 | 565.97 | 264.12 | MVS
312 | PURBA MEDINIPUR | GATHRA AND ADJOINING MOUJAS PWSS | TSM/013973 | SM/12299 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 3418 | 627.78 | Yes | 627.78 | 06/01/2023 | 07/06/2024 | 8 | 67.63 | 307.49 | MVS
313 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC (1841 Nos.) of Chandibenia Zone-II and its adjoining mouzas water supply scheme under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the district Purba Medinipur. | TSM/010962 | SM/12300 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 15/07/2022 | 1841 | 94.16 | Yes | 94.16 |  | 26/09/2022 | 2 | 69.23 | 69.04 | MVS
314 | PURBA MEDINIPUR | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the district of Purba Medinipur. | TSM/010963 | SM/12301 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 15/07/2022 | 2244 | 112.8 | Yes | 112.8 |  | 26/09/2022 | 2 | 86.96 | 68.76 | MVS
315 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Nijkasba PWSS under Khejuri-II Block. | TSM/010936 | SM/12302 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 15/07/2022 | 763 | 45.03 | Yes | 45.03 |  | 10/05/2023 | 4 | 44.7 | 42.38 | MVS
316 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Baranalgeria (Zone-I) PWSS under Egra-II Block. | TSM/013464 | SM/12303 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 15/07/2022 | 2340 | 135.48 | Yes | 135.48 | 27/11/2024 | 16/10/2023 | 3 | 146.17 | 68.75 | MVS
317 | PURBA MEDINIPUR | BARDA AND ADJOINING MOUJAS PWSS | TSM/014245 | SM/12306 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1396 | 594.37 | Yes | 594.37 | 14/03/2023 | 02/08/2024 | 5 | 74.68 | 151.46 | MVS
318 | PURBA MEDINIPUR | KALYANPUR AND ADJOINING MOUJAS PWSS at Potashpur-II Block. | TSM/014232 | SM/12307 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1198 | 514.51 | Yes | 514.51 | 28/02/2023 | 29/04/2024 | 5 | 54.81 | 51.65 | MVS
319 | PURBA MEDINIPUR | JERTHAN AND ADJOINING MOUJAS PWSS | TSM/014233 | SM/12308 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 2232 | 762.33 | Yes | 762.33 | 14/03/2023 | 10/12/2024 | 5 | 78.35 | 468.18 | MVS
320 | PURBA MEDINIPUR | SARBERYA AND ADJOINING MOUJAS PWSS at Bhagwanpur-I Block. | TSM/014235 | SM/12310 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 2095 | 899.01 | Yes | 899.01 | 07/01/2023 | 04/05/2023 | 14 | 765.14 | 461.35 | MVS
321 | PURBA MEDINIPUR | CHONGRA AND ADJOINING MOUJAS PWSS at Moyna Block. | TSM/014236 | SM/12318 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1929 | 727.81 | Yes | 727.81 | 27/02/2025 | 10/01/2024 | 6 | 113.4 | 355.97 | MVS
322 | PURBA MEDINIPUR | TAPINDA AND ADJOINING MOUJAS PWSS at Potashpur_I Block. | TSM/014237 | SM/12319 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1165 | 532.38 | Yes | 532.38 | 14/03/2023 | 16/01/2023 | 4 | 62.87 | 147.97 | MVS
323 | PURBA MEDINIPUR | ALANGIRI AND ADJOINING MOUJAS PWSS at Agra-I Block. | TSM/014317 | SM/12320 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1497 | 674.76 | Yes | 674.76 | 14/03/2023 | 10/12/2024 | 5 | 71.98 | 220.78 | MVS
324 | PURBA MEDINIPUR | UTTAR SILAMPUR AND IT'S ADJOININGT MOUJAS PWSS at Egra_II Block. | TSM/014330 | SM/12321 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1155 | 630.08 | Yes | 630.08 | 15/03/2023 | 19/07/2023 | 5 | 505.79 | 291.54 | MVS
325 | PURBA MEDINIPUR | SANTRA AND IT'S ADJOINING MOUJAS PWSS at Ramnagar-I Block. | TSM/014333 | SM/12322 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1709 | 556 | Yes | 556 | 15/03/2023 | 30/10/2023 | 6 | 490.12 | 286.32 | MVS
326 | PURBA MEDINIPUR | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B). | TSM/011153 | SM/12364 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 25/04/2022 | 5100 | 1068.67 | Yes | 1068.67 | 28/11/2022 | 29/04/2024 | 22 | 1048.23 | 489.58 | MVS
327 | PURBA MEDINIPUR | MUSTAPHAPUR AND ADJOINING MOUJAS PWSS | TSM/014495 | SM/12398 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1806 | 645.5 | Yes | 645.5 | 14/03/2023 | 09/07/2024 | 6 | 65.8 | 211.13 | MVS
328 | PURBA MEDINIPUR | BARAHAT AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014484 | SM/12399 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1808 | 696.35 | Yes | 696.35 | 17/02/2023 | 26/09/2023 | 5 | 578.56 | 157.84 | MVS
329 | PURBA MEDINIPUR | PAHARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014480 | SM/12400 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1112 | 465.14 | Yes | 465.14 | 14/03/2023 | 16/01/2023 | 3 | 83.1 | 197.19 | MVS
330 | PURBA MEDINIPUR | NARAYAN DANRI AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014472 | SM/12401 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2186 | 706.42 | Yes | 706.42 | 07/01/2023 | 05/01/2024 | 3 | 543.83 | 53.04 | MVS
331 | PURBA MEDINIPUR | NILKANTHAPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | TSM/014433 | SM/12402 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1669 | 650.26 | Yes | 650.26 | 07/01/2023 | 10/04/2023 | 6 | 554.4 | 187.26 | MVS
332 | PURBA MEDINIPUR | KANCHANPUR AND ADJOINING MOUJAS PWSS | TSM/014432 | SM/12403 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1704 | 584.24 | Yes | 584.24 | 11/08/2023 | 11/05/2023 | 17 | 414.37 | 217.35 | MVS
333 | PURBA MEDINIPUR | DWARIKAPUR AND IT'S ADJOINING MOUJAAS PWSS | TSM/014419 | SM/12404 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1656 | 572.81 | Yes | 572.81 | 07/01/2023 | 10/04/2023 | 4 | 453.98 | 13.98 | MVS
334 | PURBA MEDINIPUR | DAKSHIN KADUA AND ADJOINING MOUJAS PWSS | TSM/014390 | SM/12405 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 893 | 466.31 | Yes | 466.31 | 28/02/2023 | 21/07/2023 | 4 | 418.36 | 25.77 | MVS
335 | PURBA MEDINIPUR | DAKSHIN KALAMDAN AND ADJOINING MOUJAS PWSS | TSM/014320 | SM/12406 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2186 | 1061.78 | Yes | 1061.78 | 22/05/2023 | 12/09/2024 | 6 | 88.97 | 627.06 | MVS
336 | PURBA MEDINIPUR | DAKSHIN SHITALA AND ADJOINING MOUJAS PWSS | TSM/014290 | SM/12407 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1020 | 545.08 | Yes | 545.08 | 16/03/2023 | 11/04/2023 | 16 | 455.99 | 251.4 | MVS
337 | PURBA MEDINIPUR | PURBO PURUSHOTTAMPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/014867 | SM/12428 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 618 | 412.24 | Yes | 412.24 | 16/03/2023 | 01/06/2023 | 7 | 330.23 | 210.46 | MVS
338 | PURBA MEDINIPUR | BAGMARI AND IT'S ADJOINING MOUJAS PWSS | TSM/014858 | SM/12429 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1230 | 560.42 | Yes | 560.42 | 14/01/2023 | 07/06/2024 | 8 | 520.64 | 338.01 | MVS
339 | PURBA MEDINIPUR | PADIMA AND ADJOINING MOUJAS PWSS | TSM/014852 | SM/12430 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 960 | 460.25 | Yes | 460.25 | 23/05/2023 | 11/04/2025 | 8 | 405.62 | 266.36 | MVS
340 | PURBA MEDINIPUR | CHINGUR DANIA AND IT'S ADJOINING MOUJAS PWSS | TSM/014797 | SM/12431 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1342 | 827.64 | Yes | 827.64 | 16/03/2023 | 12/09/2024 | 4 | 38.36 | 379.15 | MVS
341 | PURBA MEDINIPUR | TALCHITKINI AND IT'S ADJOINING MOUJAS PWSS | TSM/014777 | SM/12433 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1833 | 540.95 | Yes | 540.95 | 14/02/2023 | 25/07/2023 | 3 | 522.91 | 20.29 | MVS
342 | PURBA MEDINIPUR | PURBA MUKUNDAPUR AND IT'S ADJOINING MOUJAS | TSM/014736 | SM/12434 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1267 | 617.73 | Yes | 617.73 | 15/03/2023 | 07/06/2024 | 6 | 587.06 | 363.1 | MVS
343 | PURBA MEDINIPUR | TIKASHI PWSS at Khejuri-I Block in Tamluk Division P.H.E. Dte. | TSM/014642 | SM/12482 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2478 | 1000.8 | Yes | 1000.8 | 22/05/2023 | 20/04/2023 | 18 | 583.84 | 583.34 | MVS
344 | PURBA MEDINIPUR | KHAGDA PWSS at Egra-II Block in Tamluk Division P.H.E. Dte. | TSM/014423 | SM/12483 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1068 | 520.66 | Yes | 520.66 | 11/04/2023 | 31/07/2023 | 4 | 423.77 | 180.26 | MVS
345 | PURBA MEDINIPUR | DHANKAR & IT'S ADJOINING MOUJAS at Potashpur-I Block. | TSM/014727 | SM/12484 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1463 | 482.07 | Yes | 482.07 | 14/02/2023 | 25/07/2023 | 5 | 465.2 | 194.02 | MVS
346 | PURBA MEDINIPUR | Augmentation of Ramnagar (Zone-I) PWSS | TSM/012859 | SM/12485 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 3086 | 835.22 | Yes | 835.22 | 07/12/2023 | 19/01/2023 | 9 | 542.33 | 254.43 | MVS
347 | PURBA MEDINIPUR | Augmentation of Ramnagar (Zone-II) PWSS | TSM/012861 | SM/12486 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2941 | 889.59 | Yes | 889.59 | 07/12/2023 | 04/07/2022 | 9 | 628.82 | 319.26 | MVS
348 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I | TSM/012804 | SM/12487 | Augmentation | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 4400 | 989.31 | Yes | 989.31 | 28/11/2022 | 19/09/2024 | 10 | 222.84 | 264.35 | MVS
349 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II | TSM/012805 | SM/12488 | Augmentation | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2338 | 740.92 | Yes | 740.92 |  | 17/05/2023 | 13 | 533.13 | 390.43 | MVS
350 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | TSM/012050 | SM/12489 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2596 | 712.69 | Yes | 712.69 | 01/03/2024 | 04/01/2024 | 10 | 699.37 | 402.68 | MVS
351 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | TSM/012051 | SM/12490 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2244 | 662.45 | Yes | 662.45 | 28/11/2022 | 24/11/2022 | 11 | 608.84 | 374.34 | MVS
352 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | TSM/011282 | SM/12491 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 3188 | 745.53 | Yes | 745.53 | 07/12/2022 | 27/04/2023 | 11 | 600.23 | 333.32 | MVS
353 | PURBA MEDINIPUR | SIMULYA & IT'S ADJOINING MOUJAS PWSS | TSM/014706 | SM/12492 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2740 | 917.62 | Yes | 917.62 | 07/01/2023 | 09/07/2024 | 6 | 761.36 | 299.01 | MVS
354 | PURBA MEDINIPUR | BAMANPUR AND ADJOINING MOUJAS PWSS | TSM/014648 | SM/12493 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1362 | 606.04 | Yes | 606.04 | 02/02/2023 | 15/12/2023 | 11 | 245.86 | 252.31 | MVS
355 | PURBA MEDINIPUR | SHWNIA AND ADJOINING MOUJAS PWSS | TSM/014643 | SM/12494 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 734 | 453.35 | Yes | 453.35 | 14/03/2023 | 10/12/2024 | 4 | 46.22 | 171.35 | MVS
356 | PURBA MEDINIPUR | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS | TSM/014595 | SM/12495 | New | Contai Sub-Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1623 | 581.74 | Yes | 581.74 | 13/02/2023 | 05/01/2024 | 4 | 542.67 | 124.65 | MVS
357 | PURBA MEDINIPUR | SHOULA BHERI AND ADJOINING MOUJAS PWSS | TSM/014514 | SM/12496 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2921 | 922.95 | Yes | 922.95 | 14/03/2023 | 16/01/2023 | 4 | 52.61 | 274.39 | MVS
358 | PURBA MEDINIPUR | BIRAMPUT AND ADJOINING MOUJAS PWSS | TSM/014502 | SM/12497 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 940 | 512.1 | Yes | 512.1 | 17/02/2023 | 24/06/2024 | 5 | 75.7 | 273.01 | MVS
359 | PURBA MEDINIPUR | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | TSM/014501 | SM/12498 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1757 | 767.33 | Yes | 767.33 | 18/01/2024 | 15/12/2023 | 14 | 491.03 | 352.12 | MVS
360 | PURBA MEDINIPUR | KAJI BASAN AND ADJOINING MOUJAS PWSS | TSM/014499 | SM/12499 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1276 | 576.08 | Yes | 576.08 | 14/03/2023 | 12/09/2024 | 4 | 58.4 | 199.97 | MVS
361 | PURBA MEDINIPUR | FULESHWAR AND ADJOINING MOUJAS PWSS | TSM/014498 | SM/12500 | New | Contai Sub-Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1268 | 658.22 | Yes | 658.22 | 14/03/2023 | 14/03/2024 | 6 | 81.01 | 209 | MVS
362 | PURBA MEDINIPUR | BARTTAN AND ADJOINING MOUJAS PWSS | TSM/014483 | SM/12501 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 3076 | 1048.66 | Yes | 1048.66 | 07/01/2023 | 04/05/2023 | 6 | 867.26 | 404.82 | MVS
363 | PURBA MEDINIPUR | JAYNAGAR AND ADJOINING MOUJAS PWSS | TSM/014479 | SM/12502 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2174 | 773.24 | Yes | 773.24 | 29/12/2022 | 07/04/2025 | 13 | 484.08 | 228.7 | MVS
364 | PURBA MEDINIPUR | SHIPUR AND ADJOINING MOUJAS PWSS | TSM/014470 | SM/12503 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1484 | 698.5 | Yes | 698.5 | 14/03/2023 | 24/06/2024 | 3 | 43.71 | 262.8 | MVS
365 | PURBA MEDINIPUR | KHAGA AND IT'S ADJOINING MOUJAS PWSS | TSM/014443 | SM/12504 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1806 | 764.31 | Yes | 764.31 | 07/01/2023 | 23/05/2023 | 7 | 683.2 | 310.87 | MVS
366 | PURBA MEDINIPUR | CHALTI AND ADJOINING MOUJAS PWSS | TSM/014430 | SM/12505 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1098 | 592.82 | Yes | 592.82 | 14/03/2023 | 29/07/2024 | 6 | 105.52 | 102.27 | MVS
367 | PURBA MEDINIPUR | PANUSI AND ADJOINING MOUJAS PWSS | TSM/014429 | SM/12506 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2037 | 788.16 | Yes | 788.16 | 16/03/2023 | 27/04/2023 | 17 | 675.37 | 374.85 | MVS
368 | PURBA MEDINIPUR | PURBA MUKUNDAPUR AND ADJOINING MOUJAS PWSS | TSM/014426 | SM/12507 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1702 | 593.43 | Yes | 593.43 | 28/02/2023 | 21/07/2023 | 4 | 542.09 | 149.77 | MVS
369 | PURBA MEDINIPUR | PALPARA AND ADJOINING MOUJAS PWSS | TSM/014407 | SM/12508 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2861 | 754.82 | Yes | 754.82 | 07/01/2023 | 26/04/2024 | 6 | 728.75 | 166.7 | MVS
370 | PURBA MEDINIPUR | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | TSM/014405 | SM/12509 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1660 | 683.07 | Yes | 683.07 | 16/03/2023 | 19/04/2023 | 10 | 572.6 | 367.53 | MVS
371 | PURBA MEDINIPUR | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | TSM/014394 | SM/12510 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2000 | 755.87 | Yes | 755.87 | 14/03/2023 | 29/08/2024 | 5 | 72.44 | 244.45 | MVS
372 | PURBA MEDINIPUR | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | TSM/014393 | SM/12511 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1138 | 524.62 | Yes | 524.62 | 14/03/2023 | 29/04/2024 | 5 | 78.11 | 136.86 | MVS
373 | PURBA MEDINIPUR | SRIKANTHA AND ADJOINING MOUJAS PWSS | TSM/014392 | SM/12512 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2575 | 756.99 | Yes | 756.99 | 28/02/2025 | 04/04/2025 | 16 | 58.4 | 183.95 | MVS
374 | PURBA MEDINIPUR | KSHETRAPAL AND IT'S ADJOINING MOUJAS | TSM/014735 | SM/12513 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1880 | 695.17 | Yes | 695.17 | 14/03/2023 | 24/06/2024 | 7 | 63.66 | 299.56 | MVS
375 | PURBA MEDINIPUR | KAINARA & IT'S ADJOING MOUJAS | TSM/014729 | SM/12514 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2233 | 784.6 | Yes | 784.6 | 15/03/2023 | 30/10/2023 | 7 | 669.07 | 461.78 | MVS
376 | PURBA MEDINIPUR | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | TSM/014728 | SM/12515 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1635 | 657.71 | Yes | 657.71 | 29/11/2023 | 07/06/2024 | 22 | 634.47 | 387.74 | MVS
377 | PURBA MEDINIPUR | MIRJAPUR AND IT'S ADJOINING MOUJAS | TSM/014726 | SM/12516 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1035 | 515.17 | Yes | 515.17 | 16/03/2023 | 19/04/2023 | 9 | 296.66 | 110.51 | MVS
378 | PURBA MEDINIPUR | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | TSM/014534 | SM/12517 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2007 | 743.4 | Yes | 743.4 | 28/02/2023 | 25/07/2023 | 6 | 619.58 | 275.23 | MVS
379 | PURBA MEDINIPUR | SELMABAD AND ADJOINING MOUJAS PWSS | TSM/014513 | SM/12518 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2717 | 757.8 | Yes | 757.8 | 14/03/2023 | 06/11/2024 | 5 | 48.38 | 168.33 | MVS
380 | PURBA MEDINIPUR | Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | TSM/011901 | SM/12570 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 20/05/2022 | 7341 | 1708.39 | Yes | 1708.39 | 28/11/2022 | 27/04/2023 | 10 | 1718.51 | 1201.37 | MVS
381 | PURBA MEDINIPUR | KIARANA AND ADJOINING MOUJAS PWSS | TSM/014257 | SM/12628 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1424 | 710.87 | Yes | 710.87 | 17/02/2023 | 10/01/2024 | 6 | 87.72 | 433.43 | MVS
382 | PURBA MEDINIPUR | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | TSM/014306 | SM/12634 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1062 | 503.6 | Yes | 503.6 | 14/03/2023 | 24/06/2024 | 5 | 50.24 | 123.87 | MVS
383 | PURBA MEDINIPUR | BARA BHAGIA AND ADJOINING MOUJAS PWSS | TSM/014512 | SM/12704 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1110 | 498.09 | Yes | 498.09 | 28/02/2023 | 16/01/2023 | 4 | 64.93 | 54.22 | MVS
384 | PURBA MEDINIPUR | BELDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013396 | SM/12710 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2385 | 699.88 | Yes | 699.88 | 14/03/2023 | 16/01/2023 | 3 | 49.46 | 210.13 | MVS
385 | PURBA MEDINIPUR | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/014776 | SM/12774 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1680 | 676.58 | Yes | 676.58 | 14/03/2023 | 09/07/2024 | 6 | 57.01 | 162.43 | MVS
386 | PURBA MEDINIPUR | SOYA DIGHI AND IT'S ADJOINING MOUJAS | TSM/014723 | SM/12809 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1914 | 554.17 | Yes | 554.17 | 27/01/2023 | 02/05/2023 | 6 | 481.91 | 96.42 | MVS
387 | PURBA MEDINIPUR | GOJINA AND IT'S ADJOINING MOUJAS PWSS | TSM/014708 | SM/12812 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2437 | 766.35 | Yes | 766.35 | 17/02/2023 | 10/01/2024 | 6 | 94.8 | 425.11 | MVS
388 | PURBA MEDINIPUR | JAHANABAD AND IT'S ADJOINING MOUJAS | TSM/014704 | SM/12813 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2411 | 974.08 | Yes | 974.08 | 22/05/2023 | 12/07/2023 | 5 | 869.37 | 386.69 | MVS
389 | PURBA MEDINIPUR | KIA AND IT'S ADJOINING MOUJAS | TSM/014692 | SM/12814 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1897 | 720.1 | Yes | 720.1 | 14/03/2023 | 24/06/2024 | 5 | 67.46 | 309.49 | MVS
390 | PURBA MEDINIPUR | KATARI AND ADJOINING MOUJAS PWSS | TSM/014682 | SM/12815 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 767 | 416.52 | Yes | 416.52 | 22/05/2023 | 12/09/2024 | 8 | 80.45 | 193.22 | MVS
391 | PURBA MEDINIPUR | BARAMRIT BERE AND IT'S ADJOINING MOUJAS PWSS | TSM/014666 | SM/12816 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1500 | 600.38 | Yes | 600.38 | 17/02/2023 | 29/07/2024 | 8 | 534.34 | 345.61 | MVS
392 | PURBA MEDINIPUR | PURANDA AND IT'S ADJOINING MOUJAS PWSS | TSM/014593 | SM/12818 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1330 | 640.79 | Yes | 640.79 | 14/03/2023 | 09/07/2024 | 5 | 58.06 | 278.73 | MVS
393 | PURBA MEDINIPUR | DURMUT AND ADJOINING MOUJAS PWSS | TSM/014591 | SM/12820 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1698 | 690.44 | Yes | 690.44 | 14/03/2023 | 12/09/2024 | 3 | 75.17 | 66.73 | MVS
394 | PURBA MEDINIPUR | HALUD BARI AND ADJOINING MOUJAS | TSM/014557 | SM/12821 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2543 | 728 | Yes | 728 | 13/01/2023 | 07/02/2024 | 5 | 55.04 | 525.6 | MVS
395 | PURBA MEDINIPUR | BARMUNDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013148 | SM/12878 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 1527 | 721.18 | Yes | 721.18 | 13/02/2023 | 25/07/2023 | 7 | 653.3 | 36.61 | MVS
396 | PURBA MEDINIPUR | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | TSM/014444 | SM/12886 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 1045 | 531.79 | Yes | 531.79 | 17/02/2023 | 24/06/2024 | 4 | 47.29 | 326.74 | MVS
397 | PURBA MEDINIPUR | JUMKI AND ADJOINING MOUJAS PWSS | TSM/014230 | SM/12995 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 15/07/2022 | 1636 | 620.99 | Yes | 620.99 | 17/02/2023 | 27/09/2024 | 6 | 521.51 | 285.02 | MVS
398 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | TSM/014506 | SM/13238 | Retrofitting | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 364 | 143.18 | Yes | 143.18 | 16/02/2023 | 16/09/2022 | 6 | 89.7 | 64.7 | MVS
399 | PURBA MEDINIPUR | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015729 | SM/13683 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 2111 | 710.43 | Yes | 710.43 | 16/03/2023 | 11/04/2023 | 12 | 438.83 | 319 | MVS
400 | PURBA MEDINIPUR | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | TSM/015583 | SM/13686 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1135 | 520.05 | Yes | 520.05 | 28/02/2023 | 21/07/2023 | 6 | 463.87 | 206.2 | MVS
401 | PURBA MEDINIPUR | FATEPUR AND ADJOINING MOUJAS PWSS | TSM/015723 | SM/13687 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 377 | 231 | Yes | 231 | 11/01/2023 | 04/12/2024 | 6 | 34.09 | 88.39 | MVS
402 | PURBA MEDINIPUR | SAR BERYA AND ADJOINING MOUJAS PWSS | TSM/015727 | SM/13688 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 875 | 479.68 | Yes | 479.68 | 18/01/2024 | 26/07/2024 | 12 | 354.85 | 260.32 | MVS
403 | PURBA MEDINIPUR | KADUA AND IT'S ADJOINING MOUJAS | TSM/015580 | SM/13689 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 2150 | 741.86 | Yes | 741.86 | 16/03/2023 | 12/05/2023 | 13 | 617.29 | 257.33 | MVS
404 | PURBA MEDINIPUR | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015573 | SM/13690 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 695 | 464.83 | Yes | 464.83 | 17/02/2023 | 29/07/2024 | 6 | 77.44 | 136.51 | MVS
405 | PURBA MEDINIPUR | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | TSM/015571 | SM/13691 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 985 | 571.07 | Yes | 571.07 | 17/02/2023 | 10/01/2024 | 5 | 78.18 | 299.3 | MVS
406 | PURBA MEDINIPUR | KAPASDA & IT'S ADJOINING MOUJAS PWSS | TSM/015579 | SM/13692 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1475 | 778.74 | Yes | 778.74 | 17/02/2023 | 12/09/2024 | 3 | 66.54 | 180.01 | MVS
407 | PURBA MEDINIPUR | CHANDPUR AND ADJOINING MOUJAS PWSS | TSM/015438 | SM/13693 | New | Contai Sub-Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1358 | 613.46 | Yes | 613.46 | 25/05/2023 | 06/02/2023 | 2 | 44.82 | 165.51 | MVS
408 | PURBA MEDINIPUR | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | TSM/015575 | SM/13694 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1365 | 625.23 | Yes | 625.23 | 22/11/2022 | 06/03/2024 | 7 | 564.14 | 304.51 | MVS
409 | PURBA MEDINIPUR | MOHANPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/015485 | SM/13695 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1991 | 719.9 | Yes | 719.9 | 11/08/2023 | 02/08/2024 | 12 | 732.71 | 232.88 | MVS
410 | PURBA MEDINIPUR | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS | TSM/015381 | SM/13696 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 792 | 422.36 | Yes | 422.36 | 28/02/2023 | 06/02/2023 | 4 | 51.52 | 45.75 | MVS
411 | PURBA MEDINIPUR | BARTTANA & IT'S ADJOINING MOUJAS PWSS | TSM/015437 | SM/13697 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1639 | 695.93 | Yes | 695.93 | 14/03/2023 | 26/11/2024 | 5 | 87.33 | 324.18 | MVS
412 | PURBA MEDINIPUR | URDDHABMAL AND ADJOINING MOUJAS PWSS | TSM/015165 | SM/13698 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1797 | 803.45 | Yes | 803.45 | 29/12/2022 | 10/04/2023 | 20 | 749.98 | 319.51 | MVS
413 | PURBA MEDINIPUR | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | TSM/015384 | SM/13699 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 3181 | 1097.22 | Yes | 1097.22 | 07/01/2023 | 04/05/2023 | 7 | 979.99 | 682.23 | MVS
414 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | TSM/010584 | SM/13716 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/03/2022 | 3882 | 1060.08 | Yes | 1060.08 | 19/12/2023 | 06/04/2023 | 11 | 953.54 | 597.45 | MVS
415 | PURBA MEDINIPUR | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015572 | SM/13740 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1327 | 669.57 | Yes | 669.57 | 17/02/2023 | 14/03/2024 | 5 | 67.73 | 285.64 | MVS
416 | PURBA MEDINIPUR | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | TSM/015436 | SM/13741 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 580 | 357.16 | Yes | 357.16 | 15/03/2023 | 30/10/2023 | 5 | 330.78 | 164.67 | MVS
417 | PURBA MEDINIPUR | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | TSM/015383 | SM/13742 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1517 | 694.6 | Yes | 694.6 | 11/01/2023 | 08/06/2023 | 6 | 621.93 | 487.75 | MVS
418 | PURBA MEDINIPUR | KHAR & IT'S ADJOINING MOUJAS PWSS | TSM/015435 | SM/13743 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 2849 | 987.25 | Yes | 987.25 | 14/03/2023 | 04/02/2025 | 6 | 108.24 | 57.8 | MVS
419 | PURBA MEDINIPUR | DEULI & IT'S ADJOINING MOUJAS PWSS | TSM/015434 | SM/13744 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 1586 | 725.58 | Yes | 725.58 | 11/01/2023 | 05/09/2024 | 8 | 668.2 | 462.38 | MVS
420 | PURBA MEDINIPUR | MATHURA AND IT'S ADJOINING MOUJAS PWSS | TSM/014944 | SM/13745 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 09/09/2022 | 2170 | 732.18 | Yes | 732.18 | 14/03/2023 | 09/07/2024 | 5 | 83.01 | 195.37 | MVS
421 | PURBA MEDINIPUR | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | TSM/016060 | SM/13850 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 230 | 179.48 | Yes | 179.48 | 02/02/2024 | 05/01/2024 | 5 | 15.63 | 100.92 | MVS
422 | PURBA MEDINIPUR | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | TSM/016024 | SM/13851 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 249 | 167.94 | Yes | 167.94 | 11/08/2023 | 05/06/2023 | 6 | 72.05 | 66.17 | MVS
423 | PURBA MEDINIPUR | AJANGECHHYA PIPED WATER SUPPLY SCHEME. | TSM/015760 | SM/13852 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 314 | 166.59 | Yes | 166.59 | 12/01/2023 | 13/04/2023 | 4 | 167.37 | 41.55 | MVS
424 | PURBA MEDINIPUR | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | TSM/016081 | SM/13853 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1023 | 507.49 | Yes | 507.49 | 17/02/2023 | 12/09/2024 | 3 | 52.97 | 45.05 | MVS
425 | PURBA MEDINIPUR | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | TSM/016073 | SM/13854 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1503 | 749.32 | Yes | 749.32 | 17/02/2023 | 27/05/2024 | 7 | 84.52 | 480.77 | MVS
426 | PURBA MEDINIPUR | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | TSM/016014 | SM/13855 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1908 | 786.94 | Yes | 786.94 | 16/03/2023 | 12/05/2023 | 12 | 685.12 | 479.42 | MVS
427 | PURBA MEDINIPUR | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | TSM/015988 | SM/13856 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 477 | 227.92 | Yes | 227.92 | 11/01/2024 | 14/06/2024 | 11 | 241.7 | 77.29 | MVS
428 | PURBA MEDINIPUR | NONAKOURDA AND IT'S ADJOINING MOUJAS | TSM/015987 | SM/13857 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1018 | 428.88 | Yes | 428.88 | 20/02/2023 | 24/06/2024 | 6 | 380.39 | 82.33 | MVS
429 | PURBA MEDINIPUR | MASHAGON AND ITS ADJOINING MOUJAS PWSS | TSM/015974 | SM/13883 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 401 | 204.23 | Yes | 204.23 | 28/02/2023 | 25/07/2023 | 4 | 190.9 | 3.7 | MVS
430 | PURBA MEDINIPUR | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | TSM/015973 | SM/13884 | New | Haldia Electrical Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1427 | 589.91 | Yes | 589.91 | 27/02/2025 | 30/07/2024 | 7 | 69.98 | 310.11 | MVS
431 | PURBA MEDINIPUR | BARAGECHA AND ADJOINING MOUJAS PWSS | TSM/015972 | SM/13885 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 785 | 461.96 | Yes | 461.96 | 06/01/2023 | 04/05/2023 | 4 | 389.31 | 82.98 | MVS
432 | PURBA MEDINIPUR | POTA PAKURIA AND IT'S ADJOINING MOUJAS | TSM/015859 | SM/13886 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 981 | 555.33 | Yes | 555.33 | 17/02/2023 | 24/06/2024 | 5 | 54.19 | 188.56 | MVS
433 | PURBA MEDINIPUR | BADALPUR AND IT'S ADJOINING MOUJAS | TSM/015813 | SM/13887 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 635 | 381.66 | Yes | 381.66 | 16/03/2023 | 17/05/2023 | 7 | 425.35 | 274.31 | MVS
434 | PURBA MEDINIPUR | GULURI AND IT'S ADJOING MOUJAS | TSM/015793 | SM/13888 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1376 | 533.49 | Yes | 533.49 | 06/01/2023 | 17/04/2023 | 8 | 465.08 | 142.52 | MVS
435 | PURBA MEDINIPUR | Providing FHTC (Functional Household Tap Connection) with Augmentation of Murisai Water Supply Scheme | TSM/016062 | SM/13889 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 26/09/2022 | 0 | 133.52 | Yes | 133.52 | 17/02/2023 | 01/08/2023 | 1 | 130.06 | 0 | MVS
436 | PURBA MEDINIPUR | ITA BARIA & ADJOINING MOUZAS | TSM/013169 | SM/14042 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2068 | 934.72 | Yes | 934.72 | 16/03/2023 | 12/05/2023 | 11 | 699.76 | 485.26 | MVS
437 | PURBA MEDINIPUR | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | TSM/009748 | SM/14113 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 27/01/2022 | 5920 | 1300.67 | Yes | 1300.67 | 11/01/2024 | 17/04/2023 | 17 | 1215.2 | 868.13 | MVS
438 | PURBA MEDINIPUR | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | TSM/017153 | SM/14451 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 1581 | 525.09 | Yes | 525.09 | 14/02/2023 | 12/07/2023 | 5 | 474.78 | 141.27 | MVS
439 | PURBA MEDINIPUR | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | TSM/017200 | SM/14455 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 700 | 412.43 | Yes | 412.43 | 15/03/2023 | 13/06/2025 | 5 | 387.29 | 189.69 | MVS
440 | PURBA MEDINIPUR | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | TSM/017188 | SM/14456 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 672 | 351.84 | Yes | 351.84 | 15/03/2023 | 31/05/2023 | 6 | 353.56 | 220.73 | MVS
441 | PURBA MEDINIPUR | KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS | TSM/017178 | SM/14457 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 570 | 317.67 | Yes | 317.67 | 14/03/2023 | 09/07/2024 | 5 | 42.92 | 69.11 | MVS
442 | PURBA MEDINIPUR | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | TSM/017387 | SM/14486 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 0 | 42.52 | Yes | 42.52 | 14/12/2022 | 20/02/2023 | 1 | 41.28 | 0 | MVS
443 | PURBA MEDINIPUR | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | TSM/016738 | SM/14671 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 1040 | 471.07 | Yes | 471.07 | 14/03/2023 | 16/01/2023 | 4 | 55.96 | 149.21 | MVS
444 | PURBA MEDINIPUR | CHISTIPUR AND ADJOINING MOUJAS | TSM/016729 | SM/14672 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 2004 | 668.48 | Yes | 668.48 | 13/02/2023 | 24/06/2024 | 4 | 45.78 | 17.94 | MVS
445 | PURBA MEDINIPUR | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | TSM/016550 | SM/14673 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 614 | 642.05 | Yes | 642.05 | 17/02/2023 | 27/01/2025 | 5 | 61.2 | 235.28 | MVS
446 | PURBA MEDINIPUR | MURARI KALUA PWSS | TSM/017101 | SM/14693 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 425 | 236.53 | Yes | 236.53 | 24/11/2022 | 20/03/2023 | 1 | 11.98 | 0 | MVS
447 | PURBA MEDINIPUR | JAMUASHANKARPUR PWSS | TSM/017103 | SM/14694 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 312 | 344.23 | Yes | 344.23 | 28/02/2023 | 25/07/2023 | 4 | 254.45 | 17.86 | MVS
448 | PURBA MEDINIPUR | SATKALUA AND IT'S ADJOINING MOUJAS PWSS | TSM/017141 | SM/14695 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 816 | 374.28 | Yes | 374.28 | 12/01/2023 | 04/05/2023 | 4 | 355.79 | 142.51 | MVS
449 | PURBA MEDINIPUR | UTTAR SAUTANCHAK Piped Water Supply Scheme. | TSM/016513 | SM/14741 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 461 | 299.47 | Yes | 299.47 | 27/01/2023 | 04/05/2023 | 5 | 277.38 | 113.75 | MVS
450 | PURBA MEDINIPUR | PURBA NUKHA AND ADJOINING MOUJAS | TSM/017102 | SM/14742 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 2344 | 668.28 | Yes | 668.28 | 14/02/2023 | 06/03/2024 | 7 | 608.56 | 165.24 | MVS
451 | PURBA MEDINIPUR | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/017133 | SM/14745 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 236 | 216.7 | Yes | 216.7 | 17/02/2023 | 06/11/2024 | 7 | 211.12 | 93.48 | MVS
452 | PURBA MEDINIPUR | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | TSM/016745 | SM/14749 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 26/09/2022 | 425 | 342.28 | Yes | 342.28 | 28/02/2023 | 25/07/2023 | 4 | 293.51 | 31.26 | MVS
453 | PURBA MEDINIPUR | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | TSM/018371 | SM/14836 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 210 | 391.4 | Yes | 391.4 | 15/02/2023 | 08/06/2023 | 7 | 284.31 | 90.57 | MVS
454 | PURBA MEDINIPUR | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | TSM/018351 | SM/14837 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 2069 | 704.17 | Yes | 704.17 | 01/03/2024 | 01/10/2024 | 9 | 644.61 | 252.65 | MVS
455 | PURBA MEDINIPUR | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | TSM/018345 | SM/14838 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 2173 | 897.92 | Yes | 897.92 | 11/04/2023 | 01/10/2024 | 6 | 177.43 | 275.62 | MVS
456 | PURBA MEDINIPUR | Piped Water Supply Scheme for Bathuari Zone-I | TSM/017717 | SM/14839 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 23 | 181.49 | Yes | 181.49 | 17/03/2023 | 21/11/2022 | 5 | 140.25 | 87.07 | MVS
457 | PURBA MEDINIPUR | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 | TSM/017929 | SM/14840 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 27 | 154.51 | Yes | 154.51 | 17/03/2023 | 12/05/2023 | 4 | 94.9 | 64.07 | MVS
458 | PURBA MEDINIPUR | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | TSM/018396 | SM/14841 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 69 | 207.52 | Yes | 207.52 | 17/03/2023 | 22/08/2024 | 6 | 202.38 | 63.23 | MVS
459 | PURBA MEDINIPUR | Piped Water Supply Scheme for Sankarpur Zone-II | TSM/017879 | SM/14842 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 197 | 70.89 | Yes | 70.89 | 16/02/2023 | 07/06/2024 | 4 | 69.87 | 18.43 | MVS
460 | PURBA MEDINIPUR | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/019290 | SM/14843 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 63.12 | Yes | 63.12 | 22/12/2022 | 06/04/2023 | 5 | 41.41 | 20.19 | MVS
461 | PURBA MEDINIPUR | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/018668 | SM/14844 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 62.78 | Yes | 62.78 | 22/12/2022 | 06/04/2023 | 8 | 46.22 | 37.59 | MVS
462 | PURBA MEDINIPUR | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/018665 | SM/14845 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 66.74 | Yes | 66.74 | 22/12/2022 | 10/05/2023 | 12 | 50.75 | 38.32 | MVS
463 | PURBA MEDINIPUR | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme | TSM/017807 | SM/15034 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 1807 | 635.84 | Yes | 635.84 | 11/04/2023 | 21/11/2022 | 4 | 524.53 | 23.49 | MVS
464 | PURBA MEDINIPUR | Augmentation of Astichak (Zone-II) PWSS | TSM/017769 | SM/15035 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 2196 | 768.16 | Yes | 768.16 | 16/02/2023 | 19/03/2025 | 7 | 691.99 | 454.91 | MVS
465 | PURBA MEDINIPUR | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/015459 | SM/15036 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 242.53 | Yes | 242.53 | 17/10/2023 | 06/04/2023 | 12 | 180.58 | 115.33 | MVS
466 | PURBA MEDINIPUR | TULIA AND ADJOINING MOUJAS PWSS | TSM/015986 | SM/15037 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 2059 | 572.93 | Yes | 572.93 | 14/02/2023 | 27/02/2023 | 3 | 63.81 | 112.1 | MVS
467 | PURBA MEDINIPUR | 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/018664 | SM/15038 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 85.63 | Yes | 85.63 | 22/12/2022 | 06/04/2023 | 8 | 75.47 | 41.51 | MVS
468 | PURBA MEDINIPUR | Augmentation of Astichak (Zone-I) PWSS | TSM/017768 | SM/15462 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 1291 | 679.21 | Yes | 679.21 | 16/02/2023 | 19/09/2023 | 7 | 515.56 | 35.8 | MVS
469 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | TSM/012055 | SM/15510 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 4683 | 1406.2 | Yes | 1406.2 | 01/03/2024 | 29/04/2024 | 19 | 548.98 | 565.6 | MVS
470 | PURBA MEDINIPUR | AMRITBERYA AND ADJOINING MOUJAS | TSM/014710 | SM/15511 | New | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 3440 | 1024.73 | Yes | 1024.73 | 23/08/2023 | 05/11/2024 | 38 | 716.32 | 401.49 | MVS
471 | PURBA MEDINIPUR | CHAK BHABANI & ADJOINING MOUJAS PWSS | TSM/013330 | SM/15512 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2843 | 1095.47 | Yes | 1095.47 | 14/02/2023 | 19/07/2023 | 7 | 1020.31 | 655.41 | MVS
472 | PURBA MEDINIPUR | DUBDA IT'S ADJOINING MOUJAS PWSS | TSM/014644 | SM/15513 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 4067 | 1290.54 | Yes | 1290.54 | 11/04/2023 | 31/07/2023 | 3 | 980.21 | 303.45 | MVS
473 | PURBA MEDINIPUR | AILAN AND IT'S ADJOINING MOUJAS PWSS | TSM/014592 | SM/15514 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 3046 | 1127.65 | Yes | 1127.65 | 14/03/2023 | 09/07/2024 | 3 | 53.13 | 284.91 | MVS
474 | PURBA MEDINIPUR | DEKHALI AND ADJOINING MOUJAS PWSS | TSM/014485 | SM/15515 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 22/08/2022 | 2820 | 1239.4 | Yes | 1239.4 | 13/01/2023 | 29/07/2024 | 4 | 68.81 | 878.48 | MVS
475 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Amtalia Accommodate FHTC under Contai-II (Deshapran) Block within Purba Medinipur District. | TSM/009926 | SM/15635 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 0 | 58.07 | Yes | 58.07 |  | 20/04/2023 | 2 | 56.66 | 55.82 | MVS
476 | PURBA MEDINIPUR | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | TSM/018410 | SM/15841 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 99 | 432.64 | Yes | 432.64 | 17/03/2023 | 30/09/2024 | 7 | 131.05 | 13.16 | MVS
477 | PURBA MEDINIPUR | JHAUGERYA PIPED WATER SUPPLY SCHEME. | TSM/019331 | SM/15842 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 158 | 179.26 | Yes | 179.26 | 17/03/2023 | 16/12/2024 | 4 | 30.71 | 99.79 | MVS
478 | PURBA MEDINIPUR | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | TSM/018403 | SM/15843 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 238 | 487.15 | Yes | 487.15 | 17/03/2023 | 18/08/2022 | 5 | 47.79 | 102.24 | MVS
479 | PURBA MEDINIPUR | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | TSM/018383 | SM/15844 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 173 | 444.01 | Yes | 444.01 | 17/03/2023 | 28/11/2022 | 5 | 305.44 | 2.89 | MVS
480 | PURBA MEDINIPUR | Piped Water Supply Scheme for Bathuari Zone-IV | TSM/017749 | SM/15845 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 48 | 428.01 | Yes | 428.01 | 17/03/2023 | 19/09/2024 | 8 | 334.32 | 38.03 | MVS
481 | PURBA MEDINIPUR | Piped Water Supply Scheme for Sankarpur Zone-III | TSM/017882 | SM/15846 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 267 | 338.75 | Yes | 338.75 | 17/03/2023 | 07/06/2024 | 10 | 295.73 | 35.28 | MVS
482 | PURBA MEDINIPUR | Piped Water Supply Scheme for Sankarpur Zone-V | TSM/017899 | SM/15847 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 321 | 342.52 | Yes | 342.52 | 17/03/2023 | 05/09/2024 | 9 | 300.38 | 92.95 | MVS
483 | PURBA MEDINIPUR | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | TSM/019327 | SM/15848 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 227 | 241.71 | Yes | 241.71 | 17/03/2023 | 22/10/2024 | 8 | 43.42 | 70.29 | MVS
484 | PURBA MEDINIPUR | DAHA DAYA PIPED WATER SUPPLY SCHEME. | TSM/019329 | SM/15849 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 270 | 158.24 | Yes | 158.24 | 17/03/2023 | 05/01/2024 | 3 | 24.02 | 17.89 | MVS
485 | PURBA MEDINIPUR | GARABAR PIPED WATER SUPPLY SCHEME. | TSM/019287 | SM/15850 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 150 | 166.18 | Yes | 166.18 | 12/09/2024 | 10/05/2024 | 10 | 157.69 | 103.59 | MVS
486 | PURBA MEDINIPUR | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | TSM/020432 | SM/15851 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 250 | 74.9 | Yes | 74.9 | 17/03/2023 | 12/07/2023 | 5 | 94.82 | 87.19 | MVS
487 | PURBA MEDINIPUR | BADALPUR PIPED WATER SUPPLY SCHEME. | TSM/020433 | SM/15852 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 162 | 74.39 | Yes | 74.39 | 17/03/2023 | 10/01/2024 | 5 | 21.26 | 12.2 | MVS
488 | PURBA MEDINIPUR | Piped Water Supply Scheme for Bathuari Zone-II | TSM/017729 | SM/15853 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 12 | 439.72 | Yes | 439.72 | 17/03/2023 | 19/09/2024 | 7 | 352.97 | 138.48 | MVS
489 | PURBA MEDINIPUR | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | TSM/017824 | SM/16194 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 1427 | 730.61 | Yes | 730.61 | 17/03/2023 | 07/06/2024 | 9 | 492.29 | 210.27 | MVS
490 | PURBA MEDINIPUR | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | TSM/019328 | SM/16200 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 147 | 197.46 | Yes | 197.46 | 16/03/2023 | 19/04/2023 | 4 | 188.8 | 157.71 | MVS
491 | PURBA MEDINIPUR | PANCHBERYA PIPED WATER SUPPLY SCHEME | TSM/019332 | SM/16201 | New | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 131 | 171.95 | Yes | 171.95 | 17/03/2023 | 01/08/2023 | 4 | 161.79 | 4.29 | MVS
492 | PURBA MEDINIPUR | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | TSM/019333 | SM/16203 | New | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 337 | 166.63 | Yes | 166.63 | 16/03/2023 | 29/07/2024 | 6 | 150.32 | 99.98 | MVS
493 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Tajpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/016269 | SM/16204 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 76.08 | Yes | 76.08 | 17/03/2023 | 06/04/2023 | 5 | 51.18 | 47.92 | MVS
494 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/016267 | SM/16205 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 75.38 | Yes | 75.38 | 17/03/2023 | 06/04/2023 | 7 | 40.01 | 48.81 | MVS
495 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Jalpai Part-II Water Supply Scheme of Nandigram-II Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/016264 | SM/16206 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 74.78 | Yes | 74.78 | 17/03/2023 | 06/04/2023 | 5 | 50.44 | 47.33 | MVS
496 | PURBA MEDINIPUR | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | TSM/017160 | SM/16257 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 958 | 520.9 | Yes | 520.9 | 27/01/2023 | 08/06/2023 | 4 | 438.48 | 93.78 | MVS
497 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Kotbar Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020317 | SM/16279 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 80.74 | Yes | 80.74 | 17/03/2023 | 06/04/2023 | 4 | 39.82 | 29.86 | MVS
498 | PURBA MEDINIPUR | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | TSM/017995 | SM/16284 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 162 | 403.81 | Yes | 403.81 | 17/03/2023 | 18/08/2022 | 5 | 56.15 | 135.26 | MVS
499 | PURBA MEDINIPUR | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | TSM/018411 | SM/16286 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 209 | 461.03 | Yes | 461.03 | 01/03/2024 | 30/09/2024 | 10 | 455.74 | 246.89 | MVS
500 | PURBA MEDINIPUR | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | TSM/018348 | SM/16288 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 782 | 522.2 | Yes | 522.2 | 01/03/2024 | 23/10/2024 | 7 | 453.52 | 171.87 | MVS
501 | PURBA MEDINIPUR | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | TSM/018417 | SM/16295 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 184 | 458.23 | Yes | 458.23 | 17/03/2023 | 14/03/2024 | 10 | 425.22 | 192.99 | MVS
502 | PURBA MEDINIPUR | Piped Water Supply Scheme for Bathuari Zone-III | TSM/017733 | SM/16300 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 55 | 396.8 | Yes | 396.8 | 17/03/2023 | 10/09/2024 | 8 | 319.74 | 82.31 | MVS
503 | PURBA MEDINIPUR | Piped Water Supply Scheme for Sankarpur Zone-IV | TSM/017890 | SM/16305 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 294 | 340.44 | Yes | 340.44 | 17/03/2023 | 25/05/2023 | 9 | 304.1 | 106.25 | MVS
504 | PURBA MEDINIPUR | 2 (Two) Nos. Boosting Tube Well for Habichak Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020319 | SM/16390 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 161.69 | Yes | 161.69 | 17/03/2023 | 06/04/2023 | 8 | 108.87 | 95.61 | MVS
505 | PURBA MEDINIPUR | Balance Work for Retrofitting to Accommodate FHTC (610 Nos.) and laying of left-out portion UPVC pipe line due to uncovered area of this Zone at different Nodal Point under JJM in Dona Zone-I Water Supply Scheme for Block-Moyna in the District of Purba Me | TSM/013424 | SM/16452 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 610 | 110.15 | Yes | 110.15 | 13/02/2023 | 19/04/2023 | 2 | 109.08 | 79.22 | MVS
506 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Arjunnagar PWSS under Bhagwanpur-II Block (Phase-II) | TSM/017483 | SM/16453 | Retrofitting | Contai Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1321 | 115.08 | Yes | 115.08 | 15/02/2023 | 08/06/2023 | 3 | 126.14 | 25.27 | MVS
507 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | TSM/018905 | SM/16458 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 675 | 170.2 | Yes | 170.2 | 13/02/2023 | 31/05/2023 | 4 | 128.18 | 10.8 | MVS
508 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) | TSM/018245 | SM/16460 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 172 | 139.71 | Yes | 139.71 | 22/12/2022 | 19/04/2023 | 4 | 79.16 | 41.98 | MVS
509 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | TSM/018238 | SM/16461 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 176 | 131.18 | Yes | 131.18 | 22/12/2022 | 17/05/2023 | 2 | 74.3 | 31.42 | MVS
510 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) | TSM/018236 | SM/16462 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 428 | 128.06 | Yes | 128.06 | 22/12/2022 | 19/04/2023 | 3 | 83.05 | 15.67 | MVS
511 | PURBA MEDINIPUR | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. | TSM/018162 | SM/16463 | Augmentation | Haldia Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 920 | 130.27 | Yes | 130.27 | 13/02/2023 | 22/01/2024 | 3 | 84.25 | 6.52 | MVS
512 | PURBA MEDINIPUR | Augmentation of Contai Saline Area Zone-IV Part-II Piped Water Supply Scheme | TSM/017823 | SM/16464 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 1636 | 665.82 | Yes | 665.82 | 11/04/2023 | 21/11/2022 | 4 | 509.47 | 3.49 | MVS
513 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) | TSM/015866 | SM/16465 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 122.31 | Yes | 122.31 | 16/02/2023 | 17/05/2023 | 3 | 53.24 | 25.01 | MVS
514 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Dulalpur PWSS under Egra-II Block (Phase-II) | TSM/018683 | SM/16466 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 305 | 39.56 | Yes | 39.56 |  | 19/04/2023 | 2 | 30.8 | 25.66 | MVS
515 | PURBA MEDINIPUR | Retrofitting to Accommodate FHTC under JJM in Paya (Mahaprabhu) PWSS under Ramnagar-I Block (Phase-II) | TSM/018682 | SM/16467 | Retrofitting | Digha Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 319 | 72.07 | Yes | 72.07 | 13/02/2023 | 19/04/2023 | 1 | 57.26 | 57.26 | MVS
516 | PURBA MEDINIPUR | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (545 NOS) UNDER JJM SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE VII,BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA MEDINIPUR. (PHASE-III) | TSM/018312 | SM/16468 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 545 | 34.18 | Yes | 34.18 | 13/02/2023 | 19/04/2023 | 1 | 30.37 | 30.37 | MVS
517 | PURBA MEDINIPUR | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (1180 NOS) AND LAYNE OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XI, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA M | TSM/018277 | SM/16469 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 1180 | 108.21 | Yes | 108.21 | 13/02/2023 | 19/04/2023 | 2 | 91.53 | 79.29 | MVS
518 | PURBA MEDINIPUR | BALANCE WORK FOR RETROFITTING TO ACCOMMODATE FHTC (851 NOS.) AND LAYING OF UPVC PIPELINE DUE TO UNCOVERED AREA OF THIS ZONE AT DIFFERENT NODAL POINT UNDER JJM IN SURFACE WATER BASED WATER SUPPLY SCHEME FOR ZONE-XII, BLOCK-KOLAGHAT IN THE DISTRICT OF PURBA | TSM/018280 | SM/16470 | Retrofitting | Tamluk Sadar Sub-Division | Assistant Engineer | Junior Engineer | 16/11/2022 | 851 | 59.08 | Yes | 59.08 | 13/02/2023 | 19/04/2023 | 2 | 56.74 | 51.09 | MVS
519 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme. | TSM/019346 | SM/16650 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 08/07/2024 | 2 | 12.54 | 0.3 | MVS
520 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme. | TSM/019356 | SM/16652 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 10/06/2024 | 2 | 11.53 | 0.18 | MVS
521 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme. | TSM/019340 | SM/16653 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 9.35 | 5.47 | MVS
522 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme. | TSM/019347 | SM/16654 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 08/07/2024 | 2 | 12.54 | 9.38 | MVS
523 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme. | TSM/019351 | SM/16655 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 10/10/2023 | 2 | 0.16 | 0.01 | MVS
524 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme. | TSM/019355 | SM/16657 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.24 | 0 | MVS
525 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme. | TSM/019349 | SM/16659 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.65 | 10.53 | MVS
526 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. | TSM/019352 | SM/16660 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 12.39 | Yes | 12.39 | 01/03/2023 | 30/07/2024 | 2 | 12.07 | 0 | MVS
527 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme. | TSM/019339 | SM/16661 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.22 | 9.89 | MVS
528 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme. | TSM/019353 | SM/16662 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 08/04/2024 | 2 | 4.4 | 4.4 | MVS
529 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme. | TSM/019341 | SM/16663 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 01/08/2024 | 2 | 12.42 | 0.18 | MVS
530 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme. | TSM/019338 | SM/16664 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.24 | 7.15 | MVS
531 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme. | TSM/019348 | SM/16665 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.66 | 6.77 | MVS
532 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme. | TSM/019342 | SM/16666 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 01/08/2024 | 2 | 12.42 | 7.32 | MVS
533 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme. | TSM/019344 | SM/16667 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.67 | 0 | MVS
534 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme. | TSM/019343 | SM/16668 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 23/03/2023 | 1 | 12.67 | 0 | MVS
535 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme. | TSM/019354 | SM/16669 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 30/03/2023 | 10/06/2024 | 2 | 11.08 | 0.26 | MVS
536 | PURBA MEDINIPUR | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme. | TSM/019345 | SM/16671 | Augmentation | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/11/2022 | 0 | 12.39 | Yes | 12.39 | 15/02/2023 | 01/08/2024 | 2 | 13.19 | 6.88 | MVS
537 | PURBA MEDINIPUR | Augmentation of Ground Water Based Bagmari Water Supply Scheme | TSM/009993 | SM/16711 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 929 | 339.13 | Yes | 339.13 | 28/11/2022 | 15/12/2023 | 9 | 315.06 | 176.47 | MVS
538 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | TSM/009925 | SM/16712 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 0 | 143.36 | Yes | 143.36 | 28/03/2023 | 10/04/2023 | 5 | 97.78 | 69.52 | MVS
539 | PURBA MEDINIPUR | Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. | TSM/009924 | SM/16713 | Augmentation | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 16/03/2022 | 0 | 140.37 | Yes | 140.37 | 28/03/2023 | 07/08/2023 | 4 | 90.18 | 0 | MVS
540 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Saripur Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020322 | SM/16938 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 80.74 | Yes | 80.74 | 17/03/2023 | 06/04/2023 | 6 | 53.78 | 42.49 | MVS
541 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Source Augmentation of Dariapur Water Supply Scheme of Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/020298 | SM/16939 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 62.87 | Yes | 62.87 | 17/03/2023 | 20/04/2023 | 3 | 34.32 | 0.83 | MVS
542 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Below 100 Household) at different JL No. 5,124,534,150,153,140,97,79,87,151,11 for different Blocks under Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/018767 | SM/16941 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 896 | 448.63 | Yes | 448.63 | 20/04/2023 | 05/10/2024 | 2 | 19.78 | 19.78 | MVS
543 | PURBA MEDINIPUR | Augmentation of Dhanghara PWSS to Accommodate FHTC under JJM with Allied works under Contai-III Block (Phase-II) | TSM/020297 | SM/16946 | Augmentation | Contai Sub-Division | Assistant Engineer | Junior Engineer | 28/12/2022 | 0 | 85.63 | Yes | 85.63 | 13/02/2023 | 19/05/2023 | 2 | 76.16 | 56.28 | MVS
544 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/020289 | SM/16948 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 322 | 71.27 | Yes | 71.27 | 28/03/2023 | 25/04/2023 | 1 | 12.14 | 0 | MVS
545 | PURBA MEDINIPUR | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different locations under Khejuri-II , Contai-II, Egra-II, Egra-I & Contai-III Block within Purba Medinipur District under Tamluk Division, PHE Dte | TSM/020403 | SM/17173 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 840 | 448.63 | Yes | 448.63 | 17/02/2023 | 21/11/2023 | 1 | 2.26 | 312.63 | MVS
546 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Dakshin Mechogram Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020309 | SM/17193 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 80.74 | Yes | 80.74 | 17/03/2023 | 06/04/2023 | 6 | 38.32 | 32.81 | MVS
547 | PURBA MEDINIPUR | 2 (Two) Nos. Boosting Tube Well for Kulbari Water Supply Scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020324 | SM/17194 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 161.69 | Yes | 161.69 | 29/11/2023 | 06/04/2023 | 6 | 93.34 | 59.38 | MVS
548 | PURBA MEDINIPUR | 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | TSM/020313 | SM/17221 | Augmentation | Tamluk Sadar Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 0 | 80.74 | Yes | 80.74 | 17/03/2023 | 06/04/2023 | 3 | 22.23 | 50.8 | MVS
549 | PURBA MEDINIPUR | NUNHUNDA AND IT'S ADJOINING MOUJAS PWSS | TSM/017173 | SM/18303 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 30/09/2022 | 4497 | 1458.55 | Yes | 1458.55 | 16/03/2023 | 12/07/2023 | 11 | 1100.28 | 498.57 | MVS
550 | PURBA MEDINIPUR | GURGRAM & ADJOINING MOUZAS | TSM/013294 | SM/18311 | New | Contai Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | 05/07/2022 | 2897 | 1027.99 | Yes | 1027.99 | 07/01/2023 | 26/07/2023 | 6 | 1023.68 | 656.92 | MVS
551 | PURBA MEDINIPUR | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | TSM/009200 | SM/18402 | New | Haldia Electrical Sub-Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | 30/03/2022 | 39657 | 49821.56 | Yes | 49821.56 | 21/01/2025 | 31/05/2023 | 18 | 5171.92 | 783.26 | MVS
552 | PURBA MEDINIPUR | 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | TSM/019291 | SM/18765 | Augmentation |  |  |  | 16/11/2022 | 0 | 63.12 | Yes | 63.12 | 22/12/2022 | 06/04/2023 | 2 | 25.27 | 1.5 | MVS
553 | PURBA MEDINIPUR | Piped Water Supply Scheme for Sankarpur Zone-I | TSM/017874 | SM/18766 | Augmentation | Digha Sub-Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | 28/12/2022 | 486 | 370.29 | Yes | 370.29 | 17/03/2023 | 10/06/2024 | 9 | 327.01 | 105.07 | MVS
554 | PURBA MEDINIPUR | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | TSM/015039 | SM/19188 | New | Kharagpur Sub-Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | 22/08/2022 | 85853 | 74155.64 | Yes | 74155.64 | 26/12/2024 | 15/03/2024 | 7 | 56044.45 | 1092.6 | MVS
Total | [9 empty] | 1154274 | 398541 |  | 398541 |  |  | 4114 | 240328.27 | 147324.83