## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | TSM/005852 | SM/07057 | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | 25/09/2020 | 2066 | 99.09 | Yes | 99.09 |  | 01/04/2022 | 14 | 139.46 | 40.71 | MVS
2 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | TSM/005854 | SM/07058 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 1036 | 82.69 | Yes | 82.69 |  | 31/08/2020 | 6 | 82.04 | 0 | MVS
3 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) | TSM/005857 | SM/07059 | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | 25/09/2020 | 967 | 97.58 | Yes | 97.58 |  | 03/09/2020 | 11 | 118.74 | 48.22 | MVS
4 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | TSM/005859 | SM/07060 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 1400 | 86.77 | Yes | 86.77 |  | 03/09/2021 | 9 | 65.01 | 85.11 | MVS
5 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) | TSM/005860 | SM/07061 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 1581 | 93.85 | Yes | 93.85 |  | 03/09/2021 | 7 | 48.48 | 25.61 | MVS
6 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | TSM/005861 | SM/07062 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 2826 | 87.86 | Yes | 87.86 |  | 06/09/2021 | 10 | 121.02 | 7.05 | MVS
7 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | TSM/005863 | SM/07063 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 1709 | 91.9 | Yes | 91.9 |  | 13/09/2021 | 8 | 108.03 | 13.62 | MVS
8 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | TSM/005866 | SM/07064 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 1612 | 99.04 | Yes | 99.04 |  | 16/09/2020 | 8 | 68.67 | 83.22 | MVS
9 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | TSM/005869 | SM/07065 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 596 | 73.85 | Yes | 73.85 | 20/05/2022 | 13/05/2022 | 7 | 60.19 | 0 | MVS
10 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | TSM/005885 | SM/07066 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 2682 | 80.75 | Yes | 80.75 |  | 13/05/2022 | 10 | 121.03 | 0 | MVS
11 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) | TSM/005886 | SM/07067 | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | 25/09/2020 | 345 | 98.86 | Yes | 98.86 |  | 03/09/2020 | 10 | 143.29 | 0 | MVS
12 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | TSM/005888 | SM/07068 | Retrofitting | Alipurduar Sadar Sub-Division | Birpara A.E | Alipurduar Sub Division | 25/09/2020 | 1509 | 85.62 | Yes | 85.62 | 16/02/2024 | 21/01/2023 | 8 | 88.75 | 0 | MVS
13 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) | TSM/005889 | SM/07069 | Retrofitting | Alipurduar Sadar Sub-Division | Birpara A.E | Alipurduar Sub Division | 25/09/2020 | 1509 | 61.34 | Yes | 61.34 |  | 03/09/2020 | 5 | 58.3 | 0 | MVS
14 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | TSM/005856 | SM/07121 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 2686 | 82.27 | Yes | 82.27 |  | 13/05/2022 | 7 | 83.23 | 0 | MVS
15 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) | TSM/005882 | SM/07122 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1623 | 98.68 | Yes | 98.68 |  | 05/10/2021 | 5 | 118.71 | 0 | MVS
16 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | TSM/005881 | SM/07123 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1051 | 98.96 | Yes | 98.96 |  | 13/09/2021 | 10 | 117.77 | 13.46 | MVS
17 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) | TSM/005876 | SM/07124 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1477 | 55.28 | Yes | 55.28 |  | 15/12/2020 | 3 | 51.41 | 0 | MVS
18 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | TSM/005880 | SM/07125 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1051 | 90.17 | Yes | 90.17 |  | 05/10/2021 | 5 | 102.55 | 0 | MVS
19 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | TSM/005879 | SM/07126 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1051 | 93 | Yes | 93 |  | 05/10/2021 | 6 | 153.73 | 78.91 | MVS
20 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) | TSM/005878 | SM/07127 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1051 | 66.37 | Yes | 66.37 |  | 13/09/2021 | 8 | 95.8 | 4.98 | MVS
21 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | TSM/005837 | SM/07128 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 895 | 62.07 | Yes | 62.07 |  | 03/09/2021 | 8 | 71.62 | 0 | MVS
22 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | TSM/005844 | SM/07129 | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | 25/09/2020 | 1328 | 72.16 | Yes | 72.16 |  | 15/12/2020 | 6 | 55.12 | 43.86 | MVS
23 | ALIPURDUAR | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | TSM/005848 | SM/07130 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 1568 | 94.15 | Yes | 94.15 | 16/02/2024 | 16/09/2020 | 9 | 110.84 | 9.61 | MVS
24 | ALIPURDUAR | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | TSM/005849 | SM/07131 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 567 | 73.16 | Yes | 73.16 |  | 03/09/2020 | 7 | 73.19 | 40.35 | MVS
25 | ALIPURDUAR | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | TSM/005851 | SM/07132 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 1847 | 88.7 | Yes | 88.7 | 16/02/2024 | 22/09/2022 | 6 | 25.76 | 0 | MVS
26 | ALIPURDUAR | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | TSM/005850 | SM/07133 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 1169 | 95.65 | Yes | 95.65 |  | 20/08/2020 | 9 | 60.38 | 52.94 | MVS
27 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) | TSM/005875 | SM/07134 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1477 | 89.44 | Yes | 89.44 |  | 10/08/2022 | 4 | 71.75 | 11.24 | MVS
28 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) | TSM/005873 | SM/07135 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 822 | 87.03 | Yes | 87.03 |  | 14/10/2020 | 6 | 116.65 | 22.41 | MVS
29 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | TSM/005874 | SM/07136 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 822 | 80.05 | Yes | 80.05 |  | 15/12/2020 | 5 | 77.51 | 0 | MVS
30 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | TSM/005883 | SM/07137 | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | 25/09/2020 | 1073 | 97.16 | Yes | 97.16 |  | 02/05/2022 | 10 | 132.87 | 66.79 | MVS
31 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | TSM/005884 | SM/07138 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 2682 | 96.46 | Yes | 96.46 | 14/06/2024 | 13/05/2022 | 8 | 83.55 | 58.17 | MVS
32 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | TSM/005853 | SM/07174 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 1388 | 76.33 | Yes | 76.33 |  | 22/09/2020 | 6 | 86.03 | 32.38 | MVS
33 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | TSM/005855 | SM/07175 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 2686 | 91.69 | Yes | 91.69 |  | 22/09/2020 | 10 | 133.39 | 15.04 | MVS
34 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | TSM/005858 | SM/07176 | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | 25/09/2020 | 1621 | 70.54 | Yes | 70.54 |  | 03/09/2020 | 14 | 91.85 | 0 | MVS
35 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | TSM/005862 | SM/07177 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 761 | 68.96 | Yes | 68.96 |  | 14/07/2021 | 8 | 53.29 | 63.22 | MVS
36 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) | TSM/005864 | SM/07178 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 1419 | 98.08 | Yes | 98.08 |  | 14/10/2020 | 10 | 132.05 | 39.99 | MVS
37 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | TSM/005865 | SM/07179 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 1419 | 69.14 | Yes | 69.14 |  | 05/10/2021 | 7 | 64.09 | 0 | MVS
38 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | TSM/005867 | SM/07180 | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Madarihat - Birpara Block | 25/09/2020 | 624 | 64.83 | Yes | 64.83 | 11/02/2025 | 21/05/2025 | 6 | 32.8 | 5.82 | MVS
39 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | TSM/005868 | SM/07181 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 571 | 89.66 | Yes | 89.66 |  | 13/05/2022 | 6 | 112.91 | 1.86 | MVS
40 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | TSM/005870 | SM/07182 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 870 | 98.81 | Yes | 98.81 |  | 14/10/2020 | 5 | 52.7 | 61.57 | MVS
41 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) | TSM/005871 | SM/07183 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 870 | 56.02 | Yes | 56.02 |  | 16/09/2020 | 3 | 46.92 | 0 | MVS
42 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | TSM/005872 | SM/07184 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 901 | 82.41 | Yes | 82.41 | 03/08/2023 | 16/10/2020 | 6 | 129.82 | 25.22 | MVS
43 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | TSM/005877 | SM/07185 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1623 | 82.87 | Yes | 82.87 | 11/12/2023 | 13/09/2021 | 10 | 96.58 | 63.32 | MVS
44 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | TSM/005887 | SM/07186 | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | 25/09/2020 | 345 | 99.29 | Yes | 99.29 | 21/09/2023 | 03/09/2020 | 14 | 114.78 | 0 | MVS
45 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | TSM/005833 | SM/07187 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 828 | 73.94 | Yes | 73.94 |  | 22/09/2020 | 9 | 78.74 | 63.91 | MVS
46 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | TSM/005834 | SM/07188 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 828 | 73.94 | Yes | 73.94 |  | 10/12/2021 | 4 | 50.08 | 0 | MVS
47 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) | TSM/005836 | SM/07189 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 895 | 97.67 | Yes | 97.67 |  | 03/09/2021 | 11 | 80.56 | 56.79 | MVS
48 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | TSM/005835 | SM/07190 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 25/09/2020 | 1026 | 83.82 | Yes | 83.82 |  | 03/09/2020 | 8 | 86.5 | 51.63 | MVS
49 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme | TSM/005838 | SM/07191 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 25/09/2020 | 788 | 62.8 | Yes | 62.8 | 01/03/2024 | 13/05/2022 | 3 | 54.13 | 25.61 | MVS
50 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | TSM/005839 | SM/07192 | Retrofitting | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | 25/09/2020 | 1000 | 83.76 | Yes | 83.76 | 13/07/2022 | 20/08/2020 | 7 | 93.96 | 83.76 | MVS
51 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | TSM/005841 | SM/07193 | Retrofitting | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | 25/09/2020 | 608 | 60.86 | Yes | 60.86 |  | 22/09/2020 | 6 | 41.4 | 27.05 | MVS
52 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | TSM/005840 | SM/07194 | Retrofitting | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | 25/09/2020 | 1298 | 98.15 | Yes | 98.15 |  | 22/09/2020 | 7 | 68.98 | 94.77 | MVS
53 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | TSM/005843 | SM/07195 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 1222 | 98.84 | Yes | 98.84 |  | 01/10/2020 | 4 | 83.27 | 56.21 | MVS
54 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | TSM/005842 | SM/07196 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 25/09/2020 | 803 | 67.24 | Yes | 67.24 | 03/11/2022 | 15/07/2021 | 4 | 41.82 | 41.2 | MVS
55 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | TSM/005847 | SM/07197 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 1121 | 84.07 | Yes | 84.07 |  | 16/09/2020 | 7 | 80.87 | 7.36 | MVS
56 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | TSM/005846 | SM/07198 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 882 | 69.04 | Yes | 69.04 |  | 03/09/2021 | 8 | 54.27 | 8.21 | MVS
57 | ALIPURDUAR | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | TSM/005845 | SM/07199 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 25/09/2020 | 688 | 61.63 | Yes | 61.63 |  | 03/09/2020 | 8 | 65.27 | 11.67 | MVS
58 | ALIPURDUAR | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | TSM/006690 | SM/08080 | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | 04/12/2020 | 29206 | 1224.31 | Yes | 1224.31 | 27/09/2022 | 17/06/2021 | 74 | 1376.58 | 262.22 | MVS
59 | ALIPURDUAR | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | TSM/006524 | SM/08580 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 08/01/2021 | 882 | 295.97 | Yes | 295.97 | 01/03/2024 | 02/12/2024 | 14 | 276.76 | 0 | MVS
60 | ALIPURDUAR | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | TSM/008218 | SM/08880 | Retrofitting | Alipurduar Sadar Sub-Division | Birpara A.E | Alipurduar Sub Division | 19/08/2021 | 2328 | 140.24 | Yes | 140.24 |  | 27/09/2021 | 9 | 195.48 | 0 | MVS
61 | ALIPURDUAR | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | TSM/008216 | SM/08881 | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 19/08/2021 | 874 | 184.32 | Yes | 184.32 |  | 03/09/2021 | 7 | 200.37 | 0 | MVS
62 | ALIPURDUAR | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | TSM/008184 | SM/08882 | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 19/08/2021 | 1096 | 129.45 | Yes | 129.45 |  | 05/10/2021 | 7 | 148.65 | 0 | MVS
63 | ALIPURDUAR | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | TSM/008185 | SM/08883 | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 19/08/2021 | 1393 | 87.85 | Yes | 87.85 |  | 03/09/2020 | 7 | 122.5 | 0 | MVS
64 | ALIPURDUAR | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | TSM/008186 | SM/08884 | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | 19/08/2021 | 2599 | 398.83 | Yes | 398.83 |  | 01/04/2022 | 17 | 455.04 | 0 | MVS
65 | ALIPURDUAR | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | TSM/009070 | SM/09883 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 6045 | 451.23 | Yes | 451.23 | 26/03/2025 | 14/11/2024 | 28 | 384.89 | 0 | MVS
66 | ALIPURDUAR | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | TSM/009073 | SM/09884 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 2333 | 484.93 | Yes | 484.93 | 03/08/2023 | 29/02/2024 | 24 | 510.31 | 0 | MVS
67 | ALIPURDUAR | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | TSM/009072 | SM/09885 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 22/11/2021 | 3226 | 449.91 | Yes | 449.91 | 17/12/2024 | 02/05/2022 | 19 | 475.74 | 0 | MVS
68 | ALIPURDUAR | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | TSM/009071 | SM/09886 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 22/11/2021 | 2202 | 257.81 | Yes | 257.81 | 03/03/2022 | 11/01/2022 | 8 | 334.8 | 0 | MVS
69 | ALIPURDUAR | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | TSM/009039 | SM/09887 | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 22/11/2021 | 0 | 92.5 | Yes | 92.5 | 11/07/2023 | 01/04/2022 | 20 | 120.16 | 0 | MVS
70 | ALIPURDUAR | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | TSM/009035 | SM/09888 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 43.87 | Yes | 43.87 | 26/03/2025 | 13/05/2022 | 4 | 29.09 | 0 | MVS
71 | ALIPURDUAR | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' | TSM/009017 | SM/09890 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 22/11/2021 | 0 | 45.21 | Yes | 45.21 | 05/12/2022 | 11/01/2022 | 3 | 31.19 | 0 | MVS
72 | ALIPURDUAR | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | TSM/008995 | SM/09891 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 47.49 | Yes | 47.49 |  | 11/01/2022 | 6 | 58.88 | 0 | MVS
73 | ALIPURDUAR | REJUVINATION OF 'CHANDIRJHAR WATER SUPPLY SCHEME' | TSM/009038 | SM/09892 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 22/11/2021 | 0 | 47.49 | Yes | 47.49 | 25/08/2022 | 05/10/2021 | 9 | 54.25 | 0 | MVS
74 | ALIPURDUAR | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | TSM/008982 | SM/09893 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 22/11/2021 | 0 | 45.22 | Yes | 45.22 | 21/02/2023 | 10/08/2022 | 4 | 34.22 | 0 | MVS
75 | ALIPURDUAR | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | TSM/009036 | SM/09894 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 44.01 | Yes | 44.01 | 11/11/2022 | 14/01/2022 | 5 | 37.81 | 0 | MVS
76 | ALIPURDUAR | Rejuvenation of Makrapara TG WSS. | TSM/008906 | SM/09895 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 45.22 | Yes | 45.22 | 16/12/2022 | 31/01/2022 | 6 | 71.74 | 0 | MVS
77 | ALIPURDUAR | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | TSM/008979 | SM/09896 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 45.23 | Yes | 45.23 | 11/02/2025 | 26/06/2025 | 8 | 32.62 | 0 | MVS
78 | ALIPURDUAR | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | TSM/009034 | SM/09897 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 45.48 | Yes | 45.48 | 28/02/2023 | 03/09/2021 | 6 | 38.9 | 0 | MVS
79 | ALIPURDUAR | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME' | TSM/009030 | SM/09898 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 608 | 47.48 | Yes | 47.48 | 22/12/2022 | 13/09/2021 | 12 | 43.36 | 0 | MVS
80 | ALIPURDUAR | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | TSM/009037 | SM/09899 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Cooch-Behar Mechanical Sub-Division, PHE Dte. | Alipurduar Sub Division,Junior Engineer 1, Northern Mechanical Division-II,PHE Dte. | 22/11/2021 | 0 | 45.28 | Yes | 45.28 | 19/09/2022 | 31/01/2022 | 6 | 42.51 | 0 | MVS
81 | ALIPURDUAR | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' | TSM/009028 | SM/09900 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 45.23 | Yes | 45.23 | 03/04/2025 | 20/05/2022 | 1 | 2.87 | 0 | MVS
82 | ALIPURDUAR | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | TSM/009031 | SM/09901 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 44.25 | Yes | 44.25 | 19/10/2022 | 18/02/2022 | 6 | 42.11 | 0 | MVS
83 | ALIPURDUAR | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | TSM/009040 | SM/09902 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 47.49 | Yes | 47.49 | 11/11/2022 | 19/05/2023 | 5 | 55.37 | 0 | MVS
84 | ALIPURDUAR | REJUVENATION OF 'CHOTO SALKUMAR WATER SUPPLY SCHEME' | TSM/009007 | SM/09903 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 22/11/2021 | 0 | 45.22 | Yes | 45.22 | 21/02/2024 | 05/10/2021 | 9 | 39.47 | 0 | MVS
85 | ALIPURDUAR | Rejuvenation Of Dima T.G. W.S.S | TSM/008975 | SM/09904 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 44.51 | Yes | 44.51 | 17/04/2025 | 03/09/2020 | 7 | 33.44 | 0 | MVS
86 | ALIPURDUAR | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | TSM/009029 | SM/09905 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 22/11/2021 | 0 | 45.51 | Yes | 45.51 |  | 13/12/2021 | 9 | 38.86 | 0 | MVS
87 | ALIPURDUAR | Rejuvenation of Gargenda Tea Garden Water Supply Scheme | TSM/008964 | SM/09906 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 45.22 | Yes | 45.22 | 19/10/2022 | 23/02/2023 | 2 | 14.94 | 0 | MVS
88 | ALIPURDUAR | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME | TSM/008978 | SM/09907 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 22/11/2021 | 0 | 44.74 | Yes | 44.74 | 21/02/2023 | 16/03/2023 | 3 | 38.67 | 0 | MVS
89 | ALIPURDUAR | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | TSM/008999 | SM/09908 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 46.31 | Yes | 46.31 | 11/11/2022 | 11/01/2022 | 6 | 53.03 | 0 | MVS
90 | ALIPURDUAR | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | TSM/009041 | SM/09909 | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 45.46 | Yes | 45.46 | 11/07/2023 | 27/12/2021 | 6 | 46.31 | 0 | MVS
91 | ALIPURDUAR | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | TSM/009033 | SM/09910 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/11/2021 | 0 | 47.45 | Yes | 47.45 | 03/10/2024 | 01/04/2022 | 5 | 28.76 | 0 | MVS
92 | ALIPURDUAR | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | TSM/006527 | SM/10038 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | 10/02/2021 | 567 | 247.03 | Yes | 247.03 | 01/03/2024 | 02/12/2024 | 4 | 97.14 | 0 | MVS
93 | ALIPURDUAR | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | TSM/006525 | SM/10039 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 10/02/2021 | 1348 | 284.23 | Yes | 284.23 | 09/08/2023 | 12/12/2022 | 9 | 307.42 | 0 | MVS
94 | ALIPURDUAR | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | TSM/006526 | SM/10054 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | 08/01/2021 | 2682 | 332.16 | Yes | 332.16 | 11/12/2024 | 12/08/2024 | 11 | 299.47 | 0 | MVS
95 | ALIPURDUAR | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | TSM/009621 | SM/10154 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 3764 | 632.84 | Yes | 632.84 | 13/12/2022 | 30/03/2024 | 23 | 659.42 | 0 | MVS
96 | ALIPURDUAR | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | TSM/009619 | SM/10155 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1040 | 140.66 | Yes | 140.66 | 23/02/2023 | 08/06/2022 | 7 | 229.6 | 0 | MVS
97 | ALIPURDUAR | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | TSM/009623 | SM/10156 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/12/2021 | 1020 | 706.17 | Yes | 706.17 | 09/02/2024 | 21/01/2023 | 24 | 728.68 | 0 | MVS
98 | ALIPURDUAR | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | TSM/009622 | SM/10169 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/12/2021 | 1527 | 378.84 | Yes | 378.84 | 05/03/2025 | 04/08/2025 | 18 | 269.4 | 0 | MVS
99 | ALIPURDUAR | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | TSM/009620 | SM/10170 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 2836 | 509.72 | Yes | 509.72 | 03/04/2025 | 20/06/2022 | 20 | 496.39 | 0 | MVS
100 | ALIPURDUAR | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | TSM/009624 | SM/10171 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 3164 | 750.42 | Yes | 750.42 | 17/04/2025 | 08/06/2022 | 22 | 751.85 | 0 | MVS
101 | ALIPURDUAR | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009549 | SM/10172 | New | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 2579 | 810.28 | Yes | 810.28 | 20/02/2024 | 14/11/2024 | 14 | 733.75 | 0 | MVS
102 | ALIPURDUAR | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009550 | SM/10173 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 2277 | 886.25 | Yes | 886.25 | 25/04/2023 | 01/04/2022 | 22 | 1213.86 | 0 | MVS
103 | ALIPURDUAR | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | TSM/009548 | SM/10174 | New | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1867 | 732.56 | Yes | 732.56 | 20/02/2024 | 01/04/2022 | 15 | 773.76 | 0 | MVS
104 | ALIPURDUAR | SIDHABARI PIED WATER SUPPLY SCHEME | TSM/009544 | SM/10175 | New | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1605 | 360.32 | Yes | 360.32 | 19/10/2022 | 01/04/2022 | 13 | 434.12 | 0 | MVS
105 | ALIPURDUAR | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009545 | SM/10176 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1425 | 426.36 | Yes | 426.36 | 07/12/2023 | 01/04/2022 | 14 | 480.17 | 0 | MVS
106 | ALIPURDUAR | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009547 | SM/10177 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1248 | 338.59 | Yes | 338.59 | 28/12/2022 | 13/05/2022 | 9 | 366.73 | 0 | MVS
107 | ALIPURDUAR | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009543 | SM/10178 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1487 | 577.33 | Yes | 577.33 | 01/03/2024 | 01/04/2022 | 19 | 764.05 | 0 | MVS
108 | ALIPURDUAR | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009546 | SM/10179 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 647 | 364.15 | Yes | 364.15 | 21/12/2023 | 01/04/2022 | 10 | 513.34 | 0 | MVS
109 | ALIPURDUAR | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | TSM/009551 | SM/10180 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/12/2021 | 1250 | 376.91 | Yes | 376.91 | 13/12/2022 | 01/04/2022 | 9 | 449.06 | 0 | MVS
110 | ALIPURDUAR | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | TSM/009616 | SM/10316 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 27/01/2022 | 2393 | 281.05 | Yes | 281.05 | 26/03/2025 | 02/05/2022 | 18 | 222.71 | 0 | MVS
111 | ALIPURDUAR | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | TSM/010851 | SM/10637 | Augmentation | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | 16/03/2022 | 3877 | 252.1 | Yes | 252.1 | 17/04/2025 | 11/05/2022 | 14 | 236.44 | 0 | MVS
112 | ALIPURDUAR | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | TSM/010085 | SM/10667 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 16/03/2022 | 40 | 186.88 | Yes | 186.88 | 17/04/2025 | 21/05/2025 | 8 | 96.99 | 0 | MVS
113 | ALIPURDUAR | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | TSM/010084 | SM/10668 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 16/03/2022 | 20 | 69.44 | Yes | 69.44 | 03/10/2024 | 06/04/2023 | 4 | 47.97 | 0 | MVS
114 | ALIPURDUAR | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | TSM/010083 | SM/10669 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 50 | 161.24 | Yes | 161.24 | 07/04/2025 | 14/11/2024 | 9 | 97.98 | 0 | MVS
115 | ALIPURDUAR | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | TSM/010081 | SM/10670 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 16/03/2022 | 45 | 108.13 | Yes | 108.13 | 07/04/2025 | 30/04/2025 | 6 | 47.4 | 0 | MVS
116 | ALIPURDUAR | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | TSM/010080 | SM/10671 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 38 | 152.39 | Yes | 152.39 | 04/10/2024 | 13/05/2022 | 7 | 88.52 | 0 | MVS
117 | ALIPURDUAR | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | TSM/010073 | SM/10672 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 30 | 162.74 | Yes | 162.74 | 11/02/2025 | 30/12/2024 | 5 | 44.31 | 0 | MVS
118 | ALIPURDUAR | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | TSM/010071 | SM/10673 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 16/03/2022 | 50 | 252.98 | Yes | 252.98 | 17/04/2025 | 13/05/2022 | 8 | 137.93 | 0 | MVS
119 | ALIPURDUAR | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | TSM/010070 | SM/10674 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 60 | 236.97 | Yes | 236.97 | 21/03/2025 | 14/11/2024 | 6 | 205.24 | 0 | MVS
120 | ALIPURDUAR | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME | TSM/010069 | SM/10675 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 50 | 178.64 | Yes | 178.64 | 05/03/2025 | 17/03/2025 | 2 | 1.73 | 0 | MVS
121 | ALIPURDUAR | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | TSM/010068 | SM/10676 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 40 | 252.39 | Yes | 252.39 | 26/03/2025 | 14/11/2024 | 8 | 66.01 | 0 | MVS
122 | ALIPURDUAR | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | TSM/010067 | SM/10677 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 2678 | 192.09 | Yes | 192.09 | 23/12/2024 | 13/05/2022 | 8 | 40.37 | 0 | MVS
123 | ALIPURDUAR | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | TSM/010066 | SM/10678 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/03/2022 | 2100 | 274.45 | Yes | 274.45 | 05/03/2025 | 04/08/2025 | 7 | 205.27 | 0 | MVS
124 | ALIPURDUAR | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME | TSM/009986 | SM/10776 | New | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | 17/02/2022 | 0 | 167.97 | Yes | 167.97 |  | 31/05/2022 | 2 | 145.62 | 0 | MVS
125 | ALIPURDUAR | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | TSM/010852 | SM/11401 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 2981 | 140.89 | Yes | 140.89 | 16/12/2022 | 03/09/2021 | 10 | 160.88 | 0 | MVS
126 | ALIPURDUAR | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | TSM/010849 | SM/11402 | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 608 | 86.31 | Yes | 86.31 | 23/02/2023 | 17/08/2022 | 10 | 96.31 | 0 | MVS
127 | ALIPURDUAR | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | TSM/009983 | SM/11459 | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 27/01/2022 | 7440 | 1873.61 | Yes | 1873.61 | 03/04/2025 | 14/11/2024 | 45 | 1707.46 | 0 | MVS
128 | ALIPURDUAR | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | TSM/010924 | SM/11482 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 1493 | 395.23 | Yes | 395.23 | 04/08/2023 | 15/07/2022 | 18 | 376.77 | 0 | MVS
129 | ALIPURDUAR | Bandpani Tea Garden Areas Piped Water Supply Scheme. | TSM/005495 | SM/11483 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 1272 | 528.37 | Yes | 528.37 | 05/03/2025 | 21/01/2023 | 18 | 398.41 | 0 | MVS
130 | ALIPURDUAR | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | TSM/010927 | SM/11484 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 1520 | 455.23 | Yes | 455.23 | 31/07/2024 | 14/11/2024 | 16 | 385.39 | 0 | MVS
131 | ALIPURDUAR | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | TSM/010925 | SM/11485 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 1567 | 389.92 | Yes | 389.92 | 21/12/2023 | 15/07/2022 | 13 | 376.91 | 0 | MVS
132 | ALIPURDUAR | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011589 | SM/11696 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 25/04/2022 | 990 | 411.35 | Yes | 411.35 | 05/03/2025 | 12/06/2025 | 9 | 336.01 | 0 | MVS
133 | ALIPURDUAR | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011590 | SM/11709 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 25/04/2022 | 1702 | 817.44 | Yes | 817.44 | 05/03/2025 | 14/11/2024 | 26 | 774.17 | 0 | MVS
134 | ALIPURDUAR | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | TSM/011786 | SM/11765 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | 25/04/2022 | 110 | 154.07 | Yes | 154.07 | 12/07/2024 | 04/04/2023 | 5 | 114.8 | 0 | MVS
135 | ALIPURDUAR | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | TSM/011781 | SM/11766 | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 25/04/2022 | 400 | 88.14 | Yes | 88.14 | 21/09/2023 | 09/11/2023 | 4 | 105.05 | 0 | MVS
136 | ALIPURDUAR | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | TSM/011251 | SM/11767 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | 25/04/2022 | 250 | 204.15 | Yes | 204.15 | 30/07/2024 | 26/06/2025 | 14 | 167.43 | 0 | MVS
137 | ALIPURDUAR | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | TSM/010089 | SM/11958 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 16/03/2022 | 493 | 562.16 | Yes | 562.16 | 13/05/2025 | 04/04/2023 | 16 | 285.48 | 0 | MVS
138 | ALIPURDUAR | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | TSM/010088 | SM/11959 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 807 | 648.63 | Yes | 648.63 | 13/05/2025 | 19/05/2023 | 10 | 384.18 | 0 | MVS
139 | ALIPURDUAR | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/010082 | SM/11960 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 1031 | 512.91 | Yes | 512.91 | 08/04/2025 | 29/07/2025 | 10 | 342.06 | 0 | MVS
140 | ALIPURDUAR | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | TSM/010087 | SM/11970 | Augmentation | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 16/03/2022 | 7780 | 1275.43 | Yes | 1275.43 | 05/03/2025 | 21/06/2024 | 28 | 1052.18 | 0 | MVS
141 | ALIPURDUAR | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | TSM/009618 | SM/11985 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/03/2022 | 7273 | 2156.38 | Yes | 2156.38 | 08/04/2025 | 21/12/2022 | 29 | 1856.93 | 0 | MVS
142 | ALIPURDUAR | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | TSM/012047 | SM/11991 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 15/07/2022 | 1128 | 432.05 | Yes | 432.05 | 05/03/2025 | 18/08/2025 | 12 | 397.57 | 0 | MVS
143 | ALIPURDUAR | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/013062 | SM/11992 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Birpara Sub Division | 15/07/2022 | 705 | 269.79 | Yes | 269.79 | 02/08/2023 | 25/08/2023 | 11 | 229.75 | 0 | MVS
144 | ALIPURDUAR | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/013061 | SM/12113 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 15/07/2022 | 2542 | 821.35 | Yes | 821.35 | 23/12/2024 | 18/05/2023 | 18 | 638.98 | 0 | MVS
145 | ALIPURDUAR | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/012048 | SM/12114 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 15/07/2022 | 1999 | 588.27 | Yes | 588.27 | 20/02/2024 | 18/04/2023 | 21 | 548.98 | 0 | MVS
146 | ALIPURDUAR | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | TSM/010086 | SM/12361 | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 16/03/2022 | 1277 | 1269.79 | Yes | 1269.79 | 13/05/2025 | 21/09/2023 | 25 | 361.65 | 0 | MVS
147 | ALIPURDUAR | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | TSM/009641 | SM/12561 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 27/01/2022 | 7617 | 1852.66 | Yes | 1852.66 | 17/04/2025 | 14/11/2024 | 46 | 1458.6 | 0 | MVS
148 | ALIPURDUAR | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | TSM/014605 | SM/12753 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 22/08/2022 | 2683 | 797.79 | Yes | 797.79 | 08/04/2025 | 17/06/2025 | 11 | 688.74 | 0 | MVS
149 | ALIPURDUAR | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | TSM/014598 | SM/12754 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 22/08/2022 | 694 | 415.72 | Yes | 415.72 | 08/04/2025 | 12/06/2025 | 10 | 388.35 | 0 | MVS
150 | ALIPURDUAR | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/015105 | SM/13239 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick),RWS Falakata Block | 09/09/2022 | 4031 | 716.98 | Yes | 716.98 | 08/04/2025 | 18/05/2023 | 18 | 691.47 | 0 | MVS
151 | ALIPURDUAR | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | TSM/015365 | SM/13240 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 929 | 741.26 | Yes | 741.26 | 13/05/2025 | 25/08/2023 | 10 | 442.33 | 0 | MVS
152 | ALIPURDUAR | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | TSM/015362 | SM/13241 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1437 | 780.16 | Yes | 780.16 | 13/05/2025 | 19/05/2023 | 15 | 575.58 | 0 | MVS
153 | ALIPURDUAR | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | TSM/015656 | SM/13242 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1001 | 615.61 | Yes | 615.61 | 13/05/2025 | 23/08/2023 | 16 | 470.35 | 0 | MVS
154 | ALIPURDUAR | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | TSM/015658 | SM/13243 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1919 | 963.61 | Yes | 963.61 | 13/05/2025 | 14/11/2024 | 15 | 633.76 | 0 | MVS
155 | ALIPURDUAR | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | TSM/014603 | SM/13244 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 09/09/2022 | 1482 | 710.27 | Yes | 710.27 | 08/04/2025 | 30/05/2025 | 15 | 658 | 0 | MVS
156 | ALIPURDUAR | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | TSM/014601 | SM/13245 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 09/09/2022 | 2797 | 969.65 | Yes | 969.65 | 05/01/2024 | 07/09/2023 | 11 | 638.08 | 0 | MVS
157 | ALIPURDUAR | BARIGURI PIPED WATER SUPPLY SCHEME | TSM/014599 | SM/13246 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 09/09/2022 | 7373 | 895.77 | Yes | 895.77 | 05/03/2025 | 16/05/2023 | 13 | 715.39 | 0 | MVS
158 | ALIPURDUAR | PRODHANPARA PIPED WATER SUPPLY SCHEME | TSM/014597 | SM/13247 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 09/09/2022 | 1353 | 638.14 | Yes | 638.14 | 05/03/2025 | 07/03/2025 | 9 | 491.11 | 0 | MVS
159 | ALIPURDUAR | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | TSM/014606 | SM/13248 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | 09/09/2022 | 2462 | 877.17 | Yes | 877.17 | 05/03/2025 | 14/11/2024 | 16 | 787.9 | 0 | MVS
160 | ALIPURDUAR | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | TSM/014604 | SM/13249 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 2652 | 860.22 | Yes | 860.22 | 21/09/2023 | 08/08/2024 | 21 | 761.94 | 0 | MVS
161 | ALIPURDUAR | KAYAKHATA PIPED WATER SUPPLY SCHEME | TSM/015411 | SM/13299 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 09/09/2022 | 1585 | 682.41 | Yes | 682.41 | 08/04/2025 | 12/06/2025 | 13 | 460.94 | 0 | MVS
162 | ALIPURDUAR | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | TSM/015364 | SM/13300 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1847 | 944.2 | Yes | 944.2 | 13/05/2025 | 10/09/2024 | 19 | 714.99 | 0 | MVS
163 | ALIPURDUAR | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | TSM/015363 | SM/13301 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 09/09/2022 | 1869 | 875.66 | Yes | 875.66 | 20/02/2024 | 10/09/2024 | 14 | 727.78 | 0 | MVS
164 | ALIPURDUAR | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | TSM/014600 | SM/13302 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 09/09/2022 | 308 | 171.75 | Yes | 171.75 | 03/07/2024 | 10/09/2024 | 7 | 157.18 | 0 | MVS
165 | ALIPURDUAR | TELIPARA PIPED WATER SUPPLY SCHEME. | TSM/015706 | SM/13303 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1029 | 488.14 | Yes | 488.14 | 23/12/2024 | 14/11/2024 | 16 | 388.13 | 0 | MVS
166 | ALIPURDUAR | MARAKHATA PIPED WATER SUPPLY SCHEME. | TSM/015657 | SM/13304 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 3129 | 839.09 | Yes | 839.09 | 13/05/2025 | 23/08/2023 | 15 | 527.34 | 0 | MVS
167 | ALIPURDUAR | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | TSM/015650 | SM/13305 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1402 | 760.21 | Yes | 760.21 | 19/03/2025 | 19/05/2023 | 16 | 588.61 | 0 | MVS
168 | ALIPURDUAR | KALABERIA PIPED WATER SUPPLY SCHEME | TSM/014585 | SM/13306 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 09/09/2022 | 1065 | 461.28 | Yes | 461.28 | 11/02/2025 | 14/11/2024 | 10 | 416.99 | 0 | MVS
169 | ALIPURDUAR | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | TSM/015538 | SM/13448 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 563 | 305.16 | Yes | 305.16 | 08/04/2025 | 06/06/2023 | 9 | 289.89 | 0 | MVS
170 | ALIPURDUAR | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/015106 | SM/13449 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 09/09/2022 | 1856 | 695.45 | Yes | 695.45 | 21/11/2024 | 16/01/2024 | 15 | 633.16 | 0 | MVS
171 | ALIPURDUAR | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017486 | SM/14092 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/09/2022 | 1884 | 895.42 | Yes | 895.42 | 23/12/2024 | 14/11/2024 | 17 | 778.4 | 0 | MVS
172 | ALIPURDUAR | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017485 | SM/14093 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 30/09/2022 | 1074 | 528.73 | Yes | 528.73 | 05/03/2025 | 14/11/2024 | 13 | 305.01 | 0 | MVS
173 | ALIPURDUAR | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | TSM/009625 | SM/14096 | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 27/01/2022 | 8070 | 2031.4 | Yes | 2031.4 | 07/04/2025 | 14/11/2024 | 59 | 1832.32 | 0 | MVS
174 | ALIPURDUAR | PARARPAR PIPED WATER SUPPLY SCHEME | TSM/015970 | SM/14209 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 26/09/2022 | 1187 | 561.82 | Yes | 561.82 | 21/03/2025 | 30/04/2025 | 15 | 539.66 | 0 | MVS
175 | ALIPURDUAR | FOSKADANGA PIPED WATER SUPPLY SCHEME | TSM/015969 | SM/14210 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 26/09/2022 | 684 | 510.99 | Yes | 510.99 | 04/10/2024 | 30/04/2025 | 11 | 452.79 | 0 | MVS
176 | ALIPURDUAR | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015968 | SM/14211 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 1604 | 530.22 | Yes | 530.22 | 26/03/2025 | 14/11/2024 | 14 | 465.37 | 0 | MVS
177 | ALIPURDUAR | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015967 | SM/14212 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 26/09/2022 | 2321 | 570.23 | Yes | 570.23 | 16/02/2024 | 06/10/2023 | 13 | 544.11 | 0 | MVS
178 | ALIPURDUAR | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015966 | SM/14213 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 26/09/2022 | 2268 | 740.97 | Yes | 740.97 | 08/04/2025 | 28/03/2024 | 13 | 533.91 | 0 | MVS
179 | ALIPURDUAR | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015965 | SM/14214 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 26/09/2022 | 1579 | 527.26 | Yes | 527.26 | 24/02/2025 | 02/07/2024 | 12 | 669.78 | 0 | MVS
180 | ALIPURDUAR | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015964 | SM/14215 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 26/09/2022 | 1002 | 336.47 | Yes | 336.47 | 20/02/2024 | 07/09/2023 | 10 | 269.47 | 0 | MVS
181 | ALIPURDUAR | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | TSM/015963 | SM/14216 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 130 | 129.41 | Yes | 129.41 | 19/03/2025 | 19/01/2023 | 6 | 134.64 | 0 | MVS
182 | ALIPURDUAR | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | TSM/015960 | SM/14217 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 794 | 409.38 | Yes | 409.38 | 31/07/2024 | 03/10/2023 | 11 | 395.31 | 0 | MVS
183 | ALIPURDUAR | NURPUR PIPED WATER SUPPLY SCHEME. | TSM/016017 | SM/14218 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 423 | 451.36 | Yes | 451.36 | 13/12/2023 | 16/08/2023 | 12 | 323.39 | 0 | MVS
184 | ALIPURDUAR | TURTURI PIPED WATER SUPPLY SCHEME. | TSM/016016 | SM/14219 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 1003 | 948.08 | Yes | 948.08 | 13/05/2025 | 23/08/2023 | 19 | 574.29 | 0 | MVS
185 | ALIPURDUAR | TORSHA FOREST PIPED WATER SUPPLY SCHEME | TSM/015971 | SM/14220 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 26/09/2022 | 201 | 142.14 | Yes | 142.14 | 25/07/2023 | 24/08/2023 | 6 | 121.5 | 0 | MVS
186 | ALIPURDUAR | BALLALGURI PIPED WATER SUPPLY SCHEME | TSM/015962 | SM/14221 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | 26/09/2022 | 609 | 413.54 | Yes | 413.54 | 13/12/2023 | 07/09/2023 | 8 | 302.65 | 0 | MVS
187 | ALIPURDUAR | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | TSM/015961 | SM/14222 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 729 | 429.71 | Yes | 429.71 | 30/07/2024 | 03/10/2023 | 8 | 143.28 | 0 | MVS
188 | ALIPURDUAR | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | TSM/015992 | SM/14223 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 26/09/2022 | 603 | 509.75 | Yes | 509.75 | 13/05/2025 | 23/08/2023 | 19 | 340.3 | 0 | MVS
189 | ALIPURDUAR | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | TSM/010090 | SM/14233 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/03/2022 | 18867 | 2288.93 | Yes | 2288.93 | 03/04/2025 | 16/04/2025 | 48 | 2120.28 | 0 | MVS
190 | ALIPURDUAR | MAIRADANGA PIPED WATER SUPPLY SCHEME | TSM/018061 | SM/15206 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/11/2022 | 3541 | 963.71 | Yes | 963.71 | 21/03/2025 | 16/05/2023 | 13 | 865.91 | 0 | MVS
191 | ALIPURDUAR | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | TSM/017889 | SM/15207 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/11/2022 | 2097 | 802.95 | Yes | 802.95 | 08/04/2025 | 26/09/2024 | 12 | 194.57 | 0 | MVS
192 | ALIPURDUAR | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | TSM/017875 | SM/15208 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/11/2022 | 1552 | 670.33 | Yes | 670.33 | 08/04/2025 | 04/08/2025 | 11 | 617.48 | 0 | MVS
193 | ALIPURDUAR | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | TSM/018090 | SM/15209 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/11/2022 | 0 | 112.19 | Yes | 112.19 | 26/03/2025 | 26/06/2025 | 6 | 43.66 | 0 | MVS
194 | ALIPURDUAR | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | TSM/018074 | SM/15210 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/11/2022 | 0 | 111.32 | Yes | 111.32 | 05/01/2024 | 16/01/2024 | 7 | 109.66 | 0 | MVS
195 | ALIPURDUAR | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009552 | SM/15482 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 27/01/2022 | 5753 | 1380.67 | Yes | 1380.67 | 23/12/2024 | 14/11/2024 | 23 | 1194.38 | 0 | MVS
196 | ALIPURDUAR | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | TSM/014896 | SM/15517 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 1645 | 1067.02 | Yes | 1067.02 | 13/05/2025 | 14/11/2024 | 16 | 748.77 | 0 | MVS
197 | ALIPURDUAR | CHALNIPAK PIPED WATER SUPPLY SCHEME. | TSM/015993 | SM/15534 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | 26/09/2022 | 1648 | 1024.4 | Yes | 1024.4 | 13/05/2025 | 30/04/2025 | 16 | 693.68 | 0 | MVS
198 | ALIPURDUAR | NARASINGPUR PIPED WATER SUPPLY SCHEME | TSM/017984 | SM/15758 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 16/11/2022 | 2461 | 842.46 | Yes | 842.46 | 25/01/2024 | 20/07/2023 | 12 | 804.79 | 0 | MVS
199 | ALIPURDUAR | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | TSM/017679 | SM/15914 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 30/09/2022 | 567 | 358.24 | Yes | 358.24 | 12/05/2023 | 24/04/2023 | 7 | 247.06 | 0 | MVS
200 | ALIPURDUAR | UMACHARANPUR PIPED WATER SUPPLY SCHEME | TSM/017944 | SM/16114 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 16/11/2022 | 3053 | 950.07 | Yes | 950.07 | 21/03/2025 | 19/09/2025 | 13 | 907.02 | 0 | MVS
201 | ALIPURDUAR | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME | TSM/018098 | SM/16115 | Augmentation | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | 16/11/2022 | 0 | 240.25 | Yes | 240.25 | 26/03/2025 | 12/06/2025 | 3 | 92.6 | 0 | MVS
202 | ALIPURDUAR | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | TSM/017682 | SM/16506 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 28/12/2022 | 1752 | 990.41 | Yes | 990.41 | 13/05/2025 | 08/08/2024 | 26 | 563.04 | 0 | MVS
203 | ALIPURDUAR | BUXA PIPE WATER SUPPLY SCHEME | TSM/017681 | SM/16507 | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 28/12/2022 | 219 | 219.61 | Yes | 219.61 | 19/03/2025 | 26/06/2025 | 8 | 104.12 | 0 | MVS
204 | ALIPURDUAR | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | TSM/015628 | SM/16537 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 09/09/2022 | 2273 | 1261.38 | Yes | 1261.38 | 21/03/2025 | 14/11/2024 | 20 | 888.73 | 0 | MVS
205 | ALIPURDUAR | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | TSM/014886 | SM/16538 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 09/09/2022 | 1888 | 1074.69 | Yes | 1074.69 | 13/05/2025 | 14/11/2024 | 15 | 625.19 | 0 | MVS
206 | ALIPURDUAR | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | TSM/014602 | SM/16539 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 09/09/2022 | 2329 | 1121.63 | Yes | 1121.63 | 05/03/2025 | 28/07/2023 | 15 | 970.62 | 0 | MVS
207 | ALIPURDUAR | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | TSM/018017 | SM/16817 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 1601 | 808.5 | Yes | 808.5 | 31/07/2024 | 20/07/2023 | 13 | 794.24 | 0 | MVS
208 | ALIPURDUAR | MALSAGAON PIPED WATER SUPPLY SCHEME | TSM/017938 | SM/16818 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 1481 | 777.46 | Yes | 777.46 | 05/03/2025 | 04/08/2025 | 10 | 722.44 | 0 | MVS
209 | ALIPURDUAR | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | TSM/017918 | SM/16819 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 1272 | 658.29 | Yes | 658.29 | 29/12/2023 | 03/08/2023 | 11 | 619.34 | 0 | MVS
210 | ALIPURDUAR | BENGKANDI PIPED WATER SUPPLY SCHEME | TSM/017878 | SM/16820 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 2074 | 964.09 | Yes | 964.09 | 27/11/2024 | 28/07/2023 | 12 | 932.54 | 0 | MVS
211 | ALIPURDUAR | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018324 | SM/16821 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 442 | 405.28 | Yes | 405.28 | 08/04/2025 | 31/03/2023 | 9 | 285.59 | 0 | MVS
212 | ALIPURDUAR | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017771 | SM/16822 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 1184 | 569.65 | Yes | 569.65 | 12/04/2025 | 19/05/2023 | 13 | 424.79 | 0 | MVS
213 | ALIPURDUAR | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017770 | SM/16823 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 28/12/2022 | 1298 | 739.67 | Yes | 739.67 | 05/03/2025 | 14/11/2024 | 13 | 539.59 | 0 | MVS
214 | ALIPURDUAR | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | TSM/018091 | SM/16824 | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 28/12/2022 | 0 | 273.66 | Yes | 273.66 | 05/03/2025 | 26/06/2025 | 13 | 203.57 | 0 | MVS
215 | ALIPURDUAR | Malangi Tea Garden Area Piped Water Supply Scheme | TSM/020703 | SM/18150 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 10/03/2023 | 2115 | 561.45 | Yes | 561.45 | 12/04/2025 | 04/05/2023 | 11 | 422.13 | 0 | MVS
216 | ALIPURDUAR | Khagenhat Piped Water Supply Scheme | TSM/020701 | SM/18151 | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | 10/03/2023 | 2057 | 822.98 | Yes | 822.98 | 12/04/2025 | 14/11/2024 | 13 | 735.75 | 0 | MVS
217 | ALIPURDUAR | Chengmari Piped Water Supply Scheme | TSM/020700 | SM/18152 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 10/03/2023 | 1699 | 772.15 | Yes | 772.15 | 26/03/2025 | 04/05/2023 | 12 | 637.53 | 0 | MVS
218 | ALIPURDUAR | Dhantali Piped Water Supply Scheme | TSM/020699 | SM/18153 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | 10/03/2023 | 206 | 285.56 | Yes | 285.56 | 28/03/2023 | 04/05/2023 | 6 | 248.07 | 0 | MVS
219 | ALIPURDUAR | Uttar Dhalkar Piped Water Supply Scheme | TSM/020698 | SM/18154 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 10/03/2023 | 594 | 404.14 | Yes | 404.14 | 24/10/2024 | 04/05/2023 | 6 | 286.86 | 0 | MVS
220 | ALIPURDUAR | Bhutri Forest Piped Water Supply Scheme | TSM/020702 | SM/18156 | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | 10/03/2023 | 48 | 59.54 | Yes | 59.54 | 03/04/2025 | 18/04/2023 | 4 | 45.63 | 0 | MVS
221 | ALIPURDUAR | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | TSM/020697 | SM/18157 | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | 10/03/2023 | 1538 | 360.16 | Yes | 360.16 | 26/03/2025 | 22/05/2023 | 6 | 265.9 | 0 | MVS
222 | ALIPURDUAR | Parpatla Khawa Piped Water Supply Scheme | TSM/020696 | SM/18158 | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | 10/03/2023 | 189 | 187.87 | Yes | 187.87 | 21/03/2025 | 04/05/2023 | 6 | 179.68 | 0 | MVS
223 | ALIPURDUAR | AUGMENTATION OF DALIMPUR PWSS | TSM/009613 | SM/18254 | Augmentation |  |  |  | 27/01/2022 | 4067 | 1020.25 | Yes | 1020.25 | 23/12/2024 | 12/07/2023 | 19 | 776.5 | 0 | MVS
Total | [9 empty] | 363885 | 89667.07 |  | 89667.07 |  |  | 2605 | 75616.72 | 1805.1