## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | KALIMPONG | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | TSM/006925 | SM/07872 | Retrofitting |  |  |  | 04/12/2020 | 625 | 72.63 | Yes | 72.63 | 08/01/2024 | 12/10/2020 | 5 | 67.79 | 106.41 | MVS
2 | KALIMPONG | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | TSM/007291 | SM/08693 | Retrofitting | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer I,Junior Engineer IV | 10/02/2021 | 1000 | 99.42 | Yes | 99.42 |  | 06/09/2021 | 4 | 99.17 | 98.58 | MVS
3 | KALIMPONG | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI | TSM/008868 | SM/09539 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4 | 29/09/2021 | 121 | 151.5 | Yes | 151.5 | 02/12/2021 | 14/01/2022 | 2 | 147.73 | 121.37 | MVS
4 | KALIMPONG | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING | TSM/008861 | SM/09540 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-4 | 29/09/2021 | 61 | 91.94 | Yes | 91.94 | 02/12/2021 | 14/01/2022 | 2 | 89.37 | 72.27 | MVS
5 | KALIMPONG | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | TSM/008864 | SM/09541 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 29/09/2021 | 400 | 568.83 | Yes | 568.83 | 01/04/2025 | 04/04/2022 | 3 | 553.22 | 405.35 | MVS
6 | KALIMPONG | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON | TSM/008869 | SM/09542 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 29/09/2021 | 87 | 108.18 | Yes | 108.18 | 21/01/2022 | 28/03/2022 | 2 | 96.64 | 89.57 | MVS
7 | KALIMPONG | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY | TSM/008860 | SM/09543 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4 | 29/09/2021 | 213 | 365.16 | Yes | 365.16 | 14/12/2021 | 21/02/2022 | 2 | 355.16 | 285.41 | MVS
8 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. | TSM/008815 | SM/09544 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-I | 29/09/2021 | 147 | 198.74 | Yes | 198.74 | 02/12/2021 | 14/01/2022 | 2 | 193.65 | 186.45 | MVS
9 | KALIMPONG | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON | TSM/008841 | SM/09545 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-4 | 29/09/2021 | 125 | 160.48 | Yes | 160.48 | 24/04/2023 | 28/07/2023 | 2 | 5.55 | 98.7 | MVS
10 | KALIMPONG | PWS SCHEME FROM MAWATAR TO UPPER DABLING | TSM/008852 | SM/09546 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-2 | 29/09/2021 | 50 | 192.44 | Yes | 192.44 | 02/12/2021 | 18/04/2023 | 4 | 186.52 | 186.34 | MVS
11 | KALIMPONG | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | TSM/008851 | SM/09547 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | 29/09/2021 | 300 | 237.68 | Yes | 237.68 | 02/12/2021 | 14/01/2022 | 6 | 239.34 | 128.7 | MVS
12 | KALIMPONG | PWS from Samphong Khola to Kagey Busty District Kalimpong | TSM/008805 | SM/09548 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | 29/09/2021 | 641 | 679.86 | Yes | 679.86 | 14/12/2021 | 21/02/2022 | 4 | 676.65 | 598.98 | MVS
13 | KALIMPONG | PWS SCHEME FROM JHOLUNG KHOLA TO 45 DHURA | TSM/008859 | SM/09584 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 08/10/2021 | 160 | 138.09 | Yes | 138.09 | 02/12/2021 | 23/02/2022 | 1 | 0.88 | 119.64 | MVS
14 | KALIMPONG | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE | TSM/008850 | SM/09594 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 29/09/2021 | 480 | 776.35 | Yes | 776.35 | 14/12/2021 | 04/04/2022 | 2 | 743.5 | 582.85 | MVS
15 | KALIMPONG | PWS SCHEME FROM UNEAK KHOLA TO DABLING | TSM/008844 | SM/09595 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-2 | 29/09/2021 | 95 | 126.98 | Yes | 126.98 | 02/12/2021 | 07/01/2022 | 2 | 123.18 | 123.18 | MVS
16 | KALIMPONG | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | TSM/008854 | SM/09596 | New |  |  |  | 29/09/2021 | 320 | 314.39 | Yes | 314.39 | 14/12/2021 | 21/02/2022 | 5 | 425.27 | 312.99 | MVS
17 | KALIMPONG | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA | TSM/008849 | SM/09597 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | 29/09/2021 | 74 | 199.67 | Yes | 199.67 | 02/12/2021 | 14/01/2022 | 2 | 193.29 | 172.38 | MVS
18 | KALIMPONG | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON | TSM/008853 | SM/09598 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-3 | 29/09/2021 | 56 | 96.33 | Yes | 96.33 | 02/12/2021 | 07/01/2022 | 2 | 186.8 | 93.52 | MVS
19 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. | TSM/008820 | SM/09599 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 29/09/2021 | 502 | 312 | Yes | 312 | 14/12/2021 | 21/02/2022 | 3 | 308.4 | 227.79 | MVS
20 | KALIMPONG | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | TSM/008848 | SM/09600 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | 29/09/2021 | 234 | 169.19 | Yes | 169.19 | 02/12/2021 | 01/11/2023 | 4 | 165.26 | 137.3 | MVS
21 | KALIMPONG | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | TSM/008836 | SM/09601 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | 29/09/2021 | 245 | 206.39 | Yes | 206.39 | 02/12/2021 | 07/11/2023 | 5 | 199.21 | 171.41 | MVS
22 | KALIMPONG | Pws scheme from 7th Mile Jhora to Algarah | TSM/008835 | SM/09602 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 29/09/2021 | 450 | 321.38 | Yes | 321.38 | 14/12/2021 | 21/02/2022 | 3 | 378.44 | 237.76 | MVS
23 | KALIMPONG | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE | TSM/008847 | SM/09603 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 29/09/2021 | 120 | 258.69 | Yes | 258.69 | 14/12/2021 | 28/03/2024 | 5 | 257.42 | 214.89 | MVS
24 | KALIMPONG | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA | TSM/008866 | SM/09605 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 29/09/2021 | 220 | 164.46 | Yes | 164.46 | 02/12/2021 | 14/01/2022 | 2 | 160.83 | 131.87 | MVS
25 | KALIMPONG | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE | TSM/008867 | SM/09606 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-4 | 29/09/2021 | 230 | 198.35 | Yes | 198.35 | 02/12/2021 | 07/01/2022 | 2 | 193.36 | 176.2 | MVS
26 | KALIMPONG | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN | TSM/008871 | SM/09607 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 29/09/2021 | 208 | 108.86 | Yes | 108.86 | 02/12/2021 | 14/01/2022 | 2 | 106.77 | 75.45 | MVS
27 | KALIMPONG | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | TSM/008862 | SM/09608 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 29/09/2021 | 448 | 367.78 | Yes | 367.78 | 23/11/2023 | 25/12/2023 | 4 | 361.24 | 271.67 | MVS
28 | KALIMPONG | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING | TSM/008857 | SM/09609 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | 29/09/2021 | 75 | 98.66 | Yes | 98.66 | 02/12/2021 | 07/01/2022 | 2 | 95.48 | 80.79 | MVS
29 | KALIMPONG | PWS SCHEME FROM CHAWA KHOLA TO RELLI | TSM/008843 | SM/09610 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4 | 29/09/2021 | 125 | 122.01 | Yes | 122.01 | 02/12/2021 | 07/01/2022 | 2 | 180.95 | 117.87 | MVS
30 | KALIMPONG | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG | TSM/008842 | SM/09611 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-II | 29/09/2021 | 70 | 80.8 | Yes | 80.8 | 02/12/2021 | 07/01/2022 | 2 | 78.77 | 70.87 | MVS
31 | KALIMPONG | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON | TSM/008855 | SM/09612 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 29/09/2021 | 110 | 180.96 | Yes | 180.96 | 21/01/2022 | 28/02/2022 | 1 | 154.6 | 90.46 | MVS
32 | KALIMPONG | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON | TSM/008840 | SM/09613 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 29/09/2021 | 88 | 110.68 | Yes | 110.68 | 21/01/2022 | 28/02/2022 | 2 | 107.88 | 81.5 | MVS
33 | KALIMPONG | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY | TSM/008838 | SM/09614 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 29/09/2021 | 61 | 88.27 | Yes | 88.27 | 02/12/2021 | 14/01/2022 | 2 | 86.02 | 68.87 | MVS
34 | KALIMPONG | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON | TSM/008856 | SM/09615 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-4 | 29/09/2021 | 55 | 118.44 | Yes | 118.44 | 02/12/2021 | 14/01/2022 | 3 | 117.29 | 118.44 | MVS
35 | KALIMPONG | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA | TSM/008846 | SM/09616 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 29/09/2021 | 50 | 143.99 | Yes | 143.99 | 02/12/2021 | 07/01/2022 | 2 | 139.12 | 123.51 | MVS
36 | KALIMPONG | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | TSM/008837 | SM/09617 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 29/09/2021 | 99 | 100.06 | Yes | 100.06 | 02/12/2021 | 07/11/2023 | 4 | 132.03 | 73.75 | MVS
37 | KALIMPONG | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI | TSM/008865 | SM/09664 | New |  |  |  | 29/09/2021 | 60 | 137.62 | Yes | 137.62 | 02/12/2021 | 07/01/2022 | 2 | 308.65 | 124.17 | MVS
38 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG | TSM/008822 | SM/09665 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | 29/09/2021 | 221 | 142.76 | Yes | 142.76 | 02/12/2021 | 14/01/2022 | 2 | 139.48 | 46.99 | MVS
39 | KALIMPONG | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE | TSM/008845 | SM/09666 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-IV | Junior Engineer-II | 29/09/2021 | 140 | 138.81 | Yes | 138.81 | 02/12/2021 | 07/01/2022 | 2 | 135.39 | 103.07 | MVS
40 | KALIMPONG | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP | TSM/008863 | SM/09667 | New |  |  |  | 29/09/2021 | 350 | 476.5 | Yes | 476.5 | 14/12/2021 | 21/02/2022 | 2 | 649.72 | 462.62 | MVS
41 | KALIMPONG | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON | TSM/008870 | SM/09668 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 29/09/2021 | 140 | 182.37 | Yes | 182.37 | 02/12/2021 | 01/11/2023 | 5 | 282.08 | 146.67 | MVS
42 | KALIMPONG | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG | TSM/008839 | SM/09669 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-I | 29/09/2021 | 56 | 125.27 | Yes | 125.27 | 24/04/2023 | 23/02/2022 | 1 | 0.31 | 110.7 | MVS
43 | KALIMPONG | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA | TSM/008858 | SM/09670 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 29/09/2021 | 65 | 122.05 | Yes | 122.05 | 02/12/2021 | 07/01/2022 | 2 | 118.14 | 106.91 | MVS
44 | KALIMPONG | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | TSM/008351 | SM/10052 | Augmentation | Neorakhola W/S Mnt. Division | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | 15/09/2021 | 0 | 4402.74 | Yes | 4402.74 |  | 13/04/2022 | 24 | 1970.3 | 787.17 | MVS
45 | KALIMPONG | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | TSM/006998 | SM/10265 | Retrofitting |  |  |  | 08/01/2021 | 1475 | 228.22 | Yes | 228.22 |  | 14/12/2022 | 14 | 199.13 | 199.13 | MVS
46 | KALIMPONG | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | TSM/006999 | SM/10266 | Retrofitting |  |  |  | 08/01/2021 | 1769 | 187.99 | Yes | 187.99 |  | 29/03/2024 | 12 | 163.77 | 163.77 | MVS
47 | KALIMPONG | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | TSM/007000 | SM/10267 | Retrofitting |  |  |  | 08/01/2021 | 1116 | 127.68 | Yes | 127.68 |  | 14/12/2022 | 9 | 116.84 | 116.84 | MVS
48 | KALIMPONG | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong | TSM/010474 | SM/10512 | Retrofitting | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | 17/02/2022 | 677 | 504.2 | Yes | 504.2 |  | 13/04/2022 | 6 | 582.5 | 409.03 | MVS
49 | KALIMPONG | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009883 | SM/10562 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 16/03/2022 | 67 | 132.05 | Yes | 132.05 |  | 24/05/2022 | 1 | 230.8 | 106.04 | MVS
50 | KALIMPONG | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009887 | SM/10563 | New |  |  |  | 16/03/2022 | 34 | 62.89 | Yes | 62.89 |  | 15/05/2023 | 2 | 3.73 | 44.12 | MVS
51 | KALIMPONG | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009884 | SM/10575 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 16/03/2022 | 43 | 49.33 | Yes | 49.33 |  | 15/05/2023 | 3 | 47.61 | 28.68 | MVS
52 | KALIMPONG | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009881 | SM/10576 | New |  |  |  | 16/03/2022 | 45 | 49.14 | Yes | 49.14 |  | 09/11/2023 | 2 | 48.22 | 30.78 | MVS
53 | KALIMPONG | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009885 | SM/10599 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 16/03/2022 | 28 | 67.06 | Yes | 67.06 |  | 26/05/2022 | 1 | 114.58 | 52.65 | MVS
54 | KALIMPONG | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | TSM/009882 | SM/10600 | New |  |  |  | 16/03/2022 | 13 | 10.62 | Yes | 10.62 |  | 26/05/2022 | 2 | 10.28 | 0 | MVS
55 | KALIMPONG | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009877 | SM/10601 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 16/03/2022 | 10 | 9.66 | Yes | 9.66 |  | 26/05/2022 | 2 | 13.19 | 8.69 | MVS
56 | KALIMPONG | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009875 | SM/10602 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 16/03/2022 | 27 | 25.25 | Yes | 25.25 |  | 26/05/2022 | 1 | 21.57 | 10.13 | MVS
57 | KALIMPONG | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009878 | SM/10603 | New |  |  |  | 16/03/2022 | 55 | 41.32 | Yes | 41.32 |  | 15/05/2023 | 3 | 84.05 | 37.19 | MVS
58 | KALIMPONG | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009886 | SM/10623 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 16/03/2022 | 28 | 41.4 | Yes | 41.4 |  | 25/05/2022 | 1 | 38.82 | 33.46 | MVS
59 | KALIMPONG | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009876 | SM/10624 | New |  |  |  | 16/03/2022 | 42 | 40.13 | Yes | 40.13 |  | 25/05/2022 | 1 | 60.93 | 38.03 | MVS
60 | KALIMPONG | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009880 | SM/10625 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer I | 16/03/2022 | 62 | 49.5 | Yes | 49.5 |  | 15/05/2023 | 3 | 51.49 | 42.76 | MVS
61 | KALIMPONG | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010479 | SM/10635 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 16/03/2022 | 70 | 143.53 | Yes | 143.53 |  | 29/07/2024 | 2 | 147.68 | 119.03 | MVS
62 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009630 | SM/10694 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 105 | 94.15 | Yes | 94.15 | 23/10/2024 | 02/04/2025 | 2 | 93.09 | 55.95 | MVS
63 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009662 | SM/10695 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III,Assistant Engineer-IV | Junior Engineer-3,Junior Engineer-II | 17/02/2022 | 136 | 138.07 | Yes | 138.07 |  | 26/05/2022 | 1 | 133.86 | 111.81 | MVS
64 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009667 | SM/10696 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 135 | 115.09 | Yes | 115.09 |  | 25/05/2022 | 2 | 107.89 | 80.87 | MVS
65 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009665 | SM/10697 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 100 | 126.09 | Yes | 126.09 |  | 01/08/2022 | 1 | 120.9 | 73.25 | MVS
66 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009664 | SM/10698 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 169 | 206.41 | Yes | 206.41 |  | 25/05/2022 | 1 | 251.91 | 186.41 | MVS
67 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009654 | SM/10699 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 350 | 152.76 | Yes | 152.76 |  | 25/05/2022 | 1 | 147.75 | 64.76 | MVS
68 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009635 | SM/10700 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 242 | 173.31 | Yes | 173.31 |  | 24/05/2022 | 1 | 164.25 | 136.83 | MVS
69 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009626 | SM/10701 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | 17/02/2022 | 90 | 114.57 | Yes | 114.57 |  | 30/06/2022 | 1 | 104.88 | 81.26 | MVS
70 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009650 | SM/10702 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-II | 17/02/2022 | 131 | 113.56 | Yes | 113.56 |  | 13/05/2022 | 1 | 100.81 | 79.21 | MVS
71 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009652 | SM/10703 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-4 | 17/02/2022 | 407 | 286.37 | Yes | 286.37 |  | 09/04/2025 | 2 | 285.38 | 252.26 | MVS
72 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009661 | SM/10704 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-III | 17/02/2022 | 226 | 338.99 | Yes | 338.99 |  | 25/12/2023 | 2 | 452.04 | 301.93 | MVS
73 | KALIMPONG | Augmentation of Lolaygoan Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission (JJM) under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009871 | SM/10705 | Augmentation | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 27/01/2022 | 105 | 99.21 | Yes | 99.21 |  | 13/04/2022 | 1 | 95.54 | 67.31 | MVS
74 | KALIMPONG | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | TSM/010520 | SM/10729 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer I | 16/03/2022 | 197 | 136.35 | Yes | 136.35 | 09/11/2023 | 21/12/2022 | 8 | 137.75 | 89.42 | MVS
75 | KALIMPONG | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009879 | SM/10739 | New |  |  |  | 16/03/2022 | 7 | 5.37 | Yes | 5.37 |  | 26/05/2022 | 1 | 4.77 | 4.77 | MVS
76 | KALIMPONG | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | TSM/009663 | SM/10741 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 80 | 92.28 | Yes | 92.28 |  | 01/11/2023 | 4 | 85.31 | 64.7 | MVS
77 | KALIMPONG | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA | TSM/009657 | SM/10743 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 87 | 79.81 | Yes | 79.81 |  | 25/05/2022 | 1 | 76.69 | 69.1 | MVS
78 | KALIMPONG | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION | TSM/009651 | SM/10744 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-I | 17/02/2022 | 405 | 225.47 | Yes | 225.47 |  | 25/05/2022 | 1 | 335.49 | 218.46 | MVS
79 | KALIMPONG | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN | TSM/009647 | SM/10745 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 90 | 91.35 | Yes | 91.35 |  | 26/05/2022 | 1 | 88.59 | 74.93 | MVS
80 | KALIMPONG | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON | TSM/009645 | SM/10746 | New |  |  |  | 17/02/2022 | 205 | 194.83 | Yes | 194.83 |  | 25/05/2022 | 2 | 227.67 | 189.16 | MVS
81 | KALIMPONG | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK | TSM/009642 | SM/10747 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 135 | 72.57 | Yes | 72.57 |  | 30/06/2022 | 1 | 70.29 | 62.34 | MVS
82 | KALIMPONG | PWS SCHEME FROM PHENTO SOURCE TO DUKA | TSM/009637 | SM/10748 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | 17/02/2022 | 143 | 165.77 | Yes | 165.77 |  | 25/05/2022 | 1 | 155.54 | 137.75 | MVS
83 | KALIMPONG | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE | TSM/009636 | SM/10749 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 105 | 105.72 | Yes | 105.72 |  | 25/05/2022 | 1 | 117.14 | 97.81 | MVS
84 | KALIMPONG | PWS SCHEME FROM BANGLA JHORA TO JOGITAR | TSM/009634 | SM/10750 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 60 | 65.73 | Yes | 65.73 |  | 03/04/2025 | 2 | 61.21 | 12.32 | MVS
85 | KALIMPONG | PWS SCHEME FROM MANDIR KHOLA TO TANYANG | TSM/009633 | SM/10751 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | 17/02/2022 | 195 | 214.24 | Yes | 214.24 |  | 26/05/2022 | 1 | 211.87 | 175.66 | MVS
86 | KALIMPONG | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY | TSM/009632 | SM/10752 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 72 | 75.91 | Yes | 75.91 |  | 30/06/2022 | 1 | 73.59 | 62.73 | MVS
87 | KALIMPONG | PWS SCHEME FROM KHANI KHOLA TO CHUKIM | TSM/009629 | SM/10753 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | 17/02/2022 | 122 | 138.36 | Yes | 138.36 |  | 25/05/2022 | 1 | 134.25 | 117.83 | MVS
88 | KALIMPONG | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY | TSM/009628 | SM/10754 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 160 | 176.39 | Yes | 176.39 |  | 26/05/2022 | 1 | 225.8 | 157.47 | MVS
89 | KALIMPONG | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP | TSM/009627 | SM/10755 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | 17/02/2022 | 160 | 201.1 | Yes | 201.1 |  | 25/05/2022 | 1 | 199.1 | 114.88 | MVS
90 | KALIMPONG | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | TSM/010521 | SM/10787 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer III | 16/03/2022 | 613 | 975.33 | Yes | 975.33 | 22/07/2024 | 01/11/2023 | 4 | 959.8 | 876.02 | MVS
91 | KALIMPONG | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010480 | SM/10791 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 16/03/2022 | 373 | 470.31 | Yes | 470.31 |  | 30/06/2022 | 1 | 448.31 | 351.96 | MVS
92 | KALIMPONG | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010478 | SM/10792 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 16/03/2022 | 457 | 606.74 | Yes | 606.74 |  | 15/05/2023 | 2 | 587.18 | 380.26 | MVS
93 | KALIMPONG | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010482 | SM/10793 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 16/03/2022 | 342 | 731.44 | Yes | 731.44 | 23/11/2023 | 01/11/2023 | 7 | 844.99 | 586.1 | MVS
94 | KALIMPONG | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | TSM/010201 | SM/10820 | New |  |  |  | 16/03/2022 | 48 | 47.33 | Yes | 47.33 |  | 30/06/2022 | 2 | 179.68 | 2.13 | MVS
95 | KALIMPONG | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME | TSM/009677 | SM/11312 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 16/03/2022 | 98 | 100.81 | Yes | 100.81 |  | 30/06/2022 | 1 | 96.46 | 66.22 | MVS
96 | KALIMPONG | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010477 | SM/11313 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer I | 16/03/2022 | 462 | 829.3 | Yes | 829.3 | 04/09/2024 | 09/11/2023 | 7 | 763.43 | 632.69 | MVS
97 | KALIMPONG | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY | TSM/009666 | SM/11340 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 17/02/2022 | 280 | 220.09 | Yes | 220.09 |  | 30/06/2022 | 1 | 174.02 | 111.36 | MVS
98 | KALIMPONG | PWS SCHEME FROM DEORALI KHOLA TO PAKANG | TSM/009653 | SM/11341 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 17/02/2022 | 150 | 117.19 | Yes | 117.19 |  | 30/06/2022 | 1 | 113.45 | 89.7 | MVS
99 | KALIMPONG | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR | TSM/009639 | SM/11354 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | 16/03/2022 | 106 | 143.23 | Yes | 143.23 |  | 21/09/2022 | 1 | 135.69 | 126.58 | MVS
100 | KALIMPONG | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/010973 | SM/11376 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer IV | 30/03/2022 | 147 | 191.02 | Yes | 191.02 |  | 25/04/2023 | 6 | 189.16 | 110.75 | MVS
101 | KALIMPONG | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/010972 | SM/11377 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer III | 30/03/2022 | 55 | 89.16 | Yes | 89.16 |  | 21/02/2024 | 2 | 92.09 | 51.77 | MVS
102 | KALIMPONG | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/011293 | SM/11577 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-II | 30/03/2022 | 32 | 47.54 | Yes | 47.54 | 23/10/2024 | 17/12/2024 | 2 | 46.76 | 18.08 | MVS
103 | KALIMPONG | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/011291 | SM/11578 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | 30/03/2022 | 296 | 393.32 | Yes | 393.32 |  | 01/10/2024 | 2 | 374.22 | 297.56 | MVS
104 | KALIMPONG | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. | TSM/010916 | SM/11806 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 16/03/2022 | 139 | 204.57 | Yes | 204.57 |  | 25/04/2023 | 2 | 186.8 | 138.48 | MVS
105 | KALIMPONG | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/012503 | SM/11955 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/05/2022 | 221 | 242.62 | Yes | 242.62 |  | 04/11/2022 | 1 | 382.6 | 156.13 | MVS
106 | KALIMPONG | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT | TSM/012581 | SM/12180 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/05/2022 | 295 | 520.75 | Yes | 520.75 |  | 18/10/2022 | 1 | 644.39 | 372.38 | MVS
107 | KALIMPONG | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK | TSM/012042 | SM/12181 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/05/2022 | 514 | 695.67 | Yes | 695.67 |  | 17/10/2023 | 2 | 662.05 | 367.45 | MVS
108 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/012504 | SM/12629 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4 | 20/05/2022 | 588 | 752.8 | Yes | 752.8 |  | 29/09/2022 | 2 | 733.03 | 425.76 | MVS
109 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/012505 | SM/12630 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | 20/05/2022 | 530 | 939.41 | Yes | 939.41 |  | 29/09/2022 | 2 | 1395.36 | 685.16 | MVS
110 | KALIMPONG | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | TSM/012582 | SM/13602 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | 20/05/2022 | 445 | 335.49 | Yes | 335.49 |  | 09/11/2023 | 5 | 327.61 | 193 | MVS
111 | KALIMPONG | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | TSM/012584 | SM/13603 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/05/2022 | 664 | 341.66 | Yes | 341.66 | 23/11/2023 | 25/12/2023 | 4 | 333.8 | 206.13 | MVS
112 | KALIMPONG | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | TSM/011801 | SM/13604 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer III | 20/05/2022 | 1015 | 564.2 | Yes | 564.2 |  | 21/02/2024 | 6 | 567.85 | 506.59 | MVS
113 | KALIMPONG | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | TSM/012583 | SM/13605 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 20/05/2022 | 991 | 419.43 | Yes | 419.43 | 24/01/2023 | 25/12/2023 | 7 | 403.54 | 62.92 | MVS
114 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG | TSM/011686 | SM/13606 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-4 | 20/05/2022 | 692 | 427.72 | Yes | 427.72 | 10/05/2023 | 24/07/2023 | 1 | 345.67 | 0 | MVS
115 | KALIMPONG | SURUK PIPED WATER SUPPLY SCHEME | TSM/012709 | SM/13607 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 05/07/2022 | 338 | 643.2 | Yes | 643.2 | 08/12/2022 | 09/02/2023 | 3 | 640.68 | 228.14 | MVS
116 | KALIMPONG | GODAK BUSTY PIPED WATER SUPPLY SCHEME. | TSM/011867 | SM/13608 | New |  |  |  | 05/07/2022 | 136 | 356.95 | Yes | 356.95 |  | 24/07/2023 | 1 | 350.72 | 165.11 | MVS
117 | KALIMPONG | PAREN FOREST PIPED WATER SUPPLY SCHEME | TSM/011674 | SM/13609 | New |  |  |  | 05/07/2022 | 46 | 133.18 | Yes | 133.18 | 23/12/2022 | 01/11/2023 | 5 | 98.62 | 74.13 | MVS
118 | KALIMPONG | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/012753 | SM/13610 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 15/07/2022 | 309 | 260.67 | Yes | 260.67 |  | 20/01/2023 | 2 | 257.62 | 199.75 | MVS
119 | KALIMPONG | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/011907 | SM/13611 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 15/07/2022 | 383 | 648.24 | Yes | 648.24 | 08/12/2022 | 17/02/2023 | 2 | 4.72 | 445.05 | MVS
120 | KALIMPONG | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | TSM/011843 | SM/13612 | New |  |  |  | 15/07/2022 | 245 | 290.97 | Yes | 290.97 | 19/10/2022 | 01/11/2023 | 4 | 283.12 | 116.92 | MVS
121 | KALIMPONG | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | TSM/013023 | SM/13613 | New |  |  |  | 15/07/2022 | 303 | 351.35 | Yes | 351.35 | 24/01/2023 | 23/08/2023 | 3 | 351.21 | 52.73 | MVS
122 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014817 | SM/13615 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer III | 22/08/2022 | 35 | 101.26 | Yes | 101.26 | 08/12/2022 | 01/02/2023 | 2 | 147.86 | 54.49 | MVS
123 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014813 | SM/13616 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer III | 22/08/2022 | 123 | 268.04 | Yes | 268.04 | 08/12/2022 | 16/01/2024 | 3 | 254.47 | 138.6 | MVS
124 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014807 | SM/13617 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 22/08/2022 | 240 | 442.25 | Yes | 442.25 | 14/10/2022 | 28/03/2024 | 2 | 1.91 | 305.29 | MVS
125 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/014805 | SM/13621 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 22/08/2022 | 124 | 236.28 | Yes | 236.28 | 14/10/2022 | 28/11/2024 | 6 | 254.88 | 109.49 | MVS
126 | KALIMPONG | BINDU PIPED WATER SUPPLY SCHEME | TSM/013475 | SM/13622 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 22/08/2022 | 174 | 130.17 | Yes | 130.17 |  | 17/02/2023 | 1 | 1.07 | 65.67 | MVS
127 | KALIMPONG | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | TSM/014292 | SM/13953 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-4 | 22/08/2022 | 663 | 882.37 | Yes | 882.37 | 08/12/2022 | 09/02/2023 | 3 | 882.57 | 484.49 | MVS
128 | KALIMPONG | UPPER FAGU PIPED WATER SUPPLY SCHEME. | TSM/012803 | SM/13954 | New |  |  |  | 22/08/2022 | 924 | 819.76 | Yes | 819.76 | 22/02/2024 | 23/08/2023 | 4 | 808.19 | 6.33 | MVS
129 | KALIMPONG | PANKHASARI KHASMAHAL PWSS | TSM/014359 | SM/14170 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer III | 22/08/2022 | 666 | 1201.07 | Yes | 1201.07 | 23/11/2023 | 06/02/2023 | 2 | 1197.7 | 985 | MVS
130 | KALIMPONG | TODAY TANGTA KHASMAHAL PWSS | TSM/014294 | SM/14171 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | 22/08/2022 | 970 | 1635.15 | Yes | 1635.15 | 23/11/2023 | 23/08/2023 | 8 | 1601.74 | 684.52 | MVS
131 | KALIMPONG | GORUBATHAN-I PWSS | TSM/014336 | SM/14172 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4 | 22/08/2022 | 1818 | 1146.86 | Yes | 1146.86 | 27/04/2023 | 18/07/2023 | 2 | 1132.56 | 11.19 | MVS
132 | KALIMPONG | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | TSM/012585 | SM/14191 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | 20/05/2022 | 915 | 693.21 | Yes | 693.21 |  | 01/11/2023 | 4 | 678.65 | 445.04 | MVS
133 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | TSM/011803 | SM/14192 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | 20/05/2022 | 690 | 839.64 | Yes | 839.64 | 23/10/2024 | 01/11/2023 | 5 | 1226.88 | 446.69 | MVS
134 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | TSM/011800 | SM/14193 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-3 | 20/05/2022 | 724 | 701.2 | Yes | 701.2 | 12/12/2022 | 26/05/2023 | 2 | 649.45 | 4.46 | MVS
135 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | TSM/011692 | SM/14194 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-2 | 20/05/2022 | 1264 | 747.62 | Yes | 747.62 | 23/10/2024 | 12/07/2023 | 3 | 739.94 | 393.76 | MVS
136 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017393 | SM/15042 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I | Junior Engineer IV | 30/09/2022 | 161 | 213.24 | Yes | 213.24 | 02/12/2022 | 09/02/2023 | 3 | 196.09 | 96.21 | MVS
137 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | TSM/015692 | SM/15463 | New | Neorakhola W/S Mnt. Division | Assistant Engineer II | Junior Engineer III | 30/09/2022 | 165 | 226.88 | Yes | 226.88 | 02/12/2022 | 28/02/2023 | 3 | 185.29 | 176.68 | MVS
138 | KALIMPONG | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | TSM/016058 | SM/15554 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 26/09/2022 | 278 | 248.56 | Yes | 248.56 | 24/01/2023 | 29/12/2023 | 3 | 197.12 | 109.74 | MVS
139 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015717 | SM/15640 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 09/09/2022 | 685 | 497.43 | Yes | 497.43 | 02/12/2022 | 28/08/2024 | 5 | 487.78 | 261.21 | MVS
140 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015694 | SM/15641 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 09/09/2022 | 275 | 214.02 | Yes | 214.02 | 28/10/2022 | 25/12/2023 | 4 | 206.66 | 144.39 | MVS
141 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015687 | SM/15642 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 09/09/2022 | 314 | 211.63 | Yes | 211.63 | 08/12/2022 | 26/09/2024 | 4 | 210.61 | 244.46 | MVS
142 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | TSM/013305 | SM/15643 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 09/09/2022 | 169 | 300.21 | Yes | 300.21 |  | 28/02/2023 | 2 | 284.6 | 49.11 | MVS
143 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | TSM/012819 | SM/15644 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 09/09/2022 | 538 | 650.72 | Yes | 650.72 | 24/01/2023 | 01/11/2023 | 3 | 629.87 | 5.03 | MVS
144 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | TSM/012818 | SM/15645 | New | Kalimpong Division | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 09/09/2022 | 651 | 973.41 | Yes | 973.41 | 12/12/2022 | 10/05/2023 | 2 | 943.34 | 706.56 | MVS
145 | KALIMPONG | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/011490 | SM/15646 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 09/09/2022 | 171 | 226.84 | Yes | 226.84 | 02/12/2022 | 03/09/2024 | 4 | 228.92 | 99.64 | MVS
146 | KALIMPONG | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS | TSM/015530 | SM/15937 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 09/09/2022 | 782 | 657.46 | Yes | 657.46 | 23/12/2022 | 03/03/2023 | 2 | 642.32 | 485.81 | MVS
147 | KALIMPONG | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG | TSM/017451 | SM/16230 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | 28/12/2022 | 1068 | 921.36 | Yes | 921.36 | 03/09/2024 | 29/05/2023 | 3 | 919.45 | 671.1 | MVS
148 | KALIMPONG | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG | TSM/017437 | SM/16231 | New | Neorakhola W/S Mnt. Division | Assistant Engineer-III | Junior Engineer-I | 28/12/2022 | 1175 | 944.04 | Yes | 944.04 | 01/02/2023 | 26/05/2023 | 2 | 855.25 | 481.69 | MVS
149 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017434 | SM/16232 | New |  |  |  | 28/12/2022 | 206 | 380.82 | Yes | 380.82 | 08/02/2023 | 05/06/2023 | 2 | 378.2 | 1.23 | MVS
150 | KALIMPONG | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017375 | SM/16233 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2 | 28/12/2022 | 700 | 963.91 | Yes | 963.91 | 01/02/2023 | 12/07/2023 | 2 | 882.06 | 3.98 | MVS
151 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017366 | SM/16234 | New |  |  |  | 28/12/2022 | 47 | 55.28 | Yes | 55.28 | 01/02/2023 | 07/11/2023 | 4 | 55.59 | 2.71 | MVS
152 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | TSM/017340 | SM/16235 | New |  |  |  | 28/12/2022 | 199 | 233.82 | Yes | 233.82 | 01/02/2023 | 12/07/2023 | 2 | 209.91 | 70.57 | MVS
153 | KALIMPONG | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG | TSM/017521 | SM/16511 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-4 | 28/12/2022 | 1013 | 964.71 | Yes | 964.71 | 23/11/2023 | 05/06/2023 | 2 | 932.62 | 278.48 | MVS
154 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017497 | SM/16512 | New | Neorakhola W/S Mnt. Division | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | 28/12/2022 | 136 | 160.61 | Yes | 160.61 | 01/02/2023 | 01/11/2023 | 6 | 159.97 | 2.38 | MVS
155 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | TSM/017496 | SM/16513 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | 28/12/2022 | 369 | 304 | Yes | 304 | 01/02/2023 | 01/11/2023 | 5 | 348.22 | 89.89 | MVS
156 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017347 | SM/16514 | New | Kalimpong Division | Assistant Engineer-I | Junior Engineer-3 | 28/12/2022 | 538 | 896.34 | Yes | 896.34 | 01/02/2023 | 05/06/2023 | 2 | 879.3 | 226.15 | MVS
157 | KALIMPONG | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017321 | SM/16649 | New | Kalimpong Division | Assistant Engineer-III | Junior Engineer-3 | 28/12/2022 | 351 | 437.66 | Yes | 437.66 | 01/02/2023 | 01/11/2023 | 5 | 382.4 | 3.41 | MVS
158 | KALIMPONG | PAGRAN BONG KHASMAHAL PWSS | TSM/015516 | SM/16854 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2 | 28/12/2022 | 187 | 473.77 | Yes | 473.77 | 23/11/2023 | 01/11/2023 | 4 | 391.06 | 319.07 | MVS
159 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015695 | SM/18247 | New |  |  |  | 28/12/2022 | 946 | 1350.54 | Yes | 1350.54 | 12/12/2023 | 18/07/2023 | 2 | 1232.78 | 4.38 | MVS
160 | KALIMPONG | PATEN GODAK KHASMAHAL PWSS | TSM/013333 | SM/18255 | New |  |  |  | 15/07/2022 | 874 | 1128.06 | Yes | 1128.06 |  | 23/08/2023 | 4 | 1123.22 | 345.78 | MVS
161 | KALIMPONG | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | TSM/012509 | SM/18322 | New |  |  |  | 20/05/2022 | 1196 | 1040.03 | Yes | 1040.03 |  | 18/07/2023 | 4 | 928 | 7.15 | MVS
162 | KALIMPONG | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | TSM/011586 | SM/18415 | New | Kalimpong Division | Assistant Engineer-IV | Junior Engineer-2 | 05/07/2022 | 475 | 1069.7 | Yes | 1069.7 | 24/01/2023 | 17/08/2023 | 2 | 957.24 | 309.14 | MVS
163 | KALIMPONG | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | TSM/020254 | SM/18442 | Augmentation |  |  |  | 28/12/2022 | 3573 | 3858.84 | Yes | 3858.84 | 29/08/2024 | 30/09/2024 | 3 | 3834.06 | 472.55 | MVS
164 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | TSM/020226 | SM/18443 | New |  |  |  | 28/12/2022 | 3512 | 3488.92 | Yes | 3488.92 | 13/06/2024 | 18/06/2024 | 22 | 2986.62 | 396.07 | MVS
165 | KALIMPONG | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | TSM/012889 | SM/18589 | New | Kalimpong Division | Assistant Engineer-II | Junior Engineer-4 | 28/12/2022 | 1130 | 1104.14 | Yes | 1104.14 | 11/02/2023 | 07/08/2023 | 1 | 1811.26 | 759.43 | MVS
166 | KALIMPONG | RANGO FOREST PWSS | TSM/013119 | SM/18823 | New |  |  |  | 15/07/2022 | 1892 | 1664.29 | Yes | 1664.29 | 24/01/2023 | 05/10/2023 | 1 | 11.65 | 392.88 | MVS
167 | KALIMPONG | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | TSM/013403 | SM/19112 | New |  |  |  | 15/07/2022 | 784 | 1414.95 | Yes | 1414.95 | 14/12/2022 | 03/01/2024 | 3 | 1408.44 | 4.82 | MVS
168 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | TSM/013034 | SM/19176 | New |  |  |  | 22/08/2022 | 1749 | 2560.38 | Yes | 2560.38 | 28/02/2023 | 03/04/2025 | 9 | 2543.15 | 123.67 | MVS
Total | [9 empty] | 66309 | 72000.72 |  | 72000.72 |  |  | 515 | 67404.99 | 32300.3