## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | PASCHIM BARDHAMAN | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | TSM/005580 | SM/07391 | Retrofitting |  |  |  | 28/08/2020 | 36446 | 1841 | Yes | 1841 |  | 29/04/2021 | 150 | 2953.42 | 1348.54 | MVS
2 | PASCHIM BARDHAMAN | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | TSM/005581 | SM/07392 | Retrofitting | RCFA Division I | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | 28/08/2020 | 9726 | 627.42 | Yes | 627.42 |  | 25/01/2024 | 72 | 647.42 | 237.27 | MVS
3 | PASCHIM BARDHAMAN | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | TSM/006413 | SM/07518 | Retrofitting |  |  |  | 04/12/2020 | 0 | 96.32 | Yes | 96.32 | 22/06/2022 | 24/05/2021 | 17 | 106.6 | 0 | MVS
4 | PASCHIM BARDHAMAN | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | TSM/006401 | SM/07519 | Retrofitting |  |  |  | 04/12/2020 | 1880 | 97.53 | Yes | 97.53 | 04/01/2023 | 14/11/2024 | 21 | 89.54 | 0 | MVS
5 | PASCHIM BARDHAMAN | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | TSM/006407 | SM/07524 | Retrofitting |  |  |  | 04/12/2020 | 1686 | 86.82 | Yes | 86.82 | 22/06/2022 | 29/04/2021 | 25 | 140.17 | 0 | MVS
6 | PASCHIM BARDHAMAN | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | TSM/006380 | SM/07558 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 04/12/2020 | 2015 | 94.74 | Yes | 94.74 |  | 07/06/2021 | 8 | 91.04 | 57.49 | MVS
7 | PASCHIM BARDHAMAN | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | TSM/006381 | SM/07559 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 04/12/2020 | 2015 | 94.74 | Yes | 94.74 |  | 07/06/2021 | 6 | 111.5 | 32.96 | MVS
8 | PASCHIM BARDHAMAN | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | TSM/006382 | SM/07560 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 04/12/2020 | 2014 | 94.68 | Yes | 94.68 |  | 07/06/2021 | 7 | 90.19 | 58.78 | MVS
9 | PASCHIM BARDHAMAN | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | TSM/006383 | SM/07561 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 04/12/2020 | 2014 | 94.68 | Yes | 94.68 |  | 07/06/2021 | 11 | 89.84 | 34.96 | MVS
10 | PASCHIM BARDHAMAN | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District | TSM/006391 | SM/07562 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 04/12/2020 | 1125 | 62.01 | Yes | 62.01 |  | 07/06/2021 | 3 | 63.09 | 0 | MVS
11 | PASCHIM BARDHAMAN | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | TSM/005153 | SM/08877 | New |  |  |  | 04/12/2020 | 7821 | 1167.42 | Yes | 1167.42 | 17/03/2025 | 10/05/2022 | 35 | 1213.11 | 0 | MVS
12 | PASCHIM BARDHAMAN | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | TSM/008245 | SM/09059 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 19/08/2021 | 4170 | 244.75 | Yes | 244.75 |  | 13/06/2024 | 29 | 236.55 | 0 | MVS
13 | PASCHIM BARDHAMAN | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | TSM/008246 | SM/09060 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 19/08/2021 | 4170 | 244.75 | Yes | 244.75 |  | 13/06/2024 | 24 | 255.6 | 0 | MVS
14 | PASCHIM BARDHAMAN | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | TSM/008247 | SM/09061 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 19/08/2021 | 850 | 48.52 | Yes | 48.52 | 28/06/2022 | 14/11/2024 | 5 | 26.7 | 0 | MVS
15 | PASCHIM BARDHAMAN | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | TSM/008248 | SM/09062 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 19/08/2021 | 1555 | 82.87 | Yes | 82.87 |  | 05/09/2023 | 9 | 103.61 | 0 | MVS
16 | PASCHIM BARDHAMAN | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | TSM/008249 | SM/09063 | Retrofitting | RCFA Division I | Assistant Engineer 1 | Junior Engineer | 19/08/2021 | 477 | 29.57 | Yes | 29.57 |  | 19/07/2024 | 6 | 30.48 | 0 | MVS
17 | PASCHIM BARDHAMAN | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | TSM/008250 | SM/09064 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 19/08/2021 | 3371 | 169.66 | Yes | 169.66 | 26/04/2022 | 08/05/2023 | 6 | 136.76 | 0 | MVS
18 | PASCHIM BARDHAMAN | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | TSM/008251 | SM/09065 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 19/08/2021 | 1613 | 92.6 | Yes | 92.6 | 23/12/2022 | 30/08/2024 | 5 | 74.56 | 0 | MVS
19 | PASCHIM BARDHAMAN | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | TSM/008889 | SM/09387 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 29/09/2021 | 3720 | 188.03 | Yes | 188.03 |  | 11/07/2024 | 20 | 244.37 | 0 | MVS
20 | PASCHIM BARDHAMAN | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | TSM/008888 | SM/09388 | Retrofitting | RCFA Division I | Assistant Engineer 2 |  | 29/09/2021 | 4045 | 220.61 | Yes | 220.61 |  | 03/07/2024 | 27 | 252.52 | 0 | MVS
21 | PASCHIM BARDHAMAN | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | TSM/008884 | SM/09389 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 29/09/2021 | 2400 | 111 | Yes | 111 | 02/08/2022 | 23/08/2024 | 16 | 116.55 | 0 | MVS
22 | PASCHIM BARDHAMAN | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | TSM/008345 | SM/09875 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 19/08/2021 | 0 | 1310.24 | Yes | 1310.24 | 17/03/2025 | 07/08/2023 | 54 | 1231.08 | 0 | MVS
23 | PASCHIM BARDHAMAN | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | TSM/004718 | SM/09916 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | 19/08/2021 | 30062 | 11874.12 | Yes | 11874.12 | 17/03/2025 | 03/05/2023 | 169 | 10652.58 | 0 | MVS
24 | PASCHIM BARDHAMAN | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | TSM/009668 | SM/10144 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I | Junior Engineer-4 | 16/12/2021 | 0 | 25.6 | Yes | 25.6 |  | 11/02/2022 | 9 | 26.31 | 0 | MVS
25 | PASCHIM BARDHAMAN | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | TSM/009727 | SM/10165 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | 16/12/2021 | 3513 | 971.48 | Yes | 971.48 | 26/07/2024 | 06/06/2024 | 23 | 924.48 | 0 | MVS
26 | PASCHIM BARDHAMAN | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | TSM/009032 | SM/10203 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/12/2021 | 0 | 943.11 | Yes | 943.11 | 17/01/2025 | 20/05/2024 | 44 | 908.75 | 0 | MVS
27 | PASCHIM BARDHAMAN | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) | TSM/009656 | SM/10208 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/12/2021 | 2538 | 700.46 | Yes | 700.46 | 17/03/2025 | 15/03/2023 | 47 | 748.19 | 0 | MVS
28 | PASCHIM BARDHAMAN | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | TSM/009821 | SM/10209 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/12/2021 | 2450 | 489.84 | Yes | 489.84 | 06/03/2025 | 11/09/2024 | 30 | 541.45 | 0 | MVS
29 | PASCHIM BARDHAMAN | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | TSM/009822 | SM/10210 | Augmentation |  |  |  | 16/12/2021 | 3113 | 780.77 | Yes | 780.77 | 25/06/2024 | 18/05/2022 | 35 | 867.87 | 0 | MVS
30 | PASCHIM BARDHAMAN | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | TSM/009659 | SM/10211 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/12/2021 | 3815 | 811.61 | Yes | 811.61 | 06/03/2025 | 30/11/2023 | 30 | 786.23 | 0 | MVS
31 | PASCHIM BARDHAMAN | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) | TSM/009820 | SM/10212 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/12/2021 | 2984 | 663.97 | Yes | 663.97 | 17/03/2025 | 24/07/2023 | 26 | 682.49 | 0 | MVS
32 | PASCHIM BARDHAMAN | Telipara Piped Water Supply Scheme. | TSM/004035 | SM/10311 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/12/2021 | 7427 | 389.8 | Yes | 389.8 | 17/03/2025 | 17/03/2023 | 15 | 439.72 | 0 | MVS
33 | PASCHIM BARDHAMAN | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | TSM/010518 | SM/10605 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | 16/03/2022 | 2994 | 608.44 | Yes | 608.44 | 03/03/2025 | 13/05/2022 | 17 | 571.8 | 0 | MVS
34 | PASCHIM BARDHAMAN | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | TSM/009730 | SM/10640 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 17/02/2022 | 0 | 866.51 | Yes | 866.51 | 17/03/2025 | 26/04/2023 | 11 | 619.49 | 0 | MVS
35 | PASCHIM BARDHAMAN | Augmentation of Ondal (Phase-I) Water Supply Scheme | TSM/010055 | SM/10641 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | 17/02/2022 | 5205 | 887.89 | Yes | 887.89 | 06/03/2025 | 12/04/2023 | 16 | 908.64 | 0 | MVS
36 | PASCHIM BARDHAMAN | Augmentation of Roshna Piped Water Supply Scheme . | TSM/010052 | SM/10642 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | 17/02/2022 | 1250 | 844.67 | Yes | 844.67 | 21/10/2024 | 21/06/2024 | 30 | 779.75 | 0 | MVS
37 | PASCHIM BARDHAMAN | Augmentation of Jamgram Piped Water Supply Scheme. | TSM/010051 | SM/10643 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 17/02/2022 | 1738 | 774.12 | Yes | 774.12 | 09/02/2024 | 12/04/2023 | 27 | 757.02 | 0 | MVS
38 | PASCHIM BARDHAMAN | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | TSM/009728 | SM/10844 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | 17/02/2022 | 2435 | 945.42 | Yes | 945.42 | 28/02/2025 | 08/01/2021 | 16 | 721.15 | 0 | MVS
39 | PASCHIM BARDHAMAN | Augmentation of Madantor Water Supply Scheme | TSM/010054 | SM/10845 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | 17/02/2022 | 1125 | 587.44 | Yes | 587.44 | 17/03/2025 | 27/08/2024 | 17 | 579 | 0 | MVS
40 | PASCHIM BARDHAMAN | KOTALPUKUR PIPED WATER SUPPLY SCHEME | TSM/009500 | SM/10996 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 173 | 54.17 | Yes | 54.17 | 22/06/2022 | 17/05/2022 | 2 | 44.06 | 0 | MVS
41 | PASCHIM BARDHAMAN | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. | TSM/009281 | SM/10998 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 126 | 41.17 | Yes | 41.17 | 22/06/2022 | 15/03/2023 | 2 | 26.92 | 0 | MVS
42 | PASCHIM BARDHAMAN | DHOBARU PIPED WATER SUPPLY SCHEME | TSM/009279 | SM/10999 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 197 | 57.63 | Yes | 57.63 | 22/06/2022 | 17/03/2023 | 2 | 45.57 | 0 | MVS
43 | PASCHIM BARDHAMAN | Augmentation of Sub-Surface water based Churulia PWSS. | TSM/009729 | SM/11205 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | 27/01/2022 | 555 | 996.67 | Yes | 996.67 | 17/03/2025 | 11/04/2023 | 15 | 1191.84 | 0 | MVS
44 | PASCHIM BARDHAMAN | BANAGRAM PIPED WATER SUPPLY SCHEME | TSM/009278 | SM/11223 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 112 | 34.78 | Yes | 34.78 | 04/01/2023 | 18/05/2022 | 1 | 22.89 | 0 | MVS
45 | PASCHIM BARDHAMAN | BIRUDIHA PIPED WATER SUPPLY SCHEME | TSM/009284 | SM/11224 | New | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | 17/02/2022 | 1697 | 633.08 | Yes | 633.08 | 01/02/2024 | 01/06/2023 | 6 | 592.44 | 0 | MVS
46 | PASCHIM BARDHAMAN | BAMUNARA PIPED WATER SUPPLY SCHEME. | TSM/009558 | SM/11227 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | 16/03/2022 | 5234 | 773.34 | Yes | 773.34 | 28/02/2025 | 24/07/2023 | 8 | 765.32 | 0 | MVS
47 | PASCHIM BARDHAMAN | Shyambazar Piped water Supply Scheme | TSM/010261 | SM/11228 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/03/2022 | 882 | 309.98 | Yes | 309.98 | 25/06/2024 | 15/03/2023 | 9 | 280.29 | 0 | MVS
48 | PASCHIM BARDHAMAN | DANDESHWAR PIPED WATER SUPPLY SCHEME. | TSM/009556 | SM/11282 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/03/2022 | 703 | 254.22 | Yes | 254.22 | 24/11/2022 | 01/06/2023 | 8 | 210.01 | 0 | MVS
49 | PASCHIM BARDHAMAN | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | TSM/009488 | SM/11454 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-2 | 17/02/2022 | 12405 | 2799.63 | Yes | 2799.63 | 17/03/2025 | 14/06/2024 | 45 | 2643.9 | 0 | MVS
50 | PASCHIM BARDHAMAN | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | TSM/011412 | SM/11575 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | 30/03/2022 | 4240 | 661.28 | Yes | 661.28 | 17/03/2025 | 26/09/2024 | 16 | 527.12 | 0 | MVS
51 | PASCHIM BARDHAMAN | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | TSM/011404 | SM/11576 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 30/03/2022 | 3367 | 808.08 | Yes | 808.08 | 06/03/2025 | 26/09/2024 | 17 | 1048.61 | 0 | MVS
52 | PASCHIM BARDHAMAN | NAPARA PIPED WATER SUPPLY SCHEME. | TSM/009283 | SM/11932 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 2252 | 657.52 | Yes | 657.52 | 17/03/2025 | 15/03/2023 | 8 | 555.6 | 0 | MVS
53 | PASCHIM BARDHAMAN | JATGARIA PIPED WATER SUPPLY SCHEME. | TSM/009285 | SM/11933 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | 17/02/2022 | 762 | 275.4 | Yes | 275.4 | 29/07/2024 | 08/06/2023 | 7 | 238.83 | 0 | MVS
54 | PASCHIM BARDHAMAN | GARADAHA PIPED WATER SUPPLY SCHEME. | TSM/009280 | SM/11934 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 171 | 51.33 | Yes | 51.33 | 04/01/2023 | 15/03/2023 | 2 | 44.26 | 0 | MVS
55 | PASCHIM BARDHAMAN | AMLAJORA PIPED WATER SUPPLY SCHEME | TSM/009286 | SM/11937 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 17/02/2022 | 1738 | 529.96 | Yes | 529.96 | 17/03/2025 | 24/07/2023 | 10 | 505.42 | 0 | MVS
56 | PASCHIM BARDHAMAN | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | TSM/012742 | SM/11986 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 20/05/2022 | 5048 | 997.15 | Yes | 997.15 | 28/02/2025 | 27/08/2024 | 18 | 940.29 | 0 | MVS
57 | PASCHIM BARDHAMAN | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE | TSM/011401 | SM/12024 | Retrofitting | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 05/07/2022 | 3551 | 365.56 | Yes | 365.56 | 06/03/2025 | 17/11/2022 | 4 | 452.18 | 0 | MVS
58 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | TSM/014345 | SM/12025 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 3450 | 901.05 | Yes | 901.05 | 28/02/2025 | 25/04/2023 | 10 | 907.91 | 0 | MVS
59 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | TSM/014346 | SM/12026 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 4411 | 910.23 | Yes | 910.23 | 28/02/2025 | 16/05/2023 | 11 | 894.5 | 0 | MVS
60 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | TSM/014347 | SM/12027 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 3468 | 818.76 | Yes | 818.76 | 17/03/2025 | 05/12/2024 | 13 | 814.51 | 0 | MVS
61 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | TSM/014348 | SM/12028 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 1976 | 530.12 | Yes | 530.12 | 04/03/2025 | 29/10/2024 | 16 | 533.64 | 0 | MVS
62 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | TSM/014349 | SM/12029 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 2623 | 771.55 | Yes | 771.55 | 25/06/2024 | 03/05/2023 | 19 | 829.32 | 0 | MVS
63 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | TSM/014350 | SM/12030 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 4933 | 991.93 | Yes | 991.93 | 26/07/2024 | 29/08/2023 | 7 | 1016.31 | 0 | MVS
64 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | TSM/014351 | SM/12031 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 2558 | 481.52 | Yes | 481.52 | 27/02/2024 | 28/10/2024 | 9 | 424.22 | 0 | MVS
65 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | TSM/014352 | SM/12032 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 15/07/2022 | 4129 | 731.25 | Yes | 731.25 | 05/08/2024 | 20/05/2024 | 17 | 404.84 | 0 | MVS
66 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | TSM/014353 | SM/12033 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 15/07/2022 | 2865 | 809.92 | Yes | 809.92 | 29/12/2022 | 29/08/2023 | 9 | 813.79 | 0 | MVS
67 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | TSM/014354 | SM/12039 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 15/07/2022 | 2426 | 587.31 | Yes | 587.31 | 05/08/2024 | 16/05/2023 | 9 | 550.31 | 0 | MVS
68 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | TSM/014355 | SM/12040 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 3700 | 568.7 | Yes | 568.7 | 29/09/2022 | 18/07/2024 | 10 | 553.37 | 0 | MVS
69 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | TSM/014356 | SM/12041 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 6807 | 896.96 | Yes | 896.96 | 18/07/2024 | 20/05/2024 | 11 | 648.32 | 0 | MVS
70 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | TSM/014357 | SM/12042 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 15/07/2022 | 4861 | 831.03 | Yes | 831.03 | 04/01/2024 | 25/04/2023 | 8 | 791.28 | 0 | MVS
71 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | TSM/014889 | SM/12210 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 2833 | 610.16 | Yes | 610.16 | 06/03/2025 | 20/05/2024 | 24 | 621.69 | 0 | MVS
72 | PASCHIM BARDHAMAN | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | TSM/014885 | SM/12215 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 2548 | 898.82 | Yes | 898.82 | 16/02/2024 | 22/11/2023 | 35 | 822.37 | 0 | MVS
73 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. | TSM/014880 | SM/12216 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 22/08/2022 | 1685 | 868.69 | Yes | 868.69 | 18/07/2024 | 25/04/2023 | 10 | 855.96 | 0 | MVS
74 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. | TSM/014890 | SM/12218 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 1081 | 878.95 | Yes | 878.95 | 05/08/2024 | 21/06/2024 | 20 | 883.76 | 0 | MVS
75 | PASCHIM BARDHAMAN | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | TSM/014376 | SM/12219 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 22/08/2022 | 2886 | 681.87 | Yes | 681.87 | 06/03/2025 | 25/04/2023 | 17 | 650.22 | 0 | MVS
76 | PASCHIM BARDHAMAN | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | TSM/014878 | SM/12220 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 1364 | 754.7 | Yes | 754.7 | 28/02/2025 | 09/06/2023 | 14 | 954.61 | 0 | MVS
77 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | TSM/013220 | SM/12221 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 22/08/2022 | 2224 | 462 | Yes | 462 | 30/12/2022 | 16/05/2023 | 5 | 478.44 | 0 | MVS
78 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone - 9) | TSM/013219 | SM/12222 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 22/08/2022 | 2096 | 579.22 | Yes | 579.22 | 28/02/2025 | 20/05/2024 | 19 | 579.44 | 0 | MVS
79 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | TSM/012791 | SM/12223 | Augmentation | RCFA Division I | Assistant Engineer 2 |  | 22/08/2022 | 2270 | 833.27 | Yes | 833.27 | 06/03/2025 | 18/04/2024 | 17 | 774.94 | 0 | MVS
80 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | TSM/012768 | SM/12224 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 181 | 689.44 | Yes | 689.44 | 28/02/2025 | 25/04/2023 | 14 | 606.85 | 0 | MVS
81 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | TSM/013221 | SM/12225 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 1992 | 424.86 | Yes | 424.86 | 05/08/2024 | 04/04/2023 | 6 | 408.99 | 0 | MVS
82 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman | TSM/012792 | SM/12226 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 2324 | 440.82 | Yes | 440.82 | 06/03/2025 | 18/07/2024 | 10 | 426.66 | 0 | MVS
83 | PASCHIM BARDHAMAN | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | TSM/012782 | SM/12227 | Augmentation | RCFA Division I | Assistant Engineer 2 | Junior Engineer | 22/08/2022 | 1237 | 543.54 | Yes | 543.54 | 05/08/2024 | 29/11/2023 | 15 | 529.02 | 0 | MVS
84 | PASCHIM BARDHAMAN | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | TSM/009489 | SM/12726 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-5 | 17/02/2022 | 13807 | 2832.34 | Yes | 2832.34 | 17/03/2025 | 06/09/2024 | 70 | 2406.02 | 0 | MVS
85 | PASCHIM BARDHAMAN | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman | TSM/013416 | SM/13416 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | 09/09/2022 | 861 | 909.45 | Yes | 909.45 | 06/03/2025 | 25/04/2023 | 19 | 837.44 | 0 | MVS
86 | PASCHIM BARDHAMAN | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | TSM/011402 | SM/13418 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 09/09/2022 | 5982 | 904.57 | Yes | 904.57 | 17/03/2025 | 09/06/2023 | 19 | 989.19 | 0 | MVS
87 | PASCHIM BARDHAMAN | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | TSM/011036 | SM/13685 | Retrofitting |  |  |  | 09/09/2022 | 1404 | 137.13 | Yes | 137.13 | 01/05/2023 | 03/05/2023 | 11 | 122.98 | 0 | MVS
88 | PASCHIM BARDHAMAN | Ground water based mini piped water supply scheme (Max 100 House Hold) for Kotalpukur ,G.P-Bankati,Block-Kanksa ,Dist-Paschim Bardhaman under Durgapur W/S Division,PHE Dte (Part-F) | TSM/014871 | SM/13861 | New |  |  |  | 26/09/2022 | 60 | 41.75 | Yes | 41.75 | 07/09/2022 | 01/08/2022 | 1 | 41.75 | 0 | MVS
89 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Bhadrapur ,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-B) | TSM/014849 | SM/13862 | New |  |  |  | 26/09/2022 | 20 | 33.6 | Yes | 33.6 | 07/09/2022 | 01/08/2022 | 1 | 28.9 | 0 | MVS
90 | PASCHIM BARDHAMAN | Ground water based mini piped W/s Scheme (Max 100 House Hold)for Gourangapur Village,Panchayet-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD,PHE Dte (Part-D) | TSM/014846 | SM/13863 | New |  |  |  | 26/09/2022 | 25 | 34.64 | Yes | 34.64 | 07/09/2022 | 01/08/2022 | 1 | 34.64 | 0 | MVS
91 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Kendula ,G.P-Pratabpur,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-C) | TSM/014848 | SM/13864 | New |  |  |  | 26/09/2022 | 53 | 40.28 | Yes | 40.28 | 07/09/2022 | 01/08/2022 | 1 | 40.28 | 0 | MVS
92 | PASCHIM BARDHAMAN | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) | TSM/014844 | SM/13866 | New |  |  |  | 26/09/2022 | 99 | 47.8 | Yes | 47.8 | 07/09/2022 | 01/08/2022 | 1 | 47.8 | 0 | MVS
93 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Maheshpur,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-A) | TSM/011035 | SM/13879 | New |  |  |  | 26/09/2022 | 68 | 42.44 | Yes | 42.44 | 07/09/2022 | 01/08/2022 | 1 | 37.9 | 0 | MVS
94 | PASCHIM BARDHAMAN | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | TSM/015956 | SM/14888 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 26/09/2022 | 0 | 882.66 | Yes | 882.66 | 03/03/2025 | 27/08/2024 | 9 | 719.65 | 0 | MVS
95 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017220 | SM/15639 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/11/2022 | 1738 | 989.75 | Yes | 989.75 | 17/03/2025 | 24/07/2024 | 12 | 909.95 | 0 | MVS
96 | PASCHIM BARDHAMAN | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | TSM/018723 | SM/15654 | Augmentation | Asansol Mechanical Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | 16/11/2022 | 2479 | 988.24 | Yes | 988.24 | 12/02/2025 | 25/04/2023 | 16 | 987.73 | 0 | MVS
97 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA | TSM/017221 | SM/15657 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I | Junior Engineer-3 | 16/11/2022 | 2092 | 929.97 | Yes | 929.97 | 06/03/2025 | 14/11/2024 | 11 | 695.96 | 0 | MVS
98 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017285 | SM/15659 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/11/2022 | 350 | 157.71 | Yes | 157.71 | 01/02/2024 | 15/05/2023 | 4 | 118.24 | 0 | MVS
99 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017286 | SM/15663 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/11/2022 | 574 | 227.43 | Yes | 227.43 | 28/11/2024 | 17/03/2023 | 6 | 175.3 | 0 | MVS
100 | PASCHIM BARDHAMAN | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | TSM/018322 | SM/15666 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-5 | 16/11/2022 | 2454 | 905.76 | Yes | 905.76 | 04/03/2025 | 15/03/2024 | 18 | 841.79 | 0 | MVS
101 | PASCHIM BARDHAMAN | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | TSM/018376 | SM/16249 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-5 | 28/12/2022 | 943 | 579.21 | Yes | 579.21 | 30/08/2024 | 01/12/2023 | 28 | 546.53 | 0 | MVS
102 | PASCHIM BARDHAMAN | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017281 | SM/16250 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 28/12/2022 | 8674 | 638.71 | Yes | 638.71 | 01/02/2024 | 18/06/2025 | 16 | 527.53 | 0 | MVS
103 | PASCHIM BARDHAMAN | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | TSM/020338 | SM/16775 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-2 | 28/12/2022 | 0 | 198.21 | Yes | 198.21 | 29/08/2024 | 04/04/2023 | 4 | 190.97 | 0 | MVS
104 | PASCHIM BARDHAMAN | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | TSM/020344 | SM/16777 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-5 | 28/12/2022 | 0 | 204.12 | Yes | 204.12 | 02/02/2023 | 19/05/2023 | 3 | 201.51 | 0 | MVS
105 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017283 | SM/16900 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 28/12/2022 | 252 | 98.83 | Yes | 98.83 | 03/10/2024 | 15/05/2023 | 4 | 115.42 | 0 | MVS
106 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017279 | SM/16901 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 28/12/2022 | 769 | 340.79 | Yes | 340.79 | 17/03/2025 | 24/05/2023 | 4 | 295.49 | 0 | MVS
107 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017277 | SM/16902 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 28/12/2022 | 262 | 94.57 | Yes | 94.57 | 01/02/2024 | 31/01/2024 | 4 | 82.66 | 0 | MVS
108 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017275 | SM/16903 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 28/12/2022 | 171 | 64.9 | Yes | 64.9 | 01/02/2024 | 18/05/2023 | 4 | 60.39 | 0 | MVS
109 | PASCHIM BARDHAMAN | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | TSM/018422 | SM/18417 | New | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-5 | 28/12/2022 | 2776 | 2340.61 | Yes | 2340.61 | 03/03/2025 | 15/03/2024 | 23 | 2230.16 | 0 | MVS
110 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017310 | SM/18467 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | 16/11/2022 | 6356 | 1401.03 | Yes | 1401.03 | 30/08/2024 | 23/12/2024 | 19 | 1233.87 | 0 | MVS
111 | PASCHIM BARDHAMAN | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | TSM/018764 | SM/18468 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I | Junior Engineer-3 | 16/11/2022 | 0 | 5020.98 | Yes | 5020.98 | 03/10/2024 | 09/09/2024 | 80 | 3958.46 | 0 | MVS
112 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/018199 | SM/18469 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 16/11/2022 | 7434 | 2403.3 | Yes | 2403.3 | 17/03/2025 | 04/07/2024 | 38 | 1768.61 | 0 | MVS
113 | PASCHIM BARDHAMAN | Ground water based mini piped water supply scheme (Max 100 House Hold) for Pathardiha,GP-Gopalpur,Block -Kanksa,Dist-Paschim Bardhaman under Durgapur W/s Division,PHE Dte (Part-G) | TSM/014872 | SM/18745 | New |  |  |  | 26/09/2022 | 0 | 39.36 | Yes | 39.36 | 07/09/2022 | 01/08/2022 | 1 | 39.36 | 0 | MVS
114 | PASCHIM BARDHAMAN | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | TSM/017799 | SM/18769 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I | Junior Engineer-4 | 16/11/2022 | 0 | 46405.37 | Yes | 46405.37 | 28/02/2025 | 05/09/2024 | 49 | 9744.6 | 0 | MVS
115 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017278 | SM/18824 | Augmentation | Asansol Mechanical Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | 28/12/2022 | 1916 | 860 | Yes | 860 | 17/01/2025 | 16/03/2024 | 6 | 557.21 | 0 | MVS
116 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017244 | SM/18825 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | 28/12/2022 | 683 | 306.19 | Yes | 306.19 | 30/08/2024 | 12/11/2024 | 6 | 296.74 | 0 | MVS
117 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017280 | SM/18826 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 28/12/2022 | 1034 | 460.11 | Yes | 460.11 | 17/01/2025 | 27/08/2024 | 7 | 357.48 | 0 | MVS
118 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020573 | SM/18877 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 10/03/2023 | 1986 | 313.27 | Yes | 313.27 | 17/03/2025 | 30/09/2024 | 6 | 255.15 | 0 | MVS
119 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020579 | SM/18886 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 10/03/2023 | 1888 | 350.95 | Yes | 350.95 | 06/03/2025 | 20/09/2023 | 5 | 290.97 | 0 | MVS
120 | PASCHIM BARDHAMAN | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020576 | SM/18887 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 10/03/2023 | 1377 | 220.53 | Yes | 220.53 | 17/03/2025 | 16/03/2024 | 2 | 18.75 | 0 | MVS
121 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020575 | SM/18888 | Augmentation | Asansol Mechanical Division | Assistant Engineer-II | Junior Engineer-3 | 10/03/2023 | 0 | 175.3 | Yes | 175.3 | 06/03/2025 | 18/06/2025 | 4 | 57.15 | 0 | MVS
122 | PASCHIM BARDHAMAN | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | TSM/020567 | SM/18889 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | 10/03/2023 | 0 | 250.38 | Yes | 250.38 | 03/10/2024 | 24/04/2024 | 5 | 185.81 | 0 | MVS
123 | PASCHIM BARDHAMAN | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JEMUA, UNDER DURGAPUR W/S DIVISION , BLOCK : DURGAPUR FARIDPUR, DISTRICT : PASCHIM BARDDHAMAN | TSM/020574 | SM/18890 | Augmentation |  |  |  | 10/03/2023 | 1657 | 219.38 | Yes | 219.38 | 12/03/2024 | 11/04/2023 | 1 | 31.1 | 0 | MVS
124 | PASCHIM BARDHAMAN | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | TSM/020833 | SM/18891 | Augmentation | Asansol Mechanical Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | 10/03/2023 | 0 | 941.12 | Yes | 941.12 | 03/03/2025 | 16/04/2024 | 27 | 508.31 | 0 | MVS
Total | [9 empty] | 350147 | 133095.55 |  | 133095.55 |  |  | 2200 | 90320.15 | 1770