## F3- Scheme wise Financial Prog
F3- Scheme wise Financial Progress (Rs. in Crore)
Sl No. | District | No. of Schemes | Sanctioned Cost |  |  | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure
|  |  | Civil | Mech./ Elec. | Total | Civil | Mech./ Elec. | Resource | Central Drilling | Total | Civil | Mech./ Elec. | Resource | Central Drilling | Total
1 | ALIPURDUAR | 223 | 819.57 | 77.1 | 896.67 | 421.16 | 34.16 | 39.94 | 0 | 495.26 | 419.26 | 35.7 | 39.94 | 0 | 494.89 | 55.19
2 | BANKURA | 966 | 2071.27 | 311.55 | 2382.82 | 723.99 | 82.83 | 127.97 | 0 | 934.79 | 729.31 | 82.69 | 127.97 | 0 | 939.96 | 39.45
3 | BIRBHUM | 384 | 2337.04 | 207.29 | 2544.33 | 580.97 | 71.63 | 186.53 | 11.94 | 851.06 | 580.89 | 71.87 | 186.53 | 11.94 | 851.22 | 33.46
4 | COOCHBEHAR | 319 | 1813.84 | 122.65 | 1936.49 | 1051.07 | 52.36 | 76.25 | 0.19 | 1179.88 | 1045.23 | 55.07 | 76.25 | 0.19 | 1176.74 | 60.77
5 | DAKSHIN DINAJPUR | 308 | 768.17 | 83.32 | 851.49 | 235.55 | 18.81 | 50.57 | 3.27 | 308.2 | 234.86 | 19.86 | 50.57 | 3.27 | 308.57 | 36.24
6 | DARJEELING | 403 | 2477.48 | 73.83 | 2551.31 | 1056.04 | 22.03 | 37.77 | 0.92 | 1116.76 | 1054.61 | 22.58 | 37.77 | 0.92 | 1115.88 | 43.74
7 | HOOGHLY | 498 | 2222.7 | 197.67 | 2420.37 | 844.03 | 78.87 | 105.75 | 6.88 | 1035.54 | 837.41 | 80.1 | 105.75 | 6.88 | 1030.15 | 42.56
8 | HOWRAH | 163 | 1751.27 | 174.07 | 1925.34 | 417.26 | 30.41 | 105.51 | 1.4 | 554.57 | 418.52 | 30.98 | 105.51 | 1.4 | 556.41 | 28.9
9 | JALPAIGURI | 250 | 1082.39 | 132.2 | 1214.59 | 453.36 | 58.07 | 64.23 | 1.26 | 576.92 | 439.57 | 60.01 | 64.23 | 1.26 | 565.06 | 46.52
10 | JHARGRAM | 205 | 878.09 | 145.52 | 1023.61 | 299.18 | 39.08 | 26.69 | 16.06 | 381.01 | 296.83 | 39.51 | 26.69 | 16.06 | 379.09 | 37.03
11 | KALIMPONG | 173 | 726.24 | 1.92 | 728.16 | 325.38 | 0 | 3.63 | 0 | 329.01 | 324.94 | 0 | 3.63 | 0 | 328.57 | 45.12
12 | MALDAH | 234 | 2856.27 | 232.87 | 3089.14 | 604.28 | 46.28 | 357.26 | 0.2 | 1008.01 | 603.38 | 48.14 | 357.26 | 0.2 | 1008.97 | 32.66
13 | MURSHIDABAD | 831 | 4957.62 | 535.34 | 5492.96 | 1055.7 | 46.46 | 245.06 | 9.33 | 1356.55 | 1049.72 | 46.47 | 245.06 | 9.33 | 1350.58 | 24.59
14 | NADIA | 637 | 3021.14 | 229.44 | 3250.58 | 1256.84 | 32.41 | 270.38 | 4.64 | 1564.27 | 1257.04 | 33.31 | 270.38 | 4.64 | 1565.37 | 48.16
15 | NORTH 24 PARGANAS | 536 | 3347.07 | 181.59 | 3528.65 | 1252.87 | 38.1 | 260.16 | 14.92 | 1566.05 | 1252.57 | 38.25 | 260.16 | 14.92 | 1565.9 | 44.38
16 | PASCHIM BARDHAMAN | 124 | 1217.6 | 113.36 | 1330.96 | 622.24 | 52.6 | 188.52 | 0 | 863.36 | 621.61 | 52.76 | 188.52 | 0 | 862.9 | 64.83
17 | PASCHIM MEDINIPUR | 591 | 2802.5 | 228.29 | 3030.79 | 773.43 | 75.41 | 79.04 | 20.62 | 948.5 | 770.36 | 75.84 | 79.04 | 20.62 | 945.85 | 31.21
18 | PURBA BARDHAMAN | 546 | 2966.9 | 265.65 | 3232.55 | 1136.37 | 77.72 | 117.3 | 1.47 | 1332.86 | 1136.77 | 82.58 | 117.3 | 1.47 | 1338.12 | 41.4
19 | PURBA MEDINIPUR | 556 | 3688.26 | 297.39 | 3985.66 | 1142.37 | 67.17 | 141.26 | 24.76 | 1375.55 | 1141.75 | 67.1 | 141.26 | 24.76 | 1374.86 | 34.5
20 | PURULIA | 84 | 3499.75 | 520.8 | 4020.55 | 526.39 | 51.33 | 448.11 | 0 | 1025.84 | 508.25 | 51.25 | 448.11 | 0 | 1007.61 | 25.06
21 | SOUTH 24 PARGANAS | 893 | 5939.75 | 362.41 | 6302.16 | 1838.91 | 72.1 | 489.78 | 0.78 | 2401.57 | 1836.2 | 78.45 | 489.78 | 0.78 | 2405.22 | 38.16
22 | UTTAR DINAJPUR | 413 | 1740.76 | 109.17 | 1849.93 | 463.43 | 62.3 | 81.69 | 0 | 607.42 | 460.67 | 64.89 | 81.69 | 0 | 607.25 | 32.83
Total |  | 9337 | 52985.69 | 4603.43 | 57589.12 | 17080.81 | 1110.14 | 3503.39 | 118.64 | 21812.97 | 17019.74 | 1137.41 | 3503.39 | 118.64 | 21779.18 | 37.82