## JJM Schemes Financial Status (J
JJM Schemes Financial Status (JALPAIGURI) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | JALPAIGURI | SM/13706 | AMGURI PIPED WATER SUPPLY SCHEME | TSM/015418 | 40033102 | New | MVS | GO2223009708PH | 14/11/2022 | 825.28 | 66.06 | 891.35 | Jalpaiguri Division | Northern Mechanical Division | 350.59 | 32.55 | 119.5 | 0 | 502.64 | 359.82 | 35.46 | 119.5 | 0 | 514.78 | 57.75 | 78
2 | JALPAIGURI | SM/14884 | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016363 | 40036020 | New | MVS | GO2223013019PH | 03/02/2023 | 636 | 74.56 | 710.56 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 2.04 | 0 | 2.04 | 0.29
3 | JALPAIGURI | SM/10071 | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | TSM/009317 | 40002902 | Augmentation | MVS | GO2122008791PH | 27/01/2022 | 504.86 | 16.3 | 521.15 | Jalpaiguri Division | Northern Mechanical Division | 274.95 | 14.85 | 40.17 | 0 | 329.97 | 241.96 | 14.85 | 40.17 | 0 | 296.98 | 56.99 | 80
4 | JALPAIGURI | SM/10089 | Augmentation of Baikur Piped Water Supply Scheme. | TSM/006971 | 40003346 | Augmentation | MVS | GO2122009022PH | 01/02/2022 | 1708 | 55.63 | 1763.64 | Jalpaiguri Division | Northern Mechanical Division | 1288.78 | 42.35 | 27.59 | 0 | 1358.72 | 1169.16 | 42.35 | 27.59 | 0 | 1239.1 | 70.26 | 82
5 | JALPAIGURI | SM/10044 | Augmentation of Banerhat Bazar Piped Water Supply Scheme | TSM/009726 | 40002974 | Augmentation | MVS | GO2122008495PH | 20/01/2022 | 634.58 | 37.19 | 671.77 | Jalpaiguri Division | Northern Mechanical Division | 293.88 | 29.46 | 116.36 | 0 | 439.69 | 293.88 | 29.46 | 116.36 | 0 | 439.69 | 65.45 | 75
6 | JALPAIGURI | SM/10090 | Augmentation of Barnes Water Supply Scheme. | TSM/006966 | 40005894 | Augmentation | MVS | GO2122009022PH | 01/02/2022 | 1080.27 | 35.27 | 1115.54 | Jalpaiguri Division | Northern Mechanical Division | 911.29 | 31.33 | 107.56 | 4.21 | 1054.39 | 808.05 | 31.33 | 107.56 | 4.21 | 951.15 | 85.26 | 85
7 | JALPAIGURI | SM/13277 | Augmentation of Bhatipara Water Supply Scheme | TSM/009740 | 40002912 | Augmentation | MVS | GO2223007816PH | 19/09/2022 | 0 | 0 | 0 | Jalpaiguri Division | Northern Mechanical Division | 632.97 | 41.79 | 7.43 | 33.56 | 715.75 | 632.97 | 41.79 | 7.43 | 33.56 | 715.75 | INF | 60
8 | JALPAIGURI | SM/09344 | Augmentation of Binnaguri Piped Water Supply Scheme | TSM/008442 | 40005897 | Augmentation | SVS | GO2122005378PH | 12/11/2021 | 852.25 | 18.83 | 871.08 | Jalpaiguri Division | Northern Mechanical Division | 461.61 | 24.77 | 0 | 8.89 | 495.27 | 351.29 | 16.61 | 0 | 8.89 | 376.79 | 43.26 | 65
9 | JALPAIGURI | SM/08876 | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | TSM/005491 | 40014972 | Augmentation | MVS | GO2122003484PH | 22/09/2021 | 943.46 | 192.93 | 1136.39 | Jalpaiguri Division | Northern Mechanical Division | 477.08 | 73.88 | 172.86 | 0 | 723.82 | 450.29 | 78.46 | 172.86 | 0 | 701.61 | 61.74 | 60
10 | JALPAIGURI | SM/19175 | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018073 | 40060659 | Augmentation | SVS | :PHE-420/28011/204/2023-SCHM CELL-Dept. of PHE | 15/02/2024 | 1061.81 | 204.46 | 1266.28 | Jalpaiguri Division | Northern Mechanical Division | 59.85 | 0 | 0 | 0 | 59.85 | 59.85 | 0 | 0 | 0 | 59.85 | 4.73 | 5
11 | JALPAIGURI | SM/10086 | Augmentation of Dakshin Berubari Water Supply Scheme. | TSM/006972 | 40006090 | Augmentation | SVS | GO2122009022PH | 01/02/2022 | 1555.51 | 18.76 | 1574.27 | Jalpaiguri Division | Northern Mechanical Division | 953.82 | 14.15 | 49.81 | 0 | 1017.77 | 778.21 | 14.15 | 49.81 | 0 | 842.17 | 53.5 | 85
12 | JALPAIGURI | SM/09561 | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | TSM/008821 | 40005275 | Augmentation | MVS | GO2122005688PH | 22/11/2021 | 663.16 | 18.63 | 681.79 | Jalpaiguri Division | Northern Mechanical Division | 365.91 | 16.56 | 0 | 0 | 382.46 | 366.93 | 16.56 | 0 | 0 | 383.49 | 56.25 | 70
13 | JALPAIGURI | SM/09345 | Augmentation of Domohani Piped Water Supply Scheme | TSM/008382 | 40006249 | Augmentation | MVS | GO2122005379PH | 12/11/2021 | 818.31 | 37.25 | 855.56 | Jalpaiguri Division | Northern Mechanical Division | 547.06 | 24.63 | 5.5 | 12.54 | 589.72 | 575.12 | 24.63 | 5.5 | 12.54 | 617.79 | 72.21 | 80
14 | JALPAIGURI | SM/09860 | Augmentation of Gairkata Piped Water Supply Scheme | TSM/008816 | 40006242 | Augmentation | SVS | GO2122006497PH | 06/12/2021 | 462.05 | 18.48 | 480.53 | Jalpaiguri Division | Northern Mechanical Division | 89.09 | 11.8 | 13.39 | 0 | 114.28 | 75.39 | 11.8 | 13.39 | 0 | 100.58 | 20.93 | 40
15 | JALPAIGURI | SM/10043 | Augmentation of Jalapara Piped Water Supply Scheme | TSM/009324 | 40002882 | Augmentation | MVS | GO2122008494PH | 20/01/2022 | 586.92 | 33.94 | 620.86 | Jalpaiguri Division | Northern Mechanical Division | 213.35 | 8.58 | 119.89 | 0 | 341.82 | 213.21 | 14.55 | 119.89 | 0 | 347.65 | 56 | 60
16 | JALPAIGURI | SM/09563 | Augmentation of Kathapara Piped Water Supply Scheme | TSM/008819 | 40006252 | Augmentation | MVS | GO2122005689PH | 22/11/2021 | 815.67 | 19.21 | 834.88 | Jalpaiguri Division | Northern Mechanical Division | 290.19 | 15 | 15.98 | 0 | 321.16 | 187.93 | 15 | 15.98 | 0 | 218.91 | 26.22 | 70
17 | JALPAIGURI | SM/10088 | Augmentation of Kharija-Berubari Water Supply Scheme. | TSM/006967 | 40005879 | Augmentation | MVS | GO2122009022PH | 01/02/2022 | 2026.85 | 37.52 | 2064.37 | Jalpaiguri Division | Northern Mechanical Division | 1237.97 | 31.51 | 114.29 | 0 | 1383.77 | 1118.39 | 31.51 | 114.29 | 0 | 1264.19 | 61.24 | 87
18 | JALPAIGURI | SM/09994 | Augmentation of Kranti Piped water supply Scheme | TSM/008381 | 40005872 | Augmentation | MVS | GO2122007047PH | 20/12/2021 | 1720.91 | 34.89 | 1755.8 | Jalpaiguri Division | Northern Mechanical Division | 1021.45 | 25.41 | 0 | 0 | 1046.86 | 975.22 | 25.41 | 0 | 0 | 1000.63 | 56.99 | 75
19 | JALPAIGURI | SM/13278 | Augmentation of Lataguri Piped Water Supply Scheme | TSM/009331 | 40002928 | Augmentation | MVS | GO2223007816PH | 19/09/2022 | 0 | 0 | 0 | Jalpaiguri Division | Northern Mechanical Division | 876.04 | 88.86 | 355.53 | 0 | 1320.44 | 869.58 | 88.86 | 355.53 | 0 | 1313.97 | INF | 75
20 | JALPAIGURI | SM/11814 | AUGMENTATION OF LUKSAN BAZAR PWSS | TSM/009997 | 40021626 | Augmentation | SVS | GO2223006327PH | 16/08/2022 | 518.33 | 97.92 | 616.25 | Jalpaiguri Division | Northern Mechanical Division | 158.25 | 64.52 | 0 | 0 | 222.77 | 138.99 | 64.52 | 0 | 0 | 203.51 | 33.02 | 48
21 | JALPAIGURI | SM/10028 | Augmentation of Madhya Khagrabari Water Supply Scheme. | TSM/006969 | 40003374 | Augmentation | MVS | GO2122008295PH | 17/01/2022 | 951.14 | 35.27 | 986.41 | Jalpaiguri Division | Northern Mechanical Division | 556.93 | 33.45 | 282.3 | 22.27 | 894.96 | 395.65 | 40.47 | 282.3 | 22.27 | 740.7 | 75.09 | 80
22 | JALPAIGURI | SM/10042 | Augmentation of Maynaguri Piped Water Supply Scheme. | TSM/006968 | 40003326 | Augmentation | SVS | GO2122008496PH | 20/01/2022 | 942.77 | 35.92 | 978.7 | Jalpaiguri Division | Northern Mechanical Division | 484.53 | 29.58 | 45.54 | 0 | 559.65 | 559.82 | 30.33 | 45.54 | 0 | 635.69 | 64.95 | 72
23 | JALPAIGURI | SM/10087 | Augmentation of Mondalghat Water Supply Scheme. | TSM/006973 | 40005895 | Augmentation | SVS | GO2122009022PH | 01/02/2022 | 1077.02 | 18.62 | 1095.64 | Jalpaiguri Division | Northern Mechanical Division | 661.81 | 11.57 | 69.61 | 0 | 742.98 | 608.56 | 11.57 | 69.61 | 0 | 689.74 | 62.95 | 95
24 | JALPAIGURI | SM/13790 | Augmentation of Odlabari Piped Water Supply Scheme | TSM/009742 | 40014561 | Augmentation | SVS | GO2223009060PH | 21/10/2022 | 946.66 | 56.87 | 1003.52 | Jalpaiguri Division | Northern Mechanical Division | 403.27 | 50.58 | 113.51 | 0 | 567.36 | 403.27 | 50.58 | 113.51 | 0 | 567.36 | 56.54 | 90
25 | JALPAIGURI | SM/15302 | Augmentation of Porjhar Pipe Water Supply Scheme | TSM/018097 | 40060589 | Augmentation | SVS | GO2223013612PH | 09/02/2023 | 502.72 | 94.29 | 597.01 | Siliguri W/S Division | Northern Mechanical Division | 104.7 | 28.86 | 33.45 | 0 | 167.01 | 104.7 | 28.86 | 33.45 | 0 | 167.01 | 27.97 | 70
26 | JALPAIGURI | SM/09560 | Augmentation of Purba Daukimari Piped Water Supply Scheme | TSM/008810 | 40010504 | Augmentation | SVS | GO2122005686PH | 22/11/2021 | 526.78 | 19.09 | 545.87 | Jalpaiguri Division | Northern Mechanical Division | 399.81 | 13.32 | 14.17 | 0 | 427.29 | 432 | 13.32 | 14.17 | 0 | 459.48 | 84.17 | 70
27 | JALPAIGURI | SM/18355 | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | TSM/018407 | 40060599 | Augmentation | SVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1460.45 | 113.47 | 1573.93 | Siliguri W/S Division | Northern Mechanical Division | 0 | 28.26 | 91.3 | 0 | 119.56 | 0 | 28.26 | 91.3 | 0 | 119.56 | 7.6 | 9
28 | JALPAIGURI | SM/09864 | Augmentation of Purbba Batabari Piped Water Supply Scheme | TSM/009026 | 40013051 | Augmentation | MVS | GO2122006495PH | 06/12/2021 | 790.65 | 19.46 | 810.11 | Jalpaiguri Division | Northern Mechanical Division | 470.52 | 13.83 | 0 | 0 | 484.35 | 473.38 | 13.83 | 0 | 0 | 487.21 | 60.14 | 75
29 | JALPAIGURI | SM/10033 | Augmentation of Ramsai Water Supply Scheme. | TSM/006970 | 40005666 | Augmentation | MVS | GO2122008426PH | 19/01/2022 | 941.96 | 34.23 | 976.19 | Jalpaiguri Division | Northern Mechanical Division | 753.65 | 28.2 | 34.98 | 0 | 816.83 | 713.27 | 28.2 | 34.98 | 0 | 776.45 | 79.54 | 90
30 | JALPAIGURI | SM/09996 | Augmentation of Sannyasikata Piped Water Supply Scheme | TSM/008408 | 40005896 | Augmentation | SVS | GO2122007047PH | 20/12/2021 | 2068.68 | 36.44 | 2105.11 | Jalpaiguri Division | Northern Mechanical Division | 1419.28 | 32.29 | 32.92 | 0 | 1484.5 | 1409.25 | 32.29 | 32.92 | 0 | 1474.47 | 70.04 | 85
31 | JALPAIGURI | SM/09562 | Augmentation of Shikarpur Piped Water Supply Scheme | TSM/008818 | 40006427 | Augmentation | MVS | GO2122005687PH | 22/11/2021 | 958.33 | 19.21 | 977.54 | Jalpaiguri Division | Northern Mechanical Division | 294.13 | 15.63 | 0 | 0 | 309.76 | 294.13 | 15.63 | 0 | 0 | 309.76 | 31.69 | 55
32 | JALPAIGURI | SM/09995 | Augmentation of Sukani Piped Water Supply Scheme | TSM/008383 | 40005283 | Augmentation | MVS | GO2122007047PH | 20/12/2021 | 4239.57 | 130.58 | 4370.14 | Jalpaiguri Division | Northern Mechanical Division | 2403.33 | 100.53 | 191.38 | 0 | 2695.24 | 2323.22 | 100.53 | 191.38 | 0 | 2615.13 | 59.84 | 75
33 | JALPAIGURI | SM/08874 | Bagrakote Tea Garden Area Piped Water Supply Scheme. | TSM/003942 | 40006426 | New | SVS | GO2122003483PH | 22/09/2021 | 457.34 | 61.03 | 518.37 | Jalpaiguri Division | Northern Mechanical Division | 82.53 | 40.72 | 109.49 | 0 | 232.74 | 82.53 | 45.99 | 109.49 | 0 | 238.01 | 45.92 | 55
34 | JALPAIGURI | SM/13703 | BARA DIGHI PIPED WATER SUPPLY SCHEME | TSM/015677 | 40033113 | New | MVS | GO2223009710PH | 14/11/2022 | 110.13 | 46.13 | 156.26 | Jalpaiguri Division | Northern Mechanical Division | 80.13 | 0 | 2.59 | 0 | 82.71 | 85.91 | 0 | 2.59 | 0 | 88.49 | 56.63 | 85
35 | JALPAIGURI | SM/15967 | BARA GHARIA PIPED WATER SUPPLY SCHEME | TSM/018232 | 40058210 | New | MVS | GO2223014710PH | 22/02/2023 | 627.9 | 75.8 | 703.7 | Jalpaiguri Division | Northern Mechanical Division | 178.31 | 41.81 | 46.03 | 0 | 266.14 | 178.31 | 41.81 | 46.03 | 0 | 266.14 | 37.82 | 60
36 | JALPAIGURI | SM/17649 | BARAGHARIA Piped Water Supply Scheme. | TSM/014917 | 40036008 | New | MVS | GO2223017473PH | 22/03/2023 | 573.89 | 39.29 | 613.18 | Jalpaiguri Division | Northern Mechanical Division | 223.45 | 31.83 | 12.71 | 0 | 267.99 | 223.45 | 35.95 | 12.71 | 0 | 272.1 | 44.38 | 90
37 | JALPAIGURI | SM/15971 | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017313 | 40036081 | New | SVS | GO2223014703PH | 22/02/2023 | 775.91 | 70.91 | 846.82 | Jalpaiguri Division | Northern Mechanical Division | 143.59 | 23.69 | 12.09 | 0 | 179.38 | 143.59 | 25.48 | 12.09 | 0 | 181.16 | 21.39 | 31
38 | JALPAIGURI | SM/16041 | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017315 | 40036080 | New | SVS | GO2223014709PH | 22/02/2023 | 847.21 | 71.26 | 918.46 | Jalpaiguri Division | Northern Mechanical Division | 298.26 | 12.86 | 14.51 | 0 | 325.63 | 298.26 | 12.86 | 14.51 | 0 | 325.63 | 35.45 | 51
39 | JALPAIGURI | SM/18359 | BASUSUBA PIPED WATER SUPPLY SCHEME | TSM/018240 | 40049256 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1135.81 | 121.84 | 1257.66 | Jalpaiguri Division | Northern Mechanical Division | 214.03 | 25.83 | 74.3 | 0 | 314.16 | 214.03 | 25.83 | 74.3 | 0 | 314.16 | 24.98 | 35
40 | JALPAIGURI | SM/09975 | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | TSM/003950 | 40006580 | New | MVS | GO2122003483PH | 22/09/2021 | 0 | 0 | 0 | Jalpaiguri Division | Northern Mechanical Division | 151.26 | 60.85 | 11.74 | 0 | 223.85 | 151.3 | 66.23 | 11.74 | 0 | 229.28 | INF | 60
41 | JALPAIGURI | SM/16676 | BHEMTIA PIPED WATER SUPPLY SCHEME | TSM/015327 | 40033213 | New | SVS | GO2223015941PH | 14/03/2023 | 348.28 | 66.55 | 414.83 | Jalpaiguri Division | Northern Mechanical Division | 0 | 31.5 | 22.86 | 0 | 54.36 | 0 | 32.32 | 22.86 | 0 | 55.18 | 13.3 | 60
42 | JALPAIGURI | SM/14198 | BINNAGURI PIPED WATER SUPPLY SCHEME | TSM/016357 | 40032757 | New | SVS | GO2223011801PH | 10/01/2023 | 340.4 | 68.79 | 409.19 | Jalpaiguri Division | Northern Mechanical Division | 132.81 | 13.06 | 44.7 | 0 | 190.57 | 141.47 | 13.37 | 44.7 | 0 | 199.54 | 48.76 | 70
43 | JALPAIGURI | SM/13705 | BRAHMAPUR PIPED WATER SUPPLY SCHEME | TSM/015422 | 40033117 | New | MVS | GO2223009701PH | 14/11/2022 | 899.2 | 88.95 | 988.14 | Jalpaiguri Division | Northern Mechanical Division | 152.3 | 12.28 | 154.86 | 0 | 319.44 | 152.3 | 12.28 | 154.86 | 0 | 319.44 | 32.33 | 40
44 | JALPAIGURI | SM/15264 | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015385 | 40033216 | New | SVS | GO2223013480PH | 07/02/2023 | 273.14 | 72.78 | 345.92 | Jalpaiguri Division | Northern Mechanical Division | 136.67 | 20.41 | 6.65 | 0 | 163.74 | 136.67 | 20.41 | 6.65 | 0 | 163.74 | 47.33 | 80
45 | JALPAIGURI | SM/18492 | Chapgar Piped Water Supply Scheme. | TSM/002874 | 40035432 | New | MVS | PHE/IV/2004/W-616/23 | 24/07/2023 | 687.89 | 69.86 | 757.75 | Jalpaiguri Division | Northern Mechanical Division | 119.53 | 7.21 | 9.79 | 0 | 136.54 | 111.76 | 7.21 | 9.79 | 0 | 128.76 | 16.99 | 40
46 | JALPAIGURI | SM/16042 | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | TSM/015374 | 40033225 | New | MVS | GO2223014580PH | 22/02/2023 | 502.96 | 65.53 | 568.49 | Jalpaiguri Division | Northern Mechanical Division | 205.15 | 26.94 | 17.49 | 0 | 249.58 | 205.15 | 29.3 | 17.49 | 0 | 251.93 | 44.32 | 70
47 | JALPAIGURI | SM/18358 | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | TSM/018490 | 40049260 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1263 | 136.32 | 1399.31 | Jalpaiguri Division | Northern Mechanical Division | 371 | 46.9 | 99.54 | 0 | 517.43 | 371 | 46.9 | 99.54 | 0 | 517.43 | 36.98 | 50
48 | JALPAIGURI | SM/13901 | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | TSM/015382 | 40033240 | New | MVS | GO2223010079PH | 25/11/2022 | 177.43 | 59.3 | 236.73 | Jalpaiguri Division | Northern Mechanical Division | 77.28 | 24.88 | 7.46 | 0 | 109.62 | 80.02 | 24.88 | 7.46 | 0 | 112.36 | 47.46 | 70
49 | JALPAIGURI | SM/15964 | CHHAR TANDU PIPED WATER SUPPLY SCHEME | TSM/017828 | 40058179 | New | SVS | GO2223014702PH | 22/02/2023 | 254.67 | 75.51 | 330.17 | Jalpaiguri Division | Northern Mechanical Division | 51.8 | 12.6 | 0 | 0 | 64.4 | 51.8 | 12.6 | 0 | 0 | 64.4 | 19.5 | 10
50 | JALPAIGURI | SM/14494 | CHHOTA FAPRI WATER SUPPLY SCHEME | TSM/011228 | 40034208 | New | SVS | GO2223012345PH | 20/01/2023 | 250.75 | 53.57 | 304.33 | Jalpaiguri Division | Northern Mechanical Division | 42.77 | 20.74 | 15.96 | 0 | 79.47 | 42.77 | 20.74 | 15.96 | 0 | 79.47 | 26.11 | 25
51 | JALPAIGURI | SM/13700 | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | TSM/015421 | 40033128 | New | MVS | GO2223009704PH | 14/11/2022 | 594.87 | 66.25 | 661.12 | Jalpaiguri Division | Northern Mechanical Division | 147.35 | 29.28 | 148.99 | 0 | 325.62 | 147.35 | 33.44 | 148.99 | 0 | 329.78 | 49.88 | 55
52 | JALPAIGURI | SM/14887 | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017494 | 40049259 | New | MVS | GO2223013016PH | 03/02/2023 | 572.31 | 68.79 | 641.1 | Jalpaiguri Division | Northern Mechanical Division | 250.49 | 27.97 | 9.97 | 0 | 288.43 | 250.49 | 34.5 | 9.97 | 0 | 294.96 | 46.01 | 75
53 | JALPAIGURI | SM/16181 | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017495 | 40058264 | New | MVS | GO2223014705PH | 22/02/2023 | 545.02 | 68.71 | 613.74 | Jalpaiguri Division | Northern Mechanical Division | 225.3 | 32.79 | 8.53 | 0 | 266.62 | 225.3 | 32.79 | 8.53 | 0 | 266.62 | 43.44 | 60
54 | JALPAIGURI | SM/15335 | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | TSM/017841 | 40035918 | New | MVS | GO2223013601PH | 09/02/2023 | 749.04 | 101.66 | 850.7 | Jalpaiguri Division | Northern Mechanical Division | 161.43 | 22.67 | 76.52 | 0 | 260.63 | 161.43 | 22.67 | 76.52 | 0 | 260.63 | 30.64 | 72
55 | JALPAIGURI | SM/18835 | Dakshin Jharalta Piped Water Supply Scheme. | TSM/005492 | 40035820 | New | MVS | 2868/PHE-28011/247/2023-ESTT CELL-Dept. of PHE | 21/09/2023 | 1134.48 | 56.35 | 1190.83 | Jalpaiguri Division | Northern Mechanical Division | 286.94 | 38.81 | 122.68 | 0 | 448.44 | 286.94 | 41.26 | 122.68 | 0 | 450.89 | 37.86 | 50
56 | JALPAIGURI | SM/14908 | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | TSM/016642 | 40032783 | New | SVS | GO2223012920PH | 03/02/2023 | 176.46 | 71.69 | 248.15 | Jalpaiguri Division | Northern Mechanical Division | 48.21 | 26.39 | 16.4 | 0 | 91 | 48.21 | 29.9 | 16.4 | 0 | 94.51 | 38.09 | 68
57 | JALPAIGURI | SM/18711 | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016182 | 40035930 | New | SVS | 2260/PHE/IV/W-404/23 | 04/08/2023 | 510.54 | 74.34 | 584.88 | Jalpaiguri Division | Northern Mechanical Division | 198.41 | 16.6 | 12.02 | 0 | 227.03 | 198.41 | 20.11 | 12.02 | 0 | 230.54 | 39.42 | 90
58 | JALPAIGURI | SM/14826 | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME | TSM/016064 | 40049263 | New | SVS | GO2223013118PH | 04/02/2023 | 482.76 | 68.92 | 551.68 | Jalpaiguri Division | Northern Mechanical Division | 178.56 | 31.38 | 6.57 | 0 | 216.51 | 178.56 | 39.48 | 6.57 | 0 | 224.61 | 40.71 | 60
59 | JALPAIGURI | SM/14882 | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015977 | 40049266 | New | SVS | GO2223013115PH | 04/02/2023 | 489.01 | 69.04 | 558.05 | Jalpaiguri Division | Northern Mechanical Division | 163.14 | 28.9 | 6.84 | 0 | 198.88 | 163.14 | 29.5 | 6.84 | 0 | 199.48 | 35.75 | 63
60 | JALPAIGURI | SM/15261 | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | TSM/014784 | 40033242 | New | SVS | GO2223013541PH | 08/02/2023 | 478.15 | 67.28 | 545.43 | Jalpaiguri Division | Northern Mechanical Division | 130.9 | 10.83 | 23.94 | 0 | 165.67 | 130.9 | 10.83 | 23.94 | 0 | 165.67 | 30.37 | 65
61 | JALPAIGURI | SM/15980 | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016184 | 40058236 | New | SVS | GO2223014704PH | 22/02/2023 | 279.74 | 70.45 | 350.2 | Jalpaiguri Division | Northern Mechanical Division | 47.71 | 17.32 | 4.28 | 0 | 69.31 | 44.96 | 17.32 | 4.28 | 0 | 66.56 | 19.01 | 37
62 | JALPAIGURI | SM/06837 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | TSM/005789 | 7845425 | Retrofitting | SVS | GO2021001731PH | 06/10/2020 | 61.53 | 0 | 61.53 | Jalpaiguri Division |  | 61.53 | 0 | 0 | 0 | 61.53 | 66.16 | 0 | 0 | 0 | 66.16 | 107.52 | 85
63 | JALPAIGURI | SM/06845 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | TSM/005800 | 7349342 | Retrofitting | MVS | GO2021001740PH | 06/10/2020 | 60.77 | 0 | 60.77 | Jalpaiguri Division |  | 60.77 | 0 | 0 | 0 | 60.77 | 68.9 | 0 | 0 | 0 | 68.9 | 113.37 | 100
64 | JALPAIGURI | SM/06838 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | TSM/005790 | 8129736 | Retrofitting | MVS | GO2021001732PH | 06/10/2020 | 92.26 | 0 | 92.26 | Jalpaiguri Division |  | 71.65 | 0 | 0 | 0 | 71.65 | 66.17 | 0 | 0 | 0 | 66.17 | 71.72 | 85
65 | JALPAIGURI | SM/06847 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme | TSM/005802 | 40064185 | Retrofitting | SVS | GO2021001743PH | 06/10/2020 | 56.03 | 0 | 56.03 | Jalpaiguri Division |  | 56.03 | 0 | 0 | 0 | 56.03 | 45 | 0 | 0 | 0 | 45 | 80.3 | 95
66 | JALPAIGURI | SM/06844 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/005799 | 8129767 | Retrofitting | SVS | GO2021001739PH | 06/10/2020 | 57.04 | 0 | 57.04 | Jalpaiguri Division |  | 57.04 | 0 | 0 | 0 | 57.04 | 55.79 | 0 | 0 | 0 | 55.79 | 97.82 | 85
67 | JALPAIGURI | SM/06846 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | TSM/005801 | 8129328 | Retrofitting | SVS | GO2021001742PH | 06/10/2020 | 37.11 | 0 | 37.11 | Jalpaiguri Division |  | 37.11 | 0 | 0 | 0 | 37.11 | 40.73 | 0 | 0 | 0 | 40.73 | 109.76 | 87
68 | JALPAIGURI | SM/07893 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | TSM/006752 | 8182576 | Retrofitting | MVS | GO2021004755PH | 19/01/2021 | 133.21 | 0 | 133.21 | Jalpaiguri Division |  | 73.51 | 0 | 0 | 0 | 73.51 | 52.02 | 0 | 0 | 0 | 52.02 | 39.05 | 50
69 | JALPAIGURI | SM/07892 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | TSM/006750 | 8182658 | Retrofitting | MVS | GO2021004754PH | 19/01/2021 | 131.79 | 0 | 131.79 | Jalpaiguri Division |  | 85.37 | 0 | 0 | 0 | 85.37 | 54.21 | 0 | 0 | 0 | 54.21 | 41.14 | 10
70 | JALPAIGURI | SM/07891 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | TSM/006751 | 8182684 | Retrofitting | MVS | GO2021004753PH | 19/01/2021 | 285.66 | 0 | 285.66 | Jalpaiguri Division |  | 74.53 | 0 | 0 | 0 | 74.53 | 74.53 | 0 | 0 | 0 | 74.53 | 26.09 | 35
71 | JALPAIGURI | SM/06843 | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme | TSM/005798 | 8136033 | Retrofitting | MVS | GO2021001737PH | 06/10/2020 | 52.3 | 0 | 52.3 | Jalpaiguri Division |  | 15.72 | 0 | 0 | 0 | 15.72 | 15.72 | 0 | 0 | 0 | 15.72 | 30.06 | 89
72 | JALPAIGURI | SM/14665 | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | TSM/016176 | 40032817 | New | SVS | GO2223012741PH | 31/01/2023 | 349.89 | 67.78 | 417.67 | Jalpaiguri Division | Northern Mechanical Division | 137.86 | 13.72 | 29.35 | 0 | 180.92 | 127.77 | 16.03 | 29.35 | 0 | 173.15 | 41.46 | 60
73 | JALPAIGURI | SM/14664 | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | TSM/016178 | 40034492 | New | SVS | GO2223012742PH | 31/01/2023 | 811.06 | 59.82 | 870.88 | Jalpaiguri Division | Northern Mechanical Division | 432.98 | 56.3 | 41.51 | 0 | 530.79 | 432.96 | 55.9 | 41.51 | 0 | 530.37 | 60.9 | 95
74 | JALPAIGURI | SM/15297 | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016344 | 40049253 | New | MVS | GO2223013599PH | 09/02/2023 | 649.85 | 74.39 | 724.23 | Jalpaiguri Division | Northern Mechanical Division | 100.76 | 24.64 | 39.98 | 0 | 165.38 | 100.76 | 27 | 39.98 | 0 | 167.74 | 23.16 | 60
75 | JALPAIGURI | SM/13701 | GAURGRAM PIPED WATER SUPPLY SCHEME | TSM/015420 | 40033145 | New | MVS | GO2223009703PH | 14/11/2022 | 527.16 | 67.73 | 594.88 | Jalpaiguri Division | Northern Mechanical Division | 175.95 | 33.49 | 132.19 | 0 | 341.63 | 175.95 | 33.49 | 132.19 | 0 | 341.63 | 57.43 | 65
76 | JALPAIGURI | SM/14666 | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016174 | 40032828 | New | SVS | GO2223012678PH | 31/01/2023 | 760.49 | 91.94 | 852.43 | Jalpaiguri Division | Northern Mechanical Division | 343.97 | 46.7 | 44.11 | 0 | 434.78 | 337.66 | 54.89 | 44.11 | 0 | 436.66 | 51.22 | 90
77 | JALPAIGURI | SM/08868 | Ghasmari Piped Water Supply Scheme. | TSM/003951 | 40011924 | New | MVS | GO2122003401PH | 20/09/2021 | 240.71 | 52.53 | 293.24 | Jalpaiguri Division | Northern Mechanical Division | 139.3 | 27.83 | 23.39 | 0 | 190.52 | 111.88 | 30.42 | 23.39 | 0 | 165.69 | 56.5 | 80
78 | JALPAIGURI | SM/16852 | HAIHAIPATHAR PWSS | TSM/016203 | 40036022 | New | MVS | GO2223015694PH | 13/03/2023 | 698.93 | 42.75 | 741.68 | Jalpaiguri Division | Northern Mechanical Division | 221.18 | 38.74 | 42.41 | 0 | 302.33 | 221.18 | 40.52 | 42.41 | 0 | 304.1 | 41 | 60
79 | JALPAIGURI | SM/10775 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | TSM/009977 | 40036954 | New | MVS | GO2223003217PH | 23/05/2022 | 422.38 | 113.74 | 536.12 | Jalpaiguri Division | Northern Mechanical Division | 74.74 | 0 | 0 | 0 | 74.74 | 74.74 | 0 | 0 | 0 | 74.74 | 13.94 | 50
80 | JALPAIGURI | SM/08873 | Indong Tea Garden Area Piped Water Supply Scheme. | TSM/005102 | 40006229 | New | SVS | GO2122003483PH | 22/09/2021 | 273.31 | 38.16 | 311.47 | Jalpaiguri Division | Northern Mechanical Division | 176.63 | 27.85 | 24.59 | 0 | 229.08 | 180.47 | 29.58 | 24.59 | 0 | 234.64 | 75.33 | 92
81 | JALPAIGURI | SM/15742 | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | TSM/014793 | 40035716 | New | SVS | GO2223014248PH | 20/02/2023 | 610.29 | 68.55 | 678.84 | Jalpaiguri Division | Northern Mechanical Division | 162.52 | 18.59 | 28.81 | 0 | 209.92 | 157.24 | 18.59 | 28.81 | 0 | 204.64 | 30.15 | 35
82 | JALPAIGURI | SM/14879 | KANTADIGHI KUMARPARA TEA GARDEN | TSM/017840 | 40036004 | New | MVS | GO2223013020PH | 03/02/2023 | 743.32 | 97.89 | 841.22 | Jalpaiguri Division | Northern Mechanical Division | 352.41 | 23.35 | 80.34 | 0 | 456.09 | 352.41 | 25.99 | 80.34 | 0 | 458.73 | 54.53 | 91
83 | JALPAIGURI | SM/14199 | KAOAGAP PIPED WATER SUPPLY SCHEME | TSM/016139 | 40032999 | New | MVS | GO2223011794PH | 10/01/2023 | 581.65 | 65.68 | 647.34 | Jalpaiguri Division | Northern Mechanical Division | 233.77 | 15.12 | 47.04 | 0 | 295.94 | 233.77 | 18.95 | 47.04 | 0 | 299.77 | 46.31 | 65
84 | JALPAIGURI | SM/14907 | KHAS JANGAL PIPED WATER SUPPLY SCHEME | TSM/016691 | 40033009 | New | SVS | GO2223012919PH | 03/02/2023 | 173.44 | 72.33 | 245.77 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0.69 | 12.35 | 0 | 13.04 | 0 | 0.69 | 12.35 | 0 | 13.04 | 5.3 | 20
85 | JALPAIGURI | SM/15263 | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | TSM/011227 | 40034213 | New | SVS | GO2223013478PH | 07/02/2023 | 345.42 | 53.91 | 399.34 | Jalpaiguri Division | Northern Mechanical Division | 6.6 | 32.93 | 21.03 | 0 | 60.57 | 6.6 | 32.93 | 21.03 | 0 | 60.57 | 15.17 | 25
86 | JALPAIGURI | SM/15953 | KHUKLUNG PIPED WATER SUPPLY SCHEME | TSM/018691 | 40058163 | New | SVS | GO2223014707PH | 22/02/2023 | 70.56 | 48.54 | 119.09 | Jalpaiguri Division | Northern Mechanical Division | 37.79 | 0 | 0 | 0 | 37.79 | 34.97 | 0 | 0 | 0 | 34.97 | 29.36 | 60
87 | JALPAIGURI | SM/18491 | Kumarpara Piped Water Supply Scheme. | TSM/003957 | 40035439 | New | MVS | PHE/IV/2004/W-616/23 | 24/07/2023 | 791.51 | 53.74 | 845.25 | Jalpaiguri Division | Northern Mechanical Division | 290.23 | 45.11 | 41.11 | 0 | 376.45 | 290.23 | 45.11 | 41.11 | 0 | 376.45 | 44.54 | 47
88 | JALPAIGURI | SM/08875 | Kumlai Tea Garden Area Piped Water Supply Scheme. | TSM/003937 | 40006101 | New | SVS | GO2122003483PH | 22/09/2021 | 265.83 | 38.01 | 303.84 | Jalpaiguri Division | Northern Mechanical Division | 235.5 | 35.21 | 20.11 | 0 | 290.82 | 199.7 | 38.76 | 20.11 | 0 | 258.56 | 85.1 | 97
89 | JALPAIGURI | SM/15262 | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/013287 | 40033247 | New | MVS | GO2223013540PH | 08/02/2023 | 564.19 | 70.98 | 635.17 | Jalpaiguri Division | Northern Mechanical Division | 225.12 | 37.08 | 19.29 | 0 | 281.49 | 225.12 | 40.6 | 19.29 | 0 | 285 | 44.87 | 90
90 | JALPAIGURI | SM/13681 | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | TSM/015307 | 40033174 | New | MVS | GO2223009709PH | 14/11/2022 | 702.34 | 104.91 | 807.25 | Jalpaiguri Division | Northern Mechanical Division | 155.57 | 36.74 | 41.46 | 0 | 233.77 | 155.57 | 36.74 | 41.46 | 0 | 233.77 | 28.96 | 40
91 | JALPAIGURI | SM/13682 | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015312 | 40033212 | New | SVS | GO2223009705PH | 14/11/2022 | 477.92 | 66.67 | 544.59 | Jalpaiguri Division | Northern Mechanical Division | 0 | 24.31 | 20.77 | 0 | 45.08 | 0 | 24.31 | 20.77 | 0 | 45.08 | 8.28
92 | JALPAIGURI | SM/13898 | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | TSM/015372 | 40033257 | New | MVS | GO2223010077PH | 25/11/2022 | 836.68 | 70.04 | 906.72 | Jalpaiguri Division | Northern Mechanical Division | 573.59 | 32.95 | 103.77 | 0 | 710.32 | 583.33 | 36.47 | 103.77 | 0 | 723.56 | 79.8 | 90
93 | JALPAIGURI | SM/13702 | MAHANBHITA PIPED WATER SUPPLY SCHEME | TSM/015639 | 40033233 | New | MVS | GO2223009702PH | 14/11/2022 | 708.92 | 159.56 | 868.48 | Jalpaiguri Division | Northern Mechanical Division | 206.47 | 87.17 | 53.96 | 0 | 347.59 | 206.47 | 91.52 | 53.96 | 0 | 351.95 | 40.52 | 44
94 | JALPAIGURI | SM/15990 | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016183 | 40035928 | New | SVS | GO2223014706PH | 22/02/2023 | 334.76 | 71.7 | 406.46 | Jalpaiguri Division | Northern Mechanical Division | 146.88 | 22.45 | 6.75 | 0 | 176.08 | 146.88 | 25.09 | 6.75 | 0 | 178.72 | 43.97 | 70
95 | JALPAIGURI | SM/13900 | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | TSM/015391 | 40033638 | New | MVS | GO2223010082PH | 25/11/2022 | 581.66 | 156.44 | 738.1 | Jalpaiguri Division | Northern Mechanical Division | 249.34 | 39.3 | 22.48 | 0 | 311.12 | 249.34 | 43.43 | 22.48 | 0 | 315.26 | 42.71 | 50
96 | JALPAIGURI | SM/15115 | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016185 | 40049252 | New | MVS | GO2223013194PH | 04/02/2023 | 487.85 | 72.52 | 560.37 | Jalpaiguri Division | Northern Mechanical Division | 234.94 | 8.92 | 55.58 | 0 | 299.43 | 234.94 | 12.43 | 55.58 | 0 | 302.94 | 54.06 | 98
97 | JALPAIGURI | SM/18357 | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | TSM/017837 | 40036013 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 883.71 | 147.36 | 1031.07 | Jalpaiguri Division | Northern Mechanical Division | 443.1 | 57.54 | 61.06 | 0 | 561.7 | 443.1 | 58.48 | 61.06 | 0 | 562.64 | 54.57 | 68
98 | JALPAIGURI | SM/14911 | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016620 | 40033011 | New | SVS | GO2223012921PH | 03/02/2023 | 200.34 | 74.08 | 274.41 | Jalpaiguri Division | Northern Mechanical Division | 77.46 | 7.56 | 22.07 | 0 | 107.09 | 77.46 | 7.56 | 22.07 | 0 | 107.09 | 39.02 | 47
99 | JALPAIGURI | SM/15296 | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017834 | 40036018 | New | MVS | GO2223013615PH | 09/02/2023 | 530.95 | 73.68 | 604.63 | Jalpaiguri Division | Northern Mechanical Division | 179.3 | 36.96 | 44.81 | 0 | 261.07 | 179.3 | 41.65 | 44.81 | 0 | 265.76 | 43.95 | 70
100 | JALPAIGURI | SM/13991 | NIRANJANPAT WATER SUPPLY SCHEME | TSM/013267 | 40033639 | New | SVS | GO2223010299PH | 01/12/2022 | 477.46 | 66.18 | 543.63 | Jalpaiguri Division | Northern Mechanical Division | 102.99 | 10.67 | 25 | 0 | 138.66 | 102.99 | 14.26 | 25 | 0 | 142.25 | 26.17 | 35
101 | JALPAIGURI | SM/18503 | NOWAPARA PIPED WATER SUPPLY SCHEME | TSM/014951 | 40058323 | New | SVS | 2038/PHE-28011/185/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 974.29 | 85.92 | 1060.21 | Jalpaiguri Division | Northern Mechanical Division | 2.22 | 5.42 | 50.76 | 0 | 58.41 | 2.22 | 5.42 | 50.76 | 0 | 58.41 | 5.51 | 10
102 | JALPAIGURI | SM/18356 | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018253 | 40049250 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1041.29 | 99.09 | 1140.38 | Jalpaiguri Division | Northern Mechanical Division | 197.25 | 38.99 | 44.52 | 0 | 280.76 | 197.25 | 44 | 44.52 | 0 | 285.77 | 25.06 | 88
103 | JALPAIGURI | SM/19097 | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017317 | 40036079 | New | SVS | 3664/PHE-28011/207/2023-SCHM CELL-Dept. of PHE | 08/12/2023 | 928.96 | 71.26 | 1000.22 | Jalpaiguri Division | Northern Mechanical Division | 164.72 | 32.72 | 63.2 | 0 | 260.64 | 164.72 | 34.21 | 63.2 | 0 | 262.13 | 26.21 | 60
104 | JALPAIGURI | SM/16779 | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017319 | 40036077 | New | SVS | GO2223015828PH | 13/03/2023 | 639.34 | 69.97 | 709.31 | Jalpaiguri Division | Northern Mechanical Division | 92.11 | 22.35 | 53.88 | 0 | 168.34 | 92.11 | 22.35 | 53.88 | 0 | 168.34 | 23.73 | 38
105 | JALPAIGURI | SM/14241 | PANI KAURI PIPED WATER SUPPLY SCHEME | TSM/015429 | 40033642 | New | MVS | GO2223012001PH | 16/01/2023 | 1132.78 | 248.58 | 1381.36 | Jalpaiguri Division | Northern Mechanical Division | 219.6 | 130.33 | 59.48 | 0 | 409.42 | 219.6 | 130.33 | 59.48 | 0 | 409.42 | 29.64 | 35
106 | JALPAIGURI | SM/14667 | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | TSM/016170 | 40033014 | New | SVS | GO2223012677PH | 31/01/2023 | 397.2 | 67.49 | 464.69 | Jalpaiguri Division | Northern Mechanical Division | 161.07 | 23.67 | 20.4 | 0 | 205.14 | 161.07 | 30.5 | 20.4 | 0 | 211.97 | 45.62 | 64
107 | JALPAIGURI | SM/15915 | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | TSM/015316 | 40033644 | New | SVS | GO2223014579PH | 22/02/2023 | 360.68 | 66.55 | 427.23 | Jalpaiguri Division | Northern Mechanical Division | 38.45 | 30.01 | 13.7 | 0 | 82.17 | 38.45 | 30.01 | 13.7 | 0 | 82.17 | 19.23 | 25
108 | JALPAIGURI | SM/16040 | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015323 | 40033647 | New | MVS | GO2223014572PH | 22/02/2023 | 320.51 | 65.51 | 386.02 | Jalpaiguri Division | Northern Mechanical Division | 163.63 | 22.71 | 16.49 | 0 | 202.83 | 163.63 | 23.09 | 16.49 | 0 | 203.21 | 52.64 | 65
109 | JALPAIGURI | SM/15978 | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016193 | 40035925 | New | SVS | GO2223014708PH | 22/02/2023 | 313.87 | 77.61 | 391.48 | Jalpaiguri Division | Northern Mechanical Division | 152.63 | 53.3 | 6.09 | 0 | 212.02 | 152.63 | 55.79 | 6.09 | 0 | 214.5 | 54.79 | 45
110 | JALPAIGURI | SM/15339 | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017390 | 40036075 | New | SVS | GO2223013616PH | 09/02/2023 | 887.14 | 93.31 | 980.45 | Jalpaiguri Division | Northern Mechanical Division | 129.26 | 30.85 | 74.64 | 0 | 234.75 | 129.26 | 30.85 | 74.64 | 0 | 234.75 | 23.94 | 60
111 | JALPAIGURI | SM/18360 | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017397 | 40036073 | New | SVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1058.75 | 93.31 | 1152.06 | Jalpaiguri Division | Northern Mechanical Division | 215.91 | 42.42 | 60.19 | 0 | 318.52 | 215.91 | 46.86 | 60.19 | 0 | 322.96 | 28.03 | 60
112 | JALPAIGURI | SM/14878 | PATKATA ZONE-III PIPED WATER SUPPLY | TSM/017407 | 40035902 | New | SVS | GO2223013013PH | 03/02/2023 | 656.42 | 71.26 | 727.68 | Jalpaiguri Division | Northern Mechanical Division | 193.67 | 26.26 | 40.16 | 0 | 260.09 | 193.67 | 26.26 | 40.16 | 0 | 260.09 | 35.74 | 60
113 | JALPAIGURI | SM/13987 | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | TSM/013298 | 40034069 | New | MVS | GO2223010300PH | 01/12/2022 | 601.92 | 154.79 | 756.71 | Jalpaiguri Division | Northern Mechanical Division | 162.69 | 53.69 | 60.81 | 0 | 277.19 | 149.34 | 53.69 | 60.81 | 0 | 263.83 | 34.87 | 40
114 | JALPAIGURI | SM/16492 | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | TSM/013278 | 40035720 | New | SVS | GO2223015190PH | 02/03/2023 | 361.16 | 100.65 | 461.81 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 65.98 | 0 | 65.98 | 0 | 0 | 65.98 | 0 | 65.98 | 14.29 | 5
115 | JALPAIGURI | SM/13990 | PIPE WATER SUPPLY SCHEME FOR TANDU | TSM/013281 | 40034077 | New | MVS | GO2223010301PH | 01/12/2022 | 131.44 | 46.22 | 177.66 | Jalpaiguri Division | Northern Mechanical Division | 75.48 | 16.23 | 2.44 | 0 | 94.15 | 66.73 | 17.98 | 2.44 | 0 | 87.15 | 49.06 | 80
116 | JALPAIGURI | SM/13989 | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | TSM/013276 | 40034082 | New | SVS | GO2223010298PH | 01/12/2022 | 99.2 | 44.35 | 143.56 | Jalpaiguri Division | Northern Mechanical Division | 76.78 | 15.82 | 2.22 | 0 | 94.82 | 77.68 | 17.01 | 2.22 | 0 | 96.91 | 67.51 | 90
117 | JALPAIGURI | SM/13988 | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | TSM/013277 | 40034086 | New | SVS | GO2223010297PH | 01/12/2022 | 282.82 | 72.78 | 355.6 | Jalpaiguri Division | Northern Mechanical Division | 209.14 | 28.13 | 23.51 | 0 | 260.78 | 209.14 | 29.9 | 23.51 | 0 | 262.55 | 73.83 | 80
118 | JALPAIGURI | SM/14224 | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | TSM/016181 | 40033017 | New | SVS | GO2223011802PH | 10/01/2023 | 91.28 | 49.15 | 140.42 | Jalpaiguri Division | Northern Mechanical Division | 6.57 | 3.66 | 3.94 | 0 | 14.17 | 6.57 | 3.66 | 3.94 | 0 | 14.17 | 10.09 | 40
119 | JALPAIGURI | SM/07044 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Porjhar Piped water Supply Scheme. | TSM/006354 | 8138300 | Retrofitting | SVS | GO2021002714PH | 24/11/2020 | 93.9 | 0 | 93.9 | Siliguri W/S Division |  | 0.48 | 0 | 0 | 0 | 0.48 | 0.48 | 0 | 0 | 0 | 0.48 | 0.51 | 70
120 | JALPAIGURI | SM/07028 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme | TSM/006355 | 8136875 | Retrofitting | MVS | GO2021002619PH | 13/11/2020 | 96.79 | 0 | 96.79 | Siliguri W/S Division |  | 70.76 | 0 | 0 | 0 | 70.76 | 70.76 | 0 | 0 | 0 | 70.76 | 73.11 | 48
121 | JALPAIGURI | SM/08036 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | TSM/006194 | 8192490 | Retrofitting | MVS | GO2021006020PH | 02/02/2021 | 349.29 | 0 | 349.29 | Jalpaiguri Division |  | 349.29 | 0 | 0 | 0 | 349.29 | 285.33 | 0 | 0 | 0 | 285.33 | 81.69 | 90
122 | JALPAIGURI | SM/06840 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | TSM/005793 | 8129285 | Retrofitting | MVS | GO2021001734PH | 06/10/2020 | 74.02 | 0 | 74.02 | Jalpaiguri Division |  | 74.02 | 0 | 0 | 0 | 74.02 | 92.52 | 0 | 0 | 0 | 92.52 | 124.99 | 99
123 | JALPAIGURI | SM/06936 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | TSM/005796 | 8129330 | Retrofitting | MVS | GO2021002302PH | 03/11/2020 | 126.48 | 0 | 126.48 | Jalpaiguri Division |  | 124.94 | 0 | 0 | 0 | 124.94 | 111.78 | 0 | 0 | 0 | 111.78 | 88.37 | 88
124 | JALPAIGURI | SM/06958 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | TSM/006192 | 8136015 | Retrofitting | MVS | GO2021002289PH | 03/11/2020 | 99.31 | 0 | 99.31 | Jalpaiguri Division |  | 99.31 | 0 | 0 | 0 | 99.31 | 121.12 | 0 | 0 | 0 | 121.12 | 121.96 | 40
125 | JALPAIGURI | SM/06954 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006193 | 8136024 | Retrofitting | SVS | GO2021002290PH | 03/11/2020 | 34.5 | 0 | 34.5 | Jalpaiguri Division |  | 34.5 | 0 | 0 | 0 | 34.5 | 60.16 | 0 | 0 | 0 | 60.16 | 174.37 | 82
126 | JALPAIGURI | SM/08285 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | TSM/006199 | 8206637 | Retrofitting | MVS | GO2021006676PH | 09/02/2021 | 268.15 | 0 | 268.15 | Jalpaiguri Division |  | 268.15 | 0 | 0 | 0 | 268.15 | 266.3 | 0 | 0 | 0 | 266.3 | 99.31 | 90
127 | JALPAIGURI | SM/06937 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | TSM/005794 | 8129777 | Retrofitting | MVS | GO2021002298PH | 03/11/2020 | 129.58 | 0 | 129.58 | Jalpaiguri Division |  | 126.3 | 0 | 0 | 0 | 126.3 | 112.72 | 0 | 0 | 0 | 112.72 | 86.99 | 80
128 | JALPAIGURI | SM/06960 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme | TSM/006214 | 8136850 | Retrofitting | SVS | GO2021002295PH | 03/11/2020 | 99.43 | 0 | 99.43 | Jalpaiguri Division |  | 50 | 0 | 0 | 0 | 50 | 8.94 | 0 | 0 | 0 | 8.94 | 8.99 | 90
129 | JALPAIGURI | SM/06961 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme | TSM/006215 | 8136865 | Retrofitting | MVS | GO2021002296PH | 03/11/2020 | 75.45 | 0 | 75.45 | Jalpaiguri Division |  | 75.45 | 0 | 0 | 0 | 75.45 | 35.13 | 0 | 0 | 0 | 35.13 | 46.56 | 90
130 | JALPAIGURI | SM/06841 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme | TSM/005795 | 8130525 | Retrofitting | MVS | GO2021001735PH | 06/10/2020 | 89.57 | 0 | 89.57 | Jalpaiguri Division |  | 89.57 | 0 | 0 | 0 | 89.57 | 89.1 | 0 | 0 | 0 | 89.1 | 99.47 | 100
131 | JALPAIGURI | SM/07301 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | TSM/006198 | 8136885 | Retrofitting | SVS | GO2021003278PH | 10/12/2020 | 30.18 | 0 | 30.18 | Jalpaiguri Division |  | 30.18 | 0 | 0 | 0 | 30.18 | 30.12 | 0 | 0 | 0 | 30.12 | 99.79 | 90
132 | JALPAIGURI | SM/08038 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | TSM/006206 | 8192577 | Retrofitting | SVS | GO2021006015PH | 02/02/2021 | 396.46 | 0 | 396.46 | Jalpaiguri Division |  | 396.46 | 0 | 0 | 0 | 396.46 | 407.81 | 0 | 0 | 0 | 407.81 | 102.86 | 99
133 | JALPAIGURI | SM/06957 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | TSM/006203 | 8129420 | Retrofitting | SVS | GO2021002293PH | 03/11/2020 | 36 | 0 | 36 | Jalpaiguri Division |  | 36 | 0 | 0 | 0 | 36 | 35.97 | 0 | 0 | 0 | 35.97 | 99.9 | 85
134 | JALPAIGURI | SM/06953 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | TSM/006201 | 8129274 | Retrofitting | SVS | GO2021002292PH | 03/11/2020 | 48.9 | 0 | 48.9 | Jalpaiguri Division |  | 48.9 | 0 | 0 | 0 | 48.9 | 48.83 | 0 | 0 | 0 | 48.83 | 99.85 | 86
135 | JALPAIGURI | SM/06952 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006195 | 8136029 | Retrofitting | SVS | GO2021002291PH | 03/11/2020 | 65.98 | 0 | 65.98 | Jalpaiguri Division |  | 65.98 | 0 | 0 | 0 | 65.98 | 65.37 | 0 | 0 | 0 | 65.37 | 99.08 | 80
136 | JALPAIGURI | SM/06839 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | TSM/005792 | 8129763 | Retrofitting | MVS | GO2021001733PH | 06/10/2020 | 99.99 | 0 | 99.99 | Jalpaiguri Division |  | 81.35 | 0 | 0 | 0 | 81.35 | 84.11 | 0 | 0 | 0 | 84.11 | 84.12 | 80
137 | JALPAIGURI | SM/06955 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006191 | 8129329 | Retrofitting | SVS | GO2021002288PH | 03/11/2020 | 62.52 | 0 | 62.52 | Jalpaiguri Division |  | 62.52 | 0 | 0 | 0 | 62.52 | 81.43 | 0 | 0 | 0 | 81.43 | 130.23 | 85
138 | JALPAIGURI | SM/06938 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | TSM/005791 | 6904511 | Retrofitting | MVS | GO2021002297PH | 03/11/2020 | 106.41 | 0 | 106.41 | Jalpaiguri Division |  | 78.09 | 0 | 0 | 0 | 78.09 | 71.51 | 0 | 0 | 0 | 71.51 | 67.2 | 100
139 | JALPAIGURI | SM/08037 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | TSM/006196 | 8192528 | Retrofitting | MVS | GO2021006018PH | 02/02/2021 | 348.32 | 0 | 348.32 | Jalpaiguri Division |  | 348.32 | 0 | 0 | 0 | 348.32 | 293.31 | 0 | 0 | 0 | 293.31 | 84.21 | 99
140 | JALPAIGURI | SM/07303 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | TSM/006213 | 8136862 | Retrofitting | SVS | GO2021003276PH | 10/12/2020 | 89.78 | 0 | 89.78 | Jalpaiguri Division |  | 62 | 0 | 0 | 0 | 62 | 109.28 | 0 | 0 | 0 | 109.28 | 121.71 | 80
141 | JALPAIGURI | SM/08284 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | TSM/006197 | 8206631 | Retrofitting | MVS | GO2021006677PH | 09/02/2021 | 137.5 | 0 | 137.5 | Jalpaiguri Division |  | 23.63 | 0 | 0 | 0 | 23.63 | 19.02 | 0 | 0 | 0 | 19.02 | 13.83 | 25
142 | JALPAIGURI | SM/06956 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006190 | 8135974 | Retrofitting | SVS | GO2021002287PH | 03/11/2020 | 64.77 | 0 | 64.77 | Jalpaiguri Division |  | 64.77 | 0 | 0 | 0 | 64.77 | 64.68 | 0 | 0 | 0 | 64.68 | 99.85 | 88
143 | JALPAIGURI | SM/07304 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme | TSM/006216 | 8136868 | Retrofitting | MVS | GO2021003275PH | 10/12/2020 | 36.39 | 0 | 36.39 | Jalpaiguri Division |  | 36.39 | 0 | 0 | 0 | 36.39 | 71.86 | 0 | 0 | 0 | 71.86 | 197.48 | 83
144 | JALPAIGURI | SM/08035 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | TSM/006189 | 8192435 | Retrofitting | SVS | GO2021006021PH | 02/02/2021 | 320.18 | 0 | 320.18 | Jalpaiguri Division |  | 130.17 | 0 | 0 | 0 | 130.17 | 125.34 | 0 | 0 | 0 | 125.34 | 39.15 | 60
145 | JALPAIGURI | SM/07302 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Pradhanpara Mouza Under Sajnapara Piped Water Supply Scheme | TSM/006208 | 8136093 | Retrofitting | SVS | GO2021003277PH | 10/12/2020 | 75.74 | 0 | 75.74 | Jalpaiguri Division |  | 75.74 | 0 | 0 | 0 | 75.74 | 3.5 | 0 | 0 | 0 | 3.5 | 4.62 | 90
146 | JALPAIGURI | SM/06959 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | TSM/006211 | 8136053 | Retrofitting | SVS | GO2021002294PH | 03/11/2020 | 57.13 | 0 | 57.13 | Jalpaiguri Division |  | 57.13 | 0 | 0 | 0 | 57.13 | 118.72 | 0 | 0 | 0 | 118.72 | 207.81 | 90
147 | JALPAIGURI | SM/08078 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block | TSM/007025 | 8193747 | Retrofitting | MVS | GO2021006209PH | 04/02/2021 | 136.18 | 0 | 136.18 | Jalpaiguri Division |  | 23.97 | 0 | 0 | 0 | 23.97 | 23.97 | 0 | 0 | 0 | 23.97 | 17.6 | 30
148 | JALPAIGURI | SM/09100 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | TSM/007026 | 8382160 | Retrofitting | MVS | GO2122004567PH | 28/10/2021 | 382.83 | 0 | 382.83 | Jalpaiguri Division |  | 260.43 | 0 | 0 | 0 | 260.43 | 247.22 | 0 | 0 | 0 | 247.22 | 64.58 | 60
149 | JALPAIGURI | SM/08077 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | TSM/007024 | 8193726 | Retrofitting | MVS | GO2021006210PH | 04/02/2021 | 62.08 | 0 | 62.08 | Jalpaiguri Division |  | 62.08 | 0 | 0 | 0 | 62.08 | 61.14 | 0 | 0 | 0 | 61.14 | 98.49 | 85
150 | JALPAIGURI | SM/09099 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | TSM/007485 | 8382155 | Retrofitting | MVS | GO2122004577PH | 28/10/2021 | 163.94 | 0 | 163.94 | Jalpaiguri Division | Northern Mechanical Division | 116.68 | 0 | 0 | 0 | 116.68 | 113.68 | 0 | 0 | 0 | 113.68 | 69.34 | 80
151 | JALPAIGURI | SM/06842 | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme | TSM/005797 | 7718340 | Retrofitting | SVS | GO2021001736PH | 06/10/2020 | 48.73 | 0 | 48.73 | Jalpaiguri Division |  | 10.56 | 0 | 0 | 0 | 10.56 | 10.56 | 0 | 0 | 0 | 10.56 | 21.66 | 84
152 | JALPAIGURI | SM/16776 | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | TSM/018684 | 40058371 | New | SVS | GO2223015826PH | 13/03/2023 | 40.49 | 48.54 | 89.03 | Jalpaiguri Division | Northern Mechanical Division | 8.92 | 0.21 | 0 | 0 | 9.13 | 8.92 | 0.21 | 0 | 0 | 9.13 | 10.25 | 65
153 | JALPAIGURI | SM/14881 | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | TSM/017836 | 40036017 | New | MVS | GO2223013012PH | 03/02/2023 | 606.88 | 74.39 | 681.26 | Jalpaiguri Division | Northern Mechanical Division | 122.49 | 17.27 | 19.04 | 0 | 158.8 | 122.49 | 17.27 | 19.04 | 0 | 158.8 | 23.31 | 62
154 | JALPAIGURI | SM/14880 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017838 | 40049257 | New | MVS | PH222371613S000 | 03/02/2023 | 633.63 | 98.46 | 732.1 | Jalpaiguri Division | Northern Mechanical Division | 77.3 | 26.43 | 12.63 | 0 | 116.36 | 72.41 | 26.43 | 12.63 | 0 | 111.46 | 15.23 | 22
155 | JALPAIGURI | SM/14885 | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016190 | 40036016 | New | MVS | GO2223013014PH | 03/02/2023 | 815.63 | 97.9 | 913.53 | Jalpaiguri Division | Northern Mechanical Division | 578.97 | 69.03 | 56.03 | 0 | 704.03 | 587.91 | 78.99 | 56.03 | 0 | 722.94 | 79.14 | 90
156 | JALPAIGURI | SM/15103 | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | TSM/017971 | 40060564 | Augmentation | SVS | GO2223013201PH | 04/02/2023 | 101.69 | 48.05 | 149.74 | Jalpaiguri Division | Northern Mechanical Division | 54.27 | 26.47 | 0 | 0 | 80.74 | 50.6 | 26.47 | 0 | 0 | 77.07 | 51.47 | 80
157 | JALPAIGURI | SM/15082 | Rejuvenation for Manabari Tea Garden | TSM/018002 | 40060611 | Augmentation | MVS | GO2223013217PH | 04/02/2023 | 159.45 | 70.17 | 229.62 | Jalpaiguri Division | Northern Mechanical Division | 19.92 | 7.51 | 21.06 | 0 | 48.49 | 19.92 | 7.51 | 21.06 | 0 | 48.49 | 21.12 | 30
158 | JALPAIGURI | SM/15085 | Rejuvenation for Patkidaha Piped Water Supply Scheme | TSM/017986 | 40057345 | Augmentation | MVS | GO2223013197PH | 04/02/2023 | 96.2 | 48.95 | 145.15 | Jalpaiguri Division | Northern Mechanical Division | 49.22 | 15.12 | 2.56 | 0 | 66.9 | 49.22 | 15.12 | 2.56 | 0 | 66.9 | 46.09 | 80
159 | JALPAIGURI | SM/17185 | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | TSM/011016 | 40060633 | Augmentation | SVS | GO2223016072PH | 15/03/2023 | 138.2 | 41.84 | 180.04 | Jalpaiguri Division | Northern Mechanical Division | 67.14 | 34.78 | 5.79 | 0 | 107.71 | 67.14 | 34.78 | 5.79 | 0 | 107.71 | 59.83 | 99
160 | JALPAIGURI | SM/15089 | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | TSM/017709 | 40057346 | Augmentation | MVS | GO2223013206PH | 04/02/2023 | 103.06 | 48.54 | 151.59 | Jalpaiguri Division | Northern Mechanical Division | 21.42 | 11.97 | 0 | 0 | 33.4 | 21.42 | 11.97 | 0 | 0 | 33.4 | 22.03 | 35
161 | JALPAIGURI | SM/09487 | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | TSM/009024 | 40005898 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 178.35 | 39.13 | 217.47 | Jalpaiguri Division | Northern Mechanical Division | 37.44 | 31.73 | 3.29 | 19.6 | 92.07 | 37.44 | 31.73 | 3.29 | 19.6 | 92.07 | 42.34 | 45
162 | JALPAIGURI | SM/15338 | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | TSM/019578 | 40059503 | Augmentation | MVS | GO2223013603PH | 09/02/2023 | 72.72 | 48.54 | 121.26 | Jalpaiguri Division | Northern Mechanical Division | 14.53 | 20.37 | 42.03 | 0 | 76.93 | 14.53 | 20.37 | 42.03 | 0 | 76.93 | 63.44 | 80
163 | JALPAIGURI | SM/09518 | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | TSM/008107 | 40003695 | Augmentation | MVS | GO2122005574PH | 19/11/2021 | 79.83 | 34.51 | 114.34 | Jalpaiguri Division | Northern Mechanical Division | 64.21 | 26.14 | 3.69 | 0 | 94.03 | 49.03 | 26.14 | 3.69 | 0 | 78.85 | 68.96 | 90
164 | JALPAIGURI | SM/15030 | REJUVENATION OF ARJI GARALBARI PWSS | TSM/018283 | 40059502 | Augmentation | MVS | GO2223013142PH | 04/02/2023 | 100.51 | 71.93 | 172.44 | Jalpaiguri Division | Northern Mechanical Division | 47.65 | 35.67 | 0 | 0 | 83.32 | 47.65 | 35.67 | 0 | 0 | 83.32 | 48.32 | 95
165 | JALPAIGURI | SM/15059 | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | TSM/018100 | 40060627 | Augmentation | SVS | GO2223013218PH | 04/02/2023 | 78.7 | 48.54 | 127.24 | Jalpaiguri Division | Northern Mechanical Division | 37.02 | 19.54 | 5.48 | 0 | 62.04 | 37.02 | 19.54 | 5.48 | 0 | 62.04 | 48.76 | 45
166 | JALPAIGURI | SM/09460 | Rejuvenation of Basilardanga piped water supply scheme. | TSM/008103 | 40004171 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 80.59 | 34.57 | 115.16 | Jalpaiguri Division | Northern Mechanical Division | 74.16 | 30.84 | 0 | 0 | 105.01 | 74.16 | 30.84 | 0 | 0 | 105.01 | 91.18 | 97
167 | JALPAIGURI | SM/16773 | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011283 | 40060643 | Augmentation | SVS | GO2223015823PH | 13/03/2023 | 132.31 | 39.25 | 171.57 | Jalpaiguri Division | Northern Mechanical Division | 79.84 | 18.6 | 0 | 0 | 98.44 | 79.84 | 18.6 | 0 | 0 | 98.44 | 57.38 | 86
168 | JALPAIGURI | SM/15094 | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | TSM/017590 | 40056773 | Augmentation | MVS | GO2223013160PH | 04/02/2023 | 76.92 | 48.95 | 125.87 | Jalpaiguri Division | Northern Mechanical Division | 23.97 | 11.01 | 1.33 | 0 | 36.31 | 23.97 | 11.01 | 1.33 | 0 | 36.31 | 28.85 | 50
169 | JALPAIGURI | SM/15096 | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | TSM/017589 | 40060635 | Augmentation | MVS | GO2223013215PH | 04/02/2023 | 70.56 | 48.54 | 119.1 | Jalpaiguri Division | Northern Mechanical Division | 10.22 | 13.9 | 0 | 0 | 24.12 | 10.22 | 13.9 | 0 | 0 | 24.12 | 20.25 | 95
170 | JALPAIGURI | SM/15032 | Rejuvenation of Bhangarhat Piped Water Supply Scheme | TSM/018110 | 40060653 | Augmentation | MVS | GO2223013202PH | 04/02/2023 | 129.77 | 48.54 | 178.3 | Jalpaiguri Division | Northern Mechanical Division | 26.99 | 8.2 | 2.77 | 0 | 37.96 | 26.99 | 8.2 | 2.77 | 0 | 37.96 | 21.29 | 95
171 | JALPAIGURI | SM/09462 | Rejuvenation of Boalmari piped water supply scheme. | TSM/008104 | 40004800 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 78.8 | 34.8 | 113.6 | Jalpaiguri Division | Northern Mechanical Division | 73.8 | 30.77 | 3.69 | 0 | 108.26 | 73.8 | 30.77 | 3.69 | 0 | 108.26 | 95.29 | 99
172 | JALPAIGURI | SM/09482 | Rejuvenation of Chakiavita Piped Water Supply Scheme | TSM/008824 | 40005902 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 81.58 | 38.39 | 119.98 | Jalpaiguri Division | Northern Mechanical Division | 74.42 | 36.08 | 0 | 0 | 110.5 | 74.05 | 36.08 | 0 | 0 | 110.12 | 91.79 | 85
173 | JALPAIGURI | SM/09458 | Rejuvenation of Charerbari piped water supply scheme. | TSM/008106 | 40003841 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 81.1 | 34.83 | 115.93 | Jalpaiguri Division | Northern Mechanical Division | 71.35 | 21.67 | 3.31 | 0 | 96.33 | 73 | 21.67 | 3.31 | 0 | 97.98 | 84.52 | 98
174 | JALPAIGURI | SM/15033 | Rejuvenation of Chauhaddi Piped Water Supply Scheme | TSM/018108 | 40059498 | Augmentation | MVS | GO2223013155PH | 04/02/2023 | 150.2 | 48.6 | 198.79 | Jalpaiguri Division | Northern Mechanical Division | 54.03 | 5.39 | 0 | 0 | 59.42 | 54.03 | 5.39 | 0 | 0 | 59.42 | 29.89 | 80
175 | JALPAIGURI | SM/09484 | Rejuvenation of Chauhaddi Piped Water Supply Scheme | TSM/009001 | 40005901 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 206.83 | 19.49 | 226.32 | Jalpaiguri Division | Northern Mechanical Division | 194.11 | 16.99 | 0 | 0 | 211.1 | 189.17 | 16.99 | 0 | 0 | 206.16 | 91.09 | 70
176 | JALPAIGURI | SM/15114 | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | TSM/011303 | 40059478 | Augmentation | SVS | GO2223013196PH | 04/02/2023 | 211.87 | 43.6 | 255.47 | Jalpaiguri Division | Northern Mechanical Division | 130.98 | 31.53 | 14.97 | 0 | 177.47 | 130.98 | 31.53 | 14.97 | 0 | 177.47 | 69.47 | 78
177 | JALPAIGURI | SM/18283 | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | TSM/010970 | 40064178 | Augmentation | SVS | 1624/PHE-28011/75/2023-ESTT CELL-Dept. of PHE | 23/06/2023 | 2617.64 | 245.14 | 2862.78 | Jalpaiguri Division | Northern Mechanical Division | 251.69 | 100.88 | 313.99 | 0 | 666.57 | 251.69 | 100.88 | 313.99 | 0 | 666.57 | 23.28 | 40
178 | JALPAIGURI | SM/15087 | REJUVENATION OF DAKSHIN SALBARI PWSS | TSM/017943 | 40060560 | Augmentation | MVS | GO2223013216PH | 04/02/2023 | 175.12 | 71.12 | 246.25 | Jalpaiguri Division | Northern Mechanical Division | 21.8 | 4.45 | 4 | 0 | 30.24 | 21.8 | 4.15 | 4 | 0 | 29.94 | 12.16 | 85
179 | JALPAIGURI | SM/11812 | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/009995 | 40060609 | Augmentation | SVS | GO2223006326PH | 16/08/2022 | 74.48 | 20.25 | 94.73 | Jalpaiguri Division | Northern Mechanical Division | 41.72 | 2.88 | 0 | 0 | 44.6 | 41.86 | 2.88 | 0 | 0 | 44.74 | 47.23 | 95
180 | JALPAIGURI | SM/09459 | Rejuvenation of Dwarikamari piped water supply scheme. | TSM/008109 | 40004150 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 86.51 | 34.89 | 121.4 | Jalpaiguri Division | Northern Mechanical Division | 86.51 | 28.98 | 0 | 0 | 115.49 | 86.51 | 27.73 | 0 | 0 | 114.24 | 94.1 | 95
181 | JALPAIGURI | SM/17681 | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011592 | 40036028 | Augmentation | SVS | GO2223015886PH | 17/03/2023 | 74.37 | 41.79 | 116.16 | Jalpaiguri Division | Northern Mechanical Division | 31.04 | 39.88 | 0 | 0 | 70.92 | 30.39 | 39.88 | 0 | 0 | 70.27 | 60.5 | 70
182 | JALPAIGURI | SM/17181 | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | TSM/011005 | 40060604 | Augmentation | SVS | GO2223016069PH | 15/03/2023 | 157.6 | 44.06 | 201.66 | Jalpaiguri Division | Northern Mechanical Division | 0 | 2.97 | 4.08 | 0 | 7.04 | 0 | 2.97 | 4.08 | 0 | 7.04 | 3.49 | 5
183 | JALPAIGURI | SM/09390 | Rejuvenation of Goralbari Piped Water Supply Scheme | TSM/008375 | 40003473 | Augmentation | SVS | GO2122005377PH | 12/11/2021 | 165.91 | 171.63 | 337.55 | Jalpaiguri Division | Northern Mechanical Division | 165.91 | 73.62 | 0 | 0 | 239.53 | 261.32 | 73.62 | 0 | 0 | 334.94 | 99.23 | 98
184 | JALPAIGURI | SM/15130 | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | TSM/018042 | 40060618 | Augmentation | SVS | GO2223013193PH | 04/02/2023 | 134.2 | 48.54 | 182.74 | Jalpaiguri Division | Northern Mechanical Division | 24.9 | 21.28 | 0 | 0 | 46.18 | 24.9 | 21.28 | 0 | 0 | 46.18 | 25.27 | 70
185 | JALPAIGURI | SM/16772 | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | TSM/017935 | 40060597 | Augmentation | SVS | GO2223015831PH | 13/03/2023 | 107.3 | 48.95 | 156.25 | Jalpaiguri Division | Northern Mechanical Division | 23.15 | 8.02 | 0 | 0 | 31.17 | 23.15 | 8.02 | 0 | 0 | 31.17 | 19.95 | 80
186 | JALPAIGURI | SM/15031 | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | TSM/018224 | 40060568 | Augmentation | MVS | GO2223013211PH | 04/02/2023 | 90.06 | 71.93 | 161.99 | Jalpaiguri Division | Northern Mechanical Division | 62.73 | 34.75 | 5.1 | 0 | 102.58 | 62.73 | 34.75 | 5.1 | 0 | 102.58 | 63.32 | 90
187 | JALPAIGURI | SM/10070 | Rejuvenation of Hila Tea Garden area piped water supply scheme | TSM/009745 | 40002852 | Augmentation | SVS | GO2122008791PH | 27/01/2022 | 167.86 | 40.48 | 208.35 | Jalpaiguri Division | Northern Mechanical Division | 122.41 | 36.64 | 0 | 0 | 159.04 | 114.69 | 36.64 | 0 | 0 | 151.33 | 72.63 | 95
188 | JALPAIGURI | SM/15109 | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | TSM/017864 | 40064182 | Augmentation | SVS | GO2223013214PH | 04/02/2023 | 111 | 71.12 | 182.13 | Jalpaiguri Division | Northern Mechanical Division | 32.93 | 10.69 | 5.1 | 0 | 48.72 | 32.93 | 10.69 | 5.1 | 0 | 48.72 | 26.75 | 44
189 | JALPAIGURI | SM/15068 | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | TSM/018310 | 40060647 | Augmentation | SVS | GO2223013204PH | 04/02/2023 | 22.33 | 48.54 | 70.86 | Jalpaiguri Division | Northern Mechanical Division | 15.01 | 20.19 | 1.33 | 0 | 36.52 | 15.01 | 20.19 | 1.33 | 0 | 36.52 | 51.54 | 82
190 | JALPAIGURI | SM/10069 | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | TSM/009749 | 7422877 | Augmentation | SVS | GO2122008791PH | 27/01/2022 | 201.53 | 42.16 | 243.7 | Jalpaiguri Division | Northern Mechanical Division | 133.41 | 37.84 | 0 | 0 | 171.25 | 133.41 | 37.84 | 0 | 0 | 171.25 | 70.27 | 100
191 | JALPAIGURI | SM/09457 | Rejuvenation of Kajaldighi piped water supply scheme. | TSM/008110 | 40003831 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 82.33 | 34.57 | 116.9 | Jalpaiguri Division | Northern Mechanical Division | 59.92 | 6.56 | 0 | 0 | 66.48 | 59.92 | 6.56 | 0 | 0 | 66.48 | 56.87 | 95
192 | JALPAIGURI | SM/15298 | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | TSM/011312 | 40060652 | Augmentation | SVS | GO2223013597PH | 09/02/2023 | 198.34 | 43.1 | 241.44 | Jalpaiguri Division | Northern Mechanical Division | 113.73 | 21.72 | 13.15 | 0 | 148.6 | 113.73 | 21.72 | 13.15 | 0 | 148.6 | 61.55 | 90
193 | JALPAIGURI | SM/09392 | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | TSM/008374 | 40020983 | Augmentation | SVS | GO2122005377PH | 12/11/2021 | 191.17 | 99.65 | 290.82 | Jalpaiguri Division | Northern Mechanical Division | 135.06 | 36.13 | 0 | 0 | 171.19 | 133.85 | 36.13 | 0 | 0 | 169.98 | 58.45 | 70
194 | JALPAIGURI | SM/09486 | Rejuvenation of Khalaigram Piped Water Supply Scheme | TSM/009016 | 40005899 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 46.61 | 19.53 | 66.14 | Jalpaiguri Division | Northern Mechanical Division | 33.96 | 15.28 | 0 | 0 | 49.24 | 33.96 | 17.97 | 0 | 0 | 51.93 | 78.52 | 80
195 | JALPAIGURI | SM/09461 | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | TSM/008155 | 7827508 | Augmentation | SVS | GO2122005570PH | 19/11/2021 | 70.07 | 0 | 70.07 | Jalpaiguri Division | Northern Mechanical Division | 70.07 | 0 | 0 | 0 | 70.07 | 88.91 | 0 | 0 | 0 | 88.91 | 126.9 | 100
196 | JALPAIGURI | SM/09456 | Rejuvenation of Madhabdanga piped water supply scheme. | TSM/008102 | 40015609 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 89.26 | 36.12 | 125.38 | Jalpaiguri Division | Northern Mechanical Division | 55.31 | 26.9 | 0 | 24.97 | 107.18 | 55.31 | 26.9 | 0 | 24.97 | 107.18 | 85.48 | 85
197 | JALPAIGURI | SM/09483 | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | TSM/008993 | 40006236 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 168.91 | 19.56 | 188.47 | Jalpaiguri Division | Northern Mechanical Division | 15.19 | 14.68 | 0 | 0 | 29.87 | 15.19 | 14.68 | 0 | 0 | 29.87 | 15.85 | 65
198 | JALPAIGURI | SM/09565 | Rejuvenation of Mainatali Piped Water Supply Scheme | TSM/008825 | 40007494 | Augmentation | MVS | GO2122005693PH | 22/11/2021 | 46.38 | 57.73 | 104.11 | Jalpaiguri Division | Northern Mechanical Division | 27.66 | 23.52 | 0 | 0 | 51.18 | 27.66 | 23.52 | 0 | 0 | 51.18 | 49.15 | 60
199 | JALPAIGURI | SM/18094 | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II | TSM/011411 | 40059494 | Augmentation | MVS | GO2223017757PH | 27/03/2023 | 185.13 | 0 | 185.13 | Jalpaiguri Division |  | 36.8 | 0 | 5.02 | 0 | 41.82 | 36.8 | 0 | 5.02 | 0 | 41.82 | 22.59 | 45
200 | JALPAIGURI | SM/09485 | Rejuvenation of Mallicksova Piped water Supply Scheme | TSM/009006 | 40005900 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 139.57 | 39.13 | 178.69 | Jalpaiguri Division | Northern Mechanical Division | 55.76 | 33.57 | 0 | 0 | 89.33 | 54.45 | 33.57 | 0 | 0 | 88.01 | 49.25 | 70
201 | JALPAIGURI | SM/15098 | Rejuvenation of Mathachulka Piped Water Supply Scheme | TSM/011305 | 40059476 | Augmentation | MVS | GO2223013213PH | 04/02/2023 | 134.56 | 40.64 | 175.2 | Jalpaiguri Division | Northern Mechanical Division | 48.5 | 9.3 | 23.23 | 0 | 81.03 | 48.5 | 9.3 | 23.23 | 0 | 81.03 | 46.25 | 60
202 | JALPAIGURI | SM/11813 | REJUVENATION OF METELIBAZAR PWSS | TSM/009996 | 40021195 | Augmentation | MVS | GO2223006326PH | 16/08/2022 | 657.92 | 63.15 | 721.07 | Jalpaiguri Division | Northern Mechanical Division | 191.14 | 14.97 | 0 | 0 | 206.11 | 191.14 | 14.97 | 0 | 0 | 206.11 | 28.58 | 25
203 | JALPAIGURI | SM/15075 | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | TSM/018016 | 40060603 | Augmentation | MVS | GO2223013200PH | 04/02/2023 | 109.33 | 48.95 | 158.29 | Jalpaiguri Division | Northern Mechanical Division | 32.43 | 13 | 2.77 | 0 | 48.19 | 32.43 | 13 | 2.77 | 0 | 48.19 | 30.45 | 80
204 | JALPAIGURI | SM/09519 | Rejuvenation of Mohitnagar piped water supply scheme. | TSM/008105 | 40003677 | Augmentation | MVS | GO2122005574PH | 19/11/2021 | 87.62 | 34.57 | 122.19 | Jalpaiguri Division | Northern Mechanical Division | 84.07 | 33.26 | 0 | 0 | 117.33 | 75.19 | 33.25 | 0 | 0 | 108.44 | 88.75 | 99
205 | JALPAIGURI | SM/09858 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/009023 | 40006395 | Augmentation | SVS | GO2122006497PH | 06/12/2021 | 132.35 | 39.15 | 171.5 | Jalpaiguri Division | Northern Mechanical Division | 72.97 | 27.76 | 0 | 0 | 100.73 | 71.91 | 27.76 | 0 | 0 | 99.67 | 58.12 | 95
206 | JALPAIGURI | SM/15060 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/018112 | 40056793 | Augmentation | SVS | GO2223013129PH | 04/02/2023 | 212.39 | 72.63 | 285.02 | Jalpaiguri Division | Northern Mechanical Division | 43.04 | 24.05 | 23.68 | 0 | 90.77 | 43.04 | 24.05 | 23.68 | 0 | 90.77 | 31.85 | 20
207 | JALPAIGURI | SM/15300 | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | TSM/011304 | 40060657 | Augmentation | SVS | GO2223013613PH | 09/02/2023 | 117.85 | 42.12 | 159.96 | Jalpaiguri Division | Northern Mechanical Division | 95.29 | 32.96 | 12.54 | 0 | 140.78 | 95.29 | 32.96 | 12.54 | 0 | 140.78 | 88.01 | 85
208 | JALPAIGURI | SM/15116 | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | TSM/018613 | 40060622 | Augmentation | SVS | GO2223013205PH | 04/02/2023 | 124.26 | 70.17 | 194.43 | Jalpaiguri Division | Northern Mechanical Division | 56.44 | 47.02 | 7.48 | 0 | 110.93 | 56.44 | 47.02 | 7.48 | 0 | 110.93 | 57.05 | 85
209 | JALPAIGURI | SM/09863 | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | TSM/009020 | 40006405 | Augmentation | SVS | GO2122006496PH | 06/12/2021 | 131.67 | 41.12 | 172.79 | Jalpaiguri Division | Northern Mechanical Division | 83.92 | 34 | 0 | 0 | 117.92 | 83.92 | 34 | 0 | 0 | 117.92 | 68.25 | 80
210 | JALPAIGURI | SM/15099 | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | TSM/018018 | 40060649 | Augmentation | SVS | GO2223013166PH | 04/02/2023 | 102.54 | 48.05 | 150.59 | Jalpaiguri Division | Northern Mechanical Division | 35.05 | 3.9 | 0 | 0 | 38.96 | 35.05 | 3.9 | 0 | 0 | 38.96 | 25.87 | 70
211 | JALPAIGURI | SM/15076 | REJUVENATION OF PASCHIM SALBARI PWSS | TSM/018057 | 40060600 | Augmentation | MVS | GO2223013146PH | 04/02/2023 | 328.27 | 71.12 | 399.4 | Jalpaiguri Division | Northern Mechanical Division | 14.83 | 31.52 | 0 | 0 | 46.34 | 14.83 | 31.52 | 0 | 0 | 46.34 | 11.6 | 25
212 | JALPAIGURI | SM/15101 | REJUVENATION OF PORA PARA PWSS | TSM/017999 | 40059500 | Augmentation | SVS | GO2223013192PH | 04/02/2023 | 371.96 | 52.31 | 424.27 | Jalpaiguri Division | Northern Mechanical Division | 61.44 | 23.45 | 0 | 0 | 84.9 | 61.44 | 23.45 | 0 | 0 | 84.9 | 20.01
213 | JALPAIGURI | SM/09463 | Rejuvenation of Porapara piped water supply scheme. | TSM/008108 | 40004181 | Augmentation | SVS | GO2122005570PH | 19/11/2021 | 85.06 | 36.2 | 121.26 | Jalpaiguri Division | Northern Mechanical Division | 81.62 | 30.5 | 0 | 0 | 112.12 | 81.62 | 29 | 0 | 0 | 110.62 | 91.22 | 90
214 | JALPAIGURI | SM/15326 | Rejuvenation of Purba Duramari Piped Water Supply Scheme | TSM/018104 | 40060660 | Augmentation | MVS | GO2223013604PH | 09/02/2023 | 158.04 | 48.54 | 206.58 | Jalpaiguri Division | Northern Mechanical Division | 23.45 | 24.26 | 3.69 | 0 | 51.4 | 23.45 | 24.26 | 3.69 | 0 | 51.4 | 24.88 | 70
215 | JALPAIGURI | SM/09564 | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | TSM/008823 | 40017895 | Augmentation | MVS | GO2122005693PH | 22/11/2021 | 52.96 | 86.22 | 139.18 | Jalpaiguri Division | Northern Mechanical Division | 38.79 | 29.14 | 0 | 0 | 67.93 | 36.42 | 29.14 | 0 | 0 | 65.56 | 47.1 | 65
216 | JALPAIGURI | SM/09861 | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | TSM/008817 | 40006244 | Augmentation | MVS | GO2122006496PH | 06/12/2021 | 677.35 | 19.24 | 696.59 | Jalpaiguri Division | Northern Mechanical Division | 620.81 | 15.65 | 26.95 | 0 | 663.42 | 518.88 | 15.65 | 26.95 | 0 | 561.48 | 80.6 | 85
217 | JALPAIGURI | SM/15071 | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | TSM/018227 | 40060630 | Augmentation | SVS | GO2223013151PH | 04/02/2023 | 108.03 | 69.01 | 177.04 | Jalpaiguri Division | Northern Mechanical Division | 37.49 | 16.5 | 0 | 0 | 53.99 | 37.49 | 16.5 | 0 | 0 | 53.99 | 30.5 | 90
218 | JALPAIGURI | SM/09391 | Rejuvenation of Sajnapara Piped Water Supply Scheme | TSM/008378 | 40003488 | Augmentation | MVS | GO2122005377PH | 12/11/2021 | 32.89 | 59.47 | 92.36 | Jalpaiguri Division | Northern Mechanical Division | 15.73 | 21.79 | 0 | 0 | 37.52 | 15.73 | 14.99 | 0 | 0 | 30.72 | 33.26 | 80
219 | JALPAIGURI | SM/15301 | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | TSM/011306 | 40060585 | Augmentation | SVS | GO2223013605PH | 09/02/2023 | 257.86 | 133.62 | 391.48 | Jalpaiguri Division | Northern Mechanical Division | 33.2 | 38.67 | 19.75 | 0 | 91.63 | 33.2 | 38.67 | 19.75 | 0 | 91.63 | 23.41 | 30
220 | JALPAIGURI | SM/18713 | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme | TSM/010092 | 40060591 | Augmentation | SVS | 2262/PHE/IV/W-615/23 | 04/08/2023 | 174.01 | 39.68 | 213.69 | Jalpaiguri Division | Northern Mechanical Division | 13.3 | 9.87 | 12.16 | 0 | 35.32 | 13.3 | 9.87 | 12.16 | 0 | 35.32 | 16.53 | 38
221 | JALPAIGURI | SM/15077 | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/017647 | 40060581 | Augmentation | SVS | GO2223013135PH | 04/02/2023 | 131.73 | 48.54 | 180.27 | Jalpaiguri Division | Northern Mechanical Division | 21.39 | 16 | 2.6 | 0 | 39.98 | 21.39 | 16 | 2.6 | 0 | 39.98 | 22.18
222 | JALPAIGURI | SM/15117 | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | TSM/011311 | 40060582 | Augmentation | SVS | GO2223013208PH | 04/02/2023 | 153.65 | 43.02 | 196.67 | Jalpaiguri Division | Northern Mechanical Division | 125.11 | 27.64 | 8.97 | 0 | 161.71 | 125.11 | 27.64 | 8.97 | 0 | 161.71 | 82.23 | 98
223 | JALPAIGURI | SM/16937 | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | TSM/018221 | 40059501 | Augmentation | MVS | GO2223016572PH | 16/03/2023 | 90.06 | 71.93 | 161.99 | Jalpaiguri Division | Northern Mechanical Division | 36.85 | 10.97 | 3.96 | 0 | 51.79 | 36.85 | 10.97 | 3.96 | 0 | 51.79 | 31.97 | 95
224 | JALPAIGURI | SM/15078 | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | TSM/018039 | 40060594 | Augmentation | MVS | GO2223013198PH | 04/02/2023 | 108.52 | 48.54 | 157.06 | Jalpaiguri Division | Northern Mechanical Division | 12.98 | 10.37 | 2.44 | 0 | 25.79 | 12.98 | 10.37 | 2.44 | 0 | 25.79 | 16.42 | 65
225 | JALPAIGURI | SM/09859 | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | TSM/009021 | 40006400 | Augmentation | SVS | GO2122006497PH | 06/12/2021 | 71.02 | 43.67 | 114.69 | Jalpaiguri Division | Northern Mechanical Division | 36.37 | 19.59 | 0 | 0 | 55.97 | 36.21 | 19.59 | 0 | 0 | 55.81 | 48.66 | 92
226 | JALPAIGURI | SM/09862 | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | TSM/009019 | 40006276 | Augmentation | SVS | GO2122006496PH | 06/12/2021 | 64.44 | 40.89 | 105.33 | Jalpaiguri Division | Northern Mechanical Division | 64.44 | 29.11 | 0 | 0 | 93.55 | 54.67 | 29.11 | 0 | 0 | 83.78 | 79.54 | 93
227 | JALPAIGURI | SM/09865 | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | TSM/009018 | 40006410 | Augmentation | SVS | GO2122006495PH | 06/12/2021 | 69.88 | 40.6 | 110.47 | Jalpaiguri Division | Northern Mechanical Division | 59.52 | 30.8 | 8.7 | 0 | 99.03 | 55.42 | 30.8 | 8.7 | 0 | 94.93 | 85.93 | 70
228 | JALPAIGURI | SM/15299 | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | TSM/011308 | 40059473 | Augmentation | SVS | GO2223013598PH | 09/02/2023 | 97.68 | 41.65 | 139.34 | Jalpaiguri Division | Northern Mechanical Division | 34.79 | 29.86 | 12.96 | 0 | 77.61 | 34.79 | 29.86 | 12.96 | 0 | 77.61 | 55.7 | 72
229 | JALPAIGURI | SM/15132 | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | TSM/018659 | 40059487 | Retrofitting | MVS | GO2223013210PH | 04/02/2023 | 189.88 | 0 | 189.88 | Jalpaiguri Division |  | 83.59 | 0 | 0 | 0 | 83.59 | 83.59 | 0 | 0 | 0 | 83.59 | 44.02 | 70
230 | JALPAIGURI | SM/15131 | RETROFITTING OF MAHITNAGAR PWSS | TSM/018681 | 40059486 | Retrofitting | MVS | GO2223013209PH | 04/02/2023 | 180.43 | 0 | 180.43 | Jalpaiguri Division |  | 75.34 | 0 | 0 | 0 | 75.34 | 75.34 | 0 | 0 | 0 | 75.34 | 41.76 | 98
231 | JALPAIGURI | SM/18625 | SALUGARA PIPED WATER SUPPLY SCHEME | TSM/014952 | 40035729 | New | SVS | 2164/PHE-28011/59/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1052.01 | 130.81 | 1182.82 | Jalpaiguri Division | Northern Mechanical Division | 163.92 | 53.67 | 95.53 | 0 | 313.11 | 163.92 | 53.67 | 95.53 | 0 | 313.11 | 26.47 | 30
232 | JALPAIGURI | SM/14200 | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | TSM/014950 | 40035736 | New | SVS | GO2223011793PH | 10/01/2023 | 649.56 | 129.54 | 779.1 | Jalpaiguri Division | Northern Mechanical Division | 206.63 | 79.44 | 48.62 | 0 | 334.69 | 199.78 | 83.61 | 48.62 | 0 | 332.01 | 42.61 | 80
233 | JALPAIGURI | SM/18759 | Saptibari Piped Water Supply Scheme. | TSM/003947 | 40035472 | New | MVS | 2526/PHE-28011/240/2023-SCHM CELL-Dept. of PHE | 23/08/2023 | 1913.89 | 112.79 | 2026.68 | Jalpaiguri Division | Northern Mechanical Division | 782.74 | 105.65 | 102.96 | 0 | 991.35 | 782.74 | 111.48 | 102.96 | 0 | 997.18 | 49.2 | 80
234 | JALPAIGURI | SM/18760 | Satkhamar Piped Water Supply Scheme. | TSM/004973 | 40035489 | New | MVS | 2526/PHE-28011/240/2023-SCHM CELL-Dept. of PHE | 23/08/2023 | 2023.64 | 114.14 | 2137.78 | Jalpaiguri Division | Northern Mechanical Division | 451.48 | 93.39 | 43.48 | 0 | 588.35 | 455.47 | 93.39 | 43.48 | 0 | 592.33 | 27.71 | 45
235 | JALPAIGURI | SM/13704 | SHAKATI PIPED WATER SUPPLY SCHEME | TSM/015419 | 40034877 | New | SVS | GO2223009706PH | 14/11/2022 | 492.17 | 65.53 | 557.7 | Jalpaiguri Division | Northern Mechanical Division | 262.84 | 27.42 | 32.99 | 0 | 323.24 | 252.03 | 29.74 | 32.99 | 0 | 314.76 | 56.44 | 75
236 | JALPAIGURI | SM/18836 | Sikarpur Piped Water Supply Scheme. | TSM/003956 | 0 | New | MVS | 2868/PHE-28011/247/2023-ESTT CELL-Dept. of PHE | 21/09/2023 | 1796.35 | 114.61 | 1910.96 | Jalpaiguri Division | Northern Mechanical Division | 574.02 | 36.35 | 0 | 0 | 610.37 | 580.6 | 36.35 | 0 | 0 | 616.95 | 32.28 | 44
237 | JALPAIGURI | SM/14240 | SIMULGURI PIPED WATER SUPPLY SCHEME | TSM/015430 | 40034094 | New | MVS | GO2223012001PH | 16/01/2023 | 944.98 | 227.29 | 1172.27 | Jalpaiguri Division | Northern Mechanical Division | 586.27 | 111.57 | 60.1 | 0 | 757.94 | 586.27 | 118.32 | 60.1 | 0 | 764.69 | 65.23 | 85
238 | JALPAIGURI | SM/18761 | Singimari Piped Water Supply Scheme. | TSM/003948 | 40035586 | New | MVS | 2526/PHE-28011/240/2023-SCHM CELL-Dept. of PHE | 23/08/2023 | 1081.59 | 57.38 | 1138.97 | Jalpaiguri Division | Northern Mechanical Division | 236.01 | 26.32 | 37.77 | 0 | 300.1 | 217.56 | 28.15 | 37.77 | 0 | 283.48 | 24.89 | 40
239 | JALPAIGURI | SM/16778 | Sisubari Tea Garden Piped Water Supply Scheme | TSM/018491 | 40058308 | New | SVS | GO2223015824PH | 13/03/2023 | 256.08 | 70.45 | 326.54 | Jalpaiguri Division | Northern Mechanical Division | 76.73 | 28.78 | 4.08 | 0 | 109.59 | 73.75 | 33.16 | 4.08 | 0 | 110.99 | 33.99
240 | JALPAIGURI | SM/15744 | SONAKHULI PIPED WATER SUPPLY SCHEME | TSM/014183 | 40035739 | New | MVS | GO2223014249PH | 20/02/2023 | 383.8 | 62.43 | 446.23 | Jalpaiguri Division | Northern Mechanical Division | 35.42 | 26.58 | 16.91 | 0 | 78.91 | 35.42 | 26.58 | 16.91 | 0 | 78.91 | 17.68 | 20
241 | JALPAIGURI | SM/08578 | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | TSM/006529 | 40037008 | New | SVS | GO2021006850PH | 10/02/2021 | 115.05 | 35.24 | 150.29 | Jalpaiguri Division | Northern Mechanical Division | 35.75 | 7.12 | 0 | 0 | 42.87 | 35.75 | 7.12 | 0 | 0 | 42.87 | 28.53 | 35
242 | JALPAIGURI | SM/08579 | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | TSM/006528 | 40053875 | New | SVS | GO2021006849PH | 10/02/2021 | 102.09 | 35.24 | 137.33 | Jalpaiguri Division | Northern Mechanical Division | 52.94 | 20.69 | 0 | 0 | 73.63 | 52.94 | 20.69 | 0 | 0 | 73.63 | 53.61
243 | JALPAIGURI | SM/08581 | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | TSM/006979 | 40021241 | New | SVS | GO2021006848PH | 10/02/2021 | 135.29 | 37.61 | 172.9 | Jalpaiguri Division | Northern Mechanical Division | 35.71 | 9.41 | 0 | 0 | 45.12 | 35.71 | 9.41 | 0 | 0 | 45.12 | 26.1 | 55
244 | JALPAIGURI | SM/15970 | TESIMALA PIPED WATER SUPPLY SCHEME | TSM/016202 | 40035912 | New | SVS | GO2223014701PH | 22/02/2023 | 355.72 | 36.02 | 391.74 | Jalpaiguri Division | Northern Mechanical Division | 105.44 | 30.22 | 7.02 | 0 | 142.68 | 105.44 | 34.09 | 7.02 | 0 | 146.55 | 37.41 | 55
245 | JALPAIGURI | SM/14883 | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | TSM/016364 | 40036019 | New | MVS | GO2223013019PH | 03/02/2023 | 470.8 | 73.51 | 544.31 | Jalpaiguri Division | Northern Mechanical Division | 35.47 | 33.2 | 44.28 | 0 | 112.95 | 35.47 | 36.7 | 44.28 | 0 | 116.45 | 21.39 | 80
246 | JALPAIGURI | SM/13899 | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | TSM/015326 | 40034109 | New | MVS | GO2223010078PH | 25/11/2022 | 685.18 | 87.68 | 772.86 | Jalpaiguri Division | Northern Mechanical Division | 449.86 | 42.11 | 34.6 | 0 | 526.56 | 449.86 | 47.69 | 34.6 | 0 | 532.15 | 68.85 | 65
247 | JALPAIGURI | SM/14660 | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | TSM/016180 | 40033019 | New | SVS | GO2223012739PH | 31/01/2023 | 482.87 | 37.59 | 520.46 | Jalpaiguri Division | Northern Mechanical Division | 163.06 | 25.07 | 19.98 | 0 | 208.11 | 163.06 | 25.07 | 19.98 | 0 | 208.11 | 39.99 | 70
248 | JALPAIGURI | SM/14919 | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | TSM/015976 | 40033020 | New | SVS | GO2223012954PH | 03/02/2023 | 297.05 | 69.04 | 366.08 | Jalpaiguri Division | Northern Mechanical Division | 101.33 | 40.39 | 22.05 | 0 | 163.76 | 101.33 | 46.72 | 22.05 | 0 | 170.09 | 46.46 | 80
249 | JALPAIGURI | SM/14914 | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | TSM/015975 | 40033022 | New | MVS | GO2223012955PH | 03/02/2023 | 409.35 | 68.87 | 478.22 | Jalpaiguri Division | Northern Mechanical Division | 154.82 | 31.43 | 52.84 | 0 | 239.08 | 154.82 | 31.43 | 52.84 | 0 | 239.08 | 49.99 | 55
250 | JALPAIGURI | SM/14886 | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016191 | 40049255 | New | MVS | GO2223013017PH | 03/02/2023 | 452.87 | 72.52 | 525.39 | Jalpaiguri Division | Northern Mechanical Division | 0 | 19.87 | 33.83 | 0 | 53.69 | 0 | 19.87 | 33.83 | 0 | 53.69 | 10.22 | 25
Total | [9 empty] | 108239.2 | 13219.68 | 121458.88 |  |  | 45336.29 | 5806.8 | 6422.64 | 126.05 | 57691.77 | 43956.84 | 6000.95 | 6422.64 | 126.05 | 56506.48 | 46.52