## JJM Schemes Financial Status (J
JJM Schemes Financial Status (JALPAIGURI) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | JALPAIGURI | SM/13706 | AMGURI PIPED WATER SUPPLY SCHEME | TSM/015418 | 40033102 | New | MVS | GO2223009708PH | 14/11/2022 | 825.28 | 66.06 | 891.35 | Jalpaiguri Division | Northern Mechanical Division | 305.34 | 10.73 | 50.5 | 0 | 366.57 | 279.53 | 10.73 | 50.5 | 0 | 340.75 | 38.23 | 11
2 | JALPAIGURI | SM/14884 | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016363 | 40036020 | New | MVS | GO2223013019PH | 03/02/2023 | 636 | 74.56 | 710.56 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JALPAIGURI | SM/10071 | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | TSM/009317 | 40002902 | Augmentation | MVS | GO2122008791PH | 27/01/2022 | 504.86 | 16.3 | 521.15 | Jalpaiguri Division | Northern Mechanical Division | 266.72 | 4.8 | 40.17 | 0 | 311.69 | 233.73 | 4.8 | 40.17 | 0 | 278.71 | 53.48 | 30
4 | JALPAIGURI | SM/10089 | Augmentation of Baikur Piped Water Supply Scheme. | TSM/006971 | 40003346 | Augmentation | MVS | GO2122009022PH | 01/02/2022 | 1708 | 55.63 | 1763.64 | Jalpaiguri Division | Northern Mechanical Division | 1257.14 | 42.35 | 27.59 | 0 | 1327.08 | 1137.53 | 42.35 | 27.59 | 0 | 1207.47 | 68.46 | 64
5 | JALPAIGURI | SM/10044 | Augmentation of Banerhat Bazar Piped Water Supply Scheme | TSM/009726 | 40002974 | Augmentation | MVS | GO2122008495PH | 20/01/2022 | 634.58 | 37.19 | 671.77 | Jalpaiguri Division | Northern Mechanical Division | 243.97 | 21.74 | 0 | 0 | 265.71 | 243.97 | 21.74 | 0 | 0 | 265.71 | 39.55 | 12
6 | JALPAIGURI | SM/10090 | Augmentation of Barnes Water Supply Scheme. | TSM/006966 | 40005894 | Augmentation | MVS | GO2122009022PH | 01/02/2022 | 1080.27 | 35.27 | 1115.54 | Jalpaiguri Division | Northern Mechanical Division | 798.34 | 31.33 | 107.56 | 4.21 | 941.44 | 695.09 | 31.33 | 107.56 | 4.21 | 838.19 | 75.14 | 56
7 | JALPAIGURI | SM/13277 | Augmentation of Bhatipara Water Supply Scheme | TSM/009740 | 40002912 | Augmentation | MVS | GO2223007816PH | 19/09/2022 | 0 | 0 | 0 | Jalpaiguri Division | Northern Mechanical Division | 490.92 | 41.79 | 0 | 33.56 | 566.27 | 490.92 | 41.79 | 0 | 33.56 | 566.27 | 0 | 1
8 | JALPAIGURI | SM/09344 | Augmentation of Binnaguri Piped Water Supply Scheme | TSM/008442 | 40005897 | Augmentation | SVS | GO2122005378PH | 12/11/2021 | 854.19 | 16.89 | 871.08 | Jalpaiguri Division | Northern Mechanical Division | 461.61 | 24.56 | 0 | 8.89 | 495.06 | 351.29 | 16.39 | 0 | 8.89 | 376.58 | 43.23 | 33
9 | JALPAIGURI | SM/08876 | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | TSM/005491 | 40014972 | Augmentation | MVS | GO2122003484PH | 22/09/2021 | 943.46 | 192.93 | 1136.39 | Jalpaiguri Division | Northern Mechanical Division | 364.5 | 54.3 | 0 | 0 | 418.8 | 337.3 | 54.3 | 0 | 0 | 391.59 | 34.46 | 18
10 | JALPAIGURI | SM/19175 | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018073 | 40060659 | Augmentation | SVS | :PHE-420/28011/204/2023-SCHM CELL-Dept. of PHE | 15/02/2024 | 789.26 | 477.02 | 1266.28 | Jalpaiguri Division | Northern Mechanical Division | 37.49 | 0 | 0 | 0 | 37.49 | 37.49 | 0 | 0 | 0 | 37.49 | 2.96 | 6
11 | JALPAIGURI | SM/10086 | Augmentation of Dakshin Berubari Water Supply Scheme. | TSM/006972 | 40006090 | Augmentation | SVS | GO2122009022PH | 01/02/2022 | 1555.51 | 18.76 | 1574.27 | Jalpaiguri Division | Northern Mechanical Division | 953.82 | 14.15 | 49.81 | 0 | 1017.77 | 778.21 | 14.15 | 49.81 | 0 | 842.17 | 53.5 | 52
12 | JALPAIGURI | SM/09561 | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme | TSM/008821 | 40005275 | Augmentation | MVS | GO2122005688PH | 22/11/2021 | 663.16 | 18.63 | 681.79 | Jalpaiguri Division | Northern Mechanical Division | 330.66 | 15.33 | 0 | 0 | 345.99 | 331.69 | 15.33 | 0 | 0 | 347.02 | 50.9 | 3
13 | JALPAIGURI | SM/09345 | Augmentation of Domohani Piped Water Supply Scheme | TSM/008382 | 40006249 | Augmentation | MVS | GO2122005379PH | 12/11/2021 | 838.64 | 16.92 | 855.56 | Jalpaiguri Division | Northern Mechanical Division | 533.82 | 16.42 | 5.5 | 10.56 | 566.31 | 561.89 | 16.42 | 5.5 | 10.56 | 594.37 | 69.47 | 70
14 | JALPAIGURI | SM/09860 | Augmentation of Gairkata Piped Water Supply Scheme | TSM/008816 | 40006242 | Augmentation | SVS | GO2122006497PH | 06/12/2021 | 462.05 | 18.48 | 480.53 | Jalpaiguri Division | Northern Mechanical Division | 83.38 | 11.8 | 3.56 | 0 | 98.74 | 69.68 | 11.8 | 3.56 | 0 | 85.04 | 17.7 | 5
15 | JALPAIGURI | SM/10043 | Augmentation of Jalapara Piped Water Supply Scheme | TSM/009324 | 40002882 | Augmentation | MVS | GO2122008494PH | 20/01/2022 | 586.92 | 33.94 | 620.86 | Jalpaiguri Division | Northern Mechanical Division | 120.13 | 0 | 0 | 0 | 120.13 | 119.99 | 0 | 0 | 0 | 119.99 | 19.33 | 12
16 | JALPAIGURI | SM/09563 | Augmentation of Kathapara Piped Water Supply Scheme | TSM/008819 | 40006252 | Augmentation | MVS | GO2122005689PH | 22/11/2021 | 815.67 | 19.21 | 834.88 | Jalpaiguri Division | Northern Mechanical Division | 290.19 | 10.48 | 11.75 | 0 | 312.42 | 187.93 | 10.48 | 0 | 0 | 198.41 | 23.77 | 20
17 | JALPAIGURI | SM/10088 | Augmentation of Kharija-Berubari Water Supply Scheme. | TSM/006967 | 40005879 | Augmentation | MVS | GO2122009022PH | 01/02/2022 | 2026.85 | 37.52 | 2064.37 | Jalpaiguri Division | Northern Mechanical Division | 993.98 | 19.14 | 114.29 | 0 | 1127.4 | 877.09 | 19.14 | 114.29 | 0 | 1010.52 | 48.95 | 40
18 | JALPAIGURI | SM/09994 | Augmentation of Kranti Piped water supply Scheme | TSM/008381 | 40005872 | Augmentation | MVS | GO2122007047PH | 20/12/2021 | 1720.91 | 34.89 | 1755.8 | Jalpaiguri Division | Northern Mechanical Division | 951.83 | 22.26 | 0 | 0 | 974.1 | 905.8 | 22.26 | 0 | 0 | 928.06 | 52.86 | 3
19 | JALPAIGURI | SM/13278 | Augmentation of Lataguri Piped Water Supply Scheme | TSM/009331 | 40002928 | Augmentation | MVS | GO2223007816PH | 19/09/2022 | 0 | 0 | 0 | Jalpaiguri Division | Northern Mechanical Division | 758.15 | 86.34 | 351.16 | 0 | 1195.65 | 751.69 | 85.79 | 351.16 | 0 | 1188.64 | 0 | 30
20 | JALPAIGURI | SM/11814 | AUGMENTATION OF LUKSAN BAZAR PWSS | TSM/009997 | 40021626 | Augmentation | SVS | GO2223006327PH | 16/08/2022 | 518.33 | 97.92 | 616.25 | Jalpaiguri Division | Northern Mechanical Division | 126.87 | 46.94 | 0 | 0 | 173.81 | 107.62 | 46.94 | 0 | 0 | 154.55 | 25.08 | 17
21 | JALPAIGURI | SM/10028 | Augmentation of Madhya Khagrabari Water Supply Scheme. | TSM/006969 | 40003374 | Augmentation | MVS | GO2122008295PH | 17/01/2022 | 951.14 | 35.27 | 986.41 | Jalpaiguri Division | Northern Mechanical Division | 538.63 | 33.45 | 282.3 | 22.27 | 876.66 | 377.36 | 33.45 | 282.3 | 22.27 | 715.39 | 72.52 | 71
22 | JALPAIGURI | SM/10042 | Augmentation of Maynaguri Piped Water Supply Scheme. | TSM/006968 | 40003326 | Augmentation | SVS | GO2122008496PH | 20/01/2022 | 942.77 | 35.92 | 978.7 | Jalpaiguri Division | Northern Mechanical Division | 480.21 | 29.58 | 45.54 | 0 | 555.33 | 555.51 | 29.58 | 45.54 | 0 | 630.62 | 64.44 | 76
23 | JALPAIGURI | SM/10087 | Augmentation of Mondalghat Water Supply Scheme. | TSM/006973 | 40005895 | Augmentation | SVS | GO2122009022PH | 01/02/2022 | 1077.02 | 18.62 | 1095.64 | Jalpaiguri Division | Northern Mechanical Division | 624.16 | 0 | 69.61 | 0 | 693.77 | 570.92 | 0 | 69.61 | 0 | 640.53 | 58.46 | 45
24 | JALPAIGURI | SM/13790 | Augmentation of Odlabari Piped Water Supply Scheme | TSM/009742 | 40014561 | Augmentation | SVS | GO2223009060PH | 21/10/2022 | 946.66 | 56.87 | 1003.52 | Jalpaiguri Division | Northern Mechanical Division | 350.96 | 50.58 | 62.95 | 0 | 464.49 | 350.96 | 50.58 | 62.95 | 0 | 464.49 | 46.29 | 12
25 | JALPAIGURI | SM/15302 | Augmentation of Porjhar Pipe Water Supply Scheme | TSM/018097 | 40060589 | Augmentation | SVS | GO2223013612PH | 09/02/2023 | 502.72 | 94.29 | 597.01 | Siliguri W/S Division | Northern Mechanical Division | 21.46 | 28.86 | 0 | 0 | 50.32 | 21.46 | 10.92 | 0 | 0 | 32.38 | 5.42 | 43
26 | JALPAIGURI | SM/09560 | Augmentation of Purba Daukimari Piped Water Supply Scheme | TSM/008810 | 40010504 | Augmentation | SVS | GO2122005686PH | 22/11/2021 | 526.78 | 19.09 | 545.87 | Jalpaiguri Division | Northern Mechanical Division | 399.81 | 0 | 1.26 | 0 | 401.07 | 432 | 0 | 1.26 | 0 | 433.26 | 79.37 | 77
27 | JALPAIGURI | SM/18355 | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | TSM/018407 | 40060599 | Augmentation | SVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1460.45 | 113.47 | 1573.93 | Siliguri W/S Division | Northern Mechanical Division | 0 | 28.26 | 33.49 | 0 | 61.74 | 0 | 28.26 | 33.49 | 0 | 61.74 | 3.92 | 2
28 | JALPAIGURI | SM/09864 | Augmentation of Purbba Batabari Piped Water Supply Scheme | TSM/009026 | 40013051 | Augmentation | MVS | GO2122006495PH | 06/12/2021 | 790.65 | 19.46 | 810.11 | Jalpaiguri Division | Northern Mechanical Division | 396.86 | 13.83 | 0 | 0 | 410.68 | 399.72 | 13.83 | 0 | 0 | 413.55 | 51.05 | 56
29 | JALPAIGURI | SM/10033 | Augmentation of Ramsai Water Supply Scheme. | TSM/006970 | 40005666 | Augmentation | MVS | GO2122008426PH | 19/01/2022 | 941.96 | 34.23 | 976.19 | Jalpaiguri Division | Northern Mechanical Division | 683.48 | 28.2 | 34.98 | 0 | 746.66 | 643.11 | 28.2 | 34.98 | 0 | 706.28 | 72.35 | 67
30 | JALPAIGURI | SM/09996 | Augmentation of Sannyasikata Piped Water Supply Scheme | TSM/008408 | 40005896 | Augmentation | SVS | GO2122007047PH | 20/12/2021 | 2068.68 | 36.44 | 2105.11 | Jalpaiguri Division | Northern Mechanical Division | 1343.68 | 32.29 | 17.04 | 0 | 1393.01 | 1315.44 | 30.45 | 17.04 | 0 | 1362.93 | 64.74 | 11
31 | JALPAIGURI | SM/09562 | Augmentation of Shikarpur Piped Water Supply Scheme | TSM/008818 | 40006427 | Augmentation | MVS | GO2122005687PH | 22/11/2021 | 958.33 | 19.21 | 977.54 | Jalpaiguri Division | Northern Mechanical Division | 104.21 | 15.63 | 0 | 0 | 119.84 | 104.21 | 15.63 | 0 | 0 | 119.84 | 12.26 | 4
32 | JALPAIGURI | SM/09995 | Augmentation of Sukani Piped Water Supply Scheme | TSM/008383 | 40005283 | Augmentation | MVS | GO2122007047PH | 20/12/2021 | 4239.57 | 130.58 | 4370.14 | Jalpaiguri Division | Northern Mechanical Division | 2066.65 | 94.37 | 154.15 | 0 | 2315.16 | 1978.93 | 92.34 | 154.15 | 0 | 2225.41 | 50.92 | 67
33 | JALPAIGURI | SM/08874 | Bagrakote Tea Garden Area Piped Water Supply Scheme. | TSM/003942 | 40006426 | New | SVS | GO2122003483PH | 22/09/2021 | 457.34 | 61.03 | 518.37 | Jalpaiguri Division | Northern Mechanical Division | 18.3 | 30.46 | 95.99 | 0 | 144.75 | 18.3 | 29.73 | 95.99 | 0 | 144.01 | 27.78 | 11
34 | JALPAIGURI | SM/13703 | BARA DIGHI PIPED WATER SUPPLY SCHEME | TSM/015677 | 40033113 | New | MVS | GO2223009710PH | 14/11/2022 | 110.13 | 46.13 | 156.26 | Jalpaiguri Division | Northern Mechanical Division | 17.37 | 0 | 0 | 0 | 17.37 | 17.37 | 0 | 0 | 0 | 17.37 | 11.12 | 9
35 | JALPAIGURI | SM/15967 | BARA GHARIA PIPED WATER SUPPLY SCHEME | TSM/018232 | 40058210 | New | MVS | GO2223014710PH | 22/02/2023 | 632.23 | 71.47 | 703.7 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 24.69 | 0 | 24.69 | 0 | 0 | 24.69 | 0 | 24.69 | 3.51 | 0
36 | JALPAIGURI | SM/17649 | BARAGHARIA Piped Water Supply Scheme. | TSM/014917 | 40036008 | New | MVS | GO2223017473PH | 22/03/2023 | 573.89 | 39.29 | 613.18 | Jalpaiguri Division | Northern Mechanical Division | 223.45 | 27.07 | 12.71 | 0 | 263.23 | 223.45 | 27.07 | 12.71 | 0 | 263.23 | 42.93 | 11
37 | JALPAIGURI | SM/15971 | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017313 | 40036081 | New | SVS | GO2223014703PH | 22/02/2023 | 775.91 | 70.91 | 846.82 | Jalpaiguri Division | Northern Mechanical Division | 0.2 | 19.35 | 12.09 | 0 | 31.64 | 0 | 19.35 | 12.09 | 0 | 31.44 | 3.71 | 3
38 | JALPAIGURI | SM/16041 | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017315 | 40036080 | New | SVS | GO2223014709PH | 22/02/2023 | 847.21 | 71.26 | 918.46 | Jalpaiguri Division | Northern Mechanical Division | 94.38 | 12.86 | 14.51 | 0 | 121.75 | 84.96 | 12.86 | 14.51 | 0 | 112.33 | 12.23 | 12
39 | JALPAIGURI | SM/18359 | BASUSUBA PIPED WATER SUPPLY SCHEME | TSM/018240 | 40049256 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1159.97 | 97.68 | 1257.66 | Jalpaiguri Division | Northern Mechanical Division | 214.03 | 17.25 | 68.49 | 0 | 299.78 | 214.03 | 17.25 | 68.49 | 0 | 299.78 | 23.84 | 12
40 | JALPAIGURI | SM/09975 | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | TSM/003950 | 40006580 | New | MVS | GO2122003483PH | 22/09/2021 | 0 | 0 | 0 | Jalpaiguri Division | Northern Mechanical Division | 146.3 | 51.83 | 0 | 0 | 198.13 | 146.34 | 51.83 | 0 | 0 | 198.17 | 0 | 50
41 | JALPAIGURI | SM/16676 | BHEMTIA PIPED WATER SUPPLY SCHEME | TSM/015327 | 40033213 | New | SVS | GO2223015941PH | 14/03/2023 | 348.28 | 66.55 | 414.83 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 4.11 | 0 | 4.11 | 0 | 0 | 4.11 | 0 | 4.11 | 0.99 | 0
42 | JALPAIGURI | SM/14198 | BINNAGURI PIPED WATER SUPPLY SCHEME | TSM/016357 | 40032757 | New | SVS | GO2223011801PH | 10/01/2023 | 340.4 | 68.79 | 409.19 | Jalpaiguri Division | Northern Mechanical Division | 68.47 | 10.04 | 13.7 | 0 | 92.21 | 61.82 | 10.04 | 13.7 | 0 | 85.56 | 20.91 | 8
43 | JALPAIGURI | SM/13705 | BRAHMAPUR PIPED WATER SUPPLY SCHEME | TSM/015422 | 40033117 | New | MVS | GO2223009701PH | 14/11/2022 | 899.2 | 88.95 | 988.14 | Jalpaiguri Division | Northern Mechanical Division | 0 | 7.64 | 67.03 | 0 | 74.67 | 0 | 7.64 | 67.03 | 0 | 74.67 | 7.56 | 1
44 | JALPAIGURI | SM/15264 | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015385 | 40033216 | New | SVS | GO2223013480PH | 07/02/2023 | 273.14 | 72.78 | 345.92 | Jalpaiguri Division | Northern Mechanical Division | 136.67 | 14.5 | 0 | 0 | 151.17 | 120.05 | 14.5 | 0 | 0 | 134.55 | 38.9 | 32
45 | JALPAIGURI | SM/18492 | Chapgar Piped Water Supply Scheme. | TSM/002874 | 40035432 | New | MVS | PHE/IV/2004/W-616/23 | 24/07/2023 | 687.89 | 69.86 | 757.75 | Jalpaiguri Division | Northern Mechanical Division | 116.96 | 7.21 | 0 | 0 | 124.18 | 109.19 | 7.21 | 0 | 0 | 116.4 | 15.36 | 7
46 | JALPAIGURI | SM/16042 | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | TSM/015374 | 40033225 | New | MVS | GO2223014580PH | 22/02/2023 | 502.96 | 65.53 | 568.49 | Jalpaiguri Division | Northern Mechanical Division | 182.85 | 13.44 | 8.44 | 0 | 204.73 | 182.85 | 13.44 | 8.44 | 0 | 204.73 | 36.01 | 12
47 | JALPAIGURI | SM/18358 | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | TSM/018490 | 40049260 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1302.98 | 96.33 | 1399.31 | Jalpaiguri Division | Northern Mechanical Division | 0 | 24.48 | 86.1 | 0 | 110.58 | 0 | 24.48 | 86.1 | 0 | 110.58 | 7.9 | 2
48 | JALPAIGURI | SM/13901 | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | TSM/015382 | 40033240 | New | MVS | GO2223010079PH | 25/11/2022 | 177.43 | 59.3 | 236.73 | Jalpaiguri Division | Northern Mechanical Division | 58.34 | 20.29 | 0 | 0 | 78.63 | 58.34 | 20.29 | 0 | 0 | 78.63 | 33.22 | 7
49 | JALPAIGURI | SM/15964 | CHHAR TANDU PIPED WATER SUPPLY SCHEME | TSM/017828 | 40058179 | New | SVS | GO2223014702PH | 22/02/2023 | 254.67 | 75.51 | 330.17 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | JALPAIGURI | SM/14494 | CHHOTA FAPRI WATER SUPPLY SCHEME | TSM/011228 | 40034208 | New | SVS | GO2223012345PH | 20/01/2023 | 250.75 | 53.57 | 304.33 | Jalpaiguri Division | Northern Mechanical Division | 0 | 16.85 | 4.67 | 0 | 21.52 | 0 | 16.85 | 4.67 | 0 | 21.52 | 7.07 | 5
51 | JALPAIGURI | SM/13700 | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | TSM/015421 | 40033128 | New | MVS | GO2223009704PH | 14/11/2022 | 594.87 | 66.25 | 661.12 | Jalpaiguri Division | Northern Mechanical Division | 147.35 | 10.62 | 109.02 | 0 | 266.98 | 137.89 | 10.62 | 109.02 | 0 | 257.53 | 38.95 | 2
52 | JALPAIGURI | SM/14887 | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017494 | 40049259 | New | MVS | GO2223013016PH | 03/02/2023 | 572.31 | 68.79 | 641.1 | Jalpaiguri Division | Northern Mechanical Division | 19.59 | 11.83 | 0 | 0 | 31.42 | 19.59 | 0 | 0 | 0 | 19.59 | 3.06 | 12
53 | JALPAIGURI | SM/16181 | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017495 | 40058264 | New | MVS | GO2223014705PH | 22/02/2023 | 545.02 | 68.71 | 613.74 | Jalpaiguri Division | Northern Mechanical Division | 170.51 | 16.52 | 0 | 0 | 187.03 | 170.51 | 0 | 0 | 0 | 170.51 | 27.78 | 12
54 | JALPAIGURI | SM/15335 | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | TSM/017841 | 40035918 | New | MVS | GO2223013601PH | 09/02/2023 | 749.04 | 101.66 | 850.7 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 54.26 | 0 | 54.26 | 0 | 0 | 54.26 | 0 | 54.26 | 6.38 | 0
55 | JALPAIGURI | SM/18835 | Dakshin Jharalta Piped Water Supply Scheme. | TSM/005492 | 40035820 | New | MVS | 2868/PHE-28011/247/2023-ESTT CELL-Dept. of PHE | 21/09/2023 | 1134.48 | 56.35 | 1190.83 | Jalpaiguri Division | Northern Mechanical Division | 286.94 | 38.81 | 114.44 | 0 | 440.19 | 286.94 | 38.81 | 42.39 | 0 | 368.14 | 30.91 | 10
56 | JALPAIGURI | SM/14908 | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | TSM/016642 | 40032783 | New | SVS | GO2223012920PH | 03/02/2023 | 176.46 | 71.69 | 248.15 | Jalpaiguri Division | Northern Mechanical Division | 0 | 9.5 | 0 | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 9.5 | 3.83 | 4
57 | JALPAIGURI | SM/18711 | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016182 | 40035930 | New | SVS | 2260/PHE/IV/W-404/23 | 04/08/2023 | 510.54 | 74.34 | 584.88 | Jalpaiguri Division | Northern Mechanical Division | 104.07 | 8.63 | 0 | 0 | 112.69 | 104.07 | 8.63 | 0 | 0 | 112.69 | 19.27 | 7
58 | JALPAIGURI | SM/14826 | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME | TSM/016064 | 40049263 | New | SVS | GO2223013118PH | 04/02/2023 | 482.76 | 68.92 | 551.68 | Jalpaiguri Division | Northern Mechanical Division | 160.55 | 10.93 | 0 | 0 | 171.48 | 160.55 | 10.93 | 0 | 0 | 171.48 | 31.08 | 11
59 | JALPAIGURI | SM/14882 | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015977 | 40049266 | New | SVS | GO2223013115PH | 04/02/2023 | 489.01 | 69.04 | 558.05 | Jalpaiguri Division | Northern Mechanical Division | 147.07 | 11.03 | 0 | 0 | 158.1 | 147.07 | 11.03 | 0 | 0 | 158.1 | 28.33 | 19
60 | JALPAIGURI | SM/15261 | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | TSM/014784 | 40033242 | New | SVS | GO2223013541PH | 08/02/2023 | 478.15 | 67.28 | 545.43 | Jalpaiguri Division | Northern Mechanical Division | 70.22 | 10.83 | 5.95 | 0 | 87 | 70.22 | 10.83 | 5.95 | 0 | 87 | 15.95 | 28
61 | JALPAIGURI | SM/15980 | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016184 | 40058236 | New | SVS | GO2223014704PH | 22/02/2023 | 279.74 | 70.45 | 350.2 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 4.28 | 0 | 4.28 | 0 | 0 | 4.28 | 0 | 4.28 | 1.22 | 0
62 | JALPAIGURI | SM/06837 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | TSM/005789 | 7845425 | Retrofitting | SVS | GO2021001731PH | 06/10/2020 | 61.53 | 0 | 61.53 | Jalpaiguri Division |  | 61.53 | 0 | 0 | 0 | 61.53 | 66.16 | 0 | 0 | 0 | 66.16 | 107.52 | 100
63 | JALPAIGURI | SM/06845 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | TSM/005800 | 7349342 | Retrofitting | MVS | GO2021001740PH | 06/10/2020 | 60.77 | 0 | 60.77 | Jalpaiguri Division |  | 60.77 | 0 | 0 | 0 | 60.77 | 68.9 | 0 | 0 | 0 | 68.9 | 113.37 | 100
64 | JALPAIGURI | SM/06838 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | TSM/005790 | 8129736 | Retrofitting | MVS | GO2021001732PH | 06/10/2020 | 92.26 | 0 | 92.26 | Jalpaiguri Division |  | 71.65 | 0 | 0 | 0 | 71.65 | 66.17 | 0 | 0 | 0 | 66.17 | 71.72 | 89
65 | JALPAIGURI | SM/06847 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme | TSM/005802 | 40064185 | Retrofitting | SVS | GO2021001743PH | 06/10/2020 | 56.03 | 0 | 56.03 | Jalpaiguri Division |  | 56.03 | 0 | 0 | 0 | 56.03 | 45 | 0 | 0 | 0 | 45 | 80.3 | 86
66 | JALPAIGURI | SM/06844 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/005799 | 8129767 | Retrofitting | SVS | GO2021001739PH | 06/10/2020 | 57.04 | 0 | 57.04 | Jalpaiguri Division |  | 57.04 | 0 | 0 | 0 | 57.04 | 55.79 | 0 | 0 | 0 | 55.79 | 97.82 | 100
67 | JALPAIGURI | SM/06846 | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | TSM/005801 | 8129328 | Retrofitting | SVS | GO2021001742PH | 06/10/2020 | 37.11 | 0 | 37.11 | Jalpaiguri Division |  | 37.11 | 0 | 0 | 0 | 37.11 | 40.73 | 0 | 0 | 0 | 40.73 | 109.76 | 100
68 | JALPAIGURI | SM/07893 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block | TSM/006752 | 8182576 | Retrofitting | MVS | GO2021004755PH | 19/01/2021 | 133.21 | 0 | 133.21 | Jalpaiguri Division |  | 73.51 | 0 | 0 | 0 | 73.51 | 52.02 | 0 | 0 | 0 | 52.02 | 39.05 | 49
69 | JALPAIGURI | SM/07892 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block | TSM/006750 | 8182658 | Retrofitting | MVS | GO2021004754PH | 19/01/2021 | 131.79 | 0 | 131.79 | Jalpaiguri Division |  | 85.37 | 0 | 0 | 0 | 85.37 | 54.21 | 0 | 0 | 0 | 54.21 | 41.14 | 59
70 | JALPAIGURI | SM/07891 | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block | TSM/006751 | 8182684 | Retrofitting | MVS | GO2021004753PH | 19/01/2021 | 285.66 | 0 | 285.66 | Jalpaiguri Division |  | 74.53 | 0 | 0 | 0 | 74.53 | 74.53 | 0 | 0 | 0 | 74.53 | 26.09 | 27
71 | JALPAIGURI | SM/06843 | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme | TSM/005798 | 8136033 | Retrofitting | MVS | GO2021001737PH | 06/10/2020 | 52.3 | 0 | 52.3 | Jalpaiguri Division |  | 15.72 | 0 | 0 | 0 | 15.72 | 15.72 | 0 | 0 | 0 | 15.72 | 30.06 | 80
72 | JALPAIGURI | SM/14665 | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | TSM/016176 | 40032817 | New | SVS | GO2223012741PH | 31/01/2023 | 349.89 | 67.78 | 417.67 | Jalpaiguri Division | Northern Mechanical Division | 81.47 | 0 | 29.35 | 0 | 110.81 | 80.63 | 0 | 29.35 | 0 | 109.98 | 26.33 | 13
73 | JALPAIGURI | SM/14664 | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | TSM/016178 | 40034492 | New | SVS | GO2223012742PH | 31/01/2023 | 811.06 | 59.82 | 870.88 | Jalpaiguri Division | Northern Mechanical Division | 432.98 | 53.32 | 19.68 | 0 | 505.98 | 432.96 | 53.32 | 19.68 | 0 | 505.95 | 58.1 | 11
74 | JALPAIGURI | SM/15297 | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016344 | 40049253 | New | MVS | GO2223013599PH | 09/02/2023 | 649.85 | 74.39 | 724.23 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 12.26 | 0 | 12.26 | 0 | 0 | 12.26 | 0 | 12.26 | 1.69 | 0
75 | JALPAIGURI | SM/13701 | GAURGRAM PIPED WATER SUPPLY SCHEME | TSM/015420 | 40033145 | New | MVS | GO2223009703PH | 14/11/2022 | 527.16 | 67.73 | 594.88 | Jalpaiguri Division | Northern Mechanical Division | 155.22 | 16.01 | 39.85 | 0 | 211.08 | 155.22 | 5.37 | 39.85 | 0 | 200.44 | 33.69 | 11
76 | JALPAIGURI | SM/14666 | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016174 | 40032828 | New | SVS | GO2223012678PH | 31/01/2023 | 760.49 | 91.94 | 852.43 | Jalpaiguri Division | Northern Mechanical Division | 343.97 | 12.14 | 14.72 | 0 | 370.83 | 337.66 | 12.14 | 14.72 | 0 | 364.52 | 42.76 | 26
77 | JALPAIGURI | SM/08868 | Ghasmari Piped Water Supply Scheme. | TSM/003951 | 40011924 | New | MVS | GO2122003401PH | 20/09/2021 | 240.71 | 52.53 | 293.24 | Jalpaiguri Division | Northern Mechanical Division | 139.3 | 26.09 | 4.8 | 0 | 170.19 | 111.88 | 17.04 | 0 | 0 | 128.92 | 43.96 | 57
78 | JALPAIGURI | SM/16852 | HAIHAIPATHAR PWSS | TSM/016203 | 40036022 | New | MVS | GO2223015694PH | 13/03/2023 | 698.93 | 42.75 | 741.68 | Jalpaiguri Division | Northern Mechanical Division | 157.66 | 34.88 | 39.31 | 0 | 231.86 | 157.66 | 34.88 | 39.31 | 0 | 231.86 | 31.26 | 15
79 | JALPAIGURI | SM/10775 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | TSM/009977 | 40036954 | New | MVS | GO2223003217PH | 23/05/2022 | 422.38 | 113.74 | 536.12 | Jalpaiguri Division | Northern Mechanical Division | 74.74 | 0 | 0 | 0 | 74.74 | 74.74 | 0 | 0 | 0 | 74.74 | 13.94 | 17
80 | JALPAIGURI | SM/08873 | Indong Tea Garden Area Piped Water Supply Scheme. | TSM/005102 | 40006229 | New | SVS | GO2122003483PH | 22/09/2021 | 273.31 | 38.16 | 311.47 | Jalpaiguri Division | Northern Mechanical Division | 104.16 | 27.85 | 0 | 0 | 132.02 | 104.16 | 27.85 | 0 | 0 | 132.02 | 42.38 | 56
81 | JALPAIGURI | SM/15742 | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | TSM/014793 | 40035716 | New | SVS | GO2223014248PH | 20/02/2023 | 610.29 | 68.55 | 678.84 | Jalpaiguri Division | Northern Mechanical Division | 52.81 | 6.75 | 8.57 | 0 | 68.13 | 47.53 | 6.75 | 8.57 | 0 | 62.85 | 9.26 | 12
82 | JALPAIGURI | SM/14879 | KANTADIGHI KUMARPARA TEA GARDEN | TSM/017840 | 40036004 | New | MVS | GO2223013020PH | 03/02/2023 | 743.32 | 97.89 | 841.22 | Jalpaiguri Division | Northern Mechanical Division | 190.75 | 11.62 | 15.26 | 0 | 217.62 | 190.75 | 11.62 | 15.26 | 0 | 217.62 | 25.87 | 11
83 | JALPAIGURI | SM/14199 | KAOAGAP PIPED WATER SUPPLY SCHEME | TSM/016139 | 40032999 | New | MVS | GO2223011794PH | 10/01/2023 | 581.65 | 65.68 | 647.34 | Jalpaiguri Division | Northern Mechanical Division | 174.77 | 9.9 | 25.56 | 0 | 210.23 | 174.77 | 5.08 | 25.56 | 0 | 205.42 | 31.73 | 13
84 | JALPAIGURI | SM/14907 | KHAS JANGAL PIPED WATER SUPPLY SCHEME | TSM/016691 | 40033009 | New | SVS | GO2223012919PH | 03/02/2023 | 173.44 | 72.33 | 245.77 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 5.8 | 0 | 5.8 | 0 | 0 | 5.8 | 0 | 5.8 | 2.36 | 1
85 | JALPAIGURI | SM/15263 | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | TSM/011227 | 40034213 | New | SVS | GO2223013478PH | 07/02/2023 | 345.42 | 53.91 | 399.34 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | JALPAIGURI | SM/15953 | KHUKLUNG PIPED WATER SUPPLY SCHEME | TSM/018691 | 40058163 | New | SVS | GO2223014707PH | 22/02/2023 | 70.56 | 48.54 | 119.09 | Jalpaiguri Division | Northern Mechanical Division | 9.59 | 0 | 0 | 0 | 9.59 | 9.59 | 0 | 0 | 0 | 9.59 | 8.05 | 6
87 | JALPAIGURI | SM/18491 | Kumarpara Piped Water Supply Scheme. | TSM/003957 | 40035439 | New | MVS | PHE/IV/2004/W-616/23 | 24/07/2023 | 791.51 | 53.74 | 845.25 | Jalpaiguri Division | Northern Mechanical Division | 290.23 | 20.62 | 14.76 | 0 | 325.61 | 290.23 | 0 | 14.76 | 0 | 304.99 | 36.08 | 11
88 | JALPAIGURI | SM/08875 | Kumlai Tea Garden Area Piped Water Supply Scheme. | TSM/003937 | 40006101 | New | SVS | GO2122003483PH | 22/09/2021 | 265.83 | 38.01 | 303.84 | Jalpaiguri Division | Northern Mechanical Division | 235.5 | 35.21 | 15.98 | 0 | 286.69 | 199.7 | 35.21 | 15.98 | 0 | 250.88 | 82.57 | 80
89 | JALPAIGURI | SM/15262 | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/013287 | 40033247 | New | MVS | GO2223013540PH | 08/02/2023 | 564.19 | 70.98 | 635.17 | Jalpaiguri Division | Northern Mechanical Division | 225.12 | 13.34 | 7.44 | 0 | 245.9 | 225.12 | 13.34 | 7.44 | 0 | 245.9 | 38.71 | 37
90 | JALPAIGURI | SM/13681 | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | TSM/015307 | 40033174 | New | MVS | GO2223009709PH | 14/11/2022 | 702.34 | 104.91 | 807.25 | Jalpaiguri Division | Northern Mechanical Division | 155.57 | 19.52 | 13.44 | 0 | 188.52 | 155.57 | 19.52 | 13.44 | 0 | 188.52 | 23.35 | 13
91 | JALPAIGURI | SM/13682 | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015312 | 40033212 | New | SVS | GO2223009705PH | 14/11/2022 | 477.92 | 66.67 | 544.59 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 8.21 | 0 | 8.21 | 0 | 0 | 8.21 | 0 | 8.21 | 1.51 | 0
92 | JALPAIGURI | SM/13898 | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | TSM/015372 | 40033257 | New | MVS | GO2223010077PH | 25/11/2022 | 836.68 | 70.04 | 906.72 | Jalpaiguri Division | Northern Mechanical Division | 375 | 32.95 | 93.46 | 0 | 501.42 | 365.71 | 32.95 | 93.46 | 0 | 492.13 | 54.28 | 11
93 | JALPAIGURI | SM/13702 | MAHANBHITA PIPED WATER SUPPLY SCHEME | TSM/015639 | 40033233 | New | MVS | GO2223009702PH | 14/11/2022 | 708.92 | 159.56 | 868.48 | Jalpaiguri Division | Northern Mechanical Division | 206.47 | 72.83 | 12.99 | 0 | 292.3 | 206.47 | 72.83 | 12.99 | 0 | 292.3 | 33.66 | 17
94 | JALPAIGURI | SM/15990 | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016183 | 40035928 | New | SVS | GO2223014706PH | 22/02/2023 | 334.76 | 71.7 | 406.46 | Jalpaiguri Division | Northern Mechanical Division | 127.69 | 18.29 | 0 | 0 | 145.99 | 127.69 | 18.29 | 0 | 0 | 145.99 | 35.92 | 22
95 | JALPAIGURI | SM/13900 | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | TSM/015391 | 40033638 | New | MVS | GO2223010082PH | 25/11/2022 | 581.66 | 156.44 | 738.1 | Jalpaiguri Division | Northern Mechanical Division | 119.65 | 31.16 | 11.03 | 0 | 161.83 | 119.65 | 31.16 | 11.03 | 0 | 161.83 | 21.93 | 14
96 | JALPAIGURI | SM/15115 | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016185 | 40049252 | New | MVS | GO2223013194PH | 04/02/2023 | 487.85 | 72.52 | 560.37 | Jalpaiguri Division | Northern Mechanical Division | 234.94 | 8.92 | 42.26 | 0 | 286.11 | 234.94 | 8.92 | 42.26 | 0 | 286.11 | 51.06 | 45
97 | JALPAIGURI | SM/18357 | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | TSM/017837 | 40036013 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 883.71 | 147.36 | 1031.07 | Jalpaiguri Division | Northern Mechanical Division | 122.26 | 34.07 | 49.54 | 0 | 205.87 | 116.52 | 34.07 | 49.54 | 0 | 200.13 | 19.41 | 11
98 | JALPAIGURI | SM/14911 | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016620 | 40033011 | New | SVS | GO2223012921PH | 03/02/2023 | 200.34 | 74.08 | 274.41 | Jalpaiguri Division | Northern Mechanical Division | 16.9 | 7.56 | 0 | 0 | 24.46 | 16.9 | 7.56 | 0 | 0 | 24.46 | 8.91 | 9
99 | JALPAIGURI | SM/15296 | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017834 | 40036018 | New | MVS | GO2223013615PH | 09/02/2023 | 530.95 | 73.68 | 604.63 | Jalpaiguri Division | Northern Mechanical Division | 0 | 18.92 | 37.53 | 0 | 56.45 | 0 | 18.92 | 37.53 | 0 | 56.45 | 9.34 | 4
100 | JALPAIGURI | SM/13991 | NIRANJANPAT WATER SUPPLY SCHEME | TSM/013267 | 40033639 | New | SVS | GO2223010299PH | 01/12/2022 | 477.46 | 66.18 | 543.63 | Jalpaiguri Division | Northern Mechanical Division | 102.99 | 0 | 5.33 | 0 | 108.33 | 102.99 | 0 | 5.33 | 0 | 108.33 | 19.93 | 4
101 | JALPAIGURI | SM/18503 | NOWAPARA PIPED WATER SUPPLY SCHEME | TSM/014951 | 40058323 | New | SVS | 2038/PHE-28011/185/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 974.29 | 85.92 | 1060.21 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 22.38 | 0 | 22.38 | 0 | 0 | 22.38 | 0 | 22.38 | 2.11 | 0
102 | JALPAIGURI | SM/18356 | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018253 | 40049250 | New | MVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1041.29 | 99.09 | 1140.38 | Jalpaiguri Division | Northern Mechanical Division | 103.33 | 10.79 | 17.21 | 0 | 131.32 | 98.51 | 10.79 | 17.21 | 0 | 126.51 | 11.09 | 35
103 | JALPAIGURI | SM/19097 | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017317 | 40036079 | New | SVS | 3664/PHE-28011/207/2023-SCHM CELL-Dept. of PHE | 08/12/2023 | 928.96 | 71.26 | 1000.22 | Jalpaiguri Division | Northern Mechanical Division | 0 | 13.55 | 20.65 | 0 | 34.2 | 0 | 13.55 | 20.65 | 0 | 34.2 | 3.42 | 2
104 | JALPAIGURI | SM/16779 | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017319 | 40036077 | New | SVS | GO2223015828PH | 13/03/2023 | 639.34 | 69.97 | 709.31 | Jalpaiguri Division | Northern Mechanical Division | 1.38 | 0 | 38.64 | 0 | 40.02 | 1.38 | 0 | 38.64 | 0 | 40.02 | 5.64 | 1
105 | JALPAIGURI | SM/14241 | PANI KAURI PIPED WATER SUPPLY SCHEME | TSM/015429 | 40033642 | New | MVS | GO2223012001PH | 16/01/2023 | 1132.78 | 248.58 | 1381.36 | Jalpaiguri Division | Northern Mechanical Division | 0 | 24.75 | 0 | 0 | 24.75 | 0 | 24.75 | 0 | 0 | 24.75 | 1.79 | 5
106 | JALPAIGURI | SM/14667 | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME | TSM/016170 | 40033014 | New | SVS | GO2223012677PH | 31/01/2023 | 397.2 | 67.49 | 464.69 | Jalpaiguri Division | Northern Mechanical Division | 123.5 | 23.67 | 0 | 0 | 147.17 | 123.5 | 23.67 | 0 | 0 | 147.17 | 31.67 | 21
107 | JALPAIGURI | SM/15915 | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | TSM/015316 | 40033644 | New | SVS | GO2223014579PH | 22/02/2023 | 360.68 | 66.55 | 427.23 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 5.41 | 0 | 5.41 | 0 | 0 | 5.41 | 0 | 5.41 | 1.27 | 0
108 | JALPAIGURI | SM/16040 | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | TSM/015323 | 40033647 | New | MVS | GO2223014572PH | 22/02/2023 | 320.51 | 65.51 | 386.02 | Jalpaiguri Division | Northern Mechanical Division | 130.21 | 10.19 | 4.77 | 0 | 145.17 | 130.21 | 10.19 | 4.77 | 0 | 145.17 | 37.61 | 13
109 | JALPAIGURI | SM/15978 | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016193 | 40035925 | New | SVS | GO2223014708PH | 22/02/2023 | 313.87 | 77.61 | 391.48 | Jalpaiguri Division | Northern Mechanical Division | 48.86 | 15.64 | 6.09 | 0 | 70.59 | 48.86 | 15.64 | 6.09 | 0 | 70.59 | 18.03 | 10
110 | JALPAIGURI | SM/15339 | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017390 | 40036075 | New | SVS | GO2223013616PH | 09/02/2023 | 887.14 | 93.31 | 980.45 | Jalpaiguri Division | Northern Mechanical Division | 2.02 | 11.24 | 58.23 | 0 | 71.49 | 2.02 | 11.24 | 58.23 | 0 | 71.49 | 7.29 | 4
111 | JALPAIGURI | SM/18360 | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017397 | 40036073 | New | SVS | 1797/PHE-28011/160/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1058.75 | 93.31 | 1152.06 | Jalpaiguri Division | Northern Mechanical Division | 109.42 | 34.32 | 60.19 | 0 | 203.93 | 101.38 | 34.32 | 60.19 | 0 | 195.9 | 17 | 12
112 | JALPAIGURI | SM/14878 | PATKATA ZONE-III PIPED WATER SUPPLY | TSM/017407 | 40035902 | New | SVS | GO2223013013PH | 03/02/2023 | 656.42 | 71.26 | 727.68 | Jalpaiguri Division | Northern Mechanical Division | 2.02 | 3.89 | 34.27 | 0 | 40.18 | 2.02 | 3.89 | 34.27 | 0 | 40.18 | 5.52 | 4
113 | JALPAIGURI | SM/13987 | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | TSM/013298 | 40034069 | New | MVS | GO2223010300PH | 01/12/2022 | 601.92 | 154.79 | 756.71 | Jalpaiguri Division | Northern Mechanical Division | 151.43 | 53.69 | 42.66 | 0 | 247.78 | 138.08 | 17.77 | 42.66 | 0 | 198.51 | 26.23 | 12
114 | JALPAIGURI | SM/16492 | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | TSM/013278 | 40035720 | New | SVS | GO2223015190PH | 02/03/2023 | 361.16 | 100.65 | 461.81 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 59.34 | 0 | 59.34 | 0 | 0 | 59.34 | 0 | 59.34 | 12.85 | 0
115 | JALPAIGURI | SM/13990 | PIPE WATER SUPPLY SCHEME FOR TANDU | TSM/013281 | 40034077 | New | MVS | GO2223010301PH | 01/12/2022 | 131.44 | 46.22 | 177.66 | Jalpaiguri Division | Northern Mechanical Division | 38.9 | 4.39 | 0 | 0 | 43.29 | 36.72 | 4.39 | 0 | 0 | 41.11 | 23.14 | 4
116 | JALPAIGURI | SM/13989 | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | TSM/013276 | 40034082 | New | SVS | GO2223010298PH | 01/12/2022 | 99.2 | 44.35 | 143.56 | Jalpaiguri Division | Northern Mechanical Division | 52.85 | 15.82 | 0 | 0 | 68.67 | 52.85 | 15.28 | 0 | 0 | 68.13 | 47.46 | 29
117 | JALPAIGURI | SM/13988 | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | TSM/013277 | 40034086 | New | SVS | GO2223010297PH | 01/12/2022 | 282.82 | 72.78 | 355.6 | Jalpaiguri Division | Northern Mechanical Division | 145.08 | 27.58 | 0 | 0 | 172.66 | 145.08 | 27.58 | 0 | 0 | 172.66 | 48.55 | 30
118 | JALPAIGURI | SM/14224 | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | TSM/016181 | 40033017 | New | SVS | GO2223011802PH | 10/01/2023 | 91.28 | 49.15 | 140.42 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0.71 | 0 | 0.71 | 0 | 0 | 0.71 | 0 | 0.71 | 0.51 | 0
119 | JALPAIGURI | SM/07044 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Porjhar Piped water Supply Scheme. | TSM/006354 | 8138300 | Retrofitting | SVS | GO2021002714PH | 24/11/2020 | 93.9 | 0 | 93.9 | Siliguri W/S Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | JALPAIGURI | SM/07028 | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme | TSM/006355 | 8136875 | Retrofitting | MVS | GO2021002619PH | 13/11/2020 | 96.79 | 0 | 96.79 | Siliguri W/S Division |  | 70.34 | 0 | 0 | 0 | 70.34 | 70.34 | 0 | 0 | 0 | 70.34 | 72.68 | 0
121 | JALPAIGURI | SM/08036 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | TSM/006194 | 8192490 | Retrofitting | MVS | GO2021006020PH | 02/02/2021 | 349.29 | 0 | 349.29 | Jalpaiguri Division |  | 349.29 | 0 | 0 | 0 | 349.29 | 285.33 | 0 | 0 | 0 | 285.33 | 81.69 | 83
122 | JALPAIGURI | SM/06840 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | TSM/005793 | 8129285 | Retrofitting | MVS | GO2021001734PH | 06/10/2020 | 74.02 | 0 | 74.02 | Jalpaiguri Division |  | 74.02 | 0 | 0 | 0 | 74.02 | 92.52 | 0 | 0 | 0 | 92.52 | 124.99 | 100
123 | JALPAIGURI | SM/06936 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | TSM/005796 | 8129330 | Retrofitting | MVS | GO2021002302PH | 03/11/2020 | 126.48 | 0 | 126.48 | Jalpaiguri Division |  | 124.94 | 0 | 0 | 0 | 124.94 | 111.78 | 0 | 0 | 0 | 111.78 | 88.37 | 93
124 | JALPAIGURI | SM/06958 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block | TSM/006192 | 8136015 | Retrofitting | MVS | GO2021002289PH | 03/11/2020 | 99.31 | 0 | 99.31 | Jalpaiguri Division |  | 99.31 | 0 | 0 | 0 | 99.31 | 121.12 | 0 | 0 | 0 | 121.12 | 121.96 | 100
125 | JALPAIGURI | SM/06954 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006193 | 8136024 | Retrofitting | SVS | GO2021002290PH | 03/11/2020 | 34.5 | 0 | 34.5 | Jalpaiguri Division |  | 34.5 | 0 | 0 | 0 | 34.5 | 60.16 | 0 | 0 | 0 | 60.16 | 174.37 | 100
126 | JALPAIGURI | SM/08285 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | TSM/006199 | 8206637 | Retrofitting | MVS | GO2021006676PH | 09/02/2021 | 268.15 | 0 | 268.15 | Jalpaiguri Division |  | 268.15 | 0 | 0 | 0 | 268.15 | 266.3 | 0 | 0 | 0 | 266.3 | 99.31 | 99
127 | JALPAIGURI | SM/06937 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | TSM/005794 | 8129777 | Retrofitting | MVS | GO2021002298PH | 03/11/2020 | 129.58 | 0 | 129.58 | Jalpaiguri Division |  | 126.3 | 0 | 0 | 0 | 126.3 | 112.72 | 0 | 0 | 0 | 112.72 | 86.99 | 57
128 | JALPAIGURI | SM/06960 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme | TSM/006214 | 8136850 | Retrofitting | SVS | GO2021002295PH | 03/11/2020 | 99.43 | 0 | 99.43 | Jalpaiguri Division |  | 50 | 0 | 0 | 0 | 50 | 8.94 | 0 | 0 | 0 | 8.94 | 8.99 | 15
129 | JALPAIGURI | SM/06961 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme | TSM/006215 | 8136865 | Retrofitting | MVS | GO2021002296PH | 03/11/2020 | 75.45 | 0 | 75.45 | Jalpaiguri Division |  | 75.45 | 0 | 0 | 0 | 75.45 | 35.13 | 0 | 0 | 0 | 35.13 | 46.56 | 61
130 | JALPAIGURI | SM/06841 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme | TSM/005795 | 8130525 | Retrofitting | MVS | GO2021001735PH | 06/10/2020 | 89.57 | 0 | 89.57 | Jalpaiguri Division |  | 89.57 | 0 | 0 | 0 | 89.57 | 89.1 | 0 | 0 | 0 | 89.1 | 99.47 | 74
131 | JALPAIGURI | SM/07301 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block | TSM/006198 | 8136885 | Retrofitting | SVS | GO2021003278PH | 10/12/2020 | 30.18 | 0 | 30.18 | Jalpaiguri Division |  | 30.18 | 0 | 0 | 0 | 30.18 | 30.12 | 0 | 0 | 0 | 30.12 | 99.79 | 99
132 | JALPAIGURI | SM/08038 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme | TSM/006206 | 8192577 | Retrofitting | SVS | GO2021006015PH | 02/02/2021 | 396.46 | 0 | 396.46 | Jalpaiguri Division |  | 396.46 | 0 | 0 | 0 | 396.46 | 407.81 | 0 | 0 | 0 | 407.81 | 102.86 | 98
133 | JALPAIGURI | SM/06957 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | TSM/006203 | 8129420 | Retrofitting | SVS | GO2021002293PH | 03/11/2020 | 36 | 0 | 36 | Jalpaiguri Division |  | 36 | 0 | 0 | 0 | 36 | 35.97 | 0 | 0 | 0 | 35.97 | 99.9 | 100
134 | JALPAIGURI | SM/06953 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | TSM/006201 | 8129274 | Retrofitting | SVS | GO2021002292PH | 03/11/2020 | 48.9 | 0 | 48.9 | Jalpaiguri Division |  | 48.9 | 0 | 0 | 0 | 48.9 | 48.83 | 0 | 0 | 0 | 48.83 | 99.85 | 96
135 | JALPAIGURI | SM/06952 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006195 | 8136029 | Retrofitting | SVS | GO2021002291PH | 03/11/2020 | 65.98 | 0 | 65.98 | Jalpaiguri Division |  | 65.98 | 0 | 0 | 0 | 65.98 | 65.37 | 0 | 0 | 0 | 65.37 | 99.08 | 100
136 | JALPAIGURI | SM/06839 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | TSM/005792 | 8129763 | Retrofitting | MVS | GO2021001733PH | 06/10/2020 | 99.99 | 0 | 99.99 | Jalpaiguri Division |  | 81.35 | 0 | 0 | 0 | 81.35 | 84.11 | 0 | 0 | 0 | 84.11 | 84.12 | 85
137 | JALPAIGURI | SM/06955 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006191 | 8129329 | Retrofitting | SVS | GO2021002288PH | 03/11/2020 | 62.52 | 0 | 62.52 | Jalpaiguri Division |  | 62.52 | 0 | 0 | 0 | 62.52 | 81.43 | 0 | 0 | 0 | 81.43 | 130.23 | 100
138 | JALPAIGURI | SM/06938 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | TSM/005791 | 6904511 | Retrofitting | MVS | GO2021002297PH | 03/11/2020 | 106.41 | 0 | 106.41 | Jalpaiguri Division |  | 78.09 | 0 | 0 | 0 | 78.09 | 71.51 | 0 | 0 | 0 | 71.51 | 67.2 | 79
139 | JALPAIGURI | SM/08037 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block | TSM/006196 | 8192528 | Retrofitting | MVS | GO2021006018PH | 02/02/2021 | 348.32 | 0 | 348.32 | Jalpaiguri Division |  | 348.32 | 0 | 0 | 0 | 348.32 | 293.31 | 0 | 0 | 0 | 293.31 | 84.21 | 92
140 | JALPAIGURI | SM/07303 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | TSM/006213 | 8136862 | Retrofitting | SVS | GO2021003276PH | 10/12/2020 | 89.78 | 0 | 89.78 | Jalpaiguri Division |  | 62 | 0 | 0 | 0 | 62 | 109.28 | 0 | 0 | 0 | 109.28 | 121.71 | 100
141 | JALPAIGURI | SM/08284 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block | TSM/006197 | 8206631 | Retrofitting | MVS | GO2021006677PH | 09/02/2021 | 137.5 | 0 | 137.5 | Jalpaiguri Division |  | 23.63 | 0 | 0 | 0 | 23.63 | 19.02 | 0 | 0 | 0 | 19.02 | 13.83 | 51
142 | JALPAIGURI | SM/06956 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | TSM/006190 | 8135974 | Retrofitting | SVS | GO2021002287PH | 03/11/2020 | 64.77 | 0 | 64.77 | Jalpaiguri Division |  | 64.77 | 0 | 0 | 0 | 64.77 | 64.68 | 0 | 0 | 0 | 64.68 | 99.85 | 99
143 | JALPAIGURI | SM/07304 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme | TSM/006216 | 8136868 | Retrofitting | MVS | GO2021003275PH | 10/12/2020 | 36.39 | 0 | 36.39 | Jalpaiguri Division |  | 36.39 | 0 | 0 | 0 | 36.39 | 71.86 | 0 | 0 | 0 | 71.86 | 197.48 | 100
144 | JALPAIGURI | SM/08035 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block | TSM/006189 | 8192435 | Retrofitting | SVS | GO2021006021PH | 02/02/2021 | 320.18 | 0 | 320.18 | Jalpaiguri Division |  | 109.02 | 0 | 0 | 0 | 109.02 | 104.19 | 0 | 0 | 0 | 104.19 | 32.54 | 19
145 | JALPAIGURI | SM/07302 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Pradhanpara Mouza Under Sajnapara Piped Water Supply Scheme | TSM/006208 | 8136093 | Retrofitting | SVS | GO2021003277PH | 10/12/2020 | 75.74 | 0 | 75.74 | Jalpaiguri Division |  | 75.74 | 0 | 0 | 0 | 75.74 | 3.5 | 0 | 0 | 0 | 3.5 | 4.62 | 18
146 | JALPAIGURI | SM/06959 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme | TSM/006211 | 8136053 | Retrofitting | SVS | GO2021002294PH | 03/11/2020 | 57.13 | 0 | 57.13 | Jalpaiguri Division |  | 57.13 | 0 | 0 | 0 | 57.13 | 118.72 | 0 | 0 | 0 | 118.72 | 207.81 | 100
147 | JALPAIGURI | SM/08078 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block | TSM/007025 | 8193747 | Retrofitting | MVS | GO2021006209PH | 04/02/2021 | 136.18 | 0 | 136.18 | Jalpaiguri Division |  | 23.97 | 0 | 0 | 0 | 23.97 | 23.97 | 0 | 0 | 0 | 23.97 | 17.6 | 27
148 | JALPAIGURI | SM/09100 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | TSM/007026 | 8382160 | Retrofitting | MVS | GO2122004567PH | 28/10/2021 | 382.83 | 0 | 382.83 | Jalpaiguri Division |  | 260.43 | 0 | 0 | 0 | 260.43 | 247.22 | 0 | 0 | 0 | 247.22 | 64.58 | 53
149 | JALPAIGURI | SM/08077 | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme | TSM/007024 | 8193726 | Retrofitting | MVS | GO2021006210PH | 04/02/2021 | 62.08 | 0 | 62.08 | Jalpaiguri Division |  | 62.08 | 0 | 0 | 0 | 62.08 | 61.14 | 0 | 0 | 0 | 61.14 | 98.49 | 61
150 | JALPAIGURI | SM/09099 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. | TSM/007485 | 8382155 | Retrofitting | MVS | GO2122004577PH | 28/10/2021 | 163.94 | 0 | 163.94 | Jalpaiguri Division | Northern Mechanical Division | 88.19 | 0 | 0 | 0 | 88.19 | 85.19 | 0 | 0 | 0 | 85.19 | 51.96 | 48
151 | JALPAIGURI | SM/06842 | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme | TSM/005797 | 7718340 | Retrofitting | SVS | GO2021001736PH | 06/10/2020 | 48.73 | 0 | 48.73 | Jalpaiguri Division |  | 10.56 | 0 | 0 | 0 | 10.56 | 10.56 | 0 | 0 | 0 | 10.56 | 21.66 | 65
152 | JALPAIGURI | SM/16776 | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | TSM/018684 | 40058371 | New | SVS | GO2223015826PH | 13/03/2023 | 40.49 | 48.54 | 89.03 | Jalpaiguri Division | Northern Mechanical Division | 8.92 | 0 | 0 | 0 | 8.92 | 8.92 | 0 | 0 | 0 | 8.92 | 10.01 | 2
153 | JALPAIGURI | SM/14881 | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME | TSM/017836 | 40036017 | New | MVS | GO2223013012PH | 03/02/2023 | 606.88 | 74.39 | 681.26 | Jalpaiguri Division | Northern Mechanical Division | 2.34 | 6.69 | 0 | 0 | 9.03 | 2.34 | 6.69 | 0 | 0 | 9.03 | 1.33 | 7
154 | JALPAIGURI | SM/14880 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017838 | 40049257 | New | MVS | PH222371613S000 | 03/02/2023 | 633.63 | 98.46 | 732.1 | Jalpaiguri Division | Northern Mechanical Division | 2.02 | 20.25 | 0 | 0 | 22.27 | 2.02 | 20.25 | 0 | 0 | 22.27 | 3.04 | 4
155 | JALPAIGURI | SM/14885 | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016190 | 40036016 | New | MVS | GO2223013014PH | 03/02/2023 | 815.63 | 97.9 | 913.53 | Jalpaiguri Division | Northern Mechanical Division | 414.33 | 16.41 | 53.84 | 0 | 484.57 | 414.33 | 16.41 | 53.84 | 0 | 484.57 | 53.04 | 34
156 | JALPAIGURI | SM/15103 | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme | TSM/017971 | 40060564 | Augmentation | SVS | GO2223013201PH | 04/02/2023 | 101.69 | 48.05 | 149.74 | Jalpaiguri Division | Northern Mechanical Division | 0 | 15.73 | 0 | 0 | 15.73 | 0 | 15.73 | 0 | 0 | 15.73 | 10.5 | 10
157 | JALPAIGURI | SM/15082 | Rejuvenation for Manabari Tea Garden | TSM/018002 | 40060611 | Augmentation | MVS | GO2223013217PH | 04/02/2023 | 159.45 | 70.17 | 229.62 | Jalpaiguri Division | Northern Mechanical Division | 19.92 | 0 | 0 | 0 | 19.92 | 19.92 | 0 | 0 | 0 | 19.92 | 8.68 | 3
158 | JALPAIGURI | SM/15085 | Rejuvenation for Patkidaha Piped Water Supply Scheme | TSM/017986 | 40057345 | Augmentation | MVS | GO2223013197PH | 04/02/2023 | 96.2 | 48.95 | 145.15 | Jalpaiguri Division | Northern Mechanical Division | 21.58 | 11.41 | 0 | 0 | 33 | 21.58 | 11.41 | 0 | 0 | 33 | 22.73 | 25
159 | JALPAIGURI | SM/17185 | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | TSM/011016 | 40060633 | Augmentation | SVS | GO2223016072PH | 15/03/2023 | 138.2 | 41.84 | 180.04 | Jalpaiguri Division | Northern Mechanical Division | 17.74 | 14.77 | 5.79 | 0 | 38.29 | 17.74 | 14.77 | 5.79 | 0 | 38.29 | 21.27 | 14
160 | JALPAIGURI | SM/15089 | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME | TSM/017709 | 40057346 | Augmentation | MVS | GO2223013206PH | 04/02/2023 | 103.06 | 48.54 | 151.59 | Jalpaiguri Division | Northern Mechanical Division | 9.86 | 9.12 | 0 | 0 | 18.98 | 9.86 | 9.12 | 0 | 0 | 18.98 | 12.52 | 16
161 | JALPAIGURI | SM/09487 | Rejuvenation of Ambari Falakata Piped Water Supply Scheme | TSM/009024 | 40005898 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 178.35 | 39.13 | 217.47 | Jalpaiguri Division | Northern Mechanical Division | 18.47 | 27.29 | 0 | 11.23 | 56.99 | 18.47 | 27.29 | 0 | 0 | 45.76 | 21.04 | 10
162 | JALPAIGURI | SM/15338 | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | TSM/019578 | 40059503 | Augmentation | MVS | GO2223013603PH | 09/02/2023 | 72.72 | 48.54 | 121.26 | Jalpaiguri Division | Northern Mechanical Division | 8.64 | 0 | 35.11 | 0 | 43.74 | 8.64 | 0 | 35.11 | 0 | 43.74 | 36.07 | 15
163 | JALPAIGURI | SM/09518 | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. | TSM/008107 | 40003695 | Augmentation | MVS | GO2122005574PH | 19/11/2021 | 79.83 | 34.51 | 114.34 | Jalpaiguri Division | Northern Mechanical Division | 53.99 | 25.06 | 0 | 0 | 79.04 | 36.1 | 25.06 | 0 | 0 | 61.16 | 53.49 | 50
164 | JALPAIGURI | SM/15030 | REJUVENATION OF ARJI GARALBARI PWSS | TSM/018283 | 40059502 | Augmentation | MVS | GO2223013142PH | 04/02/2023 | 100.51 | 71.93 | 172.44 | Jalpaiguri Division | Northern Mechanical Division | 42.42 | 22.18 | 0 | 0 | 64.6 | 42.42 | 22.18 | 0 | 0 | 64.6 | 37.46 | 8
165 | JALPAIGURI | SM/15059 | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme | TSM/018100 | 40060627 | Augmentation | SVS | GO2223013218PH | 04/02/2023 | 78.7 | 48.54 | 127.24 | Jalpaiguri Division | Northern Mechanical Division | 13.42 | 13.94 | 2.84 | 0 | 30.21 | 13.42 | 13.94 | 2.84 | 0 | 30.21 | 23.74 | 4
166 | JALPAIGURI | SM/09460 | Rejuvenation of Basilardanga piped water supply scheme. | TSM/008103 | 40004171 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 80.59 | 34.57 | 115.16 | Jalpaiguri Division | Northern Mechanical Division | 74.16 | 30.84 | 0 | 0 | 105.01 | 74.16 | 30.84 | 0 | 0 | 105.01 | 91.18 | 71
167 | JALPAIGURI | SM/16773 | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011283 | 40060643 | Augmentation | SVS | GO2223015823PH | 13/03/2023 | 132.31 | 39.25 | 171.57 | Jalpaiguri Division | Northern Mechanical Division | 35.02 | 17.23 | 0 | 0 | 52.25 | 35.02 | 17.23 | 0 | 0 | 52.25 | 30.45 | 11
168 | JALPAIGURI | SM/15094 | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | TSM/017590 | 40056773 | Augmentation | MVS | GO2223013160PH | 04/02/2023 | 76.92 | 48.95 | 125.87 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | JALPAIGURI | SM/15096 | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | TSM/017589 | 40060635 | Augmentation | MVS | GO2223013215PH | 04/02/2023 | 70.56 | 48.54 | 119.1 | Jalpaiguri Division | Northern Mechanical Division | 10.22 | 3.68 | 0 | 0 | 13.9 | 10.22 | 0 | 0 | 0 | 10.22 | 8.58 | 15
170 | JALPAIGURI | SM/15032 | Rejuvenation of Bhangarhat Piped Water Supply Scheme | TSM/018110 | 40060653 | Augmentation | MVS | GO2223013202PH | 04/02/2023 | 129.77 | 48.54 | 178.3 | Jalpaiguri Division | Northern Mechanical Division | 21.63 | 8.2 | 0 | 0 | 29.83 | 21.63 | 8.2 | 0 | 0 | 29.83 | 16.73 | 15
171 | JALPAIGURI | SM/09462 | Rejuvenation of Boalmari piped water supply scheme. | TSM/008104 | 40004800 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 78.8 | 34.8 | 113.6 | Jalpaiguri Division | Northern Mechanical Division | 73.8 | 30.77 | 0 | 0 | 104.57 | 73.8 | 28.33 | 0 | 0 | 102.13 | 89.9 | 26
172 | JALPAIGURI | SM/09482 | Rejuvenation of Chakiavita Piped Water Supply Scheme | TSM/008824 | 40005902 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 81.58 | 38.39 | 119.98 | Jalpaiguri Division | Northern Mechanical Division | 35.84 | 36.08 | 0 | 0 | 71.91 | 35.47 | 36.08 | 0 | 0 | 71.54 | 59.63 | 56
173 | JALPAIGURI | SM/09458 | Rejuvenation of Charerbari piped water supply scheme. | TSM/008106 | 40003841 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 81.1 | 34.83 | 115.93 | Jalpaiguri Division | Northern Mechanical Division | 71.35 | 21.67 | 0 | 0 | 93.02 | 71.35 | 21.67 | 0 | 0 | 93.02 | 80.24 | 49
174 | JALPAIGURI | SM/15033 | Rejuvenation of Chauhaddi Piped Water Supply Scheme | TSM/018108 | 40059498 | Augmentation | MVS | GO2223013155PH | 04/02/2023 | 150.2 | 48.6 | 198.79 | Jalpaiguri Division | Northern Mechanical Division | 29.2 | 0 | 0 | 0 | 29.2 | 29.2 | 0 | 0 | 0 | 29.2 | 14.69 | 8
175 | JALPAIGURI | SM/09484 | Rejuvenation of Chauhaddi Piped Water Supply Scheme | TSM/009001 | 40005901 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 206.83 | 19.49 | 226.32 | Jalpaiguri Division | Northern Mechanical Division | 194.11 | 11.57 | 0 | 0 | 205.68 | 189.17 | 11.57 | 0 | 0 | 200.74 | 88.7 | 62
176 | JALPAIGURI | SM/15114 | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme | TSM/011303 | 40059478 | Augmentation | SVS | GO2223013196PH | 04/02/2023 | 211.87 | 43.6 | 255.47 | Jalpaiguri Division | Northern Mechanical Division | 81.25 | 27.88 | 0 | 0 | 109.12 | 78.45 | 27.88 | 0 | 0 | 106.33 | 41.62 | 4
177 | JALPAIGURI | SM/18283 | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | TSM/010970 | 40064178 | Augmentation | SVS | 1624/PHE-28011/75/2023-ESTT CELL-Dept. of PHE | 23/06/2023 | 2617.64 | 245.14 | 2862.78 | Jalpaiguri Division | Northern Mechanical Division | 91.3 | 0 | 295.69 | 0 | 386.99 | 90.45 | 0 | 295.69 | 0 | 386.14 | 13.49 | 5
178 | JALPAIGURI | SM/15087 | REJUVENATION OF DAKSHIN SALBARI PWSS | TSM/017943 | 40060560 | Augmentation | MVS | GO2223013216PH | 04/02/2023 | 175.12 | 71.12 | 246.25 | Jalpaiguri Division | Northern Mechanical Division | 7.69 | 0 | 0 | 0 | 7.69 | 7.69 | 0 | 0 | 0 | 7.69 | 3.12 | 2
179 | JALPAIGURI | SM/11812 | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/009995 | 40060609 | Augmentation | SVS | GO2223006326PH | 16/08/2022 | 74.48 | 20.25 | 94.73 | Jalpaiguri Division | Northern Mechanical Division | 37.26 | 2.88 | 0 | 0 | 40.14 | 37.4 | 2.88 | 0 | 0 | 40.28 | 42.52 | 4
180 | JALPAIGURI | SM/09459 | Rejuvenation of Dwarikamari piped water supply scheme. | TSM/008109 | 40004150 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 86.51 | 34.89 | 121.4 | Jalpaiguri Division | Northern Mechanical Division | 86.51 | 27.04 | 0 | 0 | 113.55 | 86.51 | 25.79 | 0 | 0 | 112.31 | 92.5 | 89
181 | JALPAIGURI | SM/17681 | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011592 | 40036028 | Augmentation | SVS | GO2223015886PH | 17/03/2023 | 74.37 | 41.79 | 116.16 | Jalpaiguri Division | Northern Mechanical Division | 12.33 | 17.85 | 0 | 0 | 30.18 | 12.33 | 17.85 | 0 | 0 | 30.18 | 25.98 | 11
182 | JALPAIGURI | SM/17181 | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | TSM/011005 | 40060604 | Augmentation | SVS | GO2223016069PH | 15/03/2023 | 157.6 | 44.06 | 201.66 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | JALPAIGURI | SM/09390 | Rejuvenation of Goralbari Piped Water Supply Scheme | TSM/008375 | 40003473 | Augmentation | SVS | GO2122005377PH | 12/11/2021 | 165.91 | 171.63 | 337.55 | Jalpaiguri Division | Northern Mechanical Division | 165.91 | 66.33 | 0 | 0 | 232.25 | 261.32 | 66.33 | 0 | 0 | 327.65 | 97.07 | 62
184 | JALPAIGURI | SM/15130 | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | TSM/018042 | 40060618 | Augmentation | SVS | GO2223013193PH | 04/02/2023 | 134.2 | 48.54 | 182.74 | Jalpaiguri Division | Northern Mechanical Division | 20.68 | 9.95 | 0 | 0 | 30.63 | 20.68 | 9.95 | 0 | 0 | 30.63 | 16.76 | 7
185 | JALPAIGURI | SM/16772 | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | TSM/017935 | 40060597 | Augmentation | SVS | GO2223015831PH | 13/03/2023 | 107.3 | 48.95 | 156.25 | Jalpaiguri Division | Northern Mechanical Division | 10.2 | 5.07 | 0 | 0 | 15.27 | 10.2 | 5.07 | 0 | 0 | 15.27 | 9.77 | 13
186 | JALPAIGURI | SM/15031 | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME | TSM/018224 | 40060568 | Augmentation | MVS | GO2223013211PH | 04/02/2023 | 90.06 | 71.93 | 161.99 | Jalpaiguri Division | Northern Mechanical Division | 20.26 | 14.16 | 0 | 0 | 34.41 | 20.26 | 14.16 | 0 | 0 | 34.41 | 21.24 | 17
187 | JALPAIGURI | SM/10070 | Rejuvenation of Hila Tea Garden area piped water supply scheme | TSM/009745 | 40002852 | Augmentation | SVS | GO2122008791PH | 27/01/2022 | 167.86 | 40.48 | 208.35 | Jalpaiguri Division | Northern Mechanical Division | 112.94 | 36.64 | 0 | 0 | 149.58 | 105.23 | 34.81 | 0 | 0 | 140.04 | 67.21 | 72
188 | JALPAIGURI | SM/15109 | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME | TSM/017864 | 40064182 | Augmentation | SVS | GO2223013214PH | 04/02/2023 | 111 | 71.12 | 182.13 | Jalpaiguri Division | Northern Mechanical Division | 32.93 | 10.69 | 0 | 0 | 43.62 | 15.35 | 0 | 0 | 0 | 15.35 | 8.43 | 15
189 | JALPAIGURI | SM/15068 | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS | TSM/018310 | 40060647 | Augmentation | SVS | GO2223013204PH | 04/02/2023 | 22.33 | 48.54 | 70.86 | Jalpaiguri Division | Northern Mechanical Division | 5.18 | 12.14 | 0 | 0 | 17.32 | 5.18 | 12.14 | 0 | 0 | 17.32 | 24.44 | 12
190 | JALPAIGURI | SM/10069 | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | TSM/009749 | 7422877 | Augmentation | SVS | GO2122008791PH | 27/01/2022 | 201.53 | 42.16 | 243.7 | Jalpaiguri Division | Northern Mechanical Division | 124.9 | 15.3 | 0 | 0 | 140.2 | 124.9 | 15.3 | 0 | 0 | 140.2 | 57.53 | 43
191 | JALPAIGURI | SM/09457 | Rejuvenation of Kajaldighi piped water supply scheme. | TSM/008110 | 40003831 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 82.33 | 34.57 | 116.9 | Jalpaiguri Division | Northern Mechanical Division | 15.78 | 5.81 | 0 | 0 | 21.59 | 15.78 | 5.81 | 0 | 0 | 21.59 | 18.47 | 55
192 | JALPAIGURI | SM/15298 | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | TSM/011312 | 40060652 | Augmentation | SVS | GO2223013597PH | 09/02/2023 | 198.34 | 43.1 | 241.44 | Jalpaiguri Division | Northern Mechanical Division | 75.48 | 4.61 | 0 | 0 | 80.09 | 75.48 | 4.61 | 0 | 0 | 80.09 | 33.17 | 14
193 | JALPAIGURI | SM/09392 | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme | TSM/008374 | 40020983 | Augmentation | SVS | GO2122005377PH | 12/11/2021 | 191.17 | 99.65 | 290.82 | Jalpaiguri Division | Northern Mechanical Division | 119.93 | 12.2 | 0 | 0 | 132.13 | 118.72 | 12.2 | 0 | 0 | 130.93 | 45.02 | 34
194 | JALPAIGURI | SM/09486 | Rejuvenation of Khalaigram Piped Water Supply Scheme | TSM/009016 | 40005899 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 46.61 | 19.53 | 66.14 | Jalpaiguri Division | Northern Mechanical Division | 33.96 | 14.77 | 0 | 0 | 48.73 | 33.96 | 14.79 | 0 | 0 | 48.76 | 73.71 | 47
195 | JALPAIGURI | SM/09461 | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | TSM/008155 | 7827508 | Augmentation | SVS | GO2122005570PH | 19/11/2021 | 70.07 | 0 | 70.07 | Jalpaiguri Division | Northern Mechanical Division | 70.07 | 0 | 0 | 0 | 70.07 | 88.91 | 0 | 0 | 0 | 88.91 | 126.9 | 100
196 | JALPAIGURI | SM/09456 | Rejuvenation of Madhabdanga piped water supply scheme. | TSM/008102 | 40015609 | Augmentation | MVS | GO2122005570PH | 19/11/2021 | 89.26 | 36.12 | 125.38 | Jalpaiguri Division | Northern Mechanical Division | 55.31 | 26.05 | 0 | 24.97 | 106.32 | 55.31 | 26.05 | 0 | 24.97 | 106.32 | 84.8 | 45
197 | JALPAIGURI | SM/09483 | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme | TSM/008993 | 40006236 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 168.91 | 19.56 | 188.47 | Jalpaiguri Division | Northern Mechanical Division | 11.85 | 14.68 | 0 | 0 | 26.53 | 11.85 | 14.68 | 0 | 0 | 26.53 | 14.08 | 12
198 | JALPAIGURI | SM/09565 | Rejuvenation of Mainatali Piped Water Supply Scheme | TSM/008825 | 40007494 | Augmentation | MVS | GO2122005693PH | 22/11/2021 | 46.38 | 57.73 | 104.11 | Jalpaiguri Division | Northern Mechanical Division | 10.01 | 21.77 | 0 | 0 | 31.78 | 10.01 | 21.77 | 0 | 0 | 31.78 | 30.52 | 11
199 | JALPAIGURI | SM/18094 | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II | TSM/011411 | 40059494 | Augmentation | MVS | GO2223017757PH | 27/03/2023 | 185.13 | 0 | 185.13 | Jalpaiguri Division |  | 16.66 | 0 | 0 | 0 | 16.66 | 16.66 | 0 | 0 | 0 | 16.66 | 9 | 10
200 | JALPAIGURI | SM/09485 | Rejuvenation of Mallicksova Piped water Supply Scheme | TSM/009006 | 40005900 | Augmentation | MVS | GO2122005609PH | 19/11/2021 | 139.57 | 39.13 | 178.69 | Jalpaiguri Division | Northern Mechanical Division | 54.01 | 24.44 | 0 | 0 | 78.45 | 52.69 | 23.93 | 0 | 0 | 76.62 | 42.88 | 15
201 | JALPAIGURI | SM/15098 | Rejuvenation of Mathachulka Piped Water Supply Scheme | TSM/011305 | 40059476 | Augmentation | MVS | GO2223013213PH | 04/02/2023 | 134.56 | 40.64 | 175.2 | Jalpaiguri Division | Northern Mechanical Division | 0 | 4.59 | 4 | 0 | 8.59 | 0 | 4.59 | 0 | 0 | 4.59 | 2.62 | 5
202 | JALPAIGURI | SM/11813 | REJUVENATION OF METELIBAZAR PWSS | TSM/009996 | 40021195 | Augmentation | MVS | GO2223006326PH | 16/08/2022 | 657.92 | 63.15 | 721.07 | Jalpaiguri Division | Northern Mechanical Division | 73.14 | 14.97 | 0 | 0 | 88.11 | 73.14 | 14.97 | 0 | 0 | 88.11 | 12.22 | 5
203 | JALPAIGURI | SM/15075 | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme | TSM/018016 | 40060603 | Augmentation | MVS | GO2223013200PH | 04/02/2023 | 109.33 | 48.95 | 158.29 | Jalpaiguri Division | Northern Mechanical Division | 13.54 | 4.02 | 0 | 0 | 17.56 | 13.54 | 4.02 | 0 | 0 | 17.56 | 11.09 | 15
204 | JALPAIGURI | SM/09519 | Rejuvenation of Mohitnagar piped water supply scheme. | TSM/008105 | 40003677 | Augmentation | MVS | GO2122005574PH | 19/11/2021 | 87.62 | 34.57 | 122.19 | Jalpaiguri Division | Northern Mechanical Division | 84.07 | 33.26 | 0 | 0 | 117.33 | 75.19 | 32.52 | 0 | 0 | 107.71 | 88.15 | 79
205 | JALPAIGURI | SM/09858 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/009023 | 40006395 | Augmentation | SVS | GO2122006497PH | 06/12/2021 | 132.35 | 39.15 | 171.5 | Jalpaiguri Division | Northern Mechanical Division | 72.97 | 27.76 | 0 | 0 | 100.73 | 71.91 | 27.76 | 0 | 0 | 99.67 | 58.12 | 55
206 | JALPAIGURI | SM/15060 | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme | TSM/018112 | 40056793 | Augmentation | SVS | GO2223013129PH | 04/02/2023 | 212.39 | 72.63 | 285.02 | Jalpaiguri Division | Northern Mechanical Division | 8.93 | 0 | 19.99 | 0 | 28.93 | 8.93 | 0 | 19.99 | 0 | 28.93 | 10.15 | 1
207 | JALPAIGURI | SM/15300 | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | TSM/011304 | 40060657 | Augmentation | SVS | GO2223013613PH | 09/02/2023 | 117.85 | 42.12 | 159.96 | Jalpaiguri Division | Northern Mechanical Division | 19.93 | 14.09 | 0 | 0 | 34.02 | 15.04 | 0 | 0 | 0 | 15.04 | 9.4 | 11
208 | JALPAIGURI | SM/15116 | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | TSM/018613 | 40060622 | Augmentation | SVS | GO2223013205PH | 04/02/2023 | 124.26 | 70.17 | 194.43 | Jalpaiguri Division | Northern Mechanical Division | 12.01 | 26.68 | 0 | 0 | 38.7 | 12.01 | 26.68 | 0 | 0 | 38.7 | 19.9 | 17
209 | JALPAIGURI | SM/09863 | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | TSM/009020 | 40006405 | Augmentation | SVS | GO2122006496PH | 06/12/2021 | 131.67 | 41.12 | 172.79 | Jalpaiguri Division | Northern Mechanical Division | 68.16 | 34 | 0 | 0 | 102.16 | 68.16 | 31.02 | 0 | 0 | 99.18 | 57.4 | 11
210 | JALPAIGURI | SM/15099 | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme | TSM/018018 | 40060649 | Augmentation | SVS | GO2223013166PH | 04/02/2023 | 102.54 | 48.05 | 150.59 | Jalpaiguri Division | Northern Mechanical Division | 35.05 | 3.9 | 0 | 0 | 38.96 | 35.05 | 3.9 | 0 | 0 | 38.96 | 25.87 | 18
211 | JALPAIGURI | SM/15076 | REJUVENATION OF PASCHIM SALBARI PWSS | TSM/018057 | 40060600 | Augmentation | MVS | GO2223013146PH | 04/02/2023 | 328.27 | 71.12 | 399.4 | Jalpaiguri Division | Northern Mechanical Division | 9.91 | 17.48 | 0 | 0 | 27.4 | 9.91 | 0 | 0 | 0 | 9.91 | 2.48 | 3
212 | JALPAIGURI | SM/15101 | REJUVENATION OF PORA PARA PWSS | TSM/017999 | 40059500 | Augmentation | SVS | GO2223013192PH | 04/02/2023 | 371.96 | 52.31 | 424.27 | Jalpaiguri Division | Northern Mechanical Division | 0 | 19.88 | 0 | 0 | 19.88 | 0 | 19.88 | 0 | 0 | 19.88 | 4.69 | 7
213 | JALPAIGURI | SM/09463 | Rejuvenation of Porapara piped water supply scheme. | TSM/008108 | 40004181 | Augmentation | SVS | GO2122005570PH | 19/11/2021 | 85.06 | 36.2 | 121.26 | Jalpaiguri Division | Northern Mechanical Division | 81.62 | 30.5 | 0 | 0 | 112.12 | 81.62 | 29 | 0 | 0 | 110.62 | 91.22 | 65
214 | JALPAIGURI | SM/15326 | Rejuvenation of Purba Duramari Piped Water Supply Scheme | TSM/018104 | 40060660 | Augmentation | MVS | GO2223013604PH | 09/02/2023 | 158.04 | 48.54 | 206.58 | Jalpaiguri Division | Northern Mechanical Division | 0 | 7.78 | 0 | 0 | 7.78 | 0 | 7.78 | 0 | 0 | 7.78 | 3.77 | 8
215 | JALPAIGURI | SM/09564 | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. | TSM/008823 | 40017895 | Augmentation | MVS | GO2122005693PH | 22/11/2021 | 52.96 | 86.22 | 139.18 | Jalpaiguri Division | Northern Mechanical Division | 38.79 | 21.65 | 0 | 0 | 60.43 | 36.42 | 21.65 | 0 | 0 | 58.06 | 41.72 | 44
216 | JALPAIGURI | SM/09861 | Rejuvenation of Purbba Salbari Piped Water Supply Scheme | TSM/008817 | 40006244 | Augmentation | MVS | GO2122006496PH | 06/12/2021 | 677.35 | 19.24 | 696.59 | Jalpaiguri Division | Northern Mechanical Division | 532.58 | 15.65 | 26.95 | 0 | 575.18 | 402.47 | 15.65 | 26.95 | 0 | 445.07 | 63.89 | 39
217 | JALPAIGURI | SM/15071 | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | TSM/018227 | 40060630 | Augmentation | SVS | GO2223013151PH | 04/02/2023 | 108.03 | 69.01 | 177.04 | Jalpaiguri Division | Northern Mechanical Division | 9.46 | 16.5 | 0 | 0 | 25.96 | 9.46 | 16.5 | 0 | 0 | 25.96 | 14.66 | 15
218 | JALPAIGURI | SM/09391 | Rejuvenation of Sajnapara Piped Water Supply Scheme | TSM/008378 | 40003488 | Augmentation | MVS | GO2122005377PH | 12/11/2021 | 32.89 | 59.47 | 92.36 | Jalpaiguri Division | Northern Mechanical Division | 15.73 | 20.42 | 0 | 0 | 36.15 | 15.73 | 13.62 | 0 | 0 | 29.35 | 31.78 | 35
219 | JALPAIGURI | SM/15301 | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | TSM/011306 | 40060585 | Augmentation | SVS | GO2223013605PH | 09/02/2023 | 257.86 | 133.62 | 391.48 | Jalpaiguri Division | Northern Mechanical Division | 17.08 | 24.7 | 0 | 0 | 41.78 | 0 | 0 | 0 | 0 | 0 | 0 | 11
220 | JALPAIGURI | SM/18713 | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme | TSM/010092 | 40060591 | Augmentation | SVS | 2262/PHE/IV/W-615/23 | 04/08/2023 | 174.01 | 39.68 | 213.69 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
221 | JALPAIGURI | SM/15077 | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/017647 | 40060581 | Augmentation | SVS | GO2223013135PH | 04/02/2023 | 131.73 | 48.54 | 180.27 | Jalpaiguri Division | Northern Mechanical Division | 9.46 | 4.64 | 0 | 0 | 14.11 | 9.46 | 4.64 | 0 | 0 | 14.11 | 7.83 | 3
222 | JALPAIGURI | SM/15117 | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme | TSM/011311 | 40060582 | Augmentation | SVS | GO2223013208PH | 04/02/2023 | 153.65 | 43.02 | 196.67 | Jalpaiguri Division | Northern Mechanical Division | 110.43 | 9.08 | 0 | 0 | 119.51 | 110.43 | 9.08 | 0 | 0 | 119.51 | 60.77 | 6
223 | JALPAIGURI | SM/16937 | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | TSM/018221 | 40059501 | Augmentation | MVS | GO2223016572PH | 16/03/2023 | 90.06 | 71.93 | 161.99 | Jalpaiguri Division | Northern Mechanical Division | 8.2 | 10.97 | 0 | 0 | 19.17 | 8.2 | 0 | 0 | 0 | 8.2 | 5.06 | 16
224 | JALPAIGURI | SM/15078 | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | TSM/018039 | 40060594 | Augmentation | MVS | GO2223013198PH | 04/02/2023 | 108.52 | 48.54 | 157.06 | Jalpaiguri Division | Northern Mechanical Division | 12.98 | 5.81 | 0 | 0 | 18.79 | 12.98 | 5.81 | 0 | 0 | 18.79 | 11.96 | 16
225 | JALPAIGURI | SM/09859 | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza | TSM/009021 | 40006400 | Augmentation | SVS | GO2122006497PH | 06/12/2021 | 71.02 | 43.67 | 114.69 | Jalpaiguri Division | Northern Mechanical Division | 26.53 | 10.2 | 0 | 0 | 36.73 | 26.37 | 10.2 | 0 | 0 | 36.57 | 31.88 | 9
226 | JALPAIGURI | SM/09862 | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | TSM/009019 | 40006276 | Augmentation | SVS | GO2122006496PH | 06/12/2021 | 64.44 | 40.89 | 105.33 | Jalpaiguri Division | Northern Mechanical Division | 64.44 | 29.11 | 0 | 0 | 93.55 | 54.67 | 29.11 | 0 | 0 | 83.78 | 79.54 | 42
227 | JALPAIGURI | SM/09865 | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | TSM/009018 | 40006410 | Augmentation | SVS | GO2122006495PH | 06/12/2021 | 69.88 | 40.6 | 110.47 | Jalpaiguri Division | Northern Mechanical Division | 51.06 | 8.83 | 0 | 0 | 59.89 | 46.96 | 8.83 | 0 | 0 | 55.79 | 50.5 | 16
228 | JALPAIGURI | SM/15299 | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | TSM/011308 | 40059473 | Augmentation | SVS | GO2223013598PH | 09/02/2023 | 97.68 | 41.65 | 139.34 | Jalpaiguri Division | Northern Mechanical Division | 8.45 | 0 | 0 | 0 | 8.45 | 8.45 | 0 | 0 | 0 | 8.45 | 6.07 | 1
229 | JALPAIGURI | SM/15132 | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME | TSM/018659 | 40059487 | Retrofitting | MVS | GO2223013210PH | 04/02/2023 | 189.88 | 0 | 189.88 | Jalpaiguri Division |  | 52.94 | 0 | 0 | 0 | 52.94 | 51.35 | 0 | 0 | 0 | 51.35 | 27.04 | 18
230 | JALPAIGURI | SM/15131 | RETROFITTING OF MAHITNAGAR PWSS | TSM/018681 | 40059486 | Retrofitting | MVS | GO2223013209PH | 04/02/2023 | 180.43 | 0 | 180.43 | Jalpaiguri Division |  | 69.94 | 0 | 0 | 0 | 69.94 | 69.94 | 0 | 0 | 0 | 69.94 | 38.76 | 10
231 | JALPAIGURI | SM/18625 | SALUGARA PIPED WATER SUPPLY SCHEME | TSM/014952 | 40035729 | New | SVS | 2164/PHE-28011/59/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1052.01 | 130.81 | 1182.82 | Jalpaiguri Division | Northern Mechanical Division | 161.76 | 24.19 | 55.34 | 0 | 241.29 | 161.76 | 24.19 | 55.34 | 0 | 241.29 | 20.4 | 16
232 | JALPAIGURI | SM/14200 | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | TSM/014950 | 40035736 | New | SVS | GO2223011793PH | 10/01/2023 | 649.56 | 129.54 | 779.1 | Jalpaiguri Division | Northern Mechanical Division | 162.73 | 47.57 | 43.1 | 0 | 253.41 | 155.88 | 47.57 | 43.1 | 0 | 246.56 | 31.65 | 20
233 | JALPAIGURI | SM/18759 | Saptibari Piped Water Supply Scheme. | TSM/003947 | 40035472 | New | MVS | 2526/PHE-28011/240/2023-SCHM CELL-Dept. of PHE | 23/08/2023 | 1913.89 | 112.79 | 2026.68 | Jalpaiguri Division | Northern Mechanical Division | 382.04 | 90.26 | 55.55 | 0 | 527.85 | 350.94 | 90.26 | 37.59 | 0 | 478.8 | 23.62 | 6
234 | JALPAIGURI | SM/18760 | Satkhamar Piped Water Supply Scheme. | TSM/004973 | 40035489 | New | MVS | 2526/PHE-28011/240/2023-SCHM CELL-Dept. of PHE | 23/08/2023 | 2023.64 | 114.14 | 2137.78 | Jalpaiguri Division | Northern Mechanical Division | 4.04 | 31.3 | 43.48 | 0 | 78.82 | 4.04 | 31.3 | 43.48 | 0 | 78.82 | 3.69 | 3
235 | JALPAIGURI | SM/13704 | SHAKATI PIPED WATER SUPPLY SCHEME | TSM/015419 | 40034877 | New | SVS | GO2223009706PH | 14/11/2022 | 492.17 | 65.53 | 557.7 | Jalpaiguri Division | Northern Mechanical Division | 163.46 | 25.95 | 22.23 | 0 | 211.64 | 156.39 | 25.95 | 22.23 | 0 | 204.57 | 36.68 | 14
236 | JALPAIGURI | SM/18836 | Sikarpur Piped Water Supply Scheme. | TSM/003956 | 40035950 | New | MVS | 2868/PHE-28011/247/2023-ESTT CELL-Dept. of PHE | 21/09/2023 | 1796.35 | 114.61 | 1910.96 | Jalpaiguri Division |  | 3.89 | 0 | 0 | 0 | 3.89 | 3.89 | 0 | 0 | 0 | 3.89 | 0.2 | 2
237 | JALPAIGURI | SM/14240 | SIMULGURI PIPED WATER SUPPLY SCHEME | TSM/015430 | 40034094 | New | MVS | GO2223012001PH | 16/01/2023 | 944.98 | 227.29 | 1172.27 | Jalpaiguri Division | Northern Mechanical Division | 438.27 | 108.86 | 46.24 | 0 | 593.37 | 438.27 | 55.79 | 46.24 | 0 | 540.3 | 46.09 | 27
238 | JALPAIGURI | SM/18761 | Singimari Piped Water Supply Scheme. | TSM/003948 | 40035586 | New | MVS | 2526/PHE-28011/240/2023-SCHM CELL-Dept. of PHE | 23/08/2023 | 1081.59 | 57.38 | 1138.97 | Jalpaiguri Division | Northern Mechanical Division | 112.81 | 26.32 | 37.77 | 0 | 176.91 | 101.53 | 26.32 | 37.77 | 0 | 165.62 | 14.54 | 11
239 | JALPAIGURI | SM/16778 | Sisubari Tea Garden Piped Water Supply Scheme | TSM/018491 | 40058308 | New | SVS | GO2223015824PH | 13/03/2023 | 256.08 | 70.45 | 326.54 | Jalpaiguri Division | Northern Mechanical Division | 76.73 | 8.12 | 4.08 | 0 | 88.93 | 2.02 | 8.12 | 0 | 0 | 10.14 | 3.11 | 7
240 | JALPAIGURI | SM/15744 | SONAKHULI PIPED WATER SUPPLY SCHEME | TSM/014183 | 40035739 | New | MVS | GO2223014249PH | 20/02/2023 | 383.8 | 62.43 | 446.23 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 4.51 | 0 | 4.51 | 0 | 0 | 4.51 | 0 | 4.51 | 1.01 | 0
241 | JALPAIGURI | SM/08578 | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | TSM/006529 | 40037008 | New | SVS | GO2021006850PH | 10/02/2021 | 115.05 | 35.24 | 150.29 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
242 | JALPAIGURI | SM/08579 | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. | TSM/006528 | 40053875 | New | SVS | GO2021006849PH | 10/02/2021 | 102.09 | 35.24 | 137.33 | Jalpaiguri Division | Northern Mechanical Division | 52.94 | 12.57 | 0 | 0 | 65.51 | 52.94 | 12.57 | 0 | 0 | 65.51 | 47.7 | 67
243 | JALPAIGURI | SM/08581 | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. | TSM/006979 | 40021241 | New | SVS | GO2021006848PH | 10/02/2021 | 135.29 | 37.61 | 172.9 | Jalpaiguri Division | Northern Mechanical Division | 35.71 | 5.76 | 0 | 0 | 41.48 | 35.71 | 5.76 | 0 | 0 | 41.48 | 23.99 | 17
244 | JALPAIGURI | SM/15970 | TESIMALA PIPED WATER SUPPLY SCHEME | TSM/016202 | 40035912 | New | SVS | GO2223014701PH | 22/02/2023 | 355.72 | 36.02 | 391.74 | Jalpaiguri Division | Northern Mechanical Division | 12.43 | 30.22 | 0 | 0 | 42.65 | 12.43 | 30.22 | 0 | 0 | 42.65 | 10.89 | 3
245 | JALPAIGURI | SM/14883 | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | TSM/016364 | 40036019 | New | MVS | GO2223013019PH | 03/02/2023 | 470.8 | 73.51 | 544.31 | Jalpaiguri Division | Northern Mechanical Division | 35.47 | 12.54 | 44.28 | 0 | 92.29 | 35.47 | 12.54 | 44.28 | 0 | 92.29 | 16.96 | 3
246 | JALPAIGURI | SM/13899 | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | TSM/015326 | 40034109 | New | MVS | GO2223010078PH | 25/11/2022 | 685.18 | 87.68 | 772.86 | Jalpaiguri Division | Northern Mechanical Division | 255.66 | 42.11 | 11.08 | 0 | 308.84 | 255.66 | 42.11 | 11.08 | 0 | 308.84 | 39.96 | 17
247 | JALPAIGURI | SM/14660 | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME | TSM/016180 | 40033019 | New | SVS | GO2223012739PH | 31/01/2023 | 482.87 | 37.59 | 520.46 | Jalpaiguri Division | Northern Mechanical Division | 163.06 | 25.07 | 6.62 | 0 | 194.75 | 163.06 | 25.07 | 6.62 | 0 | 194.75 | 37.42 | 11
248 | JALPAIGURI | SM/14919 | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | TSM/015976 | 40033020 | New | SVS | GO2223012954PH | 03/02/2023 | 297.05 | 69.04 | 366.08 | Jalpaiguri Division | Northern Mechanical Division | 44 | 40.39 | 5.49 | 0 | 89.88 | 44 | 21.72 | 5.49 | 0 | 71.21 | 19.45 | 13
249 | JALPAIGURI | SM/14914 | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | TSM/015975 | 40033022 | New | MVS | GO2223012955PH | 03/02/2023 | 409.35 | 68.87 | 478.22 | Jalpaiguri Division | Northern Mechanical Division | 71.56 | 13.2 | 31.63 | 0 | 116.4 | 71.56 | 13.2 | 31.63 | 0 | 116.4 | 24.34 | 5
250 | JALPAIGURI | SM/14886 | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/016191 | 40049255 | New | MVS | GO2223013017PH | 03/02/2023 | 452.87 | 72.52 | 525.39 | Jalpaiguri Division | Northern Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [9 empty] | 108057.39 | 13401.49 | 121458.88 |  |  | 33913.53 | 3666.98 | 3916.96 | 115.69 | 41613.17 | 32215.68 | 3354.43 | 3802.32 | 104.46 | 39476.9 | 32.5