## JJM Schemes Financial Status (M
JJM Schemes Financial Status (MURSHIDABAD) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | MURSHIDABAD | SM/10606 | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph | TSM/010396 | 40013420 | Retrofitting | MVS | GO2223000407PH | 19/04/2022 | 575.23 | 0 | 575.23 | Murshidabad Division | Berhampur M/E Division | 332.5 | 0 | 0 | 0 | 332.5 | 332.5 | 0 | 0 | 0 | 332.5 | 57.8
2 | MURSHIDABAD | SM/08919 | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | TSM/007491 | 1723488 | Retrofitting | SVS | GO2122003903PH | 29/09/2021 | 183.43 | 0 | 183.43 | Berhampur Division I |  | 64.8 | 0 | 0 | 0 | 64.8 | 64.8 | 0 | 0 | 0 | 64.8 | 35.33 | 100
3 | MURSHIDABAD | SM/08910 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshid | TSM/006884 | 5272688 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 487.62 | 0 | 487.62 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4 | MURSHIDABAD | SM/08909 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begunbari (Zone-I) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | TSM/006504 | 5272688 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 460.21 | 0 | 460.21 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5 | MURSHIDABAD | SM/08908 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo | TSM/006882 | 5272688 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 384.82 | 0 | 384.82 | Berhampur Division I |  | 306.82 | 0 | 29.23 | 0 | 336.05 | 306.82 | 0 | 29.23 | 0 | 336.05 | 87.33 | 1
6 | MURSHIDABAD | SM/08906 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | TSM/006881 | 5272688 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 505.26 | 0 | 505.26 | Berhampur Division I |  | 5.88 | 0 | 0 | 0 | 5.88 | 5.88 | 0 | 0 | 0 | 5.88 | 1.16 | 1
7 | MURSHIDABAD | SM/08914 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | TSM/006888 | 8275447 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 870.99 | 0 | 870.99 | Berhampur Division I |  | 547.03 | 0 | 0 | 0 | 547.03 | 547.03 | 0 | 0 | 0 | 547.03 | 62.81
8 | MURSHIDABAD | SM/08907 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | TSM/006502 | 5272688 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 674.11 | 0 | 674.11 | Berhampur Division I |  | 3.16 | 0 | 0 | 0 | 3.16 | 3.16 | 0 | 0 | 0 | 3.16 | 0.47 | 1
9 | MURSHIDABAD | SM/07720 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground | TSM/006514 | 1723193 | Retrofitting | MVS | GO2021004312PH | 08/01/2021 | 92.89 | 0 | 92.89 | Berhampur Division I |  | 60.17 | 0 | 0 | 0 | 60.17 | 60.17 | 0 | 0 | 0 | 60.17 | 64.78 | 100
10 | MURSHIDABAD | SM/07731 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) | TSM/006442 | 8155562 | Retrofitting | SVS | GO2021004254PH | 07/01/2021 | 94.33 | 0 | 94.33 | Berhampur Division I |  | 32.65 | 0 | 0 | 0 | 32.65 | 32.65 | 0 | 0 | 0 | 32.65 | 34.61
11 | MURSHIDABAD | SM/07719 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) | TSM/006513 | 1723343 | Retrofitting | SVS | GO2021004311PH | 08/01/2021 | 85.64 | 0 | 85.64 | Berhampur Division I |  | 56.45 | 0 | 0 | 0 | 56.45 | 56.45 | 0 | 0 | 0 | 56.45 | 65.92 | 100
12 | MURSHIDABAD | SM/07703 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Char Alampur Village (Code-314767), Maheswarpur Village (Code-314768), Chatra Village (Code-314769) Under Command Area Of Moktarp | TSM/006489 | 8156363 | Retrofitting | MVS | GO2021004270PH | 07/01/2021 | 65.9 | 0 | 65.9 | Berhampur Division I |  | 28 | 0 | 0 | 0 | 28 | 28 | 0 | 0 | 0 | 28 | 42.49
13 | MURSHIDABAD | SM/07694 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag | TSM/006474 | 1723170 | Retrofitting | MVS | GO2021004257PH | 07/01/2021 | 83.34 | 0 | 83.34 | Berhampur Division I |  | 37.16 | 0 | 0 | 0 | 37.16 | 37.16 | 0 | 0 | 0 | 37.16 | 44.59 | 100
14 | MURSHIDABAD | SM/07722 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B) | TSM/006518 | 8156469 | Retrofitting | MVS | GO2021004303PH | 08/01/2021 | 43.55 | 0 | 43.55 | Berhampur Division I |  | 23.41 | 0 | 0 | 0 | 23.41 | 23.41 | 0 | 0 | 0 | 23.41 | 53.76 | 6
15 | MURSHIDABAD | SM/07783 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gobindotala Village (Code-314454), Paschim Rampur (Code-314455) In The Command Area Of Paschim Rampur Ground Water Supply Scheme | TSM/006433 | 8155480 | Retrofitting | SVS | GO2021004190PH | 07/01/2021 | 88.5 | 0 | 88.5 | Berhampur Division I |  | 66.78 | 0 | 0 | 0 | 66.78 | 66.78 | 0 | 0 | 0 | 66.78 | 75.45
16 | MURSHIDABAD | SM/07699 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) | TSM/006485 | 1723343 | Retrofitting | SVS | GO2021004269PH | 07/01/2021 | 96.83 | 0 | 96.83 | Berhampur Division I |  | 62.88 | 0 | 0 | 0 | 62.88 | 62.88 | 0 | 0 | 0 | 62.88 | 64.94 | 100
17 | MURSHIDABAD | SM/07784 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba | TSM/006453 | 1723332 | Retrofitting | SVS | GO2021004193PH | 07/01/2021 | 82.98 | 0 | 82.98 | Berhampur Division I |  | 61.35 | 0 | 0 | 0 | 61.35 | 61.35 | 0 | 0 | 0 | 61.35 | 73.94 | 100
18 | MURSHIDABAD | SM/07716 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jhaudanga (Code-314195) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-B) | TSM/006510 | 8155432 | Retrofitting | SVS | GO2021004308PH | 08/01/2021 | 12.33 | 0 | 12.33 | Berhampur Division I |  | 8.62 | 0 | 0 | 0 | 8.62 | 8.62 | 0 | 0 | 0 | 8.62 | 69.89 | 6
19 | MURSHIDABAD | SM/07723 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A) | TSM/006519 | 8156483 | Retrofitting | MVS | GO2021004304PH | 08/01/2021 | 89.7 | 0 | 89.7 | Berhampur Division I |  | 48.98 | 0 | 0 | 0 | 48.98 | 48.98 | 0 | 0 | 0 | 48.98 | 54.6
20 | MURSHIDABAD | SM/07695 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa | TSM/006476 | 1723170 | Retrofitting | MVS | GO2021004259PH | 07/01/2021 | 119.21 | 0 | 119.21 | Berhampur Division I |  | 105.71 | 0 | 0 | 0 | 105.71 | 105.71 | 0 | 0 | 0 | 105.71 | 88.67 | 100
21 | MURSHIDABAD | SM/08902 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U | TSM/006486 | 1723343 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 304.14 | 0 | 304.14 | Berhampur Division I |  | 207.87 | 0 | 0 | 0 | 207.87 | 207.87 | 0 | 0 | 0 | 207.87 | 68.35 | 100
22 | MURSHIDABAD | SM/07700 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) | TSM/006501 | 8156390 | Retrofitting | SVS | GO2021004272PH | 07/01/2021 | 164.71 | 0 | 164.71 | Berhampur Division I |  | 0 | 0 | 13.51 | 0 | 13.51 | 0 | 0 | 13.51 | 0 | 13.51 | 8.2
23 | MURSHIDABAD | SM/07698 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu | TSM/006484 | 8156282 | Retrofitting | MVS | GO2021004266PH | 07/01/2021 | 95.9 | 0 | 95.9 | Berhampur Division I |  | 53.88 | 0 | 0 | 0 | 53.88 | 53.88 | 0 | 0 | 0 | 53.88 | 56.18 | 6
24 | MURSHIDABAD | SM/07696 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kulberia Village (Code-315685) Under Command Area Of Andulberia Ground Water Supply Scheme (Part-A) | TSM/006479 | 1723331 | Retrofitting | SVS | GO2021004262PH | 07/01/2021 | 57.19 | 0 | 57.19 | Berhampur Division I |  | 31.27 | 0 | 0 | 0 | 31.27 | 31.27 | 0 | 0 | 0 | 31.27 | 54.68
25 | MURSHIDABAD | SM/07697 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(P | TSM/006483 | 8156260 | Retrofitting | MVS | GO2021004264PH | 07/01/2021 | 168.17 | 0 | 168.17 | Berhampur Division I |  | 57.28 | 0 | 0 | 0 | 57.28 | 57.28 | 0 | 0 | 0 | 57.28 | 34.06
26 | MURSHIDABAD | SM/07786 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad | TSM/006455 | 8155579 | Retrofitting | SVS | GO2021004220PH | 07/01/2021 | 16.62 | 0 | 16.62 | Berhampur Division I |  | 9.51 | 0 | 0 | 0 | 9.51 | 9.51 | 0 | 0 | 0 | 9.51 | 57.18 | 6
27 | MURSHIDABAD | SM/07734 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Maiya Village (Code-314146) In The Command Area Of Maiya Ground Water Supply Scheme (Part-A) | TSM/006451 | 1723332 | Retrofitting | SVS | GO2021004253PH | 07/01/2021 | 215.11 | 0 | 215.11 | Berhampur Division I |  | 109.18 | 0 | 0 | 0 | 109.18 | 109.18 | 0 | 0 | 0 | 109.18 | 50.76 | 100
28 | MURSHIDABAD | SM/07728 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Malipara Village (Code-314452), Saaragachi Village (Code-314453),Chainpara Village (Code-314457),Rameswarbati Village (Code-31445 | TSM/006438 | 8155506 | Retrofitting | SVS | GO2021004258PH | 07/01/2021 | 63.18 | 0 | 63.18 | Berhampur Division I |  | 37.79 | 0 | 0 | 0 | 37.79 | 37.79 | 0 | 0 | 0 | 37.79 | 59.82
29 | MURSHIDABAD | SM/07717 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Manganpara Village (Code-315662) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-A) | TSM/006511 | 1723293 | Retrofitting | SVS | GO2021004309PH | 08/01/2021 | 53.68 | 0 | 53.68 | Berhampur Division I |  | 29.89 | 0 | 0 | 0 | 29.89 | 29.89 | 0 | 0 | 0 | 29.89 | 55.68 | 100
30 | MURSHIDABAD | SM/07718 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part | TSM/006512 | 8156429 | Retrofitting | MVS | GO2021004310PH | 08/01/2021 | 93.76 | 0 | 93.76 | Berhampur Division I |  | 67.96 | 0 | 0 | 0 | 67.96 | 67.96 | 0 | 0 | 0 | 67.96 | 72.48 | 6
31 | MURSHIDABAD | SM/07888 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Moktarpur Village (Code-314766), Under Command Area Of Moktarpur Ground Water Supply Scheme(Part-A) Under Raninagar-I Block In M | TSM/006516 | 8156350 | Retrofitting | SVS | GO2021004750PH | 19/01/2021 | 162.87 | 0 | 162.87 | Berhampur Division I |  | 96.08 | 0 | 0 | 0 | 96.08 | 96.08 | 0 | 0 | 0 | 96.08 | 58.99
32 | MURSHIDABAD | SM/07690 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) | TSM/006448 | 8362354 | Retrofitting | SVS | GO2021004283PH | 07/01/2021 | 129.56 | 0 | 129.56 | Berhampur Division I |  | 102.89 | 0 | 0 | 0 | 102.89 | 102.89 | 0 | 0 | 0 | 102.89 | 79.42 | 2
33 | MURSHIDABAD | SM/07727 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B) | TSM/006437 | 8155488 | Retrofitting | SVS | GO2021004260PH | 07/01/2021 | 49.3 | 0 | 49.3 | Berhampur Division I |  | 29.48 | 0 | 0 | 0 | 29.48 | 29.48 | 0 | 0 | 0 | 29.48 | 59.8 | 6
34 | MURSHIDABAD | SM/08901 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P | TSM/006481 | 1723331 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 310.52 | 0 | 310.52 | Berhampur Division I |  | 211.95 | 0 | 0 | 0 | 211.95 | 211.95 | 0 | 0 | 0 | 211.95 | 68.25
35 | MURSHIDABAD | SM/07729 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) | TSM/006439 | 8155548 | Retrofitting | SVS | GO2021004256PH | 07/01/2021 | 64.96 | 0 | 64.96 | Berhampur Division I |  | 43.27 | 0 | 0 | 0 | 43.27 | 43.27 | 0 | 0 | 0 | 43.27 | 66.6 | 2
36 | MURSHIDABAD | SM/07785 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgo | TSM/006454 | 1723332 | Retrofitting | SVS | GO2021004216PH | 07/01/2021 | 44.45 | 0 | 44.45 | Berhampur Division I |  | 28.1 | 0 | 0 | 0 | 28.1 | 28.1 | 0 | 0 | 0 | 28.1 | 63.2 | 100
37 | MURSHIDABAD | SM/07705 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba | TSM/006428 | 8155412 | Retrofitting | SVS | GO2021004279PH | 07/01/2021 | 143.18 | 0 | 143.18 | Berhampur Division I |  | 131.88 | 0 | 0 | 0 | 131.88 | 109.88 | 0 | 0 | 0 | 109.88 | 76.74
38 | MURSHIDABAD | SM/07693 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) | TSM/006472 | 1723293 | Retrofitting | MVS | GO2021004251PH | 07/01/2021 | 131.51 | 0 | 131.51 | Berhampur Division I |  | 70.91 | 0 | 0 | 0 | 70.91 | 70.91 | 0 | 0 | 0 | 70.91 | 53.91 | 100
39 | MURSHIDABAD | SM/07889 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part | TSM/006515 | 1723193 | Retrofitting | MVS | GO2021004746PH | 19/01/2021 | 49.64 | 0 | 49.64 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
40 | MURSHIDABAD | SM/07689 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) | TSM/006427 | 8155396 | Retrofitting | SVS | GO2021004281PH | 07/01/2021 | 32.25 | 0 | 32.25 | Berhampur Division I |  | 23.33 | 0 | 0 | 0 | 23.33 | 23.33 | 0 | 0 | 0 | 23.33 | 72.34
41 | MURSHIDABAD | SM/07730 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sundarpur (Code-314445) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-B) | TSM/006440 | 8155554 | Retrofitting | SVS | GO2021004255PH | 07/01/2021 | 68.76 | 0 | 68.76 | Berhampur Division I |  | 51.13 | 0 | 0 | 0 | 51.13 | 51.13 | 0 | 0 | 0 | 51.13 | 74.36 | 6
42 | MURSHIDABAD | SM/07732 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Telia Village (Code-314466) In The Command Area Of Telia Ground Water Supply Scheme (Part-B) | TSM/006457 | 8155597 | Retrofitting | SVS | GO2021004268PH | 07/01/2021 | 118.61 | 0 | 118.61 | Berhampur Division I |  | 95.85 | 0 | 0 | 0 | 95.85 | 95.85 | 0 | 0 | 0 | 95.85 | 80.81
43 | MURSHIDABAD | SM/07714 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) | TSM/006430 | 1723408 | Retrofitting | MVS | GO2021004305PH | 08/01/2021 | 79.62 | 0 | 79.62 | Berhampur Division I |  | 75.17 | 0 | 0 | 0 | 75.17 | 75.17 | 0 | 0 | 0 | 75.17 | 94.4 | 60
44 | MURSHIDABAD | SM/07789 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Benipur (Code-314546) In The Command Area Of Benipur Ground Water Supply Scheme (Part-A) Under Bhagwangola-II Bloc | TSM/006462 | 1723443 | Retrofitting | SVS | GO2021004215PH | 07/01/2021 | 115.48 | 0 | 115.48 | Berhampur Division I |  | 78.84 | 0 | 0 | 0 | 78.84 | 78.84 | 0 | 0 | 0 | 78.84 | 68.27 | 100
45 | MURSHIDABAD | SM/07793 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagw | TSM/006466 | 1723385 | Retrofitting | SVS | GO2021004202PH | 07/01/2021 | 157.17 | 0 | 157.17 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
46 | MURSHIDABAD | SM/07791 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Char Molladanga (Code-314558) In The Command Area Of Benipur Ground Water Supply Scheme (Part-C) Under Bhagwangola | TSM/006464 | 1723443 | Retrofitting | SVS | GO2021004204PH | 07/01/2021 | 63.22 | 0 | 63.22 | Berhampur Division I |  | 43.32 | 0 | 0 | 0 | 43.32 | 43.32 | 0 | 0 | 0 | 43.32 | 68.52 | 100
47 | MURSHIDABAD | SM/07788 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kalmegha (Code-314221) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-D) Under Lalgola Block In | TSM/006461 | 4922411 | Retrofitting | SVS | GO2021004218PH | 07/01/2021 | 99.99 | 0 | 99.99 | Berhampur Division I |  | 87.33 | 0 | 0 | 0 | 87.33 | 87.33 | 0 | 0 | 0 | 87.33 | 87.34 | 100
48 | MURSHIDABAD | SM/07725 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) | TSM/006435 | 8155528 | Retrofitting | SVS | GO2021004263PH | 07/01/2021 | 119.17 | 0 | 119.17 | Berhampur Division I |  | 74.44 | 0 | 0 | 0 | 74.44 | 74.44 | 0 | 0 | 0 | 74.44 | 62.47 | 6
49 | MURSHIDABAD | SM/07790 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo | TSM/006463 | 1723443 | Retrofitting | SVS | GO2021004214PH | 07/01/2021 | 89.83 | 0 | 89.83 | Berhampur Division I |  | 44.98 | 0 | 0 | 0 | 44.98 | 44.98 | 0 | 0 | 0 | 44.98 | 50.07 | 100
50 | MURSHIDABAD | SM/08899 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu | TSM/006432 | 1723408 | Retrofitting | SVS | GO2122003903PH | 29/09/2021 | 373.6 | 0 | 373.6 | Berhampur Division I |  | 216.15 | 0 | 0 | 0 | 216.15 | 206.51 | 0 | 0 | 0 | 206.51 | 55.27 | 60
51 | MURSHIDABAD | SM/07796 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Wate | TSM/006469 | 8156232 | Retrofitting | MVS | GO2021004196PH | 07/01/2021 | 92.37 | 0 | 92.37 | Berhampur Division I |  | 60 | 0 | 0 | 0 | 60 | 57.79 | 0 | 0 | 0 | 57.79 | 62.57
52 | MURSHIDABAD | SM/07715 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P | TSM/006431 | 1723408 | Retrofitting | MVS | GO2021004307PH | 08/01/2021 | 69.44 | 0 | 69.44 | Berhampur Division I |  | 41.97 | 0 | 0 | 0 | 41.97 | 41.97 | 0 | 0 | 0 | 41.97 | 60.44 | 60
53 | MURSHIDABAD | SM/07726 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Chandipur Ramkantapur (Code-314483), Rasulpur (Code-314492) In The Command Area Of Kasba Bahadurpur Ground Water | TSM/006436 | 8155536 | Retrofitting | SVS | GO2021004261PH | 07/01/2021 | 76.06 | 0 | 76.06 | Berhampur Division I |  | 45.74 | 0 | 0 | 0 | 45.74 | 45.74 | 0 | 0 | 0 | 45.74 | 60.13
54 | MURSHIDABAD | SM/07688 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr | TSM/006412 | 8362348 | Retrofitting | SVS | GO2021004285PH | 07/01/2021 | 98.85 | 0 | 98.85 | Berhampur Division I |  | 62 | 0 | 0 | 0 | 62 | 62 | 0 | 0 | 0 | 62 | 62.72 | 2
55 | MURSHIDABAD | SM/07795 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jhikra (Code-314512), Ranitala (Code-314513) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-A) Un | TSM/006468 | 8156211 | Retrofitting | MVS | GO2021004199PH | 07/01/2021 | 83.47 | 0 | 83.47 | Berhampur Division I |  | 53.37 | 0 | 0 | 0 | 53.37 | 53.37 | 0 | 0 | 0 | 53.37 | 63.94 | 6
56 | MURSHIDABAD | SM/07787 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block | TSM/006460 | 4922411 | Retrofitting | SVS | GO2021004219PH | 07/01/2021 | 76.68 | 0 | 76.68 | Berhampur Division I |  | 64.25 | 0 | 0 | 0 | 64.25 | 64.25 | 0 | 0 | 0 | 64.25 | 83.79 | 100
57 | MURSHIDABAD | SM/08106 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- | TSM/006458 | 4922411 | Retrofitting | MVS | GO2021006700PH | 09/02/2021 | 360.94 | 0 | 360.94 | Berhampur Division I |  | 129.61 | 0 | 0 | 0 | 129.61 | 129.61 | 0 | 0 | 0 | 129.61 | 35.91 | 100
58 | MURSHIDABAD | SM/07687 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) | TSM/006395 | 8362345 | Retrofitting | SVS | GO2021004286PH | 07/01/2021 | 99.51 | 0 | 99.51 | Berhampur Division I |  | 73.75 | 0 | 0 | 0 | 73.75 | 73.75 | 0 | 0 | 0 | 73.75 | 74.11 | 2
59 | MURSHIDABAD | SM/07794 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply | TSM/006467 | 1723385 | Retrofitting | MVS | GO2021004201PH | 07/01/2021 | 82.35 | 0 | 82.35 | Berhampur Division I |  | 48.54 | 0 | 0 | 0 | 48.54 | 48.54 | 0 | 0 | 0 | 48.54 | 58.95 | 100
60 | MURSHIDABAD | SM/07724 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C | TSM/006434 | 8155521 | Retrofitting | SVS | GO2021004265PH | 07/01/2021 | 99.92 | 0 | 99.92 | Berhampur Division I |  | 66.39 | 0 | 0 | 0 | 66.39 | 66.39 | 0 | 0 | 0 | 66.39 | 66.44
61 | MURSHIDABAD | SM/07733 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Ramchandrapur (Code-314219) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-B) | TSM/006459 | 4922411 | Retrofitting | SVS | GO2021004267PH | 07/01/2021 | 55.09 | 0 | 55.09 | Berhampur Division I |  | 11.14 | 0 | 0 | 0 | 11.14 | 11.14 | 0 | 0 | 0 | 11.14 | 20.23 | 100
62 | MURSHIDABAD | SM/07691 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | TSM/006429 | 1723408 | Retrofitting | SVS | GO2021004276PH | 07/01/2021 | 84.54 | 0 | 84.54 | Berhampur Division I |  | 47 | 0 | 0 | 0 | 47 | 46.98 | 0 | 0 | 0 | 46.98 | 55.57 | 60
63 | MURSHIDABAD | SM/07792 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) | TSM/006465 | 1723443 | Retrofitting | MVS | GO2021004203PH | 07/01/2021 | 94.73 | 0 | 94.73 | Berhampur Division I |  | 59.74 | 0 | 0 | 0 | 59.74 | 59.74 | 0 | 0 | 0 | 59.74 | 63.07 | 100
64 | MURSHIDABAD | SM/08911 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | TSM/006885 | 8275475 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 717.96 | 0 | 717.96 | Berhampur Division I |  | 371.06 | 0 | 0 | 0 | 371.06 | 371.06 | 0 | 0 | 0 | 371.06 | 51.68
65 | MURSHIDABAD | SM/08912 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | TSM/006886 | 8275467 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 995.85 | 0 | 995.85 | Berhampur Division I |  | 521.97 | 0 | 0.1 | 0 | 522.07 | 521.97 | 0 | 0.1 | 0 | 522.07 | 52.42
66 | MURSHIDABAD | SM/08916 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | TSM/006890 | 8275486 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 1325.56 | 0 | 1325.56 | Berhampur Division I |  | 759.05 | 0 | 0 | 0 | 759.05 | 759.05 | 0 | 0 | 0 | 759.05 | 57.26 | 68
67 | MURSHIDABAD | SM/07721 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District | TSM/006517 | 8156454 | Retrofitting | SVS | GO2021004302PH | 08/01/2021 | 53.33 | 0 | 53.33 | Berhampur Division I |  | 41.84 | 0 | 0 | 0 | 41.84 | 41.07 | 0 | 0 | 0 | 41.07 | 77.01 | 6
68 | MURSHIDABAD | SM/08903 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | TSM/006488 | 8156317 | Retrofitting | SVS | GO2122003903PH | 29/09/2021 | 362.25 | 0 | 362.25 | Berhampur Division I |  | 244.29 | 0 | 0 | 0 | 244.29 | 244.27 | 0 | 0 | 0 | 244.27 | 67.43
69 | MURSHIDABAD | SM/07233 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Bansgara ground water supply scheme | TSM/006069 | 1723419 | Retrofitting | MVS | GO2021003164PH | 08/12/2020 | 97.22 | 0 | 97.22 | Berhampur Division I |  | 58.68 | 0 | 0 | 0 | 58.68 | 58.68 | 0 | 0 | 0 | 58.68 | 60.36 | 100
70 | MURSHIDABAD | SM/08115 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | TSM/006902 | 8275548 | Retrofitting | MVS | GO2021006702PH | 09/02/2021 | 552.45 | 0 | 552.45 | Berhampur Division I |  | 383.12 | 0 | 0 | 0 | 383.12 | 325.67 | 0 | 0 | 0 | 325.67 | 58.95 | 2
71 | MURSHIDABAD | SM/08113 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | TSM/006509 | 2482067 | Retrofitting | MVS | GO2021006699PH | 09/02/2021 | 746.48 | 0 | 746.48 | Berhampur Division I |  | 339.06 | 0 | 18.66 | 0 | 357.72 | 339.06 | 0 | 18.66 | 0 | 357.72 | 47.92 | 65
72 | MURSHIDABAD | SM/08904 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | TSM/006499 | 1723215 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 385.71 | 0 | 385.71 | Berhampur Division I |  | 157.6 | 0 | 11.65 | 0 | 169.25 | 157.6 | 0 | 11.65 | 0 | 169.25 | 43.88 | 100
73 | MURSHIDABAD | SM/08109 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | TSM/006507 | 8275498 | Retrofitting | MVS | GO2021006711PH | 09/02/2021 | 886.86 | 0 | 886.86 | Berhampur Division I |  | 584.51 | 0 | 0 | 0 | 584.51 | 584.51 | 0 | 0 | 0 | 584.51 | 65.91 | 2
74 | MURSHIDABAD | SM/07228 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | TSM/006054 | 1723195 | Retrofitting | MVS | GO2021003168PH | 08/12/2020 | 84.17 | 0 | 84.17 | Berhampur Division I |  | 45.64 | 0 | 0 | 0 | 45.64 | 45.64 | 0 | 0 | 0 | 45.64 | 54.22 | 100
75 | MURSHIDABAD | SM/07692 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | TSM/006470 | 1723244 | Retrofitting | MVS | GO2021004274PH | 07/01/2021 | 283.13 | 0 | 283.13 | Berhampur Division I |  | 198.17 | 0 | 4.56 | 0 | 202.73 | 198.17 | 0 | 4.56 | 0 | 202.73 | 71.6 | 100
76 | MURSHIDABAD | SM/08913 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | TSM/006887 | 8275456 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 964.85 | 0 | 964.85 | Berhampur Division I |  | 632.36 | 0 | 0 | 0 | 632.36 | 632.36 | 0 | 0 | 0 | 632.36 | 65.54
77 | MURSHIDABAD | SM/06980 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme | TSM/006034 | 8136297 | Retrofitting | MVS | GO2021002468PH | 09/11/2020 | 80.61 | 0 | 80.61 | Berhampur Division I |  | 63.68 | 0 | 0 | 0 | 63.68 | 63.68 | 0 | 0 | 0 | 63.68 | 78.99 | 12
78 | MURSHIDABAD | SM/06982 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme | TSM/006052 | 8136601 | Retrofitting | MVS | GO2021002457PH | 09/11/2020 | 71.77 | 0 | 71.77 | Berhampur Division I |  | 53.57 | 0 | 0 | 0 | 53.57 | 53.57 | 0 | 0 | 0 | 53.57 | 74.65 | 2
79 | MURSHIDABAD | SM/08114 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | TSM/006897 | 5272688 | Retrofitting | MVS | GO2021006696PH | 09/02/2021 | 312.34 | 0 | 312.34 | Berhampur Division I |  | 168.87 | 0 | 0 | 0 | 168.87 | 168.87 | 0 | 0 | 0 | 168.87 | 54.06 | 1
80 | MURSHIDABAD | SM/06985 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | TSM/006070 | 1723386 | Retrofitting | MVS | GO2021002460PH | 09/11/2020 | 99.86 | 0 | 99.86 | Berhampur Division I |  | 50.05 | 0 | 0 | 0 | 50.05 | 50.05 | 0 | 0 | 0 | 50.05 | 50.11 | 100
81 | MURSHIDABAD | SM/08915 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | TSM/006506 | 8275430 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 983.07 | 0 | 983.07 | Berhampur Division I |  | 363.8 | 0 | 0 | 0 | 363.8 | 363.8 | 0 | 0 | 0 | 363.8 | 37.01 | 2
82 | MURSHIDABAD | SM/07227 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme | TSM/006051 | 1723251 | Retrofitting | MVS | GO2021003169PH | 08/12/2020 | 92.47 | 0 | 92.47 | Berhampur Division I |  | 74.36 | 0 | 0 | 0 | 74.36 | 74.36 | 0 | 0 | 0 | 74.36 | 80.42 | 100
83 | MURSHIDABAD | SM/06984 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | TSM/006063 | 1723220 | Retrofitting | MVS | GO2021002459PH | 09/11/2020 | 99.87 | 0 | 99.87 | Berhampur Division I |  | 50.56 | 0 | 0 | 0 | 50.56 | 38.64 | 0 | 0 | 0 | 38.64 | 38.69 | 100
84 | MURSHIDABAD | SM/07231 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme | TSM/006065 | 1723220 | Retrofitting | MVS | GO2021003162PH | 08/12/2020 | 71.2 | 0 | 71.2 | Berhampur Division I |  | 56.41 | 0 | 0 | 0 | 56.41 | 56.41 | 0 | 0 | 0 | 56.41 | 79.23 | 100
85 | MURSHIDABAD | SM/07223 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme | TSM/006033 | 8136589 | Retrofitting | SVS | GO2021003174PH | 08/12/2020 | 59.03 | 0 | 59.03 | Berhampur Division I |  | 34.35 | 0 | 0 | 0 | 34.35 | 34.35 | 0 | 0 | 0 | 34.35 | 58.19 | 70
86 | MURSHIDABAD | SM/08917 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | TSM/006508 | 8275507 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 865.34 | 0 | 865.34 | Berhampur Division I |  | 412.79 | 0 | 0 | 0 | 412.79 | 412.79 | 0 | 0 | 0 | 412.79 | 47.7
87 | MURSHIDABAD | SM/07890 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I | TSM/006900 | 5272688 | Retrofitting | MVS | GO2021004751PH | 19/01/2021 | 173.44 | 0 | 173.44 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
88 | MURSHIDABAD | SM/06981 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | TSM/006036 | 1723263 | Retrofitting | MVS | GO2021002469PH | 09/11/2020 | 94.89 | 0 | 94.89 | Berhampur Division I |  | 57.27 | 0 | 0 | 0 | 57.27 | 57.27 | 0 | 0 | 0 | 57.27 | 60.35 | 100
89 | MURSHIDABAD | SM/07701 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | TSM/006503 | 5272688 | Retrofitting | SVS | GO2021004289PH | 07/01/2021 | 169.75 | 0 | 169.75 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
90 | MURSHIDABAD | SM/08107 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-J) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | TSM/006505 | 5272688 | Retrofitting | MVS | GO2021006713PH | 09/02/2021 | 383.46 | 0 | 383.46 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
91 | MURSHIDABAD | SM/07704 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mirzapur (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | TSM/006901 | 5272688 | Retrofitting | SVS | GO2021004288PH | 07/01/2021 | 64.01 | 0 | 64.01 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
92 | MURSHIDABAD | SM/07702 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Naopukuria (Zone-K) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | TSM/006883 | 5272688 | Retrofitting | SVS | GO2021004223PH | 07/01/2021 | 240.81 | 0 | 240.81 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
93 | MURSHIDABAD | SM/08110 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | TSM/006891 | 8275522 | Retrofitting | MVS | GO2021006712PH | 09/02/2021 | 1021.1 | 0 | 1021.1 | Berhampur Division I |  | 414.13 | 0 | 0 | 0 | 414.13 | 414.13 | 0 | 0 | 0 | 414.13 | 40.56 | 2
94 | MURSHIDABAD | SM/08108 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | TSM/006889 | 8363450 | Retrofitting | MVS | GO2021006710PH | 09/02/2021 | 1063.3 | 0 | 1063.3 | Berhampur Division I |  | 575.1 | 0 | 0 | 0 | 575.1 | 575.09 | 0 | 0 | 0 | 575.09 | 54.09
95 | MURSHIDABAD | SM/08111 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | TSM/006892 | 8275533 | Retrofitting | MVS | GO2021006697PH | 09/02/2021 | 1011.33 | 0 | 1011.33 | Berhampur Division I |  | 400.52 | 0 | 0 | 0 | 400.52 | 400.52 | 0 | 0 | 0 | 400.52 | 39.6 | 25
96 | MURSHIDABAD | SM/07232 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme | TSM/006067 | 8136628 | Retrofitting | SVS | GO2021003163PH | 08/12/2020 | 21.55 | 0 | 21.55 | Berhampur Division I |  | 13.39 | 0 | 0 | 0 | 13.39 | 12.99 | 0 | 0 | 0 | 12.99 | 60.31 | 2
97 | MURSHIDABAD | SM/08905 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | TSM/006500 | 1723404 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 650.52 | 0 | 650.52 | Berhampur Division I |  | 390.89 | 0 | 16.49 | 0 | 407.37 | 390.89 | 0 | 16.49 | 0 | 407.37 | 62.62 | 100
98 | MURSHIDABAD | SM/08900 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | TSM/006471 | 1723330 | Retrofitting | MVS | GO2122003903PH | 29/09/2021 | 579.45 | 0 | 579.45 | Berhampur Division I |  | 241.07 | 0 | 15.4 | 0 | 256.47 | 241.07 | 0 | 15.4 | 0 | 256.47 | 44.26 | 99
99 | MURSHIDABAD | SM/07229 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramnapara ground water supply scheme | TSM/006056 | 8136608 | Retrofitting | SVS | GO2021003160PH | 08/12/2020 | 18.59 | 0 | 18.59 | Berhampur Division I |  | 13.34 | 0 | 0 | 0 | 13.34 | 13.34 | 0 | 0 | 0 | 13.34 | 71.77 | 70
100 | MURSHIDABAD | SM/08116 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | TSM/006903 | 8275564 | Retrofitting | MVS | GO2021006703PH | 09/02/2021 | 823.92 | 0 | 823.92 | Berhampur Division I |  | 654.06 | 0 | 0 | 0 | 654.06 | 654.06 | 0 | 0 | 0 | 654.06 | 79.38
101 | MURSHIDABAD | SM/08112 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | TSM/006894 | 8363463 | Retrofitting | MVS | GO2021006698PH | 09/02/2021 | 777.42 | 0 | 777.42 | Berhampur Division I |  | 559.14 | 0 | 0 | 0 | 559.14 | 531.37 | 0 | 0 | 0 | 531.37 | 68.35
102 | MURSHIDABAD | SM/07225 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sarkarpara ground water supply scheme | TSM/006037 | 8136302 | Retrofitting | SVS | GO2021003167PH | 08/12/2020 | 30.52 | 0 | 30.52 | Berhampur Division I |  | 16.81 | 0 | 0 | 0 | 16.81 | 16.81 | 0 | 0 | 0 | 16.81 | 55.08 | 2
103 | MURSHIDABAD | SM/08117 | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector | TSM/006904 | 8275574 | Retrofitting | MVS | GO2021006709PH | 09/02/2021 | 533.01 | 0 | 533.01 | Berhampur Division I |  | 322.52 | 0 | 0 | 0 | 322.52 | 322.51 | 0 | 0 | 0 | 322.51 | 60.51 | 60
104 | MURSHIDABAD | SM/07226 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme | TSM/006049 | 8136593 | Retrofitting | SVS | GO2021003170PH | 08/12/2020 | 87.91 | 0 | 87.91 | Berhampur Division I |  | 62 | 0 | 0 | 0 | 62 | 62 | 0 | 0 | 0 | 62 | 70.53 | 2
105 | MURSHIDABAD | SM/07224 | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme | TSM/006035 | 1723388 | Retrofitting | SVS | GO2021003175PH | 08/12/2020 | 52.11 | 0 | 52.11 | Berhampur Division I |  | 30.04 | 0 | 0 | 0 | 30.04 | 30.04 | 0 | 0 | 0 | 30.04 | 57.66 | 100
106 | MURSHIDABAD | SM/07236 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | TSM/006024 | 1723179 | Retrofitting | MVS | GO2021003171PH | 08/12/2020 | 58.14 | 0 | 58.14 | Berhampur Division I |  | 39.68 | 0 | 0 | 0 | 39.68 | 39.68 | 0 | 0 | 0 | 39.68 | 68.26 | 100
107 | MURSHIDABAD | SM/07221 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) | TSM/006023 | 1723179 | Retrofitting | SVS | GO2021003172PH | 08/12/2020 | 62.74 | 0 | 62.74 | Berhampur Division I |  | 48.51 | 0 | 0 | 0 | 48.51 | 48.51 | 0 | 0 | 0 | 48.51 | 77.32 | 100
108 | MURSHIDABAD | SM/06976 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate | TSM/006028 | 8130587 | Retrofitting | SVS | GO2021002464PH | 09/11/2020 | 72.72 | 0 | 72.72 | Berhampur Division I |  | 21.82 | 0 | 0 | 0 | 21.82 | 9.78 | 0 | 0 | 0 | 9.78 | 13.45 | 25
109 | MURSHIDABAD | SM/07235 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o | TSM/006075 | 8136655 | Retrofitting | SVS | GO2021003166PH | 08/12/2020 | 81.52 | 0 | 81.52 | Berhampur Division I |  | 61.37 | 0 | 0 | 0 | 61.37 | 61.37 | 0 | 0 | 0 | 61.37 | 75.28 | 2
110 | MURSHIDABAD | SM/06975 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Digha (VillageCode-314460) under command area under Digha ground water supply scheme (Part-A) | TSM/006027 | 8136586 | Retrofitting | SVS | GO2021002463PH | 09/11/2020 | 86.87 | 0 | 86.87 | Berhampur Division I |  | 55.61 | 0 | 0 | 0 | 55.61 | 29.55 | 0 | 0 | 0 | 29.55 | 34.02 | 2
111 | MURSHIDABAD | SM/06983 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) | TSM/006059 | 8136615 | Retrofitting | SVS | GO2021002458PH | 09/11/2020 | 93.43 | 0 | 93.43 | Berhampur Division I |  | 75.82 | 0 | 0 | 0 | 75.82 | 47.79 | 0 | 0 | 0 | 47.79 | 51.15 | 2
112 | MURSHIDABAD | SM/07234 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s | TSM/006073 | 8136633 | Retrofitting | SVS | GO2021003165PH | 08/12/2020 | 87.8 | 0 | 87.8 | Berhampur Division I |  | 60.85 | 0 | 0 | 0 | 60.85 | 60.85 | 0 | 0 | 0 | 60.85 | 69.31 | 10
113 | MURSHIDABAD | SM/07230 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) | TSM/006061 | 8136620 | Retrofitting | SVS | GO2021003161PH | 08/12/2020 | 74.26 | 0 | 74.26 | Berhampur Division I |  | 47.4 | 0 | 0 | 0 | 47.4 | 46.21 | 0 | 0 | 0 | 46.21 | 62.23 | 2
114 | MURSHIDABAD | SM/07222 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Sahebnagar (VillageCode-314609) under command area of Kazipara ground water supply scheme (Part-A) | TSM/006029 | 8136587 | Retrofitting | MVS | GO2021003173PH | 08/12/2020 | 66.28 | 0 | 66.28 | Berhampur Division I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | MURSHIDABAD | SM/06977 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code | TSM/006030 | 8130032 | Retrofitting | SVS | GO2021002465PH | 09/11/2020 | 99.54 | 0 | 99.54 | Berhampur Division I |  | 79.84 | 0 | 0 | 0 | 79.84 | 79.84 | 0 | 0 | 0 | 79.84 | 80.21 | 25
116 | MURSHIDABAD | SM/06978 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 | TSM/006031 | 8130058 | Retrofitting | SVS | GO2021002466PH | 09/11/2020 | 90.08 | 0 | 90.08 | Berhampur Division I |  | 86.54 | 0 | 0 | 0 | 86.54 | 68.03 | 0 | 0 | 0 | 68.03 | 75.52 | 25
117 | MURSHIDABAD | SM/06973 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) | TSM/006025 | 1723191 | Retrofitting | SVS | GO2021002461PH | 09/11/2020 | 50.08 | 0 | 50.08 | Berhampur Division I |  | 40.07 | 0 | 0 | 0 | 40.07 | 40.07 | 0 | 0 | 0 | 40.07 | 80.02 | 100
118 | MURSHIDABAD | SM/06979 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme | TSM/006032 | 8136588 | Retrofitting | MVS | GO2021002467PH | 09/11/2020 | 46.15 | 0 | 46.15 | Berhampur Division I |  | 37.69 | 0 | 0 | 0 | 37.69 | 36.83 | 0 | 0 | 0 | 36.83 | 79.81 | 6
119 | MURSHIDABAD | SM/06974 | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | TSM/006026 | 1723191 | Retrofitting | SVS | GO2021002462PH | 09/11/2020 | 91.48 | 0 | 91.48 | Berhampur Division I |  | 76.08 | 0 | 0 | 0 | 76.08 | 76.08 | 0 | 0 | 0 | 76.08 | 83.17 | 100
120 | MURSHIDABAD | SM/08918 | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLDTAP CONNECTION (FHTC) IN CONNECTION WITH JALJEEVAN MISSION AND JAL SWAPNA AT KASIMBAZAR CT(CODE-315444) UNDER COMMAND AREA OF (ZONE-A) OFSURFACE WATER BASED WATER SUPPLY SCHEME IN THEARSENIC AFFECTED AREAS OF | TSM/007705 | 40004303 | Retrofitting | SVS | GO2122003903PH | 29/09/2021 | 229.8 | 0 | 229.8 | Berhampur Division I |  | 136.63 | 0 | 0 | 0 | 136.63 | 136.63 | 0 | 0 | 0 | 136.63 | 59.46 | 75
121 | MURSHIDABAD | SM/07506 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | TSM/006540 | 1756852 | Retrofitting | MVS | GO2021003727PH | 29/12/2020 | 83.51 | 0 | 83.51 | Murshidabad Division |  | 70.8 | 0 | 0 | 0 | 70.8 | 70.8 | 0 | 0 | 0 | 70.8 | 84.79 | 80
122 | MURSHIDABAD | SM/07511 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) | TSM/006555 | 40001730 | Retrofitting | SVS | GO2021003733PH | 29/12/2020 | 62.34 | 0 | 62.34 | Murshidabad Division |  | 49.17 | 0 | 0 | 0 | 49.17 | 49.17 | 0 | 0 | 0 | 49.17 | 78.87 | 85
123 | MURSHIDABAD | SM/07516 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bilaspur (314681) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) | TSM/006561 | 8136472 | Retrofitting | SVS | GO2021003739PH | 29/12/2020 | 79.12 | 0 | 79.12 | Murshidabad Division |  | 3.46 | 0 | 0 | 0 | 3.46 | 3.46 | 0 | 0 | 0 | 3.46 | 4.37 | 69
124 | MURSHIDABAD | SM/07508 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR | TSM/006543 | 8354195 | Retrofitting | SVS | GO2021003729PH | 29/12/2020 | 58.94 | 0 | 58.94 | Murshidabad Division |  | 42.39 | 0 | 0 | 0 | 42.39 | 42.39 | 0 | 0 | 0 | 42.39 | 71.92 | 38
125 | MURSHIDABAD | SM/08198 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | TSM/006546 | 40001351 | Retrofitting | MVS | GO2021006389PH | 05/02/2021 | 348.01 | 0 | 348.01 | Murshidabad Division |  | 170.91 | 0 | 0 | 0 | 170.91 | 170.91 | 0 | 0 | 0 | 170.91 | 49.11 | 85
126 | MURSHIDABAD | SM/07512 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) | TSM/006557 | 8231199 | Retrofitting | SVS | GO2021003732PH | 29/12/2020 | 66.82 | 0 | 66.82 | Murshidabad Division |  | 43.57 | 0 | 0 | 0 | 43.57 | 43.57 | 0 | 0 | 0 | 43.57 | 65.21 | 39
127 | MURSHIDABAD | SM/07509 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hamidhati Pilkhandi & Purbbagram (315713 & 315718 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murs | TSM/006547 | 40001728 | Retrofitting | MVS | GO2021003730PH | 29/12/2020 | 97.74 | 0 | 97.74 | Murshidabad Division |  | 2.9 | 0 | 0 | 0 | 2.9 | 2.9 | 0 | 0 | 0 | 2.9 | 2.97 | 90
128 | MURSHIDABAD | SM/08199 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | TSM/006550 | 40002987 | Retrofitting | MVS | GO2021006388PH | 05/02/2021 | 386.05 | 0 | 386.05 | Murshidabad Division |  | 70.93 | 0 | 0 | 0 | 70.93 | 70.93 | 0 | 0 | 0 | 70.93 | 18.37
129 | MURSHIDABAD | SM/07507 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | TSM/006542 | 1756852 | Retrofitting | SVS | GO2021003728PH | 29/12/2020 | 63.33 | 0 | 63.33 | Murshidabad Division |  | 50.06 | 0 | 2.2 | 0 | 52.26 | 50.06 | 0 | 2.2 | 0 | 52.26 | 82.53 | 80
130 | MURSHIDABAD | SM/07514 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahisha Thali ( 313851 ) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-III | TSM/006559 | 40001411 | Retrofitting | SVS | GO2021003735PH | 29/12/2020 | 45.43 | 0 | 45.43 | Murshidabad Division |  | 25 | 0 | 0 | 0 | 25 | 24.36 | 0 | 0 | 0 | 24.36 | 53.61 | 35
131 | MURSHIDABAD | SM/07510 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | TSM/006552 | 8152697 | Retrofitting | MVS | GO2021003731PH | 29/12/2020 | 97.32 | 0 | 97.32 | Murshidabad Division |  | 77.44 | 0 | 0 | 0 | 77.44 | 77.44 | 0 | 0 | 0 | 77.44 | 79.57 | 80
132 | MURSHIDABAD | SM/07517 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sekhalipara (314580) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | TSM/006563 | 40014552 | Retrofitting | SVS | GO2021003736PH | 29/12/2020 | 77.39 | 0 | 77.39 | Murshidabad Division |  | 50.08 | 0 | 0 | 0 | 50.08 | 50.08 | 0 | 0 | 0 | 50.08 | 64.71 | 65
133 | MURSHIDABAD | SM/07513 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | TSM/006558 | 8131982 | Retrofitting | MVS | GO2021003734PH | 29/12/2020 | 61.91 | 0 | 61.91 | Murshidabad Division |  | 61.91 | 0 | 0 | 0 | 61.91 | 61.91 | 0 | 0 | 0 | 61.91 | 100 | 25
134 | MURSHIDABAD | SM/09835 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan (315979) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Buwan Block of Murshidabad District under Murshidabad Divisi | TSM/007492 | 8332370 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 13.03 | 0 | 13.03 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
135 | MURSHIDABAD | SM/09738 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Alampur ( 313932 ) of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District u | TSM/007516 | 40015580 | Retrofitting | SVS | GO2122006167PH | 29/11/2021 | 54.13 | 0 | 54.13 | Murshidabad Division |  | 32.33 | 0 | 3.95 | 0 | 36.29 | 32.33 | 0 | 3.95 | 0 | 36.29 | 67.03 | 5
136 | MURSHIDABAD | SM/07916 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagdanga ( 314725 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV | TSM/006577 | 8204905 | Retrofitting | SVS | GO2021004772PH | 19/01/2021 | 61.03 | 0 | 61.03 | Murshidabad Division |  | 20.67 | 0 | 0 | 0 | 20.67 | 20.67 | 0 | 0 | 0 | 20.67 | 33.86 | 38
137 | MURSHIDABAD | SM/07923 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- | TSM/006584 | 8195706 | Retrofitting | SVS | GO2021004766PH | 19/01/2021 | 152.87 | 0 | 152.87 | Murshidabad Division |  | 69.65 | 0 | 0 | 0 | 69.65 | 69.65 | 0 | 0 | 0 | 69.65 | 45.56
138 | MURSHIDABAD | SM/09746 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II | TSM/007507 | 40018876 | Retrofitting | MVS | GO2122006168PH | 29/11/2021 | 328.18 | 0 | 328.18 | Murshidabad Division |  | 7.88 | 0 | 30.5 | 0 | 38.39 | 7.88 | 0 | 30.5 | 0 | 38.39 | 11.7 | 27
139 | MURSHIDABAD | SM/08202 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B | TSM/006564 | 8202031 | Retrofitting | MVS | GO2021006391PH | 05/02/2021 | 873.95 | 0 | 873.95 | Murshidabad Division |  | 381.7 | 0 | 0 | 0 | 381.7 | 381.7 | 0 | 0 | 0 | 381.7 | 43.68 | 57
140 | MURSHIDABAD | SM/09836 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | TSM/007493 | 40002925 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 32.06 | 0 | 32.06 | Murshidabad Division |  | 31.13 | 0 | 0 | 0 | 31.13 | 31.13 | 0 | 0 | 0 | 31.13 | 97.09
141 | MURSHIDABAD | SM/09842 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Batkamari ( 314689 ) of Jorgachha under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad | TSM/007500 | 40001406 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 34.36 | 0 | 34.36 | Murshidabad Division |  | 22.28 | 0 | 0 | 0 | 22.28 | 22.28 | 0 | 0 | 0 | 22.28 | 64.84 | 47
142 | MURSHIDABAD | SM/08099 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | TSM/006572 | 8334414 | Retrofitting | MVS | GO2021006570PH | 08/02/2021 | 366.99 | 0 | 366.99 | Murshidabad Division |  | 160.31 | 0 | 0 | 0 | 160.31 | 160.31 | 0 | 0 | 0 | 160.31 | 43.68 | 25
143 | MURSHIDABAD | SM/09747 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brahmanigram ( 314319 ) and Bergram ( 314328 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of | TSM/007511 | 40019392 | Retrofitting | MVS | GO2122006168PH | 29/11/2021 | 94.96 | 0 | 94.96 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | MURSHIDABAD | SM/07921 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur (314567) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART- | TSM/006582 | 8218898 | Retrofitting | SVS | GO2021004778PH | 19/01/2021 | 91.1 | 0 | 91.1 | Murshidabad Division |  | 63.01 | 0 | 0 | 0 | 63.01 | 63.01 | 0 | 0 | 0 | 63.01 | 69.16 | 45
145 | MURSHIDABAD | SM/07914 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur Chak ( 314703 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District | TSM/006576 | 8195709 | Retrofitting | SVS | GO2021004781PH | 19/01/2021 | 63.09 | 0 | 63.09 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
146 | MURSHIDABAD | SM/09837 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di | TSM/007494 | 8363710 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 34.02 | 0 | 34.02 | Murshidabad Division |  | 32.91 | 0 | 0 | 0 | 32.91 | 32.91 | 0 | 0 | 0 | 32.91 | 96.75 | 80
147 | MURSHIDABAD | SM/09848 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Jitpur ( 314713 ) of Garibpur (Zone- I & Zone - II) under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad D | TSM/007506 | 8214936 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 34.24 | 0 | 34.24 | Murshidabad Division |  | 20.78 | 0 | 0 | 0 | 20.78 | 20.73 | 0 | 0 | 0 | 20.73 | 60.54 | 25
148 | MURSHIDABAD | SM/07917 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | TSM/006578 | 8230996 | Retrofitting | MVS | GO2021004773PH | 19/01/2021 | 97.32 | 0 | 97.32 | Murshidabad Division |  | 69.64 | 0 | 0 | 0 | 69.64 | 69.64 | 0 | 0 | 0 | 69.64 | 71.56 | 50
149 | MURSHIDABAD | SM/08196 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | TSM/006709 | 8317145 | Retrofitting | MVS | GO2021006384PH | 05/02/2021 | 532.59 | 0 | 532.59 | Murshidabad Division |  | 214.87 | 0 | 10.18 | 0 | 225.05 | 214.87 | 0 | 10.18 | 0 | 225.05 | 42.26 | 50
150 | MURSHIDABAD | SM/09843 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debottar Lakshminarayanpur ( 314678 ) of Jitpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District und | TSM/007501 | 40019415 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 44.72 | 0 | 44.72 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | MURSHIDABAD | SM/09840 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D | TSM/007498 | 8366664 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 29.12 | 0 | 29.12 | Murshidabad Division |  | 28.27 | 0 | 0 | 0 | 28.27 | 28.27 | 0 | 0 | 0 | 28.27 | 97.09 | 25
152 | MURSHIDABAD | SM/09752 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 313951 ) and Kadamtala ( 313953 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Bl | TSM/007518 | 1723341 | Retrofitting | MVS | GO2122006210PH | 30/11/2021 | 46.25 | 0 | 46.25 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
153 | MURSHIDABAD | SM/07919 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di | TSM/006580 | 8357132 | Retrofitting | MVS | GO2021004775PH | 19/01/2021 | 235.36 | 0 | 235.36 | Murshidabad Division |  | 168.9 | 0 | 0 | 0 | 168.9 | 168.9 | 0 | 0 | 0 | 168.9 | 71.76 | 55
154 | MURSHIDABAD | SM/07926 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | TSM/006585 | 8180936 | Retrofitting | SVS | GO2021004770PH | 19/01/2021 | 38.41 | 0 | 38.41 | Murshidabad Division |  | 37.29 | 0 | 0 | 0 | 37.29 | 37.29 | 0 | 0 | 0 | 37.29 | 97.09
155 | MURSHIDABAD | SM/08201 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Garaimari ( 314734 ) of Garaimari under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | TSM/006562 | 8346957 | Retrofitting | SVS | GO2021006392PH | 05/02/2021 | 548.73 | 0 | 548.73 | Murshidabad Division |  | 216.06 | 0 | 0 | 0 | 216.06 | 216.06 | 0 | 0 | 0 | 216.06 | 39.37 | 80
156 | MURSHIDABAD | SM/08100 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida | TSM/006574 | 40019343 | Retrofitting | MVS | GO2021006571PH | 08/02/2021 | 420.14 | 0 | 420.14 | Murshidabad Division |  | 65.42 | 0 | 0 | 0 | 65.42 | 65.42 | 0 | 0 | 0 | 65.42 | 15.57 | 5
157 | MURSHIDABAD | SM/07908 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) | TSM/006567 | 8231008 | Retrofitting | SVS | GO2021004796PH | 19/01/2021 | 63.81 | 0 | 63.81 | Murshidabad Division |  | 42.78 | 0 | 0 | 0 | 42.78 | 42.78 | 0 | 0 | 0 | 42.78 | 67.04 | 80
158 | MURSHIDABAD | SM/07771 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) | TSM/006549 | 40015189 | Retrofitting | SVS | GO2021004210PH | 07/01/2021 | 113.58 | 0 | 113.58 | Murshidabad Division |  | 75.21 | 0 | 0 | 0 | 75.21 | 70.42 | 0 | 0 | 0 | 70.42 | 62 | 58
159 | MURSHIDABAD | SM/07773 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs | TSM/006553 | 8259163 | Retrofitting | MVS | GO2021004207PH | 07/01/2021 | 139.17 | 0 | 139.17 | Murshidabad Division |  | 77.48 | 0 | 0 | 0 | 77.48 | 77.48 | 0 | 0 | 0 | 77.48 | 55.67 | 40
160 | MURSHIDABAD | SM/07769 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | TSM/006545 | 40008223 | Retrofitting | SVS | GO2021004212PH | 07/01/2021 | 173.5 | 0 | 173.5 | Murshidabad Division |  | 165.21 | 0 | 0 | 0 | 165.21 | 165.21 | 0 | 0 | 0 | 165.21 | 95.22 | 95
161 | MURSHIDABAD | SM/09751 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc | TSM/007517 | 40019398 | Retrofitting | MVS | GO2122006210PH | 30/11/2021 | 71.75 | 0 | 71.75 | Murshidabad Division |  | 54.26 | 0 | 0 | 0 | 54.26 | 54.26 | 0 | 0 | 0 | 54.26 | 75.62 | 18
162 | MURSHIDABAD | SM/07909 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | TSM/006568 | 40019334 | Retrofitting | SVS | GO2021004795PH | 19/01/2021 | 114.54 | 0 | 114.54 | Murshidabad Division |  | 43.3 | 0 | 0 | 0 | 43.3 | 43.3 | 0 | 0 | 0 | 43.3 | 37.8 | 40
163 | MURSHIDABAD | SM/07767 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | TSM/006538 | 40008197 | Retrofitting | SVS | GO2021004205PH | 07/01/2021 | 285.68 | 0 | 285.68 | Murshidabad Division |  | 44.81 | 0 | 15.31 | 0 | 60.12 | 44.81 | 0 | 15.31 | 0 | 60.12 | 21.04 | 50
164 | MURSHIDABAD | SM/09841 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | TSM/007499 | 1723365 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 36.56 | 0 | 36.56 | Murshidabad Division |  | 23.83 | 0 | 0 | 0 | 23.83 | 23.83 | 0 | 0 | 0 | 23.83 | 65.19 | 65
165 | MURSHIDABAD | SM/08195 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | TSM/006539 | 40004404 | Retrofitting | SVS | GO2021006386PH | 05/02/2021 | 480.62 | 0 | 480.62 | Murshidabad Division |  | 129.34 | 0 | 12.11 | 0 | 141.45 | 129.34 | 0 | 12.11 | 0 | 141.45 | 29.43 | 58
166 | MURSHIDABAD | SM/07907 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- | TSM/006566 | 8380507 | Retrofitting | SVS | GO2021004798PH | 19/01/2021 | 263.57 | 0 | 263.57 | Murshidabad Division |  | 198.62 | 0 | 0 | 0 | 198.62 | 198.62 | 0 | 0 | 0 | 198.62 | 75.36 | 77
167 | MURSHIDABAD | SM/09849 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Keyadanga ( 313966 ) of Keyadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District under Murshida | TSM/007509 | 40014233 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 44.53 | 0 | 44.53 | Murshidabad Division |  | 21.64 | 0 | 3.12 | 0 | 24.76 | 21.64 | 0 | 3.12 | 0 | 24.76 | 55.61 | 5
168 | MURSHIDABAD | SM/08200 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | TSM/006556 | 8355401 | Retrofitting | SVS | GO2021006390PH | 05/02/2021 | 380.89 | 0 | 380.89 | Murshidabad Division |  | 141.86 | 0 | 0 | 0 | 141.86 | 141.86 | 0 | 0 | 0 | 141.86 | 37.25 | 62
169 | MURSHIDABAD | SM/08197 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | TSM/006541 | 1756852 | Retrofitting | MVS | GO2021006380PH | 05/02/2021 | 521.6 | 0 | 521.6 | Murshidabad Division |  | 352.67 | 0 | 0 | 0 | 352.67 | 352.67 | 0 | 0 | 0 | 352.67 | 67.61 | 80
170 | MURSHIDABAD | SM/07911 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | TSM/006570 | 40018875 | Retrofitting | SVS | GO2021004790PH | 19/01/2021 | 167.77 | 0 | 167.77 | Murshidabad Division |  | 0 | 0 | 11.77 | 0 | 11.77 | 0 | 0 | 11.77 | 0 | 11.77 | 7.02 | 10
171 | MURSHIDABAD | SM/07912 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kusbaria (314722) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) | TSM/006571 | 40002856 | Retrofitting | SVS | GO2021004785PH | 19/01/2021 | 105.04 | 0 | 105.04 | Murshidabad Division |  | 68.95 | 0 | 0 | 0 | 68.95 | 68.95 | 0 | 0 | 0 | 68.95 | 65.64 | 40
172 | MURSHIDABAD | SM/07922 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) | TSM/006583 | 8341684 | Retrofitting | SVS | GO2021004764PH | 19/01/2021 | 105.77 | 0 | 105.77 | Murshidabad Division |  | 100.15 | 0 | 2.54 | 0 | 102.69 | 100.15 | 0 | 2.54 | 0 | 102.69 | 97.09 | 25
173 | MURSHIDABAD | SM/09753 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | TSM/007519 | 1723341 | Retrofitting | MVS | GO2122006210PH | 30/11/2021 | 389.19 | 0 | 389.19 | Murshidabad Division |  | 214.88 | 0 | 0 | 0 | 214.88 | 206.01 | 0 | 0 | 0 | 206.01 | 52.93 | 100
174 | MURSHIDABAD | SM/09737 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan | TSM/007515 | 40001752 | Retrofitting | MVS | GO2122006167PH | 29/11/2021 | 875.99 | 0 | 875.99 | Murshidabad Division |  | 108.22 | 0 | 67.97 | 0 | 176.19 | 108.22 | 0 | 67.97 | 0 | 176.19 | 20.11 | 5
175 | MURSHIDABAD | SM/07927 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malibbari ( 314569 ) of Malibari under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-I ) | TSM/006586 | 40008590 | Retrofitting | SVS | GO2021004780PH | 19/01/2021 | 48 | 0 | 48 | Murshidabad Division |  | 28.85 | 0 | 2.56 | 0 | 31.41 | 28.85 | 0 | 2.56 | 0 | 31.41 | 65.43 | 5
176 | MURSHIDABAD | SM/07918 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | TSM/006579 | 8365160 | Retrofitting | MVS | GO2021004774PH | 19/01/2021 | 79.52 | 0 | 79.52 | Murshidabad Division |  | 47.22 | 0 | 0 | 0 | 47.22 | 47.22 | 0 | 0 | 0 | 47.22 | 59.39 | 25
177 | MURSHIDABAD | SM/09839 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Maradighi ( 315674 ) of Rejinagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh | TSM/007497 | 1723375 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 17.46 | 0 | 17.46 | Murshidabad Division |  | 16.95 | 0 | 0 | 0 | 16.95 | 14.47 | 0 | 0 | 0 | 14.47 | 82.9 | 95
178 | MURSHIDABAD | SM/07920 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II | TSM/006581 | 8217930 | Retrofitting | SVS | GO2021004777PH | 19/01/2021 | 95.93 | 0 | 95.93 | Murshidabad Division |  | 34.42 | 0 | 0 | 0 | 34.42 | 34.42 | 0 | 0 | 0 | 34.42 | 35.88 | 38
179 | MURSHIDABAD | SM/07515 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of | TSM/006560 | 8131950 | Retrofitting | MVS | GO2021003738PH | 29/12/2020 | 89.95 | 0 | 89.95 | Murshidabad Division |  | 25.19 | 0 | 0 | 0 | 25.19 | 25.19 | 0 | 0 | 0 | 25.19 | 28 | 54
180 | MURSHIDABAD | SM/07774 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi | TSM/006554 | 8206521 | Retrofitting | SVS | GO2021004208PH | 07/01/2021 | 205.5 | 0 | 205.5 | Murshidabad Division |  | 124.88 | 0 | 0 | 0 | 124.88 | 124.88 | 0 | 0 | 0 | 124.88 | 60.77 | 29
181 | MURSHIDABAD | SM/09847 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pairmari ( 314672 ) of Dhulauri under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Di | TSM/007505 | 8206407 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 67.61 | 0 | 67.61 | Murshidabad Division |  | 13.15 | 0 | 0 | 0 | 13.15 | 13.15 | 0 | 0 | 0 | 13.15 | 19.45 | 25
182 | MURSHIDABAD | SM/07770 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) | TSM/006548 | 8162625 | Retrofitting | SVS | GO2021004211PH | 07/01/2021 | 162.06 | 0 | 162.06 | Murshidabad Division |  | 156.7 | 0 | 0 | 0 | 156.7 | 136.17 | 0 | 0 | 0 | 136.17 | 84.02 | 80
183 | MURSHIDABAD | SM/09845 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Paraspur ( 314616 ) of Muradpur-Jalangi (Zone-I, Zone - II & Zone - III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block o | TSM/007503 | 8206453 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 16.64 | 0 | 16.64 | Murshidabad Division |  | 8.24 | 0 | 0 | 0 | 8.24 | 8.24 | 0 | 0 | 0 | 8.24 | 49.52 | 25
184 | MURSHIDABAD | SM/07924 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M | TSM/006711 | 7941263 | Retrofitting | MVS | GO2021004767PH | 19/01/2021 | 66.03 | 0 | 66.03 | Murshidabad Division |  | 40.14 | 0 | 0 | 0 | 40.14 | 38.17 | 0 | 0 | 0 | 38.17 | 57.81 | 30
185 | MURSHIDABAD | SM/07925 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | TSM/006710 | 7941263 | Retrofitting | MVS | GO2021004768PH | 19/01/2021 | 69.2 | 0 | 69.2 | Murshidabad Division |  | 47.28 | 0 | 0 | 0 | 47.28 | 25.5 | 0 | 0 | 0 | 25.5 | 36.85 | 30
186 | MURSHIDABAD | SM/07913 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | TSM/006573 | 8160140 | Retrofitting | SVS | GO2021004784PH | 19/01/2021 | 96.61 | 0 | 96.61 | Murshidabad Division |  | 18.1 | 0 | 0 | 0 | 18.1 | 18.1 | 0 | 0 | 0 | 18.1 | 18.74 | 50
187 | MURSHIDABAD | SM/09748 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M | TSM/007512 | 40019394 | Retrofitting | SVS | GO2122006168PH | 29/11/2021 | 157.21 | 0 | 157.21 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
188 | MURSHIDABAD | SM/09851 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pradipdanga ( 315470 ) of Kismat Imadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Hariharpara Block of Murshidabad District under | TSM/007495 | 40008333 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 28.53 | 0 | 28.53 | Murshidabad Division |  | 27.7 | 0 | 0 | 0 | 27.7 | 9 | 0 | 0 | 0 | 9 | 31.56 | 5
189 | MURSHIDABAD | SM/07772 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | TSM/006551 | 8354197 | Retrofitting | MVS | GO2021004209PH | 07/01/2021 | 295.16 | 0 | 295.16 | Murshidabad Division |  | 194.13 | 0 | 0 | 0 | 194.13 | 194.13 | 0 | 0 | 0 | 194.13 | 65.77 | 60
190 | MURSHIDABAD | SM/07915 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II | TSM/006575 | 8201496 | Retrofitting | SVS | GO2021004782PH | 19/01/2021 | 98.09 | 0 | 98.09 | Murshidabad Division |  | 65.22 | 0 | 0 | 0 | 65.22 | 65.22 | 0 | 0 | 0 | 65.22 | 66.49 | 39
191 | MURSHIDABAD | SM/07768 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | TSM/006544 | 40002734 | Retrofitting | SVS | GO2021004206PH | 07/01/2021 | 281.95 | 0 | 281.95 | Murshidabad Division |  | 140.94 | 0 | 0 | 0 | 140.94 | 140.94 | 0 | 0 | 0 | 140.94 | 49.99 | 55
192 | MURSHIDABAD | SM/09850 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Santoshpur (314329) &Chandanbati ( 314330 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of M | TSM/007510 | 40019416 | Retrofitting | MVS | GO2122006343PH | 02/12/2021 | 91.63 | 0 | 91.63 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | MURSHIDABAD | SM/07906 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sibnagar Laskarpur (314702) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (P | TSM/006565 | 40016815 | Retrofitting | SVS | GO2021004799PH | 19/01/2021 | 291.34 | 0 | 291.34 | Murshidabad Division |  | 149.55 | 0 | 0 | 0 | 149.55 | 149.55 | 0 | 0 | 0 | 149.55 | 51.33 | 10
194 | MURSHIDABAD | SM/07910 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | TSM/006569 | 40008236 | Retrofitting | SVS | GO2021004792PH | 19/01/2021 | 38.44 | 0 | 38.44 | Murshidabad Division |  | 20.34 | 0 | 2.7 | 0 | 23.04 | 19.96 | 0 | 2.7 | 0 | 22.66 | 58.94 | 5
195 | MURSHIDABAD | SM/09844 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh | TSM/007502 | 8365869 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 9.41 | 0 | 9.41 | Murshidabad Division |  | 3.97 | 0 | 0 | 0 | 3.97 | 3.97 | 0 | 0 | 0 | 3.97 | 42.18 | 25
196 | MURSHIDABAD | SM/09846 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Srikrishnapur ( 314737 ) of Aminabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshid | TSM/007504 | 40014973 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 67.42 | 0 | 67.42 | Murshidabad Division |  | 38.99 | 0 | 0 | 0 | 38.99 | 38.99 | 0 | 0 | 0 | 38.99 | 57.83 | 50
197 | MURSHIDABAD | SM/09838 | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh | TSM/007496 | 1723426 | Retrofitting | SVS | GO2122006343PH | 02/12/2021 | 25.62 | 0 | 25.62 | Murshidabad Division |  | 30.15 | 0 | 0 | 0 | 30.15 | 14.91 | 0 | 0 | 0 | 14.91 | 58.19 | 100
198 | MURSHIDABAD | SM/07675 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ahiron (313929) of Ahiron under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - I Block of Murshidabad District (PART-I) | TSM/006060 | 40008206 | Retrofitting | SVS | GO2021004352PH | 08/01/2021 | 173.36 | 0 | 173.36 | Murshidabad Division |  | 87.54 | 0 | 0 | 0 | 87.54 | 87.54 | 0 | 0 | 0 | 87.54 | 50.5 | 25
199 | MURSHIDABAD | SM/07278 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | TSM/006099 | 8130018 | Retrofitting | MVS | GO2021003308PH | 10/12/2020 | 88.35 | 0 | 88.35 | Murshidabad Division |  | 70.12 | 0 | 0 | 0 | 70.12 | 70.12 | 0 | 0 | 0 | 70.12 | 79.36 | 53
200 | MURSHIDABAD | SM/09749 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amdahara Haziganja ( 314497) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis | TSM/007513 | 40012671 | Retrofitting | SVS | GO2122006168PH | 29/11/2021 | 81.3 | 0 | 81.3 | Murshidabad Division |  | 34.05 | 0 | 0 | 0 | 34.05 | 34.05 | 0 | 0 | 0 | 34.05 | 41.88 | 50
201 | MURSHIDABAD | SM/09765 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M | TSM/007532 | 40001538 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 79.54 | 0 | 79.54 | Murshidabad Division |  | 72.52 | 0 | 0 | 0 | 72.52 | 68.38 | 0 | 0 | 0 | 68.38 | 85.97 | 26
202 | MURSHIDABAD | SM/08275 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Aurangabad (313981) of Aurangabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District (PART-I) | TSM/006062 | 40005130 | Retrofitting | SVS | GO2021007305H | 19/02/2021 | 558.86 | 0 | 558.86 | Murshidabad Division |  | 137.5 | 0 | 42.35 | 0 | 179.85 | 137.5 | 0 | 42.35 | 0 | 179.85 | 32.18 | 10
203 | MURSHIDABAD | SM/08281 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | TSM/006080 | 8380385 | Retrofitting | MVS | GO2021007295PH | 19/02/2021 | 434.98 | 0 | 434.98 | Murshidabad Division |  | 142.07 | 0 | 0 | 0 | 142.07 | 142.07 | 0 | 0 | 0 | 142.07 | 32.66 | 40
204 | MURSHIDABAD | SM/07670 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) | TSM/006125 | 8130427 | Retrofitting | SVS | GO2021004313PH | 08/01/2021 | 155.88 | 0 | 155.88 | Murshidabad Division |  | 72.78 | 0 | 0 | 0 | 72.78 | 72.78 | 0 | 0 | 0 | 72.78 | 46.69 | 25
205 | MURSHIDABAD | SM/07674 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of | TSM/006055 | 8355164 | Retrofitting | MVS | GO2021004349PH | 08/01/2021 | 295.52 | 0 | 295.52 | Murshidabad Division |  | 210.09 | 0 | 0 | 0 | 210.09 | 210.09 | 0 | 0 | 0 | 210.09 | 71.09 | 92
206 | MURSHIDABAD | SM/07671 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagharpur Ramna (314665) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-V) | TSM/006128 | 8195706 | Retrofitting | SVS | GO2021004315PH | 08/01/2021 | 138.2 | 0 | 138.2 | Murshidabad Division |  | 10.04 | 0 | 0 | 0 | 10.04 | 10.04 | 0 | 0 | 0 | 10.04 | 7.27
207 | MURSHIDABAD | SM/07277 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs | TSM/006098 | 8129967 | Retrofitting | MVS | GO2021003307PH | 10/12/2020 | 51.55 | 0 | 51.55 | Murshidabad Division |  | 44.26 | 0 | 2.47 | 0 | 46.73 | 44.26 | 0 | 2.47 | 0 | 46.73 | 90.65 | 50
208 | MURSHIDABAD | SM/07679 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarambati, Manigram (314285, 314284) of Monigram Balarambati under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block of Mursh | TSM/006079 | 8350306 | Retrofitting | MVS | GO2021004341PH | 08/01/2021 | 122.92 | 0 | 122.92 | Murshidabad Division |  | 86.98 | 0 | 0 | 0 | 86.98 | 86.98 | 0 | 0 | 0 | 86.98 | 70.76 | 25
209 | MURSHIDABAD | SM/07281 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi | TSM/006102 | 8136452 | Retrofitting | MVS | GO2021003285PH | 10/12/2020 | 99.11 | 0 | 99.11 | Murshidabad Division |  | 32.91 | 0 | 0 | 0 | 32.91 | 32.91 | 0 | 0 | 0 | 32.91 | 33.21 | 2
210 | MURSHIDABAD | SM/07280 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of | TSM/006101 | 8136145 | Retrofitting | MVS | GO2021003284PH | 10/12/2020 | 97.62 | 0 | 97.62 | Murshidabad Division |  | 29.29 | 0 | 0 | 0 | 29.29 | 29.29 | 0 | 0 | 0 | 29.29 | 30 | 50
211 | MURSHIDABAD | SM/07276 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | TSM/006083 | 8136476 | Retrofitting | SVS | GO2021003305PH | 10/12/2020 | 95.4 | 0 | 95.4 | Murshidabad Division |  | 83.62 | 0 | 7.16 | 0 | 90.78 | 83.62 | 0 | 7.16 | 0 | 90.78 | 95.16 | 40
212 | MURSHIDABAD | SM/09759 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bamuha (313962) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad D | TSM/007525 | 40019404 | Retrofitting | SVS | GO2122006210PH | 30/11/2021 | 64.56 | 0 | 64.56 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
213 | MURSHIDABAD | SM/07662 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | TSM/006038 | 8195708 | Retrofitting | MVS | GO2021004329PH | 08/01/2021 | 170.09 | 0 | 170.09 | Murshidabad Division |  | 152.85 | 0 | 0 | 0 | 152.85 | 152.71 | 0 | 0 | 0 | 152.71 | 89.78 | 65
214 | MURSHIDABAD | SM/07686 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs | TSM/006110 | 8196757 | Retrofitting | SVS | GO2021004366PH | 08/01/2021 | 200.91 | 0 | 200.91 | Murshidabad Division |  | 86.29 | 0 | 0 | 0 | 86.29 | 86.29 | 0 | 0 | 0 | 86.29 | 42.95 | 25
215 | MURSHIDABAD | SM/08687 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | TSM/006041 | 40026637 | Retrofitting | MVS | GO2122007313PH | 13/07/2021 | 601.79 | 0 | 601.79 | Murshidabad Division |  | 232.02 | 0 | 18.8 | 0 | 250.82 | 232.02 | 0 | 18.8 | 0 | 250.82 | 41.68 | 82
216 | MURSHIDABAD | SM/08185 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | TSM/006046 | 8131446 | Retrofitting | MVS | GO2021007216PH | 18/02/2021 | 329.04 | 0 | 329.04 | Murshidabad Division |  | 96.26 | 0 | 0 | 0 | 96.26 | 96.26 | 0 | 0 | 0 | 96.26 | 29.25 | 85
217 | MURSHIDABAD | SM/07665 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | TSM/006084 | 40018543 | Retrofitting | SVS | GO2021004321PH | 08/01/2021 | 197.42 | 0 | 197.42 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
218 | MURSHIDABAD | SM/07681 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-II) | TSM/006085 | 40018543 | Retrofitting | MVS | GO2021004335PH | 08/01/2021 | 290.84 | 0 | 290.84 | Murshidabad Division |  | 63.06 | 0 | 0 | 0 | 63.06 | 63.06 | 0 | 0 | 0 | 63.06 | 21.68 | 60
219 | MURSHIDABAD | SM/07672 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | TSM/006137 | 40019316 | Retrofitting | SVS | GO2021004317PH | 08/01/2021 | 161.68 | 0 | 161.68 | Murshidabad Division |  | 81.63 | 0 | 0 | 0 | 81.63 | 81.63 | 0 | 0 | 0 | 81.63 | 50.49 | 85
220 | MURSHIDABAD | SM/08272 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | TSM/006048 | 8223167 | Retrofitting | SVS | GO2021007309PH | 19/02/2021 | 385.47 | 0 | 385.47 | Murshidabad Division |  | 133.19 | 0 | 0 | 0 | 133.19 | 133.19 | 0 | 0 | 0 | 133.19 | 34.55 | 55
221 | MURSHIDABAD | SM/09755 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhandata (314524) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad District under | TSM/007521 | 8329373 | Retrofitting | SVS | GO2122006210PH | 30/11/2021 | 81.3 | 0 | 81.3 | Murshidabad Division |  | 34.33 | 0 | 0 | 0 | 34.33 | 34.33 | 0 | 0 | 0 | 34.33 | 42.23 | 50
222 | MURSHIDABAD | SM/07274 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) | TSM/006050 | 8136472 | Retrofitting | SVS | GO2021003304PH | 10/12/2020 | 85.16 | 0 | 85.16 | Murshidabad Division |  | 82.42 | 0 | 0 | 0 | 82.42 | 82.42 | 0 | 0 | 0 | 82.42 | 96.79 | 69
223 | MURSHIDABAD | SM/07286 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Mu | TSM/006112 | 8136463 | Retrofitting | SVS | GO2021003290PH | 10/12/2020 | 98.3 | 0 | 98.3 | Murshidabad Division |  | 95.43 | 0 | 0 | 0 | 95.43 | 95.43 | 0 | 0 | 0 | 95.43 | 97.09 | 47
224 | MURSHIDABAD | SM/07283 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | TSM/006108 | 8136456 | Retrofitting | SVS | GO2021003287PH | 10/12/2020 | 52.54 | 0 | 52.54 | Murshidabad Division |  | 29.21 | 0 | 0 | 0 | 29.21 | 29.21 | 0 | 0 | 0 | 29.21 | 55.59 | 27
225 | MURSHIDABAD | SM/07664 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur | TSM/006043 | 8219465 | Retrofitting | MVS | GO2021004327PH | 08/01/2021 | 183.02 | 0 | 183.02 | Murshidabad Division |  | 42.3 | 0 | 0 | 0 | 42.3 | 42.3 | 0 | 0 | 0 | 42.3 | 23.11 | 85
226 | MURSHIDABAD | SM/09739 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | TSM/007536 | 8386102 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 96.99 | 0 | 96.99 | Murshidabad Division |  | 54.94 | 0 | 0 | 0 | 54.94 | 54.94 | 0 | 0 | 0 | 54.94 | 56.65 | 50
227 | MURSHIDABAD | SM/07279 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of | TSM/006100 | 8129999 | Retrofitting | MVS | GO2021003283PH | 10/12/2020 | 68.99 | 0 | 68.99 | Murshidabad Division |  | 43.27 | 0 | 0 | 0 | 43.27 | 43.27 | 0 | 0 | 0 | 43.27 | 62.72 | 50
228 | MURSHIDABAD | SM/07684 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur | TSM/006106 | 8130352 | Retrofitting | MVS | GO2021004362PH | 08/01/2021 | 112.77 | 0 | 112.77 | Murshidabad Division |  | 43.73 | 0 | 0 | 0 | 43.73 | 43.73 | 0 | 0 | 0 | 43.73 | 38.78 | 33
229 | MURSHIDABAD | SM/09764 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | TSM/007531 | 40002542 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 313.08 | 0 | 313.08 | Murshidabad Division |  | 23.48 | 0 | 0 | 0 | 23.48 | 23.48 | 0 | 0 | 0 | 23.48 | 7.5 | 70
230 | MURSHIDABAD | SM/07200 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | TSM/006072 | 8132988 | Retrofitting | SVS | GO2021003137PH | 08/12/2020 | 57.01 | 0 | 57.01 | Murshidabad Division |  | 57.01 | 0 | 0 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 57.01 | 100 | 25
231 | MURSHIDABAD | SM/07682 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram | TSM/006097 | 8130321 | Retrofitting | MVS | GO2021004357PH | 08/01/2021 | 131.02 | 0 | 131.02 | Murshidabad Division |  | 61.17 | 0 | 0 | 0 | 61.17 | 61.17 | 0 | 0 | 0 | 61.17 | 46.69 | 25
232 | MURSHIDABAD | SM/07673 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhulauri (314671) of Dhulauri under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | TSM/006053 | 8358373 | Retrofitting | SVS | GO2021004344PH | 08/01/2021 | 142.93 | 0 | 142.93 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
233 | MURSHIDABAD | SM/07282 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) | TSM/006104 | 8136435 | Retrofitting | SVS | GO2021003286PH | 10/12/2020 | 99.99 | 0 | 99.99 | Murshidabad Division |  | 75.8 | 0 | 0 | 0 | 75.8 | 75.8 | 0 | 0 | 0 | 75.8 | 75.8 | 75
234 | MURSHIDABAD | SM/07293 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part | TSM/006130 | 8130442 | Retrofitting | MVS | GO2021003297PH | 10/12/2020 | 99.3 | 0 | 99.3 | Murshidabad Division |  | 71.41 | 0 | 0 | 0 | 71.41 | 71.41 | 0 | 0 | 0 | 71.41 | 71.92 | 85
235 | MURSHIDABAD | SM/09763 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | TSM/007530 | 40005129 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 184.33 | 0 | 184.33 | Murshidabad Division |  | 113.27 | 0 | 0 | 0 | 113.27 | 113.27 | 0 | 0 | 0 | 113.27 | 61.45 | 26
236 | MURSHIDABAD | SM/09762 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba | TSM/007529 | 40013952 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 85.85 | 0 | 85.85 | Murshidabad Division |  | 73.53 | 0 | 9.82 | 0 | 83.35 | 73.53 | 0 | 9.82 | 0 | 83.35 | 97.09 | 98
237 | MURSHIDABAD | SM/08277 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl | TSM/006066 | 8389140 | Retrofitting | MVS | GO2021007302PH | 19/02/2021 | 418.69 | 0 | 418.69 | Murshidabad Division |  | 101.55 | 0 | 0 | 0 | 101.55 | 101.55 | 0 | 0 | 0 | 101.55 | 24.25 | 25
238 | MURSHIDABAD | SM/07273 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District | TSM/006040 | 8135800 | Retrofitting | SVS | GO2021003302PH | 10/12/2020 | 44.21 | 0 | 44.21 | Murshidabad Division |  | 42.42 | 0 | 0 | 0 | 42.42 | 42.42 | 0 | 0 | 0 | 42.42 | 95.97 | 87
239 | MURSHIDABAD | SM/08279 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas | TSM/006074 | 8317144 | Retrofitting | MVS | GO2021007298PH | 19/02/2021 | 340.16 | 0 | 340.16 | Murshidabad Division |  | 204.98 | 0 | 8.08 | 0 | 213.06 | 204.98 | 0 | 8.08 | 0 | 213.06 | 62.64 | 25
240 | MURSHIDABAD | SM/07669 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II | TSM/006118 | 8130412 | Retrofitting | SVS | GO2021004306PH | 08/01/2021 | 151.27 | 0 | 151.27 | Murshidabad Division |  | 103.01 | 0 | 0 | 0 | 103.01 | 103.01 | 0 | 0 | 0 | 103.01 | 68.1 | 85
241 | MURSHIDABAD | SM/07666 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | TSM/006087 | 8130172 | Retrofitting | MVS | GO2021004322PH | 08/01/2021 | 299.57 | 0 | 299.57 | Murshidabad Division |  | 41.47 | 0 | 0 | 0 | 41.47 | 41.47 | 0 | 0 | 0 | 41.47 | 13.84 | 85
242 | MURSHIDABAD | SM/07685 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harharia Chak (CT) (314806) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PA | TSM/006107 | 40005584 | Retrofitting | SVS | GO2021004365PH | 08/01/2021 | 146.33 | 0 | 146.33 | Murshidabad Division |  | 58.55 | 0 | 0 | 0 | 58.55 | 58.55 | 0 | 0 | 0 | 58.55 | 40.01 | 55
243 | MURSHIDABAD | SM/08276 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme | TSM/006064 | 8348838 | Retrofitting | MVS | GO2021007304PH | 19/02/2021 | 342.72 | 0 | 342.72 | Murshidabad Division |  | 184.18 | 0 | 0 | 0 | 184.18 | 184.18 | 0 | 0 | 0 | 184.18 | 53.74 | 25
244 | MURSHIDABAD | SM/08191 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | TSM/006093 | 8130196 | Retrofitting | MVS | GO2021007215PH | 18/02/2021 | 333.13 | 0 | 333.13 | Murshidabad Division |  | 86.87 | 0 | 1.34 | 0 | 88.2 | 86.87 | 0 | 1.34 | 0 | 88.2 | 26.48 | 95
245 | MURSHIDABAD | SM/07287 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B | TSM/006113 | 8131933 | Retrofitting | MVS | GO2021003291PH | 10/12/2020 | 72.14 | 0 | 72.14 | Murshidabad Division |  | 61.77 | 0 | 0 | 0 | 61.77 | 61.77 | 0 | 0 | 0 | 61.77 | 85.62 | 28
246 | MURSHIDABAD | SM/07683 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II | TSM/006103 | 40019318 | Retrofitting | SVS | GO2021004359PH | 08/01/2021 | 158.56 | 0 | 158.56 | Murshidabad Division |  | 31.16 | 0 | 0 | 0 | 31.16 | 31.16 | 0 | 0 | 0 | 31.16 | 19.65 | 35
247 | MURSHIDABAD | SM/07275 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par | TSM/006082 | 8136480 | Retrofitting | SVS | GO2021003306PH | 10/12/2020 | 21.9 | 0 | 21.9 | Murshidabad Division |  | 17.5 | 0 | 1.47 | 0 | 18.97 | 17.5 | 0 | 1.47 | 0 | 18.97 | 86.62 | 40
248 | MURSHIDABAD | SM/09761 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad | TSM/007528 | 40001757 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 43.78 | 0 | 43.78 | Murshidabad Division |  | 4.17 | 0 | 2.92 | 0 | 7.08 | 4.17 | 0 | 2.92 | 0 | 7.08 | 16.18 | 50
249 | MURSHIDABAD | SM/07296 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | TSM/006140 | 8136470 | Retrofitting | SVS | GO2021003301PH | 10/12/2020 | 90.93 | 0 | 90.93 | Murshidabad Division |  | 81.36 | 0 | 6.92 | 0 | 88.28 | 81.36 | 0 | 6.92 | 0 | 88.28 | 97.09 | 45
250 | MURSHIDABAD | SM/07677 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block | TSM/006076 | 1723426 | Retrofitting | MVS | GO2021004346PH | 08/01/2021 | 248.75 | 0 | 248.75 | Murshidabad Division |  | 137.1 | 0 | 0 | 0 | 137.1 | 137.1 | 0 | 0 | 0 | 137.1 | 55.12 | 100
251 | MURSHIDABAD | SM/09744 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | TSM/007542 | 40019388 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 186.4 | 0 | 186.4 | Murshidabad Division |  | 54.85 | 0 | 0 | 0 | 54.85 | 54.85 | 0 | 0 | 0 | 54.85 | 29.43 | 13
252 | MURSHIDABAD | SM/09743 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad | TSM/007541 | 8350310 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 251.5 | 0 | 251.5 | Murshidabad Division |  | 18.23 | 0 | 0 | 0 | 18.23 | 18.23 | 0 | 0 | 0 | 18.23 | 7.25 | 25
253 | MURSHIDABAD | SM/08278 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas | TSM/006068 | 8196405 | Retrofitting | MVS | GO2021007300PH | 19/02/2021 | 517.99 | 0 | 517.99 | Murshidabad Division |  | 261.23 | 0 | 15.08 | 0 | 276.31 | 261.23 | 0 | 15.08 | 0 | 276.31 | 53.34 | 91
254 | MURSHIDABAD | SM/07676 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of | TSM/006071 | 40004082 | Retrofitting | MVS | GO2021004354PH | 08/01/2021 | 150.4 | 0 | 150.4 | Murshidabad Division |  | 52.6 | 0 | 0 | 0 | 52.6 | 52.6 | 0 | 0 | 0 | 52.6 | 34.97 | 70
255 | MURSHIDABAD | SM/09742 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M | TSM/007540 | 40019381 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 191.97 | 0 | 191.97 | Murshidabad Division |  | 69.5 | 0 | 0 | 0 | 69.5 | 69.5 | 0 | 0 | 0 | 69.5 | 36.2 | 13
256 | MURSHIDABAD | SM/08192 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | TSM/006094 | 6154928 | Retrofitting | MVS | GO2021007209PH | 18/02/2021 | 349.63 | 0 | 349.63 | Murshidabad Division |  | 113.75 | 0 | 2.7 | 0 | 116.45 | 113.75 | 0 | 2.7 | 0 | 116.45 | 33.31 | 95
257 | MURSHIDABAD | SM/07668 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) | TSM/006095 | 8257092 | Retrofitting | SVS | GO2021004325PH | 08/01/2021 | 241.26 | 0 | 241.26 | Murshidabad Division |  | 128.06 | 0 | 0 | 0 | 128.06 | 128.06 | 0 | 0 | 0 | 128.06 | 53.08 | 85
258 | MURSHIDABAD | SM/09750 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B | TSM/007514 | 40002545 | Retrofitting | MVS | GO2122006168PH | 29/11/2021 | 265.85 | 0 | 265.85 | Murshidabad Division |  | 2.38 | 0 | 0 | 0 | 2.38 | 2.38 | 0 | 0 | 0 | 2.38 | 0.89
259 | MURSHIDABAD | SM/08188 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari (314589) of Katlamari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District (PART-I) | TSM/006089 | 40019357 | Retrofitting | SVS | GO2021007206PH | 18/02/2021 | 578.36 | 0 | 578.36 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
260 | MURSHIDABAD | SM/08190 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | TSM/006091 | 6086670 | Retrofitting | MVS | GO2021007208PH | 18/02/2021 | 1045.27 | 0 | 1045.27 | Murshidabad Division |  | 529.04 | 0 | 0 | 0 | 529.04 | 529.04 | 0 | 0 | 0 | 529.04 | 50.61 | 50
261 | MURSHIDABAD | SM/09757 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad | TSM/007523 | 40016534 | Retrofitting | SVS | GO2122006210PH | 30/11/2021 | 86.3 | 0 | 86.3 | Murshidabad Division |  | 9.99 | 0 | 0 | 0 | 9.99 | 9.99 | 0 | 0 | 0 | 9.99 | 11.58 | 65
262 | MURSHIDABAD | SM/09758 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba | TSM/007524 | 40019403 | Retrofitting | SVS | GO2122006210PH | 30/11/2021 | 76.56 | 0 | 76.56 | Murshidabad Division |  | 35.15 | 0 | 0 | 0 | 35.15 | 35.15 | 0 | 0 | 0 | 35.15 | 45.91 | 38
263 | MURSHIDABAD | SM/08282 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa | TSM/006105 | 8130511 | Retrofitting | MVS | GO2021007293PH | 19/02/2021 | 497.66 | 0 | 497.66 | Murshidabad Division |  | 174.52 | 0 | 6.96 | 0 | 181.47 | 174.52 | 0 | 6.96 | 0 | 181.47 | 36.46 | 10
264 | MURSHIDABAD | SM/09760 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis | TSM/007526 | 40009419 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 66.1 | 0 | 66.1 | Murshidabad Division |  | 38.52 | 0 | 0 | 0 | 38.52 | 38.52 | 0 | 0 | 0 | 38.52 | 58.28 | 60
265 | MURSHIDABAD | SM/09754 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kolan Radhakantapur (314523) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis | TSM/007520 | 40008832 | Retrofitting | SVS | GO2122006210PH | 30/11/2021 | 94.97 | 0 | 94.97 | Murshidabad Division |  | 31.97 | 0 | 0 | 0 | 31.97 | 31.97 | 0 | 0 | 0 | 31.97 | 33.66 | 87
266 | MURSHIDABAD | SM/08271 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh | TSM/006047 | 8202449 | Retrofitting | MVS | GO2021007310PH | 19/02/2021 | 423.18 | 0 | 423.18 | Murshidabad Division |  | 168.69 | 0 | 1.2 | 0 | 169.89 | 168.69 | 0 | 1.2 | 0 | 169.89 | 40.15 | 98
267 | MURSHIDABAD | SM/07667 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | TSM/006092 | 8130187 | Retrofitting | MVS | GO2021004320PH | 08/01/2021 | 241.98 | 0 | 241.98 | Murshidabad Division |  | 100.47 | 0 | 0 | 0 | 100.47 | 100.47 | 0 | 0 | 0 | 100.47 | 41.52 | 85
268 | MURSHIDABAD | SM/07290 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) | TSM/006120 | 8136466 | Retrofitting | SVS | GO2021003294PH | 10/12/2020 | 99.96 | 0 | 99.96 | Murshidabad Division |  | 94.43 | 0 | 0 | 0 | 94.43 | 94.43 | 0 | 0 | 0 | 94.43 | 94.46 | 40
269 | MURSHIDABAD | SM/09768 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | TSM/007535 | 40019405 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 60.39 | 0 | 60.39 | Murshidabad Division |  | 2.29 | 0 | 5.23 | 0 | 7.52 | 2.29 | 0 | 5.23 | 0 | 7.52 | 12.45 | 10
270 | MURSHIDABAD | SM/07292 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric | TSM/006126 | 8130136 | Retrofitting | MVS | GO2021003296PH | 10/12/2020 | 63.73 | 0 | 63.73 | Murshidabad Division |  | 61.87 | 0 | 0 | 0 | 61.87 | 61.87 | 0 | 0 | 0 | 61.87 | 97.09 | 80
271 | MURSHIDABAD | SM/07678 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | TSM/006077 | 8191028 | Retrofitting | SVS | GO2021004343PH | 08/01/2021 | 109.83 | 0 | 109.83 | Murshidabad Division |  | 69.5 | 0 | 0 | 0 | 69.5 | 69.5 | 0 | 0 | 0 | 69.5 | 63.28 | 13
272 | MURSHIDABAD | SM/07291 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) | TSM/006123 | 8136465 | Retrofitting | SVS | GO2021003295PH | 10/12/2020 | 51.34 | 0 | 51.34 | Murshidabad Division |  | 15.4 | 0 | 0 | 0 | 15.4 | 15.4 | 0 | 0 | 0 | 15.4 | 30 | 38
273 | MURSHIDABAD | SM/07294 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid | TSM/006132 | 8130135 | Retrofitting | MVS | GO2021003298PH | 10/12/2020 | 95.06 | 0 | 95.06 | Murshidabad Division |  | 48.5 | 0 | 0 | 0 | 48.5 | 48.5 | 0 | 0 | 0 | 48.5 | 51.02 | 55
274 | MURSHIDABAD | SM/07680 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | TSM/006081 | 40008221 | Retrofitting | SVS | GO2021004342PH | 08/01/2021 | 207.09 | 0 | 207.09 | Murshidabad Division |  | 35.65 | 0 | 15.81 | 0 | 51.46 | 35.34 | 0 | 15.81 | 0 | 51.15 | 24.7 | 68
275 | MURSHIDABAD | SM/08184 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A | TSM/006045 | 1723365 | Retrofitting | MVS | GO2021007204PH | 18/02/2021 | 376.23 | 0 | 376.23 | Murshidabad Division |  | 186.07 | 0 | 0 | 0 | 186.07 | 186.07 | 0 | 0 | 0 | 186.07 | 49.46 | 65
276 | MURSHIDABAD | SM/07285 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff | TSM/006111 | 8136458 | Retrofitting | MVS | GO2021003289PH | 10/12/2020 | 87.45 | 0 | 87.45 | Murshidabad Division |  | 78.32 | 0 | 0 | 0 | 78.32 | 78.32 | 0 | 0 | 0 | 78.32 | 89.55 | 47
277 | MURSHIDABAD | SM/07284 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid | TSM/006109 | 8136460 | Retrofitting | SVS | GO2021003288PH | 10/12/2020 | 74.76 | 0 | 74.76 | Murshidabad Division |  | 72.9 | 0 | 0 | 0 | 72.9 | 72.9 | 0 | 0 | 0 | 72.9 | 97.51 | 81
278 | MURSHIDABAD | SM/09740 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Pakamati Mahula ( 315353 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under | TSM/007537 | 40002904 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 9.7 | 0 | 9.7 | Murshidabad Division |  | 4.16 | 0 | 0 | 0 | 4.16 | 4.16 | 0 | 0 | 0 | 4.16 | 42.91
279 | MURSHIDABAD | SM/09756 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Palasi Sonadanga (314527) and Ramnapara (314496) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Bloc | TSM/007522 | 8230973 | Retrofitting | MVS | GO2122006210PH | 30/11/2021 | 87.01 | 0 | 87.01 | Murshidabad Division |  | 40.79 | 0 | 0 | 0 | 40.79 | 40.79 | 0 | 0 | 0 | 40.79 | 46.87 | 25
280 | MURSHIDABAD | SM/07288 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist | TSM/006115 | 8130398 | Retrofitting | MVS | GO2021003292PH | 10/12/2020 | 99.99 | 0 | 99.99 | Murshidabad Division |  | 47.04 | 0 | 0 | 0 | 47.04 | 47.04 | 0 | 0 | 0 | 47.04 | 47.04 | 80
281 | MURSHIDABAD | SM/08183 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba | TSM/006044 | 1723375 | Retrofitting | MVS | GO2021007203PH | 18/02/2021 | 389.91 | 0 | 389.91 | Murshidabad Division |  | 281.76 | 0 | 1.14 | 0 | 282.9 | 281.76 | 0 | 1.14 | 0 | 282.9 | 72.56 | 95
282 | MURSHIDABAD | SM/07663 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | TSM/006039 | 8198088 | Retrofitting | MVS | GO2021004328PH | 08/01/2021 | 121.53 | 0 | 121.53 | Murshidabad Division |  | 30.7 | 0 | 4.6 | 0 | 35.3 | 30.7 | 0 | 4.6 | 0 | 35.3 | 29.05 | 80
283 | MURSHIDABAD | SM/09745 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ratanpur ( 313841 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Mursh | TSM/007543 | 40018891 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 210.01 | 0 | 210.01 | Murshidabad Division |  | 13.05 | 0 | 0 | 0 | 13.05 | 13.05 | 0 | 0 | 0 | 13.05 | 6.22 | 1
284 | MURSHIDABAD | SM/10036 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | TSM/007538 | 40013828 | Retrofitting | MVS | GO2122008399PH | 19/01/2022 | 1037.9 | 0 | 1037.9 | Murshidabad Division |  | 49.6 | 0 | 55.44 | 0 | 105.04 | 49.6 | 0 | 55.44 | 0 | 105.04 | 10.12 | 50
285 | MURSHIDABAD | SM/07295 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad | TSM/006135 | 8136469 | Retrofitting | MVS | GO2021003300PH | 10/12/2020 | 93.16 | 0 | 93.16 | Murshidabad Division |  | 50.22 | 0 | 0 | 0 | 50.22 | 50.22 | 0 | 0 | 0 | 50.22 | 53.91 | 39
286 | MURSHIDABAD | SM/08193 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | TSM/006096 | 8130312 | Retrofitting | MVS | GO2021007211PH | 18/02/2021 | 494.79 | 0 | 494.79 | Murshidabad Division |  | 147.69 | 0 | 5.12 | 0 | 152.81 | 147.69 | 0 | 5.12 | 0 | 152.81 | 30.88 | 99
287 | MURSHIDABAD | SM/08688 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc | TSM/006042 | 8180946 | Retrofitting | MVS | GO2122000639PH | 13/07/2021 | 461.79 | 0 | 461.79 | Murshidabad Division |  | 171.79 | 0 | 10.31 | 0 | 182.1 | 171.79 | 0 | 10.31 | 0 | 182.1 | 39.43 | 25
288 | MURSHIDABAD | SM/08280 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | TSM/006078 | 40001733 | Retrofitting | SVS | GO2021007296PH | 19/02/2021 | 305.04 | 0 | 305.04 | Murshidabad Division |  | 109.29 | 0 | 21.96 | 0 | 131.25 | 109.29 | 0 | 21.96 | 0 | 131.25 | 43.03 | 83
289 | MURSHIDABAD | SM/09767 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | TSM/007534 | 40013973 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 107.76 | 0 | 107.76 | Murshidabad Division |  | 89.17 | 0 | 7.3 | 0 | 96.47 | 89.17 | 0 | 7.3 | 0 | 96.47 | 89.52 | 29
290 | MURSHIDABAD | SM/07289 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do | TSM/006117 | 8130137 | Retrofitting | MVS | GO2021003293PH | 10/12/2020 | 78.74 | 0 | 78.74 | Murshidabad Division |  | 27.96 | 0 | 0 | 0 | 27.96 | 27.96 | 0 | 0 | 0 | 27.96 | 35.5 | 28
291 | MURSHIDABAD | SM/09766 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sungai ( 315363 ) of Sungai under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad D | TSM/007533 | 40008287 | Retrofitting | SVS | GO2122006208PH | 30/11/2021 | 13.96 | 0 | 13.96 | Murshidabad Division |  | 10 | 0 | 0 | 0 | 10 | 9.67 | 0 | 0 | 0 | 9.67 | 69.31 | 20
292 | MURSHIDABAD | SM/09741 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Surangapur (315540) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad | TSM/007539 | 40019360 | Retrofitting | SVS | GO2122006205PH | 30/11/2021 | 11.7 | 0 | 11.7 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
293 | MURSHIDABAD | SM/08187 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa | TSM/006088 | 6154932 | Retrofitting | MVS | GO2021007205PH | 18/02/2021 | 489.6 | 0 | 489.6 | Murshidabad Division |  | 120.96 | 0 | 4.98 | 0 | 125.94 | 120.96 | 0 | 4.98 | 0 | 125.94 | 25.72 | 100
294 | MURSHIDABAD | SM/08186 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Taraf Rasulpur (314679) of P.T. Rasulpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | TSM/006086 | 40019348 | Retrofitting | SVS | GO2021007213PH | 18/02/2021 | 357.84 | 0 | 357.84 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
295 | MURSHIDABAD | SM/08273 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | TSM/006057 | 8357851 | Retrofitting | MVS | GO2021007307PH | 19/02/2021 | 665.47 | 0 | 665.47 | Murshidabad Division |  | 178.69 | 0 | 1.46 | 0 | 180.15 | 178.69 | 0 | 1.46 | 0 | 180.15 | 27.07 | 50
296 | MURSHIDABAD | SM/08274 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | TSM/006058 | 8206497 | Retrofitting | MVS | GO2021007306PH | 19/02/2021 | 384.16 | 0 | 384.16 | Murshidabad Division |  | 231.94 | 0 | 0 | 0 | 231.94 | 231.94 | 0 | 0 | 0 | 231.94 | 60.38 | 1
297 | MURSHIDABAD | SM/08194 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur | TSM/006141 | 1723329 | Retrofitting | MVS | GO2021007212PH | 18/02/2021 | 442.13 | 0 | 442.13 | Murshidabad Division |  | 297.11 | 0 | 0 | 0 | 297.11 | 297.11 | 0 | 0 | 0 | 297.11 | 67.2 | 100
298 | MURSHIDABAD | SM/08189 | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) | TSM/006090 | 8158928 | Retrofitting | MVS | GO2021007207PH | 18/02/2021 | 2032.59 | 0 | 2032.59 | Murshidabad Division |  | 1077.44 | 0 | 15.28 | 0 | 1092.72 | 1077.44 | 0 | 15.28 | 0 | 1092.72 | 53.76
299 | MURSHIDABAD | SM/10459 | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | TSM/008739 | 40013028 | Retrofitting | MVS | GO2223000271 PH | 13/04/2022 | 835.07 | 0 | 835.07 | Murshidabad Division |  | 101.35 | 0 | 0 | 0 | 101.35 | 101.35 | 0 | 0 | 0 | 101.35 | 12.14 | 50
300 | MURSHIDABAD | SM/18488 | Retrofitting of Ground Water Based Water Supply Scheme for Kamalakantapur and its Adjoining Mouzas to provided last mile connectivety and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/021516 | 7941276 | Retrofitting | MVS | PHE/IV/2001/W-617/23 | 24/07/2023 | 135.04 | 0 | 135.04 | Murshidabad Division |  | 36.32 | 0 | 0 | 0 | 36.32 | 36.32 | 0 | 0 | 0 | 36.32 | 26.89 | 95
301 | MURSHIDABAD | SM/16674 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- I & Zone- V) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. | TSM/014918 | 7749914 | Retrofitting | MVS | GO2223015905PH | 14/03/2023 | 996.89 | 0 | 996.89 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
302 | MURSHIDABAD | SM/16673 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. | TSM/014922 | 7749914 | Retrofitting | MVS | GO2223015903PH | 14/03/2023 | 998.82 | 0 | 998.82 | Murshidabad Division |  | 20.99 | 0 | 0 | 0 | 20.99 | 20.99 | 0 | 0 | 0 | 20.99 | 2.1 | 35
303 | MURSHIDABAD | SM/16986 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/019260 | 7749914 | Retrofitting | MVS | GO2223016428PH | 16/03/2023 | 733.3 | 0 | 733.3 | Murshidabad Division |  | 79.4 | 0 | 0 | 0 | 79.4 | 79.4 | 0 | 0 | 0 | 79.4 | 10.83 | 35
304 | MURSHIDABAD | SM/16987 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IV)to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/019263 | 7749914 | Retrofitting | MVS | GO2223016423PH | 16/03/2023 | 950.83 | 0 | 950.83 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
305 | MURSHIDABAD | SM/16672 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IX & X )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/014929 | 7749914 | Retrofitting | MVS | GO2223015900PH | 14/03/2023 | 998.65 | 0 | 998.65 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
306 | MURSHIDABAD | SM/16988 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VI & VII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/019262 | 7749914 | Retrofitting | MVS | GO2223016424PH | 16/03/2023 | 934.56 | 0 | 934.56 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
307 | MURSHIDABAD | SM/16989 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VIII & XII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/019259 | 7749914 | Retrofitting | MVS | GO2223016425PH | 16/03/2023 | 999.61 | 0 | 999.61 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
308 | MURSHIDABAD | SM/16990 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XIV & XVI )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/019258 | 7749914 | Retrofitting | MVS | GO2223016419PH | 16/03/2023 | 928.12 | 0 | 928.12 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
309 | MURSHIDABAD | SM/16985 | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XV & XVII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | TSM/019261 | 7749914 | Retrofitting | MVS | GO2223016426PH | 16/03/2023 | 965.79 | 0 | 965.79 | Murshidabad Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
Total | [9 empty] | 75215.53 | 0 | 75215.53 |  |  | 30154.34 | 0 | 550.41 | 0 | 30704.75 | 29835.1 | 0 | 550.41 | 0 | 30385.51 | 40.4