## JJM Schemes Financial Status (B
JJM Schemes Financial Status (BIRBHUM) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | BIRBHUM | SM/12679 | Abdullahpur Piped Water Supply Scheme. | TSM/014520 | 40032563 | New | MVS | GO2223008012PH | 21/09/2022 | 743.52 | 55.57 | 799.1 | Birbhum Division | Bolpur Mechanical Division | 131.41 | 10.52 | 41.03 | 0 | 182.96 | 131.41 | 17.35 | 41.03 | 0 | 189.79 | 23.75 | 70
2 | BIRBHUM | SM/12536 | Abhirampur and Adjoining Mouzas PWSS | TSM/013171 | 40033592 | New | MVS | GO2223007613PH | 13/09/2022 | 341.25 | 36.32 | 377.57 | Birbhum Division | Bolpur Mechanical Division | 113.08 | 23.63 | 51.31 | 0 | 188.02 | 113.08 | 23.63 | 51.31 | 0 | 188.02 | 49.8 | 55
3 | BIRBHUM | SM/14889 | Ahmadpur Piped Water Supply Scheme | TSM/016714 | 40037228 | New | MVS | GO2223013126PH | 03/02/2023 | 767.02 | 129.84 | 896.86 | Birbhum Division | Bolpur Mechanical Division | 256.41 | 87.53 | 174.72 | 0 | 518.67 | 256.41 | 90.66 | 174.72 | 0 | 521.8 | 58.18 | 59
4 | BIRBHUM | SM/14533 | Albandha Piped Water Supply Scheme. | TSM/015177 | 40033618 | New | MVS | GO2223012548PH | 30/01/2023 | 1156.3 | 91.42 | 1247.73 | Birbhum Division | Bolpur Mechanical Division | 193.7 | 49.02 | 203.81 | 11.11 | 457.64 | 193.7 | 49.02 | 203.81 | 11.11 | 457.64 | 36.68 | 40
5 | BIRBHUM | SM/14083 | Aliat Piped Water Supply Scheme | TSM/016735 | 40036905 | New | MVS | GO2223010849PH | 12/12/2022 | 414.62 | 0 | 414.62 | Birbhum Division |  | 2.37 | 0 | 67.67 | 0 | 70.04 | 2.37 | 0 | 67.67 | 0 | 70.04 | 16.89 | 19
6 | BIRBHUM | SM/16387 | Amlachaturi Piped Water Supply Scheme | TSM/016716 | 40053979 | New | MVS | GO2223014977PH | 28/02/2023 | 777.72 | 127.15 | 904.87 | Birbhum Division | Bolpur Mechanical Division | 179.77 | 63.38 | 19.65 | 0 | 262.8 | 179.77 | 64.42 | 19.65 | 0 | 263.84 | 29.16 | 60
7 | BIRBHUM | SM/12676 | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | TSM/011621 | 40033119 | New | MVS | GO2223007809PH | 19/09/2022 | 261.63 | 38.39 | 300.02 | Birbhum Division | Bolpur Mechanical Division | 205.7 | 28.38 | 15.9 | 0 | 249.99 | 209.26 | 31.39 | 15.9 | 0 | 256.56 | 85.51 | 90
8 | BIRBHUM | SM/13971 | ANGORA PIPED WATER SUPPLY SCHEME | TSM/016091 | 40037162 | New | MVS | GO2223010283PH | 01/12/2022 | 797.43 | 114.44 | 911.87 | Birbhum Division | Bolpur Mechanical Division | 4.89 | 14.77 | 11.71 | 0 | 31.37 | 4.89 | 14.77 | 11.71 | 0 | 31.37 | 3.44 | 5
9 | BIRBHUM | SM/12680 | Asenga Piped Water Supply Scheme. | TSM/014568 | 40030025 | New | MVS | GO2223007947PH | 20/09/2022 | 579.43 | 37.97 | 617.4 | Birbhum Division | Bolpur Mechanical Division | 255.1 | 34.52 | 99.56 | 0 | 389.17 | 255.1 | 36.25 | 99.56 | 0 | 390.91 | 63.32 | 80
10 | BIRBHUM | SM/13376 | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | TSM/015465 | 40035150 | New | MVS | GO2223008921PH | 18/10/2022 | 716.24 | 77.77 | 794.01 | Birbhum Division | Bolpur Mechanical Division | 154.9 | 31.2 | 8.96 | 0 | 195.06 | 154.9 | 32.42 | 8.96 | 0 | 196.28 | 24.72 | 65
11 | BIRBHUM | SM/18301 | Atkulia Piped Water Supply Scheme | TSM/015432 | 40033931 | New | MVS | 1664/PHE-28011/40/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 895.21 | 112.42 | 1007.63 | Birbhum Division | Bolpur Mechanical Division | 307.24 | 30 | 58.03 | 0 | 395.27 | 307.24 | 31.48 | 58.03 | 0 | 396.75 | 39.37 | 55
12 | BIRBHUM | SM/10313 | Augmentation of Ahmedpur Piped Water Supply Scheme | TSM/009869 | 40026533 | Augmentation | MVS | GO2122010484PH | 04/03/2022 | 727.75 | 38.55 | 766.3 | Birbhum Division | Bolpur Mechanical Division | 468.06 | 18.27 | 4.89 | 0 | 491.23 | 468.06 | 18.27 | 4.89 | 0 | 491.23 | 64.1 | 70
13 | BIRBHUM | SM/18787 | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | TSM/014732 | 40064179 | Augmentation | MVS | PHE/IV/2610/W-644/23 | 29/08/2023 | 688.02 | 192.37 | 880.39 | Birbhum Division | Bolpur Mechanical Division | 76.59 | 101.01 | 0 | 0 | 177.6 | 76.59 | 103.39 | 0 | 0 | 179.98 | 20.44 | 30
14 | BIRBHUM | SM/14960 | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | TSM/015001 | 40060309 | Augmentation | MVS | GO2223013083PH | 04/02/2023 | 625.92 | 89.42 | 715.34 | Birbhum Division | Bolpur Mechanical Division | 0 | 53.88 | 160.54 | 0 | 214.42 | 0 | 53.88 | 160.54 | 0 | 214.42 | 29.97 | 35
15 | BIRBHUM | SM/15236 | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | TSM/015009 | 40060292 | Augmentation | MVS | GO2223013392PH | 07/02/2023 | 649.03 | 89.42 | 738.45 | Birbhum Division | Bolpur Mechanical Division | 139.4 | 58.58 | 87.67 | 0 | 285.65 | 139.4 | 59.75 | 87.67 | 0 | 286.82 | 38.84 | 70
16 | BIRBHUM | SM/10321 | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | TSM/007455 | 40009546 | Augmentation | MVS | GO2122010530PH | 07/03/2022 | 6450.63 | 233 | 6683.63 | Birbhum Division | Bolpur Mechanical Division | 3560.46 | 177.3 | 604.9 | 0 | 4342.67 | 3562.37 | 189.25 | 604.9 | 0 | 4356.52 | 65.18 | 70
17 | BIRBHUM | SM/10343 | Augmentation of Khoyrasole Piped Water Supply Scheme | TSM/009739 | 40005935 | Augmentation | MVS | GO2122010692PH | 14/03/2022 | 1265.98 | 0 | 1265.98 | Birbhum Division | Bolpur Mechanical Division | 930.36 | 0 | 0 | 0 | 930.36 | 930.36 | 0 | 0 | 0 | 930.36 | 73.49 | 88
18 | BIRBHUM | SM/10320 | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | TSM/007454 | 40009544 | Augmentation | MVS | GO2122010530PH | 07/03/2022 | 7592.91 | 315 | 7907.91 | Birbhum Division | Bolpur Mechanical Division | 3113.66 | 242.78 | 204.32 | 0 | 3560.76 | 3113.66 | 268.72 | 204.32 | 0 | 3586.7 | 45.36 | 50
19 | BIRBHUM | SM/18372 | Augmentation of Margram piped water supply scheme. | TSM/011981 | 40060285 | Augmentation | SVS | 1805/PHE-28011/97/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1850.79 | 128.86 | 1979.65 | Birbhum Division | Bolpur Mechanical Division | 73.54 | 69.28 | 0 | 0 | 142.82 | 73.54 | 71.48 | 0 | 0 | 145.02 | 7.33 | 65
20 | BIRBHUM | SM/10315 | Augmentation of Mathpalsa Piped Water Supply Scheme | TSM/009564 | 40015003 | Augmentation | MVS | GO2122010482PH | 04/03/2022 | 258.48 | 24.56 | 283.04 | Birbhum Division | Bolpur Mechanical Division | 181.16 | 16.46 | 0 | 0 | 197.62 | 183.57 | 19.64 | 0 | 0 | 203.21 | 71.79 | 72
21 | BIRBHUM | SM/10312 | Augmentation of Nagari Piped Water Supply Scheme | TSM/009571 | 40026525 | Augmentation | MVS | GO2122010480PH | 04/03/2022 | 215.26 | 57.54 | 272.8 | Birbhum Division | Bolpur Mechanical Division | 138.87 | 23.22 | 10.19 | 0 | 172.28 | 138.87 | 23.22 | 10.19 | 0 | 172.28 | 63.15 | 80
22 | BIRBHUM | SM/10314 | Augmentation of Panchiara Piped Water Supply Scheme | TSM/009572 | 40024023 | Augmentation | MVS | GO2122010481PH | 04/03/2022 | 818.34 | 103.05 | 921.39 | Birbhum Division | Bolpur Mechanical Division | 392.12 | 78.07 | 141.63 | 0 | 611.82 | 392.12 | 78.07 | 141.63 | 0 | 611.82 | 66.4 | 68
23 | BIRBHUM | SM/09437 | Augmentation of Purandarpur Piped Water Supply Scheme | TSM/008567 | 40006349 | Augmentation | MVS | GO2122005372PH | 12/11/2021 | 638.91 | 40.49 | 679.4 | Birbhum Division | Bolpur Mechanical Division | 480.54 | 31.68 | 81.08 | 0 | 593.3 | 480.54 | 34.12 | 81.08 | 0 | 595.74 | 87.69 | 88
24 | BIRBHUM | SM/10319 | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | TSM/007453 | 40009541 | Augmentation | MVS | GO2122010530PH | 07/03/2022 | 11339.45 | 300 | 11639.45 | Birbhum Division | Bolpur Mechanical Division | 9481.19 | 274.25 | 867.08 | 0 | 10622.52 | 9485.27 | 294.46 | 867.08 | 0 | 10646.82 | 91.47 | 85
25 | BIRBHUM | SM/09438 | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | TSM/008501 | 40006424 | Augmentation | MVS | GO2122004681PH | 29/10/2021 | 594.69 | 167.57 | 762.27 | Birbhum Division | Bolpur Mechanical Division | 374.45 | 136.28 | 42.5 | 0 | 553.23 | 374.45 | 136.28 | 42.5 | 0 | 553.23 | 72.58 | 80
26 | BIRBHUM | SM/14744 | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | TSM/014955 | 40060314 | Augmentation | MVS | GO2223012669PH | 31/01/2023 | 642.08 | 265.04 | 907.13 | Birbhum Division | Bolpur Mechanical Division | 0 | 198.16 | 101.49 | 0 | 299.65 | 0 | 198.16 | 101.49 | 0 | 299.65 | 33.03 | 35
27 | BIRBHUM | SM/18366 | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | TSM/015914 | 40060415 | Augmentation | MVS | 1802/PHE-28011/279/2022-ESTT CELL-Dept. of PHE | 11/07/2023 | 949.66 | 91.04 | 1040.7 | Birbhum Division | Bolpur Mechanical Division | 182.63 | 24.65 | 142.06 | 0 | 349.35 | 182.63 | 25.7 | 142.06 | 0 | 350.39 | 33.67 | 45
28 | BIRBHUM | SM/10166 | Augmentation of Tejhati PWSS | TSM/009559 | 40005932 | Augmentation | MVS | GO2122009645PH | 11/02/2022 | 343.95 | 23.85 | 367.8 | Birbhum Division | Bolpur Mechanical Division | 226.26 | 20.82 | 8.44 | 0 | 255.52 | 226.26 | 20.82 | 8.44 | 0 | 255.52 | 69.47 | 85
29 | BIRBHUM | SM/18669 | Ayas Piped Water Supply Scheme. | TSM/016379 | 40037346 | New | MVS | 2238/PHE-28011/235/2022-SCHM CELL-Dept. of PHE | 04/08/2023 | 2083.63 | 167.89 | 2251.52 | Birbhum Division | Bolpur Mechanical Division | 0 | 99.01 | 278.61 | 0 | 377.62 | 0 | 99.01 | 278.61 | 0 | 377.62 | 16.77 | 20
30 | BIRBHUM | SM/14084 | Bagahola Piped Water Supply Scheme | TSM/016715 | 40036894 | New | MVS | GO2223010831PH | 12/12/2022 | 389.21 | 0 | 389.21 | Birbhum Division |  | 12.76 | 0 | 69.14 | 0 | 81.9 | 12.76 | 0 | 69.14 | 0 | 81.9 | 21.04 | 25
31 | BIRBHUM | SM/12681 | Bahadurpur Piped Water Supply Scheme. | TSM/014567 | 40033337 | New | MVS | GO2223008030PH | 21/09/2022 | 711.2 | 38.1 | 749.3 | Birbhum Division | Bolpur Mechanical Division | 175.39 | 20.72 | 21.11 | 0 | 217.22 | 175.39 | 22.22 | 21.11 | 0 | 218.72 | 29.19 | 60
32 | BIRBHUM | SM/13983 | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. | TSM/015724 | 40037103 | New | MVS | GO2223010288PH | 01/12/2022 | 366.5 | 80.86 | 447.36 | Birbhum Division | Bolpur Mechanical Division | 168.33 | 29.01 | 6.3 | 0 | 203.64 | 169.55 | 33.78 | 6.3 | 0 | 209.63 | 46.86 | 90
33 | BIRBHUM | SM/14847 | BALIARA PIPED WATER SUPPLY SCHEME | TSM/017430 | 40053974 | New | MVS | GO2223013011PH | 03/02/2023 | 553.11 | 155.94 | 709.05 | Birbhum Division | Bolpur Mechanical Division | 4.19 | 0 | 23.68 | 0 | 27.87 | 4.19 | 0 | 23.68 | 0 | 27.87 | 3.93 | 5
34 | BIRBHUM | SM/12682 | Balijuri Piped Water Supply Scheme. | TSM/014823 | 40033308 | New | MVS | GO2223008035PH | 21/09/2022 | 847.12 | 93.15 | 940.28 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 134.51 | 0 | 134.51 | 0 | 0 | 134.51 | 0 | 134.51 | 14.31 | 15
35 | BIRBHUM | SM/12829 | BANGJITA PIPED WATER SUPPLY SCHEME. | TSM/011613 | 40032377 | New | MVS | GO2223008126PH | 22/09/2022 | 450.71 | 38.41 | 489.13 | Birbhum Division | Bolpur Mechanical Division | 14.46 | 29.77 | 15.14 | 0 | 59.38 | 14.46 | 29.77 | 15.14 | 0 | 59.38 | 12.14 | 60
36 | BIRBHUM | SM/14029 | Banhat Piped Water Supply Scheme. | TSM/016070 | 40037285 | New | MVS | GO2223010491PH | 05/12/2022 | 444.79 | 39.29 | 484.07 | Birbhum Division | Bolpur Mechanical Division | 244.5 | 24.2 | 12.43 | 0 | 281.12 | 245.71 | 25.56 | 12.43 | 0 | 283.7 | 58.61 | 90
37 | BIRBHUM | SM/14688 | Banior Piped Water Supply Scheme. | TSM/015887 | 40060381 | New | MVS | GO2223012764PH | 31/01/2023 | 2651.51 | 191.44 | 2842.94 | Birbhum Division | Bolpur Mechanical Division | 50.74 | 131.06 | 655.58 | 0 | 837.37 | 50.74 | 131.06 | 655.58 | 0 | 837.37 | 29.45 | 20
38 | BIRBHUM | SM/12889 | BANSANKHA PIPED WATER SUPPLY SCHEME. | TSM/011623 | 40032403 | New | MVS | GO2223008151PH | 23/09/2022 | 349.77 | 36.3 | 386.07 | Birbhum Division | Bolpur Mechanical Division | 33.13 | 34.3 | 5.22 | 0 | 72.65 | 33.13 | 34.3 | 5.22 | 0 | 72.65 | 18.82 | 25
39 | BIRBHUM | SM/18514 | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | TSM/016208 | 40039516 | New | MVS | 2043/PHE-28011/277/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1077 | 109.83 | 1186.83 | Birbhum Division | Bolpur Mechanical Division | 72.29 | 26.16 | 118.34 | 0 | 216.79 | 72.29 | 26.16 | 118.34 | 0 | 216.79 | 18.27 | 45
40 | BIRBHUM | SM/14852 | Baraban Piped Water Supply Scheme (Khoyrasole Block) | TSM/017781 | 40053969 | New | MVS | GO2223013006PH | 03/02/2023 | 585.66 | 0 | 585.66 | Birbhum Division |  | 22.53 | 0 | 101.85 | 0 | 124.38 | 22.53 | 0 | 101.85 | 0 | 124.38 | 21.24 | 25
41 | BIRBHUM | SM/14424 | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. | TSM/015347 | 40034522 | New | MVS | GO2223012262PH | 20/01/2023 | 1384.81 | 131.6 | 1516.41 | Birbhum Division | Bolpur Mechanical Division | 46.22 | 35.13 | 210.87 | 0 | 292.23 | 46.22 | 35.13 | 210.87 | 0 | 292.23 | 19.27 | 25
42 | BIRBHUM | SM/14535 | Barshal piped water supply scheme. | TSM/015509 | 40034065 | New | MVS | GO2223012591PH | 30/01/2023 | 1611.29 | 157.55 | 1768.83 | Birbhum Division | Bolpur Mechanical Division | 143.91 | 35.1 | 384.12 | 0 | 563.13 | 143.91 | 35.1 | 384.12 | 0 | 563.13 | 31.84 | 30
43 | BIRBHUM | SM/14421 | Barua Gopalpur Piped Water Supply Scheme. | TSM/014578 | 40033809 | New | MVS | GO2223012274PH | 20/01/2023 | 1228.25 | 59.91 | 1288.16 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 139.98 | 0 | 139.98 | 0 | 0 | 139.98 | 0 | 139.98 | 10.87 | 15
44 | BIRBHUM | SM/14536 | Bautia piped water supply scheme | TSM/015590 | 40033882 | New | MVS | GO2223012593PH | 30/01/2023 | 1340.26 | 127.3 | 1467.55 | Birbhum Division | Bolpur Mechanical Division | 21.66 | 25.34 | 410.11 | 0 | 457.12 | 21.66 | 11.31 | 410.11 | 0 | 443.08 | 30.19 | 30
45 | BIRBHUM | SM/12456 | Behira and Adjoining Mouzas PWSS | TSM/013257 | 40033594 | New | MVS | GO2223007611PH | 13/09/2022 | 277.56 | 36.28 | 313.84 | Birbhum Division | Bolpur Mechanical Division | 52.05 | 10.1 | 22.26 | 0 | 84.41 | 52.05 | 10.1 | 22.26 | 0 | 84.41 | 26.89 | 60
46 | BIRBHUM | SM/18522 | Beloa Piped Water Supply Scheme | TSM/015423 | 40033909 | New | MVS | 2045/PHE-28011/211/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 963.64 | 112.42 | 1076.07 | Birbhum Division | Bolpur Mechanical Division | 263.11 | 41.01 | 34.79 | 0 | 338.91 | 263.11 | 47.29 | 34.79 | 0 | 345.19 | 32.08 | 50
47 | BIRBHUM | SM/13634 | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | TSM/015494 | 40033737 | New | MVS | GO2223009610PH | 11/11/2022 | 281.57 | 55.12 | 336.69 | Birbhum Division | Bolpur Mechanical Division | 186.41 | 31.53 | 5.49 | 0 | 223.43 | 187.6 | 34.53 | 5.49 | 0 | 227.62 | 67.61 | 90
48 | BIRBHUM | SM/13377 | BENAGRAM PIPED WATER SUPPLY SCHEME | TSM/015486 | 40033576 | New | MVS | GO2223008922PH | 18/10/2022 | 473.98 | 150.76 | 624.74 | Birbhum Division | Bolpur Mechanical Division | 3.62 | 0 | 46.62 | 0 | 50.24 | 3.62 | 0 | 46.62 | 0 | 50.24 | 8.04 | 10
49 | BIRBHUM | SM/13408 | BENGA CHATRA PIPED WATER SUPPLY SCHEME | TSM/015476 | 40033575 | New | MVS | GO2223009163PH | 02/11/2022 | 602.28 | 114.44 | 716.72 | Birbhum Division | Bolpur Mechanical Division | 4.16 | 0 | 30.97 | 0 | 35.13 | 4.16 | 0 | 30.97 | 0 | 35.13 | 4.9 | 5
50 | BIRBHUM | SM/13482 | Bergram Piped Water Supply Scheme. | TSM/015559 | 40034627 | New | MVS | GO2223009219PH | 02/11/2022 | 489.64 | 37.76 | 527.4 | Birbhum Division | Bolpur Mechanical Division | 0 | 9.24 | 32.2 | 19.48 | 60.92 | 0 | 9.24 | 32.2 | 19.48 | 60.92 | 11.55 | 10
51 | BIRBHUM | SM/18351 | Bhabani Water Supply Scheme | TSM/015496 | 40033657 | New | MVS | 1796/PHE-28011/266/2022-SCHM CELL-Dept. of PHE | 11/07/2023 | 1398.34 | 53.42 | 1451.76 | Birbhum Division | Bolpur Mechanical Division | 114.2 | 4.93 | 0 | 54.81 | 173.94 | 114.2 | 4.93 | 0 | 54.81 | 173.94 | 11.98 | 30
52 | BIRBHUM | SM/14114 | Bhaddi Piped Water Supply Scheme | TSM/016712 | 40036878 | New | MVS | GO2223011506PH | 02/01/2023 | 422.65 | 0 | 422.65 | Birbhum Division |  | 25.5 | 0 | 69.14 | 0 | 94.64 | 25.5 | 0 | 69.14 | 0 | 94.64 | 22.39 | 24
53 | BIRBHUM | SM/14674 | Bhadulia Piped Water Supply Scheme | TSM/016717 | 40060340 | New | MVS | GO2223012676PH | 31/01/2023 | 474.51 | 0 | 474.51 | Birbhum Division |  | 2.71 | 0 | 74.31 | 0 | 77.03 | 2.71 | 0 | 74.31 | 0 | 77.03 | 16.23 | 15
54 | BIRBHUM | SM/13475 | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | TSM/015470 | 40033753 | New | MVS | GO2223009218PH | 02/11/2022 | 367.62 | 77.77 | 445.39 | Birbhum Division | Bolpur Mechanical Division | 191.04 | 25.71 | 6.95 | 0 | 223.71 | 192.24 | 27.47 | 6.95 | 0 | 226.65 | 50.89 | 90
55 | BIRBHUM | SM/12834 | BHALIAN PIPED WATER SUPPLY SCHME. | TSM/011721 | 40032255 | New | MVS | GO2223008130PH | 22/09/2022 | 534.6 | 38.61 | 573.21 | Birbhum Division | Bolpur Mechanical Division | 90.23 | 28.45 | 41.6 | 9.04 | 169.31 | 90.23 | 30.81 | 41.6 | 9.04 | 171.67 | 29.95 | 80
56 | BIRBHUM | SM/14958 | BHATRA PIPED WATER SUPPLY SCHEME | TSM/017151 | 40037064 | New | MVS | GO2223013095PH | 04/02/2023 | 627.95 | 158.02 | 785.97 | Birbhum Division | Bolpur Mechanical Division | 3.72 | 0 | 71.86 | 0 | 75.58 | 3.72 | 0 | 71.86 | 0 | 75.58 | 9.62 | 15
57 | BIRBHUM | SM/12833 | BHEJENA PIPED WATER SUPPLY SCHEME. | TSM/011620 | 40033111 | New | MVS | GO2223008121PH | 22/09/2022 | 208.26 | 36.25 | 244.52 | Birbhum Division | Bolpur Mechanical Division | 82.69 | 25.06 | 22.45 | 0 | 130.2 | 82.69 | 25.06 | 22.45 | 0 | 130.2 | 53.25 | 65
58 | BIRBHUM | SM/13759 | BHEPUR PIPED WATER SUPPLY SCHEME | TSM/015433 | 40033972 | New | MVS | GO2223009911PH | 18/11/2022 | 552.84 | 152.84 | 705.69 | Birbhum Division | Bolpur Mechanical Division | 4.1 | 17.02 | 16.1 | 0 | 37.22 | 4.1 | 17.02 | 16.1 | 0 | 37.22 | 5.27 | 5
59 | BIRBHUM | SM/14848 | BHETER PIPED WATER SUPPLY SCHEME | TSM/016086 | 40053975 | New | MVS | GO2223013009PH | 03/02/2023 | 374.36 | 133.11 | 507.47 | Birbhum Division | Bolpur Mechanical Division | 3.14 | 0 | 35.3 | 0 | 38.44 | 3.14 | 0 | 35.3 | 0 | 38.44 | 7.57 | 10
60 | BIRBHUM | SM/13387 | BHUBANESWAR PIPED WATER SUPPLY SCHEME | TSM/015542 | 40035032 | New | MVS | GO2223008925PH | 18/10/2022 | 871.38 | 40.33 | 911.71 | Birbhum Division | Bolpur Mechanical Division | 5.19 | 16.61 | 117.52 | 44.45 | 183.77 | 5.19 | 16.61 | 117.52 | 44.45 | 183.77 | 20.16 | 20
61 | BIRBHUM | SM/13708 | Bidhyadharpur Piped Water Supply Scheme. | TSM/015556 | 40033646 | New | MVS | GO2223009716PH | 14/11/2022 | 583.26 | 37.9 | 621.16 | Birbhum Division | Bolpur Mechanical Division | 0 | 9.59 | 13.32 | 30.35 | 53.25 | 0 | 9.59 | 13.32 | 30.35 | 53.25 | 8.57 | 10
62 | BIRBHUM | SM/12594 | BILASPUR PIPED WATER SUPPLY SCHEME. | TSM/013015 | 40033489 | New | MVS | GO2223007728PH | 15/09/2022 | 822.3 | 40.25 | 862.54 | Birbhum Division | Bolpur Mechanical Division | 113.69 | 28.43 | 21.51 | 0 | 163.63 | 114.63 | 31.43 | 21.51 | 0 | 167.57 | 19.43 | 50
63 | BIRBHUM | SM/14141 | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | TSM/015354 | 40034526 | New | MVS | GO2223011534PH | 02/01/2023 | 1075.35 | 131.6 | 1206.94 | Birbhum Division | Bolpur Mechanical Division | 167.79 | 63.59 | 52.38 | 0 | 283.77 | 167.79 | 64.78 | 52.38 | 0 | 284.96 | 23.61 | 50
64 | BIRBHUM | SM/12830 | BIRSINGHA PIPED WATER SUPPLY SCHEME. | TSM/011614 | 40032316 | New | MVS | GO2223008128PH | 22/09/2022 | 372.87 | 38.85 | 411.72 | Birbhum Division | Bolpur Mechanical Division | 56.08 | 29.34 | 6.18 | 17.48 | 109.08 | 56.08 | 29.96 | 6.18 | 17.48 | 109.7 | 26.65 | 40
65 | BIRBHUM | SM/12591 | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | TSM/013012 | 40033478 | New | MVS | GO2223007724PH | 15/09/2022 | 504.5 | 40.37 | 544.87 | Birbhum Division | Bolpur Mechanical Division | 119.81 | 29.39 | 53.4 | 0 | 202.6 | 119.81 | 31.78 | 53.4 | 0 | 204.99 | 37.62 | 60
66 | BIRBHUM | SM/14534 | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | TSM/015460 | 40033990 | New | MVS | GO2223012594PH | 30/01/2023 | 917.93 | 153.12 | 1071.04 | Birbhum Division | Bolpur Mechanical Division | 5.83 | 0 | 40.92 | 0 | 46.75 | 5.83 | 0 | 40.92 | 0 | 46.75 | 4.36 | 5
67 | BIRBHUM | SM/16762 | Budhigram Piped Water Supply Scheme | TSM/015741 | 40039436 | New | MVS | GO2223015711PH | 13/03/2023 | 682.98 | 80.86 | 763.84 | Birbhum Division | Bolpur Mechanical Division | 4.51 | 18.66 | 15.45 | 0 | 38.61 | 4.51 | 18.66 | 15.45 | 0 | 38.61 | 5.06 | 5
68 | BIRBHUM | SM/13638 | Chakpara piped water supply scheme. | TSM/015256 | 40034058 | New | MVS | GO2223009629PH | 11/11/2022 | 585.47 | 55.46 | 640.93 | Birbhum Division | Bolpur Mechanical Division | 59.42 | 40.17 | 34.77 | 0 | 134.35 | 59.42 | 43.14 | 34.77 | 0 | 137.33 | 21.43 | 65
69 | BIRBHUM | SM/12683 | Chanchali piped water supply scheme. | TSM/014574 | 40033404 | New | MVS | GO2223008033PH | 21/09/2022 | 993.59 | 40.74 | 1034.33 | Birbhum Division | Bolpur Mechanical Division | 245.55 | 26.06 | 161.56 | 0 | 433.17 | 245.55 | 26.06 | 161.56 | 0 | 433.17 | 41.88 | 30
70 | BIRBHUM | SM/14893 | Chandrapur Piped Water Supply Scheme | TSM/016710 | 40045566 | New | MVS | GO2223013138PH | 04/02/2023 | 522.79 | 130.43 | 653.22 | Birbhum Division | Bolpur Mechanical Division | 279.36 | 42.71 | 115.86 | 0 | 437.93 | 279.36 | 43.72 | 115.86 | 0 | 438.94 | 67.2 | 90
71 | BIRBHUM | SM/18512 | Charicha Piped Water Supply Scheme. | TSM/016237 | 40038391 | New | MVS | 2043/PHE-28011/277/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1380.52 | 133.96 | 1514.48 | Birbhum Division | Bolpur Mechanical Division | 25 | 0 | 486.68 | 0 | 511.68 | 25 | 5.1 | 486.68 | 0 | 516.78 | 34.12 | 35
72 | BIRBHUM | SM/13481 | Charkalgram Piped Water Supply Scheme | TSM/015455 | 40033985 | New | MVS | GO2223009252PH | 02/11/2022 | 839.04 | 114.44 | 953.48 | Birbhum Division | Central Mechanical Division | 5.14 | 0 | 9.61 | 0 | 14.75 | 5.14 | 0 | 9.61 | 0 | 14.75 | 1.55 | 3
73 | BIRBHUM | SM/12835 | CHAUTI PIPED WATER SUPPLY SCHEME. | TSM/011724 | 40033411 | New | MVS | GO2223008133PH | 22/09/2022 | 534.2 | 40.26 | 574.46 | Birbhum Division | Bolpur Mechanical Division | 187.17 | 27.03 | 10.16 | 0 | 224.35 | 189.06 | 31.37 | 10.16 | 0 | 230.59 | 40.14 | 70
74 | BIRBHUM | SM/13710 | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | TSM/015479 | 40033703 | New | MVS | GO2223009719PH | 14/11/2022 | 879.56 | 100.42 | 979.98 | Birbhum Division | Bolpur Mechanical Division | 398.51 | 62.54 | 25.98 | 0 | 487.03 | 398.51 | 67.3 | 25.98 | 0 | 491.79 | 50.18 | 86
75 | BIRBHUM | SM/18354 | CHHATAR BANDI PIPED WATER SUPPLY SCHEME | TSM/015489 | 40033692 | New | MVS | 1796/PHE-28011/266/2022-SCHM CELL-Dept. of PHE | 11/07/2023 | 980.79 | 40.91 | 1021.7 | Birbhum Division | Bolpur Mechanical Division | 90.91 | 4.83 | 31.62 | 31.88 | 159.23 | 90.91 | 4.83 | 31.62 | 31.88 | 159.23 | 15.59 | 25
76 | BIRBHUM | SM/16761 | Chhora Piped Water Supply Scheme. | TSM/016498 | 40037395 | New | MVS | GO2223015709PH | 13/03/2023 | 457.72 | 39.65 | 497.37 | Birbhum Division | Bolpur Mechanical Division | 0 | 23.74 | 21.49 | 0 | 45.23 | 0 | 26.66 | 21.49 | 0 | 48.15 | 9.68 | 13
77 | BIRBHUM | SM/18513 | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | TSM/016652 | 40038263 | New | MVS | 2043/PHE-28011/277/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 986.16 | 136.5 | 1122.66 | Birbhum Division | Bolpur Mechanical Division | 5.69 | 91.27 | 83.34 | 0 | 180.3 | 5.69 | 93.09 | 83.34 | 0 | 182.12 | 16.22 | 45
78 | BIRBHUM | SM/18462 | Chinpai Piped Water Supply Scheme. | TSM/016742 | 40036891 | New | MVS | 1964/PHE-28011/56/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 1311.14 | 132.84 | 1443.97 | Birbhum Division | Bolpur Mechanical Division | 267.6 | 90.34 | 183.3 | 0 | 541.24 | 267.6 | 90.34 | 183.3 | 0 | 541.24 | 37.48 | 75
79 | BIRBHUM | SM/15523 | Chora Piped Water Supply Scheme | TSM/016718 | 40036896 | New | MVS | GO2223013871PH | 16/02/2023 | 248.08 | 0 | 248.08 | Birbhum Division | Bolpur Mechanical Division | 1.41 | 0 | 23.75 | 0 | 25.17 | 1.41 | 0 | 23.75 | 0 | 25.17 | 10.15 | 10
80 | BIRBHUM | SM/14030 | Chormara Piped Water Supply Scheme. | TSM/015886 | 40039089 | New | MVS | GO2223010480PH | 05/12/2022 | 365.61 | 37.19 | 402.81 | Birbhum Division | Bolpur Mechanical Division | 17.24 | 1.3 | 13.58 | 0 | 32.12 | 17.24 | 1.3 | 13.58 | 0 | 32.12 | 7.97 | 30
81 | BIRBHUM | SM/13637 | CHUNPALASHI PIPED WATER SUPPLY SCHEME | TSM/015493 | 40033689 | New | MVS | GO2223009604PH | 11/11/2022 | 699.83 | 40.21 | 740.04 | Birbhum Division | Bolpur Mechanical Division | 4.21 | 0 | 27.01 | 23.04 | 54.26 | 4.21 | 0 | 27.01 | 23.04 | 54.26 | 7.33 | 5
82 | BIRBHUM | SM/18425 | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | TSM/017932 | 40063537 | New | MVS | 1923/PHE-28011/146/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 4707.51 | 194.47 | 4901.98 | Birbhum Division | Bolpur Mechanical Division | 1670.16 | 78.51 | 1630.08 | 0 | 3378.75 | 1670.16 | 78.51 | 1630.08 | 0 | 3378.75 | 68.93 | 65
83 | BIRBHUM | SM/13480 | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | TSM/015431 | 40033803 | New | MVS | GO2223009221PH | 02/11/2022 | 456.74 | 77.77 | 534.51 | Birbhum Division | Bolpur Mechanical Division | 110.71 | 24.46 | 25.97 | 0 | 161.13 | 110.71 | 25.62 | 25.97 | 0 | 162.29 | 30.36 | 80
84 | BIRBHUM | SM/12684 | Dadpur Piped Water Supply Scheme. | TSM/014515 | 40033196 | New | MVS | GO2223008024PH | 21/09/2022 | 555.73 | 37.78 | 593.51 | Birbhum Division | Bolpur Mechanical Division | 205.01 | 35.43 | 29 | 0 | 269.44 | 205.92 | 38.73 | 29 | 0 | 273.65 | 46.11 | 70
85 | BIRBHUM | SM/18363 | Dakhalbati Piped Water Supply Scheme. | TSM/016763 | 40037479 | New | MVS | 1799/PHE-28011/63/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 2371.21 | 182.46 | 2553.67 | Birbhum Division | Bolpur Mechanical Division | 25 | 127.96 | 40.37 | 0 | 193.33 | 25 | 127.96 | 40.37 | 0 | 193.33 | 7.57 | 8
86 | BIRBHUM | SM/12685 | Dakshin Chandipur Piped Water Supply Scheme. | TSM/014563 | 40032929 | New | MVS | GO2223008017PH | 21/09/2022 | 521.11 | 35.62 | 556.73 | Birbhum Division | Bolpur Mechanical Division | 0 | 21.12 | 43.74 | 0 | 64.87 | 0 | 21.73 | 43.74 | 0 | 65.48 | 11.76 | 55
87 | BIRBHUM | SM/18521 | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | TSM/015454 | 40033778 | New | MVS | 2045/PHE-28011/211/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 938.11 | 105.77 | 1043.88 | Birbhum Division | Bolpur Mechanical Division | 218.18 | 46.3 | 92.12 | 0 | 356.61 | 218.18 | 50.19 | 92.12 | 0 | 360.5 | 34.53 | 70
88 | BIRBHUM | SM/12686 | Dakshin Kasila Piped Water Supply Scheme. | TSM/014528 | 40033210 | New | MVS | GO2223008037PH | 21/09/2022 | 868.89 | 40.56 | 909.45 | Birbhum Division | Bolpur Mechanical Division | 0 | 26.95 | 16.63 | 0 | 43.58 | 0 | 26.95 | 16.63 | 0 | 43.58 | 4.79 | 10
89 | BIRBHUM | SM/12687 | Dakshin Madanpur Piped Water Supply Scheme. | TSM/014821 | 40033299 | New | MVS | GO2223008026PH | 21/09/2022 | 394.95 | 78.16 | 473.11 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 31.24 | 0 | 31.24 | 0 | 0 | 31.24 | 0 | 31.24 | 6.6 | 10
90 | BIRBHUM | SM/12592 | DALIMA PIPED WATER SUPPLY SCHEME. | TSM/013064 | 40033161 | New | MVS | GO2223007730PH | 15/09/2022 | 619.38 | 43.1 | 662.48 | Birbhum Division | Bolpur Mechanical Division | 15.08 | 23.89 | 36.48 | 0 | 75.45 | 15.08 | 23.89 | 36.48 | 0 | 75.45 | 11.39 | 25
91 | BIRBHUM | SM/18353 | Daskalgram Piped Water Supply Scheme | TSM/015491 | 40034001 | New | MVS | 1796/PHE-28011/266/2022-SCHM CELL-Dept. of PHE | 11/07/2023 | 1046.55 | 150.76 | 1197.31 | Birbhum Division | Central Mechanical Division | 6.57 | 0 | 83.96 | 0 | 90.53 | 6.57 | 0 | 83.96 | 0 | 90.53 | 7.56 | 10
92 | BIRBHUM | SM/13600 | DELORA PIPED WATER SUPPLY SCHEME | TSM/015497 | 40033701 | New | MVS | GO2223009528PH | 09/11/2022 | 349.3 | 38.92 | 388.22 | Birbhum Division | Bolpur Mechanical Division | 19.82 | 0.44 | 10.55 | 29.72 | 60.52 | 19.82 | 0.74 | 10.55 | 29.72 | 60.82 | 15.67 | 45
93 | BIRBHUM | SM/14981 | Demurtita Piped Water Supply Scheme. | TSM/016788 | 40036963 | New | MVS | GO2223013125PH | 04/02/2023 | 279.34 | 0 | 279.34 | Birbhum Division |  | 2.53 | 0 | 25 | 0 | 27.52 | 2.53 | 0 | 25 | 0 | 27.52 | 9.85 | 10
94 | BIRBHUM | SM/12670 | Deoash and Adjoining Mouzas PWSS | TSM/013165 | 40032454 | New | MVS | GO2223007819PH | 19/09/2022 | 604.15 | 38.85 | 643 | Birbhum Division | Bolpur Mechanical Division | 396.88 | 36.78 | 31.95 | 0 | 465.62 | 396.88 | 37.97 | 31.95 | 0 | 466.81 | 72.6 | 70
95 | BIRBHUM | SM/12832 | DERPUR PIPED WATER SUPPLY SCHEME. | TSM/011618 | 40033580 | New | MVS | GO2223008131PH | 22/09/2022 | 438.89 | 38.62 | 477.52 | Birbhum Division | Bolpur Mechanical Division | 252.32 | 34.6 | 23.39 | 44.91 | 355.22 | 252.32 | 34.6 | 23.39 | 44.91 | 355.22 | 74.39 | 80
96 | BIRBHUM | SM/15256 | Dhalla Piped Water Supply Scheme | TSM/015726 | 40039237 | New | MVS | GO2223013439PH | 07/02/2023 | 879.53 | 80.86 | 960.39 | Birbhum Division | Bolpur Mechanical Division | 5.73 | 22.39 | 68.85 | 0 | 96.96 | 5.73 | 22.39 | 68.85 | 0 | 96.96 | 10.1 | 35
97 | BIRBHUM | SM/14898 | Dhamara Piped Water Supply Scheme. | TSM/016240 | 40038398 | New | MVS | GO2223013097PH | 04/02/2023 | 431.69 | 39.51 | 471.2 | Birbhum Division | Bolpur Mechanical Division | 179.29 | 27.5 | 8.53 | 0 | 215.32 | 179.29 | 32.3 | 8.53 | 0 | 220.13 | 46.72 | 85
98 | BIRBHUM | SM/12688 | Dhananjaypur Piped Water Supply Scheme. | TSM/014564 | 40033234 | New | MVS | GO2223008014PH | 21/09/2022 | 663.08 | 37.97 | 701.06 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 31.3 | 0 | 31.3 | 0 | 0 | 31.3 | 0 | 31.3 | 4.46 | 5
99 | BIRBHUM | SM/18352 | DHANASAHA PIPED WATER SUPPLY SCHEME | TSM/015498 | 40034340 | New | MVS | 1796/PHE-28011/266/2022-SCHM CELL-Dept. of PHE | 11/07/2023 | 1160.78 | 41.32 | 1202.1 | Birbhum Division | Bolpur Mechanical Division | 32.83 | 3.52 | 176.31 | 53.89 | 266.55 | 32.83 | 3.52 | 176.31 | 53.89 | 266.55 | 22.17 | 25
100 | BIRBHUM | SM/17633 | Dhitora Right side and adjoining mouzas piped water supply scheme. | TSM/015508 | 40033830 | New | SVS | GO2223017450PH | 22/03/2023 | 408.19 | 37.76 | 445.95 | Birbhum Division | Bolpur Mechanical Division | 155.26 | 29.17 | 8.82 | 0 | 193.25 | 155.91 | 32.18 | 8.82 | 0 | 196.9 | 44.15 | 90
101 | BIRBHUM | SM/14746 | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | TSM/017017 | 40037062 | New | MVS | GO2223012673PH | 31/01/2023 | 841.19 | 158.02 | 999.21 | Birbhum Division | Bolpur Mechanical Division | 5.26 | 0 | 23.08 | 0 | 28.34 | 5.26 | 0 | 23.08 | 0 | 28.34 | 2.84 | 5
102 | BIRBHUM | SM/12689 | Dumugram piped water supply scheme. | TSM/014510 | 40033184 | New | MVS | GO2223008018PH | 21/09/2022 | 855.18 | 39.74 | 894.92 | Birbhum Division | Bolpur Mechanical Division | 218.35 | 28.68 | 11.89 | 0 | 258.92 | 218.35 | 28.68 | 11.89 | 0 | 258.92 | 28.93 | 60
103 | BIRBHUM | SM/14675 | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | TSM/016711 | 40038306 | New | MVS | GO2223012662PH | 31/01/2023 | 840.38 | 109.83 | 950.21 | Birbhum Division | Bolpur Mechanical Division | 38.95 | 11.98 | 32.87 | 0 | 83.8 | 38.95 | 11.98 | 32.87 | 0 | 83.8 | 8.82
104 | BIRBHUM | SM/12690 | Ekpara Piped Water Supply Scheme. | TSM/014680 | 40035165 | New | SVS | GO2223007950PH | 20/09/2022 | 254.06 | 35.49 | 289.55 | Birbhum Division | Bolpur Mechanical Division | 0 | 18.35 | 9.14 | 0 | 27.49 | 0 | 18.35 | 9.14 | 0 | 27.49 | 9.49 | 10
105 | BIRBHUM | SM/13949 | Ekura Piped Water Supply Scheme. | TSM/016748 | 40036931 | New | MVS | GO2223010355PH | 01/12/2022 | 461.93 | 0 | 461.93 | Birbhum Division | Bolpur Mechanical Division | 2.64 | 0 | 69.14 | 0 | 71.78 | 2.64 | 0 | 69.14 | 0 | 71.78 | 15.54 | 18
106 | BIRBHUM | SM/14971 | FARIDPUR PIPED WATER SUPPLY SCHEME | TSM/016785 | 40037057 | New | MVS | GO2223013092PH | 04/02/2023 | 567.5 | 157.74 | 725.24 | Birbhum Division | Bolpur Mechanical Division | 3.69 | 0 | 76.24 | 0 | 79.93 | 3.69 | 0 | 76.24 | 0 | 79.93 | 11.02 | 15
107 | BIRBHUM | SM/13477 | FEUGRAM PIPED WATER SUPPLY SCHEME | TSM/015471 | 40033995 | New | MVS | GO2223009222PH | 02/11/2022 | 660.69 | 153.12 | 813.8 | Birbhum Division | Bolpur Mechanical Division | 4.73 | 8.46 | 34.7 | 0 | 47.9 | 4.73 | 8.46 | 34.7 | 0 | 47.9 | 5.89 | 5
108 | BIRBHUM | SM/12691 | Gaganpur piped water supply scheme. | TSM/014511 | 40033545 | New | MVS | GO2223007948PH | 20/09/2022 | 873.7 | 39.66 | 913.35 | Birbhum Division | Bolpur Mechanical Division | 141.05 | 26.34 | 76.48 | 0 | 243.86 | 141.05 | 26.34 | 76.48 | 0 | 243.86 | 26.7 | 60
109 | BIRBHUM | SM/13712 | Gaytha Piped Water Supply Scheme | TSM/015546 | 40034133 | New | MVS | GO2223009720PH | 14/11/2022 | 455.4 | 77.77 | 533.16 | Birbhum Division | Bolpur Mechanical Division | 123.15 | 32 | 16.2 | 0 | 171.35 | 123.15 | 37.04 | 16.2 | 0 | 176.39 | 33.08 | 80
110 | BIRBHUM | SM/15528 | GOALDIHI PIPED WATER SUPPLY SCHEME | TSM/016090 | 40037150 | New | MVS | GO2223013869PH | 15/02/2023 | 367.17 | 155.94 | 523.1 | Birbhum Division | Central Mechanical Division | 3.03 | 0 | 10.34 | 0 | 13.37 | 3.03 | 0 | 10.34 | 0 | 13.37 | 2.56 | 5
111 | BIRBHUM | SM/13631 | Gokrui Piped Water Supply Scheme. | TSM/015224 | 40030009 | New | MVS | GO2223009591PH | 11/11/2022 | 349.91 | 76.87 | 426.79 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 60.12 | 0 | 60.12 | 0 | 0 | 60.12 | 0 | 60.12 | 14.09 | 16
112 | BIRBHUM | SM/14897 | GOPINATHPUR PIPED WATER SUPPLY SCHEME | TSM/016258 | 40037052 | New | MVS | GO2223013132PH | 04/02/2023 | 569.33 | 157.94 | 727.26 | Birbhum Division | Bolpur Mechanical Division | 3.7 | 0 | 18.71 | 1.68 | 24.09 | 3.7 | 0 | 18.71 | 1.68 | 24.09 | 3.31 | 5
113 | BIRBHUM | SM/15253 | GOPINATHPUR PIPED WATER SUPPLY SCHEME | TSM/015544 | 40034507 | New | MVS | GO2223013339PH | 06/02/2023 | 609.94 | 40.01 | 649.94 | Birbhum Division | Central Mechanical Division | 3.67 | 0 | 26.28 | 20.05 | 50 | 3.67 | 0.88 | 26.28 | 20.05 | 50.88 | 7.83 | 10
114 | BIRBHUM | SM/11906 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHICHUNRI AND OTHER 3 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010647 | 40026545 | New | MVS | GO2223006609PH | 22/08/2022 | 127 | 0 | 127 | Birbhum Division | Bolpur Mechanical Division | 100.03 | 0 | 0 | 0 | 100.03 | 100.03 | 0 | 0 | 0 | 100.03 | 78.76 | 90
115 | BIRBHUM | SM/11909 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR KATUNIA AND OTHER 2 NOS. MOUZAS UNDER MD. BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010627 | 40026550 | New | MVS | GO2223006618PH | 22/08/2022 | 102 | 0 | 102 | Birbhum Division | Bolpur Mechanical Division | 80.27 | 0 | 0 | 0 | 80.27 | 80.27 | 0 | 0 | 0 | 80.27 | 78.7 | 85
116 | BIRBHUM | SM/11901 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR NISHPARUN AND OTHER 4 NOS. MOUZAS UNDER RAMPURHAT-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010657 | 40026542 | New | MVS | GO2223006602PH | 22/08/2022 | 206 | 0 | 206 | Birbhum Division | Bolpur Mechanical Division | 104.19 | 0 | 0 | 0 | 104.19 | 106.74 | 0 | 0 | 0 | 106.74 | 51.81 | 60
117 | BIRBHUM | SM/11935 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR PARKANDI AND OTHER 7 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010653 | 40034454 | New | MVS | GO2223006656PH | 24/08/2022 | 313 | 0 | 313 | Birbhum Division | Bolpur Mechanical Division | 186.46 | 0 | 0 | 0 | 186.46 | 186.46 | 0 | 0 | 0 | 186.46 | 59.57 | 50
118 | BIRBHUM | SM/11904 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR SABASIDANGA AND OTHER 4 NOS. MOUZAS UNDER NALHATI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010636 | 40026531 | New | MVS | GO2223006605PH | 22/08/2022 | 189 | 0 | 189 | Birbhum Division | Bolpur Mechanical Division | 126.66 | 0 | 0 | 0 | 126.66 | 126.66 | 0 | 0 | 0 | 126.66 | 67.01 | 85
119 | BIRBHUM | SM/12074 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010610 | 40033981 | New | MVS | GO2223006995PH | 02/09/2022 | 998 | 0 | 998 | Birbhum Division | Bolpur Mechanical Division | 305.51 | 0 | 0 | 0 | 305.51 | 319.79 | 0 | 0 | 0 | 319.79 | 32.04 | 35
120 | BIRBHUM | SM/14038 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALPUR AND OTHER 5 NOS. MOUZAS UNDER NALHATI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010635 | 40034301 | New | MVS | GO2223010880PH | 12/12/2022 | 225 | 0 | 225 | Birbhum Division | Bolpur Mechanical Division | 20.58 | 0 | 0 | 0 | 20.58 | 20.58 | 0 | 0 | 0 | 20.58 | 9.15 | 50
121 | BIRBHUM | SM/11902 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMDAHARA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010668 | 40026527 | New | MVS | GO2223006603PH | 22/08/2022 | 754 | 0 | 754 | Birbhum Division | Bolpur Mechanical Division | 514.07 | 0 | 0 | 0 | 514.07 | 514.32 | 2.14 | 0 | 0 | 516.47 | 68.5 | 75
122 | BIRBHUM | SM/11936 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010642 | 40034402 | New | MVS | GO2223006655PH | 24/08/2022 | 394 | 0 | 394 | Birbhum Division | Bolpur Mechanical Division | 335.06 | 0 | 0 | 0 | 335.06 | 335.06 | 0 | 0 | 0 | 335.06 | 85.04 | 90
123 | BIRBHUM | SM/11908 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMRITAPUR AND MAJHARA MOUZAS UNDER MURARAI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010631 | 40026540 | New | MVS | GO2223006621PH | 22/08/2022 | 85 | 0 | 85 | Birbhum Division | Bolpur Mechanical Division | 2.8 | 0 | 0 | 0 | 2.8 | 2.8 | 0 | 0 | 0 | 2.8 | 3.3 | 10
124 | BIRBHUM | SM/11900 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010658 | 40026538 | New | MVS | GO2223006601PH | 22/08/2022 | 448 | 0 | 448 | Birbhum Division | Bolpur Mechanical Division | 286.38 | 0 | 0 | 0 | 286.38 | 286.38 | 0 | 0 | 0 | 286.38 | 63.92 | 90
125 | BIRBHUM | SM/11899 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BABUPUR AND OTHER 5 NOS. MOUZAS UNDER SURI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010667 | 40026537 | New | MVS | GO2223006600PH | 22/08/2022 | 222 | 0 | 222 | Birbhum Division | Bolpur Mechanical Division | 201.54 | 0 | 0 | 0 | 201.54 | 201.54 | 0 | 0 | 0 | 201.54 | 90.78 | 90
126 | BIRBHUM | SM/12068 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BAMUNDIHA AND OTHER 14 NOS. MOUZAS UNDER MD BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010621 | 40034198 | New | MVS | GO2223006994PH | 02/09/2022 | 541 | 0 | 541 | Birbhum Division | Bolpur Mechanical Division | 342.83 | 0 | 0 | 0 | 342.83 | 342.83 | 0 | 0 | 0 | 342.83 | 63.37 | 90
127 | BIRBHUM | SM/12070 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BISERGHATA AND OTHER 23 NOS. MOUZAS UNDER BOLPUR SRINIKETAN BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010616 | 40033933 | New | MVS | GO2223006996PH | 02/09/2022 | 901 | 0 | 901 | Birbhum Division | Bolpur Mechanical Division | 623.54 | 0 | 0 | 0 | 623.54 | 628.85 | 0 | 0 | 0 | 628.85 | 69.79 | 75
128 | BIRBHUM | SM/14043 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR CHANDANPUR AND OTHER 5 NOS. MOUZAS UNDER MURARAI-I & NALHATI-I BLOCKS UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010632 | 40034381 | New | MVS | GO2223010879PH | 12/12/2022 | 217 | 0 | 217 | Birbhum Division | Bolpur Mechanical Division | 100.42 | 0 | 0 | 0 | 100.42 | 100.42 | 0 | 0 | 0 | 100.42 | 46.28 | 45
129 | BIRBHUM | SM/11910 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR DHEKA AND OTHER 21 NOS. MOUZAS UNDER MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010620 | 40026553 | New | MVS | GO2223006610PH | 22/08/2022 | 840 | 0 | 840 | Birbhum Division | Bolpur Mechanical Division | 472.26 | 0 | 0 | 0 | 472.26 | 472.26 | 0 | 0 | 0 | 472.26 | 56.22 | 70
130 | BIRBHUM | SM/11903 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GANUTIA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010675 | 40026529 | New | MVS | GO2223006604PH | 22/08/2022 | 849 | 0 | 849 | Birbhum Division | Bolpur Mechanical Division | 571.45 | 0 | 0 | 0 | 571.45 | 571.45 | 0 | 0 | 0 | 571.45 | 67.31 | 75
131 | BIRBHUM | SM/11905 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GHOGAN AND OTHER 11 NOS. MOUZAS UNDER NANOOR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010639 | 40026534 | New | MVS | GO2223006606PH | 22/08/2022 | 458 | 0 | 458 | Birbhum Division | Bolpur Mechanical Division | 433.29 | 0 | 0 | 0 | 433.29 | 433.29 | 0 | 0 | 0 | 433.29 | 94.61 | 90
132 | BIRBHUM | SM/14037 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GOPALPUR AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010671 | 40060546 | New | MVS | GO2223010859PH | 12/12/2022 | 831.2 | 0 | 831.2 | Birbhum Division | Bolpur Mechanical Division | 259.74 | 0 | 0 | 0 | 259.74 | 261.06 | 0 | 0 | 0 | 261.06 | 31.41 | 80
133 | BIRBHUM | SM/14015 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR HARISHCHANDRAPUR AND OTHER 14 NOS. MOUZAS UNDER ILLAMBAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010612 | 40034022 | New | MVS | GO2223010496PH | 05/12/2022 | 570 | 0 | 570 | Birbhum Division | Bolpur Mechanical Division | 392.72 | 0 | 0 | 0 | 392.72 | 392.72 | 0 | 0 | 0 | 392.72 | 68.9 | 70
134 | BIRBHUM | SM/12073 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR MAJURIA AND OTHER 19 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010611 | 40034004 | New | MVS | GO2223006998PH | 02/09/2022 | 775 | 0 | 775 | Birbhum Division | Bolpur Mechanical Division | 281.43 | 0 | 0 | 0 | 281.43 | 281.43 | 0 | 0 | 0 | 281.43 | 36.31 | 65
135 | BIRBHUM | SM/11907 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR NAYIT AND OTHER 3 NOS. MOUZAS UNDER MURARAI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010629 | 40026536 | New | MVS | GO2223006607PH | 22/08/2022 | 151 | 0 | 151 | Birbhum Division | Bolpur Mechanical Division | 123.22 | 0 | 0 | 0 | 123.22 | 123.22 | 0 | 0 | 0 | 123.22 | 81.6 | 85
136 | BIRBHUM | SM/12072 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR SIMJURI AND OTHER 19 NOS. MOUZAS UNDER KHOYRASOLE BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010614 | 40060464 | New | MVS | GO2223006999PH | 02/09/2022 | 712 | 0 | 712 | Birbhum Division | Bolpur Mechanical Division | 348.78 | 0 | 0 | 0 | 348.78 | 348.78 | 0.71 | 0 | 0 | 349.49 | 49.09 | 50
137 | BIRBHUM | SM/14039 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR TALA AND OTHER 25 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010618 | 40060431 | New | MVS | GO2223010858PH | 12/12/2022 | 974.91 | 0 | 974.91 | Birbhum Division | Bolpur Mechanical Division | 361.68 | 0 | 0 | 0 | 361.68 | 361.68 | 0 | 0 | 0 | 361.68 | 37.1 | 30
138 | BIRBHUM | SM/12069 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010615 | 40034015 | New | MVS | GO2223007000PH | 02/09/2022 | 291 | 0 | 291 | Birbhum Division | Bolpur Mechanical Division | 146.21 | 0 | 0 | 0 | 146.21 | 146.21 | 0 | 0 | 0 | 146.21 | 50.24 | 80
139 | BIRBHUM | SM/12071 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UTTAR BHAGABATIPUR AND OTHER 8 NOS. MOUZAS UNDER MAYURESWAR-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | TSM/010619 | 40034071 | New | MVS | GO2223007001PH | 02/09/2022 | 343 | 0 | 343 | Birbhum Division | Bolpur Mechanical Division | 237.69 | 0 | 0 | 0 | 237.69 | 237.69 | 0 | 0 | 0 | 237.69 | 69.3 | 50
140 | BIRBHUM | SM/18419 | Gulalgachi Piped Supply Scheme | TSM/016743 | 40053978 | New | MVS | 1918/PHE-28011/237/2023-SCHM CELL-Dept. of PHE | 18/07/2023 | 1117.94 | 149.64 | 1267.58 | Birbhum Division | Bolpur Mechanical Division | 297.91 | 26.51 | 394.22 | 0 | 718.64 | 297.91 | 28.55 | 394.22 | 0 | 720.68 | 56.85 | 65
141 | BIRBHUM | SM/14900 | HANSAN PIPED WATER SUPPLY SCHEME | TSM/016218 | 40039548 | New | MVS | GO2223013143PH | 04/02/2023 | 819.81 | 80.86 | 900.67 | Birbhum Division | Bolpur Mechanical Division | 28.07 | 16.03 | 36.06 | 0 | 80.16 | 28.07 | 16.03 | 36.06 | 0 | 80.16 | 8.9 | 25
142 | BIRBHUM | SM/14028 | Haridaspur Piped Water Supply Scheme. | TSM/016071 | 40045435 | New | MVS | GO2223010479PH | 05/12/2022 | 916.22 | 60.91 | 977.13 | Birbhum Division | Bolpur Mechanical Division | 154.37 | 43.63 | 42.29 | 0 | 240.3 | 155.25 | 44.45 | 42.29 | 0 | 241.99 | 24.77 | 80
143 | BIRBHUM | SM/12692 | Harinduba Piped Water Supply Scheme. | TSM/014677 | 40033396 | New | MVS | GO2223007952PH | 20/09/2022 | 701.18 | 37.98 | 739.16 | Birbhum Division | Bolpur Mechanical Division | 42.93 | 0 | 26.33 | 0 | 69.26 | 42.93 | 0 | 26.33 | 0 | 69.26 | 9.37 | 10
144 | BIRBHUM | SM/14853 | Haripur Piped Water Supply Scheme | TSM/017492 | 40053970 | New | MVS | GO2223013004PH | 03/02/2023 | 934.11 | 0 | 934.11 | Birbhum Division |  | 5.4 | 0 | 313.76 | 0 | 319.16 | 5.4 | 0 | 313.76 | 0 | 319.16 | 34.17 | 35
145 | BIRBHUM | SM/16198 | Hatikata Piped Water Supply Scheme | TSM/017489 | 40054105 | New | MVS | GO2223014783PH | 23/02/2023 | 290.59 | 0 | 290.59 | Birbhum Division |  | 1.88 | 0 | 12.61 | 0 | 14.48 | 1.88 | 0 | 12.61 | 0 | 14.48 | 4.98 | 5
146 | BIRBHUM | SM/12893 | HATIKRA PIPED WATER SUPPLY SCHEME. | TSM/011731 | 40032886 | New | MVS | GO2223008148PH | 23/09/2022 | 420.46 | 40.26 | 460.73 | Birbhum Division | Bolpur Mechanical Division | 60.85 | 18.98 | 17.57 | 0 | 97.4 | 60.85 | 18.98 | 17.57 | 0 | 97.4 | 21.14 | 20
147 | BIRBHUM | SM/14115 | HATKALUA PIPED WATER SUPPLY SCHEME | TSM/016242 | 40037049 | New | MVS | GO2223011512PH | 02/01/2023 | 592.95 | 81.22 | 674.17 | Birbhum Division | Bolpur Mechanical Division | 80.15 | 8.62 | 18.71 | 0 | 107.48 | 80.15 | 8.62 | 18.71 | 0 | 107.48 | 15.94 | 20
148 | BIRBHUM | SM/14679 | Hazaripur Piped Water Supply Scheme | TSM/016143 | 40037114 | New | MVS | GO2223012724PH | 31/01/2023 | 676.59 | 88.34 | 764.93 | Birbhum Division | Bolpur Mechanical Division | 16.03 | 52.82 | 24.88 | 0 | 93.73 | 16.03 | 53.43 | 24.88 | 0 | 94.34 | 12.33 | 25
149 | BIRBHUM | SM/13639 | Ikshudhara piped water supply scheme. | TSM/015100 | 40033065 | New | MVS | GO2223009609PH | 11/11/2022 | 893.87 | 104.03 | 997.9 | Birbhum Division | Bolpur Mechanical Division | 416.38 | 55.96 | 121.48 | 35.51 | 629.34 | 416.38 | 55.96 | 121.48 | 35.51 | 629.34 | 63.07 | 60
150 | BIRBHUM | SM/12891 | Jashoda Piped Water Supply Scheme. | TSM/011728 | 40032251 | New | MVS | GO2223008152PH | 23/09/2022 | 324.99 | 38.97 | 363.96 | Birbhum Division | Bolpur Mechanical Division | 71.13 | 31.19 | 49.12 | 7.76 | 159.2 | 71.13 | 32.7 | 49.12 | 7.76 | 160.7 | 44.15 | 65
151 | BIRBHUM | SM/12837 | JIJIGRAM PIPED WATER SUPPLY SCHEME. | TSM/011735 | 40033470 | New | MVS | GO2223008124PH | 22/09/2022 | 860.33 | 40.04 | 900.37 | Birbhum Division | Bolpur Mechanical Division | 404.09 | 33.57 | 49.15 | 16.54 | 503.35 | 405.03 | 36.57 | 49.15 | 16.54 | 507.29 | 56.34
152 | BIRBHUM | SM/12902 | JIUI PIPED WATER SUPPLY SCHEME. | TSM/013013 | 40032343 | New | MVS | GO2223008085PH | 22/09/2022 | 560.25 | 38.85 | 599.1 | Birbhum Division | Bolpur Mechanical Division | 157.91 | 22.15 | 15.76 | 0 | 195.82 | 157.91 | 25.12 | 15.76 | 0 | 198.79 | 33.18 | 75
153 | BIRBHUM | SM/12593 | JOGAI PIPED WATER SUPPLY SCHEME. | TSM/013063 | 40033508 | New | MVS | GO2223007726PH | 15/09/2022 | 474.41 | 40.37 | 514.78 | Birbhum Division | Bolpur Mechanical Division | 187.3 | 6.41 | 8.55 | 0 | 202.26 | 188.49 | 9.55 | 8.55 | 0 | 206.6 | 40.13 | 75
154 | BIRBHUM | SM/13016 | Kachujore Piped Water Supply Scheme. | TSM/011736 | 40032915 | New | MVS | GO2223008383PH | 28/09/2022 | 137.33 | 36.17 | 173.49 | Birbhum Division | Bolpur Mechanical Division | 62.71 | 31.47 | 9.99 | 0 | 104.18 | 62.71 | 32.96 | 9.99 | 0 | 105.66 | 60.9 | 60
155 | BIRBHUM | SM/14668 | KADOA PIPED WAYER SUPPLY SCHEME | TSM/017099 | 40037065 | New | MVS | GO2223012670PH | 31/01/2023 | 436.4 | 157.94 | 594.33 | Birbhum Division | Bolpur Mechanical Division | 2.94 | 0 | 34.58 | 0 | 37.52 | 2.94 | 0 | 34.58 | 0 | 37.52 | 6.31 | 10
156 | BIRBHUM | SM/12887 | KAHINAGAR PIPED WATER SUPPLY SCHME | TSM/012842 | 40033149 | New | MVS | GO2223008162PH | 23/09/2022 | 768.11 | 38.97 | 807.08 | Birbhum Division | Bolpur Mechanical Division | 2.82 | 0 | 9.24 | 0 | 12.05 | 2.82 | 0 | 9.24 | 0 | 12.05 | 1.49 | 5
157 | BIRBHUM | SM/12675 | KAMARDANGAL PIPED WATER SUPPLY SCHEME. | TSM/011615 | 40032944 | New | MVS | GO2223007807PH | 19/09/2022 | 201.81 | 36.28 | 238.09 | Birbhum Division | Bolpur Mechanical Division | 91.79 | 23.7 | 15.77 | 0 | 131.25 | 91.79 | 23.7 | 15.77 | 0 | 131.25 | 55.13 | 65
158 | BIRBHUM | SM/12693 | Kamarkhul Piped Water Supply Scheme. | TSM/014527 | 40033550 | New | MVS | GO2223008020PH | 21/09/2022 | 726.97 | 39.35 | 766.32 | Birbhum Division | Bolpur Mechanical Division | 31.12 | 15.86 | 0 | 0 | 46.98 | 31.12 | 17.07 | 0 | 0 | 48.19 | 6.29 | 40
159 | BIRBHUM | SM/12694 | Kamdebnala piped water supply scheme. | TSM/014536 | 40033227 | New | MVS | GO2223008016PH | 21/09/2022 | 440.57 | 35.62 | 476.19 | Birbhum Division | Bolpur Mechanical Division | 124.64 | 27.97 | 12.43 | 0 | 165.04 | 124.64 | 28.58 | 12.43 | 0 | 165.65 | 34.79 | 80
160 | BIRBHUM | SM/12672 | KANAIPUR and Adjoining Mouzas PWSS | TSM/014137 | 40032518 | New | MVS | GO2223007818PH | 19/09/2022 | 805.42 | 38.97 | 844.4 | Birbhum Division | Bolpur Mechanical Division | 357.04 | 31.15 | 13.76 | 0 | 401.95 | 357.04 | 31.15 | 13.76 | 0 | 401.95 | 47.6 | 80
161 | BIRBHUM | SM/18489 | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | TSM/017162 | 40067386 | New | MVS | PHE/IV/2002/W-618/23 | 24/07/2023 | 708.41 | 105.77 | 814.18 | Birbhum Division | Bolpur Mechanical Division | 67.19 | 51.32 | 0 | 0 | 118.5 | 67.19 | 53.05 | 0 | 0 | 120.23 | 14.77 | 30
162 | BIRBHUM | SM/13640 | Kanaipur piped water supply scheme. | TSM/015178 | 40034053 | New | MVS | GO2223009608PH | 11/11/2022 | 709.21 | 91.99 | 801.2 | Birbhum Division | Bolpur Mechanical Division | 143.24 | 60.23 | 63.42 | 0 | 266.88 | 143.24 | 61.14 | 63.42 | 0 | 267.79 | 33.42 | 60
163 | BIRBHUM | SM/14824 | Kanduri Piped Water Supply Scheme. | TSM/016079 | 40037311 | New | MVS | GO2223013045PH | 04/02/2023 | 504.04 | 39.08 | 543.12 | Birbhum Division | Bolpur Mechanical Division | 25 | 7.85 | 21.25 | 0 | 54.1 | 25 | 7.85 | 21.25 | 0 | 54.1 | 9.96 | 32
164 | BIRBHUM | SM/12831 | KANIOR PIPED WATER SUPPLY SCHEME. | TSM/011616 | 40032536 | New | MVS | GO2223008132PH | 22/09/2022 | 559.26 | 41.53 | 600.79 | Birbhum Division | Bolpur Mechanical Division | 272.62 | 29.69 | 14.24 | 0 | 316.56 | 273.85 | 32.7 | 14.24 | 0 | 320.79 | 53.39 | 80
165 | BIRBHUM | SM/18518 | Kankalitala piped water supply scheme. | TSM/015186 | 40033631 | New | MVS | 2045/PHE-28011/211/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1083.86 | 90.84 | 1174.7 | Birbhum Division | Bolpur Mechanical Division | 199.53 | 72.63 | 199.67 | 18.71 | 490.54 | 199.53 | 73.05 | 199.67 | 18.71 | 490.96 | 41.79 | 70
166 | BIRBHUM | SM/14119 | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | TSM/016201 | 40037645 | New | MVS | GO2223011514PH | 02/01/2023 | 318.16 | 80.86 | 399.02 | Birbhum Division | Bolpur Mechanical Division | 106.29 | 29.85 | 7.62 | 0 | 143.76 | 107.49 | 32.85 | 7.62 | 0 | 147.97 | 37.08 | 78
167 | BIRBHUM | SM/13713 | Kasba Piped Water Supply Scheme. | TSM/015558 | 40033655 | New | MVS | GO2223009717PH | 14/11/2022 | 741.71 | 38.1 | 779.81 | Birbhum Division | Bolpur Mechanical Division | 4.29 | 8.98 | 11.94 | 27.85 | 53.07 | 4.29 | 8.98 | 11.94 | 27.85 | 53.07 | 6.81 | 25
168 | BIRBHUM | SM/12903 | KASHERHAT PIPED WATER SUPPLY SCHEME. | TSM/012814 | 40032394 | New | MVS | GO2223008081PH | 22/09/2022 | 539.91 | 38.97 | 578.88 | Birbhum Division | Bolpur Mechanical Division | 199.88 | 33.88 | 20.98 | 0 | 254.74 | 199.88 | 37.19 | 20.98 | 0 | 258.04 | 44.58 | 60
169 | BIRBHUM | SM/12595 | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | TSM/013068 | 40033512 | New | MVS | GO2223007731PH | 15/09/2022 | 844.87 | 41.29 | 886.16 | Birbhum Division | Bolpur Mechanical Division | 175.52 | 31.1 | 11.94 | 0 | 218.56 | 175.52 | 31.99 | 11.94 | 0 | 219.46 | 24.77 | 65
170 | BIRBHUM | SM/18733 | Kashtagara Piped Water Supply Scheme. | TSM/016499 | 40037431 | New | MVS | 2364/PHE-28011/63/2023-ESTT CELL-Dept. of PHE | 14/08/2023 | 1184.05 | 78.36 | 1262.41 | Birbhum Division | Bolpur Mechanical Division | 0 | 6.21 | 11.09 | 0 | 17.3 | 0 | 6.21 | 11.09 | 0 | 17.3 | 1.37 | 5
171 | BIRBHUM | SM/13641 | Kayera Water Supply Scheme | TSM/015495 | 40033664 | New | MVS | GO2223009631PH | 11/11/2022 | 449.28 | 38.95 | 488.23 | Birbhum Division | Bolpur Mechanical Division | 58.91 | 6.37 | 11.76 | 31.19 | 108.22 | 58.91 | 6.37 | 11.76 | 31.19 | 108.22 | 22.17 | 45
172 | BIRBHUM | SM/13642 | Kendangal Piped Water Supply Scheme. | TSM/015607 | 40034704 | New | MVS | GO2223009599PH | 11/11/2022 | 582.82 | 37.97 | 620.79 | Birbhum Division | Bolpur Mechanical Division | 55.89 | 3.31 | 15.15 | 56.34 | 130.68 | 55.89 | 5.18 | 15.15 | 56.34 | 132.55 | 21.35 | 40
173 | BIRBHUM | SM/14676 | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | TSM/016205 | 40038244 | New | MVS | GO2223012750PH | 31/01/2023 | 354.78 | 80.86 | 435.64 | Birbhum Division | Bolpur Mechanical Division | 133.7 | 31.77 | 12.03 | 0 | 177.5 | 133.7 | 32.37 | 12.03 | 0 | 178.11 | 40.88 | 58
174 | BIRBHUM | SM/13980 | Khamedda Piped Water Supply Scheme | TSM/015742 | 40039472 | New | MVS | GO2223010284PH | 01/12/2022 | 659.34 | 77.77 | 737.11 | Birbhum Division | Bolpur Mechanical Division | 4.37 | 28.67 | 9.09 | 0 | 42.12 | 4.37 | 31.67 | 9.09 | 0 | 45.13 | 6.12 | 45
175 | BIRBHUM | SM/14085 | Khanpur Piped Water Supply Scheme. | TSM/015753 | 40060407 | New | MVS | GO2223010895PH | 12/12/2022 | 807.62 | 39.16 | 846.77 | Birbhum Division | Bolpur Mechanical Division | 187.67 | 3.35 | 17.4 | 0 | 208.41 | 187.67 | 4.24 | 17.4 | 0 | 209.31 | 24.72 | 5
176 | BIRBHUM | SM/13539 | Khanpur piped water supply scheme. | TSM/015101 | 40034827 | New | MVS | GO2223009379PH | 04/11/2022 | 785.48 | 89.95 | 875.43 | Birbhum Division | Bolpur Mechanical Division | 193.04 | 47.42 | 111.03 | 0 | 351.49 | 193.04 | 48.03 | 111.03 | 0 | 352.1 | 40.22 | 80
177 | BIRBHUM | SM/14677 | KHAYERBANI PIPED WATER SUPPLY SCHEME | TSM/016217 | 40037018 | New | MVS | GO2223012747PH | 31/01/2023 | 365.16 | 157.74 | 522.91 | Birbhum Division | Bolpur Mechanical Division | 2.53 | 0 | 25.36 | 0 | 27.89 | 2.53 | 0 | 25.36 | 0 | 27.89 | 5.33 | 5
178 | BIRBHUM | SM/12894 | KOGRAM PIPED WATER SUPPLY SCHEME. | TSM/012811 | 40033564 | New | MVS | GO2223008161PH | 23/09/2022 | 682.46 | 38.97 | 721.43 | Birbhum Division | Bolpur Mechanical Division | 304.63 | 24.69 | 10.69 | 0 | 340.01 | 305.54 | 26.35 | 10.69 | 0 | 342.58 | 47.49 | 60
179 | BIRBHUM | SM/13601 | Kukutia piped water supply scheme. | TSM/015187 | 40034883 | New | MVS | GO2223009526PH | 09/11/2022 | 470.76 | 78.84 | 549.6 | Birbhum Division | Bolpur Mechanical Division | 0 | 8.54 | 74.96 | 0 | 83.49 | 0 | 8.54 | 74.96 | 0 | 83.49 | 15.19 | 15
180 | BIRBHUM | SM/12695 | Kulara Piped Water Supply Scheme. | TSM/014400 | 40033518 | New | MVS | GO2223008006PH | 21/09/2022 | 442.95 | 38.64 | 481.59 | Birbhum Division | Bolpur Mechanical Division | 142.28 | 31.62 | 7.59 | 0 | 181.49 | 142.28 | 31.62 | 7.59 | 0 | 181.49 | 37.69 | 60
181 | BIRBHUM | SM/14743 | KURUMBA PIPED WATER SUPPLY SCHEME | TSM/016231 | 40037035 | New | MVS | GO2223012672PH | 31/01/2023 | 592.81 | 81.22 | 674.03 | Birbhum Division | Bolpur Mechanical Division | 10.78 | 5.57 | 51.71 | 0 | 68.06 | 10.78 | 5.57 | 51.71 | 0 | 68.06 | 10.1 | 10
182 | BIRBHUM | SM/13628 | Kurumsaha Piped Water Supply Scheme. | TSM/011725 | 40034237 | New | MVS | GO2223009645PH | 11/11/2022 | 263.19 | 38.53 | 301.71 | Birbhum Division | Bolpur Mechanical Division | 120.85 | 31.75 | 19.64 | 18.08 | 190.32 | 120.85 | 34.69 | 19.64 | 18.08 | 193.27 | 64.06 | 80
183 | BIRBHUM | SM/12599 | KUSHIPUR PIPES WATER SUPPLY SCHEME. | TSM/012847 | 40033573 | New | MVS | GO2223007723PH | 15/09/2022 | 628.16 | 38.85 | 667.02 | Birbhum Division | Bolpur Mechanical Division | 245.36 | 37.61 | 6.46 | 0 | 289.42 | 246.27 | 37.61 | 6.46 | 0 | 290.34 | 43.53 | 60
184 | BIRBHUM | SM/18362 | Kusumba Piped Water Supply Scheme. | TSM/016784 | 40037118 | New | MVS | 1799/PHE-28011/63/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1092.57 | 80.66 | 1173.23 | Birbhum Division | Bolpur Mechanical Division | 0 | 28.33 | 35.72 | 0 | 64.05 | 0 | 28.33 | 35.72 | 0 | 64.05 | 5.46 | 8
185 | BIRBHUM | SM/14125 | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | TSM/015474 | 40033748 | New | MVS | GO2223011501PH | 02/01/2023 | 979.3 | 131.6 | 1110.9 | Birbhum Division | Bolpur Mechanical Division | 172.64 | 53.05 | 110.15 | 0 | 335.83 | 172.64 | 59.46 | 110.15 | 0 | 342.24 | 30.81 | 90
186 | BIRBHUM | SM/12696 | Lakshmi Narayanpur and Adjoining Mouzas PWSS | TSM/014827 | 40033326 | New | MVS | GO2223008036PH | 21/09/2022 | 756.04 | 90.93 | 846.97 | Birbhum Division | Bolpur Mechanical Division | 0 | 3.2 | 163.79 | 0 | 166.99 | 0 | 3.2 | 163.79 | 0 | 166.99 | 19.72 | 25
187 | BIRBHUM | SM/18361 | LAYEKPUR PIPED WATER SUPPLY SCHEME | TSM/016003 | 40033002 | New | MVS | 1798/PHE-28011/42/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 996.1 | 221.15 | 1217.25 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | BIRBHUM | SM/18511 | Loba Piped Water Supply Scheme. | TSM/016238 | 40036879 | New | MVS | 2043/PHE-28011/277/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 2219.3 | 163.18 | 2382.48 | Birbhum Division | Bolpur Mechanical Division | 230.59 | 86.57 | 428.87 | 0 | 746.03 | 230.59 | 86.57 | 428.87 | 0 | 746.03 | 31.31 | 25
189 | BIRBHUM | SM/15255 | MADDA PIPED WATER SUPPLY SCHEME | TSM/016100 | 40037191 | New | MVS | GO2223013443PH | 07/02/2023 | 483.62 | 155.94 | 639.56 | Birbhum Division | Central Mechanical Division | 3.72 | 0 | 8.55 | 0 | 12.26 | 3.72 | 0 | 8.55 | 0 | 12.26 | 1.92 | 5
190 | BIRBHUM | SM/13644 | Madhupur Water Supply Scheme | TSM/015317 | 40034075 | New | MVS | GO2223009596PH | 11/11/2022 | 598.55 | 77.77 | 676.32 | Birbhum Division | Bolpur Mechanical Division | 27.27 | 9.64 | 67.47 | 0 | 104.39 | 27.27 | 9.64 | 67.47 | 0 | 104.39 | 15.44 | 25
191 | BIRBHUM | SM/12671 | Madhura and Adjoining mouzas PWSS | TSM/013124 | 40033574 | New | MVS | GO2223007817PH | 19/09/2022 | 742.06 | 38.73 | 780.79 | Birbhum Division | Bolpur Mechanical Division | 274.95 | 25.11 | 110.4 | 0 | 410.46 | 274.95 | 28.11 | 110.4 | 0 | 413.46 | 52.95 | 80
192 | BIRBHUM | SM/18510 | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | TSM/016204 | 40045415 | New | MVS | 2043/PHE-28011/277/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1051.9 | 136.5 | 1188.4 | Birbhum Division | Bolpur Mechanical Division | 49.04 | 23.73 | 62.53 | 0 | 135.29 | 49.04 | 23.73 | 62.53 | 0 | 135.29 | 11.38 | 19
193 | BIRBHUM | SM/15254 | MAHESWARPUR PIPED WATER SUPPLY SCHEME | TSM/015545 | 40034514 | New | MVS | GO2223013338PH | 06/02/2023 | 432.68 | 39.01 | 471.69 | Birbhum Division | Bolpur Mechanical Division | 52.15 | 14.01 | 20.71 | 54.43 | 141.31 | 52.15 | 14.01 | 20.71 | 54.43 | 141.31 | 29.96 | 30
194 | BIRBHUM | SM/12697 | Mahurapur and Adjoining Mouzas PWSS | TSM/013256 | 40033170 | New | MVS | GO2223008009PH | 21/09/2022 | 1025.14 | 41.5 | 1066.63 | Birbhum Division | Bolpur Mechanical Division | 78.84 | 11.81 | 49.31 | 0 | 139.97 | 78.84 | 11.81 | 49.31 | 0 | 139.97 | 13.12 | 50
195 | BIRBHUM | SM/12698 | Majhara piped water supply scheme | TSM/014508 | 40033539 | New | MVS | GO2223008034PH | 21/09/2022 | 408.04 | 35.57 | 443.6 | Birbhum Division | Bolpur Mechanical Division | 0 | 25.15 | 17.77 | 0 | 42.92 | 0 | 25.15 | 17.77 | 0 | 42.92 | 9.68 | 20
196 | BIRBHUM | SM/12838 | MAJHKALITHA PIPED WATER SUPPLY SCHEME. | TSM/011737 | 40032498 | New | MVS | GO2223008123PH | 22/09/2022 | 958.96 | 40.49 | 999.45 | Birbhum Division | Bolpur Mechanical Division | 211.45 | 6.22 | 11.36 | 0 | 229.03 | 211.45 | 6.22 | 11.36 | 0 | 229.03 | 22.92 | 55
197 | BIRBHUM | SM/14896 | Majhkanda Piped Water Supply Scheme. | TSM/016377 | 40037332 | New | MVS | GO2223013044PH | 04/02/2023 | 614.55 | 39.29 | 653.84 | Birbhum Division | Bolpur Mechanical Division | 0 | 17.15 | 28.72 | 0 | 45.86 | 0 | 17.15 | 28.72 | 0 | 45.86 | 7.01 | 10
198 | BIRBHUM | SM/13632 | Majuria Piped Water Supply Scheme. | TSM/015230 | 40034911 | New | MVS | GO2223009592PH | 11/11/2022 | 905.67 | 92.82 | 998.5 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 191.87 | 0 | 191.87 | 0 | 0 | 191.87 | 0 | 191.87 | 19.22 | 21
199 | BIRBHUM | SM/18509 | MANIKPUR PIPED WATER SUPPLY SCHEME | TSM/016147 | 40036996 | New | MVS | 2043/PHE-28011/277/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1041.87 | 83.85 | 1125.72 | Birbhum Division | Bolpur Mechanical Division | 0 | 6.1 | 100.48 | 32.43 | 139.02 | 0 | 6.1 | 100.48 | 32.43 | 139.02 | 12.35 | 10
200 | BIRBHUM | SM/18463 | Masra Piped Water Supply Scheme. | TSM/016741 | 40037441 | New | MVS | 1964/PHE-28011/56/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 1126.1 | 80.66 | 1206.76 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
201 | BIRBHUM | SM/16275 | MASTALI PIPED WATER SUPPLY SCHEME | TSM/017207 | 40053976 | New | MVS | GO2223014785PH | 23/02/2023 | 405.37 | 81.22 | 486.59 | Birbhum Division | Bolpur Mechanical Division | 128.13 | 9.19 | 0 | 26.35 | 163.67 | 128.13 | 9.19 | 0 | 26.35 | 163.67 | 33.63 | 40
202 | BIRBHUM | SM/13627 | Math Basori Piped Water Supply Scheme. | TSM/011723 | 40033871 | New | SVS | GO2223009649PH | 11/11/2022 | 524.05 | 40.25 | 564.3 | Birbhum Division | Bolpur Mechanical Division | 40.86 | 26.35 | 16.57 | 0 | 83.77 | 43.29 | 29.95 | 16.57 | 0 | 89.81 | 15.92 | 50
203 | BIRBHUM | SM/12674 | MATIARA PIPED WATER SUPPLY SCHEME. | TSM/014264 | 40032254 | New | MVS | GO2223007820PH | 19/09/2022 | 348.28 | 38.64 | 386.92 | Birbhum Division | Bolpur Mechanical Division | 2.66 | 20.85 | 12.56 | 0 | 36.07 | 2.66 | 20.85 | 12.56 | 0 | 36.07 | 9.32 | 55
204 | BIRBHUM | SM/13643 | MATIKONA PIPED WATER SUPPLY SCHEME | TSM/015501 | 40034458 | New | MVS | GO2223009637PH | 11/11/2022 | 819.72 | 41.11 | 860.82 | Birbhum Division | Bolpur Mechanical Division | 9.55 | 3.04 | 13.79 | 54.53 | 80.91 | 9.55 | 3.65 | 13.79 | 54.53 | 81.52 | 9.47 | 10
205 | BIRBHUM | SM/16273 | Mayandal Piped Water Supply Scheme | TSM/017491 | 40054104 | New | MVS | GO2223014784PH | 23/02/2023 | 158.49 | 0 | 158.49 | Birbhum Division |  | 1.22 | 0 | 10.59 | 0 | 11.82 | 1.22 | 0 | 10.59 | 0 | 11.82 | 7.46 | 8
206 | BIRBHUM | SM/12457 | Meherpur and Adjoining Mouzas PWSS | TSM/013178 | 40033593 | New | MVS | GO2223007610PH | 13/09/2022 | 449.55 | 38.53 | 488.08 | Birbhum Division | Bolpur Mechanical Division | 0 | 17.81 | 30.87 | 0 | 48.68 | 0 | 17.81 | 30.87 | 0 | 48.68 | 9.97 | 12
207 | BIRBHUM | SM/12699 | Melanpur Piped Water Supply Scheme. | TSM/014519 | 40032370 | New | MVS | GO2223008011PH | 21/09/2022 | 485.1 | 37.64 | 522.74 | Birbhum Division | Bolpur Mechanical Division | 199.32 | 29.84 | 18.51 | 0 | 247.67 | 199.32 | 29.84 | 18.51 | 0 | 247.67 | 47.38 | 85
208 | BIRBHUM | SM/12700 | Metegaon and Adjoining Mouzas PWSS | TSM/014822 | 40033302 | New | MVS | GO2223008039PH | 21/09/2022 | 575.61 | 78.16 | 653.76 | Birbhum Division | Bolpur Mechanical Division | 9.2 | 0 | 111.5 | 0 | 120.69 | 9.2 | 0 | 111.5 | 0 | 120.69 | 18.46 | 20
209 | BIRBHUM | SM/12892 | MITRAPUR WATER SUPPLY SCHEME. | TSM/011730 | 40033415 | New | SVS | GO2223008149PH | 23/09/2022 | 1128.93 | 41.29 | 1170.21 | Birbhum Division | Bolpur Mechanical Division | 9.82 | 17.06 | 73.98 | 0 | 100.86 | 9.82 | 19.18 | 73.98 | 0 | 102.98 | 8.8 | 45
210 | BIRBHUM | SM/13517 | Modapa Piped Water Supply Scheme. | TSM/015577 | 40033698 | New | MVS | GO2223009224PH | 02/11/2022 | 327.18 | 18.89 | 346.07 | Birbhum Division | Bolpur Mechanical Division | 186.47 | 18.1 | 12.65 | 0 | 217.22 | 186.47 | 19.87 | 12.65 | 0 | 218.99 | 63.28 | 80
211 | BIRBHUM | SM/14450 | MONACHITURA PIPED WATER SUPPLY SCHEME | TSM/017000 | 40037059 | New | MVS | GO2223012282PH | 20/01/2023 | 688.91 | 158.02 | 846.93 | Birbhum Division | Bolpur Mechanical Division | 4.39 | 0 | 0 | 0 | 4.39 | 4.39 | 0 | 0 | 0 | 4.39 | 0.52 | 5
212 | BIRBHUM | SM/12701 | Monai Piped Water Supply Scheme. | TSM/014521 | 40031823 | New | MVS | GO2223007951PH | 20/09/2022 | 399.48 | 37.78 | 437.26 | Birbhum Division | Bolpur Mechanical Division | 99.74 | 33.29 | 20.39 | 0 | 153.42 | 99.74 | 33.43 | 20.39 | 0 | 153.56 | 35.12 | 80
213 | BIRBHUM | SM/13511 | Monoharpur Piped Water Supply Scheme. | TSM/015578 | 40034652 | New | MVS | GO2223009257PH | 02/11/2022 | 353.73 | 37.9 | 391.63 | Birbhum Division | Bolpur Mechanical Division | 0 | 6.81 | 16.04 | 55.5 | 78.35 | 0 | 6.81 | 16.04 | 55.5 | 78.35 | 20.01 | 15
214 | BIRBHUM | SM/18519 | Mostala Piped Water Supply Scheme. | TSM/015094 | 40033043 | New | MVS | 2045/PHE-28011/211/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1098.23 | 111.77 | 1209.99 | Birbhum Division | Bolpur Mechanical Division | 121.73 | 70.64 | 133.52 | 43.84 | 369.72 | 121.73 | 70.64 | 133.52 | 43.84 | 369.72 | 30.56 | 35
215 | BIRBHUM | SM/14899 | Moubelia Piped Water Supply Scheme. | TSM/016241 | 40045493 | New | MVS | GO2223013094PH | 04/02/2023 | 372.49 | 37.17 | 409.66 | Birbhum Division | Bolpur Mechanical Division | 244.99 | 31.78 | 13.19 | 0 | 289.96 | 246.02 | 32.4 | 13.19 | 0 | 291.61 | 71.18 | 85
216 | BIRBHUM | SM/13646 | Nabagram Piped Water Supply Scheme. | TSM/015339 | 40034115 | New | MVS | GO2223009597PH | 11/11/2022 | 550.64 | 77.77 | 628.41 | Birbhum Division | Bolpur Mechanical Division | 86.7 | 23.53 | 24.16 | 0 | 134.39 | 86.7 | 26.52 | 24.16 | 0 | 137.38 | 21.86 | 28
217 | BIRBHUM | SM/12673 | Nanubazar Piped Water Supply Scheme | TSM/014273 | 40032360 | New | MVS | GO2223007822PH | 19/09/2022 | 576.77 | 38.77 | 615.54 | Birbhum Division | Bolpur Mechanical Division | 0 | 20.29 | 126.25 | 0 | 146.54 | 0 | 20.29 | 126.25 | 0 | 146.54 | 23.81 | 25
218 | BIRBHUM | SM/12904 | Naoadangal and Adjoining Mouzas PWSS | TSM/014825 | 40033314 | New | MVS | GO2223008087PH | 22/09/2022 | 642.88 | 79.16 | 722.04 | Birbhum Division | Bolpur Mechanical Division | 161.13 | 39.73 | 241.71 | 0 | 442.57 | 161.13 | 39.73 | 241.71 | 0 | 442.57 | 61.29 | 70
219 | BIRBHUM | SM/13625 | NARAYANPUR PIPED WATER SUPPLY SCHEME. | TSM/011617 | 40034183 | New | MVS | GO2223009642PH | 11/11/2022 | 487.26 | 38.4 | 525.66 | Birbhum Division | Bolpur Mechanical Division | 0 | 27.66 | 66.37 | 0 | 94.03 | 0 | 30.59 | 66.37 | 0 | 96.96 | 18.44 | 60
220 | BIRBHUM | SM/14682 | NAWADA PALANDI PIPED WATER SUPPLY SCHEME | TSM/016083 | 40037143 | New | MVS | GO2223012765PH | 31/01/2023 | 873.13 | 155.94 | 1029.06 | Birbhum Division | Bolpur Mechanical Division | 5.57 | 0 | 37.59 | 0 | 43.16 | 5.57 | 0 | 37.59 | 0 | 43.16 | 4.19 | 5
221 | BIRBHUM | SM/13479 | Nawapara Piped Water Supply Scheme | TSM/015458 | 40033951 | New | MVS | GO2223009253PH | 02/11/2022 | 631.7 | 88.34 | 720.04 | Birbhum Division | Bolpur Mechanical Division | 135.35 | 24.57 | 45.25 | 0 | 205.17 | 135.35 | 24.57 | 45.25 | 0 | 205.17 | 28.49 | 40
222 | BIRBHUM | SM/12656 | NETURI PIPED WATER SUPPLY SCHEME. | TSM/011612 | 40032256 | New | MVS | GO2223007810PH | 19/09/2022 | 457.13 | 38.97 | 496.1 | Birbhum Division | Bolpur Mechanical Division | 316.48 | 37.6 | 10.81 | 17.08 | 381.96 | 316.48 | 39.69 | 10.81 | 17.08 | 384.05 | 77.41 | 85
223 | BIRBHUM | SM/16271 | Nichinta Piped Water Supply Scheme (Khoyrasole Block) | TSM/017782 | 40053980 | New | MVS | GO2223014879PH | 24/02/2023 | 145.99 | 0 | 145.99 | Birbhum Division |  | 0.82 | 0 | 0 | 0 | 0.82 | 0.82 | 0 | 0 | 0 | 0.82 | 0.56 | 8
224 | BIRBHUM | SM/14089 | Ninga Piped Water Supply Scheme | TSM/015711 | 40039204 | New | MVS | GO2223010844PH | 12/12/2022 | 766.58 | 77.77 | 844.34 | Birbhum Division | Bolpur Mechanical Division | 5.06 | 0 | 57.11 | 0 | 62.17 | 5.06 | 0 | 57.11 | 0 | 62.17 | 7.36 | 3
225 | BIRBHUM | SM/14854 | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) | TSM/017490 | 40053971 | New | MVS | GO2223013007PH | 03/02/2023 | 582.15 | 0 | 582.15 | Birbhum Division |  | 34.59 | 0 | 92.93 | 0 | 127.52 | 34.59 | 0 | 92.93 | 0 | 127.52 | 21.9 | 20
226 | BIRBHUM | SM/12905 | Nohana and Adjoining Mouzas PWSS | TSM/013127 | 40033591 | New | MVS | GO2223008086PH | 22/09/2022 | 282.55 | 18.71 | 301.26 | Birbhum Division | Bolpur Mechanical Division | 100.85 | 11.95 | 9.49 | 0 | 122.29 | 100.85 | 11.95 | 9.49 | 0 | 122.29 | 40.59 | 62
227 | BIRBHUM | SM/13645 | NOHNA PIPED WATER SUPPLY SCHEME | TSM/015499 | 40034357 | New | MVS | GO2223009633PH | 11/11/2022 | 773.38 | 40.01 | 813.39 | Birbhum Division | Bolpur Mechanical Division | 105.15 | 18 | 123.73 | 54.96 | 301.82 | 105.15 | 18 | 123.73 | 54.96 | 301.82 | 37.11 | 40
228 | BIRBHUM | SM/14544 | Paduma Piped Water Supply Scheme. | TSM/015096 | 40034781 | New | MVS | GO2223012604PH | 30/01/2023 | 1510.56 | 101.36 | 1611.92 | Birbhum Division | Bolpur Mechanical Division | 60.89 | 48.67 | 0 | 0 | 109.55 | 60.89 | 48.67 | 0 | 0 | 109.55 | 6.8 | 30
229 | BIRBHUM | SM/12669 | Paikpara Piped Water Supply Scheme. | TSM/014279 | 40060535 | New | MVS | GO2223007821PH | 19/09/2022 | 318.83 | 36.28 | 355.1 | Birbhum Division | Bolpur Mechanical Division | 116.72 | 25.02 | 6.95 | 0 | 148.69 | 116.72 | 27.13 | 6.95 | 0 | 150.8 | 42.47 | 90
230 | BIRBHUM | SM/12836 | PAIKPARA WATER SUPPLY SCHEME. | TSM/011726 | 40033557 | New | MVS | GO2223008127PH | 22/09/2022 | 884.29 | 40.02 | 924.31 | Birbhum Division | Bolpur Mechanical Division | 384.84 | 34.58 | 4.9 | 0 | 424.31 | 385.75 | 38.47 | 4.9 | 0 | 429.12 | 46.43 | 90
231 | BIRBHUM | SM/12596 | PAKURIA PIPED WATER SUPPLY SCHEME. | TSM/013065 | 40033588 | New | MVS | GO2223007725PH | 15/09/2022 | 539.84 | 38.73 | 578.57 | Birbhum Division | Bolpur Mechanical Division | 193.28 | 30.97 | 16.42 | 0 | 240.66 | 193.28 | 30.97 | 16.42 | 0 | 240.66 | 41.6 | 30
232 | BIRBHUM | SM/14851 | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) | TSM/017783 | 40053968 | New | MVS | GO2223013005PH | 03/02/2023 | 475.95 | 0 | 475.95 | Birbhum Division |  | 22.38 | 0 | 69.26 | 0 | 91.64 | 22.38 | 0 | 69.26 | 0 | 91.64 | 19.25 | 20
233 | BIRBHUM | SM/12906 | Palsa piped water supply scheme. | TSM/014679 | 40033460 | New | SVS | GO2223008090PH | 22/09/2022 | 511.49 | 37.64 | 549.14 | Birbhum Division | Bolpur Mechanical Division | 87.4 | 26.03 | 10.42 | 0 | 123.86 | 87.4 | 28.76 | 10.42 | 0 | 126.58 | 23.05 | 60
234 | BIRBHUM | SM/13951 | PANCHPARA PIPED WATER SUPPLY SCHEME | TSM/016098 | 40033008 | New | MVS | GO2223010287PH | 01/12/2022 | 481.71 | 158.02 | 639.73 | Birbhum Division | Bolpur Mechanical Division | 3.19 | 0 | 11.38 | 0 | 14.57 | 3.19 | 0 | 11.38 | 0 | 14.57 | 2.28 | 5
235 | BIRBHUM | SM/12907 | Paniara Piped Water Supply Scheme. | TSM/014676 | 40033454 | New | SVS | GO2223008093PH | 22/09/2022 | 91.9 | 32.93 | 124.83 | Birbhum Division | Bolpur Mechanical Division | 0 | 18.91 | 9.2 | 0 | 28.11 | 0 | 18.91 | 9.2 | 0 | 28.11 | 22.52 | 24
236 | BIRBHUM | SM/14691 | PAPURI PIPED WATER SUPPLY SCHEME | TSM/015547 | 40037132 | New | MVS | GO2223012674PH | 31/01/2023 | 738.43 | 151.11 | 889.54 | Birbhum Division | Bolpur Mechanical Division | 4.76 | 3.48 | 47.96 | 0 | 56.21 | 4.76 | 3.48 | 47.96 | 0 | 56.21 | 6.32 | 10
237 | BIRBHUM | SM/13474 | Paratpur Piped Water Supply Scheme. | TSM/015616 | 40033694 | New | MVS | GO2223009225PH | 02/11/2022 | 707.07 | 99.81 | 806.88 | Birbhum Division | Bolpur Mechanical Division | 65.66 | 0 | 69.87 | 0 | 135.53 | 65.66 | 0 | 69.87 | 0 | 135.53 | 16.8 | 20
238 | BIRBHUM | SM/14959 | PARKUTA PIPED WATER SUPPLY SCHEME | TSM/017348 | 40060351 | New | MVS | GO2223013096PH | 04/02/2023 | 190.63 | 80.86 | 271.5 | Birbhum Division | Bolpur Mechanical Division | 86.08 | 51.5 | 9.24 | 0 | 146.82 | 87.69 | 54.5 | 9.24 | 0 | 151.43 | 55.78 | 76
239 | BIRBHUM | SM/14855 | Parsundi Piped Water Supply Scheme | TSM/017487 | 40053972 | New | MVS | GO2223013008PH | 03/02/2023 | 506.23 | 0 | 506.23 | Birbhum Division |  | 15.6 | 0 | 96.28 | 0 | 111.88 | 15.6 | 0 | 96.28 | 0 | 111.88 | 22.1 | 25
240 | BIRBHUM | SM/14538 | PARULIA PIPED WATER SUPPLY SCHEME. | TSM/012871 | 40034733 | New | MVS | GO2223012592PH | 30/01/2023 | 1015.4 | 89.07 | 1104.48 | Birbhum Division | Bolpur Mechanical Division | 343.11 | 8.26 | 194.44 | 0 | 545.81 | 343.11 | 8.26 | 194.44 | 0 | 545.81 | 49.42 | 70
241 | BIRBHUM | SM/12458 | Paschim Naopara and Adjoining Mouzas PWSS | TSM/013258 | 40033595 | New | MVS | GO2223007612PH | 13/09/2022 | 428.46 | 38.39 | 466.85 | Birbhum Division | Bolpur Mechanical Division | 281.09 | 32.14 | 40.74 | 0 | 353.98 | 281.09 | 35.15 | 40.74 | 0 | 356.99 | 76.47 | 80
242 | BIRBHUM | SM/14955 | Patalpur Piped Water Supply Scheme | TSM/017157 | 40045584 | New | MVS | GO2223013131PH | 04/02/2023 | 121.47 | 87.91 | 209.38 | Birbhum Division | Bolpur Mechanical Division | 7.27 | 4.68 | 0 | 0 | 11.94 | 7.27 | 4.68 | 0 | 0 | 11.94 | 5.7 | 25
243 | BIRBHUM | SM/16282 | Penchalia Piped Water Supply Scheme | TSM/017488 | 40054106 | New | MVS | GO2223014882PH | 24/02/2023 | 389.54 | 0 | 389.54 | Birbhum Division |  | 9.49 | 0 | 51.69 | 0 | 61.18 | 9.49 | 0 | 51.69 | 0 | 61.18 | 15.71 | 20
244 | BIRBHUM | SM/12901 | PHULUR PIPED WATER SUPPLY SCHEME. | TSM/013014 | 40033581 | New | MVS | GO2223008078PH | 22/09/2022 | 614.9 | 38.85 | 653.75 | Birbhum Division | Bolpur Mechanical Division | 72.4 | 22.91 | 22.98 | 0 | 118.29 | 72.4 | 22.91 | 22.98 | 0 | 118.29 | 18.09 | 70
245 | BIRBHUM | SM/14016 | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District | TSM/009459 | 40060280 | New | SVS | GO2223010518PH | 05/12/2022 | 155.21 | 36.05 | 191.26 | Birbhum Division | Bolpur Mechanical Division | 87.33 | 19.66 | 0 | 0 | 106.99 | 90.06 | 20.55 | 0 | 0 | 110.62 | 57.84 | 75
246 | BIRBHUM | SM/13714 | Podda Piped Water Supply Scheme | TSM/015557 | 40034173 | New | MVS | GO2223009713PH | 14/11/2022 | 346.32 | 77.77 | 424.09 | Birbhum Division | Bolpur Mechanical Division | 81.32 | 47.7 | 14.42 | 0 | 143.44 | 84.04 | 50.7 | 14.42 | 0 | 149.16 | 35.17 | 90
247 | BIRBHUM | SM/13478 | Prasadpur Piped Water Supply Scheme | TSM/015461 | 40033956 | New | MVS | GO2223009223PH | 02/11/2022 | 745.26 | 88.34 | 833.6 | Birbhum Division | Bolpur Mechanical Division | 188.49 | 48.29 | 7.75 | 0 | 244.53 | 188.49 | 48.29 | 7.75 | 0 | 244.53 | 29.33 | 10
248 | BIRBHUM | SM/14088 | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | TSM/015739 | 40038382 | New | MVS | GO2223010868PH | 12/12/2022 | 809.69 | 104.19 | 913.88 | Birbhum Division | Bolpur Mechanical Division | 200.95 | 11.3 | 39.34 | 0 | 251.59 | 200.95 | 13.13 | 39.34 | 0 | 253.42 | 27.73 | 32
249 | BIRBHUM | SM/14903 | PUNNA PIPED WATER SUPPLY SCHEME | TSM/016169 | 40037006 | New | MVS | GO2223013133PH | 04/02/2023 | 876.7 | 119.67 | 996.36 | Birbhum Division | Bolpur Mechanical Division | 85.05 | 4.75 | 33.71 | 30.43 | 153.94 | 85.05 | 4.75 | 33.71 | 30.43 | 153.94 | 15.45 | 25
250 | BIRBHUM | SM/13715 | Purba Anantapur Piped Water Supply Scheme | TSM/015554 | 40034148 | New | MVS | GO2223009714PH | 14/11/2022 | 508.36 | 77.77 | 586.12 | Birbhum Division | Bolpur Mechanical Division | 182.8 | 26.83 | 60.25 | 0 | 269.87 | 183.98 | 33.89 | 60.25 | 0 | 278.13 | 47.45 | 90
251 | BIRBHUM | SM/13470 | PURBA BANKATI PIPED WATER SUPPLY SCHEME. | TSM/011733 | 40034256 | New | MVS | GO2223009220PH | 02/11/2022 | 159.71 | 19.08 | 178.79 | Birbhum Division | Bolpur Mechanical Division | 102.14 | 17.16 | 7.77 | 0 | 127.06 | 102.14 | 18.65 | 7.77 | 0 | 128.55 | 71.9 | 75
252 | BIRBHUM | SM/12598 | PURBA SIUR PIPED WATER SUPPLY SCHEME. | TSM/013016 | 40033586 | New | MVS | GO2223007722PH | 15/09/2022 | 457.42 | 40.37 | 497.79 | Birbhum Division | Bolpur Mechanical Division | 35.05 | 26.24 | 17.91 | 0 | 79.2 | 35.05 | 29.13 | 17.91 | 0 | 82.08 | 16.49 | 55
253 | BIRBHUM | SM/14027 | Radipur Piped Water Supply Scheme. | TSM/016078 | 40037293 | New | MVS | GO2223010494PH | 05/12/2022 | 480.65 | 39.08 | 519.73 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 11.68 | 0 | 11.68 | 0 | 0 | 11.68 | 0 | 11.68 | 2.25 | 3
254 | BIRBHUM | SM/14747 | RAGHABPUR PIPED WATER SUPPLY SCHEME | TSM/016570 | 40037055 | New | MVS | GO2223012675PH | 31/01/2023 | 298.08 | 81.03 | 379.11 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 40.62 | 24.01 | 64.63 | 0 | 0 | 40.62 | 24.01 | 64.63 | 17.05 | 20
255 | BIRBHUM | SM/14026 | Rajpur Piped Water Supply Scheme | TSM/016740 | 40037498 | New | MVS | GO2223010489PH | 05/12/2022 | 605.29 | 127.26 | 732.55 | Birbhum Division | Bolpur Mechanical Division | 97.62 | 56.72 | 0 | 0 | 154.34 | 97.62 | 56.72 | 0 | 0 | 154.34 | 21.07 | 60
256 | BIRBHUM | SM/13950 | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME | TSM/016099 | 40037169 | New | MVS | GO2223010309PH | 01/12/2022 | 682.88 | 117.53 | 800.41 | Birbhum Division | Bolpur Mechanical Division | 4.66 | 0 | 11.14 | 0 | 15.81 | 4.66 | 0 | 11.14 | 0 | 15.81 | 1.97 | 5
257 | BIRBHUM | SM/16373 | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | TSM/015482 | 40033708 | New | MVS | GO2223014967PH | 28/02/2023 | 651.11 | 100.42 | 751.53 | Birbhum Division | Bolpur Mechanical Division | 267.56 | 68.31 | 22.39 | 0 | 358.26 | 267.56 | 71.86 | 22.39 | 0 | 361.81 | 48.14 | 80
258 | BIRBHUM | SM/14850 | RANIBAZAR PIPED WATER SUPPLY SCHEME | TSM/017432 | 40053973 | New | MVS | GO2223013010PH | 03/02/2023 | 502.89 | 143.11 | 646 | Birbhum Division | Bolpur Mechanical Division | 3.89 | 0 | 14.34 | 0 | 18.23 | 3.89 | 0 | 14.34 | 0 | 18.23 | 2.82 | 5
259 | BIRBHUM | SM/16276 | RANIPARA PIPED WATER SUPPLY SCHEME | TSM/017183 | 40053977 | New | MVS | GO2223014883PH | 24/02/2023 | 382.88 | 157.94 | 540.82 | Birbhum Division | Bolpur Mechanical Division | 2.53 | 0 | 5.39 | 0 | 7.92 | 2.53 | 0 | 5.39 | 0 | 7.92 | 1.46 | 2
260 | BIRBHUM | SM/12888 | RAUTARA PIPED WATER SUPPLY SCHEME. | TSM/011622 | 40033123 | New | MVS | GO2223008150PH | 23/09/2022 | 210.98 | 36.17 | 247.15 | Birbhum Division | Bolpur Mechanical Division | 98.35 | 33.34 | 4.01 | 0 | 135.69 | 98.35 | 33.34 | 4.01 | 0 | 135.69 | 54.9 | 70
261 | BIRBHUM | SM/14894 | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | TSM/016708 | 40037740 | New | MVS | GO2223013130PH | 04/02/2023 | 245.59 | 80.86 | 326.46 | Birbhum Division | Bolpur Mechanical Division | 154.02 | 34.92 | 3.8 | 0 | 192.73 | 155.2 | 37.31 | 3.8 | 0 | 196.31 | 60.13 | 90
262 | BIRBHUM | SM/14957 | RAYEN PIPED WATER SUPPLY SCHEME | TSM/017123 | 40037222 | New | MVS | GO2223013084PH | 04/02/2023 | 298.25 | 154.2 | 452.46 | Birbhum Division | Bolpur Mechanical Division | 2.61 | 0 | 18.19 | 0 | 20.81 | 2.61 | 0 | 18.19 | 0 | 20.81 | 4.6 | 5
263 | BIRBHUM | SM/12659 | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | TSM/014524 | 40035566 | Retrofitting | MVS | GO2223007835PH | 19/09/2022 | 149.48 | 0 | 149.48 | Birbhum Division |  | 44.79 | 0 | 0 | 0 | 44.79 | 44.79 | 0 | 0 | 0 | 44.79 | 29.97 | 70
264 | BIRBHUM | SM/06943 | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | TSM/006171 | 8138343 | Retrofitting | MVS | GO2021002278PH | 03/11/2020 | 97.5 | 0 | 97.5 | Birbhum Division |  | 94.66 | 0 | 0 | 0 | 94.66 | 94.66 | 0 | 0 | 0 | 94.66 | 97.09 | 95
265 | BIRBHUM | SM/12677 | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | TSM/014923 | 40035328 | Retrofitting | MVS | GO2223007827PH | 19/09/2022 | 613.51 | 48 | 661.51 | Birbhum Division | Bolpur Mechanical Division | 244.79 | 0 | 0 | 0 | 244.79 | 244.79 | 0 | 0 | 0 | 244.79 | 37 | 45
266 | BIRBHUM | SM/09365 | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008570 | 40035630 | Retrofitting | MVS | GO2122005373PH | 12/11/2021 | 120.18 | 0 | 120.18 | Birbhum Division |  | 82.16 | 0 | 10.17 | 0 | 92.33 | 82.16 | 0 | 10.17 | 0 | 92.33 | 76.83 | 78
267 | BIRBHUM | SM/09490 | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008521 | 7940637 | Retrofitting | MVS | GO2122005585PH | 19/11/2021 | 299.8 | 0 | 299.8 | Birbhum Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78
268 | BIRBHUM | SM/10665 | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme | TSM/010390 | 40026521 | Retrofitting | MVS | GO2223000520PH | 22/04/2022 | 58.24 | 0 | 58.24 | Birbhum Division |  | 56.54 | 0 | 0 | 0 | 56.54 | 56.54 | 0 | 0 | 0 | 56.54 | 97.09 | 90
269 | BIRBHUM | SM/10543 | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | TSM/010389 | 40014217 | Retrofitting | MVS | GO2223000258PH | 13/04/2022 | 68.88 | 0 | 68.88 | Birbhum Division |  | 50.97 | 0 | 0 | 0 | 50.97 | 50.97 | 0 | 0 | 0 | 50.97 | 73.99 | 75
270 | BIRBHUM | SM/06733 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) | TSM/005600 | 8129935 | Retrofitting | MVS | GO2021001255PH | 18/09/2020 | 99.93 | 0 | 99.93 | Birbhum Division |  | 95.17 | 0 | 0 | 0 | 95.17 | 95.17 | 0 | 0 | 0 | 95.17 | 95.24 | 95
271 | BIRBHUM | SM/07645 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | TSM/006720 | 8223420 | Retrofitting | MVS | GO2021004245PH | 07/01/2021 | 93.68 | 0 | 93.68 | Birbhum Division |  | 65.01 | 0 | 0 | 0 | 65.01 | 65.01 | 0 | 0 | 0 | 65.01 | 69.4 | 70
272 | BIRBHUM | SM/07530 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | TSM/006178 | 7401848 | Retrofitting | MVS | GO2021003922PH | 31/12/2020 | 296.93 | 0 | 296.93 | Birbhum Division |  | 285.55 | 0 | 0 | 0 | 285.55 | 285.55 | 0 | 0 | 0 | 285.55 | 96.17 | 89
273 | BIRBHUM | SM/07648 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS | TSM/006721 | 7728675 | Retrofitting | MVS | GO2021004248PH | 07/01/2021 | 99.48 | 0 | 99.48 | Birbhum Division |  | 75.48 | 0 | 0 | 0 | 75.48 | 75.48 | 0 | 0 | 0 | 75.48 | 75.88 | 90
274 | BIRBHUM | SM/07006 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | TSM/005603 | 8129887 | Retrofitting | MVS | GO2021002618PH | 13/11/2020 | 99.48 | 0 | 99.48 | Birbhum Division |  | 94.77 | 0 | 0 | 0 | 94.77 | 94.77 | 0 | 0 | 0 | 94.77 | 95.27 | 90
275 | BIRBHUM | SM/09371 | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008514 | 7940753 | Retrofitting | MVS | GO2122005374PH | 12/11/2021 | 105.12 | 0 | 105.12 | Birbhum Division |  | 102.06 | 0 | 0 | 0 | 102.06 | 102.06 | 0 | 0 | 0 | 102.06 | 97.09 | 95
276 | BIRBHUM | SM/09341 | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | TSM/008512 | 7940777 | Retrofitting | MVS | GO2122005375PH | 12/11/2021 | 896.76 | 0 | 896.76 | Birbhum Division |  | 107.49 | 0 | 0 | 0 | 107.49 | 107.49 | 0 | 0 | 0 | 107.49 | 11.99 | 22
277 | BIRBHUM | SM/08172 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | TSM/007021 | 8334988 | Retrofitting | MVS | GO2021006567PH | 08/02/2021 | 95.12 | 0 | 95.12 | Birbhum Division |  | 89.98 | 0 | 0 | 0 | 89.98 | 89.98 | 0 | 0 | 0 | 89.98 | 94.59 | 75
278 | BIRBHUM | SM/06735 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | TSM/005602 | 8130012 | Retrofitting | MVS | GO2021001260PH | 18/09/2020 | 99.99 | 0 | 99.99 | Birbhum Division |  | 89.34 | 0 | 0 | 0 | 89.34 | 94.11 | 0 | 0 | 0 | 94.11 | 94.12 | 95
279 | BIRBHUM | SM/09364 | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008571 | 7940757 | Retrofitting | MVS | GO2122005373PH | 12/11/2021 | 234.01 | 0 | 234.01 | Birbhum Division |  | 148.19 | 0 | 0 | 0 | 148.19 | 148.19 | 0 | 0 | 0 | 148.19 | 63.32 | 70
280 | BIRBHUM | SM/06737 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | TSM/005607 | 6169086 | Retrofitting | MVS | GO2021001266PH | 18/09/2020 | 95.3 | 0 | 95.3 | Birbhum Division |  | 95.3 | 0 | 0 | 0 | 95.3 | 93.59 | 0 | 0 | 0 | 93.59 | 98.21 | 100
281 | BIRBHUM | SM/07647 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) | TSM/006722 | 40064148 | Retrofitting | MVS | GO2021004247PH | 07/01/2021 | 64.73 | 0 | 64.73 | Birbhum Division |  | 7.83 | 0 | 0 | 0 | 7.83 | 7.83 | 0 | 0 | 0 | 7.83 | 12.09 | 10
282 | BIRBHUM | SM/08286 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | TSM/006181 | 7366998 | Retrofitting | MVS | GO2021006694PH | 09/02/2021 | 865 | 0 | 865 | Birbhum Division |  | 813.49 | 0 | 0 | 0 | 813.49 | 815.82 | 0 | 0 | 0 | 815.82 | 94.31 | 90
283 | BIRBHUM | SM/09369 | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008516 | 7940543 | Retrofitting | MVS | GO2122005374PH | 12/11/2021 | 77.81 | 0 | 77.81 | Birbhum Division |  | 25.18 | 0 | 0 | 0 | 25.18 | 25.18 | 0 | 0 | 0 | 25.18 | 32.36 | 60
284 | BIRBHUM | SM/07531 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | TSM/006183 | 6904412 | Retrofitting | MVS | GO2021003923PH | 31/12/2020 | 190.61 | 0 | 190.61 | Birbhum Division |  | 185.06 | 0 | 0 | 0 | 185.06 | 185.06 | 0 | 0 | 0 | 185.06 | 97.09 | 90
285 | BIRBHUM | SM/07650 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | TSM/006725 | 7940657 | Retrofitting | SVS | GO2021004250PH | 07/01/2021 | 53.59 | 0 | 53.59 | Birbhum Division |  | 50.84 | 0 | 0 | 0 | 50.84 | 50.84 | 0 | 0 | 0 | 50.84 | 94.88 | 90
286 | BIRBHUM | SM/06736 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | TSM/005604 | 8130218 | Retrofitting | MVS | GO2021001267PH | 18/09/2020 | 99.68 | 0 | 99.68 | Birbhum Division |  | 85.19 | 0 | 0 | 0 | 85.19 | 85.19 | 0 | 0 | 0 | 85.19 | 85.46 | 90
287 | BIRBHUM | SM/09368 | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008519 | 7940625 | Retrofitting | MVS | GO2122005374PH | 12/11/2021 | 68.35 | 0 | 68.35 | Birbhum Division |  | 54.62 | 0 | 5.74 | 0 | 60.36 | 54.62 | 0 | 5.74 | 0 | 60.36 | 88.31 | 90
288 | BIRBHUM | SM/06732 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | TSM/005613 | 8131554 | Retrofitting | MVS | GO2021001256PH | 18/09/2020 | 99.79 | 0 | 99.79 | Birbhum Division |  | 92.81 | 0 | 0 | 0 | 92.81 | 92.81 | 0 | 0 | 0 | 92.81 | 93 | 95
289 | BIRBHUM | SM/07532 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | TSM/006186 | 7401858 | Retrofitting | MVS | GO2021003924PH | 31/12/2020 | 179.67 | 0 | 179.67 | Birbhum Division |  | 157.86 | 0 | 0 | 0 | 157.86 | 157.86 | 0 | 0 | 0 | 157.86 | 87.86 | 80
290 | BIRBHUM | SM/09367 | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008520 | 40049469 | Retrofitting | SVS | GO2122005374PH | 12/11/2021 | 453.12 | 0 | 453.12 | Birbhum Division |  | 236.06 | 0 | 30.66 | 0 | 266.71 | 236.06 | 0 | 30.66 | 0 | 266.71 | 58.86 | 60
291 | BIRBHUM | SM/07646 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | TSM/006726 | 8223453 | Retrofitting | MVS | GO2021004246PH | 07/01/2021 | 82.04 | 0 | 82.04 | Birbhum Division |  | 79.66 | 0 | 0 | 0 | 79.66 | 79.66 | 0 | 0 | 0 | 79.66 | 97.09 | 95
292 | BIRBHUM | SM/08171 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | TSM/007022 | 7401850 | Retrofitting | MVS | GO2021006568PH | 08/02/2021 | 97.14 | 0 | 97.14 | Birbhum Division |  | 82.11 | 0 | 0 | 0 | 82.11 | 82.11 | 0 | 0 | 0 | 82.11 | 84.52 | 80
293 | BIRBHUM | SM/07533 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | TSM/006187 | 6904406 | Retrofitting | MVS | GO2021003925PH | 31/12/2020 | 206.39 | 0 | 206.39 | Birbhum Division |  | 183.35 | 0 | 0 | 0 | 183.35 | 183.35 | 0 | 0 | 0 | 183.35 | 88.83 | 90
294 | BIRBHUM | SM/07651 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | TSM/006724 | 4737015 | Retrofitting | MVS | GO2021004252PH | 07/01/2021 | 99.95 | 0 | 99.95 | Birbhum Division |  | 97.04 | 0 | 0 | 0 | 97.04 | 97.04 | 0 | 0 | 0 | 97.04 | 97.09 | 100
295 | BIRBHUM | SM/07649 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | TSM/006723 | 7728726 | Retrofitting | MVS | GO2021004249PH | 07/01/2021 | 99.46 | 0 | 99.46 | Birbhum Division |  | 96.57 | 0 | 0 | 0 | 96.57 | 96.57 | 0 | 0 | 0 | 96.57 | 97.09 | 80
296 | BIRBHUM | SM/09366 | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008522 | 7940767 | Retrofitting | MVS | GO2122005373PH | 12/11/2021 | 181.79 | 0 | 181.79 | Birbhum Division |  | 122.01 | 0 | 15.63 | 0 | 137.64 | 122.01 | 0 | 15.63 | 0 | 137.64 | 75.71 | 90
297 | BIRBHUM | SM/09363 | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008572 | 7940704 | Retrofitting | MVS | GO2122005373PH | 12/11/2021 | 188.82 | 0 | 188.82 | Birbhum Division |  | 59.52 | 0 | 0 | 0 | 59.52 | 59.52 | 0 | 0 | 0 | 59.52 | 31.52 | 35
298 | BIRBHUM | SM/06734 | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | TSM/005601 | 8129913 | Retrofitting | MVS | GO2021001259PH | 18/09/2020 | 94.74 | 0 | 94.74 | Birbhum Division |  | 68.47 | 0 | 0 | 0 | 68.47 | 68.47 | 0 | 0 | 0 | 68.47 | 72.27 | 90
299 | BIRBHUM | SM/09362 | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008573 | 7940651 | Retrofitting | MVS | GO2122005373PH | 12/11/2021 | 259.6 | 0 | 259.6 | Birbhum Division |  | 150.93 | 0 | 0 | 0 | 150.93 | 150.93 | 0 | 0 | 0 | 150.93 | 58.14 | 60
300 | BIRBHUM | SM/09491 | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | TSM/009066 | 40001077 | Retrofitting | MVS | GO2122005585PH | 19/11/2021 | 149.02 | 0 | 149.02 | Birbhum Division |  | 107.1 | 0 | 0 | 0 | 107.1 | 107.1 | 0 | 0 | 0 | 107.1 | 71.87 | 70
301 | BIRBHUM | SM/08893 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | TSM/008200 | 40001344 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 293.51 | 0 | 293.51 | Birbhum Division |  | 284.96 | 0 | 0 | 0 | 284.96 | 284.96 | 0 | 0 | 0 | 284.96 | 97.09 | 70
302 | BIRBHUM | SM/08897 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | TSM/008208 | 7940719 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 109.18 | 0 | 109.18 | Birbhum Division |  | 91.01 | 0 | 0 | 0 | 91.01 | 91.01 | 0 | 0 | 0 | 91.01 | 83.36 | 90
303 | BIRBHUM | SM/08896 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | TSM/008205 | 40008882 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 206.23 | 0 | 206.23 | Birbhum Division |  | 79.09 | 0 | 26.49 | 0 | 105.58 | 79.09 | 0 | 26.49 | 0 | 105.58 | 51.19 | 60
304 | BIRBHUM | SM/08894 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. | TSM/008201 | 7940790 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 148.29 | 0 | 148.29 | Birbhum Division |  | 111.16 | 0 | 0 | 0 | 111.16 | 111.16 | 0 | 0 | 0 | 111.16 | 74.97 | 80
305 | BIRBHUM | SM/08895 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | TSM/008202 | 7940805 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 94.58 | 0 | 94.58 | Birbhum Division |  | 42.31 | 0 | 0 | 0 | 42.31 | 42.31 | 0 | 0 | 0 | 42.31 | 44.74 | 50
306 | BIRBHUM | SM/12637 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) | TSM/014500 | 40035662 | Retrofitting | MVS | GO2223007830PH | 19/09/2022 | 34.45 | 0 | 34.45 | Birbhum Division |  | 19.93 | 0 | 0 | 0 | 19.93 | 19.93 | 0 | 0 | 0 | 19.93 | 57.85 | 90
307 | BIRBHUM | SM/12664 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Amdole Phase-II Water Supply Scheme | TSM/014561 | 40035589 | Retrofitting | MVS | GO2223007831PH | 19/09/2022 | 58.66 | 0 | 58.66 | Birbhum Division |  | 56.95 | 0 | 0 | 0 | 56.95 | 56.95 | 0 | 0 | 0 | 56.95 | 97.09 | 60
308 | BIRBHUM | SM/12662 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Basudebpur Phase-II Water Supply Scheme. | TSM/014573 | 40035492 | Retrofitting | MVS | GO2223007837PH | 19/09/2022 | 42.93 | 0 | 42.93 | Birbhum Division |  | 7.57 | 0 | 0 | 0 | 7.57 | 7.57 | 0 | 0 | 0 | 7.57 | 17.62 | 10
309 | BIRBHUM | SM/12657 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | TSM/014636 | 40035504 | Retrofitting | MVS | GO2223007833PH | 19/09/2022 | 23.91 | 0 | 23.91 | Birbhum Division |  | 16.74 | 0 | 0 | 0 | 16.74 | 16.74 | 0 | 0 | 0 | 16.74 | 70 | 70
310 | BIRBHUM | SM/12660 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Belera Phase-II Water Supply Scheme. | TSM/014631 | 40035516 | Retrofitting | MVS | GO2223007836PH | 19/09/2022 | 21.01 | 0 | 21.01 | Birbhum Division |  | 17.31 | 0 | 0 | 0 | 17.31 | 17.31 | 0 | 0 | 0 | 17.31 | 82.39 | 85
311 | BIRBHUM | SM/09792 | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008807 | 6323768 | Retrofitting | MVS | GO2122006240PH | 30/11/2021 | 771.82 | 0 | 771.82 | Birbhum Division |  | 330.79 | 0 | 67.95 | 0 | 398.74 | 330.79 | 0 | 67.95 | 0 | 398.74 | 51.66 | 75
312 | BIRBHUM | SM/12665 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Danghara (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | TSM/014667 | 40060330 | Retrofitting | MVS | GO2223007829PH | 19/09/2022 | 17.6 | 0 | 17.6 | Birbhum Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
313 | BIRBHUM | SM/12666 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | TSM/014635 | 40035632 | Retrofitting | MVS | GO2223007838PH | 19/09/2022 | 99.4 | 0 | 99.4 | Birbhum Division |  | 18.79 | 0 | 0 | 0 | 18.79 | 18.79 | 0 | 0 | 0 | 18.79 | 18.91 | 60
314 | BIRBHUM | SM/12658 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme | TSM/014584 | 40035620 | Retrofitting | MVS | GO2223007825PH | 19/09/2022 | 13.68 | 0 | 13.68 | Birbhum Division |  | 5.16 | 0 | 0 | 0 | 5.16 | 5.16 | 0 | 0 | 0 | 5.16 | 37.71 | 50
315 | BIRBHUM | SM/12667 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. | TSM/014656 | 40035469 | Retrofitting | MVS | GO2223007832PH | 19/09/2022 | 24.91 | 0 | 24.91 | Birbhum Division |  | 19.43 | 0 | 0 | 0 | 19.43 | 19.43 | 0 | 0 | 0 | 19.43 | 78.01 | 80
316 | BIRBHUM | SM/12661 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. | TSM/014641 | 40035457 | Retrofitting | MVS | GO2223007824PH | 19/09/2022 | 43.64 | 0 | 43.64 | Birbhum Division |  | 36.03 | 0 | 0 | 0 | 36.03 | 36.03 | 0 | 0 | 0 | 36.03 | 82.54 | 75
317 | BIRBHUM | SM/12668 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kurumgram (Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | TSM/014743 | 40035647 | Retrofitting | MVS | GO2223007828PH | 19/09/2022 | 11.63 | 0 | 11.63 | Birbhum Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
318 | BIRBHUM | SM/13371 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. | TSM/014645 | 40035532 | Retrofitting | MVS | GO2223008969PH | 19/10/2022 | 33.38 | 0 | 33.38 | Birbhum Division |  | 17.94 | 0 | 0 | 0 | 17.94 | 17.94 | 0 | 0 | 0 | 17.94 | 53.75 | 55
319 | BIRBHUM | SM/13372 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme | TSM/014630 | 40035624 | Retrofitting | MVS | GO2223008967PH | 19/10/2022 | 20.61 | 0 | 20.61 | Birbhum Division |  | 20.01 | 0 | 0 | 0 | 20.01 | 20.01 | 0 | 0 | 0 | 20.01 | 97.09 | 90
320 | BIRBHUM | SM/18783 | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum | TSM/021456 | 40067392 | Retrofitting | MVS | PHE/IV/2606/W-643/23 | 29/08/2023 | 99.79 | 0 | 99.79 | Birbhum Division |  | 60.04 | 0 | 0 | 0 | 60.04 | 60.04 | 0 | 0 | 0 | 60.04 | 60.16
321 | BIRBHUM | SM/12663 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | TSM/014565 | 40027371 | Retrofitting | MVS | GO2223007839PH | 19/09/2022 | 108.02 | 0 | 108.02 | Birbhum Division |  | 51.38 | 0 | 0 | 0 | 51.38 | 51.38 | 0 | 0 | 0 | 51.38 | 47.57 | 60
322 | BIRBHUM | SM/13373 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sadasibpur (Phase-II) Water Supply Scheme of Murarai-II Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | TSM/014686 | 40035613 | Retrofitting | MVS | GO2223008966PH | 19/10/2022 | 13.41 | 0 | 13.41 | Birbhum Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
323 | BIRBHUM | SM/13374 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sekhpur Phase-II Water Supply Scheme. | TSM/014690 | 40035479 | Retrofitting | MVS | GO2223008963PH | 19/10/2022 | 14.22 | 0 | 14.22 | Birbhum Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | BIRBHUM | SM/13375 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Tarapith Phase-II Water Supply Scheme. | TSM/014696 | 40035683 | Retrofitting | MVS | GO2223008968PH | 19/10/2022 | 34.41 | 0 | 34.41 | Birbhum Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
325 | BIRBHUM | SM/08898 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | TSM/008210 | 40006129 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 147.83 | 0 | 147.83 | Birbhum Division |  | 85.77 | 0 | 0 | 0 | 85.77 | 85.77 | 0 | 0 | 0 | 85.77 | 58.02 | 97
326 | BIRBHUM | SM/08892 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | TSM/008199 | 40003749 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 96.68 | 0 | 96.68 | Birbhum Division |  | 72.23 | 0 | 0 | 0 | 72.23 | 72.23 | 0 | 0 | 0 | 72.23 | 74.71 | 95
327 | BIRBHUM | SM/08891 | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | TSM/008198 | 7940745 | Retrofitting | MVS | GO2122003904PH | 29/09/2021 | 176.25 | 0 | 176.25 | Birbhum Division |  | 26.35 | 0 | 0 | 0 | 26.35 | 26.35 | 0 | 0 | 0 | 26.35 | 14.95 | 25
328 | BIRBHUM | SM/06744 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | TSM/005612 | 8131542 | Retrofitting | SVS | GO2021001258PH | 18/09/2020 | 99.59 | 0 | 99.59 | Birbhum Division |  | 94.81 | 0 | 0 | 0 | 94.81 | 73.61 | 0 | 0 | 0 | 73.61 | 73.92 | 75
329 | BIRBHUM | SM/06740 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | TSM/005608 | 7063164 | Retrofitting | MVS | GO2021001263PH | 18/09/2020 | 99.84 | 0 | 99.84 | Birbhum Division |  | 95.63 | 0 | 0 | 0 | 95.63 | 95.63 | 0 | 0 | 0 | 95.63 | 95.79 | 85
330 | BIRBHUM | SM/09370 | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | TSM/008515 | 7940534 | Retrofitting | MVS | GO2122005374PH | 12/11/2021 | 145.06 | 0 | 145.06 | Birbhum Division |  | 98.55 | 0 | 0 | 0 | 98.55 | 98.55 | 0 | 0 | 0 | 98.55 | 67.94 | 80
331 | BIRBHUM | SM/06742 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | TSM/005610 | 8131518 | Retrofitting | MVS | GO2021001262PH | 18/09/2020 | 98.25 | 0 | 98.25 | Birbhum Division |  | 57 | 0 | 0 | 0 | 57 | 57 | 0 | 0 | 0 | 57 | 58.02 | 65
332 | BIRBHUM | SM/06739 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) | TSM/005605 | 6858833 | Retrofitting | MVS | GO2021001264PH | 18/09/2020 | 96.06 | 0 | 96.06 | Birbhum Division |  | 89.61 | 0 | 0 | 0 | 89.61 | 90.4 | 0 | 0 | 0 | 90.4 | 94.11 | 100
333 | BIRBHUM | SM/06738 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | TSM/005606 | 6275445 | Retrofitting | MVS | GO2021001265PH | 18/09/2020 | 99.99 | 0 | 99.99 | Birbhum Division |  | 96.79 | 0 | 0 | 0 | 96.79 | 96.79 | 0 | 0 | 0 | 96.79 | 96.8 | 100
334 | BIRBHUM | SM/06741 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | TSM/005609 | 8131499 | Retrofitting | MVS | GO2021001261PH | 18/09/2020 | 99.97 | 0 | 99.97 | Birbhum Division |  | 97.06 | 0 | 0 | 0 | 97.06 | 93.37 | 0 | 0 | 0 | 93.37 | 93.4 | 95
335 | BIRBHUM | SM/06743 | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | TSM/005611 | 8131534 | Retrofitting | MVS | GO2021001257PH | 18/09/2020 | 97.37 | 0 | 97.37 | Birbhum Division |  | 52 | 0 | 0 | 0 | 52 | 52 | 0 | 0 | 0 | 52 | 53.4 | 55
336 | BIRBHUM | SM/06951 | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | TSM/006184 | 6919680 | Retrofitting | MVS | GO2021002284PH | 03/11/2020 | 72.24 | 0 | 72.24 | Birbhum Division |  | 53.11 | 0 | 0 | 0 | 53.11 | 53.11 | 0 | 0 | 0 | 53.11 | 73.51 | 85
337 | BIRBHUM | SM/07155 | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | TSM/006179 | 7481806 | Retrofitting | MVS | GO2021002894PH | 01/12/2020 | 94.45 | 0 | 94.45 | Birbhum Division |  | 91.7 | 0 | 0 | 0 | 91.7 | 91.7 | 0 | 0 | 0 | 91.7 | 97.09 | 90
338 | BIRBHUM | SM/06949 | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | TSM/006180 | 7728689 | Retrofitting | MVS | GO2021002283PH | 03/11/2020 | 99.96 | 0 | 99.96 | Birbhum Division |  | 97.05 | 0 | 0 | 0 | 97.05 | 97.05 | 0 | 0 | 0 | 97.05 | 97.09 | 90
339 | BIRBHUM | SM/06944 | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | TSM/006176 | 8138363 | Retrofitting | MVS | GO2021002282PH | 03/11/2020 | 97.37 | 0 | 97.37 | Birbhum Division |  | 94.53 | 0 | 0 | 0 | 94.53 | 55.19 | 0 | 0 | 0 | 55.19 | 56.68 | 45
340 | BIRBHUM | SM/06945 | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | TSM/006174 | 6169086 | Retrofitting | MVS | GO2021002280PH | 04/11/2020 | 98.81 | 0 | 98.81 | Birbhum Division |  | 56.55 | 0 | 0 | 0 | 56.55 | 73.85 | 0 | 0 | 0 | 73.85 | 74.75 | 100
341 | BIRBHUM | SM/06948 | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | TSM/006188 | 8135976 | Retrofitting | MVS | GO2021002286PH | 03/11/2020 | 99.22 | 0 | 99.22 | Birbhum Division |  | 97.91 | 0 | 0 | 0 | 97.91 | 97.91 | 0 | 0 | 0 | 97.91 | 98.67 | 70
342 | BIRBHUM | SM/06946 | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area | TSM/006172 | 40060494 | Retrofitting | MVS | GO2021002279PH | 03/11/2020 | 97.74 | 0 | 97.74 | Birbhum Division |  | 38.5 | 0 | 0 | 0 | 38.5 | 38.5 | 0 | 0 | 0 | 38.5 | 39.39 | 40
343 | BIRBHUM | SM/07152 | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | TSM/006173 | 6275445 | Retrofitting | MVS | GO2021002892PH | 01/12/2020 | 65.97 | 0 | 65.97 | Birbhum Division |  | 53.3 | 0 | 0 | 0 | 53.3 | 53.3 | 0 | 0 | 0 | 53.3 | 80.78 | 100
344 | BIRBHUM | SM/06947 | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | TSM/006175 | 8138377 | Retrofitting | MVS | GO2021002281PH | 03/11/2020 | 99.28 | 0 | 99.28 | Birbhum Division |  | 94.25 | 0 | 0 | 0 | 94.25 | 94.25 | 0 | 0 | 0 | 94.25 | 94.93 | 92
345 | BIRBHUM | SM/07154 | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | TSM/006185 | 7728708 | Retrofitting | MVS | GO2021002895PH | 01/12/2020 | 99.92 | 0 | 99.92 | Birbhum Division |  | 83.72 | 0 | 0 | 0 | 83.72 | 83.72 | 0 | 0 | 0 | 83.72 | 83.79 | 60
346 | BIRBHUM | SM/06950 | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | TSM/006182 | 7728691 | Retrofitting | MVS | GO2021002284PH | 03/11/2020 | 99.83 | 0 | 99.83 | Birbhum Division |  | 96.92 | 0 | 0 | 0 | 96.92 | 96.92 | 0 | 0 | 0 | 96.92 | 97.09 | 90
347 | BIRBHUM | SM/07153 | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | TSM/006177 | 8140658 | Retrofitting | MVS | GO2021002893PH | 01/12/2020 | 99.72 | 0 | 99.72 | Birbhum Division |  | 59.73 | 0 | 0 | 16.7 | 76.43 | 59.73 | 0 | 0 | 16.7 | 76.43 | 76.64 | 45
348 | BIRBHUM | SM/14081 | Rupaspur Piped Water Supply Scheme. | TSM/016778 | 40036942 | New | MVS | GO2223010855PH | 12/12/2022 | 436.17 | 0 | 436.17 | Birbhum Division |  | 12.54 | 0 | 68.31 | 0 | 80.85 | 12.54 | 0 | 68.31 | 0 | 80.85 | 18.54 | 20
349 | BIRBHUM | SM/14686 | Ruppur and adjoining mouzas Piped Water Supply Scheme. | TSM/015095 | 40033058 | New | MVS | GO2223012783PH | 31/01/2023 | 1282.85 | 104.94 | 1387.78 | Birbhum Division | Bolpur Mechanical Division | 0 | 58.84 | 257.52 | 0 | 316.35 | 0 | 58.84 | 257.52 | 0 | 316.35 | 22.8 | 25
350 | BIRBHUM | SM/13648 | Sadanandapur piped water supply scheme. | TSM/015506 | 40033733 | New | MVS | GO2223009602PH | 11/11/2022 | 412.52 | 35.54 | 448.06 | Birbhum Division | Bolpur Mechanical Division | 178.08 | 28.56 | 8.53 | 0 | 215.17 | 178.08 | 30.67 | 8.53 | 0 | 217.28 | 48.49 | 75
351 | BIRBHUM | SM/16270 | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) | TSM/017780 | 40053981 | New | MVS | GO2223014880PH | 24/02/2023 | 153.88 | 0 | 153.88 | Birbhum Division |  | 11.81 | 0 | 2.55 | 0 | 14.36 | 11.81 | 0 | 2.55 | 0 | 14.36 | 9.33 | 10
352 | BIRBHUM | SM/18520 | Sahapur Piped Water Supply Scheme. | TSM/013004 | 40064144 | New | MVS | 2045/PHE-28011/211/2022-ESTT CELL-Dept. of PHE | 26/07/2023 | 1496.79 | 112.69 | 1609.49 | Birbhum Division | Bolpur Mechanical Division | 5.91 | 50.06 | 176.34 | 0 | 232.31 | 5.91 | 50.06 | 176.34 | 0 | 232.31 | 14.43 | 15
353 | BIRBHUM | SM/13649 | Sahapur Piped water Supply Scheme. | TSM/015328 | 40034087 | New | MVS | GO2223009595PH | 11/11/2022 | 911.19 | 77.77 | 988.96 | Birbhum Division | Bolpur Mechanical Division | 146.59 | 0 | 144.79 | 0 | 291.38 | 146.59 | 2.68 | 144.79 | 0 | 294.07 | 29.74 | 27
354 | BIRBHUM | SM/14678 | SAJNOR PIPED WATER SUPPLY SCHEME | TSM/016227 | 40037215 | New | MVS | GO2223012748PH | 31/01/2023 | 716.3 | 155.92 | 872.23 | Birbhum Division | Bolpur Mechanical Division | 4.64 | 0 | 25.96 | 0 | 30.6 | 4.64 | 0 | 25.96 | 0 | 30.6 | 3.51 | 5
355 | BIRBHUM | SM/14207 | Salan Piped Water Supply Scheme. | TSM/015574 | 40034637 | New | MVS | GO2223011788PH | 10/01/2023 | 738.9 | 39.27 | 778.17 | Birbhum Division | Bolpur Mechanical Division | 0 | 10.92 | 18 | 45.2 | 74.13 | 0 | 10.92 | 18 | 45.2 | 74.13 | 9.53 | 2
356 | BIRBHUM | SM/12597 | SAMSA PIPED WATER SUPPLY SCHEME. | TSM/013066 | 40031815 | New | MVS | GO2223007721PH | 15/09/2022 | 513.98 | 38.73 | 552.71 | Birbhum Division | Bolpur Mechanical Division | 10.76 | 27.81 | 38.7 | 0 | 77.27 | 10.76 | 27.81 | 38.7 | 0 | 77.27 | 13.98 | 60
357 | BIRBHUM | SM/13981 | Sandhyajol Piped Water Supply Scheme | TSM/015736 | 40039399 | New | MVS | GO2223010280PH | 01/12/2022 | 694.35 | 80.86 | 775.21 | Birbhum Division | Bolpur Mechanical Division | 4.58 | 10.24 | 58.16 | 0 | 72.99 | 4.58 | 10.24 | 58.16 | 0 | 72.99 | 9.42 | 2
358 | BIRBHUM | SM/14895 | SANTOSHPUR PIPED WATER SUPPLY SCHEME | TSM/016256 | 40037217 | New | MVS | GO2223013140PH | 04/02/2023 | 623.21 | 154.2 | 777.41 | Birbhum Division | Bolpur Mechanical Division | 4.53 | 0 | 27.27 | 0 | 31.8 | 4.53 | 0 | 27.27 | 0 | 31.8 | 4.09 | 5
359 | BIRBHUM | SM/12900 | SARIHA PIPED WATER SUPPLY SCHEME | TSM/012830 | 40033565 | New | MVS | GO2223008088PH | 22/09/2022 | 768.27 | 38.85 | 807.12 | Birbhum Division | Bolpur Mechanical Division | 155.83 | 13.56 | 13.23 | 0 | 182.62 | 155.83 | 13.56 | 13.23 | 0 | 182.62 | 22.63 | 50
360 | BIRBHUM | SM/13982 | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division | TSM/015731 | 40038336 | New | MVS | GO2223010308PH | 01/12/2022 | 618.07 | 80.86 | 698.94 | Birbhum Division | Bolpur Mechanical Division | 4.06 | 31.51 | 38.26 | 0 | 73.83 | 4.06 | 31.51 | 38.26 | 0 | 73.83 | 10.56 | 25
361 | BIRBHUM | SM/12890 | SEHANA PIPED WATER SUPPLY SCHEME. | TSM/011624 | 40032396 | New | MVS | GO2223008147PH | 23/09/2022 | 490.44 | 36.32 | 526.76 | Birbhum Division | Bolpur Mechanical Division | 53.63 | 28.82 | 25.56 | 0 | 108.01 | 53.63 | 31.82 | 25.56 | 0 | 111.01 | 21.07 | 55
362 | BIRBHUM | SM/14683 | Sekedda Piped Water Supply Scheme. | TSM/015615 | 40033730 | New | MVS | GO2223012784PH | 31/01/2023 | 2254.21 | 189.56 | 2443.77 | Birbhum Division | Bolpur Mechanical Division | 0 | 10.38 | 453.26 | 0 | 463.64 | 0 | 10.38 | 453.26 | 0 | 463.64 | 18.97 | 20
363 | BIRBHUM | SM/13650 | Sekupur piped water supply scheme. | TSM/015254 | 40034986 | New | MVS | GO2223009600PH | 11/11/2022 | 311.74 | 37.76 | 349.5 | Birbhum Division | Bolpur Mechanical Division | 0 | 0 | 12.93 | 0 | 12.93 | 0 | 0 | 12.93 | 0 | 12.93 | 3.7 | 5
364 | BIRBHUM | SM/14082 | Shankarpur Piped Water Scheme | TSM/016732 | 40037230 | New | MVS | GO2223010833PH | 12/12/2022 | 592.08 | 125.72 | 717.8 | Birbhum Division | Bolpur Mechanical Division | 112.45 | 41.76 | 113.26 | 0 | 267.48 | 112.45 | 43.21 | 113.26 | 0 | 268.93 | 37.47 | 79
365 | BIRBHUM | SM/13651 | Shaspur Piped Water Supply Scheme. | TSM/015337 | 40034102 | New | MVS | GO2223009593PH | 11/11/2022 | 717.05 | 77.77 | 794.81 | Birbhum Division | Bolpur Mechanical Division | 57.02 | 28.04 | 98.49 | 0 | 183.55 | 57.02 | 31.01 | 98.49 | 0 | 186.52 | 23.47 | 27
366 | BIRBHUM | SM/14956 | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | TSM/017121 | 40037063 | New | MVS | GO2223013085PH | 04/02/2023 | 586.97 | 157.65 | 744.62 | Birbhum Division | Bolpur Mechanical Division | 3.8 | 0 | 28.45 | 0 | 32.26 | 3.8 | 0 | 28.45 | 0 | 32.26 | 4.33 | 5
367 | BIRBHUM | SM/13476 | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | TSM/015462 | 40033759 | New | MVS | GO2223009256PH | 02/11/2022 | 676.96 | 77.77 | 754.73 | Birbhum Division | Bolpur Mechanical Division | 153.02 | 7.05 | 4 | 0 | 164.07 | 153.02 | 7.05 | 4 | 0 | 164.07 | 21.74 | 37
368 | BIRBHUM | SM/13647 | SHIRSHA PIPED WATER SUPPLY SCHEME | TSM/015543 | 40034490 | New | MVS | GO2223009636PH | 11/11/2022 | 922.61 | 51.43 | 974.04 | Birbhum Division | Bolpur Mechanical Division | 5.54 | 0 | 19.32 | 21.55 | 46.4 | 5.54 | 0 | 19.32 | 21.55 | 46.4 | 4.76 | 5
369 | BIRBHUM | SM/14087 | Shitalgram Piped Water Supply Scheme | TSM/016141 | 40037112 | New | MVS | GO2223010854PH | 12/12/2022 | 496.99 | 88.34 | 585.33 | Birbhum Division | Bolpur Mechanical Division | 192.94 | 35.04 | 19.51 | 0 | 247.49 | 192.94 | 36.55 | 19.51 | 0 | 249 | 42.54 | 70
370 | BIRBHUM | SM/13516 | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME | TSM/015539 | 40034469 | New | SVS | GO2223009208PH | 02/11/2022 | 250.16 | 38.2 | 288.36 | Birbhum Division | Bolpur Mechanical Division | 41.63 | 11.33 | 0 | 60.4 | 113.37 | 41.63 | 11.94 | 0 | 60.4 | 113.98 | 39.53 | 58
371 | BIRBHUM | SM/16272 | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) | TSM/017779 | 40053983 | New | MVS | GO2223014881PH | 24/02/2023 | 249.14 | 0 | 249.14 | Birbhum Division |  | 91.64 | 0 | 4.31 | 0 | 95.95 | 91.64 | 0 | 4.31 | 0 | 95.95 | 38.51 | 40
372 | BIRBHUM | SM/12908 | Simgram Piped Water Supply Scheme. | TSM/014678 | 40033597 | New | SVS | GO2223008089PH | 22/09/2022 | 93.11 | 32.77 | 125.88 | Birbhum Division | Bolpur Mechanical Division | 40.44 | 25.49 | 9.97 | 0 | 75.9 | 42.26 | 25.49 | 9.97 | 0 | 77.72 | 61.74 | 85
373 | BIRBHUM | SM/14208 | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | TSM/015492 | 40033741 | New | MVS | GO2223011787PH | 10/01/2023 | 352.53 | 55.12 | 407.65 | Birbhum Division | Bolpur Mechanical Division | 2.38 | 7.1 | 8.17 | 0 | 17.65 | 2.38 | 7.1 | 8.17 | 0 | 17.65 | 4.33 | 20
374 | BIRBHUM | SM/14537 | Siur Piped Water Supply Scheme. | TSM/015624 | 40034291 | New | MVS | GO2223012595PH | 30/01/2023 | 1057.41 | 112.45 | 1169.86 | Birbhum Division | Bolpur Mechanical Division | 259.21 | 85.87 | 192.73 | 0 | 537.81 | 259.21 | 60.57 | 192.73 | 0 | 512.51 | 43.81 | 65
375 | BIRBHUM | SM/13630 | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division | TSM/015442 | 40033794 | New | MVS | GO2223009589PH | 11/11/2022 | 798.1 | 105.77 | 903.87 | Birbhum Division | Bolpur Mechanical Division | 323.22 | 56.45 | 57.71 | 0 | 437.37 | 323.22 | 60.96 | 57.71 | 0 | 441.89 | 48.89 | 68
376 | BIRBHUM | SM/13652 | Srikantapur piped water supply scheme. | TSM/015507 | 40033709 | New | MVS | GO2223009601PH | 11/11/2022 | 736.46 | 37.85 | 774.31 | Birbhum Division | Bolpur Mechanical Division | 0 | 15.46 | 37.57 | 0 | 53.03 | 0 | 15.46 | 37.57 | 0 | 53.03 | 6.85 | 10
377 | BIRBHUM | SM/14160 | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division | TSM/015737 | 40038365 | New | MVS | GO2223011622PH | 05/01/2023 | 1058.12 | 127.52 | 1185.64 | Birbhum Division | Bolpur Mechanical Division | 102.08 | 85.98 | 11.38 | 0 | 199.43 | 102.08 | 86.9 | 11.38 | 0 | 200.35 | 16.9 | 50
378 | BIRBHUM | SM/13653 | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | TSM/015342 | 40034519 | New | MVS | GO2223009598PH | 11/11/2022 | 459.84 | 77.77 | 537.6 | Birbhum Division | Bolpur Mechanical Division | 84.04 | 29.82 | 0 | 0 | 113.86 | 84.04 | 29.82 | 0 | 0 | 113.86 | 21.18 | 75
379 | BIRBHUM | SM/18739 | Tamra Piped Water Supply Scheme | TSM/017038 | 40036974 | New | MVS | 2440/PHE/IV/W-626/23 | 17/08/2023 | 284.35 | 0 | 284.35 | Birbhum Division |  | 1.62 | 0 | 32.65 | 0 | 34.28 | 1.62 | 0 | 32.65 | 0 | 34.28 | 12.05 | 15
380 | BIRBHUM | SM/13979 | TATINAPARA PIPED WATER SUPPLY SCHEME | TSM/015894 | 40032984 | New | MVS | GO2223010282PH | 01/12/2022 | 799.17 | 81.31 | 880.48 | Birbhum Division | Bolpur Mechanical Division | 4.59 | 0 | 0 | 0 | 4.59 | 4.59 | 0 | 0 | 0 | 4.59 | 0.52 | 1
381 | BIRBHUM | SM/14968 | THIBA PIPEED WATER SUPPLY SCHEME | TSM/017115 | 40037061 | New | MVS | GO2223013086PH | 04/02/2023 | 380.14 | 157.94 | 538.07 | Birbhum Division | Bolpur Mechanical Division | 2.62 | 0 | 18.17 | 0 | 20.79 | 2.62 | 0 | 18.17 | 0 | 20.79 | 3.86 | 5
382 | BIRBHUM | SM/13127 | Tilai piped water supply scheme. | TSM/014575 | 40033577 | New | MVS | GO2223008561PH | 10/10/2022 | 367.06 | 37.64 | 404.7 | Birbhum Division | Bolpur Mechanical Division | 0 | 20.82 | 7.67 | 0 | 28.48 | 0 | 20.82 | 7.67 | 0 | 28.48 | 7.04 | 10
383 | BIRBHUM | SM/13654 | ULANDI PIPED WATER SUPPLY SCHEME | TSM/015500 | 40034395 | New | MVS | GO2223009635PH | 11/11/2022 | 586.99 | 39.04 | 626.02 | Birbhum Division | Bolpur Mechanical Division | 57.31 | 16.61 | 25.7 | 52.22 | 151.84 | 57.31 | 16.61 | 25.7 | 52.22 | 151.84 | 24.25 | 25
384 | BIRBHUM | SM/13626 | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | TSM/011722 | 40034207 | New | MVS | GO2223009647PH | 11/11/2022 | 439.83 | 38.53 | 478.35 | Birbhum Division | Bolpur Mechanical Division | 87.31 | 35.95 | 39.46 | 0 | 162.72 | 87.31 | 40.08 | 39.46 | 0 | 166.86 | 34.88 | 60
Total | [9 empty] | 233704.17 | 20728.58 | 254432.75 |  |  | 58096.57 | 7163.28 | 18652.55 | 1193.51 | 85105.92 | 58123.57 | 7421.43 | 18652.55 | 1193.51 | 85391.06 | 33.56