## JJM Schemes Financial Status (N
JJM Schemes Financial Status (NORTH 24 PARGANAS) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | NORTH 24 PARGANAS | SM/10781 | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | TSM/009736 | 40065640 | Augmentation | SVS | GO2223003526PH | 25/05/2022 | 477.26 | 42.43 | 519.69 | Barasat Division | Eastern Mechanical Division | 367.28 | 20.53 | 18.15 | 0 | 405.96 | 367.28 | 20.53 | 18.15 | 0 | 405.96 | 78.12 | 85
2 | NORTH 24 PARGANAS | SM/11214 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | TSM/009082 | 40002871 | Augmentation | MVS | GO2223004062PH | 13/06/2022 | 1343.1 | 31.45 | 1374.55 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 736.95 | 0 | 105.39 | 0 | 842.35 | 736.95 | 0 | 105.39 | 0 | 842.35 | 61.28 | 71
3 | NORTH 24 PARGANAS | SM/13984 | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | TSM/014709 | 40032846 | Augmentation | MVS | GO2223010356PH | 01/12/2022 | 273.98 | 0 | 273.98 | Barasat Division |  | 182.86 | 0 | 25.26 | 0 | 208.12 | 182.86 | 0 | 25.26 | 0 | 208.12 | 75.96 | 85
4 | NORTH 24 PARGANAS | SM/11558 | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | TSM/009584 | 40026999 | Augmentation | MVS | GO2223005423PH | 22/07/2022 | 630.9 | 63.85 | 694.76 | Barasat Arsenic Division | Eastern Mechanical Division | 334.18 | 35.1 | 41.83 | 0 | 411.11 | 334.18 | 35.1 | 41.83 | 0 | 411.11 | 59.17 | 49
5 | NORTH 24 PARGANAS | SM/14490 | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | TSM/015718 | 40032840 | Augmentation | MVS | GO2223012266PH | 20/01/2023 | 1497.85 | 64.43 | 1562.27 | Barasat Division | Eastern Mechanical Division | 221.46 | 3.5 | 214.04 | 0 | 438.99 | 221.46 | 3.5 | 214.04 | 0 | 438.99 | 28.1 | 30
6 | NORTH 24 PARGANAS | SM/13893 | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | TSM/015719 | 40032895 | Augmentation | MVS | GO2223010098PH | 25/11/2022 | 997.56 | 61.36 | 1058.92 | Barasat Division | Eastern Mechanical Division | 356.88 | 0 | 46.18 | 0 | 403.05 | 356.88 | 0 | 46.18 | 0 | 403.05 | 38.06 | 50
7 | NORTH 24 PARGANAS | SM/13894 | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | TSM/015720 | 40032853 | Augmentation | MVS | GO2223010058PH | 25/11/2022 | 1108.64 | 61.36 | 1170 | Barasat Division | Eastern Mechanical Division | 392.21 | 4.64 | 145.88 | 0 | 542.73 | 392.21 | 4.64 | 145.88 | 0 | 542.73 | 46.39 | 62
8 | NORTH 24 PARGANAS | SM/15323 | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | TSM/015721 | 40032777 | Augmentation | MVS | GO2223013655PH | 09/02/2023 | 1645.95 | 64.43 | 1710.38 | Barasat Division | Eastern Mechanical Division | 210.38 | 3.05 | 271.83 | 26.25 | 511.51 | 210.38 | 3.05 | 271.83 | 26.25 | 511.51 | 29.91 | 30
9 | NORTH 24 PARGANAS | SM/13892 | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | TSM/015722 | 40032819 | Augmentation | MVS | GO2223010097PH | 25/11/2022 | 1112.65 | 61.36 | 1174.01 | Barasat Division | Eastern Mechanical Division | 208.87 | 4.19 | 108.63 | 0 | 321.69 | 208.87 | 4.19 | 108.63 | 0 | 321.69 | 27.4 | 30
10 | NORTH 24 PARGANAS | SM/14511 | Augmentation of Bermajur Piped water supply scheme | TSM/018703 | 40060623 | Augmentation | SVS | GO2223012327PH | 20/01/2023 | 914.67 | 85.89 | 1000.57 | Barasat Division | Eastern Mechanical Division | 316.56 | 34.96 | 36.68 | 0 | 388.21 | 316.56 | 34.96 | 36.68 | 0 | 388.21 | 38.8 | 80
11 | NORTH 24 PARGANAS | SM/14514 | Augmentation of Chhota Sehara Piped water supply scheme | TSM/018702 | 40060612 | Augmentation | MVS | GO2223012323PH | 20/01/2023 | 746.18 | 45.09 | 791.27 | Barasat Division | Eastern Mechanical Division | 234.27 | 5.02 | 29.43 | 0 | 268.72 | 234.27 | 5.02 | 29.43 | 0 | 268.72 | 33.96 | 80
12 | NORTH 24 PARGANAS | SM/13420 | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/015209 | 40036608 | Augmentation | MVS | GO2223009246PH | 02/11/2022 | 403.44 | 45.18 | 448.62 | Barasat Arsenic Division | Eastern Mechanical Division | 161.53 | 0 | 49.81 | 0 | 211.34 | 161.53 | 0 | 49.81 | 0 | 211.34 | 47.11 | 13
13 | NORTH 24 PARGANAS | SM/11544 | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010752 | 40035125 | Augmentation | MVS | GO2223005393PH | 22/07/2022 | 591.88 | 42.57 | 634.45 | Barasat Arsenic Division | Eastern Mechanical Division | 286.48 | 10.2 | 45.07 | 0 | 341.74 | 286.48 | 10.2 | 45.07 | 0 | 341.74 | 53.86 | 48
14 | NORTH 24 PARGANAS | SM/11545 | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010751 | 40026966 | Augmentation | MVS | GO2223005394PH | 22/07/2022 | 264.52 | 20.85 | 285.37 | Barasat Arsenic Division | Eastern Mechanical Division | 172.76 | 2.06 | 1.53 | 29.72 | 206.08 | 172.76 | 2.06 | 1.53 | 29.72 | 206.08 | 72.21 | 60
15 | NORTH 24 PARGANAS | SM/11559 | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010753 | 40026940 | Augmentation | MVS | GO2223005392PH | 22/07/2022 | 233.01 | 20.85 | 253.86 | Barasat Arsenic Division | Eastern Mechanical Division | 169.11 | 0 | 0 | 0 | 169.11 | 169.11 | 0 | 0 | 0 | 169.11 | 66.61 | 50
16 | NORTH 24 PARGANAS | SM/13468 | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | TSM/015553 | 40033263 | Augmentation | SVS | GO2223009234PH | 02/11/2022 | 975.56 | 80.64 | 1056.2 | Barasat Division | Eastern Mechanical Division | 575.23 | 27.2 | 99.83 | 11.99 | 714.25 | 575.23 | 27.2 | 99.83 | 11.99 | 714.25 | 67.62 | 70
17 | NORTH 24 PARGANAS | SM/18416 | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | TSM/015584 | 40033542 | Augmentation | MVS | 1871/PHE-28011/200/2022-ESTT CELL-Dept. of PHE | 13/07/2023 | 2601.03 | 115 | 2716.04 | Barasat Division | Eastern Mechanical Division | 451.68 | 0 | 293.27 | 23.73 | 768.68 | 451.68 | 0 | 293.27 | 23.73 | 768.68 | 28.3 | 38
18 | NORTH 24 PARGANAS | SM/14161 | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | TSM/015769 | 40032791 | Augmentation | MVS | GO2223011630PH | 05/01/2023 | 2650.35 | 134.5 | 2784.85 | Barasat Division | Eastern Mechanical Division | 570.53 | 18.12 | 218.29 | 40.53 | 847.46 | 570.53 | 18.12 | 218.29 | 40.53 | 847.46 | 30.43 | 36
19 | NORTH 24 PARGANAS | SM/14127 | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | TSM/011254 | 40032898 | Augmentation | MVS | GO2223011523PH | 02/01/2023 | 454.3 | 40.32 | 494.62 | Barasat Division | Eastern Mechanical Division | 91.5 | 17.05 | 30.43 | 0 | 138.98 | 91.5 | 17.05 | 30.43 | 0 | 138.98 | 28.1 | 38
20 | NORTH 24 PARGANAS | SM/15324 | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | TSM/015764 | 40032816 | Augmentation | SVS | GO2223013702PH | 10/02/2023 | 1110.55 | 73.61 | 1184.15 | Barasat Division | Eastern Mechanical Division | 265.73 | 0 | 85.65 | 24.2 | 375.58 | 265.73 | 0 | 85.65 | 24.2 | 375.58 | 31.72 | 38
21 | NORTH 24 PARGANAS | SM/14733 | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | TSM/015552 | 40033562 | Augmentation | SVS | GO2223012649PH | 31/01/2023 | 686.09 | 46 | 732.09 | Barasat Division | Eastern Mechanical Division | 347.63 | 24.17 | 16.51 | 0 | 388.31 | 347.63 | 24.17 | 16.51 | 0 | 388.31 | 53.04 | 62
22 | NORTH 24 PARGANAS | SM/13446 | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | TSM/011247 | 40032100 | Augmentation | SVS | GO2223009241PH | 02/11/2022 | 824.14 | 42.93 | 867.07 | Barasat Division | Eastern Mechanical Division | 181.27 | 0 | 117.14 | 23.95 | 322.36 | 181.27 | 0 | 117.14 | 23.95 | 322.36 | 37.18 | 41
23 | NORTH 24 PARGANAS | SM/13471 | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | TSM/011244 | 40032969 | Augmentation | SVS | GO2223009260PH | 02/11/2022 | 473.88 | 64.4 | 538.28 | Barasat Division | Eastern Mechanical Division | 211.12 | 0 | 70.08 | 23.55 | 304.75 | 211.12 | 0 | 70.08 | 23.55 | 304.75 | 56.62 | 55
24 | NORTH 24 PARGANAS | SM/13469 | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | TSM/011245 | 40032946 | Augmentation | SVS | GO2223009261PH | 02/11/2022 | 1086.94 | 64.4 | 1151.34 | Barasat Division | Eastern Mechanical Division | 137.96 | 0 | 86.51 | 0 | 224.47 | 137.96 | 0 | 86.51 | 0 | 224.47 | 19.5 | 30
25 | NORTH 24 PARGANAS | SM/11940 | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | TSM/012009 | 40035639 | Augmentation | MVS | GO2223006667PH | 24/08/2022 | 200.23 | 0 | 200.23 | North 24 Pgs W/S Division I |  | 59.45 | 0 | 0 | 0 | 59.45 | 59.45 | 0 | 0 | 0 | 59.45 | 29.69 | 35
26 | NORTH 24 PARGANAS | SM/11664 | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | TSM/011212 | 40059430 | Augmentation | MVS | GO2223005641PH | 27/07/2022 | 939.47 | 71.09 | 1010.56 | Barasat Division | Eastern Mechanical Division | 485.31 | 25.26 | 135.86 | 0 | 646.43 | 485.31 | 25.26 | 135.86 | 0 | 646.43 | 63.97 | 10
27 | NORTH 24 PARGANAS | SM/11533 | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | TSM/011084 | 40036108 | Augmentation | MVS | GO2223005234PH | 19/07/2022 | 396.4 | 40.41 | 436.8 | Barasat Division | Eastern Mechanical Division | 105.64 | 19.72 | 22.67 | 10.76 | 158.79 | 105.64 | 19.72 | 22.67 | 10.76 | 158.79 | 36.35 | 70
28 | NORTH 24 PARGANAS | SM/11700 | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | TSM/011315 | 40029255 | Augmentation | MVS | GO2223005720PH | 29/07/2022 | 1079.51 | 41.57 | 1121.08 | Barasat Division | Eastern Mechanical Division | 435.76 | 0 | 116.62 | 22.94 | 575.33 | 435.76 | 0 | 116.62 | 22.94 | 575.33 | 51.32 | 70
29 | NORTH 24 PARGANAS | SM/10558 | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | TSM/010450 | 40018934 | Augmentation | MVS | GO2223000387PH | 18/04/2022 | 860.26 | 41.7 | 901.97 | Barasat Division | Eastern Mechanical Division | 314.21 | 0 | 0 | 0 | 314.21 | 314.21 | 0 | 0 | 0 | 314.21 | 34.84 | 80
30 | NORTH 24 PARGANAS | SM/11597 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | TSM/011163 | 40036144 | Augmentation | MVS | GO2223005374PH | 22/07/2022 | 317.52 | 39.58 | 357.1 | Barasat Division | Eastern Mechanical Division | 163.62 | 0 | 20.08 | 0 | 183.7 | 163.62 | 0 | 20.08 | 0 | 183.7 | 51.44 | 80
31 | NORTH 24 PARGANAS | SM/11705 | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011252 | 40026475 | Augmentation | SVS | GO2223005727PH | 29/07/2022 | 504.75 | 20.84 | 525.59 | Barasat Arsenic Division | Eastern Mechanical Division | 282.49 | 10.12 | 0 | 0 | 292.62 | 282.49 | 10.12 | 0 | 0 | 292.62 | 55.67 | 51
32 | NORTH 24 PARGANAS | SM/13040 | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | TSM/011320 | 40029321 | Augmentation | MVS | GO2223008513PH | 29/09/2022 | 1367.83 | 62.36 | 1430.19 | Barasat Division | Eastern Mechanical Division | 660.5 | 0 | 120.68 | 0 | 781.19 | 660.5 | 0 | 120.68 | 0 | 781.19 | 54.62 | 60
33 | NORTH 24 PARGANAS | SM/10102 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | TSM/009323 | 40002976 | Augmentation | MVS | GO2122009115PH | 02/02/2022 | 620.68 | 0 | 620.68 | North 24 Pgs W/S Division I |  | 249.53 | 0 | 31.59 | 0 | 281.12 | 249.53 | 0 | 31.59 | 0 | 281.12 | 45.29 | 52
34 | NORTH 24 PARGANAS | SM/10310 | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | TSM/009251 | 40005414 | Augmentation | MVS | GO2122010483PH | 04/03/2022 | 672.9 | 32.61 | 705.5 | Barasat Division | Eastern Mechanical Division | 329.64 | 19.3 | 63.39 | 0 | 412.33 | 329.64 | 19.3 | 63.39 | 0 | 412.33 | 58.45 | 70
35 | NORTH 24 PARGANAS | SM/11756 | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | TSM/011318 | 40029290 | Augmentation | MVS | GO2223005912PH | 02/08/2022 | 963.51 | 41.57 | 1005.08 | Barasat Division | Eastern Mechanical Division | 287.61 | 27.93 | 33.28 | 0 | 348.82 | 287.61 | 27.93 | 33.28 | 0 | 348.82 | 34.71 | 60
36 | NORTH 24 PARGANAS | SM/11701 | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | TSM/011316 | 40029273 | Augmentation | MVS | GO2223005718PH | 29/07/2022 | 565.42 | 41.57 | 606.99 | Barasat Division | Eastern Mechanical Division | 306.72 | 0 | 10.1 | 0 | 316.82 | 306.72 | 0 | 10.1 | 0 | 316.82 | 52.2 | 70
37 | NORTH 24 PARGANAS | SM/10109 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | TSM/009515 | 40002703 | Augmentation | MVS | GO2122009114PH | 02/02/2022 | 843.1 | 0 | 843.1 | North 24 Pgs W/S Division I |  | 614.09 | 0 | 116 | 0 | 730.1 | 614.09 | 0 | 116 | 0 | 730.1 | 86.6 | 95
38 | NORTH 24 PARGANAS | SM/18618 | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | TSM/011390 | 40062805 | Augmentation | SVS | 2161/PHE-28011/238/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 955.72 | 62.36 | 1018.08 | Barasat Division | Eastern Mechanical Division | 439.26 | 0 | 107.31 | 0 | 546.57 | 439.26 | 0 | 107.31 | 0 | 546.57 | 53.69 | 60
39 | NORTH 24 PARGANAS | SM/12276 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | TSM/011166 | 40022726 | Augmentation | MVS | GO2223007385PH | 09/09/2022 | 1436.99 | 39.58 | 1476.58 | Barasat Division | Eastern Mechanical Division | 767.42 | 24.11 | 136.32 | 0 | 927.84 | 767.42 | 24.11 | 136.32 | 0 | 927.84 | 62.84 | 80
40 | NORTH 24 PARGANAS | SM/11634 | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | TSM/011024 | 40035335 | Augmentation | MVS | GO2223005581PH | 26/07/2022 | 470.94 | 40.41 | 511.35 | Barasat Division | Eastern Mechanical Division | 169.23 | 21.9 | 103.67 | 0 | 294.8 | 169.23 | 21.9 | 103.67 | 0 | 294.8 | 57.65 | 65
41 | NORTH 24 PARGANAS | SM/11704 | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | TSM/011389 | 40030494 | Augmentation | MVS | GO2223005719PH | 29/07/2022 | 810.88 | 41.57 | 852.45 | Barasat Division | Eastern Mechanical Division | 375.4 | 3.67 | 134.42 | 0 | 513.49 | 375.4 | 3.67 | 134.42 | 0 | 513.49 | 60.24 | 70
42 | NORTH 24 PARGANAS | SM/11987 | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | TSM/011200 | 40036205 | Augmentation | MVS | GO2223006902PH | 01/09/2022 | 1716.2 | 100.62 | 1816.81 | Barasat Division | Eastern Mechanical Division | 1101.93 | 71.8 | 68.8 | 0 | 1242.53 | 1101.93 | 71.77 | 68.8 | 0 | 1242.5 | 68.39 | 80
43 | NORTH 24 PARGANAS | SM/10514 | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | TSM/010006 | 40026963 | Augmentation | MVS | GO2223000235PH | 13/04/2022 | 950.13 | 33.75 | 983.88 | Barasat Division | Eastern Mechanical Division | 700.65 | 0 | 36.38 | 0 | 737.04 | 700.65 | 0 | 36.38 | 0 | 737.04 | 74.91 | 82
44 | NORTH 24 PARGANAS | SM/11534 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | TSM/011109 | 40030441 | Augmentation | SVS | GO2223005247PH | 19/07/2022 | 387.01 | 35.74 | 422.75 | Barasat Division | Eastern Mechanical Division | 211 | 0 | 7.57 | 0 | 218.57 | 211 | 0 | 7.57 | 0 | 218.57 | 51.7 | 85
45 | NORTH 24 PARGANAS | SM/12126 | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | TSM/011161 | 40036203 | Augmentation | MVS | GO2223007075PH | 06/09/2022 | 2381.85 | 134.3 | 2516.15 | Barasat Division | Eastern Mechanical Division | 775.32 | 3.25 | 323.82 | 0 | 1102.39 | 775.32 | 3.25 | 323.82 | 0 | 1102.39 | 43.81 | 50
46 | NORTH 24 PARGANAS | SM/10782 | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | TSM/010461 | 40018990 | Augmentation | MVS | GO2223003488PH | 25/05/2022 | 1057.58 | 35.56 | 1093.14 | Barasat Division | Eastern Mechanical Division | 404.59 | 19.18 | 276.16 | 0 | 699.93 | 404.59 | 19.18 | 276.16 | 0 | 699.93 | 64.03 | 65
47 | NORTH 24 PARGANAS | SM/13737 | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | TSM/011746 | 1723424 | Augmentation | MVS | GO2223009850PH | 17/11/2022 | 1375.94 | 83.14 | 1459.08 | Barasat Division | Eastern Mechanical Division | 422.34 | 0 | 141.78 | 0 | 564.13 | 422.34 | 0 | 141.78 | 0 | 564.13 | 38.66 | 60
48 | NORTH 24 PARGANAS | SM/12895 | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | TSM/011747 | 1723424 | Augmentation | MVS | GO2223008137PH | 23/09/2022 | 795.95 | 41.57 | 837.52 | Barasat Division | Eastern Mechanical Division | 352.33 | 5.77 | 71.59 | 0 | 429.7 | 352.33 | 5.77 | 71.59 | 0 | 429.7 | 51.31 | 60
49 | NORTH 24 PARGANAS | SM/14162 | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | TSM/011276 | 40032894 | Augmentation | MVS | GO2223011629PH | 05/01/2023 | 1945.88 | 101.21 | 2047.08 | Barasat Division | Eastern Mechanical Division | 153.25 | 17.33 | 158.32 | 35.97 | 364.87 | 153.25 | 17.33 | 158.32 | 35.97 | 364.87 | 17.82 | 20
50 | NORTH 24 PARGANAS | SM/10374 | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | TSM/009733 | 40007144 | Augmentation | SVS | GO2122010928PH | 16/03/2022 | 1094.7 | 42.43 | 1137.13 | Barasat Division | Eastern Mechanical Division | 588.64 | 21.15 | 8.01 | 0 | 617.79 | 588.64 | 21.15 | 8.01 | 0 | 617.79 | 54.33 | 70
51 | NORTH 24 PARGANAS | SM/11536 | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | TSM/011171 | 40018936 | Augmentation | MVS | GO2223005246PH | 19/07/2022 | 954.51 | 109.49 | 1064.01 | Barasat Division | Eastern Mechanical Division | 661.45 | 57.89 | 3.29 | 0 | 722.62 | 661.45 | 59.65 | 3.29 | 0 | 724.39 | 68.08 | 73
52 | NORTH 24 PARGANAS | SM/10371 | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | TSM/009734 | 40007148 | Augmentation | SVS | GO2122010932PH | 16/03/2022 | 1111.13 | 40.41 | 1151.54 | Barasat Division | Eastern Mechanical Division | 504.81 | 19.92 | 5.96 | 0 | 530.68 | 504.81 | 19.92 | 5.96 | 0 | 530.68 | 46.08 | 80
53 | NORTH 24 PARGANAS | SM/11669 | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | TSM/011167 | 40037196 | Augmentation | MVS | GO2223005635PH | 27/07/2022 | 1026.66 | 41.57 | 1068.23 | Barasat Division | Eastern Mechanical Division | 534.61 | 13.02 | 88.41 | 0 | 636.05 | 534.61 | 13.02 | 88.41 | 0 | 636.05 | 59.54 | 70
54 | NORTH 24 PARGANAS | SM/10584 | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | TSM/010452 | 40018881 | Augmentation | MVS | GO2223000383PH | 18/04/2022 | 532.75 | 43.8 | 576.54 | Barasat Division | Eastern Mechanical Division | 166.01 | 26.52 | 0 | 0 | 192.53 | 166.01 | 26.52 | 0 | 0 | 192.53 | 33.39 | 70
55 | NORTH 24 PARGANAS | SM/11586 | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | TSM/011072 | 40036135 | Augmentation | MVS | GO2223005411PH | 22/07/2022 | 446.99 | 40.41 | 487.39 | Barasat Division | Eastern Mechanical Division | 210.11 | 0 | 6.16 | 0 | 216.27 | 210.11 | 0 | 6.16 | 0 | 216.27 | 44.37 | 60
56 | NORTH 24 PARGANAS | SM/18582 | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | TSM/011307 | 40033230 | Augmentation | MVS | 2145/PHE-28011/130/2022-SCHM CELL-Dept. of PHE | 31/07/2023 | 1261.7 | 41.57 | 1303.27 | Barasat Division | Eastern Mechanical Division | 807.5 | 0 | 124.58 | 7.38 | 939.46 | 807.5 | 0 | 124.58 | 7.38 | 939.46 | 72.09 | 80
57 | NORTH 24 PARGANAS | SM/10587 | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | TSM/010456 | 40029463 | Augmentation | MVS | GO2223000361 PH | 18/04/2022 | 976.51 | 54.62 | 1031.13 | Barasat Division | Eastern Mechanical Division | 499.95 | 7.75 | 41.96 | 0 | 549.66 | 499.95 | 7.75 | 41.96 | 0 | 549.66 | 53.31 | 75
58 | NORTH 24 PARGANAS | SM/13313 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | TSM/011206 | 40036802 | Augmentation | MVS | GO2223008873PH | 17/10/2022 | 1473.91 | 88.57 | 1562.48 | Barasat Division | Eastern Mechanical Division | 717.55 | 45.99 | 80.08 | 0 | 843.61 | 717.55 | 45.99 | 80.08 | 0 | 843.61 | 53.99 | 50
59 | NORTH 24 PARGANAS | SM/10299 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | TSM/009123 | 1723303 | Augmentation | MVS | GO2122010325PH | 02/03/2022 | 429.81 | 0 | 429.81 | North 24 Pgs W/S Division I |  | 213.97 | 0 | 16.11 | 0 | 230.08 | 213.97 | 0 | 16.11 | 0 | 230.08 | 53.53 | 60
60 | NORTH 24 PARGANAS | SM/11592 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | TSM/011106 | 40023367 | Augmentation | SVS | GO2223005407PH | 22/07/2022 | 708.05 | 35.74 | 743.79 | Barasat Division | Eastern Mechanical Division | 264.87 | 29.71 | 196.01 | 0 | 490.59 | 264.87 | 29.71 | 196.01 | 0 | 490.59 | 65.96 | 80
61 | NORTH 24 PARGANAS | SM/13767 | Augmentation of ground water based piped water supply scheme for Chhaimalpur | TSM/012028 | 40032932 | Augmentation | MVS | GO2223009912PH | 18/11/2022 | 349.82 | 39.58 | 389.4 | Barasat Division | Eastern Mechanical Division | 223.84 | 35.1 | 3.43 | 0 | 262.37 | 223.84 | 35.1 | 3.43 | 0 | 262.37 | 67.38 | 90
62 | NORTH 24 PARGANAS | SM/11593 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | TSM/011107 | 40022722 | Augmentation | MVS | GO2223005410PH | 22/07/2022 | 920.37 | 33.75 | 954.12 | Barasat Division | Eastern Mechanical Division | 484.91 | 19.38 | 56.04 | 0 | 560.33 | 484.91 | 19.38 | 56.04 | 0 | 560.33 | 58.73 | 70
63 | NORTH 24 PARGANAS | SM/11594 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | TSM/011110 | 40022738 | Augmentation | MVS | GO2223005417PH | 22/07/2022 | 718.46 | 35.74 | 754.2 | Barasat Division | Eastern Mechanical Division | 323.32 | 19.6 | 159.65 | 0 | 502.57 | 323.32 | 19.6 | 159.65 | 0 | 502.57 | 66.64 | 80
64 | NORTH 24 PARGANAS | SM/11535 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | TSM/011169 | 40022721 | Augmentation | MVS | GO2223005244PH | 19/07/2022 | 436.85 | 33.75 | 470.6 | Barasat Division | Eastern Mechanical Division | 213.49 | 20.13 | 59.3 | 0 | 292.93 | 213.49 | 20.13 | 59.3 | 0 | 292.93 | 62.25 | 70
65 | NORTH 24 PARGANAS | SM/10690 | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | TSM/010451 | 40036817 | Augmentation | MVS | GO2223001397PH | 12/05/2022 | 815.28 | 54.62 | 869.9 | Barasat Division | Eastern Mechanical Division | 537.67 | 15.4 | 41.21 | 0 | 594.28 | 537.67 | 15.4 | 41.21 | 0 | 594.28 | 68.32 | 75
66 | NORTH 24 PARGANAS | SM/11754 | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC | TSM/011431 | 40029482 | Augmentation | MVS | GO2223005904PH | 02/08/2022 | 145.95 | 20.2 | 166.16 | Barasat Division | Eastern Mechanical Division | 43.28 | 0 | 17.36 | 0 | 60.63 | 43.28 | 0 | 17.36 | 0 | 60.63 | 36.49 | 65
67 | NORTH 24 PARGANAS | SM/12123 | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC | TSM/010932 | 40036196 | Augmentation | MVS | GO2223007076PH | 06/09/2022 | 1478.59 | 61.14 | 1539.73 | Barasat Division | Eastern Mechanical Division | 736.72 | 15.54 | 129.86 | 0 | 882.12 | 736.72 | 15.54 | 129.86 | 0 | 882.12 | 57.29 | 60
68 | NORTH 24 PARGANAS | SM/12277 | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | TSM/010933 | 40035631 | Augmentation | MVS | GO2223007391PH | 09/09/2022 | 1926.5 | 91.88 | 2018.38 | Barasat Division | Eastern Mechanical Division | 1059.5 | 0 | 261.29 | 0 | 1320.78 | 1059.5 | 0 | 261.29 | 0 | 1320.78 | 65.44 | 70
69 | NORTH 24 PARGANAS | SM/11658 | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | TSM/011370 | 40022577 | Augmentation | MVS | GO2223005636PH | 27/07/2022 | 677.36 | 41.57 | 718.93 | Barasat Division | Eastern Mechanical Division | 342.54 | 0 | 85.15 | 0 | 427.7 | 342.54 | 0 | 85.15 | 0 | 427.7 | 59.49 | 75
70 | NORTH 24 PARGANAS | SM/12568 | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | TSM/011317 | 40029281 | Augmentation | MVS | GO2223007712PH | 14/09/2022 | 1635.7 | 41.57 | 1677.27 | Barasat Division | Eastern Mechanical Division | 694.3 | 0 | 289.7 | 25.6 | 1009.6 | 694.3 | 0 | 289.7 | 25.6 | 1009.6 | 60.19 | 70
71 | NORTH 24 PARGANAS | SM/11703 | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | TSM/011421 | 40022709 | Augmentation | MVS | GO2223005722PH | 29/07/2022 | 414.92 | 40.41 | 455.33 | Barasat Division | Eastern Mechanical Division | 218.56 | 0 | 0 | 0 | 218.56 | 218.56 | 0 | 0 | 0 | 218.56 | 48 | 70
72 | NORTH 24 PARGANAS | SM/11537 | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | TSM/011178 | 40060048 | Augmentation | MVS | GO2223005245PH | 19/07/2022 | 664.86 | 39.58 | 704.44 | Barasat Division | Eastern Mechanical Division | 295.73 | 20.11 | 7.62 | 0 | 323.47 | 295.73 | 20.11 | 7.62 | 0 | 323.47 | 45.92 | 95
73 | NORTH 24 PARGANAS | SM/17679 | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | TSM/011275 | 40033868 | Augmentation | SVS | GO2223016648PH | 17/03/2023 | 922.81 | 46 | 968.81 | Barasat Division | Eastern Mechanical Division | 105.85 | 3.79 | 112.6 | 0 | 222.24 | 105.85 | 3.79 | 112.6 | 0 | 222.24 | 22.94 | 30
74 | NORTH 24 PARGANAS | SM/11753 | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | TSM/011429 | 40029481 | Augmentation | MVS | GO2223005983PH | 03/08/2022 | 465.1 | 40.41 | 505.51 | Barasat Division | Eastern Mechanical Division | 202.41 | 0 | 16.05 | 0 | 218.46 | 202.41 | 0 | 16.05 | 0 | 218.46 | 43.22 | 60
75 | NORTH 24 PARGANAS | SM/12274 | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | TSM/011071 | 40035375 | Augmentation | MVS | GO2223007387PH | 09/09/2022 | 1586.76 | 60.61 | 1647.37 | Barasat Division | Eastern Mechanical Division | 535.09 | 0 | 138.07 | 22.73 | 695.89 | 535.09 | 0 | 138.07 | 22.73 | 695.89 | 42.24 | 60
76 | NORTH 24 PARGANAS | SM/11527 | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | TSM/011069 | 40036096 | Augmentation | MVS | GO2223005230PH | 19/07/2022 | 660.27 | 60.61 | 720.88 | Barasat Division | Eastern Mechanical Division | 303 | 30.16 | 34.28 | 0 | 367.44 | 303 | 30.16 | 34.28 | 0 | 367.44 | 50.97 | 70
77 | NORTH 24 PARGANAS | SM/11668 | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC | TSM/011165 | 40036157 | Augmentation | MVS | GO2223005634PH | 27/07/2022 | 841.02 | 39.58 | 880.6 | Barasat Division | Eastern Mechanical Division | 421.05 | 36.87 | 133.75 | 0 | 591.67 | 421.05 | 36.87 | 133.75 | 0 | 591.67 | 67.19 | 80
78 | NORTH 24 PARGANAS | SM/11660 | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | TSM/011387 | 40022568 | Augmentation | MVS | GO2223005637PH | 27/07/2022 | 651.99 | 41.57 | 693.56 | Barasat Division | Eastern Mechanical Division | 198.49 | 19.82 | 91.26 | 0 | 309.57 | 205.05 | 19.82 | 91.26 | 0 | 316.13 | 45.58 | 70
79 | NORTH 24 PARGANAS | SM/10370 | Augmentation of Ground water based piped water supply scheme for Durgamandap | TSM/009737 | 40007150 | Augmentation | SVS | GO2122010918PH | 16/03/2022 | 824.92 | 42.43 | 867.35 | Barasat Division | Eastern Mechanical Division | 459.64 | 20.71 | 0 | 0 | 480.35 | 459.64 | 20.71 | 0 | 0 | 480.35 | 55.38 | 70
80 | NORTH 24 PARGANAS | SM/12275 | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | TSM/011157 | 40035515 | Augmentation | MVS | GO2223007388PH | 09/09/2022 | 1511.98 | 41.57 | 1553.55 | Barasat Division | Eastern Mechanical Division | 0 | 0 | 96.34 | 0 | 96.34 | 0 | 0 | 96.34 | 0 | 96.34 | 6.2 | 70
81 | NORTH 24 PARGANAS | SM/12111 | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | TSM/010457 | 40035515 | Augmentation | MVS | GO2223006987PH | 02/09/2022 | 888.35 | 43.8 | 932.15 | Barasat Division | Eastern Mechanical Division | 580.27 | 18.16 | 0 | 0 | 598.43 | 580.27 | 18.16 | 0 | 0 | 598.43 | 64.2 | 70
82 | NORTH 24 PARGANAS | SM/11707 | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011253 | 40026488 | Augmentation | SVS | GO2223005728PH | 29/07/2022 | 569.2 | 44.76 | 613.96 | Barasat Arsenic Division | Eastern Mechanical Division | 318.53 | 14.73 | 0 | 0 | 333.26 | 318.53 | 14.73 | 0 | 0 | 333.26 | 54.28 | 41
83 | NORTH 24 PARGANAS | SM/11629 | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | TSM/011078 | 40034961 | Augmentation | MVS | GO2223005586PH | 26/07/2022 | 657.3 | 40.41 | 697.7 | Barasat Division | Eastern Mechanical Division | 306.28 | 0 | 57.91 | 0 | 364.2 | 306.28 | 0 | 57.91 | 0 | 364.2 | 52.2 | 70
84 | NORTH 24 PARGANAS | SM/10392 | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | TSM/009735 | 40007158 | Augmentation | SVS | GO2122011266PH | 24/03/2022 | 858.9 | 40.41 | 899.31 | Barasat Division | Eastern Mechanical Division | 436.09 | 17.25 | 10.3 | 0 | 463.63 | 436.09 | 17.25 | 10.3 | 0 | 463.63 | 51.55 | 80
85 | NORTH 24 PARGANAS | SM/11541 | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | TSM/011028 | 40022713 | Augmentation | MVS | GO2223005238PH | 19/07/2022 | 227.97 | 20.2 | 248.17 | Barasat Division | Eastern Mechanical Division | 55.84 | 0 | 0 | 0 | 55.84 | 55.84 | 0 | 0 | 0 | 55.84 | 22.5 | 60
86 | NORTH 24 PARGANAS | SM/11761 | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | TSM/011197 | 40033222 | Augmentation | MVS | GO2223005910PH | 02/08/2022 | 665.63 | 39.58 | 705.21 | Barasat Division | Eastern Mechanical Division | 375.2 | 0 | 13.82 | 0 | 389.01 | 375.2 | 0 | 13.82 | 0 | 389.01 | 55.16 | 80
87 | NORTH 24 PARGANAS | SM/11762 | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | TSM/011198 | 40022724 | Augmentation | MVS | GO2223005911PH | 02/08/2022 | 806.38 | 39.58 | 845.97 | Barasat Division | Eastern Mechanical Division | 208.37 | 16.35 | 123.44 | 0 | 348.17 | 208.37 | 16.35 | 123.44 | 0 | 348.17 | 41.16 | 70
88 | NORTH 24 PARGANAS | SM/10519 | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | TSM/010005 | 40026956 | Augmentation | MVS | GO2223000250PH | 13/04/2022 | 776.76 | 50.61 | 827.36 | Barasat Division | Eastern Mechanical Division | 449.48 | 16.05 | 179.95 | 0 | 645.49 | 449.48 | 16.05 | 179.95 | 0 | 645.49 | 78.02 | 90
89 | NORTH 24 PARGANAS | SM/10309 | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | TSM/009254 | 40005273 | Augmentation | MVS | GO2122010479PH | 04/03/2022 | 531.01 | 34.57 | 565.58 | Barasat Division | Eastern Mechanical Division | 323.85 | 22.57 | 118.73 | 0 | 465.15 | 323.85 | 22.57 | 118.73 | 0 | 465.15 | 82.24 | 85
90 | NORTH 24 PARGANAS | SM/11540 | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | TSM/010862 | 40036002 | Augmentation | MVS | GO2223005249PH | 19/07/2022 | 916.88 | 39.58 | 956.46 | Barasat Division | Eastern Mechanical Division | 476.21 | 0 | 98.69 | 0 | 574.89 | 476.21 | 0 | 98.69 | 0 | 574.89 | 60.11 | 75
91 | NORTH 24 PARGANAS | SM/11666 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | TSM/011105 | 40022717 | Augmentation | MVS | GO2223005646PH | 27/07/2022 | 950.53 | 39.58 | 990.11 | Barasat Division | Eastern Mechanical Division | 403.09 | 7.28 | 75.92 | 0 | 486.29 | 403.09 | 7.28 | 75.92 | 0 | 486.29 | 49.11 | 70
92 | NORTH 24 PARGANAS | SM/11627 | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | TSM/011073 | 40034944 | Augmentation | MVS | GO2223005583PH | 26/07/2022 | 399.09 | 40.41 | 439.49 | Barasat Division | Eastern Mechanical Division | 179.93 | 0 | 58.11 | 21.92 | 259.96 | 179.93 | 0 | 58.11 | 21.92 | 259.96 | 59.15 | 75
93 | NORTH 24 PARGANAS | SM/11599 | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | TSM/010856 | 40036148 | Augmentation | MVS | GO2223005357PH | 22/07/2022 | 591.55 | 39.58 | 631.14 | Barasat Division | Eastern Mechanical Division | 489.35 | 10.17 | 0 | 0 | 499.52 | 489.35 | 10.17 | 0 | 0 | 499.52 | 79.15 | 85
94 | NORTH 24 PARGANAS | SM/11532 | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | TSM/011083 | 40022746 | Augmentation | MVS | GO2223005248PH | 20/07/2022 | 714.46 | 40.41 | 754.87 | Barasat Division | Eastern Mechanical Division | 384.56 | 17.24 | 53.92 | 0 | 455.72 | 384.56 | 17.24 | 53.92 | 0 | 455.72 | 60.37 | 75
95 | NORTH 24 PARGANAS | SM/11764 | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | TSM/011388 | 40028582 | Augmentation | MVS | GO2223005905PH | 02/08/2022 | 921.22 | 62.36 | 983.58 | Barasat Division | Eastern Mechanical Division | 193.11 | 0 | 189.08 | 0 | 382.18 | 193.11 | 0 | 189.08 | 0 | 382.18 | 38.86 | 65
96 | NORTH 24 PARGANAS | SM/13405 | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | TSM/011319 | 40029316 | Augmentation | MVS | GO2223009058PH | 21/10/2022 | 2930.79 | 83.14 | 3013.93 | Barasat Division | Eastern Mechanical Division | 778.6 | 15.59 | 485.54 | 22.76 | 1302.49 | 778.6 | 15.59 | 485.54 | 22.76 | 1302.49 | 43.22 | 20
97 | NORTH 24 PARGANAS | SM/11604 | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | TSM/011023 | 40029311 | Augmentation | MVS | GO2223005415PH | 22/07/2022 | 666.24 | 40.41 | 706.65 | Barasat Division | Eastern Mechanical Division | 364.61 | 0 | 16.02 | 0 | 380.63 | 364.61 | 0 | 16.02 | 0 | 380.63 | 53.86 | 65
98 | NORTH 24 PARGANAS | SM/11759 | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | TSM/011374 | 40022566 | Augmentation | MVS | GO2223005909PH | 02/08/2022 | 764.71 | 41.57 | 806.28 | Barasat Division | Eastern Mechanical Division | 364.84 | 15.3 | 34.72 | 0 | 414.86 | 364.84 | 15.3 | 34.72 | 0 | 414.86 | 51.45 | 75
99 | NORTH 24 PARGANAS | SM/11633 | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | TSM/011030 | 40036123 | Augmentation | MVS | GO2223005577PH | 26/07/2022 | 986.68 | 40.41 | 1027.09 | Barasat Division | Eastern Mechanical Division | 346.73 | 21.11 | 194.67 | 0 | 562.52 | 346.73 | 21.11 | 194.67 | 0 | 562.52 | 54.77 | 65
100 | NORTH 24 PARGANAS | SM/11601 | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | TSM/010858 | 40046293 | Augmentation | MVS | GO2223005399PH | 22/07/2022 | 492.1 | 39.58 | 531.68 | Barasat Division | Eastern Mechanical Division | 191.05 | 23.4 | 11.16 | 0 | 225.61 | 191.05 | 23.4 | 11.16 | 0 | 225.61 | 42.43 | 75
101 | NORTH 24 PARGANAS | SM/12124 | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | TSM/010922 | 40036198 | Augmentation | MVS | GO2223007044PH | 06/09/2022 | 1155.59 | 83.14 | 1238.73 | Barasat Division | Eastern Mechanical Division | 385.62 | 10.61 | 135.39 | 0 | 531.61 | 385.62 | 10.61 | 135.39 | 0 | 531.61 | 42.92 | 50
102 | NORTH 24 PARGANAS | SM/12127 | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | TSM/010863 | 40036111 | Augmentation | MVS | GO2223007071PH | 06/09/2022 | 1478.9 | 68.11 | 1547.01 | Barasat Division | Eastern Mechanical Division | 730.3 | 19.67 | 147.38 | 0 | 897.36 | 730.3 | 19.67 | 147.38 | 0 | 897.36 | 58.01 | 75
103 | NORTH 24 PARGANAS | SM/10565 | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | TSM/010453 | 40046500 | Augmentation | MVS | GO2223000365PH | 18/04/2022 | 741.35 | 35.56 | 776.91 | Barasat Division | Eastern Mechanical Division | 511.55 | 19.75 | 10.74 | 0 | 542.04 | 511.55 | 19.75 | 10.74 | 0 | 542.04 | 69.77 | 80
104 | NORTH 24 PARGANAS | SM/10101 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | TSM/009520 | 40002854 | Augmentation | MVS | GO2122009121PH | 02/02/2022 | 592.32 | 0 | 592.32 | North 24 Pgs W/S Division I |  | 379.56 | 0 | 37.47 | 0 | 417.03 | 379.56 | 0 | 37.47 | 0 | 417.03 | 70.41 | 81
105 | NORTH 24 PARGANAS | SM/11626 | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | TSM/011033 | 40036027 | Augmentation | MVS | GO2223005558PH | 26/07/2022 | 1167.21 | 40.41 | 1207.61 | Barasat Division | Eastern Mechanical Division | 182.01 | 17.71 | 116.15 | 0 | 315.87 | 182.01 | 17.71 | 116.15 | 0 | 315.87 | 26.16 | 60
106 | NORTH 24 PARGANAS | SM/11585 | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | TSM/011065 | 40060403 | Augmentation | SVS | GO2223005369PH | 22/07/2022 | 762 | 40.41 | 802.4 | Barasat Division | Eastern Mechanical Division | 463.28 | 0 | 28.3 | 0 | 491.58 | 463.28 | 0 | 28.3 | 0 | 491.58 | 61.26 | 70
107 | NORTH 24 PARGANAS | SM/10529 | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | TSM/009758 | 40030032 | Augmentation | SVS | GO2223000256PH | 13/04/2022 | 404.89 | 33.75 | 438.64 | Barasat Division | Eastern Mechanical Division | 211.79 | 0 | 15.2 | 0 | 226.99 | 211.79 | 0 | 15.2 | 0 | 226.99 | 51.75 | 90
108 | NORTH 24 PARGANAS | SM/11663 | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010997 | 40026492 | Augmentation | MVS | GO2223005686PH | 28/07/2022 | 440.66 | 21.28 | 461.93 | Barasat Arsenic Division | Eastern Mechanical Division | 214.07 | 14.9 | 0 | 0 | 228.97 | 214.07 | 14.9 | 0 | 0 | 228.97 | 49.57 | 48
109 | NORTH 24 PARGANAS | SM/11708 | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010998 | 40026460 | Augmentation | MVS | GO2223005725PH | 29/07/2022 | 556.66 | 36.42 | 593.08 | Barasat Arsenic Division | Eastern Mechanical Division | 322.8 | 16.02 | 0 | 0 | 338.82 | 322.8 | 16.02 | 0 | 0 | 338.82 | 57.13 | 26
110 | NORTH 24 PARGANAS | SM/11662 | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011234 | 40026333 | Augmentation | SVS | GO2223005690PH | 28/07/2022 | 526.81 | 20.84 | 547.66 | Barasat Arsenic Division | Eastern Mechanical Division | 286.48 | 3 | 0 | 0 | 289.48 | 286.48 | 3 | 0 | 0 | 289.48 | 52.86 | 44
111 | NORTH 24 PARGANAS | SM/11529 | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | TSM/011074 | 40060508 | Augmentation | SVS | GO2223005232PH | 19/07/2022 | 150.03 | 40.41 | 190.44 | Barasat Division | Eastern Mechanical Division | 57.09 | 19.99 | 0 | 0 | 77.08 | 57.09 | 19.99 | 0 | 0 | 77.08 | 40.47 | 75
112 | NORTH 24 PARGANAS | SM/11591 | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | TSM/011082 | 40036137 | Augmentation | MVS | GO2223005412PH | 22/07/2022 | 753.09 | 40.41 | 793.5 | Barasat Division | Eastern Mechanical Division | 390.22 | 0 | 104.84 | 15.66 | 510.72 | 390.22 | 0 | 104.84 | 15.66 | 510.72 | 64.36 | 75
113 | NORTH 24 PARGANAS | SM/14153 | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | TSM/012030 | 40033250 | Augmentation | MVS | GO2223011608PH | 05/01/2023 | 2236.09 | 166.28 | 2402.37 | Barasat Division | Eastern Mechanical Division | 1668.22 | 0 | 292.44 | 0 | 1960.67 | 1668.22 | 0 | 292.44 | 0 | 1960.67 | 81.61 | 85
114 | NORTH 24 PARGANAS | SM/11631 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | TSM/011108 | 40023337 | Augmentation | MVS | GO2223005559PH | 26/07/2022 | 1131.12 | 33.75 | 1164.88 | Barasat Division | Eastern Mechanical Division | 453.17 | 24.26 | 132.49 | 0 | 609.91 | 453.17 | 24.26 | 132.49 | 0 | 609.91 | 52.36 | 80
115 | NORTH 24 PARGANAS | SM/10727 | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | TSM/009764 | 40018992 | Augmentation | MVS | GO2223002005PH | 18/05/2022 | 351.87 | 33.75 | 385.63 | Barasat Division | Eastern Mechanical Division | 228.81 | 17.61 | 4.56 | 0 | 250.99 | 228.81 | 17.61 | 4.56 | 0 | 250.99 | 65.08 | 80
116 | NORTH 24 PARGANAS | SM/11602 | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | TSM/010859 | 40046492 | Augmentation | MVS | GO2223005424PH | 22/07/2022 | 468.82 | 39.58 | 508.4 | Barasat Division | Eastern Mechanical Division | 189.83 | 3.9 | 18.62 | 0 | 212.35 | 189.83 | 3.9 | 18.62 | 0 | 212.35 | 41.77 | 75
117 | NORTH 24 PARGANAS | SM/12125 | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | TSM/011158 | 40036200 | Augmentation | MVS | GO2223007046PH | 06/09/2022 | 1122.3 | 45.99 | 1168.29 | Barasat Division | Eastern Mechanical Division | 595.24 | 23.98 | 5.96 | 0 | 625.18 | 595.24 | 23.98 | 5.96 | 0 | 625.18 | 53.51 | 60
118 | NORTH 24 PARGANAS | SM/11657 | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC | TSM/011160 | 40034988 | Augmentation | MVS | GO2223005644PH | 27/07/2022 | 955.77 | 43.65 | 999.42 | Barasat Division | Eastern Mechanical Division | 561.26 | 24.6 | 18.98 | 0 | 604.83 | 561.26 | 24.6 | 18.98 | 0 | 604.83 | 60.52 | 70
119 | NORTH 24 PARGANAS | SM/11600 | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | TSM/010857 | 40029478 | Augmentation | MVS | GO2223005368PH | 22/07/2022 | 783.07 | 39.58 | 822.65 | Barasat Division | Eastern Mechanical Division | 409.67 | 30.48 | 30.2 | 0 | 470.34 | 409.67 | 30.48 | 30.2 | 0 | 470.34 | 57.17 | 10
120 | NORTH 24 PARGANAS | SM/10530 | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | TSM/009763 | 40026968 | Augmentation | MVS | GO2223000290PH | 13/04/2022 | 614.96 | 33.75 | 648.71 | Barasat Division | Eastern Mechanical Division | 307.41 | 0 | 92.28 | 0 | 399.69 | 307.41 | 0 | 92.28 | 0 | 399.69 | 61.61 | 85
121 | NORTH 24 PARGANAS | SM/11763 | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | TSM/011373 | 40022559 | Augmentation | MVS | GO2223005984PH | 03/08/2022 | 450.66 | 41.57 | 492.23 | Barasat Division | Eastern Mechanical Division | 209.33 | 4.17 | 0 | 0 | 213.5 | 209.33 | 4.17 | 0 | 0 | 213.5 | 43.37 | 70
122 | NORTH 24 PARGANAS | SM/10570 | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | TSM/010448 | 40019753 | Augmentation | MVS | GO2223000359PH | 18/04/2022 | 586.33 | 41.7 | 628.03 | Barasat Division | Eastern Mechanical Division | 358.07 | 6.82 | 21.66 | 0 | 386.54 | 358.07 | 6.82 | 21.66 | 0 | 386.54 | 61.55 | 90
123 | NORTH 24 PARGANAS | SM/12735 | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | TSM/011193 | 40036208 | Augmentation | MVS | GO2223008041PH | 21/09/2022 | 1442.03 | 59.35 | 1501.39 | Barasat Division | Eastern Mechanical Division | 579.45 | 54.3 | 93.9 | 0 | 727.65 | 579.45 | 62.85 | 93.9 | 0 | 736.2 | 49.04 | 75
124 | NORTH 24 PARGANAS | SM/11699 | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | TSM/011177 | 40031711 | Augmentation | SVS | GO2223005724PH | 29/07/2022 | 712.51 | 62.36 | 774.86 | Barasat Division | Eastern Mechanical Division | 443.7 | 51.11 | 63.54 | 0 | 558.36 | 443.7 | 42.55 | 63.54 | 0 | 549.8 | 70.95 | 74
125 | NORTH 24 PARGANAS | SM/11538 | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | TSM/010860 | 40022744 | Augmentation | MVS | GO2223005251PH | 19/07/2022 | 722.37 | 39.58 | 761.95 | Barasat Division | Eastern Mechanical Division | 390.8 | 0 | 34.54 | 0 | 425.33 | 390.8 | 0 | 34.54 | 0 | 425.33 | 55.82 | 75
126 | NORTH 24 PARGANAS | SM/11661 | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | TSM/011147 | 40026325 | Augmentation | MVS | GO2223005687PH | 28/07/2022 | 452.23 | 34.75 | 486.98 | Barasat Arsenic Division | Eastern Mechanical Division | 174.06 | 0 | 6.92 | 0 | 180.99 | 174.06 | 0 | 6.92 | 0 | 180.99 | 37.16 | 11
127 | NORTH 24 PARGANAS | SM/10376 | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | TSM/009732 | 40007165 | Augmentation | SVS | GO2122010916PH | 16/03/2022 | 628.64 | 42.43 | 671.07 | Barasat Division | Eastern Mechanical Division | 471.16 | 20.19 | 7.56 | 0 | 498.92 | 471.16 | 20.19 | 7.56 | 0 | 498.92 | 74.35 | 80
128 | NORTH 24 PARGANAS | SM/10308 | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | TSM/009318 | 40005456 | Augmentation | MVS | GO2122010478PH | 04/03/2022 | 626.3 | 34.57 | 660.87 | Barasat Division | Eastern Mechanical Division | 416.17 | 24.13 | 34.52 | 0 | 474.82 | 416.17 | 24.13 | 34.52 | 0 | 474.82 | 71.85 | 85
129 | NORTH 24 PARGANAS | SM/11706 | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010982 | 40026491 | Augmentation | MVS | GO2223005726PH | 29/07/2022 | 307.2 | 21.28 | 328.48 | Barasat Arsenic Division | Eastern Mechanical Division | 93.05 | 0 | 0 | 0 | 93.05 | 93.05 | 0 | 0 | 0 | 93.05 | 28.33 | 26
130 | NORTH 24 PARGANAS | SM/11755 | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC | TSM/011309 | 40033099 | Augmentation | SVS | GO2223005907PH | 02/08/2022 | 258.46 | 20.79 | 279.25 | Barasat Division | Eastern Mechanical Division | 72.44 | 0 | 2.6 | 0 | 75.04 | 72.44 | 0 | 2.6 | 0 | 75.04 | 26.87 | 70
131 | NORTH 24 PARGANAS | SM/10302 | Augmentation of Ground water based piped water supply scheme for Kumarjole | TSM/009738 | 40005461 | Augmentation | MVS | GO2122010328PH | 02/03/2022 | 1012.73 | 39.57 | 1052.3 | Barasat Division | Eastern Mechanical Division | 450.14 | 19.26 | 0 | 0 | 469.4 | 450.14 | 19.26 | 0 | 0 | 469.4 | 44.61 | 70
132 | NORTH 24 PARGANAS | SM/10298 | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | TSM/009320 | 40014573 | Augmentation | MVS | GO2122010324PH | 02/03/2022 | 691.75 | 32.61 | 724.36 | Barasat Division | Eastern Mechanical Division | 353.59 | 23.54 | 11.88 | 0 | 389.01 | 353.59 | 23.54 | 11.88 | 0 | 389.01 | 53.7 | 70
133 | NORTH 24 PARGANAS | SM/10301 | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | TSM/009252 | 40013189 | Augmentation | MVS | GO2122010327PH | 02/03/2022 | 559.12 | 33.77 | 592.89 | Barasat Division | Eastern Mechanical Division | 392.07 | 16.8 | 31.06 | 0 | 439.93 | 392.07 | 16.8 | 31.06 | 0 | 439.93 | 74.2 | 85
134 | NORTH 24 PARGANAS | SM/11655 | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | TSM/011314 | 40029239 | Augmentation | MVS | GO2223005643PH | 27/07/2022 | 1111.98 | 41.57 | 1153.55 | Barasat Division | Eastern Mechanical Division | 400.47 | 0 | 64.81 | 0 | 465.28 | 400.47 | 0 | 64.81 | 0 | 465.28 | 40.33 | 65
135 | NORTH 24 PARGANAS | SM/11596 | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | TSM/011213 | 40036142 | Augmentation | MVS | GO2223005371PH | 22/07/2022 | 1025.28 | 71.09 | 1096.37 | Barasat Division | Eastern Mechanical Division | 686.44 | 34.24 | 13.52 | 0 | 734.19 | 686.44 | 34.24 | 13.52 | 0 | 734.19 | 66.97 | 80
136 | NORTH 24 PARGANAS | SM/10574 | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | TSM/010446 | 40019523 | Augmentation | MVS | GO2223000351PH | 18/04/2022 | 976.82 | 43.8 | 1020.62 | Barasat Division | Eastern Mechanical Division | 418.08 | 0 | 16.03 | 0 | 434.11 | 418.08 | 0 | 16.03 | 0 | 434.11 | 42.53 | 70
137 | NORTH 24 PARGANAS | SM/11539 | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | TSM/010861 | 40022742 | Augmentation | MVS | GO2223005252PH | 19/07/2022 | 412.68 | 39.58 | 452.26 | Barasat Division | Eastern Mechanical Division | 236.57 | 20 | 13.47 | 0 | 270.04 | 236.57 | 20 | 13.47 | 0 | 270.04 | 59.71 | 85
138 | NORTH 24 PARGANAS | SM/11665 | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | TSM/011081 | 40022557 | Augmentation | MVS | GO2223005640PH | 27/07/2022 | 408.92 | 40.41 | 449.33 | Barasat Division | Eastern Mechanical Division | 158.25 | 14.79 | 11.09 | 0 | 184.13 | 158.25 | 14.79 | 11.09 | 0 | 184.13 | 40.98 | 10
139 | NORTH 24 PARGANAS | SM/11654 | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | TSM/011313 | 40029522 | Augmentation | MVS | GO2223005647PH | 27/07/2022 | 362.12 | 41.57 | 403.69 | Barasat Division | Eastern Mechanical Division | 136.69 | 0 | 24.24 | 0 | 160.93 | 136.69 | 0 | 24.24 | 0 | 160.93 | 39.86 | 65
140 | NORTH 24 PARGANAS | SM/10531 | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | TSM/009760 | 40032583 | Augmentation | MVS | GO2223000259PH | 13/04/2022 | 773.72 | 47.72 | 821.44 | Barasat Division | Eastern Mechanical Division | 550.17 | 25.78 | 24.99 | 0 | 600.94 | 550.17 | 25.78 | 24.99 | 0 | 600.94 | 73.16 | 80
141 | NORTH 24 PARGANAS | SM/10533 | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | TSM/009761 | 40019376 | Augmentation | MVS | GO2223000257PH | 13/04/2022 | 804.64 | 47.72 | 852.36 | Barasat Division | Eastern Mechanical Division | 432.01 | 26.94 | 35.17 | 0 | 494.11 | 432.01 | 26.94 | 35.17 | 0 | 494.11 | 57.97 | 70
142 | NORTH 24 PARGANAS | SM/11530 | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | TSM/011075 | 40036103 | Augmentation | MVS | GO2223005250PH | 19/07/2022 | 552.53 | 40.41 | 592.93 | Barasat Division | Eastern Mechanical Division | 285.78 | 23.36 | 38.72 | 0 | 347.87 | 285.78 | 23.36 | 38.72 | 0 | 347.87 | 58.67 | 75
143 | NORTH 24 PARGANAS | SM/11667 | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | TSM/011164 | 40022581 | Augmentation | MVS | GO2223005642PH | 27/07/2022 | 468.77 | 39.58 | 508.35 | Barasat Division | Eastern Mechanical Division | 159.15 | 3.94 | 6.13 | 0 | 169.22 | 159.15 | 3.94 | 6.13 | 0 | 169.22 | 33.29 | 80
144 | NORTH 24 PARGANAS | SM/11702 | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | TSM/011080 | 40035037 | Augmentation | MVS | GO2223005731PH | 29/07/2022 | 511.05 | 40.41 | 551.46 | Barasat Division | Eastern Mechanical Division | 287.73 | 0 | 53.89 | 0 | 341.62 | 287.73 | 0 | 53.89 | 0 | 341.62 | 61.95 | 65
145 | NORTH 24 PARGANAS | SM/14151 | Augmentation of ground water based piped water supply scheme for Mohanpur | TSM/012029 | 40033556 | Augmentation | SVS | GO2223011609PH | 05/01/2023 | 1232.67 | 100.62 | 1333.28 | Barasat Division | Eastern Mechanical Division | 629.46 | 13.51 | 0 | 0 | 642.97 | 629.46 | 13.51 | 0 | 0 | 642.97 | 48.22 | 60
146 | NORTH 24 PARGANAS | SM/11632 | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | TSM/011192 | 40027749 | Augmentation | SVS | GO2223005556PH | 26/07/2022 | 691.01 | 67.32 | 758.33 | Barasat Division | Eastern Mechanical Division | 459.66 | 15.05 | 4.45 | 0 | 479.16 | 459.66 | 15.05 | 4.45 | 0 | 479.16 | 63.19 | 90
147 | NORTH 24 PARGANAS | SM/10555 | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | TSM/010454 | 40036596 | Augmentation | MVS | GO2223000338PH | 18/04/2022 | 909.27 | 87.83 | 997.1 | Barasat Division | Eastern Mechanical Division | 571.39 | 0 | 27.37 | 0 | 598.76 | 571.39 | 0 | 27.37 | 0 | 598.76 | 60.05 | 60
148 | NORTH 24 PARGANAS | SM/11760 | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | TSM/011379 | 40022579 | Augmentation | MVS | GO2223005906PH | 02/08/2022 | 437.51 | 41.57 | 479.08 | Barasat Division | Eastern Mechanical Division | 250.1 | 15.54 | 0 | 0 | 265.64 | 250.1 | 15.54 | 0 | 0 | 265.64 | 55.45 | 70
149 | NORTH 24 PARGANAS | SM/12377 | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | TSM/011383 | 40022580 | Augmentation | MVS | GO2223007583PH | 13/09/2022 | 2182.78 | 83.14 | 2265.92 | Barasat Division | Eastern Mechanical Division | 1108.04 | 23.95 | 456.58 | 0 | 1588.57 | 1108.04 | 23.95 | 456.58 | 0 | 1588.57 | 70.11 | 80
150 | NORTH 24 PARGANAS | SM/11524 | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | TSM/011059 | 40023625 | Augmentation | SVS | GO2223005228PH | 19/07/2022 | 246.47 | 20.2 | 266.67 | Barasat Division | Eastern Mechanical Division | 87.9 | 0 | 23.93 | 0 | 111.83 | 87.9 | 0 | 23.93 | 0 | 111.83 | 41.93 | 65
151 | NORTH 24 PARGANAS | SM/11974 | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | TSM/011372 | 40022553 | Augmentation | MVS | GO2223006801PH | 29/08/2022 | 542.28 | 41.57 | 583.85 | Barasat Division | Eastern Mechanical Division | 239.99 | 0 | 62.48 | 24.41 | 326.89 | 239.99 | 0 | 62.48 | 24.41 | 326.89 | 55.99 | 65
152 | NORTH 24 PARGANAS | SM/11595 | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | TSM/011203 | 40018886 | Augmentation | MVS | GO2223005426PH | 22/07/2022 | 496.05 | 41.57 | 537.62 | Barasat Division | Eastern Mechanical Division | 257.05 | 14.37 | 0 | 0 | 271.42 | 257.05 | 14.37 | 0 | 0 | 271.42 | 50.49 | 70
153 | NORTH 24 PARGANAS | SM/13314 | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | TSM/011170 | 40036210 | Augmentation | MVS | GO2223008872PH | 17/10/2022 | 1613.56 | 88.57 | 1702.13 | Barasat Division | Eastern Mechanical Division | 896.7 | 12.13 | 170.43 | 0 | 1079.26 | 896.7 | 12.13 | 170.43 | 0 | 1079.26 | 63.41 | 69
154 | NORTH 24 PARGANAS | SM/12273 | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | TSM/011034 | 40028586 | Augmentation | MVS | GO2223007386PH | 09/09/2022 | 1620.66 | 62.36 | 1683.01 | Barasat Division | Eastern Mechanical Division | 296.76 | 0 | 378.57 | 0 | 675.33 | 296.76 | 0 | 378.57 | 0 | 675.33 | 40.13 | 65
155 | NORTH 24 PARGANAS | SM/10300 | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | TSM/009255 | 40005470 | Augmentation | MVS | GO2122010326PH | 02/03/2022 | 664.92 | 34.57 | 699.49 | Barasat Division | Eastern Mechanical Division | 413.95 | 22.28 | 24.82 | 0 | 461.05 | 413.95 | 22.28 | 24.82 | 0 | 461.05 | 65.91 | 80
156 | NORTH 24 PARGANAS | SM/13350 | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | TSM/011380 | 40030470 | Augmentation | MVS | GO2223008973PH | 19/10/2022 | 1349.73 | 62.36 | 1412.09 | Barasat Division | Eastern Mechanical Division | 483.87 | 3.51 | 215.18 | 0 | 702.55 | 483.87 | 3.51 | 215.18 | 0 | 702.55 | 49.75 | 60
157 | NORTH 24 PARGANAS | SM/11606 | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | TSM/011027 | 40022715 | Augmentation | MVS | GO2223005421PH | 22/07/2022 | 822.62 | 62.36 | 884.98 | Barasat Division | Eastern Mechanical Division | 436.61 | 0 | 68.49 | 0 | 505.1 | 436.61 | 0 | 68.49 | 0 | 505.1 | 57.08 | 70
158 | NORTH 24 PARGANAS | SM/10104 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | TSM/009270 | 40002892 | Augmentation | MVS | GO2122009119PH | 02/02/2022 | 630.72 | 0 | 630.72 | North 24 Pgs W/S Division I |  | 369.41 | 0 | 11.02 | 0 | 380.43 | 369.41 | 0 | 11.02 | 0 | 380.43 | 60.32 | 66
159 | NORTH 24 PARGANAS | SM/11656 | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | TSM/011371 | 40022574 | Augmentation | MVS | GO2223005639PH | 27/07/2022 | 676.99 | 41.57 | 718.56 | Barasat Division | Eastern Mechanical Division | 228.92 | 15.43 | 53.15 | 0 | 297.5 | 228.92 | 15.43 | 53.15 | 0 | 297.5 | 41.4 | 70
160 | NORTH 24 PARGANAS | SM/10100 | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | TSM/009519 | 40002672 | Augmentation | MVS | GO2122009053PH | 02/02/2022 | 1063.69 | 0 | 1063.69 | North 24 Pgs W/S Division I |  | 645.2 | 0 | 127.76 | 0 | 772.96 | 645.2 | 0 | 127.76 | 0 | 772.96 | 72.67 | 79
161 | NORTH 24 PARGANAS | SM/11635 | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | TSM/011025 | 40036129 | Augmentation | MVS | GO2223005580PH | 26/07/2022 | 562.37 | 60.61 | 622.98 | Barasat Division | Eastern Mechanical Division | 281.92 | 11.8 | 58.04 | 0 | 351.76 | 281.92 | 11.8 | 58.04 | 0 | 351.76 | 56.46 | 70
162 | NORTH 24 PARGANAS | SM/11628 | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | TSM/011076 | 40036115 | Augmentation | MVS | GO2223005562PH | 26/07/2022 | 324.65 | 40.41 | 365.06 | Barasat Division | Eastern Mechanical Division | 155.48 | 22.74 | 10.15 | 0 | 188.37 | 155.48 | 22.74 | 10.15 | 0 | 188.37 | 51.6 | 70
163 | NORTH 24 PARGANAS | SM/11531 | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | TSM/011077 | 40036104 | Augmentation | MVS | GO2223005237PH | 19/07/2022 | 314.61 | 40.41 | 355.01 | Barasat Division | Eastern Mechanical Division | 139.49 | 22.8 | 27.48 | 0 | 189.76 | 139.49 | 22.8 | 27.48 | 0 | 189.76 | 53.45 | 80
164 | NORTH 24 PARGANAS | SM/17408 | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | TSM/011322 | 40036883 | Augmentation | MVS | GO2223016354PH | 15/03/2023 | 608.22 | 41.57 | 649.79 | Barasat Division | Eastern Mechanical Division | 270.56 | 17.92 | 0 | 0 | 288.48 | 270.56 | 17.92 | 0 | 0 | 288.48 | 44.4 | 60
165 | NORTH 24 PARGANAS | SM/13761 | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011116 | 40037205 | Augmentation | MVS | GO2223009893PH | 18/11/2022 | 332.1 | 21.28 | 353.38 | Barasat Arsenic Division | Eastern Mechanical Division | 183.74 | 0 | 1.72 | 0 | 185.46 | 183.74 | 0 | 1.72 | 0 | 185.46 | 52.48 | 20
166 | NORTH 24 PARGANAS | SM/11526 | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | TSM/011068 | 40031739 | Augmentation | SVS | GO2223005226PH | 19/07/2022 | 650.62 | 40.41 | 691.03 | Barasat Division | Eastern Mechanical Division | 331.26 | 19.21 | 79.14 | 14.5 | 444.11 | 331.26 | 19.21 | 79.14 | 14.5 | 444.11 | 64.27 | 80
167 | NORTH 24 PARGANAS | SM/11630 | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | TSM/011079 | 40023371 | Augmentation | SVS | GO2223005578PH | 26/07/2022 | 178.08 | 20.2 | 198.28 | Barasat Division | Eastern Mechanical Division | 65.03 | 9.03 | 0 | 0 | 74.06 | 65.03 | 9.03 | 0 | 0 | 74.06 | 37.35 | 75
168 | NORTH 24 PARGANAS | SM/11603 | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | TSM/010864 | 40030448 | Augmentation | SVS | GO2223005372PH | 22/07/2022 | 362.56 | 39.58 | 402.14 | Barasat Division | Eastern Mechanical Division | 246.58 | 19.14 | 20.67 | 0 | 286.39 | 246.58 | 19.14 | 20.67 | 0 | 286.39 | 71.21 | 75
169 | NORTH 24 PARGANAS | SM/12122 | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | TSM/011175 | 40036131 | Augmentation | MVS | GO2223007090PH | 06/09/2022 | 1372.36 | 131.39 | 1503.75 | Barasat Division | Eastern Mechanical Division | 963.75 | 66.05 | 91.24 | 0 | 1121.03 | 973.29 | 66.05 | 91.24 | 0 | 1130.58 | 75.18 | 75
170 | NORTH 24 PARGANAS | SM/11525 | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | TSM/011067 | 40022748 | Augmentation | MVS | GO2223005225PH | 19/07/2022 | 774.99 | 40.41 | 815.39 | Barasat Division | Eastern Mechanical Division | 413.07 | 23.03 | 34.2 | 0 | 470.3 | 413.07 | 23.03 | 34.2 | 0 | 470.3 | 57.68 | 10
171 | NORTH 24 PARGANAS | SM/11523 | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | TSM/011066 | 40060411 | Augmentation | MVS | GO2223005227PH | 19/07/2022 | 466.58 | 40.41 | 506.98 | Barasat Division | Eastern Mechanical Division | 161.21 | 22.76 | 10.13 | 0 | 194.11 | 161.21 | 22.76 | 10.13 | 0 | 194.11 | 38.29 | 75
172 | NORTH 24 PARGANAS | SM/10577 | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | TSM/009759 | 40028458 | Augmentation | SVS | GO2223000347PH | 18/04/2022 | 157.06 | 19.79 | 176.85 | Barasat Division | Eastern Mechanical Division | 47.38 | 3.39 | 2.11 | 0 | 52.88 | 47.38 | 3.39 | 2.11 | 0 | 52.88 | 29.9 | 70
173 | NORTH 24 PARGANAS | SM/12278 | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | TSM/010949 | 40035651 | Augmentation | MVS | GO2223007390PH | 09/09/2022 | 1862.55 | 140.12 | 2002.67 | Barasat Division | Eastern Mechanical Division | 1053.17 | 36.57 | 112.96 | 0 | 1202.71 | 1054.32 | 36.57 | 112.96 | 0 | 1203.86 | 60.11 | 70
174 | NORTH 24 PARGANAS | SM/14152 | Augmentation of ground water based piped water supply scheme for Sandeshkhali | TSM/012006 | 40060626 | Augmentation | SVS | GO2223011610PH | 05/01/2023 | 1102.38 | 37.48 | 1139.85 | Barasat Division | Eastern Mechanical Division | 171.37 | 0 | 31.53 | 0 | 202.9 | 171.37 | 0 | 31.53 | 0 | 202.9 | 17.8 | 60
175 | NORTH 24 PARGANAS | SM/11605 | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | TSM/011031 | 40029312 | Augmentation | MVS | GO2223005422PH | 22/07/2022 | 1068.42 | 40.41 | 1108.82 | Barasat Division | Eastern Mechanical Division | 722.22 | 5.64 | 92.91 | 0 | 820.77 | 722.22 | 5.64 | 92.91 | 0 | 820.77 | 74.02 | 80
176 | NORTH 24 PARGANAS | SM/11653 | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | TSM/011430 | 40033087 | Augmentation | MVS | GO2223005645PH | 27/07/2022 | 893.05 | 62.36 | 955.4 | Barasat Division | Eastern Mechanical Division | 312.24 | 0 | 175.5 | 0 | 487.74 | 312.24 | 0 | 175.5 | 0 | 487.74 | 51.05 | 65
177 | NORTH 24 PARGANAS | SM/10111 | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | TSM/009219 | 40003520 | Augmentation | MVS | GO2122009116PH | 02/02/2022 | 938.03 | 0 | 938.03 | North 24 Pgs W/S Division I |  | 596.46 | 0 | 135.82 | 0 | 732.28 | 596.46 | 0 | 135.82 | 0 | 732.28 | 78.07 | 85
178 | NORTH 24 PARGANAS | SM/10110 | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | TSM/009271 | 40002861 | Augmentation | MVS | GO2122009117PH | 02/02/2022 | 673.06 | 0 | 673.06 | North 24 Pgs W/S Division I |  | 483.05 | 0 | 24.83 | 0 | 507.88 | 483.05 | 0 | 24.83 | 0 | 507.88 | 75.46 | 83
179 | NORTH 24 PARGANAS | SM/11607 | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | TSM/011032 | 40036025 | Augmentation | MVS | GO2223005370PH | 22/07/2022 | 898.11 | 40.41 | 938.51 | Barasat Division | Eastern Mechanical Division | 363.26 | 13.36 | 104.14 | 0 | 480.77 | 363.26 | 13.36 | 104.14 | 0 | 480.77 | 51.23 | 75
180 | NORTH 24 PARGANAS | SM/13472 | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | TSM/011976 | 40032923 | Augmentation | MVS | GO2223009255PH | 02/11/2022 | 832.46 | 42.93 | 875.39 | Barasat Division | Eastern Mechanical Division | 192.55 | 0 | 36.84 | 46.12 | 275.51 | 192.55 | 0 | 36.84 | 46.12 | 275.51 | 31.47 | 54
181 | NORTH 24 PARGANAS | SM/12569 | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | TSM/011321 | 40029298 | Augmentation | MVS | GO2223007700PH | 14/09/2022 | 1435.73 | 62.36 | 1498.08 | Barasat Division | Eastern Mechanical Division | 513.33 | 6.57 | 88.84 | 0 | 608.74 | 513.33 | 6.57 | 88.84 | 0 | 608.74 | 40.63 | 60
182 | NORTH 24 PARGANAS | SM/11598 | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | TSM/011168 | 40029461 | Augmentation | MVS | GO2223005353PH | 22/07/2022 | 1113.25 | 51.84 | 1165.1 | Barasat Division | Eastern Mechanical Division | 767.1 | 27.49 | 92.51 | 0 | 887.11 | 767.1 | 27.49 | 92.51 | 0 | 887.11 | 76.14 | 85
183 | NORTH 24 PARGANAS | SM/10786 | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | TSM/009319 | 40007129 | Augmentation | MVS | GO2223003490PH | 25/05/2022 | 502.81 | 34.57 | 537.38 | Barasat Division | Eastern Mechanical Division | 390.05 | 8.89 | 18.5 | 0 | 417.43 | 390.05 | 8.89 | 18.5 | 0 | 417.43 | 77.68 | 82
184 | NORTH 24 PARGANAS | SM/10375 | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | TSM/009253 | 40007128 | Augmentation | MVS | GO2122010913PH | 16/03/2022 | 474.91 | 34.57 | 509.48 | Barasat Division | Eastern Mechanical Division | 301.03 | 21.02 | 91.71 | 0 | 413.76 | 301.03 | 21.02 | 91.71 | 0 | 413.76 | 81.21 | 85
185 | NORTH 24 PARGANAS | SM/11758 | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | TSM/011385 | 40029479 | Augmentation | MVS | GO2223005908PH | 02/08/2022 | 321.56 | 20.79 | 342.34 | Barasat Division | Eastern Mechanical Division | 130.56 | 3.12 | 6.16 | 0 | 139.85 | 130.56 | 3.12 | 6.16 | 0 | 139.85 | 40.85 | 65
186 | NORTH 24 PARGANAS | SM/11528 | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | TSM/011070 | 40022708 | Augmentation | MVS | GO2223005231PH | 19/07/2022 | 916.69 | 40.41 | 957.1 | Barasat Division | Eastern Mechanical Division | 352.81 | 7.65 | 86.85 | 0 | 447.32 | 352.81 | 7.65 | 86.85 | 0 | 447.32 | 46.74 | 55
187 | NORTH 24 PARGANAS | SM/10706 | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | TSM/010459 | 40032574 | Augmentation | MVS | GO2223001541PH | 12/05/2022 | 438.65 | 43.92 | 482.57 | Barasat Division | Eastern Mechanical Division | 243.65 | 21.88 | 15.09 | 0 | 280.62 | 243.65 | 21.88 | 15.09 | 0 | 280.62 | 58.15 | 75
188 | NORTH 24 PARGANAS | SM/10693 | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | TSM/009762 | 40018988 | Augmentation | MVS | GO2223001398PH | 12/05/2022 | 433.63 | 33.75 | 467.39 | Barasat Division | Eastern Mechanical Division | 242.23 | 24.67 | 0 | 0 | 266.89 | 242.23 | 24.67 | 0 | 0 | 266.89 | 57.1 | 78
189 | NORTH 24 PARGANAS | SM/11757 | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | TSM/011377 | 40022562 | Augmentation | MVS | GO2223005968PH | 03/08/2022 | 545.88 | 20.79 | 566.66 | Barasat Division | Eastern Mechanical Division | 270.35 | 0.93 | 5.52 | 0 | 276.81 | 270.35 | 0.93 | 5.52 | 0 | 276.81 | 48.85 | 65
190 | NORTH 24 PARGANAS | SM/17409 | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | TSM/011381 | 40037048 | Augmentation | MVS | GO2223016353PH | 15/03/2023 | 354.69 | 20.79 | 375.47 | Barasat Division | Eastern Mechanical Division | 213.62 | 0 | 16.09 | 0 | 229.7 | 213.62 | 0 | 16.09 | 0 | 229.7 | 61.18 | 75
191 | NORTH 24 PARGANAS | SM/11659 | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010996 | 40026444 | Augmentation | MVS | GO2223005689PH | 28/07/2022 | 529.51 | 34.75 | 564.26 | Barasat Arsenic Division | Eastern Mechanical Division | 207.03 | 17.76 | 0 | 0 | 224.8 | 207.03 | 17.76 | 0 | 0 | 224.8 | 39.84 | 30
192 | NORTH 24 PARGANAS | SM/10549 | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010570 | 40026434 | Augmentation | MVS | GO2223000378PH | 18/04/2022 | 820.44 | 42.57 | 863.01 | Barasat Arsenic Division | Eastern Mechanical Division | 370.49 | 15.44 | 168.38 | 0 | 554.31 | 370.49 | 15.44 | 168.38 | 0 | 554.31 | 64.23 | 57
193 | NORTH 24 PARGANAS | SM/10551 | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010571 | 40035047 | Augmentation | MVS | GO2223000380PH | 18/04/2022 | 934.84 | 42.57 | 977.41 | Barasat Arsenic Division | Eastern Mechanical Division | 378.44 | 2.73 | 238.35 | 0 | 619.52 | 378.44 | 2.73 | 238.35 | 0 | 619.52 | 63.38 | 47
194 | NORTH 24 PARGANAS | SM/18410 | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | TSM/011241 | 40033886 | Augmentation | MVS | 1853/PHE-28011/198/2022-ESTT CELL-Dept. of PHE | 12/07/2023 | 1137.12 | 73.61 | 1210.72 | Barasat Division | Eastern Mechanical Division | 160.28 | 9.09 | 95.29 | 40.55 | 305.21 | 160.28 | 9.09 | 95.29 | 40.55 | 305.21 | 25.21 | 36
195 | NORTH 24 PARGANAS | SM/18712 | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | TSM/011242 | 40033881 | Augmentation | MVS | 2261/PHE/IV/W-516/23 | 04/08/2023 | 981.89 | 73.61 | 1055.5 | Barasat Division | Eastern Mechanical Division | 92.09 | 0 | 62.26 | 51.19 | 205.53 | 92.09 | 0 | 62.26 | 51.19 | 205.53 | 19.47 | 15
196 | NORTH 24 PARGANAS | SM/14512 | Augmentation of Hingalganj Piped water supply scheme Zone-I | TSM/018807 | 40060592 | Augmentation | MVS | GO2223012331PH | 20/01/2023 | 837.11 | 107.37 | 944.47 | Barasat Division | Eastern Mechanical Division | 407.69 | 47.08 | 50.77 | 0 | 505.54 | 407.69 | 47.08 | 50.77 | 0 | 505.54 | 53.53 | 90
197 | NORTH 24 PARGANAS | SM/14513 | Augmentation of Hingalganj Piped water supply scheme Zone-II | TSM/018809 | 40060595 | Augmentation | MVS | GO2223012333PH | 20/01/2023 | 1026.51 | 125.18 | 1151.69 | Barasat Division | Eastern Mechanical Division | 390.51 | 18.79 | 0 | 0 | 409.3 | 390.51 | 18.79 | 0 | 0 | 409.3 | 35.54 | 20
198 | NORTH 24 PARGANAS | SM/15816 | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | TSM/015278 | 40059894 | Augmentation | MVS | GO2223014387PH | 20/02/2023 | 7877.4 | 1037.68 | 8915.09 | North 24 Pgs W/S Division I | Electrical Division | 294.53 | 430.06 | 1736.63 | 0 | 2461.21 | 294.53 | 430.06 | 1736.63 | 0 | 2461.21 | 27.61 | 30
199 | NORTH 24 PARGANAS | SM/10559 | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | TSM/009206 | 40033175 | Augmentation | SVS | GO2223000392PH | 18/04/2022 | 31.05 | 43.02 | 74.08 | Barasat Arsenic Division | Eastern Mechanical Division | 24.31 | 11.88 | 0 | 0 | 36.19 | 24.31 | 11.88 | 0 | 0 | 36.19 | 48.86 | 44
200 | NORTH 24 PARGANAS | SM/19108 | Augmentation of Mathurabil Zone-I in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | TSM/020571 | 40067351 | Augmentation | MVS | PHE/IV/3741/W-770/23 | 18/12/2023 | 985.92 | 0 | 985.92 | Barasat Division |  | 814.6 | 0 | 0 | 0 | 814.6 | 815.71 | 0 | 0 | 0 | 815.71 | 82.74 | 35
201 | NORTH 24 PARGANAS | SM/19109 | Augmentation of Mathurabil Zone-II in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | TSM/020570 | 40067360 | Augmentation | MVS | PHE/IV/3741/W-770/23 | 18/12/2023 | 940.91 | 0 | 940.91 | Barasat Division |  | 394.57 | 0 | 0 | 0 | 394.57 | 394.57 | 0 | 0 | 0 | 394.57 | 41.94 | 45
202 | NORTH 24 PARGANAS | SM/19110 | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | TSM/020569 | 40067363 | Augmentation | MVS | PHE/IV/3741/W-770/23 | 18/12/2023 | 874.94 | 0 | 874.94 | Barasat Division |  | 63.83 | 0 | 18.92 | 0 | 82.75 | 63.83 | 0 | 18.92 | 0 | 82.75 | 9.46 | 12
203 | NORTH 24 PARGANAS | SM/14515 | Augmentation of Rajbari Piped water supply scheme | TSM/018704 | 40060619 | Augmentation | SVS | GO2223012357PH | 20/01/2023 | 689.37 | 42.95 | 732.31 | Barasat Division | Eastern Mechanical Division | 285.9 | 19.49 | 25.03 | 0 | 330.42 | 285.9 | 19.49 | 25.03 | 0 | 330.42 | 45.12 | 90
204 | NORTH 24 PARGANAS | SM/11557 | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | TSM/009609 | 40026992 | Augmentation | MVS | GO2223005406PH | 22/07/2022 | 582.3 | 51.78 | 634.07 | Barasat Arsenic Division | Eastern Mechanical Division | 458.93 | 13.44 | 32.56 | 0 | 504.93 | 458.93 | 13.44 | 32.56 | 0 | 504.93 | 79.63 | 82
205 | NORTH 24 PARGANAS | SM/14510 | Augmentation of Sultanpur Piped water supply scheme | TSM/018805 | 40060606 | Augmentation | MVS | GO2223012324PH | 20/01/2023 | 408.54 | 46.45 | 454.99 | Barasat Division | Eastern Mechanical Division | 260.38 | 19.39 | 0 | 0 | 279.77 | 260.38 | 19.39 | 0 | 0 | 279.77 | 61.49 | 80
206 | NORTH 24 PARGANAS | SM/18259 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015463 | 40033366 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1001.31 | 61.03 | 1062.34 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 56.9 | 5.27 | 18.07 | 21.95 | 102.19 | 56.9 | 5.27 | 18.07 | 21.95 | 102.19 | 9.62 | 20
207 | NORTH 24 PARGANAS | SM/15822 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014788 | 40033427 | Augmentation | MVS | GO2223014375PH | 20/02/2023 | 1273 | 67.99 | 1340.98 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 524.32 | 3.36 | 224.55 | 0 | 752.23 | 524.32 | 3.36 | 224.55 | 0 | 752.23 | 56.1 | 66
208 | NORTH 24 PARGANAS | SM/15819 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014881 | 40033417 | Augmentation | MVS | GO2223014384PH | 20/02/2023 | 1248.37 | 67.99 | 1316.36 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 426.97 | 3.64 | 250.48 | 26.19 | 707.28 | 426.97 | 3.64 | 250.48 | 26.19 | 707.28 | 53.73 | 69
209 | NORTH 24 PARGANAS | SM/12383 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014883 | 40024318 | Augmentation | MVS | GO2223007607PH | 13/09/2022 | 972.52 | 64.3 | 1036.82 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 187.41 | 3.93 | 63.64 | 27.78 | 282.76 | 187.41 | 3.93 | 63.64 | 27.78 | 282.76 | 27.27 | 36
210 | NORTH 24 PARGANAS | SM/15821 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014754 | 40033125 | Augmentation | MVS | GO2223014377PH | 20/02/2023 | 1047.51 | 67.53 | 1115.04 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 396.56 | 3.66 | 96.53 | 24.6 | 521.35 | 396.56 | 3.66 | 96.53 | 24.6 | 521.35 | 46.76 | 57
211 | NORTH 24 PARGANAS | SM/15820 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014790 | 40033375 | Augmentation | MVS | GO2223014372PH | 20/02/2023 | 1329.34 | 70.11 | 1399.45 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 612.93 | 2.53 | 127.22 | 26.76 | 769.43 | 612.93 | 2.53 | 127.22 | 26.76 | 769.43 | 54.98 | 68
212 | NORTH 24 PARGANAS | SM/18265 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015249 | 40033338 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1081.59 | 64.3 | 1145.89 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.72 | 7.1 | 19.73 | 21.65 | 52.2 | 3.72 | 7.1 | 19.73 | 21.65 | 52.2 | 4.56 | 5
213 | NORTH 24 PARGANAS | SM/18264 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015086 | 40033139 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1280.02 | 67.53 | 1347.55 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 4.29 | 0 | 0 | 0 | 4.29 | 4.29 | 0 | 0 | 0 | 4.29 | 0.32 | 1
214 | NORTH 24 PARGANAS | SM/18262 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015472 | 40033154 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1248.94 | 64.3 | 1313.24 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 22.13 | 5.4 | 43.82 | 22.41 | 93.75 | 22.13 | 5.4 | 43.82 | 22.41 | 93.75 | 7.14 | 25
215 | NORTH 24 PARGANAS | SM/18263 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015074 | 40033400 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1207.07 | 64.3 | 1271.37 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.87 | 3.86 | 19.98 | 0 | 27.7 | 3.87 | 3.86 | 19.98 | 0 | 27.7 | 2.18 | 7
216 | NORTH 24 PARGANAS | SM/18261 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015092 | 40033344 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1324.61 | 67.99 | 1392.6 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 212.4 | 4.53 | 76.49 | 27.14 | 320.55 | 212.4 | 0 | 76.49 | 27.14 | 316.03 | 22.69 | 27
217 | NORTH 24 PARGANAS | SM/13435 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015250 | 40033407 | Augmentation | MVS | GO2223009177PH | 02/11/2022 | 946.46 | 64.3 | 1010.75 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 127.89 | 37.84 | 148.54 | 24.03 | 338.3 | 127.89 | 37.84 | 148.54 | 24.03 | 338.3 | 33.47 | 34
218 | NORTH 24 PARGANAS | SM/12413 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014786 | 40024353 | Augmentation | MVS | GO2223007608PH | 13/09/2022 | 968.12 | 64.3 | 1032.42 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 319.83 | 2.48 | 115.33 | 0 | 437.64 | 319.83 | 2.48 | 115.33 | 0 | 437.64 | 42.39 | 60
219 | NORTH 24 PARGANAS | SM/12414 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014753 | 40024331 | Augmentation | MVS | GO2223007609PH | 13/09/2022 | 996.63 | 67.99 | 1064.62 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 567.03 | 2.34 | 136.39 | 16.85 | 722.62 | 567.03 | 2.34 | 136.39 | 16.85 | 722.62 | 67.88 | 75
220 | NORTH 24 PARGANAS | SM/15817 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014836 | 40058926 | Augmentation | MVS | GO2223014255PH | 20/02/2023 | 1049.24 | 127.97 | 1177.21 | North 24 Pgs W/S Division I | Electrical Division | 1.62 | 0 | 9.62 | 0 | 11.23 | 1.62 | 0 | 9.62 | 0 | 11.23 | 0.95 | 5
221 | NORTH 24 PARGANAS | SM/15818 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014884 | 40033167 | Augmentation | MVS | GO2223014380PH | 20/02/2023 | 1409.53 | 67.53 | 1477.06 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 210.04 | 3.65 | 154.15 | 0 | 367.84 | 210.04 | 3.65 | 154.15 | 0 | 367.84 | 24.9 | 30
222 | NORTH 24 PARGANAS | SM/18260 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015251 | 40033389 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1211.93 | 67.53 | 1279.46 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 518.39 | 4.73 | 94.61 | 26.06 | 643.79 | 518.39 | 4.73 | 94.61 | 26.06 | 643.79 | 50.32 | 75
223 | NORTH 24 PARGANAS | SM/13902 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011942 | 40034263 | Augmentation | MVS | GO2223010167PH | 28/11/2022 | 1076.47 | 34.94 | 1111.41 | North 24 Pgs W/S Division I | Electrical Division | 246.85 | 0 | 81.77 | 0 | 328.63 | 246.85 | 0 | 81.77 | 0 | 328.63 | 29.57 | 38
224 | NORTH 24 PARGANAS | SM/11827 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011868 | 40019311 | Augmentation | MVS | GO2223006287PH | 16/08/2022 | 774.71 | 30.71 | 805.42 | North 24 Pgs W/S Division I | Electrical Division | 149.75 | 0 | 3.64 | 0 | 153.39 | 149.75 | 0 | 3.64 | 0 | 153.39 | 19.04 | 28
225 | NORTH 24 PARGANAS | SM/12728 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011949 | 40024231 | Augmentation | MVS | GO2223008010PH | 21/09/2022 | 1369.2 | 59.75 | 1428.95 | North 24 Pgs W/S Division I | Electrical Division | 105.95 | 5.04 | 81.51 | 0 | 192.5 | 105.95 | 5.04 | 81.51 | 0 | 192.5 | 13.47 | 19
226 | NORTH 24 PARGANAS | SM/11826 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011866 | 40019310 | Augmentation | MVS | GO2223006288PH | 16/08/2022 | 883.76 | 30.71 | 914.47 | North 24 Pgs W/S Division I | Electrical Division | 138.55 | 8.52 | 51.84 | 0 | 198.91 | 138.55 | 8.52 | 51.84 | 0 | 198.91 | 21.75 | 27
227 | NORTH 24 PARGANAS | SM/11864 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011948 | 40019331 | Augmentation | MVS | GO2223006446PH | 17/08/2022 | 747.77 | 58.24 | 806.01 | North 24 Pgs W/S Division I | Electrical Division | 164.03 | 3.95 | 19.19 | 0 | 187.16 | 164.03 | 3.95 | 19.19 | 0 | 187.16 | 23.22 | 31
228 | NORTH 24 PARGANAS | SM/13794 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/012002 | 40042163 | Augmentation | MVS | GO2223009959PH | 22/11/2022 | 932.42 | 0 | 932.42 | North 24 Pgs W/S Division I |  | 168.33 | 0 | 142.43 | 0 | 310.76 | 168.33 | 0 | 142.43 | 0 | 310.76 | 33.33 | 40
229 | NORTH 24 PARGANAS | SM/13434 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | TSM/013337 | 40040239 | Augmentation | MVS | GO2223009178PH | 02/11/2022 | 892.16 | 0 | 892.16 | North 24 Pgs W/S Division I |  | 179.75 | 0 | 23.28 | 0 | 203.03 | 179.75 | 0 | 23.28 | 0 | 203.03 | 22.76 | 27
230 | NORTH 24 PARGANAS | SM/12625 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | TSM/012003 | 40024395 | Augmentation | MVS | GO2223007845PH | 19/09/2022 | 1285.8 | 0 | 1285.8 | North 24 Pgs W/S Division I |  | 318.42 | 0 | 73.46 | 0 | 391.88 | 319.17 | 0 | 73.46 | 0 | 392.63 | 30.54 | 36
231 | NORTH 24 PARGANAS | SM/18258 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/013336 | 40037648 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1544.28 | 0 | 1544.28 | North 24 Pgs W/S Division I |  | 4.88 | 0 | 0 | 0 | 4.88 | 4.88 | 0 | 0 | 0 | 4.88 | 0.32 | 1
232 | NORTH 24 PARGANAS | SM/11921 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011601 | 40019337 | Augmentation | MVS | GO2223006613PH | 22/08/2022 | 767.04 | 0 | 767.04 | North 24 Pgs W/S Division I |  | 191.61 | 0 | 0 | 0 | 191.61 | 191.61 | 0 | 0 | 0 | 191.61 | 24.98 | 31
233 | NORTH 24 PARGANAS | SM/12563 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/010887 | 40024322 | Augmentation | MVS | GO2223007702PH | 14/09/2022 | 1134.55 | 0 | 1134.55 | North 24 Pgs W/S Division I |  | 114.6 | 0 | 213.75 | 0 | 328.35 | 114.6 | 0 | 213.75 | 0 | 328.35 | 28.94 | 35
234 | NORTH 24 PARGANAS | SM/12730 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011602 | 40024435 | Augmentation | MVS | GO2223008045PH | 21/09/2022 | 1212.9 | 0 | 1212.9 | North 24 Pgs W/S Division I |  | 4.3 | 0 | 141.06 | 0 | 145.36 | 4.3 | 0 | 141.06 | 0 | 145.36 | 11.98 | 16
235 | NORTH 24 PARGANAS | SM/12566 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011870 | 40024236 | Augmentation | MVS | GO2223007696PH | 14/09/2022 | 1163.85 | 33.87 | 1197.72 | North 24 Pgs W/S Division I | Electrical Division | 233.15 | 0 | 142.17 | 0 | 375.32 | 233.15 | 0 | 142.17 | 0 | 375.32 | 31.34 | 39
236 | NORTH 24 PARGANAS | SM/12372 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011863 | 40024239 | Augmentation | MVS | GO2223007577PH | 13/09/2022 | 1265.6 | 59.75 | 1325.35 | North 24 Pgs W/S Division I | Electrical Division | 94.2 | 0 | 152.17 | 0 | 246.37 | 94.2 | 0 | 152.17 | 0 | 246.37 | 18.59 | 26
237 | NORTH 24 PARGANAS | SM/11941 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011892 | 40024380 | Augmentation | MVS | GO2223006668PH | 24/08/2022 | 867.92 | 30.71 | 898.63 | North 24 Pgs W/S Division I | Electrical Division | 108.65 | 10.06 | 84.9 | 0 | 203.61 | 108.65 | 10.06 | 84.9 | 0 | 203.61 | 22.66 | 30
238 | NORTH 24 PARGANAS | SM/12565 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011891 | 40024390 | Augmentation | MVS | GO2223007694PH | 14/09/2022 | 1208.02 | 59.75 | 1267.76 | North 24 Pgs W/S Division I | Electrical Division | 155.29 | 0 | 118.07 | 0 | 273.36 | 155.29 | 0 | 118.07 | 0 | 273.36 | 21.56 | 29
239 | NORTH 24 PARGANAS | SM/12564 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011897 | 40024375 | Augmentation | MVS | GO2223007711PH | 14/09/2022 | 1491.42 | 62.91 | 1554.33 | North 24 Pgs W/S Division I | Electrical Division | 197.18 | 0 | 115.47 | 0 | 312.64 | 197.18 | 0 | 115.47 | 0 | 312.64 | 20.11 | 25
240 | NORTH 24 PARGANAS | SM/11922 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011824 | 40019339 | Augmentation | MVS | GO2223006615PH | 22/08/2022 | 737.22 | 0 | 737.22 | North 24 Pgs W/S Division I |  | 181.08 | 0 | 0 | 0 | 181.08 | 181.08 | 0 | 0 | 0 | 181.08 | 24.56 | 28
241 | NORTH 24 PARGANAS | SM/12729 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011825 | 40024391 | Augmentation | MVS | GO2223008013PH | 21/09/2022 | 1214.95 | 105.5 | 1320.45 | North 24 Pgs W/S Division I | Electrical Division | 312.48 | 0 | 167 | 0 | 479.48 | 312.48 | 0 | 167 | 0 | 479.48 | 36.31 | 45
242 | NORTH 24 PARGANAS | SM/11971 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011826 | 40024418 | Augmentation | MVS | GO2223006797PH | 29/08/2022 | 909.24 | 0 | 909.24 | North 24 Pgs W/S Division I |  | 221.4 | 0 | 40.36 | 0 | 261.76 | 221.4 | 0 | 40.36 | 0 | 261.76 | 28.79 | 34
243 | NORTH 24 PARGANAS | SM/15559 | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | TSM/017800 | 40061372 | Augmentation | MVS | GO2223013909PH | 16/02/2023 | 270.31 | 37.75 | 308.06 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 39.04 | 0 | 0 | 0 | 39.04 | 51.98 | 0 | 0 | 0 | 51.98 | 16.87
244 | NORTH 24 PARGANAS | SM/17680 | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME | TSM/015003 | 40033878 | Augmentation | SVS | GO2223016655PH | 17/03/2023 | 225.01 | 69.27 | 294.29 | Barasat Division | Eastern Mechanical Division | 52.32 | 0 | 0 | 0 | 52.32 | 52.32 | 0 | 0 | 0 | 52.32 | 17.78 | 75
245 | NORTH 24 PARGANAS | SM/10582 | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | TSM/010664 | 40012922 | Augmentation | MVS | GO2223000337PH | 18/04/2022 | 568.21 | 32.83 | 601.04 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 131.13 | 8.11 | 50.29 | 0 | 189.53 | 131.13 | 8.11 | 50.29 | 0 | 189.53 | 31.53 | 42
246 | NORTH 24 PARGANAS | SM/10546 | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | TSM/010666 | 40012978 | Augmentation | MVS | GO2223000375PH | 18/04/2022 | 705.8 | 32.66 | 738.46 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 78.49 | 0 | 77.41 | 6.56 | 162.45 | 78.49 | 0 | 77.41 | 6.56 | 162.45 | 22 | 100
247 | NORTH 24 PARGANAS | SM/10583 | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | TSM/010275 | 40012988 | Augmentation | MVS | GO2223000389PH | 18/04/2022 | 965.67 | 87.59 | 1053.27 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 457.72 | 15.8 | 60 | 0 | 533.52 | 457.72 | 15.8 | 60 | 0 | 533.52 | 50.65 | 61
248 | NORTH 24 PARGANAS | SM/10580 | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | TSM/010408 | 40012921 | Augmentation | MVS | GO2223000343PH | 18/04/2022 | 624.56 | 65.87 | 690.43 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 320.19 | 23.06 | 119.7 | 0 | 462.95 | 320.19 | 23.06 | 119.7 | 0 | 462.95 | 67.05 | 81
249 | NORTH 24 PARGANAS | SM/10412 | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | TSM/010391 | 40013014 | Augmentation | MVS | GO2223000122PH | 08/04/2022 | 686.29 | 45.13 | 731.42 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 298 | 15.36 | 258.58 | 0 | 571.93 | 298 | 15.36 | 258.58 | 0 | 571.93 | 78.2 | 93
250 | NORTH 24 PARGANAS | SM/10758 | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | TSM/010573 | 40012925 | Augmentation | MVS | GO2223003141PH | 23/05/2022 | 1316.99 | 32.66 | 1349.65 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 48.14 | 0 | 58.71 | 0 | 106.85 | 48.14 | 0 | 58.71 | 0 | 106.85 | 7.92 | 10
251 | NORTH 24 PARGANAS | SM/10777 | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | TSM/009938 | 40013002 | Augmentation | MVS | GO2223003485PH | 25/05/2022 | 1054.95 | 0 | 1054.95 | North 24 Pgs W/S Division I |  | 848.98 | 0 | 43.57 | 0 | 892.55 | 848.98 | 0 | 43.57 | 0 | 892.55 | 84.61 | 95
252 | NORTH 24 PARGANAS | SM/10607 | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | TSM/010566 | 40012924 | Augmentation | MVS | GO2223000413PH | 19/04/2022 | 1065.93 | 32.66 | 1098.59 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 228.73 | 6.63 | 233.47 | 0 | 468.83 | 228.73 | 6.63 | 233.47 | 0 | 468.83 | 42.68 | 45
253 | NORTH 24 PARGANAS | SM/10105 | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | TSM/009496 | 40003034 | Augmentation | MVS | GO2122009125PH | 02/02/2022 | 918.69 | 0 | 918.69 | North 24 Pgs W/S Division I |  | 768.49 | 0 | 58.06 | 0 | 826.55 | 768.49 | 0 | 58.06 | 0 | 826.55 | 89.97 | 97
254 | NORTH 24 PARGANAS | SM/10098 | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | TSM/009448 | 40002898 | Augmentation | MVS | GO2122009131PH | 02/02/2022 | 906.75 | 0 | 906.75 | North 24 Pgs W/S Division I |  | 632.47 | 0 | 91.62 | 0 | 724.09 | 632.47 | 0 | 91.62 | 0 | 724.09 | 79.86 | 84
255 | NORTH 24 PARGANAS | SM/10579 | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | TSM/010599 | 40012932 | Augmentation | MVS | GO2223000344PH | 18/04/2022 | 1046.68 | 27.39 | 1074.06 | North 24 Pgs W/S Division I | Electrical Division | 352.81 | 15.59 | 76.8 | 0 | 445.21 | 352.81 | 17.47 | 76.8 | 0 | 447.08 | 41.63 | 46
256 | NORTH 24 PARGANAS | SM/11556 | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | TSM/011191 | 40019328 | Augmentation | MVS | GO2223005396PH | 22/07/2022 | 469.36 | 74.9 | 544.26 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 120.26 | 5.48 | 33.87 | 21.62 | 181.22 | 120.26 | 5.48 | 33.87 | 21.62 | 181.22 | 33.3 | 46
257 | NORTH 24 PARGANAS | SM/10415 | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | TSM/010388 | 40013020 | Augmentation | MVS | GO2223000125PH | 08/04/2022 | 567.08 | 43.92 | 611 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 354.01 | 21.86 | 22.87 | 0 | 398.74 | 354.01 | 21.86 | 22.87 | 0 | 398.74 | 65.26 | 78
258 | NORTH 24 PARGANAS | SM/10639 | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | TSM/010276 | 40012939 | Augmentation | MVS | GO2223000478PH | 21/04/2022 | 850.64 | 83.14 | 933.78 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 621.29 | 15.53 | 143.45 | 0 | 780.27 | 621.29 | 15.53 | 143.45 | 0 | 780.27 | 83.56 | 93
259 | NORTH 24 PARGANAS | SM/10638 | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | TSM/010263 | 40012970 | Augmentation | MVS | GO2223000477PH | 21/04/2022 | 846.71 | 83.14 | 929.85 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 449.71 | 15.18 | 221.57 | 0 | 686.46 | 449.71 | 15.18 | 221.57 | 0 | 686.46 | 73.83 | 82
260 | NORTH 24 PARGANAS | SM/11212 | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | TSM/010262 | 40012940 | Augmentation | MVS | GO2223003936PH | 09/06/2022 | 1186.58 | 83.14 | 1269.72 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 521.48 | 34.06 | 248.69 | 0 | 804.22 | 521.48 | 34.06 | 248.69 | 0 | 804.22 | 63.34 | 75
261 | NORTH 24 PARGANAS | SM/10608 | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. | TSM/010405 | 40012991 | Augmentation | MVS | GO2223000414PH | 19/04/2022 | 285.33 | 43.92 | 329.25 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 182 | 15.46 | 9.38 | 0 | 206.84 | 182 | 15.46 | 9.38 | 0 | 206.84 | 62.82 | 75
262 | NORTH 24 PARGANAS | SM/11555 | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. | TSM/011010 | 40019068 | Augmentation | MVS | GO2223005395PH | 22/07/2022 | 646.37 | 32.66 | 679.03 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.33 | 3.33 | 44.07 | 13.98 | 64.71 | 3.33 | 3.33 | 44.07 | 13.98 | 64.71 | 9.53 | 12
263 | NORTH 24 PARGANAS | SM/10581 | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | TSM/009939 | 40012928 | Augmentation | MVS | GO2223000340PH | 18/04/2022 | 702.18 | 0 | 702.18 | North 24 Pgs W/S Division I |  | 536.86 | 0 | 25.46 | 0 | 562.32 | 536.86 | 0 | 25.46 | 0 | 562.32 | 80.08 | 91
264 | NORTH 24 PARGANAS | SM/10153 | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | TSM/009497 | 40003042 | Augmentation | MVS | GO2122009656PH | 11/02/2022 | 1043.42 | 0 | 1043.42 | North 24 Pgs W/S Division I |  | 533.13 | 0 | 94.3 | 0 | 627.43 | 533.13 | 0 | 94.3 | 0 | 627.43 | 60.13 | 70
265 | NORTH 24 PARGANAS | SM/19040 | SURFACE BASED PWSS FOR BARASAT-II BLOCK | TSM/018399 | 40061389 | Augmentation | MVS | 3497/PHE-28011/135/2023-SCHM CELL-Dept. of PHE | 17/11/2023 | 8113.35 | 1369.99 | 9483.34 | Barasat Arsenic Division | Eastern Mechanical Division | 285.26 | 0 | 2389.9 | 0 | 2675.15 | 285.26 | 0 | 2389.9 | 0 | 2675.15 | 28.21 | 30
Total | [9 empty] | 243846.61 | 14610.77 | 258457.38 |  |  | 91757.95 | 3262.69 | 23356.63 | 874 | 119251.27 | 91790.01 | 3261.78 | 23356.63 | 874 | 119282.41 | 46.15