## JJM Schemes Financial Status (N
JJM Schemes Financial Status (NORTH 24 PARAGANAS) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | NORTH 24 PARAGANAS | SM/10781 | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | TSM/009736 | 40065640 | Augmentation | SVS | GO2223003526PH | 25/05/2022 | 477.26 | 42.43 | 519.69 | Barasat Division | Eastern Mechanical Division | 367.28 | 0 | 0 | 0 | 367.28 | 367.28 | 0 | 0 | 0 | 367.28 | 70.67 | 44
2 | NORTH 24 PARAGANAS | SM/11214 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | TSM/009082 | 40002871 | Augmentation | MVS | GO2223004062PH | 13/06/2022 | 1343.1 | 31.45 | 1374.55 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 736.95 | 0 | 103.55 | 0 | 840.5 | 709.92 | 0 | 103.55 | 0 | 813.47 | 59.18 | 59
3 | NORTH 24 PARAGANAS | SM/12714 | Niruli Piped Water Supply Scheme | TSM/014715 | 40031732 | New | MVS | GO2223008028PH | 21/09/2022 | 725.22 | 61.01 | 786.23 | Barasat Division | Eastern Mechanical Division | 246.59 | 7.18 | 0 | 0 | 253.77 | 246.59 | 7.18 | 0 | 0 | 253.77 | 32.28 | 25
4 | NORTH 24 PARAGANAS | SM/13984 | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota | TSM/014709 | 40032846 | Augmentation | MVS | GO2223010356PH | 01/12/2022 | 273.98 | 0 | 273.98 | Barasat Division |  | 122.79 | 0 | 25.26 | 0 | 148.04 | 122.79 | 0 | 25.26 | 0 | 148.04 | 54.03 | 35
5 | NORTH 24 PARAGANAS | SM/15831 | Ambaria Piped Water Supply Scheme | TSM/015378 | 40033589 | New | MVS | GO2223014386PH | 20/02/2023 | 1062.64 | 58.4 | 1121.04 | Barasat Division | Eastern Mechanical Division | 348.79 | 10.41 | 21.04 | 0 | 380.23 | 348.79 | 10.41 | 21.04 | 0 | 380.23 | 33.92 | 8
6 | NORTH 24 PARAGANAS | SM/15828 | Atpukur Zone-I Piped Water Supply Scheme | TSM/015515 | 40033567 | New | MVS | GO2223014379PH | 20/02/2023 | 1035.72 | 91.52 | 1127.24 | Barasat Division | Eastern Mechanical Division | 180.21 | 29.53 | 24.51 | 0 | 234.25 | 174.95 | 29.53 | 24.51 | 0 | 228.99 | 20.31 | 10
7 | NORTH 24 PARAGANAS | SM/13510 | Atpukur Zone-II Piped Water Supply Scheme | TSM/015451 | 40032099 | New | SVS | GO2223009236PH | 02/11/2022 | 558 | 61.01 | 619.01 | Barasat Division | Eastern Mechanical Division | 185.66 | 21.15 | 15.73 | 0 | 222.54 | 184.79 | 21.15 | 15.73 | 0 | 221.66 | 35.81 | 19
8 | NORTH 24 PARAGANAS | SM/11558 | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | TSM/009584 | 40026999 | Augmentation | MVS | GO2223005423PH | 22/07/2022 | 630.9 | 63.85 | 694.76 | Barasat Arsenic Division | Eastern Mechanical Division | 311.16 | 14.79 | 41.83 | 0 | 367.77 | 311.16 | 14.79 | 41.83 | 0 | 367.77 | 52.93 | 81
9 | NORTH 24 PARAGANAS | SM/14490 | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme | TSM/015718 | 40032840 | Augmentation | MVS | GO2223012266PH | 20/01/2023 | 1497.85 | 64.43 | 1562.27 | Barasat Division | Eastern Mechanical Division | 4.74 | 3.5 | 122.45 | 0 | 130.68 | 3.86 | 3.5 | 122.45 | 0 | 129.8 | 8.31 | 6
10 | NORTH 24 PARAGANAS | SM/13893 | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme | TSM/015719 | 40032895 | Augmentation | MVS | GO2223010098PH | 25/11/2022 | 997.56 | 61.36 | 1058.92 | Barasat Division | Eastern Mechanical Division | 171.99 | 0 | 24.75 | 0 | 196.74 | 171.1 | 0 | 24.75 | 0 | 195.85 | 18.5 | 19
11 | NORTH 24 PARAGANAS | SM/13894 | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | TSM/015720 | 40032853 | Augmentation | MVS | GO2223010058PH | 25/11/2022 | 1108.64 | 61.36 | 1170 | Barasat Division | Eastern Mechanical Division | 198.66 | 4.64 | 122.9 | 0 | 326.2 | 197.79 | 4.64 | 122.9 | 0 | 325.33 | 27.81 | 24
12 | NORTH 24 PARAGANAS | SM/15323 | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme | TSM/015721 | 40032777 | Augmentation | MVS | GO2223013655PH | 09/02/2023 | 1645.95 | 64.43 | 1710.38 | Barasat Division | Eastern Mechanical Division | 4.83 | 3.05 | 105.55 | 0 | 113.42 | 3.95 | 3.05 | 105.55 | 0 | 112.55 | 6.58 | 7
13 | NORTH 24 PARAGANAS | SM/13892 | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme | TSM/015722 | 40032819 | Augmentation | MVS | GO2223010097PH | 25/11/2022 | 1112.65 | 61.36 | 1174.01 | Barasat Division | Eastern Mechanical Division | 70.61 | 4.19 | 65.99 | 0 | 140.79 | 70.61 | 4.19 | 65.99 | 0 | 140.79 | 11.99 | 21
14 | NORTH 24 PARAGANAS | SM/14511 | Augmentation of Bermajur Piped water supply scheme | TSM/018703 | 40060623 | Augmentation | SVS | GO2223012327PH | 20/01/2023 | 914.67 | 85.89 | 1000.57 | Barasat Division | Eastern Mechanical Division | 246.67 | 0 | 36.68 | 0 | 283.35 | 246.67 | 0 | 36.68 | 0 | 283.35 | 28.32 | 81
15 | NORTH 24 PARAGANAS | SM/14514 | Augmentation of Chhota Sehara Piped water supply scheme | TSM/018702 | 40060612 | Augmentation | MVS | GO2223012323PH | 20/01/2023 | 746.18 | 45.09 | 791.27 | Barasat Division | Eastern Mechanical Division | 234.27 | 5.02 | 0 | 0 | 239.29 | 234.27 | 5.02 | 0 | 0 | 239.29 | 30.24 | 39
16 | NORTH 24 PARAGANAS | SM/13420 | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/015209 | 40036608 | Augmentation | MVS | GO2223009246PH | 02/11/2022 | 403.44 | 45.18 | 448.62 | Barasat Arsenic Division | Eastern Mechanical Division | 112.07 | 0 | 0 | 0 | 112.07 | 112.07 | 0 | 0 | 0 | 112.07 | 24.98 | 27
17 | NORTH 24 PARAGANAS | SM/11544 | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010752 | 40035125 | Augmentation | MVS | GO2223005393PH | 22/07/2022 | 591.88 | 42.57 | 634.45 | Barasat Arsenic Division | Eastern Mechanical Division | 280.66 | 0 | 45.07 | 0 | 325.73 | 280.66 | 0 | 45.07 | 0 | 325.73 | 51.34 | 67
18 | NORTH 24 PARAGANAS | SM/11545 | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010751 | 40026966 | Augmentation | MVS | GO2223005394PH | 22/07/2022 | 264.52 | 20.85 | 285.37 | Barasat Arsenic Division | Eastern Mechanical Division | 169.48 | 2.06 | 1.53 | 19.06 | 192.12 | 169.48 | 2.06 | 1.53 | 19.06 | 192.12 | 67.32 | 64
19 | NORTH 24 PARAGANAS | SM/11559 | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010753 | 40026940 | Augmentation | MVS | GO2223005392PH | 22/07/2022 | 233.01 | 20.85 | 253.86 | Barasat Arsenic Division | Eastern Mechanical Division | 147.28 | 0 | 0 | 0 | 147.28 | 147.28 | 0 | 0 | 0 | 147.28 | 58.02 | 70
20 | NORTH 24 PARAGANAS | SM/13468 | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | TSM/015553 | 40033263 | Augmentation | SVS | GO2223009234PH | 02/11/2022 | 975.56 | 80.64 | 1056.2 | Barasat Division | Eastern Mechanical Division | 297.82 | 27.2 | 99.83 | 11.99 | 436.84 | 297.82 | 27.2 | 99.83 | 11.99 | 436.84 | 41.36 | 33
21 | NORTH 24 PARAGANAS | SM/18416 | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | TSM/015584 | 40033542 | Augmentation | MVS | 1871/PHE-28011/200/2022-ESTT CELL-Dept. of PHE | 13/07/2023 | 2601.03 | 115 | 2716.04 | Barasat Division | Eastern Mechanical Division | 167.42 | 0 | 144.71 | 13.11 | 325.24 | 165.66 | 0 | 87.2 | 13.11 | 265.97 | 9.79 | 2
22 | NORTH 24 PARAGANAS | SM/14161 | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC | TSM/015769 | 40032791 | Augmentation | MVS | GO2223011630PH | 05/01/2023 | 2650.35 | 134.5 | 2784.85 | Barasat Division | Eastern Mechanical Division | 1.81 | 13.45 | 218.29 | 26.66 | 260.2 | 0 | 13.45 | 218.29 | 26.66 | 258.39 | 9.28 | 13
23 | NORTH 24 PARAGANAS | SM/14127 | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. | TSM/011254 | 40032898 | Augmentation | MVS | GO2223011523PH | 02/01/2023 | 454.3 | 40.32 | 494.62 | Barasat Division | Eastern Mechanical Division | 83.01 | 0 | 30.43 | 0 | 113.44 | 83.01 | 0 | 30.43 | 0 | 113.44 | 22.93 | 32
24 | NORTH 24 PARAGANAS | SM/15324 | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | TSM/015764 | 40032816 | Augmentation | SVS | GO2223013702PH | 10/02/2023 | 1110.55 | 73.61 | 1184.15 | Barasat Division | Eastern Mechanical Division | 218.39 | 0 | 85.65 | 13.27 | 317.3 | 217.13 | 0 | 85.65 | 13.27 | 316.05 | 26.69 | 2
25 | NORTH 24 PARAGANAS | SM/14733 | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC | TSM/015552 | 40033562 | Augmentation | SVS | GO2223012649PH | 31/01/2023 | 686.09 | 46 | 732.09 | Barasat Division | Eastern Mechanical Division | 316.62 | 12.03 | 16.51 | 0 | 345.16 | 314.92 | 0 | 16.51 | 0 | 331.43 | 45.27 | 34
26 | NORTH 24 PARAGANAS | SM/13446 | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. | TSM/011247 | 40032100 | Augmentation | SVS | GO2223009241PH | 02/11/2022 | 824.14 | 42.93 | 867.07 | Barasat Division | Eastern Mechanical Division | 126.88 | 0 | 110.19 | 13.33 | 250.4 | 126.88 | 0 | 110.19 | 13.33 | 250.4 | 28.88 | 19
27 | NORTH 24 PARAGANAS | SM/13471 | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. | TSM/011244 | 40032969 | Augmentation | SVS | GO2223009260PH | 02/11/2022 | 473.88 | 64.4 | 538.28 | Barasat Division | Eastern Mechanical Division | 90.23 | 0 | 61.71 | 13.53 | 165.46 | 90.23 | 0 | 61.71 | 13.53 | 165.46 | 30.74 | 16
28 | NORTH 24 PARAGANAS | SM/13469 | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. | TSM/011245 | 40032946 | Augmentation | SVS | GO2223009261PH | 02/11/2022 | 1086.94 | 64.4 | 1151.34 | Barasat Division | Eastern Mechanical Division | 0 | 0 | 24.5 | 0 | 24.5 | 0 | 0 | 24.5 | 0 | 24.5 | 2.13 | 9
29 | NORTH 24 PARAGANAS | SM/11940 | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | TSM/012009 | 40035639 | Augmentation | MVS | GO2223006667PH | 24/08/2022 | 200.23 | 0 | 200.23 | North 24 Pgs W/S Division I |  | 59.45 | 0 | 0 | 0 | 59.45 | 59.45 | 0 | 0 | 0 | 59.45 | 29.69 | 25
30 | NORTH 24 PARAGANAS | SM/11664 | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. | TSM/011212 | 40059430 | Augmentation | MVS | GO2223005641PH | 27/07/2022 | 939.47 | 71.09 | 1010.56 | Barasat Division | Eastern Mechanical Division | 433.16 | 25.26 | 135.86 | 0 | 594.28 | 433.16 | 25.26 | 135.86 | 0 | 594.28 | 58.81 | 62
31 | NORTH 24 PARAGANAS | SM/11533 | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | TSM/011084 | 40036108 | Augmentation | MVS | GO2223005234PH | 19/07/2022 | 396.4 | 40.41 | 436.8 | Barasat Division | Eastern Mechanical Division | 72.5 | 19.72 | 20.77 | 0 | 112.99 | 72.5 | 19.72 | 20.77 | 0 | 112.99 | 25.87 | 18
32 | NORTH 24 PARAGANAS | SM/11700 | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC | TSM/011315 | 40029255 | Augmentation | MVS | GO2223005720PH | 29/07/2022 | 1079.51 | 41.57 | 1121.08 | Barasat Division | Eastern Mechanical Division | 319.4 | 0 | 30.93 | 14.99 | 365.32 | 319.4 | 0 | 30.93 | 14.99 | 365.32 | 32.59 | 10
33 | NORTH 24 PARAGANAS | SM/10558 | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | TSM/010450 | 40018934 | Augmentation | MVS | GO2223000387PH | 18/04/2022 | 860.26 | 41.7 | 901.97 | Barasat Division | Eastern Mechanical Division | 314.21 | 0 | 0 | 0 | 314.21 | 314.21 | 0 | 0 | 0 | 314.21 | 34.84 | 63
34 | NORTH 24 PARAGANAS | SM/11597 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | TSM/011163 | 40036144 | Augmentation | MVS | GO2223005374PH | 22/07/2022 | 317.52 | 39.58 | 357.1 | Barasat Division | Eastern Mechanical Division | 136.24 | 0 | 17.47 | 0 | 153.71 | 136.24 | 0 | 17.47 | 0 | 153.71 | 43.05 | 45
35 | NORTH 24 PARAGANAS | SM/11705 | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011252 | 40026475 | Augmentation | SVS | GO2223005727PH | 29/07/2022 | 504.75 | 20.84 | 525.59 | Barasat Arsenic Division | Eastern Mechanical Division | 234.85 | 10.12 | 0 | 0 | 244.97 | 234.85 | 10.12 | 0 | 0 | 244.97 | 46.61 | 52
36 | NORTH 24 PARAGANAS | SM/13040 | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC | TSM/011320 | 40029321 | Augmentation | MVS | GO2223008513PH | 29/09/2022 | 1367.83 | 62.36 | 1430.19 | Barasat Division | Eastern Mechanical Division | 536.89 | 0 | 103.98 | 0 | 640.87 | 536.89 | 0 | 103.98 | 0 | 640.87 | 44.81 | 46
37 | NORTH 24 PARAGANAS | SM/10102 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | TSM/009323 | 40002976 | Augmentation | MVS | GO2122009115PH | 02/02/2022 | 620.68 | 0 | 620.68 | North 24 Pgs W/S Division I |  | 249.53 | 0 | 31.59 | 0 | 281.12 | 249.53 | 0 | 31.59 | 0 | 281.12 | 45.29 | 88
38 | NORTH 24 PARAGANAS | SM/10310 | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC | TSM/009251 | 40005414 | Augmentation | MVS | GO2122010483PH | 04/03/2022 | 672.9 | 32.61 | 705.5 | Barasat Division | Eastern Mechanical Division | 312.19 | 19.3 | 63.39 | 0 | 394.88 | 261.56 | 19.3 | 63.39 | 0 | 344.25 | 48.8 | 63
39 | NORTH 24 PARAGANAS | SM/11756 | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | TSM/011318 | 40029290 | Augmentation | MVS | GO2223005912PH | 02/08/2022 | 963.51 | 41.57 | 1005.08 | Barasat Division | Eastern Mechanical Division | 287.61 | 27.93 | 33.28 | 0 | 348.82 | 287.61 | 27.93 | 33.28 | 0 | 348.82 | 34.71 | 24
40 | NORTH 24 PARAGANAS | SM/11701 | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC | TSM/011316 | 40029273 | Augmentation | MVS | GO2223005718PH | 29/07/2022 | 565.42 | 41.57 | 606.99 | Barasat Division | Eastern Mechanical Division | 306.72 | 0 | 10.1 | 0 | 316.82 | 306.72 | 0 | 10.1 | 0 | 316.82 | 52.2 | 62
41 | NORTH 24 PARAGANAS | SM/10109 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | TSM/009515 | 40002703 | Augmentation | MVS | GO2122009114PH | 02/02/2022 | 843.1 | 0 | 843.1 | North 24 Pgs W/S Division I |  | 611.48 | 0 | 116 | 0 | 727.49 | 566.1 | 0 | 116 | 0 | 682.1 | 80.9 | 85
42 | NORTH 24 PARAGANAS | SM/18618 | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | TSM/011390 | 40062805 | Augmentation | SVS | 2161/PHE-28011/238/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 955.72 | 62.36 | 1018.08 | Barasat Division | Eastern Mechanical Division | 255.62 | 0 | 0 | 0 | 255.62 | 255.62 | 0 | 0 | 0 | 255.62 | 25.11 | 2
43 | NORTH 24 PARAGANAS | SM/12276 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC | TSM/011166 | 40022726 | Augmentation | MVS | GO2223007385PH | 09/09/2022 | 1436.99 | 39.58 | 1476.58 | Barasat Division | Eastern Mechanical Division | 718.4 | 18.74 | 136.32 | 0 | 873.46 | 718.4 | 18.74 | 136.32 | 0 | 873.46 | 59.15 | 38
44 | NORTH 24 PARAGANAS | SM/11634 | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | TSM/011024 | 40035335 | Augmentation | MVS | GO2223005581PH | 26/07/2022 | 470.94 | 40.41 | 511.35 | Barasat Division | Eastern Mechanical Division | 169.23 | 0 | 103.67 | 0 | 272.9 | 169.23 | 0 | 103.67 | 0 | 272.9 | 53.37 | 40
45 | NORTH 24 PARAGANAS | SM/11704 | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC | TSM/011389 | 40030494 | Augmentation | MVS | GO2223005719PH | 29/07/2022 | 810.88 | 41.57 | 852.45 | Barasat Division | Eastern Mechanical Division | 325.25 | 0 | 66.01 | 0 | 391.26 | 325.25 | 0 | 66.01 | 0 | 391.26 | 45.9 | 55
46 | NORTH 24 PARAGANAS | SM/11987 | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. | TSM/011200 | 40036205 | Augmentation | MVS | GO2223006902PH | 01/09/2022 | 1716.2 | 100.62 | 1816.81 | Barasat Division | Eastern Mechanical Division | 965.93 | 68.06 | 68.8 | 0 | 1102.78 | 965.93 | 68.03 | 68.8 | 0 | 1102.76 | 60.7 | 94
47 | NORTH 24 PARAGANAS | SM/10514 | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | TSM/010006 | 40026963 | Augmentation | MVS | GO2223000235PH | 13/04/2022 | 950.13 | 33.75 | 983.88 | Barasat Division | Eastern Mechanical Division | 657.67 | 0 | 36.38 | 0 | 694.05 | 657.67 | 0 | 36.38 | 0 | 694.05 | 70.54 | 94
48 | NORTH 24 PARAGANAS | SM/11534 | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | TSM/011109 | 40030441 | Augmentation | SVS | GO2223005247PH | 19/07/2022 | 387.01 | 35.74 | 422.75 | Barasat Division | Eastern Mechanical Division | 157.92 | 0 | 7.57 | 0 | 165.5 | 157.92 | 0 | 7.57 | 0 | 165.5 | 39.15 | 100
49 | NORTH 24 PARAGANAS | SM/12126 | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC | TSM/011161 | 40036203 | Augmentation | MVS | GO2223007075PH | 06/09/2022 | 2381.85 | 134.3 | 2516.15 | Barasat Division | Eastern Mechanical Division | 542.95 | 0 | 308.01 | 0 | 850.96 | 542.95 | 0 | 308.01 | 0 | 850.96 | 33.82 | 38
50 | NORTH 24 PARAGANAS | SM/10782 | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | TSM/010461 | 40018990 | Augmentation | MVS | GO2223003488PH | 25/05/2022 | 1057.58 | 35.56 | 1093.14 | Barasat Division | Eastern Mechanical Division | 382.07 | 19.18 | 274.11 | 0 | 675.37 | 382.07 | 19.18 | 274.11 | 0 | 675.37 | 61.78 | 37
51 | NORTH 24 PARAGANAS | SM/13737 | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC | TSM/011746 | 1723424 | Augmentation | MVS | GO2223009850PH | 17/11/2022 | 1375.94 | 83.14 | 1459.08 | Barasat Division | Eastern Mechanical Division | 324.97 | 0 | 110.2 | 0 | 435.17 | 324.97 | 0 | 110.2 | 0 | 435.17 | 29.83 | 4
52 | NORTH 24 PARAGANAS | SM/12895 | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC | TSM/011747 | 1723424 | Augmentation | MVS | GO2223008137PH | 23/09/2022 | 795.95 | 41.57 | 837.52 | Barasat Division | Eastern Mechanical Division | 273.33 | 0 | 23.94 | 0 | 297.27 | 273.33 | 0 | 23.94 | 0 | 297.27 | 35.49 | 2
53 | NORTH 24 PARAGANAS | SM/14162 | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC | TSM/011276 | 40032894 | Augmentation | MVS | GO2223011629PH | 05/01/2023 | 1945.88 | 101.21 | 2047.08 | Barasat Division | Eastern Mechanical Division | 4.27 | 0 | 75.8 | 12.84 | 92.9 | 3.39 | 0 | 75.8 | 12.84 | 92.02 | 4.5 | 5
54 | NORTH 24 PARAGANAS | SM/10374 | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | TSM/009733 | 40007144 | Augmentation | SVS | GO2122010928PH | 16/03/2022 | 1094.7 | 42.43 | 1137.13 | Barasat Division | Eastern Mechanical Division | 536.25 | 19.9 | 0 | 0 | 556.15 | 535.41 | 19.9 | 0 | 0 | 555.31 | 48.83 | 91
55 | NORTH 24 PARAGANAS | SM/11536 | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | TSM/011171 | 40018936 | Augmentation | MVS | GO2223005246PH | 19/07/2022 | 954.51 | 109.49 | 1064.01 | Barasat Division | Eastern Mechanical Division | 657.72 | 57.89 | 0 | 0 | 715.6 | 657.72 | 57.89 | 0 | 0 | 715.6 | 67.26 | 71
56 | NORTH 24 PARAGANAS | SM/10371 | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | TSM/009734 | 40007148 | Augmentation | SVS | GO2122010932PH | 16/03/2022 | 1111.13 | 40.41 | 1151.54 | Barasat Division | Eastern Mechanical Division | 504.81 | 19.92 | 0 | 0 | 524.72 | 504.81 | 19.92 | 0 | 0 | 524.72 | 45.57 | 96
57 | NORTH 24 PARAGANAS | SM/11669 | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC | TSM/011167 | 40037196 | Augmentation | MVS | GO2223005635PH | 27/07/2022 | 1026.66 | 41.57 | 1068.23 | Barasat Division | Eastern Mechanical Division | 407.05 | 0 | 88.41 | 0 | 495.46 | 407.05 | 0 | 88.41 | 0 | 495.46 | 46.38 | 67
58 | NORTH 24 PARAGANAS | SM/10584 | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | TSM/010452 | 40018881 | Augmentation | MVS | GO2223000383PH | 18/04/2022 | 532.75 | 43.8 | 576.54 | Barasat Division | Eastern Mechanical Division | 147.38 | 14.37 | 0 | 0 | 161.74 | 147.38 | 14.37 | 0 | 0 | 161.74 | 28.05 | 97
59 | NORTH 24 PARAGANAS | SM/11586 | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | TSM/011072 | 40036135 | Augmentation | MVS | GO2223005411PH | 22/07/2022 | 446.99 | 40.41 | 487.39 | Barasat Division | Eastern Mechanical Division | 192.42 | 0 | 6.16 | 0 | 198.58 | 192.42 | 0 | 6.16 | 0 | 198.58 | 40.74 | 49
60 | NORTH 24 PARAGANAS | SM/18582 | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | TSM/011307 | 40033230 | Augmentation | MVS | 2145/PHE-28011/130/2022-SCHM CELL-Dept. of PHE | 31/07/2023 | 1261.7 | 41.57 | 1303.27 | Barasat Division | Eastern Mechanical Division | 769.19 | 0 | 124.58 | 0 | 893.77 | 769.19 | 0 | 124.58 | 0 | 893.77 | 68.58 | 69
61 | NORTH 24 PARAGANAS | SM/10587 | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | TSM/010456 | 40029463 | Augmentation | MVS | GO2223000361 PH | 18/04/2022 | 976.51 | 54.62 | 1031.13 | Barasat Division | Eastern Mechanical Division | 446.24 | 0 | 41.96 | 0 | 488.2 | 446.24 | 0 | 41.96 | 0 | 488.2 | 47.35 | 53
62 | NORTH 24 PARAGANAS | SM/13313 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | TSM/011206 | 40036802 | Augmentation | MVS | GO2223008873PH | 17/10/2022 | 1473.91 | 88.57 | 1562.48 | Barasat Division | Eastern Mechanical Division | 572.79 | 9.13 | 64.36 | 0 | 646.28 | 572.79 | 9.13 | 64.36 | 0 | 646.28 | 41.36 | 57
63 | NORTH 24 PARAGANAS | SM/10299 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | TSM/009123 | 1723303 | Augmentation | MVS | GO2122010325PH | 02/03/2022 | 429.81 | 0 | 429.81 | North 24 Pgs W/S Division I |  | 208.12 | 0 | 14.26 | 0 | 222.38 | 208.12 | 0 | 14.26 | 0 | 222.38 | 51.74 | 68
64 | NORTH 24 PARAGANAS | SM/11592 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | TSM/011106 | 40023367 | Augmentation | SVS | GO2223005407PH | 22/07/2022 | 708.05 | 35.74 | 743.79 | Barasat Division | Eastern Mechanical Division | 259.3 | 0 | 196.01 | 0 | 455.32 | 259.3 | 0 | 196.01 | 0 | 455.32 | 61.22 | 77
65 | NORTH 24 PARAGANAS | SM/13767 | Augmentation of ground water based piped water supply scheme for Chhaimalpur | TSM/012028 | 40032932 | Augmentation | MVS | GO2223009912PH | 18/11/2022 | 349.82 | 39.58 | 389.4 | Barasat Division | Eastern Mechanical Division | 223.84 | 35.1 | 0 | 0 | 258.94 | 223.84 | 35.1 | 0 | 0 | 258.94 | 66.5 | 51
66 | NORTH 24 PARAGANAS | SM/11593 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | TSM/011107 | 40022722 | Augmentation | MVS | GO2223005410PH | 22/07/2022 | 920.37 | 33.75 | 954.12 | Barasat Division | Eastern Mechanical Division | 481.76 | 0 | 56.04 | 0 | 537.8 | 481.76 | 0 | 56.04 | 0 | 537.8 | 56.37 | 75
67 | NORTH 24 PARAGANAS | SM/11594 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | TSM/011110 | 40022738 | Augmentation | MVS | GO2223005417PH | 22/07/2022 | 718.46 | 35.74 | 754.2 | Barasat Division | Eastern Mechanical Division | 312.15 | 0 | 159.65 | 0 | 471.8 | 312.15 | 0 | 159.65 | 0 | 471.8 | 62.56 | 80
68 | NORTH 24 PARAGANAS | SM/11535 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | TSM/011169 | 40022721 | Augmentation | MVS | GO2223005244PH | 19/07/2022 | 436.85 | 33.75 | 470.6 | Barasat Division | Eastern Mechanical Division | 185.51 | 16.02 | 59.3 | 0 | 260.83 | 173.57 | 16.02 | 59.3 | 0 | 248.88 | 52.89 | 75
69 | NORTH 24 PARAGANAS | SM/10690 | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | TSM/010451 | 40036817 | Augmentation | MVS | GO2223001397PH | 12/05/2022 | 815.28 | 54.62 | 869.9 | Barasat Division | Eastern Mechanical Division | 484.89 | 0 | 41.21 | 0 | 526.1 | 484.89 | 0 | 41.21 | 0 | 526.1 | 60.48 | 42
70 | NORTH 24 PARAGANAS | SM/11754 | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC | TSM/011431 | 40029482 | Augmentation | MVS | GO2223005904PH | 02/08/2022 | 145.95 | 20.2 | 166.16 | Barasat Division | Eastern Mechanical Division | 43.28 | 0 | 17.36 | 0 | 60.63 | 43.28 | 0 | 17.36 | 0 | 60.63 | 36.49 | 27
71 | NORTH 24 PARAGANAS | SM/12123 | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC | TSM/010932 | 40036196 | Augmentation | MVS | GO2223007076PH | 06/09/2022 | 1478.59 | 61.14 | 1539.73 | Barasat Division | Eastern Mechanical Division | 551.7 | 0 | 129.86 | 0 | 681.55 | 551.7 | 0 | 129.86 | 0 | 681.55 | 44.26 | 24
72 | NORTH 24 PARAGANAS | SM/12277 | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | TSM/010933 | 40035631 | Augmentation | MVS | GO2223007391PH | 09/09/2022 | 1926.5 | 91.88 | 2018.38 | Barasat Division | Eastern Mechanical Division | 916.08 | 0 | 192.01 | 0 | 1108.09 | 916.08 | 0 | 192.01 | 0 | 1108.09 | 54.9 | 28
73 | NORTH 24 PARAGANAS | SM/11658 | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC | TSM/011370 | 40022577 | Augmentation | MVS | GO2223005636PH | 27/07/2022 | 677.36 | 41.57 | 718.93 | Barasat Division | Eastern Mechanical Division | 277.94 | 0 | 85.15 | 0 | 363.09 | 277.94 | 0 | 85.15 | 0 | 363.09 | 50.5 | 22
74 | NORTH 24 PARAGANAS | SM/12568 | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | TSM/011317 | 40029281 | Augmentation | MVS | GO2223007712PH | 14/09/2022 | 1635.7 | 41.57 | 1677.27 | Barasat Division | Eastern Mechanical Division | 410.06 | 0 | 201.01 | 14.98 | 626.05 | 410.06 | 0 | 201.01 | 14.98 | 626.05 | 37.33 | 39
75 | NORTH 24 PARAGANAS | SM/11703 | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC | TSM/011421 | 40022709 | Augmentation | MVS | GO2223005722PH | 29/07/2022 | 414.92 | 40.41 | 455.33 | Barasat Division | Eastern Mechanical Division | 218.56 | 0 | 0 | 0 | 218.56 | 218.56 | 0 | 0 | 0 | 218.56 | 48 | 40
76 | NORTH 24 PARAGANAS | SM/11537 | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | TSM/011178 | 40060048 | Augmentation | MVS | GO2223005245PH | 19/07/2022 | 664.86 | 39.58 | 704.44 | Barasat Division | Eastern Mechanical Division | 295.41 | 14.38 | 7.62 | 0 | 317.41 | 293.79 | 14.38 | 7.62 | 0 | 315.8 | 44.83 | 5
77 | NORTH 24 PARAGANAS | SM/17679 | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | TSM/011275 | 40033868 | Augmentation | SVS | GO2223016648PH | 17/03/2023 | 922.81 | 46 | 968.81 | Barasat Division | Eastern Mechanical Division | 78.28 | 3.79 | 112.6 | 0 | 194.67 | 75.48 | 3.79 | 112.6 | 0 | 191.87 | 19.81 | 33
78 | NORTH 24 PARAGANAS | SM/11753 | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC | TSM/011429 | 40029481 | Augmentation | MVS | GO2223005983PH | 03/08/2022 | 465.1 | 40.41 | 505.51 | Barasat Division | Eastern Mechanical Division | 202.41 | 0 | 0 | 0 | 202.41 | 202.41 | 0 | 0 | 0 | 202.41 | 40.04 | 4
79 | NORTH 24 PARAGANAS | SM/12274 | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC | TSM/011071 | 40035375 | Augmentation | MVS | GO2223007387PH | 09/09/2022 | 1586.76 | 60.61 | 1647.37 | Barasat Division | Eastern Mechanical Division | 358 | 0 | 93.57 | 0 | 451.57 | 358 | 0 | 93.57 | 0 | 451.57 | 27.41 | 17
80 | NORTH 24 PARAGANAS | SM/11527 | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | TSM/011069 | 40036096 | Augmentation | MVS | GO2223005230PH | 19/07/2022 | 660.27 | 60.61 | 720.88 | Barasat Division | Eastern Mechanical Division | 303 | 30.16 | 34.28 | 0 | 367.44 | 303 | 30.16 | 34.28 | 0 | 367.44 | 50.97 | 81
81 | NORTH 24 PARAGANAS | SM/11668 | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC | TSM/011165 | 40036157 | Augmentation | MVS | GO2223005634PH | 27/07/2022 | 841.02 | 39.58 | 880.6 | Barasat Division | Eastern Mechanical Division | 383.24 | 14.38 | 133.75 | 0 | 531.37 | 369.45 | 14.38 | 133.75 | 0 | 517.58 | 58.78 | 85
82 | NORTH 24 PARAGANAS | SM/11660 | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC | TSM/011387 | 40022568 | Augmentation | MVS | GO2223005637PH | 27/07/2022 | 651.99 | 41.57 | 693.56 | Barasat Division | Eastern Mechanical Division | 126.92 | 12.15 | 91.26 | 0 | 230.33 | 126.92 | 12.15 | 91.26 | 0 | 230.33 | 33.21 | 26
83 | NORTH 24 PARAGANAS | SM/10370 | Augmentation of Ground water based piped water supply scheme for Durgamandap | TSM/009737 | 40007150 | Augmentation | SVS | GO2122010918PH | 16/03/2022 | 824.92 | 42.43 | 867.35 | Barasat Division | Eastern Mechanical Division | 374.72 | 20.71 | 0 | 0 | 395.42 | 373.75 | 20.71 | 0 | 0 | 394.46 | 45.48 | 48
84 | NORTH 24 PARAGANAS | SM/12111 | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | TSM/010457 | 40035515 | Augmentation | MVS | GO2223006987PH | 02/09/2022 | 888.35 | 43.8 | 932.15 | Barasat Division | Eastern Mechanical Division | 570.39 | 18.16 | 0 | 0 | 588.55 | 570.39 | 18.16 | 0 | 0 | 588.55 | 63.14 | 100
85 | NORTH 24 PARAGANAS | SM/12275 | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC | TSM/011157 | 40035515 | Augmentation | MVS | GO2223007388PH | 09/09/2022 | 1511.98 | 41.57 | 1553.55 | Barasat Division | Eastern Mechanical Division | 0 | 0 | 70.29 | 0 | 70.29 | 0 | 0 | 70.29 | 0 | 70.29 | 4.52 | 0
86 | NORTH 24 PARAGANAS | SM/11707 | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011253 | 40026488 | Augmentation | SVS | GO2223005728PH | 29/07/2022 | 569.2 | 44.76 | 613.96 | Barasat Arsenic Division | Eastern Mechanical Division | 268.54 | 0 | 0 | 0 | 268.54 | 268.54 | 0 | 0 | 0 | 268.54 | 43.74 | 54
87 | NORTH 24 PARAGANAS | SM/11629 | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | TSM/011078 | 40034961 | Augmentation | MVS | GO2223005586PH | 26/07/2022 | 657.3 | 40.41 | 697.7 | Barasat Division | Eastern Mechanical Division | 306.28 | 0 | 57.91 | 0 | 364.2 | 257.81 | 0 | 57.91 | 0 | 315.73 | 45.25 | 41
88 | NORTH 24 PARAGANAS | SM/10392 | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | TSM/009735 | 40007158 | Augmentation | SVS | GO2122011266PH | 24/03/2022 | 858.9 | 40.41 | 899.31 | Barasat Division | Eastern Mechanical Division | 355.57 | 17.25 | 10.3 | 0 | 383.12 | 355.57 | 17.25 | 10.3 | 0 | 383.12 | 42.6 | 95
89 | NORTH 24 PARAGANAS | SM/11541 | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | TSM/011028 | 40022713 | Augmentation | MVS | GO2223005238PH | 19/07/2022 | 227.97 | 20.2 | 248.17 | Barasat Division | Eastern Mechanical Division | 55.84 | 0 | 0 | 0 | 55.84 | 55.84 | 0 | 0 | 0 | 55.84 | 22.5 | 23
90 | NORTH 24 PARAGANAS | SM/11761 | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC | TSM/011197 | 40033222 | Augmentation | MVS | GO2223005910PH | 02/08/2022 | 665.63 | 39.58 | 705.21 | Barasat Division | Eastern Mechanical Division | 321.09 | 0 | 13.82 | 0 | 334.91 | 241.39 | 0 | 13.82 | 0 | 255.21 | 36.19 | 23
91 | NORTH 24 PARAGANAS | SM/11762 | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC | TSM/011198 | 40022724 | Augmentation | MVS | GO2223005911PH | 02/08/2022 | 806.38 | 39.58 | 845.97 | Barasat Division | Eastern Mechanical Division | 172.43 | 9.05 | 123.44 | 0 | 304.92 | 157.21 | 9.05 | 123.44 | 0 | 289.7 | 34.24 | 50
92 | NORTH 24 PARAGANAS | SM/10519 | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | TSM/010005 | 40026956 | Augmentation | MVS | GO2223000250PH | 13/04/2022 | 776.76 | 50.61 | 827.36 | Barasat Division | Eastern Mechanical Division | 430.25 | 0 | 179.95 | 0 | 610.2 | 430.25 | 0 | 179.95 | 0 | 610.2 | 73.75 | 80
93 | NORTH 24 PARAGANAS | SM/10309 | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC | TSM/009254 | 40005273 | Augmentation | MVS | GO2122010479PH | 04/03/2022 | 531.01 | 34.57 | 565.58 | Barasat Division | Eastern Mechanical Division | 307.97 | 22.57 | 118.73 | 0 | 449.28 | 307.97 | 22.57 | 118.73 | 0 | 449.28 | 79.44 | 93
94 | NORTH 24 PARAGANAS | SM/11540 | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | TSM/010862 | 40036002 | Augmentation | MVS | GO2223005249PH | 19/07/2022 | 916.88 | 39.58 | 956.46 | Barasat Division | Eastern Mechanical Division | 443.23 | 0 | 98.69 | 0 | 541.92 | 443.23 | 0 | 98.69 | 0 | 541.92 | 56.66 | 100
95 | NORTH 24 PARAGANAS | SM/11666 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC | TSM/011105 | 40022717 | Augmentation | MVS | GO2223005646PH | 27/07/2022 | 950.53 | 39.58 | 990.11 | Barasat Division | Eastern Mechanical Division | 381.96 | 0 | 75.92 | 0 | 457.88 | 381.96 | 0 | 75.92 | 0 | 457.88 | 46.25 | 52
96 | NORTH 24 PARAGANAS | SM/11627 | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | TSM/011073 | 40034944 | Augmentation | MVS | GO2223005583PH | 26/07/2022 | 399.09 | 40.41 | 439.49 | Barasat Division | Eastern Mechanical Division | 179.93 | 0 | 55.83 | 0 | 235.75 | 179.93 | 0 | 55.83 | 0 | 235.75 | 53.64 | 51
97 | NORTH 24 PARAGANAS | SM/11599 | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | TSM/010856 | 40036148 | Augmentation | MVS | GO2223005357PH | 22/07/2022 | 591.55 | 39.58 | 631.14 | Barasat Division | Eastern Mechanical Division | 489.35 | 0 | 0 | 0 | 489.35 | 489.35 | 0 | 0 | 0 | 489.35 | 77.53 | 75
98 | NORTH 24 PARAGANAS | SM/11532 | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | TSM/011083 | 40022746 | Augmentation | MVS | GO2223005248PH | 20/07/2022 | 714.46 | 40.41 | 754.87 | Barasat Division | Eastern Mechanical Division | 361.35 | 17.24 | 53.92 | 0 | 432.51 | 361.35 | 17.24 | 53.92 | 0 | 432.51 | 57.3 | 32
99 | NORTH 24 PARAGANAS | SM/11764 | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC | TSM/011388 | 40028582 | Augmentation | MVS | GO2223005905PH | 02/08/2022 | 921.22 | 62.36 | 983.58 | Barasat Division | Eastern Mechanical Division | 70.39 | 0 | 189.08 | 0 | 259.46 | 70.39 | 0 | 189.08 | 0 | 259.46 | 26.38 | 42
100 | NORTH 24 PARAGANAS | SM/13405 | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC | TSM/011319 | 40029316 | Augmentation | MVS | GO2223009058PH | 21/10/2022 | 2930.79 | 83.14 | 3013.93 | Barasat Division | Eastern Mechanical Division | 475.65 | 0 | 345.44 | 14.82 | 835.91 | 475.65 | 0 | 345.44 | 0 | 821.09 | 27.24 | 17
101 | NORTH 24 PARAGANAS | SM/11604 | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | TSM/011023 | 40029311 | Augmentation | MVS | GO2223005415PH | 22/07/2022 | 666.24 | 40.41 | 706.65 | Barasat Division | Eastern Mechanical Division | 337.03 | 0 | 16.02 | 0 | 353.05 | 337.03 | 0 | 16.02 | 0 | 353.05 | 49.96 | 11
102 | NORTH 24 PARAGANAS | SM/11759 | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | TSM/011374 | 40022566 | Augmentation | MVS | GO2223005909PH | 02/08/2022 | 764.71 | 41.57 | 806.28 | Barasat Division | Eastern Mechanical Division | 364.84 | 15.3 | 34.72 | 0 | 414.86 | 364.84 | 15.3 | 34.72 | 0 | 414.86 | 51.45 | 6
103 | NORTH 24 PARAGANAS | SM/11633 | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | TSM/011030 | 40036123 | Augmentation | MVS | GO2223005577PH | 26/07/2022 | 986.68 | 40.41 | 1027.09 | Barasat Division | Eastern Mechanical Division | 295.79 | 21.11 | 137.38 | 0 | 454.28 | 295.79 | 21.11 | 137.38 | 0 | 454.28 | 44.23 | 13
104 | NORTH 24 PARAGANAS | SM/11601 | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | TSM/010858 | 40046293 | Augmentation | MVS | GO2223005399PH | 22/07/2022 | 492.1 | 39.58 | 531.68 | Barasat Division | Eastern Mechanical Division | 86.29 | 0 | 11.16 | 0 | 97.44 | 86.29 | 0 | 11.16 | 0 | 97.44 | 18.33 | 19
105 | NORTH 24 PARAGANAS | SM/12124 | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC | TSM/010922 | 40036198 | Augmentation | MVS | GO2223007044PH | 06/09/2022 | 1155.59 | 83.14 | 1238.73 | Barasat Division | Eastern Mechanical Division | 288.14 | 10.61 | 115.5 | 0 | 414.25 | 288.14 | 10.61 | 115.5 | 0 | 414.25 | 33.44 | 10
106 | NORTH 24 PARAGANAS | SM/12127 | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC | TSM/010863 | 40036111 | Augmentation | MVS | GO2223007071PH | 06/09/2022 | 1478.9 | 68.11 | 1547.01 | Barasat Division | Eastern Mechanical Division | 678.51 | 0 | 83 | 0 | 761.5 | 678.51 | 0 | 83 | 0 | 761.5 | 49.22 | 49
107 | NORTH 24 PARAGANAS | SM/10565 | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | TSM/010453 | 40046500 | Augmentation | MVS | GO2223000365PH | 18/04/2022 | 741.35 | 35.56 | 776.91 | Barasat Division | Eastern Mechanical Division | 503.09 | 0 | 10.74 | 0 | 513.83 | 503.09 | 0 | 10.74 | 0 | 513.83 | 66.14 | 69
108 | NORTH 24 PARAGANAS | SM/10101 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | TSM/009520 | 40002854 | Augmentation | MVS | GO2122009121PH | 02/02/2022 | 592.32 | 0 | 592.32 | North 24 Pgs W/S Division I |  | 376.2 | 0 | 37.47 | 0 | 413.66 | 349.64 | 0 | 37.47 | 0 | 387.1 | 65.35 | 78
109 | NORTH 24 PARAGANAS | SM/11626 | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | TSM/011033 | 40036027 | Augmentation | MVS | GO2223005558PH | 26/07/2022 | 1167.21 | 40.41 | 1207.61 | Barasat Division | Eastern Mechanical Division | 182.01 | 17.71 | 38.23 | 0 | 237.94 | 182.01 | 17.71 | 38.23 | 0 | 237.94 | 19.7 | 11
110 | NORTH 24 PARAGANAS | SM/11585 | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | TSM/011065 | 40060403 | Augmentation | SVS | GO2223005369PH | 22/07/2022 | 762 | 40.41 | 802.4 | Barasat Division | Eastern Mechanical Division | 438.38 | 0 | 28.3 | 0 | 466.68 | 438.38 | 0 | 28.3 | 0 | 466.68 | 58.16 | 49
111 | NORTH 24 PARAGANAS | SM/10529 | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | TSM/009758 | 40030032 | Augmentation | SVS | GO2223000256PH | 13/04/2022 | 404.89 | 33.75 | 438.64 | Barasat Division | Eastern Mechanical Division | 206.52 | 0 | 15.2 | 0 | 221.72 | 206.52 | 0 | 15.2 | 0 | 221.72 | 50.55 | 68
112 | NORTH 24 PARAGANAS | SM/11663 | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010997 | 40026492 | Augmentation | MVS | GO2223005686PH | 28/07/2022 | 440.66 | 21.28 | 461.93 | Barasat Arsenic Division | Eastern Mechanical Division | 212.89 | 2.83 | 0 | 0 | 215.71 | 201.14 | 2.83 | 0 | 0 | 203.97 | 44.16 | 52
113 | NORTH 24 PARAGANAS | SM/11708 | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010998 | 40026460 | Augmentation | MVS | GO2223005725PH | 29/07/2022 | 556.66 | 36.42 | 593.08 | Barasat Arsenic Division | Eastern Mechanical Division | 306.89 | 3.86 | 0 | 0 | 310.75 | 306.89 | 3.86 | 0 | 0 | 310.75 | 52.4 | 50
114 | NORTH 24 PARAGANAS | SM/11662 | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011234 | 40026333 | Augmentation | SVS | GO2223005690PH | 28/07/2022 | 526.81 | 20.84 | 547.66 | Barasat Arsenic Division | Eastern Mechanical Division | 265 | 3 | 0 | 0 | 268 | 265 | 3 | 0 | 0 | 268 | 48.94 | 61
115 | NORTH 24 PARAGANAS | SM/11529 | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | TSM/011074 | 40060508 | Augmentation | SVS | GO2223005232PH | 19/07/2022 | 150.03 | 40.41 | 190.44 | Barasat Division | Eastern Mechanical Division | 57.09 | 10.07 | 0 | 0 | 67.16 | 57.09 | 10.07 | 0 | 0 | 67.16 | 35.27 | 47
116 | NORTH 24 PARAGANAS | SM/11591 | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | TSM/011082 | 40036137 | Augmentation | MVS | GO2223005412PH | 22/07/2022 | 753.09 | 40.41 | 793.5 | Barasat Division | Eastern Mechanical Division | 390.22 | 0 | 104.84 | 0 | 495.05 | 390.22 | 0 | 104.84 | 0 | 495.05 | 62.39 | 74
117 | NORTH 24 PARAGANAS | SM/14153 | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas | TSM/012030 | 40033250 | Augmentation | MVS | GO2223011608PH | 05/01/2023 | 2236.09 | 166.28 | 2402.37 | Barasat Division | Eastern Mechanical Division | 1441.58 | 0 | 141.46 | 0 | 1583.04 | 1441.58 | 0 | 141.46 | 0 | 1583.04 | 65.89 | 27
118 | NORTH 24 PARAGANAS | SM/11631 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | TSM/011108 | 40023337 | Augmentation | MVS | GO2223005559PH | 26/07/2022 | 1131.12 | 33.75 | 1164.88 | Barasat Division | Eastern Mechanical Division | 436.34 | 0 | 132.49 | 0 | 568.83 | 436.34 | 0 | 132.49 | 0 | 568.83 | 48.83 | 59
119 | NORTH 24 PARAGANAS | SM/10727 | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | TSM/009764 | 40018992 | Augmentation | MVS | GO2223002005PH | 18/05/2022 | 351.87 | 33.75 | 385.63 | Barasat Division | Eastern Mechanical Division | 225.85 | 0 | 1.26 | 0 | 227.11 | 225.85 | 0 | 1.26 | 0 | 227.11 | 58.89 | 55
120 | NORTH 24 PARAGANAS | SM/11602 | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | TSM/010859 | 40046492 | Augmentation | MVS | GO2223005424PH | 22/07/2022 | 468.82 | 39.58 | 508.4 | Barasat Division | Eastern Mechanical Division | 146.86 | 3.9 | 14.27 | 0 | 165.03 | 146.86 | 3.9 | 14.27 | 0 | 165.03 | 32.46 | 99
121 | NORTH 24 PARAGANAS | SM/12125 | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC | TSM/011158 | 40036200 | Augmentation | MVS | GO2223007046PH | 06/09/2022 | 1122.3 | 45.99 | 1168.29 | Barasat Division | Eastern Mechanical Division | 519.97 | 15.74 | 0 | 0 | 535.71 | 519.97 | 15.74 | 0 | 0 | 535.71 | 45.85 | 99
122 | NORTH 24 PARAGANAS | SM/11657 | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC | TSM/011160 | 40034988 | Augmentation | MVS | GO2223005644PH | 27/07/2022 | 955.77 | 43.65 | 999.42 | Barasat Division | Eastern Mechanical Division | 456.38 | 24.6 | 18.98 | 0 | 499.96 | 455.63 | 24.6 | 18.98 | 0 | 499.2 | 49.95 | 38
123 | NORTH 24 PARAGANAS | SM/11600 | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | TSM/010857 | 40029478 | Augmentation | MVS | GO2223005368PH | 22/07/2022 | 783.07 | 39.58 | 822.65 | Barasat Division | Eastern Mechanical Division | 350.56 | 20.33 | 30.2 | 0 | 401.08 | 350.56 | 0 | 30.2 | 0 | 380.75 | 46.28 | 50
124 | NORTH 24 PARAGANAS | SM/10530 | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | TSM/009763 | 40026968 | Augmentation | MVS | GO2223000290PH | 13/04/2022 | 614.96 | 33.75 | 648.71 | Barasat Division | Eastern Mechanical Division | 288.55 | 0 | 88.98 | 0 | 377.53 | 288.55 | 0 | 88.98 | 0 | 377.53 | 58.2 | 73
125 | NORTH 24 PARAGANAS | SM/11763 | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC | TSM/011373 | 40022559 | Augmentation | MVS | GO2223005984PH | 03/08/2022 | 450.66 | 41.57 | 492.23 | Barasat Division | Eastern Mechanical Division | 209.33 | 0 | 0 | 0 | 209.33 | 209.33 | 0 | 0 | 0 | 209.33 | 42.53 | 32
126 | NORTH 24 PARAGANAS | SM/10570 | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | TSM/010448 | 40019753 | Augmentation | MVS | GO2223000359PH | 18/04/2022 | 586.33 | 41.7 | 628.03 | Barasat Division | Eastern Mechanical Division | 347.44 | 0 | 13.42 | 0 | 360.86 | 347.44 | 0 | 13.42 | 0 | 360.86 | 57.46 | 90
127 | NORTH 24 PARAGANAS | SM/12735 | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. | TSM/011193 | 40036208 | Augmentation | MVS | GO2223008041PH | 21/09/2022 | 1442.03 | 59.35 | 1501.39 | Barasat Division | Eastern Mechanical Division | 547.48 | 53.68 | 93.9 | 0 | 695.07 | 545.86 | 62.23 | 93.9 | 0 | 702 | 46.76 | 38
128 | NORTH 24 PARAGANAS | SM/11699 | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC | TSM/011177 | 40031711 | Augmentation | SVS | GO2223005724PH | 29/07/2022 | 712.51 | 62.36 | 774.86 | Barasat Division | Eastern Mechanical Division | 443.7 | 51.11 | 57.53 | 0 | 552.34 | 441.82 | 42.55 | 57.53 | 0 | 541.9 | 69.94 | 72
129 | NORTH 24 PARAGANAS | SM/11538 | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | TSM/010860 | 40022744 | Augmentation | MVS | GO2223005251PH | 19/07/2022 | 722.37 | 39.58 | 761.95 | Barasat Division | Eastern Mechanical Division | 380.08 | 0 | 34.54 | 0 | 414.62 | 348.8 | 0 | 34.54 | 0 | 383.34 | 50.31 | 52
130 | NORTH 24 PARAGANAS | SM/11661 | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte | TSM/011147 | 40026325 | Augmentation | MVS | GO2223005687PH | 28/07/2022 | 452.23 | 34.75 | 486.98 | Barasat Arsenic Division | Eastern Mechanical Division | 57.93 | 0 | 6.92 | 0 | 64.86 | 57.93 | 0 | 6.92 | 0 | 64.86 | 13.32 | 23
131 | NORTH 24 PARAGANAS | SM/10376 | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | TSM/009732 | 40007165 | Augmentation | SVS | GO2122010916PH | 16/03/2022 | 628.64 | 42.43 | 671.07 | Barasat Division | Eastern Mechanical Division | 423.77 | 20.19 | 7.56 | 0 | 451.52 | 423.77 | 19.64 | 7.56 | 0 | 450.97 | 67.2 | 45
132 | NORTH 24 PARAGANAS | SM/10308 | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon | TSM/009318 | 40005456 | Augmentation | MVS | GO2122010478PH | 04/03/2022 | 626.3 | 34.57 | 660.87 | Barasat Division | Eastern Mechanical Division | 285.65 | 0 | 34.52 | 0 | 320.17 | 285.65 | 0 | 34.52 | 0 | 320.17 | 48.45 | 95
133 | NORTH 24 PARAGANAS | SM/11706 | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010982 | 40026491 | Augmentation | MVS | GO2223005726PH | 29/07/2022 | 307.2 | 21.28 | 328.48 | Barasat Arsenic Division | Eastern Mechanical Division | 93.05 | 0 | 0 | 0 | 93.05 | 93.05 | 0 | 0 | 0 | 93.05 | 28.33 | 37
134 | NORTH 24 PARAGANAS | SM/11755 | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC | TSM/011309 | 40033099 | Augmentation | SVS | GO2223005907PH | 02/08/2022 | 258.46 | 20.79 | 279.25 | Barasat Division | Eastern Mechanical Division | 72.44 | 0 | 0 | 0 | 72.44 | 72.44 | 0 | 0 | 0 | 72.44 | 25.94 | 23
135 | NORTH 24 PARAGANAS | SM/10302 | Augmentation of Ground water based piped water supply scheme for Kumarjole | TSM/009738 | 40005461 | Augmentation | MVS | GO2122010328PH | 02/03/2022 | 1012.73 | 39.57 | 1052.3 | Barasat Division | Eastern Mechanical Division | 415.25 | 19.26 | 0 | 0 | 434.51 | 414.45 | 19.26 | 0 | 0 | 433.71 | 41.22 | 99
136 | NORTH 24 PARAGANAS | SM/10298 | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah | TSM/009320 | 40014573 | Augmentation | MVS | GO2122010324PH | 02/03/2022 | 691.75 | 32.61 | 724.36 | Barasat Division | Eastern Mechanical Division | 340.39 | 23.54 | 11.88 | 0 | 375.8 | 254.28 | 23.54 | 11.88 | 0 | 289.7 | 39.99 | 66
137 | NORTH 24 PARAGANAS | SM/10301 | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC | TSM/009252 | 40013189 | Augmentation | MVS | GO2122010327PH | 02/03/2022 | 559.12 | 33.77 | 592.89 | Barasat Division | Eastern Mechanical Division | 376.04 | 1.34 | 31.06 | 0 | 408.43 | 376.04 | 1.34 | 31.06 | 0 | 408.43 | 68.89 | 100
138 | NORTH 24 PARAGANAS | SM/11655 | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | TSM/011314 | 40029239 | Augmentation | MVS | GO2223005643PH | 27/07/2022 | 1111.98 | 41.57 | 1153.55 | Barasat Division | Eastern Mechanical Division | 396.63 | 0 | 64.81 | 0 | 461.43 | 396.63 | 0 | 64.81 | 0 | 461.43 | 40 | 47
139 | NORTH 24 PARAGANAS | SM/11596 | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | TSM/011213 | 40036142 | Augmentation | MVS | GO2223005371PH | 22/07/2022 | 1025.28 | 71.09 | 1096.37 | Barasat Division | Eastern Mechanical Division | 556.94 | 34.24 | 11.15 | 0 | 602.33 | 555.04 | 34.24 | 11.15 | 0 | 600.43 | 54.77 | 40
140 | NORTH 24 PARAGANAS | SM/10574 | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | TSM/010446 | 40019523 | Augmentation | MVS | GO2223000351PH | 18/04/2022 | 976.82 | 43.8 | 1020.62 | Barasat Division | Eastern Mechanical Division | 418.08 | 0 | 13.63 | 0 | 431.7 | 418.08 | 0 | 13.63 | 0 | 431.7 | 42.3 | 95
141 | NORTH 24 PARAGANAS | SM/11539 | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | TSM/010861 | 40022742 | Augmentation | MVS | GO2223005252PH | 19/07/2022 | 412.68 | 39.58 | 452.26 | Barasat Division | Eastern Mechanical Division | 229.42 | 20 | 13.47 | 0 | 262.89 | 229.42 | 20 | 13.47 | 0 | 262.89 | 58.13 | 72
142 | NORTH 24 PARAGANAS | SM/11665 | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC | TSM/011081 | 40022557 | Augmentation | MVS | GO2223005640PH | 27/07/2022 | 408.92 | 40.41 | 449.33 | Barasat Division | Eastern Mechanical Division | 158.25 | 0 | 11.09 | 0 | 169.34 | 158.25 | 0 | 11.09 | 0 | 169.34 | 37.69 | 25
143 | NORTH 24 PARAGANAS | SM/11654 | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | TSM/011313 | 40029522 | Augmentation | MVS | GO2223005647PH | 27/07/2022 | 362.12 | 41.57 | 403.69 | Barasat Division | Eastern Mechanical Division | 126.32 | 0 | 24.24 | 0 | 150.56 | 126.32 | 0 | 24.24 | 0 | 150.56 | 37.3 | 45
144 | NORTH 24 PARAGANAS | SM/10531 | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | TSM/009760 | 40032583 | Augmentation | MVS | GO2223000259PH | 13/04/2022 | 773.72 | 47.72 | 821.44 | Barasat Division | Eastern Mechanical Division | 509.34 | 0 | 24.99 | 0 | 534.34 | 509.34 | 0 | 24.99 | 0 | 534.34 | 65.05 | 61
145 | NORTH 24 PARAGANAS | SM/10533 | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | TSM/009761 | 40019376 | Augmentation | MVS | GO2223000257PH | 13/04/2022 | 804.64 | 47.72 | 852.36 | Barasat Division | Eastern Mechanical Division | 414.09 | 19.89 | 26.56 | 0 | 460.55 | 414.09 | 19.89 | 26.56 | 0 | 460.55 | 54.03 | 93
146 | NORTH 24 PARAGANAS | SM/11530 | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | TSM/011075 | 40036103 | Augmentation | MVS | GO2223005250PH | 19/07/2022 | 552.53 | 40.41 | 592.93 | Barasat Division | Eastern Mechanical Division | 285.78 | 23.36 | 38.72 | 0 | 347.87 | 285.78 | 23.36 | 38.72 | 0 | 347.87 | 58.67 | 45
147 | NORTH 24 PARAGANAS | SM/11667 | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | TSM/011164 | 40022581 | Augmentation | MVS | GO2223005642PH | 27/07/2022 | 468.77 | 39.58 | 508.35 | Barasat Division | Eastern Mechanical Division | 136.18 | 3.94 | 6.13 | 0 | 146.25 | 104.02 | 3.94 | 6.13 | 0 | 114.09 | 22.44 | 19
148 | NORTH 24 PARAGANAS | SM/11702 | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC | TSM/011080 | 40035037 | Augmentation | MVS | GO2223005731PH | 29/07/2022 | 511.05 | 40.41 | 551.46 | Barasat Division | Eastern Mechanical Division | 233.88 | 0 | 53.89 | 0 | 287.77 | 233.88 | 0 | 53.89 | 0 | 287.77 | 52.18 | 46
149 | NORTH 24 PARAGANAS | SM/14151 | Augmentation of ground water based piped water supply scheme for Mohanpur | TSM/012029 | 40033556 | Augmentation | SVS | GO2223011609PH | 05/01/2023 | 1232.67 | 100.62 | 1333.28 | Barasat Division | Eastern Mechanical Division | 626.54 | 5.03 | 0 | 0 | 631.58 | 626.54 | 5.03 | 0 | 0 | 631.58 | 47.37 | 54
150 | NORTH 24 PARAGANAS | SM/11632 | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | TSM/011192 | 40027749 | Augmentation | SVS | GO2223005556PH | 26/07/2022 | 691.01 | 67.32 | 758.33 | Barasat Division | Eastern Mechanical Division | 388.31 | 0 | 4.45 | 0 | 392.77 | 388.31 | 0 | 4.45 | 0 | 392.77 | 51.79 | 72
151 | NORTH 24 PARAGANAS | SM/10555 | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | TSM/010454 | 40036596 | Augmentation | MVS | GO2223000338PH | 18/04/2022 | 909.27 | 87.83 | 997.1 | Barasat Division | Eastern Mechanical Division | 517.43 | 0 | 26.17 | 0 | 543.59 | 514.64 | 0 | 26.17 | 0 | 540.8 | 54.24 | 27
152 | NORTH 24 PARAGANAS | SM/11760 | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC | TSM/011379 | 40022579 | Augmentation | MVS | GO2223005906PH | 02/08/2022 | 437.51 | 41.57 | 479.08 | Barasat Division | Eastern Mechanical Division | 249.22 | 0 | 0 | 0 | 249.22 | 249.22 | 0 | 0 | 0 | 249.22 | 52.02 | 34
153 | NORTH 24 PARAGANAS | SM/12377 | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC | TSM/011383 | 40022580 | Augmentation | MVS | GO2223007583PH | 13/09/2022 | 2182.78 | 83.14 | 2265.92 | Barasat Division | Eastern Mechanical Division | 910.88 | 16.96 | 338.41 | 0 | 1266.25 | 927.24 | 16.96 | 338.41 | 0 | 1282.62 | 56.6 | 33
154 | NORTH 24 PARAGANAS | SM/11524 | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | TSM/011059 | 40023625 | Augmentation | SVS | GO2223005228PH | 19/07/2022 | 246.47 | 20.2 | 266.67 | Barasat Division | Eastern Mechanical Division | 71.13 | 0 | 23.93 | 0 | 95.06 | 71.13 | 0 | 23.93 | 0 | 95.06 | 35.65 | 28
155 | NORTH 24 PARAGANAS | SM/11974 | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC | TSM/011372 | 40022553 | Augmentation | MVS | GO2223006801PH | 29/08/2022 | 542.28 | 41.57 | 583.85 | Barasat Division | Eastern Mechanical Division | 226.82 | 0 | 62.48 | 0 | 289.3 | 226.82 | 0 | 62.48 | 0 | 289.3 | 49.55 | 24
156 | NORTH 24 PARAGANAS | SM/11595 | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | TSM/011203 | 40018886 | Augmentation | MVS | GO2223005426PH | 22/07/2022 | 496.05 | 41.57 | 537.62 | Barasat Division | Eastern Mechanical Division | 228.9 | 14.37 | 0 | 0 | 243.27 | 228.9 | 14.37 | 0 | 0 | 243.27 | 45.25 | 61
157 | NORTH 24 PARAGANAS | SM/13314 | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC | TSM/011170 | 40036210 | Augmentation | MVS | GO2223008872PH | 17/10/2022 | 1613.56 | 88.57 | 1702.13 | Barasat Division | Eastern Mechanical Division | 818.13 | 12.13 | 170.43 | 0 | 1000.68 | 818.13 | 12.13 | 170.43 | 0 | 1000.68 | 58.79 | 99
158 | NORTH 24 PARAGANAS | SM/12273 | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC | TSM/011034 | 40028586 | Augmentation | MVS | GO2223007386PH | 09/09/2022 | 1620.66 | 62.36 | 1683.01 | Barasat Division | Eastern Mechanical Division | 267.41 | 0 | 60.08 | 0 | 327.49 | 267.41 | 0 | 60.08 | 0 | 327.49 | 19.46 | 18
159 | NORTH 24 PARAGANAS | SM/10300 | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC | TSM/009255 | 40005470 | Augmentation | MVS | GO2122010326PH | 02/03/2022 | 664.92 | 34.57 | 699.49 | Barasat Division | Eastern Mechanical Division | 409.55 | 22.28 | 24.82 | 0 | 456.65 | 409.55 | 22.28 | 24.82 | 0 | 456.65 | 65.28 | 72
160 | NORTH 24 PARAGANAS | SM/13350 | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC | TSM/011380 | 40030470 | Augmentation | MVS | GO2223008973PH | 19/10/2022 | 1349.73 | 62.36 | 1412.09 | Barasat Division | Eastern Mechanical Division | 396.91 | 3.51 | 134.36 | 0 | 534.78 | 396.91 | 3.51 | 131.03 | 0 | 531.45 | 37.64 | 6
161 | NORTH 24 PARAGANAS | SM/11606 | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | TSM/011027 | 40022715 | Augmentation | MVS | GO2223005421PH | 22/07/2022 | 822.62 | 62.36 | 884.98 | Barasat Division | Eastern Mechanical Division | 418.17 | 0 | 46.26 | 0 | 464.43 | 418.17 | 0 | 46.26 | 0 | 464.43 | 52.48 | 48
162 | NORTH 24 PARAGANAS | SM/10104 | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | TSM/009270 | 40002892 | Augmentation | MVS | GO2122009119PH | 02/02/2022 | 630.72 | 0 | 630.72 | North 24 Pgs W/S Division I |  | 358.18 | 0 | 11.02 | 0 | 369.2 | 358.18 | 0 | 11.02 | 0 | 369.2 | 58.54 | 84
163 | NORTH 24 PARAGANAS | SM/11656 | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | TSM/011371 | 40022574 | Augmentation | MVS | GO2223005639PH | 27/07/2022 | 676.99 | 41.57 | 718.56 | Barasat Division | Eastern Mechanical Division | 121.42 | 0 | 51.99 | 0 | 173.4 | 4.16 | 0 | 51.99 | 0 | 56.15 | 7.81 | 42
164 | NORTH 24 PARAGANAS | SM/10100 | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | TSM/009519 | 40002672 | Augmentation | MVS | GO2122009053PH | 02/02/2022 | 1063.69 | 0 | 1063.69 | North 24 Pgs W/S Division I |  | 618.49 | 0 | 127.76 | 0 | 746.26 | 617.97 | 0 | 127.76 | 0 | 745.73 | 70.11 | 55
165 | NORTH 24 PARAGANAS | SM/11635 | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | TSM/011025 | 40036129 | Augmentation | MVS | GO2223005580PH | 26/07/2022 | 562.37 | 60.61 | 622.98 | Barasat Division | Eastern Mechanical Division | 243.45 | 11.8 | 58.04 | 0 | 313.29 | 243.45 | 11.8 | 58.04 | 0 | 313.29 | 50.29 | 26
166 | NORTH 24 PARAGANAS | SM/11628 | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | TSM/011076 | 40036115 | Augmentation | MVS | GO2223005562PH | 26/07/2022 | 324.65 | 40.41 | 365.06 | Barasat Division | Eastern Mechanical Division | 155.48 | 22.74 | 10.15 | 0 | 188.37 | 155.48 | 22.74 | 10.15 | 0 | 188.37 | 51.6 | 51
167 | NORTH 24 PARAGANAS | SM/11531 | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | TSM/011077 | 40036104 | Augmentation | MVS | GO2223005237PH | 19/07/2022 | 314.61 | 40.41 | 355.01 | Barasat Division | Eastern Mechanical Division | 139.49 | 22.8 | 27.48 | 0 | 189.76 | 139.49 | 22.8 | 27.48 | 0 | 189.76 | 53.45 | 32
168 | NORTH 24 PARAGANAS | SM/17408 | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | TSM/011322 | 40036883 | Augmentation | MVS | GO2223016354PH | 15/03/2023 | 608.22 | 41.57 | 649.79 | Barasat Division | Eastern Mechanical Division | 270.56 | 0 | 0 | 0 | 270.56 | 270.56 | 0 | 0 | 0 | 270.56 | 41.64 | 44
169 | NORTH 24 PARAGANAS | SM/13761 | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/011116 | 40037205 | Augmentation | MVS | GO2223009893PH | 18/11/2022 | 332.1 | 21.28 | 353.38 | Barasat Arsenic Division | Eastern Mechanical Division | 168.39 | 0 | 1.72 | 0 | 170.11 | 168.39 | 0 | 1.72 | 0 | 170.11 | 48.14 | 26
170 | NORTH 24 PARAGANAS | SM/11526 | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | TSM/011068 | 40031739 | Augmentation | SVS | GO2223005226PH | 19/07/2022 | 650.62 | 40.41 | 691.03 | Barasat Division | Eastern Mechanical Division | 293.36 | 16.66 | 45.74 | 0 | 355.76 | 293.36 | 16.66 | 45.74 | 0 | 355.76 | 51.48 | 50
171 | NORTH 24 PARAGANAS | SM/11630 | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | TSM/011079 | 40023371 | Augmentation | SVS | GO2223005578PH | 26/07/2022 | 178.08 | 20.2 | 198.28 | Barasat Division | Eastern Mechanical Division | 65.03 | 0 | 0 | 0 | 65.03 | 65.03 | 0 | 0 | 0 | 65.03 | 32.8 | 32
172 | NORTH 24 PARAGANAS | SM/11603 | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | TSM/010864 | 40030448 | Augmentation | SVS | GO2223005372PH | 22/07/2022 | 362.56 | 39.58 | 402.14 | Barasat Division | Eastern Mechanical Division | 227.97 | 0 | 20.67 | 0 | 248.64 | 227.97 | 0 | 20.67 | 0 | 248.64 | 61.83 | 100
173 | NORTH 24 PARAGANAS | SM/12122 | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. | TSM/011175 | 40036131 | Augmentation | MVS | GO2223007090PH | 06/09/2022 | 1372.36 | 131.39 | 1503.75 | Barasat Division | Eastern Mechanical Division | 879.86 | 29.75 | 91.24 | 0 | 1000.86 | 876.24 | 29.75 | 91.24 | 0 | 997.24 | 66.32 | 62
174 | NORTH 24 PARAGANAS | SM/11525 | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | TSM/011067 | 40022748 | Augmentation | MVS | GO2223005225PH | 19/07/2022 | 774.99 | 40.41 | 815.39 | Barasat Division | Eastern Mechanical Division | 399.16 | 23.03 | 34.2 | 0 | 456.39 | 399.16 | 23.03 | 34.2 | 0 | 456.39 | 55.97 | 42
175 | NORTH 24 PARAGANAS | SM/11523 | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | TSM/011066 | 40060411 | Augmentation | MVS | GO2223005227PH | 19/07/2022 | 466.58 | 40.41 | 506.98 | Barasat Division | Eastern Mechanical Division | 131.82 | 22.76 | 10.13 | 0 | 164.72 | 131.82 | 22.76 | 10.13 | 0 | 164.72 | 32.49 | 31
176 | NORTH 24 PARAGANAS | SM/10577 | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | TSM/009759 | 40028458 | Augmentation | SVS | GO2223000347PH | 18/04/2022 | 157.06 | 19.79 | 176.85 | Barasat Division | Eastern Mechanical Division | 31.64 | 0 | 2.11 | 0 | 33.74 | 31.64 | 0 | 2.11 | 0 | 33.74 | 19.08 | 28
177 | NORTH 24 PARAGANAS | SM/12278 | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC | TSM/010949 | 40035651 | Augmentation | MVS | GO2223007390PH | 09/09/2022 | 1862.55 | 140.12 | 2002.67 | Barasat Division | Eastern Mechanical Division | 817.56 | 0 | 62.15 | 0 | 879.72 | 817.56 | 0 | 62.15 | 0 | 879.72 | 43.93 | 41
178 | NORTH 24 PARAGANAS | SM/14152 | Augmentation of ground water based piped water supply scheme for Sandeshkhali | TSM/012006 | 40060626 | Augmentation | SVS | GO2223011610PH | 05/01/2023 | 1102.38 | 37.48 | 1139.85 | Barasat Division | Eastern Mechanical Division | 118.2 | 0 | 10.35 | 0 | 128.55 | 118.2 | 0 | 10.35 | 0 | 128.55 | 11.28 | 9
179 | NORTH 24 PARAGANAS | SM/11605 | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | TSM/011031 | 40029312 | Augmentation | MVS | GO2223005422PH | 22/07/2022 | 1068.42 | 40.41 | 1108.82 | Barasat Division | Eastern Mechanical Division | 656.78 | 5.64 | 78.81 | 0 | 741.23 | 656.78 | 5.64 | 78.81 | 0 | 741.23 | 66.85 | 66
180 | NORTH 24 PARAGANAS | SM/11653 | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | TSM/011430 | 40033087 | Augmentation | MVS | GO2223005645PH | 27/07/2022 | 893.05 | 62.36 | 955.4 | Barasat Division | Eastern Mechanical Division | 311.93 | 0 | 120.06 | 0 | 431.99 | 311.93 | 0 | 120.06 | 0 | 431.99 | 45.21 | 23
181 | NORTH 24 PARAGANAS | SM/10111 | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | TSM/009219 | 40003520 | Augmentation | MVS | GO2122009116PH | 02/02/2022 | 938.03 | 0 | 938.03 | North 24 Pgs W/S Division I |  | 568.43 | 0 | 130.29 | 0 | 698.72 | 568.43 | 0 | 130.29 | 0 | 698.72 | 74.49 | 88
182 | NORTH 24 PARAGANAS | SM/10110 | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | TSM/009271 | 40002861 | Augmentation | MVS | GO2122009117PH | 02/02/2022 | 673.06 | 0 | 673.06 | North 24 Pgs W/S Division I |  | 475.76 | 0 | 22.37 | 0 | 498.13 | 475.76 | 0 | 22.37 | 0 | 498.13 | 74.01 | 86
183 | NORTH 24 PARAGANAS | SM/11607 | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | TSM/011032 | 40036025 | Augmentation | MVS | GO2223005370PH | 22/07/2022 | 898.11 | 40.41 | 938.51 | Barasat Division | Eastern Mechanical Division | 346.92 | 13.36 | 46.17 | 0 | 406.46 | 346.92 | 13.36 | 46.17 | 0 | 406.46 | 43.31 | 46
184 | NORTH 24 PARAGANAS | SM/13472 | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. | TSM/011976 | 40032923 | Augmentation | MVS | GO2223009255PH | 02/11/2022 | 832.46 | 42.93 | 875.39 | Barasat Division | Eastern Mechanical Division | 160.49 | 0 | 36.84 | 26.06 | 223.39 | 160.49 | 0 | 36.84 | 26.06 | 223.39 | 25.52 | 19
185 | NORTH 24 PARAGANAS | SM/12569 | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | TSM/011321 | 40029298 | Augmentation | MVS | GO2223007700PH | 14/09/2022 | 1435.73 | 62.36 | 1498.08 | Barasat Division | Eastern Mechanical Division | 513.33 | 3.46 | 44.17 | 0 | 560.96 | 513.33 | 3.46 | 44.17 | 0 | 560.96 | 37.45 | 45
186 | NORTH 24 PARAGANAS | SM/11598 | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | TSM/011168 | 40029461 | Augmentation | MVS | GO2223005353PH | 22/07/2022 | 1113.25 | 51.84 | 1165.1 | Barasat Division | Eastern Mechanical Division | 622.12 | 0 | 88.81 | 0 | 710.93 | 622.12 | 0 | 88.81 | 0 | 710.93 | 61.02 | 73
187 | NORTH 24 PARAGANAS | SM/10786 | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | TSM/009319 | 40007129 | Augmentation | MVS | GO2223003490PH | 25/05/2022 | 502.81 | 34.57 | 537.38 | Barasat Division | Eastern Mechanical Division | 351.79 | 0 | 18.5 | 0 | 370.28 | 351.79 | 0 | 18.5 | 0 | 370.28 | 68.91 | 92
188 | NORTH 24 PARAGANAS | SM/10375 | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | TSM/009253 | 40007128 | Augmentation | MVS | GO2122010913PH | 16/03/2022 | 474.91 | 34.57 | 509.48 | Barasat Division | Eastern Mechanical Division | 297.92 | 21.02 | 91.71 | 0 | 410.65 | 297.92 | 21.02 | 91.71 | 0 | 410.65 | 80.6 | 100
189 | NORTH 24 PARAGANAS | SM/11758 | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC | TSM/011385 | 40029479 | Augmentation | MVS | GO2223005908PH | 02/08/2022 | 321.56 | 20.79 | 342.34 | Barasat Division | Eastern Mechanical Division | 130.56 | 3.12 | 6.16 | 0 | 139.85 | 130.56 | 3.12 | 6.16 | 0 | 139.85 | 40.85 | 46
190 | NORTH 24 PARAGANAS | SM/11528 | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | TSM/011070 | 40022708 | Augmentation | MVS | GO2223005231PH | 19/07/2022 | 916.69 | 40.41 | 957.1 | Barasat Division | Eastern Mechanical Division | 294.34 | 7.65 | 86.85 | 0 | 388.85 | 294.34 | 7.65 | 86.85 | 0 | 388.85 | 40.63 | 34
191 | NORTH 24 PARAGANAS | SM/10706 | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | TSM/010459 | 40032574 | Augmentation | MVS | GO2223001541PH | 12/05/2022 | 438.65 | 43.92 | 482.57 | Barasat Division | Eastern Mechanical Division | 240.42 | 0 | 12.62 | 0 | 253.04 | 240.42 | 0 | 12.62 | 0 | 253.04 | 52.44 | 96
192 | NORTH 24 PARAGANAS | SM/10693 | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | TSM/009762 | 40018988 | Augmentation | MVS | GO2223001398PH | 12/05/2022 | 433.63 | 33.75 | 467.39 | Barasat Division | Eastern Mechanical Division | 242.23 | 0 | 0 | 0 | 242.23 | 242.23 | 0 | 0 | 0 | 242.23 | 51.83 | 76
193 | NORTH 24 PARAGANAS | SM/11757 | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC | TSM/011377 | 40022562 | Augmentation | MVS | GO2223005968PH | 03/08/2022 | 545.88 | 20.79 | 566.66 | Barasat Division | Eastern Mechanical Division | 270.35 | 0 | 3.3 | 0 | 273.65 | 270.35 | 0 | 3.3 | 0 | 273.65 | 48.29 | 33
194 | NORTH 24 PARAGANAS | SM/17409 | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | TSM/011381 | 40037048 | Augmentation | MVS | GO2223016353PH | 15/03/2023 | 354.69 | 20.79 | 375.47 | Barasat Division | Eastern Mechanical Division | 192.48 | 0 | 16.09 | 0 | 208.57 | 144.51 | 0 | 16.09 | 0 | 160.6 | 42.77 | 12
195 | NORTH 24 PARAGANAS | SM/11659 | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010996 | 40026444 | Augmentation | MVS | GO2223005689PH | 28/07/2022 | 529.51 | 34.75 | 564.26 | Barasat Arsenic Division | Eastern Mechanical Division | 207.03 | 4.17 | 0 | 0 | 211.2 | 207.03 | 4.17 | 0 | 0 | 211.2 | 37.43 | 34
196 | NORTH 24 PARAGANAS | SM/10549 | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010570 | 40026434 | Augmentation | MVS | GO2223000378PH | 18/04/2022 | 820.44 | 42.57 | 863.01 | Barasat Arsenic Division | Eastern Mechanical Division | 354.42 | 15.44 | 168.38 | 0 | 538.24 | 354.42 | 15.44 | 168.38 | 0 | 538.24 | 62.37 | 87
197 | NORTH 24 PARAGANAS | SM/10551 | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | TSM/010571 | 40035047 | Augmentation | MVS | GO2223000380PH | 18/04/2022 | 934.84 | 42.57 | 977.41 | Barasat Arsenic Division | Eastern Mechanical Division | 333.46 | 0 | 238.35 | 0 | 571.81 | 333.46 | 0 | 238.35 | 0 | 571.81 | 58.5 | 79
198 | NORTH 24 PARAGANAS | SM/18410 | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | TSM/011241 | 40033886 | Augmentation | MVS | 1853/PHE-28011/198/2022-ESTT CELL-Dept. of PHE | 12/07/2023 | 1137.12 | 73.61 | 1210.72 | Barasat Division | Eastern Mechanical Division | 110.2 | 2.2 | 95.29 | 0 | 207.69 | 109.32 | 2.2 | 95.29 | 0 | 206.81 | 17.08 | 25
199 | NORTH 24 PARAGANAS | SM/18712 | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | TSM/011242 | 40033881 | Augmentation | MVS | 2261/PHE/IV/W-516/23 | 04/08/2023 | 981.89 | 73.61 | 1055.5 | Barasat Division | Eastern Mechanical Division | 0.88 | 0 | 62.26 | 0 | 63.14 | 0 | 0 | 11.7 | 0 | 11.7 | 1.11 | 9
200 | NORTH 24 PARAGANAS | SM/14512 | Augmentation of Hingalganj Piped water supply scheme Zone-I | TSM/018807 | 40060592 | Augmentation | MVS | GO2223012331PH | 20/01/2023 | 837.11 | 107.37 | 944.47 | Barasat Division | Eastern Mechanical Division | 330.48 | 41.39 | 50.77 | 0 | 422.63 | 330.48 | 41.39 | 50.77 | 0 | 422.63 | 44.75 | 54
201 | NORTH 24 PARAGANAS | SM/14513 | Augmentation of Hingalganj Piped water supply scheme Zone-II | TSM/018809 | 40060595 | Augmentation | MVS | GO2223012333PH | 20/01/2023 | 1026.51 | 125.18 | 1151.69 | Barasat Division | Eastern Mechanical Division | 335.11 | 0 | 0 | 0 | 335.11 | 335.11 | 0 | 0 | 0 | 335.11 | 29.1 | 79
202 | NORTH 24 PARAGANAS | SM/15816 | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | TSM/015278 | 40059894 | Augmentation | MVS | GO2223014387PH | 20/02/2023 | 7877.4 | 1037.68 | 8915.09 | North 24 Pgs W/S Division I | Electrical Division | 244.16 | 19.56 | 1627.91 | 0 | 1891.62 | 222.17 | 19.56 | 1547.5 | 0 | 1789.23 | 20.07 | 1
203 | NORTH 24 PARAGANAS | SM/10559 | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) | TSM/009206 | 40033175 | Augmentation | SVS | GO2223000392PH | 18/04/2022 | 31.05 | 43.02 | 74.08 | Barasat Arsenic Division | Eastern Mechanical Division | 24.31 | 11.88 | 0 | 0 | 36.19 | 24.31 | 11.88 | 0 | 0 | 36.19 | 48.86 | 72
204 | NORTH 24 PARAGANAS | SM/19108 | Augmentation of Mathurabil Zone-I in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | TSM/020571 | 0 | Augmentation | MVS | PHE/IV/3741/W-770/23 | 18/12/2023 | 985.92 | 0 | 985.92 | Barasat Division |  | 485.29 | 0 | 0 | 0 | 485.29 | 485.29 | 0 | 0 | 0 | 485.29 | 49.22 | 5
205 | NORTH 24 PARAGANAS | SM/19109 | Augmentation of Mathurabil Zone-II in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | TSM/020570 | 0 | Augmentation | MVS | PHE/IV/3741/W-770/23 | 18/12/2023 | 940.91 | 0 | 940.91 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | NORTH 24 PARAGANAS | SM/19110 | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | TSM/020569 | 0 | Augmentation | MVS | PHE/IV/3741/W-770/23 | 18/12/2023 | 874.94 | 0 | 874.94 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | NORTH 24 PARAGANAS | SM/14515 | Augmentation of Rajbari Piped water supply scheme | TSM/018704 | 40060619 | Augmentation | SVS | GO2223012357PH | 20/01/2023 | 689.37 | 42.95 | 732.31 | Barasat Division | Eastern Mechanical Division | 281.45 | 19.49 | 25.03 | 0 | 325.97 | 281.45 | 19.49 | 25.03 | 0 | 325.97 | 44.51 | 81
208 | NORTH 24 PARAGANAS | SM/11557 | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. | TSM/009609 | 40026992 | Augmentation | MVS | GO2223005406PH | 22/07/2022 | 582.3 | 51.78 | 634.07 | Barasat Arsenic Division | Eastern Mechanical Division | 433.29 | 10.59 | 32.56 | 0 | 476.43 | 432.1 | 10.59 | 32.56 | 0 | 475.24 | 74.95 | 94
209 | NORTH 24 PARAGANAS | SM/14510 | Augmentation of Sultanpur Piped water supply scheme | TSM/018805 | 40060606 | Augmentation | MVS | GO2223012324PH | 20/01/2023 | 408.54 | 46.45 | 454.99 | Barasat Division | Eastern Mechanical Division | 214.73 | 0 | 0 | 0 | 214.73 | 213.08 | 0 | 0 | 0 | 213.08 | 46.83 | 56
210 | NORTH 24 PARAGANAS | SM/18259 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015463 | 40033366 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1001.31 | 61.03 | 1062.34 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.8 | 0 | 0 | 0 | 3.8 | 3.8 | 0 | 0 | 0 | 3.8 | 0.36 | 1
211 | NORTH 24 PARAGANAS | SM/15822 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014788 | 40033427 | Augmentation | MVS | GO2223014375PH | 20/02/2023 | 1273 | 67.99 | 1340.98 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 524.32 | 3.36 | 224.55 | 0 | 752.23 | 373.2 | 3.36 | 224.55 | 0 | 601.11 | 44.83 | 6
212 | NORTH 24 PARAGANAS | SM/15819 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014881 | 40033417 | Augmentation | MVS | GO2223014384PH | 20/02/2023 | 1248.37 | 67.99 | 1316.36 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 216.43 | 3.64 | 216.52 | 16.08 | 452.67 | 216.43 | 3.64 | 216.52 | 16.08 | 452.67 | 34.39 | 12
213 | NORTH 24 PARAGANAS | SM/12383 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014883 | 40024318 | Augmentation | MVS | GO2223007607PH | 13/09/2022 | 972.52 | 64.3 | 1036.82 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 187.41 | 3.93 | 54.18 | 17.11 | 262.64 | 79.51 | 3.93 | 54.18 | 17.11 | 154.74 | 14.92 | 11
214 | NORTH 24 PARAGANAS | SM/15821 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014754 | 40033125 | Augmentation | MVS | GO2223014377PH | 20/02/2023 | 1047.51 | 67.53 | 1115.04 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 396.56 | 3.66 | 96.53 | 15.02 | 511.77 | 396.56 | 3.66 | 96.53 | 15.02 | 511.77 | 45.9 | 6
215 | NORTH 24 PARAGANAS | SM/15820 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014790 | 40033375 | Augmentation | MVS | GO2223014372PH | 20/02/2023 | 1329.34 | 70.11 | 1399.45 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 539.12 | 2.53 | 118.66 | 16.64 | 676.96 | 490.46 | 2.53 | 118.66 | 16.64 | 628.3 | 44.9 | 19
216 | NORTH 24 PARAGANAS | SM/18265 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015249 | 40033338 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1081.59 | 64.3 | 1145.89 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.72 | 0 | 19.73 | 0 | 23.45 | 3.72 | 0 | 19.73 | 0 | 23.45 | 2.05 | 1
217 | NORTH 24 PARAGANAS | SM/18264 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015086 | 40033139 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1280.02 | 67.53 | 1347.55 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 4.29 | 0 | 0 | 0 | 4.29 | 4.29 | 0 | 0 | 0 | 4.29 | 0.32 | 1
218 | NORTH 24 PARAGANAS | SM/18262 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015472 | 40033154 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1248.94 | 64.3 | 1313.24 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.76 | 5.4 | 43.82 | 0 | 52.98 | 3.76 | 5.4 | 43.82 | 0 | 52.98 | 4.03 | 5
219 | NORTH 24 PARAGANAS | SM/18263 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015074 | 40033400 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1207.07 | 64.3 | 1271.37 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.87 | 3.86 | 0 | 0 | 7.73 | 3.87 | 3.86 | 0 | 0 | 7.73 | 0.61 | 6
220 | NORTH 24 PARAGANAS | SM/18261 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015092 | 40033344 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1324.61 | 67.99 | 1392.6 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 109.58 | 4.53 | 53.85 | 15.29 | 183.24 | 109.58 | 0 | 53.85 | 15.29 | 178.72 | 12.83 | 5
221 | NORTH 24 PARAGANAS | SM/13435 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015250 | 40033407 | Augmentation | MVS | GO2223009177PH | 02/11/2022 | 946.46 | 64.3 | 1010.75 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 45.45 | 9.41 | 100.26 | 14.75 | 169.88 | 3.49 | 9.41 | 63.58 | 14.75 | 91.24 | 9.03 | 15
222 | NORTH 24 PARAGANAS | SM/12413 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014786 | 40024353 | Augmentation | MVS | GO2223007608PH | 13/09/2022 | 968.12 | 64.3 | 1032.42 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 247.01 | 2.48 | 109.23 | 0 | 358.72 | 180.71 | 2.48 | 109.23 | 0 | 292.43 | 28.32 | 7
223 | NORTH 24 PARAGANAS | SM/12414 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014753 | 40024331 | Augmentation | MVS | GO2223007609PH | 13/09/2022 | 996.63 | 67.99 | 1064.62 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 380.4 | 2.34 | 128.42 | 0 | 511.17 | 193.9 | 2.34 | 128.42 | 0 | 324.67 | 30.5 | 7
224 | NORTH 24 PARAGANAS | SM/15817 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014836 | 40058926 | Augmentation | MVS | GO2223014255PH | 20/02/2023 | 1049.24 | 127.97 | 1177.21 | North 24 Pgs W/S Division I | Electrical Division | 1.62 | 0 | 0 | 0 | 1.62 | 1.62 | 0 | 0 | 0 | 1.62 | 0.14 | 1
225 | NORTH 24 PARAGANAS | SM/15818 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/014884 | 40033167 | Augmentation | MVS | GO2223014380PH | 20/02/2023 | 1409.53 | 67.53 | 1477.06 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 4.17 | 0 | 77.1 | 0 | 81.27 | 4.17 | 0 | 30.11 | 0 | 34.29 | 2.32 | 2
226 | NORTH 24 PARAGANAS | SM/18260 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/015251 | 40033389 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1211.93 | 67.53 | 1279.46 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 283.39 | 4.73 | 22.34 | 16.03 | 326.49 | 143.5 | 4.73 | 22.34 | 16.03 | 186.6 | 14.58 | 24
227 | NORTH 24 PARAGANAS | SM/13902 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011942 | 40034263 | Augmentation | MVS | GO2223010167PH | 28/11/2022 | 1076.47 | 34.94 | 1111.41 | North 24 Pgs W/S Division I | Electrical Division | 21.03 | 0 | 68.34 | 0 | 89.37 | 12.36 | 0 | 68.34 | 0 | 80.7 | 7.26 | 2
228 | NORTH 24 PARAGANAS | SM/11827 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011868 | 40019311 | Augmentation | MVS | GO2223006287PH | 16/08/2022 | 774.71 | 30.71 | 805.42 | North 24 Pgs W/S Division I | Electrical Division | 50.32 | 0 | 0 | 0 | 50.32 | 34.43 | 0 | 0 | 0 | 34.43 | 4.27 | 1
229 | NORTH 24 PARAGANAS | SM/12728 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011949 | 40024231 | Augmentation | MVS | GO2223008010PH | 21/09/2022 | 1369.2 | 59.75 | 1428.95 | North 24 Pgs W/S Division I | Electrical Division | 18.33 | 5.04 | 2.75 | 0 | 26.12 | 3.79 | 5.04 | 2.75 | 0 | 11.58 | 0.81 | 1
230 | NORTH 24 PARAGANAS | SM/11826 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011866 | 40019310 | Augmentation | MVS | GO2223006288PH | 16/08/2022 | 883.76 | 30.71 | 914.47 | North 24 Pgs W/S Division I | Electrical Division | 48.92 | 0 | 49.64 | 0 | 98.56 | 7.99 | 0 | 49.64 | 0 | 57.63 | 6.3 | 2
231 | NORTH 24 PARAGANAS | SM/11864 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011948 | 40019331 | Augmentation | MVS | GO2223006446PH | 17/08/2022 | 747.77 | 58.24 | 806.01 | North 24 Pgs W/S Division I | Electrical Division | 149.29 | 0 | 0 | 0 | 149.29 | 149.29 | 0 | 0 | 0 | 149.29 | 18.52 | 2
232 | NORTH 24 PARAGANAS | SM/13794 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/012002 | 40042163 | Augmentation | MVS | GO2223009959PH | 22/11/2022 | 932.42 | 0 | 932.42 | North 24 Pgs W/S Division I |  | 74.98 | 0 | 55.55 | 0 | 130.53 | 27.4 | 0 | 55.55 | 0 | 82.95 | 8.9 | 2
233 | NORTH 24 PARAGANAS | SM/13434 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | TSM/013337 | 40040239 | Augmentation | MVS | GO2223009178PH | 02/11/2022 | 892.16 | 0 | 892.16 | North 24 Pgs W/S Division I |  | 138.06 | 0 | 0 | 0 | 138.06 | 98.95 | 0 | 0 | 0 | 98.95 | 11.09 | 1
234 | NORTH 24 PARAGANAS | SM/12625 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | TSM/012003 | 40024395 | Augmentation | MVS | GO2223007845PH | 19/09/2022 | 1285.8 | 0 | 1285.8 | North 24 Pgs W/S Division I |  | 189.9 | 0 | 44.83 | 0 | 234.73 | 79.48 | 0 | 44.83 | 0 | 124.31 | 9.67 | 1
235 | NORTH 24 PARAGANAS | SM/18258 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/013336 | 40037648 | Augmentation | MVS | 1587/PHE-28011/203/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 1544.28 | 0 | 1544.28 | North 24 Pgs W/S Division I |  | 4.88 | 0 | 0 | 0 | 4.88 | 4.88 | 0 | 0 | 0 | 4.88 | 0.32 | 1
236 | NORTH 24 PARAGANAS | SM/11921 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011601 | 40019337 | Augmentation | MVS | GO2223006613PH | 22/08/2022 | 767.04 | 0 | 767.04 | North 24 Pgs W/S Division I |  | 10.3 | 0 | 0 | 0 | 10.3 | 6.45 | 0 | 0 | 0 | 6.45 | 0.84 | 2
237 | NORTH 24 PARAGANAS | SM/12563 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/010887 | 40024322 | Augmentation | MVS | GO2223007702PH | 14/09/2022 | 1024.61 | 0 | 1024.61 | North 24 Pgs W/S Division I |  | 19.88 | 0 | 213.75 | 0 | 233.62 | 6.77 | 0 | 0 | 0 | 6.77 | 0.66 | 2
238 | NORTH 24 PARAGANAS | SM/12730 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011602 | 40024435 | Augmentation | MVS | GO2223008045PH | 21/09/2022 | 1212.9 | 0 | 1212.9 | North 24 Pgs W/S Division I |  | 4.3 | 0 | 39.74 | 0 | 44.04 | 4.3 | 0 | 39.74 | 0 | 44.04 | 3.63 | 1
239 | NORTH 24 PARAGANAS | SM/12566 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011870 | 40024236 | Augmentation | MVS | GO2223007696PH | 14/09/2022 | 1163.85 | 33.87 | 1197.72 | North 24 Pgs W/S Division I | Electrical Division | 111.45 | 0 | 116.3 | 0 | 227.75 | 57.61 | 0 | 116.3 | 0 | 173.91 | 14.52 | 4
240 | NORTH 24 PARAGANAS | SM/12372 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011863 | 40024239 | Augmentation | MVS | GO2223007577PH | 13/09/2022 | 1265.6 | 59.75 | 1325.35 | North 24 Pgs W/S Division I | Electrical Division | 18.9 | 0 | 74.39 | 0 | 93.29 | 4.21 | 0 | 74.39 | 0 | 78.6 | 5.93 | 1
241 | NORTH 24 PARAGANAS | SM/11941 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011892 | 40024380 | Augmentation | MVS | GO2223006668PH | 24/08/2022 | 867.92 | 30.71 | 898.63 | North 24 Pgs W/S Division I | Electrical Division | 63.2 | 0 | 80.44 | 0 | 143.64 | 47.73 | 0 | 80.44 | 0 | 128.17 | 14.26 | 2
242 | NORTH 24 PARAGANAS | SM/12565 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011891 | 40024390 | Augmentation | MVS | GO2223007694PH | 14/09/2022 | 1208.02 | 59.75 | 1267.76 | North 24 Pgs W/S Division I | Electrical Division | 39.82 | 0 | 42.49 | 0 | 82.31 | 14.17 | 0 | 42.49 | 0 | 56.66 | 4.47 | 2
243 | NORTH 24 PARAGANAS | SM/12564 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011897 | 40024375 | Augmentation | MVS | GO2223007711PH | 14/09/2022 | 1491.42 | 62.91 | 1554.33 | North 24 Pgs W/S Division I | Electrical Division | 125.01 | 0 | 0 | 0 | 125.01 | 74.99 | 0 | 0 | 0 | 74.99 | 4.82 | 2
244 | NORTH 24 PARAGANAS | SM/11922 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011824 | 40019339 | Augmentation | MVS | GO2223006615PH | 22/08/2022 | 737.22 | 0 | 737.22 | North 24 Pgs W/S Division I |  | 12.67 | 0 | 0 | 0 | 12.67 | 6.85 | 0 | 0 | 0 | 6.85 | 0.93 | 1
245 | NORTH 24 PARAGANAS | SM/12729 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011825 | 40024391 | Augmentation | MVS | GO2223008013PH | 21/09/2022 | 1214.95 | 105.5 | 1320.45 | North 24 Pgs W/S Division I | Electrical Division | 286.09 | 0 | 36.16 | 0 | 322.26 | 221.09 | 0 | 36.16 | 0 | 257.25 | 19.48 | 3
246 | NORTH 24 PARAGANAS | SM/11971 | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | TSM/011826 | 40024418 | Augmentation | MVS | GO2223006797PH | 29/08/2022 | 909.24 | 0 | 909.24 | North 24 Pgs W/S Division I |  | 103.47 | 0 | 0 | 0 | 103.47 | 32.77 | 0 | 0 | 0 | 32.77 | 3.6 | 1
247 | NORTH 24 PARAGANAS | SM/15559 | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. | TSM/017800 | 40061372 | Augmentation | MVS | GO2223013909PH | 16/02/2023 | 270.31 | 37.75 | 308.06 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 18.16 | 0 | 0 | 0 | 18.16 | 18.16 | 0 | 0 | 0 | 18.16 | 5.9 | 5
248 | NORTH 24 PARAGANAS | SM/17680 | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME | TSM/015003 | 40033878 | Augmentation | SVS | GO2223016655PH | 17/03/2023 | 225.01 | 69.27 | 294.29 | Barasat Division | Eastern Mechanical Division | 35.86 | 0 | 0 | 0 | 35.86 | 35.86 | 0 | 0 | 0 | 35.86 | 12.19 | 15
249 | NORTH 24 PARAGANAS | SM/12712 | Bachhra piped Water supply scheme | TSM/014837 | 40031785 | New | MVS | GO2223008029PH | 21/09/2022 | 581.13 | 61.01 | 642.14 | Barasat Division | Eastern Mechanical Division | 218.74 | 4.14 | 31.28 | 0 | 254.16 | 218.74 | 4.14 | 31.28 | 0 | 254.16 | 39.58 | 20
250 | NORTH 24 PARAGANAS | SM/14498 | Balibhara Piped Water Supply Scheme | TSM/016295 | 40065231 | New | SVS | GO2223012294PH | 20/01/2023 | 921.07 | 69.82 | 990.89 | North 24 Pgs W/S Division I | Electrical Division | 68.72 | 4.33 | 22.72 | 0 | 95.76 | 7.04 | 0 | 22.72 | 0 | 29.76 | 3 | 2
251 | NORTH 24 PARAGANAS | SM/13814 | Bamanpukuria Piped Water Supply Scheme. | TSM/014705 | 40032799 | New | SVS | GO2223009980PH | 23/11/2022 | 1118.09 | 61.01 | 1179.1 | Barasat Division | Eastern Mechanical Division | 283.85 | 0 | 0.83 | 0 | 284.67 | 283.85 | 0 | 0.83 | 0 | 284.67 | 24.14 | 17
252 | NORTH 24 PARAGANAS | SM/16626 | BARDASIA Piped Water Supply Scheme | TSM/016108 | 40037402 | New | MVS | GO2223015884PH | 14/03/2023 | 852.53 | 109.06 | 961.59 | Barasat Arsenic Division | Eastern Mechanical Division | 7.16 | 0 | 12.12 | 0 | 19.29 | 7.16 | 0 | 12.12 | 0 | 19.29 | 2.01 | 5
253 | NORTH 24 PARAGANAS | SM/15902 | Bargan Gopalpur Piped Water Supply Scheme | TSM/015449 | 40033568 | New | MVS | GO2223014385PH | 20/02/2023 | 1012.6 | 61.01 | 1073.62 | Barasat Division | Eastern Mechanical Division | 280.89 | 9.81 | 23.65 | 0 | 314.35 | 280.89 | 9.81 | 23.65 | 0 | 314.35 | 29.28 | 6
254 | NORTH 24 PARAGANAS | SM/15827 | Bhandarkhali Piped Water Supply Scheme | TSM/015379 | 40033910 | New | SVS | GO2223014374PH | 20/02/2023 | 1260.66 | 87.59 | 1348.25 | Barasat Division | Eastern Mechanical Division | 279.76 | 0 | 40.1 | 0 | 319.85 | 279.76 | 0 | 40.1 | 0 | 319.85 | 23.72 | 3
255 | NORTH 24 PARAGANAS | SM/14501 | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | TSM/017266 | 40034276 | New | MVS | GO2223012303PH | 20/01/2023 | 92.11 | 29.15 | 121.26 | North 24 Pgs W/S Division I | Electrical Division | 18.82 | 0.79 | 0 | 0 | 19.62 | 0.91 | 0 | 0 | 0 | 0.91 | 0.75 | 1
256 | NORTH 24 PARAGANAS | SM/13524 | Chutkia Radhanagar Piped Water Supply Scheme | TSM/015450 | 40032002 | New | MVS | GO2223009347PH | 04/11/2022 | 698.74 | 61.01 | 759.76 | Barasat Division | Eastern Mechanical Division | 217.28 | 11.01 | 0.96 | 0 | 229.25 | 217.28 | 11.01 | 0.96 | 0 | 229.25 | 30.17 | 17
257 | NORTH 24 PARAGANAS | SM/18617 | Dakshin Akhratala Piped Water Supply Scheme | TSM/015754 | 40060524 | New | SVS | 2161/PHE-28011/238/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1906.42 | 122.02 | 2028.44 | Barasat Division | Eastern Mechanical Division | 311.78 | 0 | 222.59 | 0 | 534.36 | 311.78 | 0 | 222.59 | 0 | 534.36 | 26.34 | 5
258 | NORTH 24 PARAGANAS | SM/13523 | Debitala Piped Water Supply Scheme | TSM/015448 | 40032763 | New | SVS | GO2223009342PH | 04/11/2022 | 917 | 61.01 | 978.01 | Barasat Division | Eastern Mechanical Division | 242.96 | 0 | 6.05 | 0 | 249.01 | 242.96 | 0 | 6.05 | 0 | 249.01 | 25.46 | 18
259 | NORTH 24 PARAGANAS | SM/14625 | Electrocoagulation based package Surface water based water supply scheme (Solar Power) in Minakhan Block | TSM/015125 | 40063367 | New | MVS | GO2223012660PH | 31/01/2023 | 46.97 | 0 | 46.97 | Barasat Division |  | 35.83 | 0 | 0 | 0 | 35.83 | 35.83 | 0 | 0 | 0 | 35.83 | 76.28 | 78
260 | NORTH 24 PARAGANAS | SM/14504 | Gar Shyamnagar Piped Water Supply Scheme | TSM/016489 | 40065221 | New | SVS | GO2223012302PH | 20/01/2023 | 861.12 | 59.49 | 920.61 | North 24 Pgs W/S Division I | Electrical Division | 6.53 | 0 | 0 | 0 | 6.53 | 6.53 | 0 | 0 | 0 | 6.53 | 0.71 | 1
261 | NORTH 24 PARAGANAS | SM/13897 | Garibpur Piped water supply scheme | TSM/016336 | 40032877 | New | MVS | GO2223010101PH | 25/11/2022 | 566.95 | 27.4 | 594.36 | Barasat Division | Eastern Mechanical Division | 136.47 | 7.5 | 4.65 | 0 | 148.62 | 136.47 | 7.5 | 4.65 | 0 | 148.62 | 25.01 | 9
262 | NORTH 24 PARAGANAS | SM/12718 | Ghipukuria Piped Water Supply Scheme. | TSM/014711 | 40031743 | New | MVS | GO2223008023PH | 21/09/2022 | 695.26 | 61.01 | 756.27 | Barasat Division | Eastern Mechanical Division | 117.39 | 0 | 0 | 0 | 117.39 | 117.39 | 0 | 0 | 0 | 117.39 | 15.52 | 9
263 | NORTH 24 PARAGANAS | SM/18537 | GHUNI Piped Water Supply Scheme | TSM/016293 | 40041816 | New | SVS | 2056/PHE-28011/57/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1607.92 | 113.24 | 1721.16 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 12.92 | 0 | 0 | 0 | 12.92 | 12.92 | 0 | 0 | 0 | 12.92 | 0.75 | 6
264 | NORTH 24 PARAGANAS | SM/10582 | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | TSM/010664 | 40012922 | Augmentation | MVS | GO2223000337PH | 18/04/2022 | 568.21 | 32.83 | 601.04 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 130.99 | 8.11 | 29.12 | 0 | 168.22 | 130.99 | 8.11 | 29.12 | 0 | 168.22 | 27.99 | 10
265 | NORTH 24 PARAGANAS | SM/10546 | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | TSM/010666 | 40012978 | Augmentation | MVS | GO2223000375PH | 18/04/2022 | 705.8 | 32.66 | 738.46 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.67 | 0 | 55.03 | 0 | 58.7 | 3.67 | 0 | 55.03 | 0 | 58.7 | 7.95 | 5
266 | NORTH 24 PARAGANAS | SM/13525 | Hatbhanga Piped Water Supply Scheme | TSM/015443 | 40032011 | New | MVS | GO2223009348PH | 04/11/2022 | 691.15 | 61.01 | 752.17 | Barasat Division | Eastern Mechanical Division | 64.4 | 17.5 | 1.79 | 0 | 83.69 | 64.4 | 17.5 | 1.79 | 0 | 83.69 | 11.13 | 12
267 | NORTH 24 PARAGANAS | SM/16625 | JATRAGACHHI Piped Water Supply Scheme | TSM/016452 | 40037877 | New | SVS | GO2223015883PH | 14/03/2023 | 864.54 | 75.49 | 940.04 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 7.05 | 0 | 12.65 | 0 | 19.7 | 7.05 | 0 | 12.65 | 0 | 19.7 | 2.1 | 6
268 | NORTH 24 PARAGANAS | SM/12719 | Jhikra Piped Water Supply Scheme. | TSM/014699 | 40031662 | New | MVS | GO2223008021PH | 21/09/2022 | 780.61 | 61.01 | 841.62 | Barasat Division | Eastern Mechanical Division | 272.49 | 12.25 | 4.54 | 0 | 289.28 | 272.49 | 16.78 | 4.54 | 0 | 293.81 | 34.91 | 11
269 | NORTH 24 PARAGANAS | SM/13522 | Kachurhula Zone-I Piped Water Supply Scheme | TSM/015511 | 40032059 | New | SVS | GO2223009343PH | 04/11/2022 | 541 | 61.01 | 602.01 | Barasat Division | Eastern Mechanical Division | 80.11 | 0 | 0 | 0 | 80.11 | 79.23 | 0 | 0 | 0 | 79.23 | 13.16 | 3
270 | NORTH 24 PARAGANAS | SM/13445 | Kachurhula Zone-II Piped Water Supply Scheme | TSM/015445 | 40031993 | New | MVS | GO2223009239PH | 02/11/2022 | 352.71 | 61.01 | 413.72 | Barasat Division | Eastern Mechanical Division | 132.83 | 0 | 0 | 0 | 132.83 | 132.83 | 0 | 0 | 0 | 132.83 | 32.11 | 12
271 | NORTH 24 PARAGANAS | SM/15826 | Katakhali Piped Water Supply Scheme | TSM/015510 | 40033569 | New | SVS | GO2223014376PH | 20/02/2023 | 1091.5 | 91.52 | 1183.01 | Barasat Division | Eastern Mechanical Division | 193.92 | 0 | 12.1 | 0 | 206.02 | 193.92 | 0 | 12.1 | 0 | 206.02 | 17.41 | 3
272 | NORTH 24 PARAGANAS | SM/14499 | Kaugachhi Zone-I Piped Water Supply Scheme | TSM/016327 | 40032887 | New | SVS | GO2223012300PH | 20/01/2023 | 661.84 | 35.88 | 697.72 | North 24 Pgs W/S Division I | Electrical Division | 4.96 | 0 | 0 | 0 | 4.96 | 4.96 | 0 | 0 | 0 | 4.96 | 0.71 | 1
273 | NORTH 24 PARAGANAS | SM/14500 | Kaugachhi Zone-II Piped Water Supply Scheme | TSM/016488 | 40032900 | New | SVS | GO2223012382PH | 20/01/2023 | 864.81 | 59.49 | 924.3 | North 24 Pgs W/S Division I | Electrical Division | 6.49 | 0 | 45.72 | 0 | 52.21 | 6.49 | 0 | 45.72 | 0 | 52.21 | 5.65 | 1
274 | NORTH 24 PARAGANAS | SM/14502 | Kaugachhi Zone-III Piped Water Supply Scheme | TSM/016342 | 40032916 | New | SVS | GO2223012301PH | 20/01/2023 | 660.72 | 35.88 | 696.59 | North 24 Pgs W/S Division I | Electrical Division | 4.95 | 0 | 0 | 0 | 4.95 | 4.95 | 0 | 0 | 0 | 4.95 | 0.71 | 1
275 | NORTH 24 PARAGANAS | SM/15833 | Ketarchak Piped Water Supply Scheme | TSM/015343 | 40033566 | New | MVS | GO2223014371PH | 20/02/2023 | 1245.94 | 87.59 | 1333.54 | Barasat Division | Eastern Mechanical Division | 9.65 | 0 | 32.35 | 0 | 42 | 9.65 | 0 | 32.35 | 0 | 42 | 3.15 | 3
276 | NORTH 24 PARAGANAS | SM/15829 | Khariat Abad Piped Water Supply Scheme | TSM/015513 | 40033590 | New | MVS | GO2223014381PH | 20/02/2023 | 1429.5 | 91.52 | 1521.01 | Barasat Division | Eastern Mechanical Division | 11.37 | 17.18 | 30.63 | 0 | 59.18 | 11.37 | 17.18 | 30.63 | 0 | 59.18 | 3.89 | 8
277 | NORTH 24 PARAGANAS | SM/13519 | Kharibaria Piped Water Supply Scheme. | TSM/015444 | 40032035 | New | MVS | GO2223009235PH | 02/11/2022 | 917.76 | 61.01 | 978.77 | Barasat Division | Eastern Mechanical Division | 235.69 | 25.56 | 6.11 | 0 | 267.36 | 235.69 | 25.56 | 6.11 | 0 | 267.36 | 27.32 | 22
278 | NORTH 24 PARAGANAS | SM/18591 | KOLA Piped Water Supply Scheme | TSM/016122 | 40037428 | New | MVS | 2149/PHE-28011/154/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1395.39 | 137.53 | 1532.91 | Barasat Arsenic Division | Eastern Mechanical Division | 11.36 | 35.11 | 20.22 | 0 | 66.69 | 11.36 | 35.11 | 20.22 | 0 | 66.69 | 4.35 | 13
279 | NORTH 24 PARAGANAS | SM/15832 | Kusangra Piped Water Supply Scheme | TSM/015447 | 40033905 | New | MVS | GO2223014383PH | 20/02/2023 | 1014.29 | 91.52 | 1105.8 | Barasat Division | Eastern Mechanical Division | 175.36 | 17.09 | 15.71 | 0 | 208.16 | 175.36 | 17.09 | 15.71 | 0 | 208.16 | 18.82 | 10
280 | NORTH 24 PARAGANAS | SM/13813 | Mallik Gheri Piped Water Supply Scheme. | TSM/014697 | 40032813 | New | MVS | GO2223009981PH | 23/11/2022 | 929.36 | 91.52 | 1020.87 | Barasat Division | Eastern Mechanical Division | 282.31 | 11.57 | 0 | 0 | 293.89 | 282.31 | 11.57 | 0 | 0 | 293.89 | 28.79 | 49
281 | NORTH 24 PARAGANAS | SM/15825 | Matbari Abad Piped Water Supply Scheme | TSM/015514 | 40033570 | New | SVS | GO2223014378PH | 20/02/2023 | 1265 | 61.01 | 1326.01 | Barasat Division | Eastern Mechanical Division | 258.49 | 11.16 | 0 | 0 | 269.65 | 257.66 | 11.16 | 0 | 0 | 268.82 | 20.27 | 7
282 | NORTH 24 PARAGANAS | SM/12716 | Niruli Abad Piped Water Supply Scheme. | TSM/014701 | 40031759 | New | MVS | GO2223008022PH | 21/09/2022 | 430.84 | 61.01 | 491.85 | Barasat Division | Eastern Mechanical Division | 122.21 | 4.92 | 0 | 0 | 127.13 | 122.21 | 4.92 | 0 | 0 | 127.13 | 25.85 | 33
283 | NORTH 24 PARAGANAS | SM/10182 | NITYABARIA PIPED WATER SUPPLY SCHEME | TSM/008650 | 40010109 | New | MVS | GO2122009754PH | 17/02/2022 | 1092.47 | 126.77 | 1219.24 | Barasat Division | Eastern Mechanical Division | 70.4 | 21.65 | 0 | 0 | 92.05 | 70.4 | 21.65 | 0 | 0 | 92.05 | 7.55 | 45
284 | NORTH 24 PARAGANAS | SM/13895 | Paschim Huda Piped water supply scheme | TSM/016341 | 40032864 | New | MVS | GO2223010100PH | 25/11/2022 | 668.37 | 28.71 | 697.08 | Barasat Division | Eastern Mechanical Division | 216.91 | 18.51 | 7.45 | 0 | 242.87 | 216.91 | 18.51 | 7.45 | 0 | 242.87 | 34.84 | 34
285 | NORTH 24 PARAGANAS | SM/15830 | Petua Dhanihati Piped Water Supply Scheme | TSM/015512 | 40033571 | New | MVS | GO2223014373PH | 20/02/2023 | 1061.49 | 61.01 | 1122.5 | Barasat Division | Eastern Mechanical Division | 166.07 | 4.12 | 20.17 | 0 | 190.36 | 166.07 | 4.12 | 20.17 | 0 | 190.36 | 16.96 | 7
286 | NORTH 24 PARAGANAS | SM/12717 | Phulbari Abad Piped Water Supply Scheme. | TSM/014714 | 40031780 | New | MVS | GO2223008025PH | 21/09/2022 | 586.7 | 61.01 | 647.71 | Barasat Division | Eastern Mechanical Division | 162.39 | 6.66 | 0 | 0 | 169.05 | 162.39 | 6.66 | 0 | 0 | 169.05 | 26.1 | 37
287 | NORTH 24 PARAGANAS | SM/12721 | Pipuldaha Piped Water Supply Scheme. | TSM/014691 | 40031791 | New | MVS | GO2223008032PH | 21/09/2022 | 509.23 | 61.01 | 570.24 | Barasat Division | Eastern Mechanical Division | 137 | 10.48 | 173.78 | 0 | 321.27 | 137 | 10.48 | 173.78 | 0 | 321.27 | 56.34 | 19
288 | NORTH 24 PARAGANAS | SM/10583 | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | TSM/010275 | 40012988 | Augmentation | MVS | GO2223000389PH | 18/04/2022 | 965.67 | 87.59 | 1053.27 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 452.59 | 15.8 | 60 | 0 | 528.39 | 425.52 | 15.8 | 60 | 0 | 501.32 | 47.6 | 52
289 | NORTH 24 PARAGANAS | SM/10580 | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | TSM/010408 | 40012921 | Augmentation | MVS | GO2223000343PH | 18/04/2022 | 624.56 | 65.87 | 690.43 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 320.19 | 0 | 119.7 | 0 | 439.89 | 320.19 | 0 | 119.7 | 0 | 439.89 | 63.71 | 63
290 | NORTH 24 PARAGANAS | SM/10412 | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | TSM/010391 | 40013014 | Augmentation | MVS | GO2223000122PH | 08/04/2022 | 686.29 | 45.13 | 731.42 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 298 | 0 | 258.58 | 0 | 556.57 | 204.57 | 0 | 258.58 | 0 | 463.14 | 63.32 | 37
291 | NORTH 24 PARAGANAS | SM/10758 | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | TSM/010573 | 40012925 | Augmentation | MVS | GO2223003141PH | 23/05/2022 | 1316.99 | 32.66 | 1349.65 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 4.15 | 0 | 25.56 | 0 | 29.71 | 4.15 | 0 | 25.56 | 0 | 29.71 | 2.2 | 2
292 | NORTH 24 PARAGANAS | SM/10777 | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | TSM/009938 | 40013002 | Augmentation | MVS | GO2223003485PH | 25/05/2022 | 1054.95 | 0 | 1054.95 | North 24 Pgs W/S Division I |  | 777.4 | 0 | 43.57 | 0 | 820.97 | 777.4 | 0 | 43.57 | 0 | 820.97 | 77.82 | 52
293 | NORTH 24 PARAGANAS | SM/10607 | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | TSM/010566 | 40012924 | Augmentation | MVS | GO2223000413PH | 19/04/2022 | 1065.93 | 32.66 | 1098.59 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 4.65 | 6.63 | 233.47 | 0 | 244.75 | 4.65 | 6.63 | 185.89 | 0 | 197.17 | 17.95 | 7
294 | NORTH 24 PARAGANAS | SM/10105 | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | TSM/009496 | 40003034 | Augmentation | MVS | GO2122009125PH | 02/02/2022 | 918.69 | 0 | 918.69 | North 24 Pgs W/S Division I |  | 729.91 | 0 | 58.06 | 0 | 787.97 | 581.72 | 0 | 58.06 | 0 | 639.78 | 69.64 | 75
295 | NORTH 24 PARAGANAS | SM/10098 | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | TSM/009448 | 40002898 | Augmentation | MVS | GO2122009131PH | 02/02/2022 | 906.75 | 0 | 906.75 | North 24 Pgs W/S Division I |  | 465.13 | 0 | 91.62 | 0 | 556.75 | 445.19 | 0 | 91.62 | 0 | 536.81 | 59.2 | 78
296 | NORTH 24 PARAGANAS | SM/10579 | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | TSM/010599 | 40012932 | Augmentation | MVS | GO2223000344PH | 18/04/2022 | 1046.68 | 27.39 | 1074.06 | North 24 Pgs W/S Division I | Electrical Division | 223.68 | 5.43 | 76.8 | 0 | 305.92 | 138.97 | 5.43 | 12.32 | 0 | 156.72 | 14.59 | 5
297 | NORTH 24 PARAGANAS | SM/11556 | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | TSM/011191 | 40019328 | Augmentation | MVS | GO2223005396PH | 22/07/2022 | 469.36 | 74.9 | 544.26 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 59.47 | 5.48 | 33.87 | 0 | 98.82 | 51.15 | 5.48 | 33.87 | 0 | 90.5 | 16.63 | 17
298 | NORTH 24 PARAGANAS | SM/10415 | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | TSM/010388 | 40013020 | Augmentation | MVS | GO2223000125PH | 08/04/2022 | 567.08 | 43.92 | 611 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 354.01 | 21.86 | 22.87 | 0 | 398.74 | 313.23 | 21.86 | 22.87 | 0 | 357.96 | 58.59 | 69
299 | NORTH 24 PARAGANAS | SM/10639 | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | TSM/010276 | 40012939 | Augmentation | MVS | GO2223000478PH | 21/04/2022 | 850.64 | 83.14 | 933.78 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 593.53 | 15.53 | 143.45 | 0 | 752.5 | 459.81 | 15.53 | 143.45 | 0 | 618.78 | 66.27 | 70
300 | NORTH 24 PARAGANAS | SM/10638 | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | TSM/010263 | 40012970 | Augmentation | MVS | GO2223000477PH | 21/04/2022 | 846.71 | 83.14 | 929.85 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 434.2 | 0 | 215.42 | 0 | 649.61 | 434.2 | 0 | 215.42 | 0 | 649.61 | 69.86 | 50
301 | NORTH 24 PARAGANAS | SM/11212 | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | TSM/010262 | 40012940 | Augmentation | MVS | GO2223003936PH | 09/06/2022 | 1186.58 | 83.14 | 1269.72 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 385.98 | 15.3 | 245.61 | 0 | 646.89 | 381.95 | 15.3 | 245.61 | 0 | 642.87 | 50.63 | 43
302 | NORTH 24 PARAGANAS | SM/10608 | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. | TSM/010405 | 40012991 | Augmentation | MVS | GO2223000414PH | 19/04/2022 | 285.33 | 43.92 | 329.25 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 182 | 0 | 9.38 | 0 | 191.38 | 156.93 | 0 | 9.38 | 0 | 166.31 | 50.51 | 56
303 | NORTH 24 PARAGANAS | SM/11555 | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. | TSM/011010 | 40019068 | Augmentation | MVS | GO2223005395PH | 22/07/2022 | 646.37 | 32.66 | 679.03 | North 24 Pgs W/S Division I | Eastern Mechanical Division | 3.33 | 3.33 | 29.38 | 0 | 36.04 | 3.33 | 3.33 | 29.38 | 0 | 36.04 | 5.31 | 44
304 | NORTH 24 PARAGANAS | SM/10581 | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | TSM/009939 | 40012928 | Augmentation | MVS | GO2223000340PH | 18/04/2022 | 702.18 | 0 | 702.18 | North 24 Pgs W/S Division I |  | 520.86 | 0 | 25.46 | 0 | 546.32 | 474.68 | 0 | 25.46 | 0 | 500.15 | 71.23 | 67
305 | NORTH 24 PARAGANAS | SM/10153 | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | TSM/009497 | 40003042 | Augmentation | MVS | GO2122009656PH | 11/02/2022 | 1043.42 | 0 | 1043.42 | North 24 Pgs W/S Division I |  | 481.78 | 0 | 94.3 | 0 | 576.07 | 395 | 0 | 94.3 | 0 | 489.3 | 46.89 | 55
306 | NORTH 24 PARAGANAS | SM/08640 | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | TSM/007626 | 40006019 | Retrofitting | MVS | GO2122001202PH | 18/06/2021 | 260.99 | 0 | 260.99 | Barasat Division |  | 172.98 | 0 | 61.5 | 0 | 234.48 | 172.98 | 0 | 61.5 | 0 | 234.48 | 89.84 | 100
307 | NORTH 24 PARAGANAS | SM/08641 | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | TSM/007632 | 40000930 | Retrofitting | MVS | GO2122001203PH | 18/06/2021 | 253.69 | 0 | 253.69 | Barasat Division |  | 222.84 | 0 | 30.8 | 0 | 253.64 | 222.84 | 0 | 30.8 | 0 | 253.64 | 99.98 | 100
308 | NORTH 24 PARAGANAS | SM/08767 | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh | TSM/007349 | 40001044 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 60.31 | 0 | 60.31 | Barasat Division |  | 57.61 | 0 | 0 | 0 | 57.61 | 57.61 | 0 | 0 | 0 | 57.61 | 95.51 | 100
309 | NORTH 24 PARAGANAS | SM/08638 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | TSM/007644 | 40001064 | Retrofitting | MVS | GO2122001200PH | 18/06/2021 | 61.11 | 0 | 61.11 | Barasat Division |  | 56.27 | 0 | 0 | 0 | 56.27 | 56.27 | 0 | 0 | 0 | 56.27 | 92.09 | 91
310 | NORTH 24 PARAGANAS | SM/08787 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of ARSULA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/007637 | 40000961 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 230.14 | 0 | 230.14 | Barasat Division |  | 163.93 | 0 | 43.2 | 0 | 207.13 | 163.93 | 0 | 43.2 | 0 | 207.13 | 90 | 100
311 | NORTH 24 PARAGANAS | SM/08659 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007634 | 40000360 | Retrofitting | MVS | GO2122001217PH | 18/06/2021 | 225.64 | 0 | 225.64 | Barasat Division |  | 189.44 | 0 | 25 | 0 | 214.44 | 189.44 | 0 | 25 | 0 | 214.44 | 95.03 | 100
312 | NORTH 24 PARAGANAS | SM/08651 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007635 | 40001074 | Retrofitting | MVS | GO2122001214PH | 18/06/2021 | 78.68 | 0 | 78.68 | Barasat Division |  | 75 | 0 | 0 | 0 | 75 | 74.9 | 0 | 0 | 0 | 74.9 | 95.2 | 100
313 | NORTH 24 PARAGANAS | SM/09226 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MASIA- NABASTIA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/007639 | 40008835 | Retrofitting | MVS | GO2122004775PH | 01/11/2021 | 67.73 | 0 | 67.73 | Barasat Division |  | 52.45 | 0 | 11.09 | 0 | 63.54 | 52.44 | 0 | 11.09 | 0 | 63.53 | 93.8 | 100
314 | NORTH 24 PARAGANAS | SM/08650 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BANSJHARI MALLIKPUR W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007629 | 40011022 | Retrofitting | MVS | GO2122001212PH | 18/06/2021 | 54.59 | 0 | 54.59 | Barasat Division |  | 51.55 | 0 | 0 | 0 | 51.55 | 51.55 | 0 | 0 | 0 | 51.55 | 94.44 | 100
315 | NORTH 24 PARAGANAS | SM/08658 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of CHAMPAPUKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007648 | 40001053 | Retrofitting | MVS | GO2122001220PH | 18/06/2021 | 80.66 | 0 | 80.66 | Barasat Division |  | 73.65 | 0 | 0 | 0 | 73.65 | 73.65 | 0 | 0 | 0 | 73.65 | 91.31 | 100
316 | NORTH 24 PARAGANAS | SM/08643 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DEBOG W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | TSM/007638 | 40006011 | Retrofitting | MVS | GO2122001205PH | 18/06/2021 | 100.22 | 0 | 100.22 | Barasat Division |  | 38.72 | 0 | 61.5 | 0 | 100.22 | 38.72 | 0 | 61.5 | 0 | 100.22 | 100 | 100
317 | NORTH 24 PARAGANAS | SM/08788 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/007647 | 40008865 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 89.79 | 0 | 89.79 | Barasat Division |  | 79.62 | 0 | 7.38 | 0 | 87 | 79.62 | 0 | 7.38 | 0 | 87 | 96.89 | 100
318 | NORTH 24 PARAGANAS | SM/08655 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007643 | 40008842 | Retrofitting | MVS | GO2122001223PH | 18/06/2021 | 97.8 | 0 | 97.8 | Barasat Division |  | 80.56 | 0 | 14.76 | 0 | 95.32 | 80.56 | 0 | 14.76 | 0 | 95.32 | 97.46 | 100
319 | NORTH 24 PARAGANAS | SM/08648 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007649 | 40001259 | Retrofitting | MVS | GO2122001211PH | 18/06/2021 | 67.63 | 0 | 67.63 | Barasat Division |  | 62.87 | 0 | 0 | 0 | 62.87 | 62.87 | 0 | 0 | 0 | 62.87 | 92.97 | 100
320 | NORTH 24 PARAGANAS | SM/08647 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007641 | 40005892 | Retrofitting | MVS | GO2122001210PH | 18/06/2021 | 262.67 | 0 | 262.67 | Barasat Division |  | 223.66 | 0 | 33.83 | 0 | 257.49 | 223.66 | 0 | 33.83 | 0 | 257.49 | 98.03 | 100
321 | NORTH 24 PARAGANAS | SM/08642 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | TSM/007633 | 40002767 | Retrofitting | MVS | GO2122001204PH | 18/06/2021 | 99.01 | 0 | 99.01 | Barasat Division |  | 96.82 | 0 | 0 | 0 | 96.82 | 96.82 | 0 | 0 | 0 | 96.82 | 97.79 | 100
322 | NORTH 24 PARAGANAS | SM/09735 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/008770 | 40012782 | Retrofitting | MVS | GO2122005969PH | 26/11/2021 | 180.22 | 0 | 180.22 | Barasat Division |  | 108.96 | 0 | 63.87 | 0 | 172.83 | 108.96 | 0 | 63.87 | 0 | 172.83 | 95.9 | 100
323 | NORTH 24 PARAGANAS | SM/08656 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MATHURAPUR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007646 | 40001062 | Retrofitting | MVS | GO2122001224PH | 18/06/2021 | 100.07 | 0 | 100.07 | Barasat Division |  | 87.1 | 0 | 0 | 0 | 87.1 | 87.1 | 0 | 0 | 0 | 87.1 | 87.04 | 100
324 | NORTH 24 PARAGANAS | SM/09729 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Nabatkati W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | TSM/009443 | 40013460 | Retrofitting | MVS | GO2122005975PH | 26/11/2021 | 200.79 | 0 | 200.79 | Barasat Division |  | 123.38 | 0 | 71.35 | 0 | 194.73 | 123.38 | 0 | 71.35 | 0 | 194.73 | 96.98 | 100
325 | NORTH 24 PARAGANAS | SM/09730 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | TSM/009440 | 40013183 | Retrofitting | MVS | GO2122005975PH | 26/11/2021 | 197.1 | 0 | 197.1 | Barasat Division |  | 172.97 | 0 | 0 | 0 | 172.97 | 172.97 | 0 | 0 | 0 | 172.97 | 87.76 | 100
326 | NORTH 24 PARAGANAS | SM/08789 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of PIFA W/S Scheme at Basirhat -I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | TSM/007640 | 40006016 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 80.66 | 0 | 80.66 | Barasat Division |  | 71.65 | 0 | 7.38 | 0 | 79.03 | 71.51 | 0 | 7.38 | 0 | 78.89 | 97.8 | 100
327 | NORTH 24 PARAGANAS | SM/08646 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of RAHARHATI W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). | TSM/007642 | 40001055 | Retrofitting | MVS | GO2122001208PH | 18/06/2021 | 67.63 | 0 | 67.63 | Barasat Division |  | 62.47 | 0 | 0 | 0 | 62.47 | 62.47 | 0 | 0 | 0 | 62.47 | 92.38 | 100
328 | NORTH 24 PARAGANAS | SM/08649 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of SANKCHURA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). | TSM/007628 | 40006004 | Retrofitting | MVS | GO2122001216PH | 18/06/2021 | 93.7 | 0 | 93.7 | Barasat Division |  | 81.33 | 0 | 9.24 | 0 | 90.57 | 81.33 | 0 | 9.24 | 0 | 90.57 | 96.66 | 100
329 | NORTH 24 PARAGANAS | SM/09728 | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Taranipur W/S Scheme (Zone-II) at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). | TSM/009446 | 40013462 | Retrofitting | MVS | GO2122005975PH | 26/11/2021 | 148.48 | 0 | 148.48 | Barasat Division |  | 91.82 | 0 | 49.28 | 0 | 141.1 | 91.82 | 0 | 49.28 | 0 | 141.1 | 95.03 | 100
330 | NORTH 24 PARAGANAS | SM/10616 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Bermajur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | TSM/010695 | 7044616 | Retrofitting | SVS | GO2223000438PH | 20/04/2022 | 158.22 | 0 | 158.22 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | NORTH 24 PARAGANAS | SM/10554 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | TSM/010694 | 40029302 | Retrofitting | MVS | GO2223000385PH | 18/04/2022 | 150.09 | 0 | 150.09 | Barasat Division |  | 145.72 | 0 | 0 | 0 | 145.72 | 145.72 | 0 | 0 | 0 | 145.72 | 97.09 | 88
332 | NORTH 24 PARAGANAS | SM/10556 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010696 | 40037210 | Retrofitting | MVS | GO2223000388PH | 18/04/2022 | 430.12 | 0 | 430.12 | Barasat Division |  | 279.45 | 0 | 0 | 0 | 279.45 | 279.45 | 0 | 0 | 0 | 279.45 | 64.97 | 100
333 | NORTH 24 PARAGANAS | SM/10557 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010697 | 40037229 | Retrofitting | MVS | GO2223000390PH | 18/04/2022 | 309.66 | 0 | 309.66 | Barasat Division |  | 293.07 | 0 | 0 | 0 | 293.07 | 293.07 | 0 | 0 | 0 | 293.07 | 94.64 | 97
334 | NORTH 24 PARAGANAS | SM/10553 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | TSM/010693 | 40023079 | Retrofitting | SVS | GO2223000382PH | 18/04/2022 | 89.4 | 0 | 89.4 | Barasat Division |  | 86.79 | 0 | 0 | 0 | 86.79 | 86.79 | 0 | 0 | 0 | 86.79 | 97.09 | 36
335 | NORTH 24 PARAGANAS | SM/10552 | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | TSM/010692 | 40023087 | Retrofitting | MVS | GO2223000374PH | 18/04/2022 | 122.05 | 0 | 122.05 | Barasat Division |  | 81.65 | 0 | 30 | 0 | 111.65 | 81.65 | 0 | 30 | 0 | 111.65 | 91.48 | 100
336 | NORTH 24 PARAGANAS | SM/13536 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proj | TSM/011510 | 40033259 | Retrofitting | MVS | GO2223009336PH | 04/11/2022 | 735.64 | 0 | 735.64 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | NORTH 24 PARAGANAS | SM/13531 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011524 | 40033268 | Retrofitting | MVS | GO2223009344PH | 04/11/2022 | 678.06 | 0 | 678.06 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | NORTH 24 PARAGANAS | SM/13547 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011538 | 40033307 | Retrofitting | MVS | GO2223009354PH | 04/11/2022 | 860.32 | 0 | 860.32 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | NORTH 24 PARAGANAS | SM/13546 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011562 | 40033306 | Retrofitting | MVS | GO2223009353PH | 04/11/2022 | 870.02 | 0 | 870.02 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
340 | NORTH 24 PARAGANAS | SM/13530 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011527 | 40033238 | Retrofitting | MVS | GO2223009345PH | 04/11/2022 | 864.01 | 0 | 864.01 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | NORTH 24 PARAGANAS | SM/13528 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011539 | 40033245 | Retrofitting | MVS | GO2223009349PH | 04/11/2022 | 764.12 | 0 | 764.12 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | NORTH 24 PARAGANAS | SM/13529 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011536 | 40033252 | Retrofitting | MVS | GO2223009346PH | 04/11/2022 | 798.89 | 0 | 798.89 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | NORTH 24 PARAGANAS | SM/13527 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa | TSM/011540 | 40033218 | Retrofitting | MVS | GO2223009350PH | 04/11/2022 | 646.01 | 0 | 646.01 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | NORTH 24 PARAGANAS | SM/07605 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) | TSM/006914 | 8162419 | Retrofitting | MVS | GO2021004111PH | 05/01/2021 | 73.51 | 0 | 73.51 | North 24 Pgs W/S Division I |  | 71.79 | 0 | 0 | 0 | 71.79 | 71.79 | 0 | 0 | 0 | 71.79 | 97.66 | 98
345 | NORTH 24 PARAGANAS | SM/08039 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) | TSM/007047 | 8359418 | Retrofitting | MVS | GO2021005932PH | 01/02/2021 | 252.36 | 0 | 252.36 | North 24 Pgs W/S Division I |  | 230.41 | 0 | 0 | 0 | 230.41 | 230.41 | 0 | 0 | 0 | 230.41 | 91.3 | 98
346 | NORTH 24 PARAGANAS | SM/08044 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bangangram (Zone-I) Water Supply Scheme at Bongaon Block (Phase-II) | TSM/007084 | 8358833 | Retrofitting | SVS | GO2021005937PH | 01/02/2021 | 39.06 | 0 | 39.06 | North 24 Pgs W/S Division I |  | 37.4 | 0 | 0 | 0 | 37.4 | 37.4 | 0 | 0 | 0 | 37.4 | 95.77 | 98
347 | NORTH 24 PARAGANAS | SM/07608 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006923 | 8171512 | Retrofitting | MVS | GO2021004102PH | 05/01/2021 | 74.49 | 0 | 74.49 | North 24 Pgs W/S Division I |  | 69.88 | 0 | 0 | 0 | 69.88 | 69.88 | 0 | 0 | 0 | 69.88 | 93.81 | 98
348 | NORTH 24 PARAGANAS | SM/07609 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006924 | 8171564 | Retrofitting | MVS | GO2021004101PH | 05/01/2021 | 53.91 | 0 | 53.91 | North 24 Pgs W/S Division I |  | 52.01 | 0 | 0 | 0 | 52.01 | 52.01 | 0 | 0 | 0 | 52.01 | 96.48 | 90
349 | NORTH 24 PARAGANAS | SM/07602 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006915 | 8162380 | Retrofitting | SVS | GO2021004110PH | 05/01/2021 | 94.17 | 0 | 94.17 | North 24 Pgs W/S Division I |  | 93.02 | 0 | 0 | 0 | 93.02 | 93.02 | 0 | 0 | 0 | 93.02 | 98.77 | 98
350 | NORTH 24 PARAGANAS | SM/08732 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). | TSM/007650 | 8382831 | Retrofitting | SVS | GO2122003145PH | 09/09/2021 | 91.82 | 0 | 91.82 | North 24 Pgs W/S Division I |  | 89.14 | 0 | 0 | 0 | 89.14 | 89.14 | 0 | 0 | 0 | 89.14 | 97.08 | 98
351 | NORTH 24 PARAGANAS | SM/10510 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010490 | 7941357 | Retrofitting | SVS | GO2223000242PH | 13/04/2022 | 371.96 | 0 | 371.96 | Barasat Division |  | 322.46 | 0 | 0 | 0 | 322.46 | 322.46 | 0 | 0 | 0 | 322.46 | 86.69 | 74
352 | NORTH 24 PARAGANAS | SM/08042 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chandpur Water Supply Scheme at Bagdah Block under (Phase-I) | TSM/007085 | 1723303 | Retrofitting | MVS | GO2021005933PH | 01/02/2021 | 75.47 | 0 | 75.47 | North 24 Pgs W/S Division I |  | 70.66 | 0 | 0 | 0 | 70.66 | 70.66 | 0 | 0 | 0 | 70.66 | 93.63 | 98
353 | NORTH 24 PARAGANAS | SM/10509 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010493 | 7941420 | Retrofitting | MVS | GO2223000243PH | 13/04/2022 | 749.52 | 0 | 749.52 | Barasat Division |  | 727.69 | 0 | 0 | 0 | 727.69 | 727.69 | 0 | 0 | 0 | 727.69 | 97.09 | 100
354 | NORTH 24 PARAGANAS | SM/10503 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010486 | 7941315 | Retrofitting | SVS | GO2223000234PH | 13/04/2022 | 393.8 | 0 | 393.8 | Barasat Division |  | 180.98 | 0 | 0 | 0 | 180.98 | 180.98 | 0 | 0 | 0 | 180.98 | 45.96 | 43
355 | NORTH 24 PARAGANAS | SM/07599 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006919 | 8162467 | Retrofitting | MVS | GO2021004106PH | 05/01/2021 | 70.98 | 0 | 70.98 | North 24 Pgs W/S Division I |  | 68.17 | 0 | 0 | 0 | 68.17 | 67.12 | 0 | 0 | 0 | 67.12 | 94.56 | 98
356 | NORTH 24 PARAGANAS | SM/08048 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dighari Water Supply Scheme at Bongaon Block (Phase-II). | TSM/007083 | 8360116 | Retrofitting | MVS | GO2021005939PH | 01/02/2021 | 62.67 | 0 | 62.67 | North 24 Pgs W/S Division I |  | 60 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 95.75 | 98
357 | NORTH 24 PARAGANAS | SM/08730 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gainpur Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. | TSM/007651 | 8382848 | Retrofitting | MVS | GO2122003145PH | 09/09/2021 | 53.55 | 0 | 53.55 | North 24 Pgs W/S Division I |  | 48.08 | 0 | 0 | 0 | 48.08 | 48.08 | 0 | 0 | 0 | 48.08 | 89.78 | 98
358 | NORTH 24 PARAGANAS | SM/07601 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006918 | 8162489 | Retrofitting | MVS | GO2021004107PH | 05/01/2021 | 85.45 | 0 | 85.45 | North 24 Pgs W/S Division I |  | 80.99 | 0 | 0 | 0 | 80.99 | 80.99 | 0 | 0 | 0 | 80.99 | 94.77 | 98
359 | NORTH 24 PARAGANAS | SM/10504 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | TSM/010488 | 7941531 | Retrofitting | SVS | GO2223000232PH | 13/04/2022 | 324.12 | 0 | 324.12 | Barasat Division |  | 151.84 | 0 | 0 | 0 | 151.84 | 151.84 | 0 | 0 | 0 | 151.84 | 46.85 | 100
360 | NORTH 24 PARAGANAS | SM/10505 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010489 | 40062817 | Retrofitting | SVS | GO2223000248PH | 13/04/2022 | 404.01 | 0 | 404.01 | Barasat Division |  | 237.86 | 0 | 0 | 0 | 237.86 | 237.86 | 0 | 0 | 0 | 237.86 | 58.88 | 100
361 | NORTH 24 PARAGANAS | SM/10501 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Joy Gaopalpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010431 | 7941370 | Retrofitting | MVS | GO2223000238PH | 13/04/2022 | 570.78 | 0 | 570.78 | Barasat Division |  | 213.07 | 0 | 0 | 0 | 213.07 | 213.07 | 0 | 0 | 0 | 213.07 | 37.33 | 100
362 | NORTH 24 PARAGANAS | SM/10507 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | TSM/010494 | 7940727 | Retrofitting | MVS | GO2223000231PH | 13/04/2022 | 619.21 | 0 | 619.21 | Barasat Division |  | 451.65 | 0 | 0 | 0 | 451.65 | 451.65 | 0 | 0 | 0 | 451.65 | 72.94 | 100
363 | NORTH 24 PARAGANAS | SM/10508 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | TSM/010495 | 7940727 | Retrofitting | MVS | GO2223000233PH | 13/04/2022 | 455.09 | 0 | 455.09 | Barasat Division |  | 380.33 | 0 | 0 | 0 | 380.33 | 380.33 | 0 | 0 | 0 | 380.33 | 83.57 | 47
364 | NORTH 24 PARAGANAS | SM/07600 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006920 | 8162444 | Retrofitting | MVS | GO2021004105PH | 05/01/2021 | 92.84 | 0 | 92.84 | North 24 Pgs W/S Division I |  | 91.12 | 0 | 0 | 0 | 91.12 | 91.12 | 0 | 0 | 0 | 91.12 | 98.14 | 98
365 | NORTH 24 PARAGANAS | SM/10506 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | TSM/010492 | 7941386 | Retrofitting | MVS | GO2223000241PH | 13/04/2022 | 603.79 | 0 | 603.79 | Barasat Division |  | 420.4 | 0 | 35.12 | 0 | 455.52 | 420.4 | 0 | 35.12 | 0 | 455.52 | 75.44 | 82
366 | NORTH 24 PARAGANAS | SM/08731 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). | TSM/007652 | 8390602 | Retrofitting | MVS | GO2122003145PH | 09/09/2021 | 99.33 | 0 | 99.33 | North 24 Pgs W/S Division I |  | 93.41 | 0 | 0 | 0 | 93.41 | 93.37 | 0 | 0 | 0 | 93.37 | 93.99 | 98
367 | NORTH 24 PARAGANAS | SM/07603 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006917 | 8162510 | Retrofitting | SVS | GO2021004108PH | 05/01/2021 | 69.29 | 0 | 69.29 | North 24 Pgs W/S Division I |  | 64.5 | 0 | 0 | 0 | 64.5 | 64.5 | 0 | 0 | 0 | 64.5 | 93.09 | 98
368 | NORTH 24 PARAGANAS | SM/08043 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Paikpara Water Supply Scheme at Bongaon Block (Phase-II). | TSM/007082 | 8360028 | Retrofitting | SVS | GO2021005934PH | 01/02/2021 | 99.82 | 0 | 99.82 | North 24 Pgs W/S Division I |  | 80.06 | 0 | 0 | 0 | 80.06 | 80.06 | 0 | 0 | 0 | 80.06 | 80.2 | 98
369 | NORTH 24 PARAGANAS | SM/08047 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Palla Water Supply Scheme at Bongaon Block (Phase-I) | TSM/007048 | 8360039 | Retrofitting | MVS | GO2021005940PH | 01/02/2021 | 73.37 | 0 | 73.37 | North 24 Pgs W/S Division I |  | 69.5 | 0 | 0 | 0 | 69.5 | 69.5 | 0 | 0 | 0 | 69.5 | 94.73 | 98
370 | NORTH 24 PARAGANAS | SM/08041 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). | TSM/007086 | 8369696 | Retrofitting | SVS | GO2021005946PH | 01/02/2021 | 89.3 | 0 | 89.3 | North 24 Pgs W/S Division I |  | 88.6 | 0 | 0 | 0 | 88.6 | 88.41 | 0 | 0 | 0 | 88.41 | 99 | 98
371 | NORTH 24 PARAGANAS | SM/07606 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006921 | 8171645 | Retrofitting | MVS | GO2021004104PH | 05/01/2021 | 40.1 | 0 | 40.1 | North 24 Pgs W/S Division I |  | 37.28 | 0 | 0 | 0 | 37.28 | 37.28 | 0 | 0 | 0 | 37.28 | 92.95 | 98
372 | NORTH 24 PARAGANAS | SM/10511 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010487 | 7940537 | Retrofitting | MVS | GO2223000240PH | 13/04/2022 | 464.15 | 0 | 464.15 | Barasat Division |  | 417.23 | 0 | 0 | 0 | 417.23 | 417.23 | 0 | 0 | 0 | 417.23 | 89.89 | 88
373 | NORTH 24 PARAGANAS | SM/07607 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006922 | 8171666 | Retrofitting | SVS | GO2021004103PH | 05/01/2021 | 65.75 | 0 | 65.75 | North 24 Pgs W/S Division I |  | 63.46 | 0 | 0 | 0 | 63.46 | 63.46 | 0 | 0 | 0 | 63.46 | 96.51 | 98
374 | NORTH 24 PARAGANAS | SM/07604 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) | TSM/006916 | 8171608 | Retrofitting | MVS | GO2021004109PH | 05/01/2021 | 56.87 | 0 | 56.87 | North 24 Pgs W/S Division I |  | 55.28 | 0 | 0 | 0 | 55.28 | 55.28 | 0 | 0 | 0 | 55.28 | 97.2 | 98
375 | NORTH 24 PARAGANAS | SM/10502 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010485 | 7940547 | Retrofitting | SVS | GO2223000239PH | 13/04/2022 | 329.73 | 0 | 329.73 | Barasat Division |  | 197.21 | 0 | 0 | 0 | 197.21 | 197.21 | 0 | 0 | 0 | 197.21 | 59.81 | 48
376 | NORTH 24 PARAGANAS | SM/08040 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North | TSM/007090 | 8360101 | Retrofitting | MVS | GO2021005945PH | 01/02/2021 | 84.03 | 0 | 84.03 | North 24 Pgs W/S Division I |  | 73.38 | 0 | 0 | 0 | 73.38 | 73.38 | 0 | 0 | 0 | 73.38 | 87.33 | 98
377 | NORTH 24 PARAGANAS | SM/08046 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under (Phase-I) for Arsenic affected areas of North 2 | TSM/007088 | 8360080 | Retrofitting | MVS | GO2021005942PH | 01/02/2021 | 94.8 | 0 | 94.8 | North 24 Pgs W/S Division I |  | 78.29 | 0 | 0 | 0 | 78.29 | 78.29 | 0 | 0 | 0 | 78.29 | 82.59 | 98
378 | NORTH 24 PARAGANAS | SM/08045 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-VIII) at Kanchiara OHR site under (Phase-I) for Arsenic affected areas of N | TSM/007089 | 8360061 | Retrofitting | MVS | GO2021005943PH | 01/02/2021 | 93.98 | 0 | 93.98 | North 24 Pgs W/S Division I |  | 68.34 | 0 | 0 | 0 | 68.34 | 68.34 | 0 | 0 | 0 | 68.34 | 72.72 | 98
379 | NORTH 24 PARAGANAS | SM/08049 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme for Arsenic affected areas at Deganga Block of North 24 Parganas | TSM/007087 | 8360132 | Retrofitting | MVS | GO2021005936PH | 01/02/2021 | 99.22 | 0 | 99.22 | North 24 Pgs W/S Division I |  | 86.14 | 0 | 0 | 0 | 86.14 | 86.14 | 0 | 0 | 0 | 86.14 | 86.82 | 100
380 | NORTH 24 PARAGANAS | SM/10550 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | TSM/010491 | 7941326 | Retrofitting | SVS | GO2223000336PH | 18/04/2022 | 448.57 | 0 | 448.57 | Barasat Division |  | 164.74 | 0 | 0 | 0 | 164.74 | 164.74 | 0 | 0 | 0 | 164.74 | 36.73 | 79
381 | NORTH 24 PARAGANAS | SM/13534 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas D | TSM/011515 | 40033300 | Retrofitting | MVS | GO2223009351PH | 04/11/2022 | 621.18 | 0 | 621.18 | Barasat Division |  | 113.88 | 0 | 0 | 0 | 113.88 | 113.88 | 0 | 0 | 0 | 113.88 | 18.33 | 20
382 | NORTH 24 PARAGANAS | SM/14542 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011507 | 40033315 | Retrofitting | MVS | GO2223012583PH | 30/01/2023 | 1138.26 | 0 | 1138.26 | Barasat Division |  | 0 | 0 | 123.26 | 0 | 123.26 | 0 | 0 | 123.26 | 0 | 123.26 | 10.83 | 0
383 | NORTH 24 PARAGANAS | SM/13543 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011559 | 40033303 | Retrofitting | MVS | GO2223009352PH | 04/11/2022 | 720.77 | 0 | 720.77 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
384 | NORTH 24 PARAGANAS | SM/13521 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011549 | 40033156 | Retrofitting | MVS | GO2223009357PH | 04/11/2022 | 961.66 | 0 | 961.66 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | NORTH 24 PARAGANAS | SM/13538 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011496 | 40033266 | Retrofitting | MVS | GO2223009331PH | 04/11/2022 | 863.74 | 0 | 863.74 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | NORTH 24 PARAGANAS | SM/14543 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011488 | 40033169 | Retrofitting | MVS | GO2223012587PH | 30/01/2023 | 1059.55 | 0 | 1059.55 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | NORTH 24 PARAGANAS | SM/14540 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011513 | 40033316 | Retrofitting | MVS | GO2223012586PH | 30/01/2023 | 1050.88 | 0 | 1050.88 | Barasat Division |  | 86.1 | 0 | 0 | 0 | 86.1 | 86.1 | 0 | 0 | 0 | 86.1 | 8.19 | 10
388 | NORTH 24 PARAGANAS | SM/15823 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011565 | 40033310 | Retrofitting | MVS | GO2223014392PH | 20/02/2023 | 1006.41 | 0 | 1006.41 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | NORTH 24 PARAGANAS | SM/13537 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011508 | 40033262 | Retrofitting | MVS | GO2223009334PH | 04/11/2022 | 660.09 | 0 | 660.09 | Barasat Division |  | 0 | 0 | 78.14 | 0 | 78.14 | 0 | 0 | 78.14 | 0 | 78.14 | 11.84 | 0
390 | NORTH 24 PARAGANAS | SM/14539 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011541 | 40033271 | Retrofitting | MVS | GO2223012584PH | 30/01/2023 | 1034.29 | 0 | 1034.29 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | NORTH 24 PARAGANAS | SM/13544 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011557 | 40063440 | Retrofitting | MVS | GO2223009356PH | 04/11/2022 | 580.6 | 0 | 580.6 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | NORTH 24 PARAGANAS | SM/15824 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011543 | 40033313 | Retrofitting | MVS | GO2223014396PH | 20/02/2023 | 1037.4 | 0 | 1037.4 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | NORTH 24 PARAGANAS | SM/13532 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011517 | 40033273 | Retrofitting | MVS | GO2223009341PH | 04/11/2022 | 683.5 | 0 | 683.5 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
394 | NORTH 24 PARAGANAS | SM/13545 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011560 | 40033304 | Retrofitting | MVS | GO2223009355PH | 04/11/2022 | 652.34 | 0 | 652.34 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
395 | NORTH 24 PARAGANAS | SM/14541 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District | TSM/011509 | 40033312 | Retrofitting | MVS | GO2223012585PH | 30/01/2023 | 1061.62 | 0 | 1061.62 | Barasat Division |  | 0 | 0 | 126.15 | 0 | 126.15 | 0 | 0 | 126.15 | 0 | 126.15 | 11.88 | 0
396 | NORTH 24 PARAGANAS | SM/13535 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje | TSM/011511 | 40033301 | Retrofitting | MVS | GO2223009339PH | 04/11/2022 | 960.53 | 0 | 960.53 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | NORTH 24 PARAGANAS | SM/13533 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje | TSM/011516 | 40033163 | Retrofitting | MVS | GO2223009340PH | 04/11/2022 | 653.74 | 0 | 653.74 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | NORTH 24 PARAGANAS | SM/08771 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur mouza (rest part after Phase-I) & Bakpukhuria mouza of Akipur Piped Water Supply Scheme, Basirhat-II Block under B | TSM/007356 | 40001052 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 60.85 | 0 | 60.85 | Barasat Division |  | 53.25 | 0 | 0 | 0 | 53.25 | 53.25 | 0 | 0 | 0 | 53.25 | 87.52 | 100
399 | NORTH 24 PARAGANAS | SM/07613 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | TSM/006778 | 8161491 | Retrofitting | SVS | GO2021004090PH | 05/01/2021 | 60.66 | 0 | 60.66 | Barasat Division |  | 49.84 | 0 | 4.93 | 0 | 54.77 | 49.84 | 0 | 4.93 | 0 | 54.77 | 90.29 | 100
400 | NORTH 24 PARAGANAS | SM/07623 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme (Phase-I) | TSM/006788 | 8163035 | Retrofitting | MVS | GO2021004099PH | 05/01/2021 | 50.43 | 0 | 50.43 | Barasat Division |  | 50.39 | 0 | 0 | 0 | 50.39 | 50.39 | 0 | 0 | 0 | 50.39 | 99.92 | 100
401 | NORTH 24 PARAGANAS | SM/07619 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | TSM/006789 | 8162134 | Retrofitting | SVS | GO2021004096PH | 05/01/2021 | 25.19 | 0 | 25.19 | Barasat Division |  | 17.69 | 0 | 2.09 | 0 | 19.78 | 17.69 | 0 | 2.09 | 0 | 19.78 | 78.52 | 100
402 | NORTH 24 PARAGANAS | SM/08261 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) | TSM/007369 | 40001095 | Retrofitting | SVS | GO2021007427PH | 22/02/2021 | 97.54 | 0 | 97.54 | Barasat Division |  | 97.54 | 0 | 0 | 0 | 97.54 | 97.54 | 0 | 0 | 0 | 97.54 | 100 | 100
403 | NORTH 24 PARAGANAS | SM/08644 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) | TSM/007615 | 40000422 | Retrofitting | MVS | GO2122001206PH | 18/06/2021 | 291.24 | 0 | 291.24 | Barasat Division |  | 184.73 | 0 | 0 | 0 | 184.73 | 184.73 | 0 | 0 | 0 | 184.73 | 63.43 | 100
404 | NORTH 24 PARAGANAS | SM/08654 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-II) Piped Water Supply Scheme at Baduria Block (Phase-I) | TSM/007660 | 40000423 | Retrofitting | SVS | GO2122001221 PH | 18/06/2021 | 154.44 | 0 | 154.44 | Barasat Division |  | 118.07 | 0 | 0 | 0 | 118.07 | 118.07 | 0 | 0 | 0 | 118.07 | 76.45 | 100
405 | NORTH 24 PARAGANAS | SM/08763 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | TSM/007372 | 40004729 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 98.97 | 0 | 98.97 | Barasat Division |  | 95.81 | 0 | 0 | 0 | 95.81 | 95.81 | 0 | 0 | 0 | 95.81 | 96.81 | 100
406 | NORTH 24 PARAGANAS | SM/08775 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) | TSM/007619 | 40001102 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 210.37 | 0 | 210.37 | Barasat Division |  | 160.7 | 0 | 0 | 0 | 160.7 | 144.05 | 0 | 0 | 0 | 144.05 | 68.47 | 100
407 | NORTH 24 PARAGANAS | SM/07610 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | TSM/006775 | 7044616 | Retrofitting | SVS | GO2021004085PH | 05/01/2021 | 223.92 | 0 | 223.92 | Barasat Division |  | 141.89 | 0 | 81.93 | 0 | 223.82 | 139.07 | 0 | 81.93 | 0 | 221 | 98.69 | 100
408 | NORTH 24 PARAGANAS | SM/08782 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) | TSM/007607 | 40002105 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 238.36 | 0 | 238.36 | Barasat Division |  | 159.85 | 0 | 0 | 0 | 159.85 | 159.85 | 0 | 0 | 0 | 159.85 | 67.06 | 0
409 | NORTH 24 PARAGANAS | SM/07851 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | TSM/006763 | 8195102 | Retrofitting | MVS | GO2021004563PH | 14/01/2021 | 84.15 | 0 | 84.15 | Barasat Division |  | 81.55 | 0 | 0 | 0 | 81.55 | 81.55 | 0 | 0 | 0 | 81.55 | 96.92 | 100
410 | NORTH 24 PARAGANAS | SM/08072 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | TSM/007046 | 8195102 | Retrofitting | SVS | GO2021006220PH | 04/02/2021 | 68.38 | 0 | 68.38 | Barasat Division |  | 51.98 | 0 | 0 | 0 | 51.98 | 51.98 | 0 | 0 | 0 | 51.98 | 76.02 | 100
411 | NORTH 24 PARAGANAS | SM/08766 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | TSM/007373 | 40001072 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 98.79 | 0 | 98.79 | Barasat Division |  | 82.24 | 0 | 0 | 0 | 82.24 | 82.24 | 0 | 0 | 0 | 82.24 | 83.25 | 100
412 | NORTH 24 PARAGANAS | SM/08260 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) | TSM/007366 | 40000999 | Retrofitting | MVS | GO2021007415PH | 22/02/2021 | 99.12 | 0 | 99.12 | Barasat Division |  | 85.6 | 0 | 13.49 | 0 | 99.09 | 85.6 | 0 | 13.49 | 0 | 99.09 | 99.97 | 100
413 | NORTH 24 PARAGANAS | SM/08269 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) | TSM/007378 | 40008828 | Retrofitting | MVS | GO2021007421PH | 22/02/2021 | 230.73 | 0 | 230.73 | Barasat Division |  | 199.02 | 0 | 15.09 | 0 | 214.11 | 198.93 | 0 | 15.09 | 0 | 214.02 | 92.76 | 100
414 | NORTH 24 PARAGANAS | SM/08073 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | TSM/007041 | 40060612 | Retrofitting | MVS | GO2021006236PH | 04/02/2021 | 216.27 | 0 | 216.27 | Barasat Division |  | 207.45 | 0 | 0 | 0 | 207.45 | 196.15 | 0 | 0 | 0 | 196.15 | 90.7 | 100
415 | NORTH 24 PARAGANAS | SM/08768 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Piped Water Supply Scheme, Basirhat-I Block under Barasat Division, P.H.E.Dte. (Phase-II) | TSM/007345 | 40000969 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 17 | 0 | 17 | Barasat Division |  | 16 | 0 | 0 | 0 | 16 | 14.77 | 0 | 0 | 0 | 14.77 | 86.89 | 100
416 | NORTH 24 PARAGANAS | SM/07845 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) | TSM/006765 | 8218578 | Retrofitting | SVS | GO2021004561PH | 14/01/2021 | 22.88 | 0 | 22.88 | Barasat Division |  | 21.16 | 0 | 0 | 0 | 21.16 | 21.16 | 0 | 0 | 0 | 21.16 | 92.5 | 100
417 | NORTH 24 PARAGANAS | SM/08773 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su | TSM/007631 | 40000354 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 296.54 | 0 | 296.54 | Barasat Division |  | 228.64 | 0 | 0 | 0 | 228.64 | 228.6 | 0 | 0 | 0 | 228.6 | 77.09 | 100
418 | NORTH 24 PARAGANAS | SM/07844 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-I) | TSM/006777 | 8218652 | Retrofitting | SVS | GO2021004550PH | 14/01/2021 | 50.79 | 0 | 50.79 | Barasat Division |  | 46.68 | 0 | 0 | 0 | 46.68 | 46.68 | 0 | 0 | 0 | 46.68 | 91.91 | 100
419 | NORTH 24 PARAGANAS | SM/07618 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-II) | TSM/006786 | 8162107 | Retrofitting | SVS | GO2021004095PH | 05/01/2021 | 22.12 | 0 | 22.12 | Barasat Division |  | 21.23 | 0 | 0 | 0 | 21.23 | 21.23 | 0 | 0 | 0 | 21.23 | 95.96 | 100
420 | NORTH 24 PARAGANAS | SM/07846 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-I) | TSM/006769 | 8197284 | Retrofitting | SVS | GO2021004557PH | 14/01/2021 | 44.61 | 0 | 44.61 | Barasat Division |  | 44.33 | 0 | 0 | 0 | 44.33 | 44.33 | 0 | 0 | 0 | 44.33 | 99.37 | 100
421 | NORTH 24 PARAGANAS | SM/08066 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-II) | TSM/007034 | 8195389 | Retrofitting | SVS | GO2021006233PH | 04/02/2021 | 6.6 | 0 | 6.6 | Barasat Division |  | 6.31 | 0 | 0 | 0 | 6.31 | 6.31 | 0 | 0 | 0 | 6.31 | 95.58 | 100
422 | NORTH 24 PARAGANAS | SM/08070 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Diara Water Supply Scheme at Bagdah Block (Phase-I) | TSM/007040 | 8195469 | Retrofitting | MVS | GO2021006222PH | 04/02/2021 | 26.81 | 0 | 26.81 | Barasat Division |  | 22.46 | 0 | 0 | 0 | 22.46 | 22.46 | 0 | 0 | 0 | 22.46 | 83.77 | 100
423 | NORTH 24 PARAGANAS | SM/08769 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) | TSM/007347 | 40019989 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 17.35 | 0 | 17.35 | Barasat Division |  | 14 | 0 | 0 | 0 | 14 | 13.84 | 0 | 0 | 0 | 13.84 | 79.76 | 100
424 | NORTH 24 PARAGANAS | SM/07854 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Water Supply Scheme at Swarupnagar Block (Phase-I) | TSM/006771 | 8196996 | Retrofitting | SVS | GO2021004555PH | 14/01/2021 | 24.84 | 0 | 24.84 | Barasat Division |  | 22.53 | 0 | 0 | 0 | 22.53 | 22.53 | 0 | 0 | 0 | 22.53 | 90.71 | 100
425 | NORTH 24 PARAGANAS | SM/08764 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | TSM/007371 | 40001000 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 99.01 | 0 | 99.01 | Barasat Division |  | 78.57 | 0 | 0 | 0 | 78.57 | 78.57 | 0 | 0 | 0 | 78.57 | 79.36 | 100
426 | NORTH 24 PARAGANAS | SM/08765 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) | TSM/007367 | 40004890 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 99.39 | 0 | 99.39 | Barasat Division |  | 82.49 | 0 | 0 | 0 | 82.49 | 82.49 | 0 | 0 | 0 | 82.49 | 83 | 100
427 | NORTH 24 PARAGANAS | SM/08256 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | TSM/007343 | 8218686 | Retrofitting | SVS | GO2021007419PH | 22/02/2021 | 97.57 | 0 | 97.57 | Barasat Division |  | 75.76 | 0 | 0 | 0 | 75.76 | 75.76 | 0 | 0 | 0 | 75.76 | 77.65 | 100
428 | NORTH 24 PARAGANAS | SM/08777 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | TSM/007616 | 40000417 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 164.51 | 0 | 164.51 | Barasat Division |  | 141.79 | 0 | 0 | 0 | 141.79 | 140.88 | 0 | 0 | 0 | 140.88 | 85.64 | 0
429 | NORTH 24 PARAGANAS | SM/08264 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) | TSM/007364 | 8215266 | Retrofitting | MVS | GO2021007425PH | 22/02/2021 | 177.55 | 0 | 177.55 | Barasat Division |  | 170.7 | 0 | 0 | 0 | 170.7 | 170.7 | 0 | 0 | 0 | 170.7 | 96.14 | 100
430 | NORTH 24 PARAGANAS | SM/08268 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ghatpatila (Zone-I) Piped Water Supply Scheme, Bagdah Block (Phase-I) | TSM/007375 | 40006021 | Retrofitting | MVS | GO2021007422PH | 22/02/2021 | 132.23 | 0 | 132.23 | Barasat Division |  | 116.57 | 0 | 0 | 0 | 116.57 | 116.57 | 0 | 0 | 0 | 116.57 | 88.16 | 100
431 | NORTH 24 PARAGANAS | SM/07850 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-I) | TSM/006773 | 8197206 | Retrofitting | MVS | GO2021004553PH | 14/01/2021 | 97.77 | 0 | 97.77 | Barasat Division |  | 93.32 | 0 | 0 | 0 | 93.32 | 93.32 | 0 | 0 | 0 | 93.32 | 95.45 | 100
432 | NORTH 24 PARAGANAS | SM/07624 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-II) | TSM/006783 | 8163033 | Retrofitting | SVS | GO2021004100PH | 05/01/2021 | 67.83 | 0 | 67.83 | Barasat Division |  | 63.12 | 0 | 3.12 | 0 | 66.23 | 63.12 | 0 | 3.12 | 0 | 66.23 | 97.64 | 100
433 | NORTH 24 PARAGANAS | SM/08076 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- | TSM/007035 | 40006137 | Retrofitting | MVS | GO2021006226PH | 04/02/2021 | 144.46 | 0 | 144.46 | Barasat Division |  | 88.81 | 0 | 0 | 0 | 88.81 | 88.81 | 0 | 0 | 0 | 88.81 | 61.48 | 100
434 | NORTH 24 PARAGANAS | SM/08067 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-I) | TSM/007036 | 8195452 | Retrofitting | MVS | GO2021006228PH | 04/02/2021 | 135.21 | 0 | 135.21 | Barasat Division |  | 123.31 | 0 | 0 | 0 | 123.31 | 123.31 | 0 | 0 | 0 | 123.31 | 91.2 | 100
435 | NORTH 24 PARAGANAS | SM/08068 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) | TSM/007037 | 8195431 | Retrofitting | MVS | GO2021006231PH | 04/02/2021 | 87.78 | 0 | 87.78 | Barasat Division |  | 84.25 | 0 | 0 | 0 | 84.25 | 84.25 | 0 | 0 | 0 | 84.25 | 95.99 | 100
436 | NORTH 24 PARAGANAS | SM/07847 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-I) | TSM/006768 | 8197256 | Retrofitting | SVS | GO2021004558PH | 14/01/2021 | 37.68 | 0 | 37.68 | Barasat Division |  | 35.25 | 0 | 0 | 0 | 35.25 | 35.25 | 0 | 0 | 0 | 35.25 | 93.53 | 100
437 | NORTH 24 PARAGANAS | SM/08071 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-II) | TSM/007039 | 8195417 | Retrofitting | SVS | GO2021006232PH | 04/02/2021 | 14.47 | 0 | 14.47 | Barasat Division |  | 14 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 14 | 96.74 | 100
438 | NORTH 24 PARAGANAS | SM/08263 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) | TSM/007361 | 8215280 | Retrofitting | MVS | GO2021007428PH | 22/02/2021 | 193.64 | 0 | 193.64 | Barasat Division |  | 187.05 | 0 | 0 | 0 | 187.05 | 187.05 | 0 | 0 | 0 | 187.05 | 96.6 | 100
439 | NORTH 24 PARAGANAS | SM/09224 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block | TSM/007044 | 7349442 | Retrofitting | MVS | GO2122004775PH | 01/11/2021 | 589.31 | 0 | 589.31 | Barasat Division |  | 531.29 | 0 | 30.8 | 0 | 562.09 | 531.29 | 0 | 30.8 | 0 | 562.09 | 95.38 | 91
440 | NORTH 24 PARAGANAS | SM/09225 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block | TSM/007045 | 7349442 | Retrofitting | MVS | GO2122004775PH | 01/11/2021 | 419.92 | 0 | 419.92 | Barasat Division |  | 251.66 | 0 | 152.24 | 0 | 403.9 | 248.21 | 0 | 152.24 | 0 | 400.45 | 95.36 | 100
441 | NORTH 24 PARAGANAS | SM/07842 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | TSM/006770 | 8195514 | Retrofitting | SVS | GO2021004556PH | 14/01/2021 | 92.43 | 0 | 92.43 | Barasat Division |  | 50.44 | 0 | 0 | 0 | 50.44 | 50.44 | 0 | 0 | 0 | 50.44 | 54.57 | 0
442 | NORTH 24 PARAGANAS | SM/08270 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ichhapur Piped Water Supply Scheme, Gaighata Block (Phase-I) | TSM/007376 | 40005891 | Retrofitting | MVS | GO2021007420PH | 22/02/2021 | 145.34 | 0 | 145.34 | Barasat Division |  | 125.26 | 0 | 15.1 | 0 | 140.36 | 125.26 | 0 | 15.1 | 0 | 140.36 | 96.57 | 100
443 | NORTH 24 PARAGANAS | SM/08786 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) | TSM/007636 | 40002096 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 197.7 | 0 | 197.7 | Barasat Division |  | 169.43 | 0 | 0 | 0 | 169.43 | 169.43 | 0 | 0 | 0 | 169.43 | 85.7 | 100
444 | NORTH 24 PARAGANAS | SM/08652 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Jadavpur, Khanpur, Odhanpur, Kumarpur, Fazilpur, Rampur & Sohai mouzas (Part) within Sohai Swetpur Zone-II Piped Water Sup | TSM/007630 | 40001069 | Retrofitting | MVS | GO2122001218PH | 18/06/2021 | 276.49 | 0 | 276.49 | Barasat Division |  | 225.94 | 0 | 0 | 0 | 225.94 | 225.09 | 0 | 0 | 0 | 225.09 | 81.41 | 100
445 | NORTH 24 PARAGANAS | SM/08780 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) | TSM/007610 | 40000926 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 91.28 | 0 | 91.28 | Barasat Division |  | 87.13 | 0 | 0 | 0 | 87.13 | 80.15 | 0 | 0 | 0 | 80.15 | 87.81 | 75
446 | NORTH 24 PARAGANAS | SM/08772 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) | TSM/007352 | 40003684 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 25.42 | 0 | 25.42 | Barasat Division |  | 22 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 22 | 86.56 | 100
447 | NORTH 24 PARAGANAS | SM/07853 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Water Supply Scheme at Basirhat-II Block (Phase-I) | TSM/006772 | 8197043 | Retrofitting | SVS | GO2021004554PH | 14/01/2021 | 50.97 | 0 | 50.97 | Barasat Division |  | 49.14 | 0 | 0 | 0 | 49.14 | 49.14 | 0 | 0 | 0 | 49.14 | 96.4 | 100
448 | NORTH 24 PARAGANAS | SM/08660 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | TSM/007645 | 40001058 | Retrofitting | MVS | GO2122001215PH | 18/06/2021 | 100.06 | 0 | 100.06 | Barasat Division |  | 89.71 | 0 | 0 | 0 | 89.71 | 89.71 | 0 | 0 | 0 | 89.71 | 89.66 | 100
449 | NORTH 24 PARAGANAS | SM/08257 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | TSM/007358 | 40003859 | Retrofitting | MVS | GO2021007418PH | 22/02/2021 | 98.87 | 0 | 98.87 | Barasat Division |  | 98.87 | 0 | 0 | 0 | 98.87 | 98 | 0 | 0 | 0 | 98 | 99.12 | 100
450 | NORTH 24 PARAGANAS | SM/08774 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | TSM/007621 | 40000998 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 79.82 | 0 | 79.82 | Barasat Division |  | 59.46 | 0 | 0 | 0 | 59.46 | 59.46 | 0 | 0 | 0 | 59.46 | 74.5 | 100
451 | NORTH 24 PARAGANAS | SM/07849 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-I) | TSM/006774 | 8197107 | Retrofitting | MVS | GO2021004551PH | 14/01/2021 | 55.2 | 0 | 55.2 | Barasat Division |  | 50.83 | 0 | 0 | 0 | 50.83 | 50.83 | 0 | 0 | 0 | 50.83 | 92.09 | 100
452 | NORTH 24 PARAGANAS | SM/07620 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-II) | TSM/006787 | 8197107 | Retrofitting | SVS | GO2021004082PH | 05/01/2021 | 133.68 | 0 | 133.68 | Barasat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
453 | NORTH 24 PARAGANAS | SM/08783 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) | TSM/007625 | 40002784 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 108.98 | 0 | 108.98 | Barasat Division |  | 79.16 | 0 | 0 | 0 | 79.16 | 79.16 | 0 | 0 | 0 | 79.16 | 72.64 | 98
454 | NORTH 24 PARAGANAS | SM/08784 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) | TSM/007620 | 40002916 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 134.94 | 0 | 134.94 | Barasat Division |  | 101.91 | 0 | 0 | 0 | 101.91 | 100.33 | 0 | 0 | 0 | 100.33 | 74.35 | 97
455 | NORTH 24 PARAGANAS | SM/08762 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) | TSM/007357 | 40001001 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 98.91 | 0 | 98.91 | Barasat Division |  | 80.33 | 0 | 0 | 0 | 80.33 | 80.33 | 0 | 0 | 0 | 80.33 | 81.21 | 100
456 | NORTH 24 PARAGANAS | SM/08069 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kola Water Supply Scheme at Bagdah Block (Phase-I) | TSM/007038 | 8195355 | Retrofitting | SVS | GO2021006234PH | 04/02/2021 | 34.3 | 0 | 34.3 | Barasat Division |  | 32.91 | 0 | 1.23 | 0 | 34.14 | 32.91 | 0 | 1.23 | 0 | 34.14 | 99.52 | 100
457 | NORTH 24 PARAGANAS | SM/08267 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) | TSM/007379 | 40006000 | Retrofitting | SVS | GO2021007423PH | 22/02/2021 | 44.13 | 0 | 44.13 | Barasat Division |  | 41.99 | 0 | 0 | 0 | 41.99 | 41.99 | 0 | 0 | 0 | 41.99 | 95.16 | 100
458 | NORTH 24 PARAGANAS | SM/08761 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Korakati Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | TSM/007368 | 40001002 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 98.6 | 0 | 98.6 | Barasat Division |  | 78.54 | 0 | 0 | 0 | 78.54 | 78.54 | 0 | 0 | 0 | 78.54 | 79.65 | 100
459 | NORTH 24 PARAGANAS | SM/08265 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) | TSM/007360 | 8215183 | Retrofitting | MVS | GO2021007426PH | 22/02/2021 | 144.14 | 0 | 144.14 | Barasat Division |  | 116.03 | 0 | 0 | 0 | 116.03 | 116.03 | 0 | 0 | 0 | 116.03 | 80.5 | 100
460 | NORTH 24 PARAGANAS | SM/08653 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m | TSM/007627 | 40001068 | Retrofitting | MVS | GO2122001219PH | 18/06/2021 | 297.03 | 0 | 297.03 | Barasat Division |  | 246.54 | 0 | 0 | 0 | 246.54 | 230.87 | 0 | 0 | 0 | 230.87 | 77.73 | 100
461 | NORTH 24 PARAGANAS | SM/08770 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Piped Water Supply Scheme, Baduria Block under Barasat Division, P.H.E.Dte. (Phase-II) | TSM/007355 | 40001042 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 22.44 | 0 | 22.44 | Barasat Division |  | 21.3 | 0 | 0 | 0 | 21.3 | 21.27 | 0 | 0 | 0 | 21.27 | 94.8 | 100
462 | NORTH 24 PARAGANAS | SM/07843 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Water Supply Scheme at Baduria Block, Dist.-North 24 Parganas (Phase-I) | TSM/006766 | 8218635 | Retrofitting | SVS | GO2021004560PH | 14/01/2021 | 47.8 | 0 | 47.8 | Barasat Division |  | 42.22 | 0 | 0 | 0 | 42.22 | 42.22 | 0 | 0 | 0 | 42.22 | 88.33 | 100
463 | NORTH 24 PARAGANAS | SM/08258 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | TSM/007374 | 40000340 | Retrofitting | MVS | GO2021007417PH | 22/02/2021 | 98.58 | 0 | 98.58 | Barasat Division |  | 45.88 | 0 | 52.67 | 0 | 98.55 | 45.88 | 0 | 52.67 | 0 | 98.55 | 99.98 | 100
464 | NORTH 24 PARAGANAS | SM/08262 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) | TSM/007370 | 8215275 | Retrofitting | SVS | GO2021007429PH | 22/02/2021 | 79.42 | 0 | 79.42 | Barasat Division |  | 71.28 | 0 | 0 | 0 | 71.28 | 71.28 | 0 | 0 | 0 | 71.28 | 89.76 | 100
465 | NORTH 24 PARAGANAS | SM/08785 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) | TSM/007608 | 40001045 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 253.71 | 0 | 253.71 | Barasat Division |  | 210.09 | 0 | 0 | 0 | 210.09 | 210.09 | 0 | 0 | 0 | 210.09 | 82.81 | 100
466 | NORTH 24 PARAGANAS | SM/07848 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-I) | TSM/006767 | 8224819 | Retrofitting | MVS | GO2021004559PH | 14/01/2021 | 59.57 | 0 | 59.57 | Barasat Division |  | 56.38 | 0 | 0 | 0 | 56.38 | 56.38 | 0 | 0 | 0 | 56.38 | 94.65 | 100
467 | NORTH 24 PARAGANAS | SM/07616 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) | TSM/006784 | 8224841 | Retrofitting | MVS | GO2021004092PH | 05/01/2021 | 64.05 | 0 | 64.05 | Barasat Division |  | 62.18 | 0 | 1.85 | 0 | 64.03 | 59.65 | 0 | 1.85 | 0 | 61.5 | 96.02 | 100
468 | NORTH 24 PARAGANAS | SM/08778 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) | TSM/007612 | 40001070 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 139.9 | 0 | 139.9 | Barasat Division |  | 112.88 | 0 | 0 | 0 | 112.88 | 112.72 | 0 | 0 | 0 | 112.72 | 80.57 | 0
469 | NORTH 24 PARAGANAS | SM/08779 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) | TSM/007614 | 40001071 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 187.55 | 0 | 187.55 | Barasat Division |  | 142.71 | 0 | 0 | 0 | 142.71 | 142.59 | 0 | 0 | 0 | 142.59 | 76.03 | 0
470 | NORTH 24 PARAGANAS | SM/07621 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) | TSM/006790 | 8162308 | Retrofitting | SVS | GO2021004097PH | 05/01/2021 | 54.83 | 0 | 54.83 | Barasat Division |  | 51.58 | 0 | 0 | 0 | 51.58 | 51.58 | 0 | 0 | 0 | 51.58 | 94.07 | 100
471 | NORTH 24 PARAGANAS | SM/07622 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | TSM/006791 | 8163039 | Retrofitting | SVS | GO2021004098PH | 05/01/2021 | 32.21 | 0 | 32.21 | Barasat Division |  | 30.7 | 0 | 0 | 0 | 30.7 | 30.7 | 0 | 0 | 0 | 30.7 | 95.3 | 100
472 | NORTH 24 PARAGANAS | SM/08639 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | TSM/007613 | 40001061 | Retrofitting | MVS | GO2122001201PH | 18/06/2021 | 100.22 | 0 | 100.22 | Barasat Division |  | 87.19 | 0 | 0 | 0 | 87.19 | 87.19 | 0 | 0 | 0 | 87.19 | 87 | 100
473 | NORTH 24 PARAGANAS | SM/08259 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) | TSM/007365 | 40001029 | Retrofitting | MVS | GO2021007416PH | 22/02/2021 | 98.93 | 0 | 98.93 | Barasat Division |  | 84.1 | 0 | 0 | 0 | 84.1 | 84.1 | 0 | 0 | 0 | 84.1 | 85.01 | 100
474 | NORTH 24 PARAGANAS | SM/08657 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Raghunathpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | TSM/007617 | 8391007 | Retrofitting | MVS | GO2122001222PH | 18/06/2021 | 61.11 | 0 | 61.11 | Barasat Division |  | 51.21 | 0 | 0 | 0 | 51.21 | 51.21 | 0 | 0 | 0 | 51.21 | 83.81 | 100
475 | NORTH 24 PARAGANAS | SM/07611 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. | TSM/006776 | 7046695 | Retrofitting | SVS | GO2021004084PH | 05/01/2021 | 198.98 | 0 | 198.98 | Barasat Division |  | 97.51 | 0 | 0 | 0 | 97.51 | 97.51 | 0 | 0 | 0 | 97.51 | 49 | 100
476 | NORTH 24 PARAGANAS | SM/08074 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | TSM/007042 | 8195069 | Retrofitting | MVS | GO2021006218PH | 04/02/2021 | 226.61 | 0 | 226.61 | Barasat Division |  | 163.91 | 0 | 45 | 0 | 208.91 | 163.91 | 0 | 45 | 0 | 208.91 | 92.19 | 100
477 | NORTH 24 PARAGANAS | SM/08075 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-II) | TSM/007043 | 8195084 | Retrofitting | SVS | GO2021006217PH | 04/02/2021 | 163.43 | 0 | 163.43 | Barasat Division |  | 13.02 | 0 | 123.2 | 0 | 136.22 | 13.02 | 0 | 123.2 | 0 | 136.22 | 83.35 | 100
478 | NORTH 24 PARAGANAS | SM/07617 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | TSM/006780 | 8162382 | Retrofitting | MVS | GO2021004094PH | 05/01/2021 | 99.98 | 0 | 99.98 | Barasat Division |  | 86.98 | 0 | 3.7 | 0 | 90.67 | 86.6 | 0 | 3.7 | 0 | 90.29 | 90.32 | 100
479 | NORTH 24 PARAGANAS | SM/08781 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) | TSM/007609 | 40062869 | Retrofitting | SVS | GO2122003213PH | 13/09/2021 | 80.33 | 0 | 80.33 | Barasat Division |  | 37.9 | 0 | 0 | 0 | 37.9 | 37.9 | 0 | 0 | 0 | 37.9 | 47.18 | 66
480 | NORTH 24 PARAGANAS | SM/08266 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) | TSM/007377 | 8215141 | Retrofitting | MVS | GO2021007424PH | 22/02/2021 | 93.01 | 0 | 93.01 | Barasat Division |  | 85.22 | 0 | 0 | 0 | 85.22 | 85.22 | 0 | 0 | 0 | 85.22 | 91.62 | 100
481 | NORTH 24 PARAGANAS | SM/07852 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | TSM/006764 | 6904540 | Retrofitting | SVS | GO2021004562PH | 14/01/2021 | 57.27 | 0 | 57.27 | Barasat Division |  | 55.15 | 0 | 0 | 0 | 55.15 | 55.15 | 0 | 0 | 0 | 55.15 | 96.3 | 0
482 | NORTH 24 PARAGANAS | SM/07615 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) | TSM/006781 | 8161552 | Retrofitting | SVS | GO2021004087PH | 05/01/2021 | 67.21 | 0 | 67.21 | Barasat Division |  | 36.39 | 0 | 0 | 0 | 36.39 | 36.39 | 0 | 0 | 0 | 36.39 | 54.15 | 100
483 | NORTH 24 PARAGANAS | SM/07612 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | TSM/006782 | 8161535 | Retrofitting | SVS | GO2021004089PH | 05/01/2021 | 87.47 | 0 | 87.47 | Barasat Division |  | 78.39 | 0 | 0 | 0 | 78.39 | 78.39 | 0 | 0 | 0 | 78.39 | 89.62 | 100
484 | NORTH 24 PARAGANAS | SM/08776 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa Piped Water Supply Scheme at Habra-II Block (Phase-I) | TSM/007618 | 40006139 | Retrofitting | MVS | GO2122003213PH | 13/09/2021 | 91.53 | 0 | 91.53 | Barasat Division |  | 69.88 | 0 | 0 | 0 | 69.88 | 69.88 | 0 | 0 | 0 | 69.88 | 76.35 | 98
485 | NORTH 24 PARAGANAS | SM/08645 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) | TSM/007606 | 40001056 | Retrofitting | SVS | GO2122001207PH | 18/06/2021 | 100.07 | 0 | 100.07 | Barasat Division |  | 85.66 | 0 | 0 | 0 | 85.66 | 85.66 | 0 | 0 | 0 | 85.66 | 85.6 | 100
486 | NORTH 24 PARAGANAS | SM/07614 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) | TSM/006779 | 8161424 | Retrofitting | MVS | GO2021004091PH | 05/01/2021 | 99.79 | 0 | 99.79 | Barasat Division |  | 99.29 | 0 | 0 | 0 | 99.29 | 98.69 | 0 | 0 | 0 | 98.69 | 98.9 | 100
487 | NORTH 24 PARAGANAS | SM/08237 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Bangangram (Zone-II) Water SupplyScheme at Bongaon Block (Phase-II). | TSM/007283 | 8390619 | Retrofitting | SVS | GO2021007388PH | 22/02/2021 | 61.96 | 0 | 61.96 | North 24 Pgs W/S Division I |  | 52.35 | 0 | 0 | 0 | 52.35 | 50.74 | 0 | 0 | 0 | 50.74 | 81.89 | 98
488 | NORTH 24 PARAGANAS | SM/08239 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | TSM/007278 | 8382857 | Retrofitting | SVS | GO2021007392PH | 22/02/2021 | 92.02 | 0 | 92.02 | North 24 Pgs W/S Division I |  | 83.57 | 0 | 0 | 0 | 83.57 | 83.57 | 0 | 0 | 0 | 83.57 | 90.81 | 98
489 | NORTH 24 PARAGANAS | SM/08234 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). | TSM/007277 | 8382874 | Retrofitting | SVS | GO2021007394PH | 22/02/2021 | 57.5 | 0 | 57.5 | North 24 Pgs W/S Division I |  | 52.03 | 0 | 0 | 0 | 52.03 | 52.03 | 0 | 0 | 0 | 52.03 | 90.5 | 98
490 | NORTH 24 PARAGANAS | SM/08236 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-I WaterSupply Scheme at Bongaon Block (Phase-II). | TSM/007285 | 8382168 | Retrofitting | MVS | GO2021007391PH | 22/02/2021 | 77.55 | 0 | 77.55 | North 24 Pgs W/S Division I |  | 70.56 | 0 | 0 | 0 | 70.56 | 70.56 | 0 | 0 | 0 | 70.56 | 90.99 | 98
491 | NORTH 24 PARAGANAS | SM/08240 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at Bongaon Block (Phase-II). | TSM/007287 | 8382822 | Retrofitting | MVS | GO2021007398PH | 22/02/2021 | 56.45 | 0 | 56.45 | North 24 Pgs W/S Division I |  | 49.97 | 0 | 0 | 0 | 49.97 | 49.95 | 0 | 0 | 0 | 49.95 | 88.48 | 98
492 | NORTH 24 PARAGANAS | SM/08235 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-II WaterSupply Scheme at Bongaon Block (Phase-I). | TSM/007279 | 8382174 | Retrofitting | MVS | GO2021007390PH | 22/02/2021 | 66.16 | 0 | 66.16 | North 24 Pgs W/S Division I |  | 58.92 | 0 | 0 | 0 | 58.92 | 58.92 | 0 | 0 | 0 | 58.92 | 89.05 | 98
493 | NORTH 24 PARAGANAS | SM/08238 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Santoshpur Zone-II Water SupplyScheme at Bongaon Block (Phase-II). | TSM/007281 | 8382813 | Retrofitting | MVS | GO2021007393PH | 22/02/2021 | 76.1 | 0 | 76.1 | North 24 Pgs W/S Division I |  | 61.73 | 0 | 0 | 0 | 61.73 | 61.73 | 0 | 0 | 0 | 61.73 | 81.11 | 98
494 | NORTH 24 PARAGANAS | SM/08242 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-II-Berunanpukuria OHR) at Barasat-I Block | TSM/007434 | 8382870 | Retrofitting | MVS | GO2021007395PH | 22/02/2021 | 88.07 | 0 | 88.07 | North 24 Pgs W/S Division I |  | 81.18 | 0 | 0 | 0 | 81.18 | 81.18 | 0 | 0 | 0 | 81.18 | 92.18 | 98
495 | NORTH 24 PARAGANAS | SM/08241 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | TSM/007436 | 40005198 | Retrofitting | MVS | GO2021007399PH | 22/02/2021 | 249.86 | 0 | 249.86 | North 24 Pgs W/S Division I |  | 203.82 | 0 | 11 | 0 | 214.82 | 202.73 | 0 | 11 | 0 | 213.73 | 85.54 | 95
496 | NORTH 24 PARAGANAS | SM/08243 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block | TSM/007435 | 40026093 | Retrofitting | MVS | GO2021007396PH | 22/02/2021 | 99.94 | 0 | 99.94 | North 24 Pgs W/S Division I |  | 65.28 | 0 | 8.77 | 0 | 74.04 | 65.28 | 0 | 8.77 | 0 | 74.04 | 74.08 | 90
497 | NORTH 24 PARAGANAS | SM/08244 | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block | TSM/007437 | 40024786 | Retrofitting | MVS | GO2021007397PH | 22/02/2021 | 92.41 | 0 | 92.41 | North 24 Pgs W/S Division I |  | 57.77 | 0 | 7.98 | 0 | 65.76 | 57.77 | 0 | 7.98 | 0 | 65.76 | 71.16 | 88
498 | NORTH 24 PARAGANAS | SM/13896 | Purana Bongaon Piped water supply scheme | TSM/016339 | 40032837 | New | SVS | GO2223010095PH | 25/11/2022 | 898.59 | 35.88 | 934.47 | Barasat Division | Eastern Mechanical Division | 225.89 | 8.89 | 14.21 | 0 | 249 | 225.89 | 8.89 | 14.21 | 0 | 249 | 26.65 | 20
499 | NORTH 24 PARAGANAS | SM/18599 | RAIGACHHI Piped Water Supply Scheme. | TSM/016043 | 40038169 | New | SVS | 2152/PHE-28011/167/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 971.13 | 75.49 | 1046.62 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 7.85 | 0 | 12.75 | 0 | 20.6 | 7.85 | 0 | 12.75 | 0 | 20.6 | 1.97 | 6
500 | NORTH 24 PARAGANAS | SM/07024 | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection | TSM/006281 | 8130416 | Retrofitting | MVS | GO2021002663PH | 18/11/2020 | 104.68 | 0 | 104.68 | Barasat Arsenic Division |  | 77.81 | 0 | 0 | 0 | 77.81 | 77.81 | 0 | 0 | 0 | 77.81 | 74.34 | 84
501 | NORTH 24 PARAGANAS | SM/07021 | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | TSM/006283 | 8129904 | Retrofitting | SVS | GO2021002664PH | 18/11/2020 | 61.28 | 0 | 61.28 | Barasat Arsenic Division |  | 42.54 | 0 | 0 | 0 | 42.54 | 42.54 | 0 | 0 | 0 | 42.54 | 69.43 | 85
502 | NORTH 24 PARAGANAS | SM/07025 | Retrofiting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection | TSM/006278 | 8130380 | Retrofitting | SVS | GO2021002661PH | 18/11/2020 | 105.21 | 0 | 105.21 | Barasat Arsenic Division |  | 95.72 | 0 | 0 | 0 | 95.72 | 95.72 | 0 | 0 | 0 | 95.72 | 90.98 | 85
503 | NORTH 24 PARAGANAS | SM/07026 | Retrofitting of Dwarir Jangle water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection | TSM/006276 | 8130330 | Retrofitting | SVS | GO2021002659PH | 18/11/2020 | 104.87 | 0 | 104.87 | Barasat Arsenic Division |  | 90.35 | 0 | 0 | 0 | 90.35 | 90.35 | 0 | 0 | 0 | 90.35 | 86.15 | 84
504 | NORTH 24 PARAGANAS | SM/07027 | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection | TSM/006279 | 8130399 | Retrofitting | MVS | GO2021002660PH | 18/11/2020 | 89.31 | 0 | 89.31 | Barasat Arsenic Division |  | 84.69 | 0 | 0 | 0 | 84.69 | 84.69 | 0 | 0 | 0 | 84.69 | 94.83 | 85
505 | NORTH 24 PARAGANAS | SM/07706 | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | TSM/006712 | 8166746 | Retrofitting | SVS | GO2021004271PH | 07/01/2021 | 78.7 | 0 | 78.7 | Barasat Arsenic Division |  | 66.31 | 0 | 0 | 0 | 66.31 | 66.31 | 0 | 0 | 0 | 66.31 | 84.25 | 83
506 | NORTH 24 PARAGANAS | SM/07709 | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006717 | 8166706 | Retrofitting | MVS | GO2021004277PH | 07/01/2021 | 93.79 | 0 | 93.79 | Barasat Arsenic Division |  | 84.93 | 0 | 0 | 0 | 84.93 | 84.93 | 0 | 0 | 0 | 84.93 | 90.55 | 100
507 | NORTH 24 PARAGANAS | SM/08177 | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . | TSM/007027 | 8227159 | Retrofitting | MVS | GO2021006588PH | 08/02/2021 | 103.74 | 0 | 103.74 | Barasat Arsenic Division |  | 91.72 | 0 | 0 | 0 | 91.72 | 91.72 | 0 | 0 | 0 | 91.72 | 88.41 | 100
508 | NORTH 24 PARAGANAS | SM/07708 | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006718 | 8166680 | Retrofitting | MVS | GO2021004275PH | 07/01/2021 | 94.8 | 0 | 94.8 | Barasat Arsenic Division |  | 84.13 | 0 | 0 | 0 | 84.13 | 84.13 | 0 | 0 | 0 | 84.13 | 88.75 | 100
509 | NORTH 24 PARAGANAS | SM/08178 | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | TSM/007029 | 8227186 | Retrofitting | MVS | GO2021006586PH | 08/02/2021 | 102.85 | 0 | 102.85 | Barasat Arsenic Division |  | 90.25 | 0 | 0 | 0 | 90.25 | 90.25 | 0 | 0 | 0 | 90.25 | 87.75 | 100
510 | NORTH 24 PARAGANAS | SM/07023 | Retrofitting of Chaumuha Water Supply scheme under Barasat - II Block for providing Functional House Tap Connection | TSM/006274 | 8130446 | Retrofitting | SVS | GO2021002667PH | 18/11/2020 | 100.03 | 0 | 100.03 | Barasat Arsenic Division |  | 83.1 | 0 | 0 | 0 | 83.1 | 83.1 | 0 | 0 | 0 | 83.1 | 83.08 | 100
511 | NORTH 24 PARAGANAS | SM/08729 | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | TSM/007656 | 8366399 | Retrofitting | MVS | GO2122003042PH | 07/09/2021 | 116.53 | 0 | 116.53 | Barasat Arsenic Division |  | 99.01 | 0 | 0 | 0 | 99.01 | 99.01 | 0 | 0 | 0 | 99.01 | 84.97 | 100
512 | NORTH 24 PARAGANAS | SM/07713 | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006714 | 8228065 | Retrofitting | MVS | GO2021004284PH | 07/01/2021 | 84.21 | 0 | 84.21 | Barasat Arsenic Division |  | 79.93 | 0 | 0 | 0 | 79.93 | 79.93 | 0 | 0 | 0 | 79.93 | 94.91 | 100
513 | NORTH 24 PARAGANAS | SM/08728 | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) | TSM/007657 | 8366449 | Retrofitting | MVS | GO2122003042PH | 07/09/2021 | 143.69 | 0 | 143.69 | Barasat Arsenic Division |  | 103.35 | 0 | 0 | 0 | 103.35 | 103.35 | 0 | 0 | 0 | 103.35 | 71.92 | 100
514 | NORTH 24 PARAGANAS | SM/09934 | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) | TSM/009214 | 40014133 | Retrofitting | MVS | GO2122006705PH | 13/12/2021 | 125.77 | 42.56 | 168.33 | Barasat Arsenic Division | Eastern Mechanical Division | 55.62 | 0 | 0 | 0 | 55.62 | 55.62 | 0 | 0 | 0 | 55.62 | 33.04 | 59
515 | NORTH 24 PARAGANAS | SM/08725 | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | TSM/007654 | 8366412 | Retrofitting | SVS | GO2122003042PH | 07/09/2021 | 73.87 | 0 | 73.87 | Barasat Arsenic Division |  | 67.41 | 0 | 0 | 0 | 67.41 | 67.41 | 0 | 0 | 0 | 67.41 | 91.25 | 100
516 | NORTH 24 PARAGANAS | SM/08724 | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) | TSM/007658 | 8366441 | Retrofitting | SVS | GO2122003042PH | 07/09/2021 | 137 | 0 | 137 | Barasat Arsenic Division |  | 114.74 | 0 | 0 | 0 | 114.74 | 114.74 | 0 | 0 | 0 | 114.74 | 83.76 | 100
517 | NORTH 24 PARAGANAS | SM/08723 | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) | TSM/007659 | 8366428 | Retrofitting | MVS | GO2122003042PH | 07/09/2021 | 100.71 | 0 | 100.71 | Barasat Arsenic Division |  | 86.5 | 0 | 0 | 0 | 86.5 | 86.5 | 0 | 0 | 0 | 86.5 | 85.89 | 100
518 | NORTH 24 PARAGANAS | SM/08245 | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | TSM/007340 | 8367838 | Retrofitting | MVS | GO2021007414PH | 22/02/2021 | 104.38 | 0 | 104.38 | Barasat Arsenic Division |  | 97.85 | 0 | 0 | 0 | 97.85 | 97.85 | 0 | 0 | 0 | 97.85 | 93.74 | 100
519 | NORTH 24 PARAGANAS | SM/08246 | Retrofitting of Jashaikati Zone II & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | TSM/007341 | 8354456 | Retrofitting | MVS | GO2021007413PH | 22/02/2021 | 100.27 | 0 | 100.27 | Barasat Arsenic Division |  | 89.56 | 0 | 0 | 0 | 89.56 | 89.56 | 0 | 0 | 0 | 89.56 | 89.32 | 86
520 | NORTH 24 PARAGANAS | SM/08726 | Retrofitting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | TSM/007655 | 8366407 | Retrofitting | SVS | GO2122003042PH | 07/09/2021 | 78.61 | 0 | 78.61 | Barasat Arsenic Division |  | 55.58 | 0 | 0 | 0 | 55.58 | 55.58 | 0 | 0 | 0 | 55.58 | 70.7 | 82
521 | NORTH 24 PARAGANAS | SM/08727 | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | TSM/007653 | 40024109 | Retrofitting | MVS | GO2122003042PH | 07/09/2021 | 104.96 | 0 | 104.96 | Barasat Arsenic Division |  | 85.03 | 0 | 0 | 0 | 85.03 | 85.03 | 0 | 0 | 0 | 85.03 | 81.01 | 84
522 | NORTH 24 PARAGANAS | SM/07710 | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006715 | 8164666 | Retrofitting | SVS | GO2021004278PH | 07/01/2021 | 105.05 | 0 | 105.05 | Barasat Arsenic Division |  | 90.28 | 0 | 0 | 0 | 90.28 | 90.28 | 0 | 0 | 0 | 90.28 | 85.94 | 85
523 | NORTH 24 PARAGANAS | SM/07711 | Retrofitting of Paltadanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006719 | 8191586 | Retrofitting | MVS | GO2021004280PH | 07/01/2021 | 94.25 | 0 | 94.25 | Barasat Arsenic Division |  | 86.53 | 0 | 0 | 0 | 86.53 | 86.53 | 0 | 0 | 0 | 86.53 | 91.81 | 100
524 | NORTH 24 PARAGANAS | SM/08176 | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) | TSM/007028 | 8227118 | Retrofitting | MVS | GO2021006584PH | 08/02/2021 | 80.2 | 0 | 80.2 | Barasat Arsenic Division |  | 70 | 0 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 70 | 87.28 | 100
525 | NORTH 24 PARAGANAS | SM/07707 | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006716 | 8164744 | Retrofitting | MVS | GO2021004273PH | 07/01/2021 | 102.91 | 0 | 102.91 | Barasat Arsenic Division |  | 84.74 | 0 | 0 | 0 | 84.74 | 84.74 | 0 | 0 | 0 | 84.74 | 82.34 | 100
526 | NORTH 24 PARAGANAS | SM/08179 | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | TSM/007030 | 8227205 | Retrofitting | MVS | GO2021006587PH | 08/02/2021 | 99.61 | 0 | 99.61 | Barasat Arsenic Division |  | 87.14 | 0 | 0 | 0 | 87.14 | 87.14 | 0 | 0 | 0 | 87.14 | 87.48 | 100
527 | NORTH 24 PARAGANAS | SM/07022 | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection | TSM/006284 | 8130435 | Retrofitting | MVS | GO2021002666PH | 18/11/2020 | 105.02 | 0 | 105.02 | Barasat Arsenic Division |  | 89.84 | 0 | 0 | 0 | 89.84 | 89.84 | 0 | 0 | 0 | 89.84 | 85.54 | 100
528 | NORTH 24 PARAGANAS | SM/08247 | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | TSM/007342 | 8356176 | Retrofitting | MVS | GO2021007412PH | 22/02/2021 | 103.23 | 0 | 103.23 | Barasat Arsenic Division |  | 97.64 | 0 | 0 | 0 | 97.64 | 97.6 | 0 | 0 | 0 | 97.6 | 94.55 | 100
529 | NORTH 24 PARAGANAS | SM/07712 | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | TSM/006713 | 8228093 | Retrofitting | MVS | GO2021004282PH | 07/01/2021 | 89.51 | 0 | 89.51 | Barasat Arsenic Division |  | 77.97 | 0 | 0 | 0 | 77.97 | 77.97 | 0 | 0 | 0 | 77.97 | 87.11 | 100
530 | NORTH 24 PARAGANAS | SM/13518 | Sankardaha Piped water supply scheme | TSM/015446 | 40032048 | New | MVS | GO2223009233PH | 02/11/2022 | 859.97 | 61.01 | 920.98 | Barasat Division | Eastern Mechanical Division | 268.96 | 10.16 | 0 | 27.68 | 306.8 | 268.96 | 10.16 | 0 | 27.68 | 306.8 | 33.31 | 20
531 | NORTH 24 PARAGANAS | SM/14634 | SULANGGARI Piped Water Supply Scheme | TSM/016291 | 40038141 | New | SVS | GO2223012759PH | 31/01/2023 | 1110.95 | 113.24 | 1224.19 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 9.68 | 0 | 23.32 | 0 | 33 | 9.68 | 0 | 23.32 | 0 | 33 | 2.7 | 5
532 | NORTH 24 PARAGANAS | SM/19040 | SURFACE BASED PWSS FOR BARASAT-II BLOCK | TSM/018399 | 40061389 | Augmentation | MVS | 3497/PHE-28011/135/2023-SCHM CELL-Dept. of PHE | 17/11/2023 | 8113.35 | 1369.99 | 9483.34 | Barasat Arsenic Division | Eastern Mechanical Division | 66.14 | 0 | 96.27 | 0 | 162.41 | 66.14 | 0 | 96.27 | 0 | 162.41 | 1.71 | 4
533 | NORTH 24 PARAGANAS | SM/12720 | Tapla Kusangra Piped Water Supply Scheme. | TSM/014693 | 40031646 | New | MVS | GO2223008019PH | 21/09/2022 | 746.89 | 61.01 | 807.9 | Barasat Division | Eastern Mechanical Division | 176.14 | 10.21 | 0 | 0 | 186.35 | 176.14 | 10.21 | 0 | 0 | 186.35 | 23.07 | 43
534 | NORTH 24 PARAGANAS | SM/18598 | TARULIA Piped Water Supply Scheme | TSM/016290 | 40038192 | New | MVS | 2152/PHE-28011/167/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1368.71 | 113.24 | 1481.95 | Barasat Arsenic Division | New Town Kolkata Mechanical Division | 11.11 | 0 | 8.59 | 0 | 19.7 | 11.11 | 0 | 8.59 | 0 | 19.7 | 1.33 | 6
535 | NORTH 24 PARAGANAS | SM/16457 | TEGHARIA Piped Water Supply Scheme | TSM/016121 | 40037451 | New | MVS | GO2223015232PH | 03/03/2023 | 672.46 | 134.5 | 806.96 | Barasat Arsenic Division | Eastern Mechanical Division | 6.01 | 0 | 8.9 | 0 | 14.91 | 6.01 | 0 | 8.9 | 0 | 14.91 | 1.85 | 5
536 | NORTH 24 PARAGANAS | SM/13815 | Uchildaha Piped water supply scheme | TSM/014828 | 40032786 | New | SVS | GO2223009979PH | 23/11/2022 | 1073.81 | 91.52 | 1165.33 | Barasat Division | Eastern Mechanical Division | 356.42 | 27 | 0 | 0 | 383.41 | 356.42 | 27 | 0 | 0 | 383.41 | 32.9 | 53
Total | [9 empty] | 334596.56 | 18158.53 | 352755.08 |  |  | 103967.15 | 2001.03 | 19196.19 | 333.24 | 125497.62 | 101066.67 | 1962.97 | 18594.93 | 318.42 | 121942.99 | 34.57