## JJM Schemes Financial Status (H
JJM Schemes Financial Status (HOOGHLY) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | HOOGHLY | SM/11293 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | TSM/010827 | 40015942 | New | MVS | GO2223004561PH | 28/06/2022 | 331.96 | 53.07 | 385.02 | Hooghly Division | Electrical Division | 258.88 | 32.79 | 10.76 | 0 | 302.43 | 258.88 | 32.79 | 10.76 | 0 | 302.43 | 78.55 | 38
2 | HOOGHLY | SM/19013 | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | TSM/020220 | 40052622 | New | SVS | PHE/IV/3273/W-710/23 | 27/10/2023 | 254.49 | 58.26 | 312.74 | Hooghly Division | Electrical Division | 109.72 | 11.81 | 3.08 | 0 | 124.61 | 109.72 | 11.81 | 3.08 | 0 | 124.61 | 39.84 | 20
3 | HOOGHLY | SM/13589 | Adra mini pipe water supply scheme | TSM/015685 | 40029755 | New | SVS | GO2223009480PH | 09/11/2022 | 34.28 | 8.75 | 43.03 | Hooghly Division | Electrical Division | 32.72 | 8.49 | 0.56 | 0 | 41.77 | 32.72 | 8.49 | 0.56 | 0 | 41.77 | 97.09 | 63
4 | HOOGHLY | SM/11581 | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME | TSM/011547 | 40017473 | New | MVS | GO2223005432PH | 22/07/2022 | 639.46 | 56.53 | 695.99 | Hooghly Division | Electrical Division | 145.1 | 35.25 | 80.46 | 0 | 260.81 | 143.73 | 35.25 | 80.46 | 0 | 259.44 | 37.28 | 22
5 | HOOGHLY | SM/13671 | Alasin Mini Piped Water Supply Scheme | TSM/015642 | 40029661 | New | SVS | GO2223009524PH | 09/11/2022 | 33.7 | 8.75 | 42.45 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
6 | HOOGHLY | SM/13660 | Arazi Krittibaspur Mini Piped Water Supply Scheme | TSM/015668 | 40029647 | New | SVS | GO2223009517PH | 09/11/2022 | 25.95 | 8.75 | 34.7 | Hooghly Division | Electrical Division | 25.08 | 8.49 | 0.12 | 0 | 33.69 | 25.08 | 8.49 | 0.12 | 0 | 33.69 | 97.09 | 59
7 | HOOGHLY | SM/11286 | ASTARA PIPED WATER SUPPLY SCHEME | TSM/010469 | 40015714 | New | MVS | GO2223004555PH | 28/06/2022 | 581.01 | 65.76 | 646.77 | Hooghly Division | Electrical Division | 405.57 | 34.98 | 53.72 | 0 | 494.28 | 405.57 | 36.2 | 53.72 | 0 | 495.49 | 76.61 | 35
8 | HOOGHLY | SM/12727 | ATISARA PIPED WATER SUPPLY SCHEME | TSM/010832 | 40027247 | New | MVS | GO2223008047PH | 21/09/2022 | 1256.6 | 65.76 | 1322.35 | Hooghly Division | Electrical Division | 648.08 | 23.2 | 159.22 | 0 | 830.5 | 648.08 | 23.2 | 159.22 | 0 | 830.5 | 62.81 | 43
9 | HOOGHLY | SM/09207 | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008681 | 40015553 | Augmentation | MVS | GO2122004728PH | 30/10/2021 | 35.42 | 0 | 35.42 | Hooghly Division |  | 31 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 31 | 87.53 | 100
10 | HOOGHLY | SM/09208 | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008680 | 40015552 | Augmentation | MVS | GO2122004728PH | 30/10/2021 | 35.42 | 0 | 35.42 | Hooghly Division |  | 6.15 | 0 | 0 | 0 | 6.15 | 6.15 | 0 | 0 | 0 | 6.15 | 17.37 | 49
11 | HOOGHLY | SM/18644 | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | TSM/019199 | 40039086 | Augmentation | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1987.77 | 111.82 | 2099.59 | Hooghly Division | Electrical Division | 24.5 | 29.68 | 69.13 | 0 | 123.31 | 24.5 | 29.68 | 69.13 | 0 | 123.31 | 5.87 | 18
12 | HOOGHLY | SM/18770 | Augmentation of Balipur Water Supply Scheme | TSM/014800 | 40033269 | Augmentation | MVS | 2562/PHE-28011/76/2023-ESTT CELL-Dept. of PHE | 25/08/2023 | 1097.18 | 55.62 | 1152.8 | Hooghly Division | Electrical Division | 383.53 | 31.88 | 3.08 | 0 | 418.48 | 383.53 | 31.88 | 3.08 | 0 | 418.48 | 36.3 | 47
13 | HOOGHLY | SM/10005 | Augmentation of Champadanga Water Supply Scheme | TSM/009191 | 40012787 | Augmentation | MVS | GO2122006985PH | 20/12/2021 | 1476.93 | 55.62 | 1532.55 | Hooghly Division | Electrical Division | 938.36 | 28.91 | 155.78 | 23.79 | 1146.84 | 936.49 | 28.91 | 155.78 | 23.79 | 1144.97 | 74.71 | 94
14 | HOOGHLY | SM/10467 | Augmentation of Chanparai Water Supply Scheme | TSM/009960 | 40013062 | Augmentation | MVS | GO2223000208PH | 13/04/2022 | 386.65 | 27.81 | 414.46 | Hooghly Division | Electrical Division | 256.52 | 13.57 | 20.44 | 0 | 290.53 | 256.52 | 13.57 | 20.44 | 0 | 290.53 | 70.1 | 89
15 | HOOGHLY | SM/15788 | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | TSM/020227 | 40039165 | Augmentation | MVS | GO2223014269PH | 20/02/2023 | 280.99 | 27.81 | 308.8 | Hooghly Division | Electrical Division | 0 | 0 | 0.31 | 0 | 0.31 | 0 | 0 | 0.31 | 0 | 0.31 | 0.1 | 19
16 | HOOGHLY | SM/18670 | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/014859 | 40032795 | Augmentation | MVS | 2239/PHE-28011/76/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1048.73 | 83.43 | 1132.16 | Hooghly Division | Electrical Division | 113.96 | 6.98 | 3.29 | 0 | 124.23 | 113.96 | 6.98 | 3.29 | 0 | 124.23 | 10.97 | 24
17 | HOOGHLY | SM/15787 | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | TSM/020224 | 40042580 | Augmentation | MVS | GO2223014276PH | 20/02/2023 | 413.65 | 27.81 | 441.46 | Hooghly Division | Electrical Division | 244.46 | 3.58 | 61 | 0 | 309.05 | 244.46 | 3.58 | 61 | 0 | 309.05 | 70.01 | 29
18 | HOOGHLY | SM/16351 | Augmentation of Gobindapur Water Supply Scheme | TSM/014860 | 40033260 | Augmentation | MVS | GO2223014970PH | 28/02/2023 | 303.38 | 27.81 | 331.19 | Hooghly Division | Electrical Division | 200.87 | 14.83 | 1.39 | 0 | 217.08 | 200.87 | 14.83 | 1.39 | 0 | 217.08 | 65.55 | 100
19 | HOOGHLY | SM/12228 | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | TSM/014829 | 40033118 | Augmentation | MVS | GO2223007106PH | 07/09/2022 | 686.37 | 55.62 | 741.99 | Hooghly Division | Electrical Division | 252.15 | 26.91 | 19.81 | 0 | 298.86 | 252.15 | 26.91 | 19.81 | 0 | 298.86 | 40.28 | 100
20 | HOOGHLY | SM/11464 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011268 | 40016297 | Augmentation | MVS | GO2223004994PH | 12/07/2022 | 314.16 | 55.62 | 369.78 | Hooghly Division | Electrical Division | 75.38 | 22.37 | 55.42 | 0 | 153.18 | 75.38 | 22.37 | 55.42 | 0 | 153.18 | 41.42 | 83
21 | HOOGHLY | SM/11463 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011273 | 40017046 | Augmentation | MVS | GO2223004989PH | 12/07/2022 | 919.3 | 55.62 | 974.92 | Hooghly Division | Electrical Division | 360.98 | 33.09 | 211.95 | 18.99 | 625.01 | 360.98 | 35.48 | 211.95 | 18.99 | 627.39 | 64.35 | 58
22 | HOOGHLY | SM/11461 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011261 | 40016288 | Augmentation | MVS | GO2223004987PH | 12/07/2022 | 273.89 | 55.62 | 329.51 | Hooghly Division | Electrical Division | 160.05 | 27.67 | 37.94 | 14.12 | 239.78 | 160.05 | 27.67 | 37.94 | 14.12 | 239.78 | 72.77 | 80
23 | HOOGHLY | SM/11468 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011249 | 40016348 | Augmentation | MVS | GO2223004993PH | 12/07/2022 | 625.73 | 83.43 | 709.16 | Hooghly Division | Electrical Division | 367.89 | 34.45 | 44.74 | 20.24 | 467.31 | 367.89 | 34.45 | 44.74 | 20.24 | 467.31 | 65.9 | 63
24 | HOOGHLY | SM/11467 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | TSM/011255 | 40016352 | Augmentation | SVS | GO2223004992PH | 12/07/2022 | 524.93 | 27.81 | 552.74 | Hooghly Division | Electrical Division | 327.44 | 24.42 | 17.86 | 9.62 | 379.33 | 327.44 | 24.42 | 17.86 | 9.62 | 379.33 | 68.63 | 86
25 | HOOGHLY | SM/11462 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011280 | 40016292 | Augmentation | MVS | GO2223004988PH | 12/07/2022 | 709.7 | 55.62 | 765.32 | Hooghly Division | Electrical Division | 371.98 | 11.4 | 34.93 | 18.83 | 437.14 | 371.98 | 11.4 | 34.93 | 18.83 | 437.14 | 57.12 | 68
26 | HOOGHLY | SM/14040 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | TSM/011881 | 40030427 | Augmentation | MVS | GO2223010771PH | 12/12/2022 | 1154.24 | 111.24 | 1265.48 | Hooghly Division | Electrical Division | 582.08 | 59.4 | 83.27 | 0 | 724.74 | 580.09 | 57.36 | 83.27 | 0 | 720.72 | 56.95 | 45
27 | HOOGHLY | SM/11868 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | TSM/011915 | 40019626 | Augmentation | MVS | GO2223006409PH | 17/08/2022 | 781.8 | 55.62 | 837.42 | Hooghly Division | Electrical Division | 445.36 | 30.85 | 38.65 | 0 | 514.86 | 445.36 | 30.85 | 38.65 | 0 | 514.86 | 61.48 | 92
28 | HOOGHLY | SM/09692 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | TSM/008348 | 40008802 | Augmentation | MVS | GO2122005911PH | 25/11/2021 | 444.24 | 0 | 444.24 | Hooghly Division |  | 296.95 | 0 | 5.48 | 10.83 | 313.26 | 296.95 | 0 | 5.48 | 10.83 | 313.26 | 70.52 | 97
29 | HOOGHLY | SM/09691 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | TSM/008347 | 40008434 | Augmentation | MVS | GO2122005911PH | 25/11/2021 | 541.55 | 0 | 541.55 | Hooghly Division |  | 320.64 | 0 | 37.65 | 0 | 358.29 | 320.64 | 0 | 37.65 | 0 | 358.29 | 66.16 | 95
30 | HOOGHLY | SM/10341 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | TSM/008350 | 40012098 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1037.36 | 0 | 1037.36 | Hooghly Division | Electrical Division | 576.94 | 0 | 82.16 | 40.98 | 700.09 | 576.94 | 0 | 82.16 | 40.98 | 700.09 | 67.49 | 86
31 | HOOGHLY | SM/10340 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | TSM/008349 | 40012138 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1822.88 | 0 | 1822.88 | Hooghly Division |  | 1056.24 | 38.52 | 112.63 | 13.75 | 1221.14 | 1056.24 | 38.52 | 112.63 | 13.75 | 1221.14 | 66.99 | 95
32 | HOOGHLY | SM/09690 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | TSM/008331 | 40008660 | Augmentation | MVS | GO2122005912PH | 25/11/2021 | 350.38 | 0 | 350.38 | Hooghly Division |  | 233.89 | 0 | 47.73 | 0 | 281.62 | 233.89 | 0 | 47.73 | 0 | 281.62 | 80.37 | 84
33 | HOOGHLY | SM/09698 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | TSM/008329 | 40008639 | Augmentation | MVS | GO2122005910PH | 25/11/2021 | 592.7 | 27.81 | 620.51 | Hooghly Division | Electrical Division | 220.08 | 20.76 | 23.57 | 0 | 264.41 | 220.08 | 20.76 | 23.57 | 0 | 264.41 | 42.61 | 91
34 | HOOGHLY | SM/11867 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | TSM/011916 | 40019539 | Augmentation | MVS | GO2223006445PH | 17/08/2022 | 391.23 | 55.62 | 446.85 | Hooghly Division | Electrical Division | 333.73 | 38.92 | 6.04 | 0 | 378.69 | 333.73 | 38.92 | 6.04 | 0 | 378.69 | 84.75 | 84
35 | HOOGHLY | SM/12369 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | TSM/009964 | 40032501 | Augmentation | MVS | GO2223007582PH | 13/09/2022 | 3422.29 | 333.72 | 3756.01 | Hooghly Division | Electrical Division | 838.98 | 151.76 | 251.86 | 0 | 1242.6 | 838.98 | 151.76 | 251.86 | 0 | 1242.6 | 33.08 | 23
36 | HOOGHLY | SM/11466 | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | TSM/011236 | 40021824 | Augmentation | SVS | GO2223004991PH | 12/07/2022 | 534.88 | 55.62 | 590.5 | Hooghly Division | Electrical Division | 273.18 | 37.18 | 11.93 | 0 | 322.29 | 273.18 | 37.18 | 11.93 | 0 | 322.29 | 54.58 | 53
37 | HOOGHLY | SM/10338 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | TSM/008325 | 40011612 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1195.42 | 111.24 | 1306.66 | Hooghly Division | Electrical Division | 572.87 | 101.8 | 43.07 | 33.69 | 751.43 | 572.87 | 101.8 | 43.07 | 33.69 | 751.43 | 57.51 | 90
38 | HOOGHLY | SM/11924 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | TSM/011627 | 40019519 | Augmentation | MVS | GO2223006611PH | 22/08/2022 | 721.01 | 27.81 | 748.82 | Hooghly Division | Electrical Division | 415.11 | 23.71 | 48.4 | 0 | 487.22 | 415.11 | 23.71 | 48.4 | 0 | 487.22 | 65.07 | 75
39 | HOOGHLY | SM/11166 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | TSM/010115 | 40014617 | Augmentation | MVS | GO2223003785PH | 02/06/2022 | 868.02 | 27.81 | 895.83 | Hooghly Division | Electrical Division | 394.49 | 27.79 | 189.22 | 0 | 611.5 | 394.49 | 27.79 | 189.22 | 0 | 611.5 | 68.26 | 94
40 | HOOGHLY | SM/15891 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | TSM/011632 | 40037190 | Augmentation | MVS | GO2223014281PH | 20/02/2023 | 95.22 | 56.53 | 151.75 | Hooghly Division | Electrical Division | 58.18 | 40.91 | 32.88 | 0 | 131.97 | 58.18 | 40.91 | 32.88 | 0 | 131.97 | 86.97 | 19
41 | HOOGHLY | SM/09695 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | TSM/008327 | 40007373 | Augmentation | MVS | GO2122005907PH | 25/11/2021 | 826.24 | 27.81 | 854.05 | Hooghly Division | Electrical Division | 532.7 | 24.13 | 88.16 | 0 | 644.99 | 532.14 | 24.13 | 88.16 | 0 | 644.43 | 75.46 | 90
42 | HOOGHLY | SM/10339 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | TSM/008330 | 40011288 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1297.28 | 55.62 | 1352.9 | Hooghly Division | Electrical Division | 465.71 | 39.01 | 79.09 | 23.93 | 607.74 | 461.51 | 39.01 | 79.09 | 23.93 | 603.54 | 44.61 | 91
43 | HOOGHLY | SM/09688 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | TSM/008326 | 40008251 | Augmentation | SVS | GO2122005912PH | 25/11/2021 | 278.45 | 0 | 278.45 | Hooghly Division | Electrical Division | 242.94 | 0 | 11.24 | 0 | 254.18 | 242.94 | 0 | 11.24 | 0 | 254.18 | 91.28 | 95
44 | HOOGHLY | SM/18397 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | TSM/009649 | 40032742 | Augmentation | MVS | 1846/PHE-28011/96/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 3602.14 | 444.96 | 4047.1 | Hooghly Division | Electrical Division | 1106.61 | 130.8 | 0 | 0 | 1237.42 | 1094.06 | 130.8 | 0 | 0 | 1224.86 | 30.27 | 17
45 | HOOGHLY | SM/09790 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | TSM/008323 | 40010372 | Augmentation | MVS | GO2122006244PH | 30/11/2021 | 508.53 | 0 | 508.53 | Hooghly Division |  | 218.12 | 0 | 40.32 | 0 | 258.44 | 218.12 | 0 | 40.32 | 0 | 258.44 | 50.82 | 95
46 | HOOGHLY | SM/09689 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | TSM/008328 | 40007487 | Augmentation | SVS | GO2122005912PH | 25/11/2021 | 333.93 | 0 | 333.93 | Hooghly Division |  | 212.85 | 0 | 28.96 | 0 | 241.82 | 212.83 | 0 | 28.96 | 0 | 241.79 | 72.41 | 98
47 | HOOGHLY | SM/11167 | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | TSM/010116 | 40014614 | Augmentation | SVS | GO2223003786PH | 02/06/2022 | 466.76 | 27.81 | 494.57 | Hooghly Division | Electrical Division | 171.57 | 15.15 | 51.92 | 0 | 238.65 | 171.57 | 15.15 | 51.92 | 0 | 238.65 | 48.25 | 89
48 | HOOGHLY | SM/11465 | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | TSM/011257 | 40016266 | Augmentation | SVS | GO2223004990PH | 12/07/2022 | 279.54 | 27.81 | 307.35 | Hooghly Division | Electrical Division | 180.08 | 17.86 | 17.06 | 0 | 215 | 180.08 | 17.86 | 17.06 | 0 | 215 | 69.95 | 80
49 | HOOGHLY | SM/09694 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | TSM/008324 | 40007155 | Augmentation | SVS | GO2122005908PH | 25/11/2021 | 716.39 | 55.62 | 772.01 | Hooghly Division | Electrical Division | 516.66 | 45.48 | 20.29 | 10.33 | 592.77 | 506.05 | 45.48 | 20.29 | 10.33 | 582.16 | 75.41 | 92
50 | HOOGHLY | SM/09693 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | TSM/008322 | 40006898 | Augmentation | MVS | GO2122005909PH | 25/11/2021 | 587.82 | 27.81 | 615.63 | Hooghly Division | Electrical Division | 416.54 | 26.1 | 56.28 | 22.59 | 521.51 | 415.87 | 26.1 | 56.28 | 22.59 | 520.85 | 84.6 | 95
51 | HOOGHLY | SM/11866 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | TSM/011917 | 40019521 | Augmentation | MVS | GO2223006401PH | 17/08/2022 | 634.18 | 55.62 | 689.8 | Hooghly Division | Electrical Division | 398.8 | 51.67 | 78.28 | 0 | 528.76 | 398.8 | 51.67 | 78.28 | 0 | 528.76 | 76.65 | 58
52 | HOOGHLY | SM/13349 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | TSM/009963 | 40027496 | Augmentation | MVS | GO2223008971PH | 19/10/2022 | 1196.03 | 139.05 | 1335.08 | Hooghly Division | Electrical Division | 529.97 | 70.57 | 20.42 | 0 | 620.96 | 529.97 | 70.57 | 20.42 | 0 | 620.96 | 46.51 | 31
53 | HOOGHLY | SM/09984 | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | TSM/009193 | 40012896 | Augmentation | MVS | GO2122006876PH | 16/12/2021 | 1251.54 | 83.43 | 1334.97 | Hooghly Division | Electrical Division | 708.31 | 53.29 | 433.57 | 30.45 | 1225.62 | 708.27 | 53.29 | 433.57 | 30.45 | 1225.58 | 91.81 | 83
54 | HOOGHLY | SM/09983 | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | TSM/009209 | 40012800 | Augmentation | MVS | GO2122006876PH | 16/12/2021 | 1207.55 | 55.62 | 1263.17 | Hooghly Division | Electrical Division | 726.98 | 25.16 | 133 | 0 | 885.14 | 726.98 | 25.16 | 133 | 0 | 885.14 | 70.07 | 93
55 | HOOGHLY | SM/10004 | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | TSM/009196 | 40017964 | Augmentation | MVS | GO2122006985PH | 20/12/2021 | 1498.34 | 55.62 | 1553.96 | Hooghly Division | Electrical Division | 827.49 | 0 | 119.79 | 0 | 947.29 | 824.49 | 0 | 119.79 | 0 | 944.29 | 60.77 | 95
56 | HOOGHLY | SM/12370 | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | TSM/009198 | 40031733 | Augmentation | MVS | GO2223007587PH | 13/09/2022 | 1185.08 | 83.43 | 1268.51 | Hooghly Division | Electrical Division | 547.08 | 38.72 | 246.81 | 0 | 832.6 | 547.08 | 38.72 | 246.81 | 0 | 832.6 | 65.64 | 100
57 | HOOGHLY | SM/09982 | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | TSM/009212 | 40012791 | Augmentation | MVS | GO2122006876PH | 16/12/2021 | 1398.41 | 83.43 | 1481.84 | Hooghly Division | Electrical Division | 1033.87 | 35.42 | 47.85 | 0 | 1117.14 | 1033.87 | 35.42 | 47.85 | 0 | 1117.14 | 75.39 | 90
58 | HOOGHLY | SM/10022 | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | TSM/009210 | 40010480 | Augmentation | MVS | GO2122007890PH | 05/01/2022 | 2139.27 | 111.24 | 2250.51 | Hooghly Division | Electrical Division | 1471.6 | 67.71 | 256.74 | 0 | 1796.05 | 1471.6 | 67.71 | 256.74 | 0 | 1796.05 | 79.81 | 92
59 | HOOGHLY | SM/09791 | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | TSM/009205 | 40014416 | Augmentation | MVS | GO2122006243PH | 30/11/2021 | 829.8 | 55.62 | 885.42 | Hooghly Division | Electrical Division | 474.74 | 26.03 | 104.61 | 20.63 | 626.01 | 474.74 | 26.03 | 104.61 | 20.63 | 626.01 | 70.7 | 89
60 | HOOGHLY | SM/16119 | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/020424 | 40053142 | Augmentation | MVS | GO2223014675PH | 22/02/2023 | 526.83 | 31.21 | 558.04 | Hooghly Division | Electrical Division | 131.11 | 20.2 | 1.23 | 0 | 152.54 | 131.11 | 20.2 | 1.23 | 0 | 152.54 | 27.33 | 24
61 | HOOGHLY | SM/15243 | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016236 | 40032891 | Augmentation | MVS | GO2223013437PH | 07/02/2023 | 426.46 | 55.91 | 482.37 | Hooghly Division | Electrical Division | 227.06 | 10.41 | 37.48 | 0 | 274.95 | 227.06 | 10.41 | 37.48 | 0 | 274.95 | 57 | 83
62 | HOOGHLY | SM/18339 | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | TSM/014834 | 40033264 | Augmentation | MVS | 1736/PHE-28011/28/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 996.6 | 55.62 | 1052.22 | Hooghly Division | Electrical Division | 488.05 | 30.94 | 24.04 | 0 | 543.04 | 488.05 | 30.94 | 24.04 | 0 | 543.04 | 51.61 | 44
63 | HOOGHLY | SM/16564 | Augmentation of Kulteghori Piped Water Supply Scheme | TSM/015885 | 40032551 | Augmentation | MVS | GO2223015499PH | 10/03/2023 | 32.83 | 26.27 | 59.1 | Hooghly Division | Electrical Division | 1.95 | 24.36 | 0 | 0 | 26.31 | 1.95 | 24.36 | 0 | 0 | 26.31 | 44.52 | 52
64 | HOOGHLY | SM/10451 | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | TSM/009987 | 40013122 | Augmentation | MVS | GO2223000189PH | 12/04/2022 | 933.74 | 55.62 | 989.36 | Hooghly Division | Electrical Division | 430.17 | 31.81 | 92.41 | 0 | 554.4 | 430.17 | 31.81 | 92.41 | 0 | 554.4 | 56.04 | 93
65 | HOOGHLY | SM/09604 | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008678 | 40029551 | Augmentation | SVS | GO2122005740PH | 23/11/2021 | 16.13 | 27.81 | 43.94 | Hooghly Division | Electrical Division | 0 | 3.06 | 0 | 11.36 | 14.42 | 0 | 3.06 | 0 | 11.36 | 14.42 | 32.82 | 100
66 | HOOGHLY | SM/16120 | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | TSM/020412 | 40059492 | Augmentation | MVS | GO2223014673PH | 22/02/2023 | 390.1 | 27.81 | 417.91 | Hooghly Division | Electrical Division | 176.31 | 13.87 | 17.17 | 0 | 207.34 | 176.31 | 13.87 | 17.17 | 0 | 207.34 | 49.61 | 52
67 | HOOGHLY | SM/18645 | Augmentation Of Piped Water Supply Scheme For KHANAKUL | TSM/017854 | 40037751 | Augmentation | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1144.5 | 55.62 | 1200.12 | Hooghly Division | Electrical Division | 84.61 | 7.74 | 31.5 | 0 | 123.85 | 83.01 | 7.74 | 31.5 | 0 | 122.25 | 10.19 | 18
68 | HOOGHLY | SM/18643 | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | TSM/017860 | 40042889 | Augmentation | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1092.79 | 55.62 | 1148.41 | Hooghly Division | Electrical Division | 180.61 | 9.2 | 39.87 | 0 | 229.69 | 180.61 | 9.2 | 39.87 | 0 | 229.69 | 20 | 18
69 | HOOGHLY | SM/10468 | Augmentation of Polba Water Supply Scheme | TSM/009961 | 40019604 | Augmentation | MVS | GO2223000209PH | 13/04/2022 | 908.02 | 55.62 | 963.64 | Hooghly Division | Electrical Division | 709.3 | 53.98 | 40.33 | 0 | 803.61 | 704.14 | 53.98 | 40.33 | 0 | 798.45 | 82.86 | 91
70 | HOOGHLY | SM/13348 | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | TSM/009962 | 40027555 | Augmentation | MVS | GO2223008972PH | 19/10/2022 | 1035.99 | 55.62 | 1091.61 | Hooghly Division | Electrical Division | 718.53 | 30.56 | 69.6 | 0 | 818.7 | 718.53 | 30.56 | 69.6 | 0 | 818.7 | 75 | 32
71 | HOOGHLY | SM/11969 | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | TSM/009988 | 40024123 | Augmentation | MVS | GO2223006753PH | 29/08/2022 | 984.79 | 111.24 | 1096.03 | Hooghly Division | Electrical Division | 425.43 | 88.57 | 90.4 | 10.04 | 614.43 | 424.85 | 88.57 | 90.4 | 10.04 | 613.85 | 56.01 | 86
72 | HOOGHLY | SM/09516 | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008674 | 40014417 | Augmentation | MVS | GO2122005586PH | 19/11/2021 | 16.13 | 27.81 | 43.94 | Hooghly Division | Electrical Division | 4.04 | 19.92 | 0 | 0 | 23.95 | 4.04 | 19.92 | 0 | 0 | 23.95 | 54.52 | 36
73 | HOOGHLY | SM/09517 | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008677 | 40014432 | Augmentation | MVS | GO2122005586PH | 19/11/2021 | 16.13 | 27.81 | 43.94 | Hooghly Division | Electrical Division | 7.73 | 25.32 | 0 | 0 | 33.05 | 7.73 | 25.32 | 0 | 0 | 33.05 | 75.22 | 36
74 | HOOGHLY | SM/10023 | Augmentation of Salepur-Duttapur Water Supply Scheme | TSM/009194 | 40009723 | Augmentation | MVS | GO2122007890PH | 05/01/2022 | 1404.39 | 55.62 | 1460.01 | Hooghly Division | Electrical Division | 963.06 | 27.61 | 86.18 | 0 | 1076.86 | 963.06 | 27.61 | 86.18 | 0 | 1076.86 | 73.76 | 91
75 | HOOGHLY | SM/18347 | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | TSM/015380 | 40032993 | Augmentation | MVS | 1738/PHE-28011/73/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 936.08 | 111.24 | 1047.32 | Hooghly Division | Electrical Division | 247.41 | 33.75 | 32.99 | 0 | 314.16 | 247.41 | 33.75 | 32.99 | 0 | 314.16 | 30 | 32
76 | HOOGHLY | SM/19036 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | TSM/018539 | 7401871 | Augmentation | MVS | 3432/PHE-28011/249/2023-ESTT CELL-Dept. of PHE | 08/11/2023 | 25379 | 421.8 | 25800.8 | Hooghly Division | Electrical Division | 5194.01 | 0 | 276.75 | 0 | 5470.76 | 5185.56 | 0 | 276.75 | 0 | 5462.31 | 21.17 | 38
77 | HOOGHLY | SM/13336 | BADE DIGARIA PIPED WATER SUPPLY SCHEME | TSM/015480 | 40033414 | New | MVS | GO2223008864PH | 17/10/2022 | 600.82 | 56.53 | 657.34 | Hooghly Division | Electrical Division | 285.06 | 26.68 | 30.77 | 0 | 342.51 | 285.06 | 26.68 | 30.77 | 0 | 342.51 | 52.11 | 27
78 | HOOGHLY | SM/13404 | BAHIRKHANDA PIPED WATER SUPPLY SCHEME | TSM/011471 | 40033424 | New | MVS | GO2223009051PH | 21/10/2022 | 1560.43 | 56.53 | 1616.96 | Hooghly Division | Electrical Division | 812.37 | 40.33 | 122.34 | 0 | 975.03 | 803.72 | 40.33 | 122.34 | 0 | 966.38 | 59.77 | 33
79 | HOOGHLY | SM/17629 | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly | TSM/018107 | 40053281 | New | MVS | GO2223017388PH | 21/03/2023 | 363.53 | 42.97 | 406.5 | Hooghly Division | Electrical Division | 75.05 | 16.32 | 30.05 | 0 | 121.42 | 75.05 | 16.32 | 30.05 | 0 | 121.42 | 29.87 | 21
80 | HOOGHLY | SM/18101 | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. | TSM/020542 | 40066234 | New | SVS | GO2223017767PH | 27/03/2023 | 168.48 | 55.91 | 224.39 | Hooghly Division | Electrical Division | 86.61 | 14.72 | 15.11 | 0 | 116.44 | 86.61 | 14.72 | 15.11 | 0 | 116.44 | 51.89 | 18
81 | HOOGHLY | SM/18671 | Baligari Piped Water Supply Scheme. | TSM/004358 | 40032367 | New | MVS | 2240/PHE-28011/122/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1991.02 | 76.14 | 2067.16 | Hooghly Division | Electrical Division | 692.36 | 73.42 | 9.8 | 0 | 775.58 | 692.36 | 73.42 | 9.8 | 0 | 775.58 | 37.52 | 18
82 | HOOGHLY | SM/12248 | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014197 | 40027077 | New | MVS | GO2223007172PH | 07/09/2022 | 606.32 | 64.87 | 671.18 | Hooghly Division | Electrical Division | 426.47 | 34.13 | 36.16 | 0 | 496.76 | 426.47 | 34.13 | 36.16 | 0 | 496.76 | 74.01 | 17
83 | HOOGHLY | SM/13592 | Bara Kumursa mini pipe water supply scheme | TSM/015686 | 40029748 | New | SVS | GO2223009479PH | 09/11/2022 | 31.39 | 8.75 | 40.14 | Hooghly Division | Electrical Division | 30.09 | 8.49 | 0.39 | 0 | 38.97 | 30.09 | 8.49 | 0.39 | 0 | 38.97 | 97.09 | 62
84 | HOOGHLY | SM/18102 | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly | TSM/020541 | 40066237 | New | SVS | GO2223017775PH | 27/03/2023 | 36.79 | 8.75 | 45.54 | Hooghly Division | Electrical Division | 32.73 | 7.58 | 0.59 | 0 | 40.9 | 32.73 | 7.58 | 0.59 | 0 | 40.9 | 89.81 | 63
85 | HOOGHLY | SM/13548 | Barul mini pipe water supply scheme | TSM/015689 | 40033774 | New | SVS | GO2223009306PH | 04/11/2022 | 32.38 | 8.75 | 41.13 | Hooghly Division | Electrical Division | 30.98 | 8.49 | 0 | 0 | 39.48 | 30.98 | 8.49 | 0 | 0 | 39.48 | 95.98 | 62
86 | HOOGHLY | SM/12246 | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014298 | 40026639 | New | MVS | GO2223007114PH | 06/09/2022 | 641.87 | 58.88 | 700.75 | Hooghly Division | Electrical Division | 259.9 | 8.49 | 25.18 | 0 | 293.57 | 259.9 | 8.49 | 25.18 | 0 | 293.57 | 41.89 | 19
87 | HOOGHLY | SM/13560 | Basantapur Mini Piped Water Supply Scheme | TSM/015632 | 40033953 | New | SVS | GO2223009329PH | 04/11/2022 | 33.31 | 8.75 | 42.06 | Hooghly Division | Electrical Division | 31.77 | 8.49 | 0.57 | 0 | 40.83 | 31.77 | 8.49 | 0.57 | 0 | 40.83 | 97.09 | 39
88 | HOOGHLY | SM/16763 | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016255 | 40032882 | New | MVS | GO2223015662PH | 13/03/2023 | 184.62 | 55.91 | 240.53 | Hooghly Division | Electrical Division | 81.67 | 26.64 | 15.16 | 0 | 123.46 | 81.67 | 26.64 | 15.16 | 0 | 123.46 | 51.33 | 65
89 | HOOGHLY | SM/12365 | BASUBATI PIPED WATER SUPPLY SCHEME | TSM/011423 | 40027375 | New | MVS | GO2223007573PH | 13/09/2022 | 1017.11 | 98.63 | 1115.75 | Hooghly Division | Electrical Division | 249.89 | 29.15 | 67.77 | 0 | 346.8 | 249.89 | 29.15 | 67.77 | 0 | 346.8 | 31.08 | 27
90 | HOOGHLY | SM/13552 | Belun Mini Piped Water Supply Scheme | TSM/015669 | 40033659 | New | SVS | GO2223009325PH | 04/11/2022 | 32.82 | 8.75 | 41.57 | Hooghly Division | Electrical Division | 31.34 | 8.49 | 0.52 | 0 | 40.36 | 31.34 | 8.49 | 0.52 | 0 | 40.36 | 97.09 | 63
91 | HOOGHLY | SM/18597 | BENGAI WATER SUPPLY SCHEME | TSM/014934 | 40033662 | New | MVS | 2151/PHE-28011/158/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1011.14 | 65.63 | 1076.77 | Hooghly Division | Electrical Division | 373.38 | 46.24 | 3.08 | 0 | 422.69 | 373.38 | 46.24 | 3.08 | 0 | 422.69 | 39.26 | 18
92 | HOOGHLY | SM/13673 | Bhabapur mini pipe water supply scheme | TSM/015568 | 40029076 | New | SVS | GO2223009523PH | 09/11/2022 | 31.09 | 8.75 | 39.84 | Hooghly Division | Electrical Division | 29.7 | 0 | 0.48 | 0 | 30.18 | 29.7 | 0 | 0.48 | 0 | 30.18 | 75.76 | 16
93 | HOOGHLY | SM/11287 | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | TSM/010839 | 40015946 | New | SVS | GO2223004554PH | 28/06/2022 | 70.15 | 29.42 | 99.57 | Hooghly Division | Electrical Division | 6.5 | 25.98 | 55.5 | 0 | 87.98 | 6.5 | 25.98 | 55.5 | 0 | 87.98 | 88.36 | 34
94 | HOOGHLY | SM/18373 | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | TSM/018133 | 40038038 | New | MVS | 1806/PHE-28011/201/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1138.32 | 120.41 | 1258.73 | Hooghly Division | Electrical Division | 446.54 | 60.62 | 0 | 0 | 507.16 | 446.54 | 60.62 | 0 | 0 | 507.16 | 40.29 | 16
95 | HOOGHLY | SM/15789 | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | TSM/018043 | 40037757 | New | MVS | GO2223014309PH | 20/02/2023 | 906.34 | 55.91 | 962.24 | Hooghly Division | Electrical Division | 93.78 | 30.5 | 47.69 | 0 | 171.96 | 93.78 | 30.5 | 47.69 | 0 | 171.96 | 17.87 | 25
96 | HOOGHLY | SM/19014 | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly | TSM/018054 | 40053283 | New | MVS | PHE/IV/3273/W-710/23 | 27/10/2023 | 155.8 | 55.91 | 211.71 | Hooghly Division | Electrical Division | 36.01 | 6.49 | 0 | 0 | 42.5 | 36.01 | 6.49 | 0 | 0 | 42.5 | 20.08 | 11
97 | HOOGHLY | SM/18096 | BHANDARDAHA PIPED WATER SUPPLY SCHEME | TSM/020545 | 40066212 | New | SVS | GO2223017764PH | 27/03/2023 | 165.69 | 49.22 | 214.91 | Hooghly Division | Electrical Division | 92.24 | 13.61 | 0 | 0 | 105.84 | 92.24 | 13.89 | 0 | 0 | 106.12 | 49.38 | 18
98 | HOOGHLY | SM/11288 | BHANJIPUR PIPED WATER SUPPLY SCHEME | TSM/010468 | 40015869 | New | MVS | GO2223004556PH | 28/06/2022 | 699.24 | 59.99 | 759.23 | Hooghly Division | Electrical Division | 306.73 | 31.92 | 54.88 | 0 | 393.52 | 306.73 | 31.92 | 54.88 | 0 | 393.52 | 51.83 | 27
99 | HOOGHLY | SM/18098 | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | TSM/020668 | 40066226 | New | SVS | GO2223017761PH | 27/03/2023 | 182.04 | 55.91 | 237.95 | Hooghly Division | Electrical Division | 56.08 | 27.14 | 4.56 | 0 | 87.78 | 56.08 | 27.14 | 4.56 | 0 | 87.78 | 36.89 | 26
100 | HOOGHLY | SM/13587 | Bhupatipur Mini Piped Water Supply Scheme | TSM/015661 | 40029796 | New | SVS | GO2223009485PH | 09/11/2022 | 25.02 | 8.75 | 33.76 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
101 | HOOGHLY | SM/17721 | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) | TSM/015849 | 40033653 | New | MVS | GO2223016708PH | 17/03/2023 | 799.95 | 61.38 | 861.33 | Hooghly Division | Electrical Division | 122.34 | 6.78 | 141.47 | 0 | 270.58 | 122.34 | 6.78 | 141.47 | 0 | 270.58 | 31.41 | 18
102 | HOOGHLY | SM/17719 | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) | TSM/015863 | 40033652 | New | MVS | GO2223016706PH | 17/03/2023 | 345.79 | 52.87 | 398.66 | Hooghly Division | Electrical Division | 140.7 | 29.61 | 23.5 | 0 | 193.81 | 140.7 | 29.61 | 23.5 | 0 | 193.81 | 48.62 | 17
103 | HOOGHLY | SM/16236 | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly | TSM/016029 | 40032459 | New | MVS | GO2223014886PH | 24/02/2023 | 808.54 | 42.97 | 851.51 | Hooghly Division | Electrical Division | 530.02 | 34.47 | 33.15 | 0 | 597.64 | 521.68 | 34.47 | 33.15 | 0 | 589.3 | 69.21 | 46
104 | HOOGHLY | SM/09825 | Bilaspur Piped Water Supply Scheme. | TSM/004576 | 40004072 | New | MVS | GO2122006342PH | 02/12/2021 | 2175.47 | 80.02 | 2255.49 | Hooghly Division | Electrical Division | 1175.75 | 73.71 | 85.04 | 0 | 1334.51 | 1175.75 | 73.71 | 85.04 | 0 | 1334.51 | 59.17 | 94
105 | HOOGHLY | SM/13568 | BINAGRAM PIPED WATER SUPPLY SCHEME | TSM/011414 | 40029737 | New | MVS | GO2223009474PH | 09/11/2022 | 1085.9 | 59.99 | 1145.89 | Hooghly Division | Electrical Division | 201.3 | 41.49 | 77.05 | 0 | 319.84 | 201.3 | 41.49 | 77.05 | 0 | 319.84 | 27.91 | 28
106 | HOOGHLY | SM/12242 | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY | TSM/014192 | 40026626 | New | MVS | GO2223007167PH | 07/09/2022 | 232.28 | 54.38 | 286.66 | Hooghly Division | Electrical Division | 158.88 | 26.15 | 2.91 | 0 | 187.93 | 158.88 | 26.15 | 2.91 | 0 | 187.93 | 65.56 | 43
107 | HOOGHLY | SM/12263 | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014425 | 40027113 | New | MVS | GO2223007155PH | 07/09/2022 | 767.32 | 64.16 | 831.48 | Hooghly Division | Electrical Division | 311.83 | 32.59 | 38.36 | 0 | 382.77 | 311.83 | 32.59 | 38.36 | 0 | 382.77 | 46.04 | 23
108 | HOOGHLY | SM/13656 | Chak Behala mini pipe water supply scheme | TSM/015569 | 40034370 | New | SVS | GO2223009515PH | 09/11/2022 | 26.66 | 8.75 | 35.41 | Hooghly Division | Electrical Division | 0 | 0 | 0.23 | 0 | 0.23 | 0 | 0 | 0.23 | 0 | 0.23 | 0.64 | 15
109 | HOOGHLY | SM/13590 | Chak mamrej mini pipe water supply scheme | TSM/015690 | 40029781 | New | SVS | GO2223009481PH | 09/11/2022 | 34 | 8.75 | 42.75 | Hooghly Division | Electrical Division | 32.46 | 8.49 | 0 | 0 | 40.96 | 32.46 | 8.49 | 0 | 0 | 40.96 | 95.82 | 63
110 | HOOGHLY | SM/13551 | Chak Netara Mini Piped Water Supply Scheme | TSM/015684 | 40033818 | New | SVS | GO2223009335PH | 04/11/2022 | 31.73 | 8.75 | 40.48 | Hooghly Division | Electrical Division | 30.39 | 8.49 | 0.41 | 0 | 39.3 | 30.39 | 8.49 | 0.41 | 0 | 39.3 | 97.09 | 62
111 | HOOGHLY | SM/12257 | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014304 | 40026727 | New | MVS | GO2223007122PH | 06/09/2022 | 747.28 | 64.16 | 811.45 | Hooghly Division | Electrical Division | 342.37 | 11.71 | 61.26 | 0 | 415.34 | 328.47 | 11.71 | 61.26 | 0 | 401.44 | 49.47 | 19
112 | HOOGHLY | SM/08995 | Chandanpur Piped Water Supply Scheme. | TSM/002250 | 40004443 | New | SVS | GO2122004667PH | 29/10/2021 | 486.65 | 0 | 486.65 | Hooghly Division | Electrical Division | 337.33 | 0 | 12.29 | 33.6 | 383.21 | 338.88 | 0 | 12.29 | 33.6 | 384.77 | 79.06 | 95
113 | HOOGHLY | SM/13657 | Char Sundalpur Mini Piped Water Supply Scheme | TSM/015633 | 40029127 | New | SVS | GO2223009522PH | 09/11/2022 | 30.39 | 8.75 | 39.14 | Hooghly Division | Electrical Division | 29.11 | 8.49 | 0 | 0 | 37.6 | 29.11 | 8.49 | 0 | 0 | 37.6 | 96.06 | 38
114 | HOOGHLY | SM/13415 | Charkona Mini Piped Water Supply Scheme | TSM/015659 | 40030199 | New | SVS | GO2223009169PH | 02/11/2022 | 26.1 | 8.75 | 34.85 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
115 | HOOGHLY | SM/12252 | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014551 | 40026624 | New | MVS | GO2223007119PH | 06/09/2022 | 468.49 | 54.66 | 523.15 | Hooghly Division | Electrical Division | 166.48 | 23.63 | 32.4 | 0 | 222.5 | 130.33 | 23.63 | 32.4 | 0 | 186.35 | 35.62 | 19
116 | HOOGHLY | SM/13596 | Chautpur Mini Piped Water Supply Scheme | TSM/015643 | 40030008 | New | SVS | GO2223009488PH | 09/11/2022 | 34.29 | 8.75 | 43.04 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
117 | HOOGHLY | SM/13558 | Chetua Mini Piped Water Supply Scheme | TSM/015644 | 40032976 | New | SVS | GO2223009328PH | 04/11/2022 | 30.19 | 8.75 | 38.93 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
118 | HOOGHLY | SM/12247 | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/015005 | 40027001 | New | MVS | GO2223007199PH | 07/09/2022 | 498.69 | 54.66 | 553.34 | Hooghly Division | Electrical Division | 356.8 | 24.43 | 16.48 | 0 | 397.71 | 356.8 | 24.43 | 16.48 | 0 | 397.71 | 71.87 | 34
119 | HOOGHLY | SM/14531 | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014549 | 40033849 | New | MVS | GO2223012602PH | 30/01/2023 | 1114.09 | 112.99 | 1227.07 | Hooghly Division | Electrical Division | 571.71 | 52.2 | 93.48 | 0 | 717.39 | 571.71 | 52.2 | 93.48 | 0 | 717.39 | 58.46 | 37
120 | HOOGHLY | SM/15898 | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | TSM/018701 | 40039081 | Augmentation | MVS | GO2223014280PH | 20/02/2023 | 37.4 | 33.73 | 71.13 | Hooghly Division | Electrical Division | 14.91 | 14.31 | 2.46 | 11.1 | 42.78 | 14.91 | 14.31 | 2.46 | 11.1 | 42.78 | 60.14 | 13
121 | HOOGHLY | SM/16449 | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | TSM/013031 | 0 | Augmentation | MVS | GO2223014987PH | 28/02/2023 | 64.68 | 64.02 | 128.7 | Hooghly Division | Electrical Division | 18.95 | 27.41 | 0 | 21.16 | 67.53 | 18.95 | 27.41 | 0 | 21.16 | 67.53 | 52.47 | 47
122 | HOOGHLY | SM/16450 | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | TSM/013033 | 40043440 | Augmentation | MVS | GO2223014986PH | 28/02/2023 | 72.15 | 64.02 | 136.17 | Hooghly Division | Electrical Division | 12.85 | 33.97 | 0.62 | 44.75 | 92.18 | 12.85 | 33.97 | 0.62 | 44.75 | 92.18 | 67.69 | 50
123 | HOOGHLY | SM/16448 | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | TSM/013029 | 40037303 | Augmentation | SVS | GO2223014989PH | 28/02/2023 | 37.31 | 26.27 | 63.58 | Hooghly Division | Electrical Division | 24.27 | 20.35 | 2.77 | 0 | 47.39 | 24.27 | 20.35 | 2.77 | 0 | 47.39 | 74.54 | 43
124 | HOOGHLY | SM/16447 | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | TSM/013254 | 40037316 | Augmentation | SVS | GO2223014988PH | 28/02/2023 | 77.88 | 31.15 | 109.03 | Hooghly Division | Electrical Division | 51.97 | 19.28 | 8.93 | 11 | 91.18 | 51.97 | 19.28 | 8.93 | 11 | 91.18 | 83.63 | 50
125 | HOOGHLY | SM/13586 | Dewanchak Mini Piped Water Supply Scheme | TSM/015683 | 40030016 | New | SVS | GO2223009491PH | 09/11/2022 | 27.47 | 8.75 | 36.22 | Hooghly Division | Electrical Division | 26.52 | 8.49 | 0 | 0 | 35.01 | 26.52 | 8.49 | 0 | 0 | 35.01 | 96.66 | 60
126 | HOOGHLY | SM/13597 | Dhanijpur Mini Piped Water Supply Scheme | TSM/015666 | 40029784 | New | SVS | GO2223009483PH | 09/11/2022 | 31.78 | 8.75 | 40.53 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
127 | HOOGHLY | SM/13670 | Digra Mini Piped Water Supply Scheme | TSM/015634 | 40029128 | New | SVS | GO2223009512PH | 09/11/2022 | 29.3 | 8.75 | 38.05 | Hooghly Division | Electrical Division | 28.12 | 8.49 | 0.33 | 0 | 36.94 | 28.12 | 8.49 | 0.33 | 0 | 36.94 | 97.09 | 37
128 | HOOGHLY | SM/12245 | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014177 | 40027121 | New | MVS | GO2223007137PH | 07/09/2022 | 625.89 | 62.54 | 688.42 | Hooghly Division | Electrical Division | 235.95 | 10.94 | 29.26 | 0 | 276.16 | 235.95 | 10.94 | 29.26 | 0 | 276.16 | 40.11 | 17
129 | HOOGHLY | SM/13591 | Dumurpara Mini Piped water Supply Scheme | TSM/015682 | 40029746 | New | SVS | GO2223009476PH | 09/11/2022 | 31.98 | 8.75 | 40.73 | Hooghly Division | Electrical Division | 30.62 | 8.49 | 0.43 | 0 | 39.54 | 30.62 | 8.49 | 0.43 | 0 | 39.54 | 97.09 | 62
130 | HOOGHLY | SM/12243 | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/015007 | 40026625 | New | MVS | GO2223007165PH | 07/09/2022 | 484.27 | 54.66 | 538.93 | Hooghly Division | Electrical Division | 234.19 | 28.72 | 31.91 | 0 | 294.83 | 212.01 | 28.72 | 31.91 | 0 | 272.65 | 50.59 | 19
131 | HOOGHLY | SM/13561 | Durlabhpur Mini Piped Water Supply Scheme | TSM/015635 | 40033954 | New | SVS | GO2223009323PH | 04/11/2022 | 31.2 | 8.75 | 39.95 | Hooghly Division | Electrical Division | 29.83 | 8.49 | 0 | 0 | 38.33 | 29.83 | 8.49 | 0 | 0 | 38.33 | 95.95 | 38
132 | HOOGHLY | SM/13553 | Dwariapur Mini Piped Water Supply Scheme | TSM/015670 | 40033658 | New | SVS | GO2223009338PH | 04/11/2022 | 31.42 | 8.75 | 40.17 | Hooghly Division | Electrical Division | 30.06 | 8.49 | 0.45 | 0 | 39 | 30.06 | 8.49 | 0.45 | 0 | 39 | 97.09 | 62
133 | HOOGHLY | SM/13665 | Dwaripara Mini Piped Water Supply Scheme | TSM/015671 | 40029656 | New | SVS | GO2223009519PH | 09/11/2022 | 34 | 8.75 | 42.75 | Hooghly Division | Electrical Division | 32.41 | 8.49 | 0.6 | 0 | 41.51 | 32.41 | 8.49 | 0.6 | 0 | 41.51 | 97.09 | 62
134 | HOOGHLY | SM/18623 | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | TSM/017299 | 40029430 | New | MVS | 2163/PHE-28011/49/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 942.95 | 118.66 | 1061.62 | Hooghly Division | Electrical Division | 396.58 | 51.53 | 25.89 | 0 | 473.99 | 396.58 | 51.53 | 25.89 | 0 | 473.99 | 44.65 | 17
135 | HOOGHLY | SM/18646 | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | TSM/018062 | 40037845 | New | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1265.99 | 55.91 | 1321.9 | Hooghly Division | Electrical Division | 0 | 13.47 | 19.35 | 0 | 32.82 | 0 | 13.47 | 19.35 | 0 | 32.82 | 2.48 | 18
136 | HOOGHLY | SM/11289 | GAURIBATI PIPED WATER SUPPLY SCHEME | TSM/010471 | 40015956 | New | MVS | GO2223004557PH | 28/06/2022 | 404.36 | 59.99 | 464.35 | Hooghly Division | Electrical Division | 271.01 | 44.5 | 25.25 | 0 | 340.76 | 271.01 | 44.5 | 25.25 | 0 | 340.76 | 73.38 | 30
137 | HOOGHLY | SM/13321 | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/015540 | 40027422 | New | MVS | GO2223008837PH | 17/10/2022 | 766.41 | 116.7 | 883.11 | Hooghly Division | Electrical Division | 502.68 | 60.91 | 43.92 | 0 | 607.51 | 502.68 | 60.91 | 43.92 | 0 | 607.51 | 68.79 | 28
138 | HOOGHLY | SM/13334 | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/015417 | 40032752 | New | MVS | GO2223008843PH | 17/10/2022 | 886.46 | 56.53 | 942.99 | Hooghly Division | Electrical Division | 555.01 | 42.71 | 35.97 | 0 | 633.69 | 555.01 | 42.71 | 35.97 | 0 | 633.69 | 67.2 | 18
139 | HOOGHLY | SM/18348 | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | TSM/015371 | 40032768 | New | MVS | 1738/PHE-28011/73/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 1035.08 | 56.53 | 1091.61 | Hooghly Division | Electrical Division | 454.08 | 31.9 | 26.2 | 0 | 512.19 | 454.08 | 31.9 | 26.2 | 0 | 512.19 | 46.92 | 44
140 | HOOGHLY | SM/13595 | Ghosha Mini Piped Water Supply Scheme | TSM/015663 | 40029794 | New | SVS | GO2223009484PH | 09/11/2022 | 33.19 | 8.75 | 41.94 | Hooghly Division | Electrical Division | 0 | 0 | 0.57 | 0 | 0.57 | 0 | 0 | 0.57 | 0 | 0.57 | 1.35 | 75
141 | HOOGHLY | SM/15247 | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly | TSM/017620 | 40033765 | New | MVS | GO2223013417PH | 07/02/2023 | 741.87 | 55.9 | 797.78 | Hooghly Division | Electrical Division | 318.53 | 27.52 | 9.97 | 0 | 356.02 | 318.53 | 27.52 | 9.97 | 0 | 356.02 | 44.63 | 75
142 | HOOGHLY | SM/14982 | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly | TSM/017627 | 40033761 | New | MVS | GO2223013128PH | 04/02/2023 | 830.51 | 55.91 | 886.42 | Hooghly Division | Electrical Division | 327.17 | 8.32 | 109.6 | 0 | 445.09 | 327.17 | 8.32 | 109.6 | 0 | 445.09 | 50.21 | 29
143 | HOOGHLY | SM/16756 | Gopalbati Piped Water Supply Scheme. | TSM/004249 | 40033840 | New | MVS | GO2223015720PH | 13/03/2023 | 385.8 | 35.39 | 421.19 | Hooghly Division | Electrical Division | 74.04 | 8.66 | 30.73 | 0 | 113.42 | 74.04 | 8.66 | 30.73 | 0 | 113.42 | 26.93 | 38
144 | HOOGHLY | SM/15890 | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | TSM/018154 | 40038049 | New | MVS | GO2223014273PH | 20/02/2023 | 873.88 | 121.58 | 995.46 | Hooghly Division | Electrical Division | 517.92 | 41.27 | 80.48 | 0 | 639.67 | 517.92 | 41.27 | 80.48 | 0 | 639.67 | 64.26 | 21
145 | HOOGHLY | SM/17628 | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS | TSM/013329 | 40053285 | New | MVS | GO2223017389PH | 21/03/2023 | 712.29 | 51.91 | 764.21 | Hooghly Division | Electrical Division | 180.65 | 32.61 | 51.17 | 0 | 264.44 | 180.65 | 32.61 | 51.17 | 0 | 264.44 | 34.6 | 19
146 | HOOGHLY | SM/10357 | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | TSM/004281 | 40033280 | New | SVS | GO2122010879PH | 16/03/2022 | 0 | 0 | 0 | Hooghly Division | Electrical Division | 387 | 28.89 | 35.43 | 10.4 | 461.71 | 387 | 28.89 | 35.43 | 10.4 | 461.71 | INF | 95
147 | HOOGHLY | SM/17627 | GROUND BASED PWSS FOR NASIBPUR | TSM/013334 | 40053287 | New | MVS | GO2223017387PH | 21/03/2023 | 847.12 | 53.07 | 900.19 | Hooghly Division | Electrical Division | 232.64 | 27.24 | 76.52 | 0 | 336.39 | 232.64 | 27.24 | 76.52 | 0 | 336.39 | 37.37 | 18
148 | HOOGHLY | SM/18642 | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017792 | 40037335 | New | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1855.23 | 119.11 | 1974.34 | Hooghly Division | Electrical Division | 0 | 1.3 | 12.79 | 0 | 14.09 | 0 | 1.3 | 12.79 | 0 | 14.09 | 0.71 | 18
149 | HOOGHLY | SM/15792 | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017805 | 40037343 | New | MVS | GO2223014311PH | 20/02/2023 | 860.87 | 55.91 | 916.78 | Hooghly Division | Electrical Division | 9.57 | 17.27 | 27.61 | 0 | 54.45 | 9.57 | 17.27 | 27.61 | 0 | 54.45 | 5.94 | 18
150 | HOOGHLY | SM/17289 | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS | TSM/016019 | 40032466 | New | MVS | GO2223016346PH | 15/03/2023 | 739.26 | 47.95 | 787.21 | Hooghly Division | Electrical Division | 437.13 | 26.55 | 20.99 | 0 | 484.67 | 430.76 | 26.55 | 20.99 | 0 | 478.3 | 60.76 | 23
151 | HOOGHLY | SM/18657 | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | TSM/020274 | 40053288 | New | MVS | 2230/PHE-28011/225/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1391.18 | 62.42 | 1453.6 | Hooghly Division | Electrical Division | 658.12 | 15.13 | 0 | 0 | 673.25 | 658.12 | 15.13 | 0 | 0 | 673.25 | 46.32 | 18
152 | HOOGHLY | SM/18594 | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017484 | 40029264 | New | MVS | 2151/PHE-28011/158/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1061 | 59.55 | 1120.56 | Hooghly Division | Electrical Division | 103.17 | 24.92 | 15.38 | 0 | 143.46 | 103.17 | 24.92 | 15.38 | 0 | 143.46 | 12.8 | 18
153 | HOOGHLY | SM/15249 | Ground Water Based Bighati (Zone -II) PWSS | TSM/017507 | 40032417 | New | MVS | GO2223013427PH | 07/02/2023 | 668.55 | 42.97 | 711.52 | Hooghly Division | Electrical Division | 322.86 | 22.15 | 68.25 | 0 | 413.25 | 322.86 | 22.15 | 68.25 | 0 | 413.25 | 58.08 | 19
154 | HOOGHLY | SM/13325 | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015550 | 40033103 | New | MVS | GO2223008841PH | 17/10/2022 | 593.98 | 53.07 | 647.04 | Hooghly Division | Electrical Division | 80 | 18.15 | 14.42 | 0 | 112.57 | 80 | 18.15 | 14.42 | 0 | 112.57 | 17.4 | 18
155 | HOOGHLY | SM/18772 | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015555 | 40033104 | New | MVS | 2564/PHE-28011/189/2023-SCHM CELL-Dept. of PHE | 25/08/2023 | 1596.3 | 58.26 | 1654.55 | Hooghly Division | Electrical Division | 135.81 | 17.06 | 22.02 | 0 | 174.89 | 135.81 | 17.06 | 22.02 | 0 | 174.89 | 10.57 | 18
156 | HOOGHLY | SM/14983 | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017581 | 40029284 | New | MVS | GO2223013187PH | 04/02/2023 | 549.74 | 55.91 | 605.65 | Hooghly Division | Electrical Division | 209.37 | 33.2 | 8.15 | 0 | 250.72 | 209.37 | 33.2 | 8.15 | 0 | 250.72 | 41.4 | 49
157 | HOOGHLY | SM/15913 | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017588 | 40029296 | New | MVS | GO2223014680PH | 22/02/2023 | 851.87 | 55.91 | 907.78 | Hooghly Division | Electrical Division | 176.39 | 22.63 | 44.94 | 0 | 243.96 | 176.39 | 22.63 | 44.94 | 0 | 243.96 | 26.87 | 23
158 | HOOGHLY | SM/17716 | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015825 | 40033253 | New | MVS | GO2223016712PH | 17/03/2023 | 672.6 | 55.91 | 728.51 | Hooghly Division | Electrical Division | 113.73 | 12.12 | 12.21 | 0 | 138.06 | 113.73 | 12.12 | 12.21 | 0 | 138.06 | 18.95 | 29
159 | HOOGHLY | SM/16651 | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME | TSM/020276 | 40053290 | New | MVS | GO2223015930PH | 14/03/2023 | 507.59 | 42.78 | 550.37 | Hooghly Division | Electrical Division | 201.4 | 24 | 12.37 | 0 | 237.77 | 201.4 | 24 | 12.37 | 0 | 237.77 | 43.2 | 27
160 | HOOGHLY | SM/15887 | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/018068 | 40037851 | New | MVS | GO2223014274PH | 20/02/2023 | 864.7 | 55.55 | 920.25 | Hooghly Division | Electrical Division | 148.7 | 39.74 | 55.73 | 0 | 244.17 | 148.7 | 39.74 | 55.73 | 0 | 244.17 | 26.53 | 24
161 | HOOGHLY | SM/19015 | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | TSM/020221 | 40053293 | New | SVS | PHE/IV/3273/W-710/23 | 27/10/2023 | 127.62 | 43.26 | 170.87 | Hooghly Division | Electrical Division | 29.15 | 20.06 | 1.82 | 0 | 51.03 | 29.15 | 20.06 | 1.82 | 0 | 51.03 | 29.86 | 11
162 | HOOGHLY | SM/12232 | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014725 | 40027411 | New | MVS | GO2223007134PH | 07/09/2022 | 709.29 | 53.07 | 762.35 | Hooghly Division | Electrical Division | 87.56 | 3.67 | 40.69 | 0 | 131.92 | 87.56 | 3.67 | 40.69 | 0 | 131.92 | 17.3 | 18
163 | HOOGHLY | SM/13320 | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015532 | 40033826 | New | MVS | GO2223008852PH | 17/10/2022 | 937.33 | 62.29 | 999.62 | Hooghly Division | Electrical Division | 254.04 | 34.56 | 46.9 | 0 | 335.5 | 254.04 | 34.56 | 46.9 | 0 | 335.5 | 33.56 | 32
164 | HOOGHLY | SM/18307 | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016111 | 40033769 | New | MVS | 1657/PHE-28011/126/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1027.42 | 62.29 | 1089.72 | Hooghly Division | Electrical Division | 421.28 | 15.88 | 35.89 | 0 | 473.05 | 421.28 | 15.88 | 35.89 | 0 | 473.05 | 43.41 | 48
165 | HOOGHLY | SM/18288 | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | TSM/017493 | 40029267 | New | MVS | 1670/PHE-28011/152/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 1123.09 | 59.55 | 1182.64 | Hooghly Division | Electrical Division | 294.27 | 24.11 | 46.45 | 0 | 364.83 | 294.27 | 24.11 | 46.45 | 0 | 364.83 | 30.85 | 25
166 | HOOGHLY | SM/18595 | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/017324 | 40033208 | New | MVS | 2151/PHE-28011/158/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1080.85 | 59.55 | 1140.41 | Hooghly Division | Electrical Division | 252.26 | 23.28 | 12.64 | 0 | 288.18 | 252.26 | 24.25 | 12.64 | 0 | 289.15 | 25.35 | 18
167 | HOOGHLY | SM/14116 | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017333 | 40033217 | New | MVS | GO2223011518PH | 02/01/2023 | 864.76 | 55.91 | 920.66 | Hooghly Division | Electrical Division | 204.99 | 10.18 | 35.96 | 0 | 251.12 | 204.99 | 10.18 | 35.96 | 0 | 251.12 | 27.28 | 14
168 | HOOGHLY | SM/17290 | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016129 | 40029263 | New | MVS | GO2223016347PH | 15/03/2023 | 347.53 | 52.87 | 400.4 | Hooghly Division | Electrical Division | 69.65 | 20.71 | 9.11 | 0 | 99.47 | 69.65 | 20.71 | 9.11 | 0 | 99.47 | 24.84 | 17
169 | HOOGHLY | SM/13324 | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015562 | 40033005 | New | MVS | GO2223008849PH | 17/10/2022 | 909.11 | 53.07 | 962.17 | Hooghly Division | Electrical Division | 191.21 | 15.2 | 14.29 | 0 | 220.7 | 191.21 | 15.2 | 14.29 | 0 | 220.7 | 22.94 | 14
170 | HOOGHLY | SM/13322 | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015564 | 40033007 | New | MVS | GO2223008845PH | 17/10/2022 | 809.87 | 53.07 | 862.94 | Hooghly Division | Electrical Division | 79.33 | 10.97 | 46.16 | 0 | 136.46 | 79.33 | 10.97 | 46.16 | 0 | 136.46 | 15.81 | 18
171 | HOOGHLY | SM/15791 | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | TSM/017827 | 40037359 | New | MVS | GO2223014298PH | 20/02/2023 | 630.95 | 111.82 | 742.77 | Hooghly Division | Electrical Division | 171.15 | 18.37 | 50.52 | 0 | 240.05 | 171.15 | 18.37 | 50.52 | 0 | 240.05 | 32.32 | 43
172 | HOOGHLY | SM/15790 | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | TSM/017830 | 40037361 | New | MVS | GO2223014304PH | 20/02/2023 | 376.84 | 55.91 | 432.75 | Hooghly Division | Electrical Division | 69.5 | 6.44 | 28.01 | 0 | 103.94 | 69.5 | 6.44 | 28.01 | 0 | 103.94 | 24.02 | 17
173 | HOOGHLY | SM/11584 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT | TSM/011523 | 40019643 | New | MVS | GO2223005419PH | 22/07/2022 | 739.72 | 201.23 | 940.95 | Hooghly Division | Electrical Division | 718.17 | 0 | 10.42 | 0 | 728.6 | 718.17 | 0 | 10.42 | 0 | 728.6 | 77.43 | 62
174 | HOOGHLY | SM/11621 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT | TSM/011522 | 40019635 | New | MVS | GO2223005561PH | 26/07/2022 | 786.94 | 209.98 | 996.92 | Hooghly Division | Electrical Division | 502.48 | 0 | 6.78 | 0 | 509.25 | 502.48 | 0 | 6.78 | 0 | 509.25 | 51.08 | 59
175 | HOOGHLY | SM/11583 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT | TSM/011514 | 40019671 | New | MVS | GO2223005413PH | 22/07/2022 | 778.97 | 218.72 | 997.69 | Hooghly Division | Electrical Division | 472.63 | 212.35 | 10.2 | 0 | 695.18 | 472.63 | 212.35 | 10.2 | 0 | 695.18 | 69.68 | 62
176 | HOOGHLY | SM/13414 | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015527 | 40033832 | New | MVS | GO2223009175PH | 02/11/2022 | 678.38 | 58.83 | 737.21 | Hooghly Division | Electrical Division | 332.9 | 31.22 | 65.55 | 0 | 429.67 | 332.9 | 31.22 | 65.55 | 0 | 429.67 | 58.28 | 79
177 | HOOGHLY | SM/16237 | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/020222 | 40053351 | New | SVS | GO2223014860PH | 24/02/2023 | 46.95 | 8.75 | 55.7 | Hooghly Division | Electrical Division | 0 | 7.43 | 24.41 | 0 | 31.84 | 0 | 7.43 | 24.41 | 0 | 31.84 | 57.17 | 20
178 | HOOGHLY | SM/12235 | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014721 | 40026627 | New | MVS | GO2223007156PH | 07/09/2022 | 922.91 | 58.26 | 981.16 | Hooghly Division | Electrical Division | 245.84 | 16.35 | 79.04 | 0 | 341.22 | 245.84 | 16.35 | 79.04 | 0 | 341.22 | 34.78 | 14
179 | HOOGHLY | SM/17626 | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/017991 | 40053352 | New | MVS | GO2223017390PH | 21/03/2023 | 553.8 | 109.39 | 663.19 | Hooghly Division | Electrical Division | 68.78 | 8.14 | 26.14 | 0 | 103.06 | 68.78 | 8.14 | 26.14 | 0 | 103.06 | 15.54 | 16
180 | HOOGHLY | SM/17625 | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/020223 | 40053356 | New | MVS | GO2223017386PH | 21/03/2023 | 627.17 | 58.26 | 685.43 | Hooghly Division | Electrical Division | 71.31 | 8.58 | 38.34 | 0 | 118.22 | 71.31 | 8.58 | 38.34 | 0 | 118.22 | 17.25 | 17
181 | HOOGHLY | SM/14118 | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017318 | 40033236 | New | MVS | GO2223011522PH | 02/01/2023 | 898.95 | 59.55 | 958.51 | Hooghly Division | Electrical Division | 173.97 | 18.35 | 64.48 | 0 | 256.8 | 147.82 | 18.35 | 64.48 | 0 | 230.64 | 24.06 | 14
182 | HOOGHLY | SM/14117 | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | TSM/017320 | 40033232 | New | MVS | GO2223011517PH | 02/01/2023 | 697.91 | 55.91 | 753.82 | Hooghly Division | Electrical Division | 274.46 | 35.62 | 32.66 | 0 | 342.75 | 274.46 | 35.62 | 32.66 | 0 | 342.75 | 45.47 | 33
183 | HOOGHLY | SM/16136 | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME | TSM/020301 | 40053375 | New | SVS | GO2223014677PH | 22/02/2023 | 188.78 | 42.78 | 231.55 | Hooghly Division | Electrical Division | 157.37 | 25.02 | 3.33 | 0 | 185.72 | 157.37 | 25.02 | 3.33 | 0 | 185.72 | 80.21 | 20
184 | HOOGHLY | SM/18429 | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014739 | 40032810 | New | MVS | 1925/PHE-28011/58/2023-SCHM CELL-Dept. of PHE | 18/07/2023 | 1083.08 | 56.53 | 1139.61 | Hooghly Division | Electrical Division | 0 | 0 | 22.47 | 0 | 22.47 | 0 | 0 | 22.47 | 0 | 22.47 | 1.97 | 22
185 | HOOGHLY | SM/12233 | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/014722 | 40027416 | New | MVS | GO2223007142PH | 07/09/2022 | 907.95 | 56.53 | 964.48 | Hooghly Division | Electrical Division | 369.63 | 8.12 | 59.21 | 0 | 436.96 | 369.63 | 8.12 | 59.21 | 0 | 436.96 | 45.31 | 14
186 | HOOGHLY | SM/18596 | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/015822 | 40029259 | New | MVS | 2151/PHE-28011/158/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1123.36 | 59.55 | 1182.91 | Hooghly Division | Electrical Division | 298.71 | 25.99 | 3.38 | 0 | 328.08 | 298.71 | 25.99 | 3.38 | 0 | 328.08 | 27.73 | 34
187 | HOOGHLY | SM/18592 | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016693 | 40033649 | New | MVS | 2150/PHE-28011/155/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1088.63 | 58.83 | 1147.47 | Hooghly Division | Electrical Division | 137.22 | 36.21 | 3.08 | 0 | 176.5 | 137.22 | 36.21 | 3.08 | 0 | 176.5 | 15.38 | 18
188 | HOOGHLY | SM/14684 | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016705 | 40033648 | New | MVS | GO2223012746PH | 31/01/2023 | 435.37 | 58.83 | 494.21 | Hooghly Division | Electrical Division | 120.14 | 18.14 | 4.96 | 0 | 143.23 | 120.14 | 18.14 | 4.96 | 0 | 143.23 | 28.98 | 17
189 | HOOGHLY | SM/18668 | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | TSM/018653 | 40053381 | New | MVS | 2237/PHE-28011/164/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1303.97 | 88.25 | 1392.22 | Hooghly Division | Electrical Division | 471.83 | 22.81 | 19.07 | 0 | 513.71 | 471.83 | 22.81 | 19.07 | 0 | 513.71 | 36.9 | 29
190 | HOOGHLY | SM/15886 | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | TSM/018655 | 40039048 | New | MVS | GO2223014275PH | 20/02/2023 | 620.46 | 58.83 | 679.29 | Hooghly Division | Electrical Division | 345.66 | 20.35 | 44.49 | 0 | 410.5 | 345.66 | 20.35 | 44.49 | 0 | 410.5 | 60.43 | 42
191 | HOOGHLY | SM/18308 | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | TSM/016117 | 40033251 | New | MVS | 1657/PHE-28011/126/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1374.39 | 59.55 | 1433.95 | Hooghly Division | Electrical Division | 96.73 | 16.63 | 19.7 | 0 | 133.05 | 96.73 | 16.63 | 19.7 | 0 | 133.05 | 9.28 | 18
192 | HOOGHLY | SM/18346 | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | TSM/015389 | 40033420 | New | MVS | 1738/PHE-28011/73/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 953.11 | 53.07 | 1006.17 | Hooghly Division | Electrical Division | 258.88 | 22.9 | 16.5 | 0 | 298.28 | 201.97 | 22.9 | 16.5 | 0 | 241.36 | 23.99 | 22
193 | HOOGHLY | SM/12254 | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014299 | 40026630 | New | MVS | GO2223007151PH | 07/09/2022 | 554.65 | 54.11 | 608.75 | Hooghly Division | Electrical Division | 65.09 | 6.67 | 34.78 | 0 | 106.55 | 65.09 | 6.67 | 34.78 | 0 | 106.55 | 17.5 | 89
194 | HOOGHLY | SM/11290 | HARAT PIPED WATER SUPPLY SCHEME | TSM/010834 | 40015940 | New | MVS | GO2223004558PH | 28/06/2022 | 610.18 | 58.26 | 668.44 | Hooghly Division | Electrical Division | 199.42 | 43.04 | 128.61 | 0 | 371.07 | 199.42 | 43.04 | 128.61 | 0 | 371.07 | 55.51 | 27
195 | HOOGHLY | SM/14122 | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016261 | 40032878 | New | MVS | GO2223011521PH | 02/01/2023 | 273.75 | 55.91 | 329.66 | Hooghly Division | Electrical Division | 177.91 | 23.47 | 22.09 | 0 | 223.47 | 177.91 | 23.47 | 22.09 | 0 | 223.47 | 67.79 | 73
196 | HOOGHLY | SM/12250 | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014199 | 40027143 | New | MVS | GO2223007121PH | 06/09/2022 | 579.25 | 57.88 | 637.12 | Hooghly Division | Electrical Division | 284.65 | 39.54 | 0 | 0 | 324.19 | 284.65 | 39.54 | 0 | 0 | 324.19 | 50.88 | 17
197 | HOOGHLY | SM/12255 | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | TSM/014302 | 40027027 | New | MVS | GO2223007129PH | 07/09/2022 | 630.24 | 58.88 | 689.12 | Hooghly Division | Electrical Division | 376.69 | 16.17 | 45.33 | 0 | 438.2 | 376.69 | 16.17 | 45.33 | 0 | 438.2 | 63.59 | 44
198 | HOOGHLY | SM/18345 | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | TSM/015413 | 40033110 | New | MVS | 1738/PHE-28011/73/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 1121 | 56.53 | 1177.52 | Hooghly Division | Electrical Division | 225.9 | 7.1 | 19.24 | 0 | 252.24 | 225.9 | 7.1 | 19.24 | 0 | 252.24 | 21.42 | 14
199 | HOOGHLY | SM/18104 | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | TSM/020533 | 40066206 | New | MVS | GO2223017763PH | 27/03/2023 | 498.65 | 55.91 | 554.56 | Hooghly Division | Electrical Division | 146.4 | 37.4 | 5.49 | 0 | 189.29 | 146.4 | 37.4 | 5.49 | 0 | 189.29 | 34.13 | 22
200 | HOOGHLY | SM/18771 | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | TSM/015416 | 40033106 | New | MVS | 2563/PHE-28011/73/2023-ESTT CELL-Dept. of PHE | 25/08/2023 | 1018.41 | 56.53 | 1074.94 | Hooghly Division | Electrical Division | 85.21 | 23.5 | 16.35 | 0 | 125.06 | 85.21 | 23.5 | 16.35 | 0 | 125.06 | 11.63 | 18
201 | HOOGHLY | SM/13762 | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | TSM/015375 | 40033115 | New | MVS | GO2223009888PH | 18/11/2022 | 924.85 | 53.07 | 977.91 | Hooghly Division | Electrical Division | 91.82 | 13.16 | 132.39 | 0 | 237.38 | 91.82 | 13.16 | 132.39 | 0 | 237.38 | 24.27 | 14
202 | HOOGHLY | SM/18927 | Improvement of BHANDARHATI Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block-Arambagh | TSM/020497 | 40067454 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 64.44 | 27.81 | 92.25 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
203 | HOOGHLY | SM/18929 | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | TSM/020405 | 40067447 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 138.69 | 55.62 | 194.31 | Hooghly Division | Electrical Division | 67.07 | 15.32 | 0 | 0 | 82.39 | 67.07 | 15.32 | 0 | 0 | 82.39 | 42.4 | 11
204 | HOOGHLY | SM/15901 | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK | TSM/020255 | 40039091 | Augmentation | MVS | GO2223014270PH | 25/02/2023 | 219.96 | 0 | 219.96 | Hooghly Division | Electrical Division | 81.58 | 0 | 0 | 0 | 81.58 | 81.58 | 0 | 0 | 0 | 81.58 | 37.09 | 90
205 | HOOGHLY | SM/18928 | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | TSM/020494 | 40067444 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 106.86 | 55.62 | 162.48 | Hooghly Division | Electrical Division | 20.43 | 0 | 0 | 0 | 20.43 | 20.43 | 0 | 0 | 0 | 20.43 | 12.57 | 10
206 | HOOGHLY | SM/18926 | Improvement of ¿MEGHSAR¿ Piped Water Supply Scheme by laying of HDPE Pipeline by HDD Process & Open cut method including restoration work at Mahanad Bandel Road within Meghsar PWSS under Chinsurah Sub Division. | TSM/020548 | 40067476 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 164.41 | 0 | 164.41 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 0.58 | 20
207 | HOOGHLY | SM/17176 | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY | TSM/014174 | 40029458 | New | MVS | GO2223016067PH | 15/03/2023 | 219.99 | 57.88 | 277.86 | Hooghly Division | Electrical Division | 98.14 | 27.61 | 9.77 | 0 | 135.52 | 98.14 | 27.61 | 9.77 | 0 | 135.52 | 48.77 | 15
208 | HOOGHLY | SM/12249 | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. | TSM/014198 | 40027192 | New | MVS | GO2223007118PH | 06/09/2022 | 601.63 | 57.88 | 659.51 | Hooghly Division | Electrical Division | 225.36 | 38.08 | 13.26 | 0 | 276.69 | 225.36 | 38.08 | 13.26 | 0 | 276.69 | 41.95 | 17
209 | HOOGHLY | SM/17632 | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. | TSM/014194 | 40029318 | New | MVS | GO2223017480PH | 22/03/2023 | 579.33 | 58.66 | 637.99 | Hooghly Division | Electrical Division | 22.64 | 17.41 | 25.53 | 0 | 65.58 | 22.64 | 17.41 | 25.53 | 0 | 65.58 | 10.28 | 17
210 | HOOGHLY | SM/13598 | Jangalpur Mini Piped Water Supply Scheme | TSM/015645 | 40030010 | New | SVS | GO2223009489PH | 09/11/2022 | 33.98 | 8.75 | 42.73 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
211 | HOOGHLY | SM/13664 | Jasapur mini pipe water supply scheme | TSM/015570 | 40029079 | New | SVS | GO2223009511PH | 09/11/2022 | 32.71 | 8.75 | 41.46 | Hooghly Division | Electrical Division | 0 | 0 | 0.59 | 0 | 0.59 | 0 | 0 | 0.59 | 0 | 0.59 | 1.42 | 17
212 | HOOGHLY | SM/13555 | Jot Mahabhat Mini Piped Water Supply Scheme | TSM/015678 | 40033824 | New | SVS | GO2223009322PH | 04/11/2022 | 30.95 | 8.75 | 39.7 | Hooghly Division | Electrical Division | 29.69 | 8.49 | 0.36 | 0 | 38.54 | 29.69 | 8.49 | 0.36 | 0 | 38.54 | 97.09 | 62
213 | HOOGHLY | SM/13672 | Jot ram mini pipe water supply scheme | TSM/015600 | 40029081 | New | SVS | GO2223009521PH | 09/11/2022 | 30.84 | 8.75 | 39.59 | Hooghly Division | Electrical Division | 0 | 0 | 0.47 | 0 | 0.47 | 0 | 0 | 0.47 | 0 | 0.47 | 1.18 | 16
214 | HOOGHLY | SM/13557 | Kaipukuria Mini Piped Water Supply Scheme | TSM/015664 | 40032473 | New | SVS | GO2223009330PH | 04/11/2022 | 32.34 | 8.75 | 41.09 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
215 | HOOGHLY | SM/18100 | KALACHHARA PIPED WATER SUPPLY SCHEME | TSM/020543 | 40066235 | New | SVS | GO2223017781PH | 27/03/2023 | 141.53 | 49.22 | 190.75 | Hooghly Division | Electrical Division | 83.28 | 12.24 | 1.8 | 0 | 97.32 | 83.28 | 12.24 | 1.8 | 0 | 97.32 | 51.02 | 17
216 | HOOGHLY | SM/18099 | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | TSM/020669 | 40066209 | New | MVS | GO2223017770PH | 27/03/2023 | 185.76 | 55.91 | 241.67 | Hooghly Division | Electrical Division | 18.07 | 21.89 | 3.22 | 0 | 43.18 | 18.07 | 21.89 | 3.22 | 0 | 43.18 | 17.87 | 21
217 | HOOGHLY | SM/12229 | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/015004 | 40026632 | New | MVS | GO2223007132PH | 07/09/2022 | 759.13 | 64.16 | 823.3 | Hooghly Division | Electrical Division | 411.28 | 18.12 | 55.9 | 0 | 485.31 | 358.92 | 18.12 | 55.9 | 0 | 432.94 | 52.59 | 26
218 | HOOGHLY | SM/12258 | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK | TSM/014418 | 40026980 | New | MVS | GO2223007168PH | 07/09/2022 | 335.71 | 54.66 | 390.37 | Hooghly Division | Electrical Division | 102.09 | 31.44 | 16.06 | 0 | 149.59 | 102.09 | 31.44 | 16.06 | 0 | 149.59 | 38.32 | 26
219 | HOOGHLY | SM/12253 | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014554 | 40026614 | New | MVS | GO2223007163PH | 08/09/2022 | 522.03 | 54.66 | 576.69 | Hooghly Division | Electrical Division | 467.08 | 32.16 | 24.81 | 0 | 524.06 | 467.08 | 32.16 | 24.81 | 0 | 524.06 | 90.87 | 18
220 | HOOGHLY | SM/18624 | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | TSM/017292 | 40029465 | New | MVS | 2163/PHE-28011/49/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 881.17 | 180.62 | 1061.79 | Hooghly Division | Electrical Division | 592.08 | 68.25 | 22.91 | 0 | 683.24 | 592.08 | 68.25 | 22.91 | 0 | 683.24 | 64.35 | 16
221 | HOOGHLY | SM/13554 | Kapsit Mini Piped Water Supply Scheme | TSM/015672 | 40033656 | New | SVS | GO2223009332PH | 04/11/2022 | 29.55 | 8.75 | 38.3 | Hooghly Division | Electrical Division | 28.37 | 8.49 | 0.33 | 0 | 37.19 | 28.37 | 8.49 | 0.33 | 0 | 37.19 | 97.09 | 61
222 | HOOGHLY | SM/12262 | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014395 | 40026934 | New | MVS | GO2223007136PH | 07/09/2022 | 695.16 | 54.66 | 749.81 | Hooghly Division | Electrical Division | 344.73 | 25.02 | 62.73 | 0 | 432.48 | 275.61 | 25.02 | 62.73 | 0 | 363.36 | 48.46 | 26
223 | HOOGHLY | SM/18097 | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME | TSM/020547 | 40066236 | New | SVS | GO2223017758PH | 27/03/2023 | 313.15 | 49.22 | 362.38 | Hooghly Division | Electrical Division | 116.64 | 36.71 | 0 | 0 | 153.35 | 116.64 | 43.78 | 0 | 0 | 160.42 | 44.27 | 20
224 | HOOGHLY | SM/18667 | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | TSM/017267 | 40033284 | New | MVS | 2237/PHE-28011/164/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1426.54 | 122.16 | 1548.7 | Hooghly Division | Electrical Division | 364.27 | 41.61 | 112.95 | 0 | 518.82 | 364.27 | 41.61 | 112.95 | 0 | 518.82 | 33.5 | 18
225 | HOOGHLY | SM/12238 | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/015006 | 40027040 | New | MVS | GO2223007147PH | 07/09/2022 | 475.76 | 58.22 | 533.98 | Hooghly Division | Electrical Division | 366.41 | 39.01 | 52.91 | 0 | 458.33 | 366.41 | 39.01 | 52.91 | 0 | 458.33 | 85.83 | 27
226 | HOOGHLY | SM/18666 | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | TSM/017304 | 40029437 | New | MVS | 2237/PHE-28011/164/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1016.97 | 119.83 | 1136.8 | Hooghly Division | Electrical Division | 495.38 | 53.9 | 119.99 | 0 | 669.26 | 495.38 | 53.9 | 119.99 | 0 | 669.26 | 58.87 | 17
227 | HOOGHLY | SM/12265 | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014552 | 40027037 | New | MVS | GO2223007139PH | 07/09/2022 | 885.45 | 62.59 | 948.04 | Hooghly Division | Electrical Division | 400.27 | 12.68 | 69.64 | 0 | 482.59 | 359.37 | 12.68 | 69.64 | 0 | 441.69 | 46.59 | 23
228 | HOOGHLY | SM/12256 | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014307 | 40026628 | New | MVS | GO2223007135PH | 07/09/2022 | 850.71 | 58.22 | 908.93 | Hooghly Division | Electrical Division | 390.25 | 22.23 | 67.26 | 0 | 479.74 | 371.19 | 22.23 | 67.26 | 0 | 460.68 | 50.68 | 19
229 | HOOGHLY | SM/13347 | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. | TSM/014169 | 40028589 | New | MVS | GO2223008455PH | 29/09/2022 | 454.06 | 63.7 | 517.76 | Hooghly Division | Electrical Division | 230.48 | 32.91 | 11.08 | 0 | 274.46 | 230.48 | 32.91 | 11.08 | 0 | 274.46 | 53.01 | 100
230 | HOOGHLY | SM/16979 | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | TSM/018155 | 40053384 | New | MVS | GO2223016567PH | 16/03/2023 | 315.64 | 55.91 | 371.55 | Hooghly Division | Electrical Division | 159.2 | 26.42 | 53.51 | 0 | 239.13 | 159.2 | 26.42 | 53.51 | 0 | 239.13 | 64.36 | 25
231 | HOOGHLY | SM/16138 | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly | TSM/018137 | 40053388 | New | MVS | GO2223014678PH | 22/02/2023 | 215.45 | 55.91 | 271.36 | Hooghly Division | Electrical Division | 156.04 | 13.13 | 7.53 | 0 | 176.69 | 156.04 | 13.13 | 7.53 | 0 | 176.69 | 65.11 | 23
232 | HOOGHLY | SM/13658 | Mamudpur Mini Piped Water Supply Scheme | TSM/015636 | 40029131 | New | SVS | GO2223009502PH | 09/11/2022 | 29.95 | 8.75 | 38.7 | Hooghly Division | Electrical Division | 28.71 | 8.49 | 0 | 0 | 37.21 | 28.71 | 8.49 | 0 | 0 | 37.21 | 96.13 | 38
233 | HOOGHLY | SM/18833 | Mayapur Piped Water Supply Scheme. | TSM/004222 | 40056346 | New | SVS | 2871/PHE-28011/244/2023-ESTT CELL-Dept. of PHE | 21/09/2023 | 1082.46 | 60.77 | 1143.23 | Hooghly Division | Electrical Division | 95.62 | 9.16 | 14.58 | 0 | 119.35 | 95.62 | 9.16 | 14.58 | 0 | 119.35 | 10.44 | 18
234 | HOOGHLY | SM/13333 | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly | TSM/015415 | 40027463 | New | MVS | GO2223008862PH | 17/10/2022 | 875.78 | 53.07 | 928.84 | Hooghly Division | Electrical Division | 73.01 | 15.94 | 30.64 | 0 | 119.59 | 73.01 | 15.94 | 30.64 | 0 | 119.59 | 12.87 | 14
235 | HOOGHLY | SM/18320 | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | TSM/018115 | 40038017 | New | MVS | 1682/PHE-28011/124/2023-SCHM CELL-Dept. of PHE | 27/06/2023 | 1255.68 | 118.66 | 1374.35 | Hooghly Division | Electrical Division | 429.61 | 29.81 | 65.04 | 0 | 524.46 | 429.61 | 29.81 | 65.04 | 0 | 524.46 | 38.16 | 17
236 | HOOGHLY | SM/13564 | Muragari Mini Piped Water Supply Scheme | TSM/015637 | 40029132 | New | SVS | GO2223009333PH | 04/11/2022 | 29.42 | 8.75 | 38.17 | Hooghly Division | Electrical Division | 28.23 | 8.49 | 0 | 0 | 36.72 | 28.23 | 8.49 | 0 | 0 | 36.72 | 96.2 | 38
237 | HOOGHLY | SM/12239 | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY | TSM/014163 | 40027230 | New | SVS | GO2223007145PH | 07/09/2022 | 586.83 | 62.54 | 649.37 | Hooghly Division | Electrical Division | 164.38 | 15.98 | 0 | 0 | 180.36 | 164.38 | 15.98 | 0 | 0 | 180.36 | 27.77 | 17
238 | HOOGHLY | SM/11291 | NAITA PIPED WATER SUPPLY SCHEME | TSM/010835 | 40015843 | New | MVS | GO2223004559PH | 28/06/2022 | 759.09 | 58.26 | 817.35 | Hooghly Division | Electrical Division | 309.14 | 26.39 | 60.83 | 11.57 | 407.93 | 309.14 | 26.39 | 60.83 | 11.57 | 407.93 | 49.91 | 85
239 | HOOGHLY | SM/12567 | NANDA PIPED WATER SUPPLY SCHEME | TSM/011424 | 40027405 | New | MVS | GO2223007710PH | 14/09/2022 | 1062.38 | 58.26 | 1120.63 | Hooghly Division | Electrical Division | 367.16 | 30.44 | 96.94 | 0 | 494.54 | 367.16 | 30.44 | 96.94 | 0 | 494.54 | 44.13 | 27
240 | HOOGHLY | SM/13562 | Naopara Mini Piped Water Supply Scheme | TSM/015638 | 40029135 | New | SVS | GO2223009327PH | 04/11/2022 | 31.81 | 8.75 | 40.56 | Hooghly Division | Electrical Division | 30.41 | 8.49 | 0 | 0 | 38.91 | 30.41 | 8.49 | 0 | 0 | 38.91 | 95.92 | 39
241 | HOOGHLY | SM/13662 | Naraharbati Mini Piped water Supply Scheme | TSM/015673 | 40029663 | New | SVS | GO2223009506PH | 09/11/2022 | 30.21 | 8.75 | 38.96 | Hooghly Division | Electrical Division | 28.96 | 8.49 | 0.37 | 0 | 37.82 | 28.96 | 8.49 | 0.37 | 0 | 37.82 | 97.09 | 61
242 | HOOGHLY | SM/18241 | NAWPARA PIPED WATER SUPPLY SCHEME | TSM/011486 | 40037181 | New | MVS | 1553/PHE-28011/141/2023-ESTT CELL-Dept. of PHE | 16/06/2023 | 1092.83 | 59.41 | 1152.24 | Hooghly Division | Electrical Division | 627.1 | 45.69 | 20.45 | 0 | 693.24 | 627.1 | 45.69 | 20.45 | 0 | 693.24 | 60.16 | 32
243 | HOOGHLY | SM/13588 | Nesraguri Mini Piped Water Supply Scheme | TSM/015646 | 40030013 | New | SVS | GO2223009490PH | 09/11/2022 | 26.83 | 8.75 | 35.58 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
244 | HOOGHLY | SM/18105 | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly | TSM/020532 | 40066207 | New | MVS | GO2223017765PH | 27/03/2023 | 617.99 | 55.91 | 673.9 | Hooghly Division | Electrical Division | 171.76 | 35.55 | 40.65 | 0 | 247.96 | 171.76 | 35.55 | 40.65 | 0 | 247.96 | 36.79 | 22
245 | HOOGHLY | SM/18778 | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | TSM/015193 | 40029442 | New | MVS | 2579/PHE-28011/164/2023-SCHM CELL-Dept. of PHE | 28/08/2023 | 990.11 | 116.92 | 1107.03 | Hooghly Division | Electrical Division | 91.79 | 36.89 | 0 | 0 | 128.68 | 91.79 | 36.89 | 0 | 0 | 128.68 | 11.62 | 22
246 | HOOGHLY | SM/13659 | Palpukur Mini Piped Water Supply Scheme | TSM/015679 | 40029662 | New | SVS | GO2223009525PH | 09/11/2022 | 27.81 | 8.75 | 36.56 | Hooghly Division | Electrical Division | 26.82 | 8.49 | 0.18 | 0 | 35.49 | 26.82 | 8.49 | 0.18 | 0 | 35.49 | 97.09 | 60
247 | HOOGHLY | SM/11292 | PANRRA PIPED WATER SUPPLY SCHEME | TSM/010824 | 40015951 | New | MVS | GO2223004560PH | 28/06/2022 | 921.77 | 65.76 | 987.53 | Hooghly Division | Electrical Division | 320.14 | 29 | 59.22 | 0 | 408.37 | 320.14 | 29 | 59.22 | 0 | 408.37 | 41.35 | 68
248 | HOOGHLY | SM/13559 | Par adra mini pipe water supply scheme | TSM/015601 | 40029091 | New | SVS | GO2223009324PH | 04/11/2022 | 32.52 | 8.75 | 41.27 | Hooghly Division | Electrical Division | 0 | 0 | 0.58 | 0 | 0.58 | 0 | 0 | 0.58 | 0 | 0.58 | 1.4 | 16
249 | HOOGHLY | SM/13335 | PARJANA PIPED WATER SUPPLY SCHEME | TSM/015453 | 40033418 | New | MVS | GO2223008863PH | 17/10/2022 | 864.26 | 85.75 | 950 | Hooghly Division | Electrical Division | 451.88 | 36.28 | 49.4 | 0 | 537.57 | 451.88 | 36.28 | 49.4 | 0 | 537.57 | 56.59 | 26
250 | HOOGHLY | SM/12259 | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK | TSM/014410 | 40027042 | New | MVS | GO2223007133PH | 07/09/2022 | 509.14 | 54.66 | 563.79 | Hooghly Division | Electrical Division | 272.31 | 13.23 | 18.31 | 0 | 303.84 | 272.31 | 13.23 | 18.31 | 0 | 303.84 | 53.89 | 34
251 | HOOGHLY | SM/18310 | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | TSM/017614 | 40033183 | New | MVS | 1657/PHE-28011/126/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1285.12 | 86.9 | 1372.02 | Hooghly Division | Electrical Division | 61.75 | 12.11 | 19.44 | 0 | 93.3 | 61.75 | 12.11 | 19.44 | 0 | 93.3 | 6.8 | 13
252 | HOOGHLY | SM/18931 | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | TSM/020469 | 40067480 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 0 | 83.25 | 83.25 |  | Electrical Division | 0 | 27.26 | 0 | 0 | 27.26 | 0 | 27.26 | 0 | 0 | 27.26 | 32.74 | 1
253 | HOOGHLY | SM/18930 | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | TSM/020453 | 40067481 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 0 | 55.3 | 55.3 |  | Electrical Division | 0 | 36.53 | 0 | 0 | 36.53 | 0 | 36.53 | 0 | 0 | 36.53 | 66.06 | 1
254 | HOOGHLY | SM/06754 | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | TSM/005640 | 8136198 | Retrofitting | MVS | GO2021001277PH | 18/09/2020 | 73.81 | 0 | 73.81 | Hooghly Division |  | 68.4 | 0 | 0 | 0 | 68.4 | 68.4 | 0 | 0 | 0 | 68.4 | 92.68 | 100
255 | HOOGHLY | SM/13666 | Purba Chakla Mini Piped Water Supply Scheme | TSM/015674 | 40029646 | New | SVS | GO2223009516PH | 09/11/2022 | 31.58 | 8.75 | 40.33 | Hooghly Division | Electrical Division | 30.2 | 8.49 | 0.46 | 0 | 39.16 | 30.2 | 8.49 | 0.46 | 0 | 39.16 | 97.09 | 61
256 | HOOGHLY | SM/11582 | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME | TSM/011485 | 40017455 | New | MVS | GO2223005433PH | 22/07/2022 | 623.86 | 57.68 | 681.54 | Hooghly Division | Electrical Division | 352.66 | 25.59 | 10.44 | 0 | 388.68 | 352.66 | 25.59 | 10.44 | 0 | 388.68 | 57.03 | 22
257 | HOOGHLY | SM/18672 | Raghubati Piped Water Supply Scheme. | TSM/002251 | 40060376 | New | MVS | 2240/PHE-28011/122/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1094.57 | 34.59 | 1129.16 | Hooghly Division | Electrical Division | 434.8 | 15.95 | 10.81 | 0 | 461.56 | 434.8 | 15.95 | 10.81 | 0 | 461.56 | 40.88 | 54
258 | HOOGHLY | SM/18095 | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK | TSM/020670 | 40066223 | New | SVS | GO2223017760PH | 27/03/2023 | 219.07 | 55.91 | 274.98 | Hooghly Division | Electrical Division | 117.72 | 39.76 | 5.88 | 0 | 163.36 | 117.72 | 40.03 | 5.88 | 0 | 163.63 | 59.51 | 26
259 | HOOGHLY | SM/16757 | Ramnagar Piped Water Supply Scheme. | TSM/004216 | 40028164 | New | MVS | GO2223015719PH | 13/03/2023 | 716.62 | 38.77 | 755.39 | Hooghly Division | Electrical Division | 584.97 | 36.26 | 41.58 | 0 | 662.81 | 584.97 | 36.26 | 41.58 | 0 | 662.81 | 87.74 | 81
260 | HOOGHLY | SM/13563 | Rampur Mini Piped Water Supply Scheme | TSM/015640 | 40029310 | New | SVS | GO2223009326PH | 04/11/2022 | 33.47 | 8.75 | 42.21 | Hooghly Division | Electrical Division | 31.91 | 8.49 | 0 | 0 | 40.41 | 31.91 | 8.49 | 0 | 0 | 40.41 | 95.72 | 38
261 | HOOGHLY | SM/13667 | Rautara Mini Piped Water Supply Scheme | TSM/015680 | 40029651 | New | SVS | GO2223009527PH | 09/11/2022 | 34.56 | 8.75 | 43.31 | Hooghly Division | Electrical Division | 27.81 | 8.49 | 0.6 | 0 | 36.9 | 27.81 | 8.49 | 0.6 | 0 | 36.9 | 85.21 | 62
262 | HOOGHLY | SM/15250 | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/016533 | 40033873 | New | MVS | GO2223013456PH | 07/02/2023 | 290.85 | 54.66 | 345.51 | Hooghly Division | Electrical Division | 158.25 | 49.51 | 24.34 | 0 | 232.1 | 158.25 | 49.51 | 24.34 | 0 | 232.1 | 67.18 | 35
263 | HOOGHLY | SM/15251 | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/016556 | 40033869 | New | MVS | GO2223013449PH | 07/02/2023 | 282.25 | 54.66 | 336.9 | Hooghly Division | Electrical Division | 179.85 | 19.92 | 9.67 | 0 | 209.44 | 179.85 | 19.92 | 9.67 | 0 | 209.44 | 62.17 | 37
264 | HOOGHLY | SM/16648 | RETROFITTING FOR BANDIPUR WS SCHEME | TSM/020287 | 40053395 | Retrofitting | MVS | GO2223015929PH | 14/03/2023 | 99.14 | 0 | 99.14 | Hooghly Division |  | 39.43 | 0 | 0 | 0 | 39.43 | 39.43 | 0 | 0 | 0 | 39.43 | 39.77 | 74
265 | HOOGHLY | SM/06987 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | TSM/006249 | 40015217 | Retrofitting | MVS | GO2021002508PH | 11/11/2020 | 92.65 | 0 | 92.65 | Hooghly Division |  | 58.57 | 0 | 0 | 0 | 58.57 | 58.57 | 0 | 0 | 0 | 58.57 | 63.22 | 100
266 | HOOGHLY | SM/07463 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | TSM/006269 | 8190797 | Retrofitting | MVS | GO2021003869PH | 30/12/2020 | 130.74 | 0 | 130.74 | Hooghly Division |  | 126.93 | 0 | 0 | 0 | 126.93 | 126.93 | 0 | 0 | 0 | 126.93 | 97.08 | 100
267 | HOOGHLY | SM/06989 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | TSM/006261 | 6132548 | Retrofitting | SVS | GO2021002510PH | 11/11/2020 | 57.3 | 0 | 57.3 | Hooghly Division |  | 20.6 | 0 | 0 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 20.6 | 35.95 | 100
268 | HOOGHLY | SM/06990 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme | TSM/006262 | 40033155 | Retrofitting | SVS | GO2021002511PH | 11/11/2020 | 80.57 | 0 | 80.57 | Hooghly Division |  | 80.02 | 0 | 0 | 0 | 80.02 | 80.02 | 0 | 0 | 0 | 80.02 | 99.32 | 99
269 | HOOGHLY | SM/06992 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | TSM/006263 | 8136239 | Retrofitting | SVS | GO2021002513PH | 11/11/2020 | 98.98 | 0 | 98.98 | Hooghly Division |  | 54.1 | 0 | 12.32 | 8.98 | 75.4 | 54.1 | 0 | 12.32 | 8.98 | 75.4 | 76.18 | 100
270 | HOOGHLY | SM/07149 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme | TSM/006264 | 8136249 | Retrofitting | MVS | GO2021002887PH | 01/12/2020 | 77.24 | 0 | 77.24 | Hooghly Division |  | 60 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 77.68 | 95
271 | HOOGHLY | SM/07150 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under | TSM/006265 | 8136249 | Retrofitting | MVS | GO2021002885PH | 01/12/2020 | 56.16 | 0 | 56.16 | Hooghly Division |  | 10.01 | 0 | 0 | 0 | 10.01 | 10.01 | 0 | 0 | 0 | 10.01 | 17.83 | 100
272 | HOOGHLY | SM/06993 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | TSM/006266 | 8136260 | Retrofitting | MVS | GO2021002515PH | 11/11/2020 | 79.51 | 0 | 79.51 | Hooghly Division |  | 27.88 | 0 | 0 | 0 | 27.88 | 27.88 | 0 | 0 | 0 | 27.88 | 35.06 | 98
273 | HOOGHLY | SM/07462 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | TSM/006270 | 8190834 | Retrofitting | MVS | GO2021003871PH | 30/12/2020 | 184.15 | 0 | 184.15 | Hooghly Division |  | 106.68 | 0 | 0 | 0 | 106.68 | 106.59 | 0 | 0 | 0 | 106.59 | 57.88 | 100
274 | HOOGHLY | SM/07461 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | TSM/006271 | 8190841 | Retrofitting | MVS | GO2021003873PH | 30/12/2020 | 111.14 | 0 | 111.14 | Hooghly Division |  | 95.18 | 0 | 0 | 0 | 95.18 | 90.79 | 0 | 0 | 0 | 90.79 | 81.69 | 100
275 | HOOGHLY | SM/06994 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio | TSM/006267 | 8136263 | Retrofitting | SVS | GO2021002516PH | 11/11/2020 | 68.52 | 0 | 68.52 | Hooghly Division |  | 68 | 0 | 0 | 0 | 68 | 68 | 0 | 0 | 0 | 68 | 99.24 | 99
276 | HOOGHLY | SM/07151 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | TSM/006268 | 8136263 | Retrofitting | SVS | GO2021002886PH | 01/12/2020 | 69.81 | 0 | 69.81 | Hooghly Division |  | 56.87 | 0 | 0 | 0 | 56.87 | 53.95 | 0 | 0 | 0 | 53.95 | 77.28 | 100
277 | HOOGHLY | SM/07460 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | TSM/006272 | 8190866 | Retrofitting | SVS | GO2021003874PH | 30/12/2020 | 145.28 | 0 | 145.28 | Hooghly Division |  | 121.48 | 0 | 0.08 | 0 | 121.56 | 113.67 | 0 | 0.08 | 0 | 113.76 | 78.3 | 100
278 | HOOGHLY | SM/06991 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | TSM/006273 | 8136271 | Retrofitting | MVS | GO2021002518PH | 11/11/2020 | 83.37 | 0 | 83.37 | Hooghly Division |  | 80.94 | 0 | 0 | 0 | 80.94 | 80.94 | 0 | 0 | 0 | 80.94 | 97.09 | 100
279 | HOOGHLY | SM/06988 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar Mouza of Borhol Zone-II Water Supply Scheme | TSM/006259 | 0 | Retrofitting | MVS | GO2021002509PH | 11/11/2020 | 75.19 | 0 | 75.19 | Hooghly Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
280 | HOOGHLY | SM/18108 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block | TSM/020536 | 40066220 | Retrofitting | MVS | GO2223017785PH | 27/03/2023 | 20.53 | 0 | 20.53 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
281 | HOOGHLY | SM/18107 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block | TSM/020540 | 40066218 | Retrofitting | MVS | GO2223017782PH | 27/03/2023 | 21.7 | 0 | 21.7 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
282 | HOOGHLY | SM/18106 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block | TSM/020539 | 40066214 | Retrofitting | MVS | GO2223017772PH | 27/03/2023 | 21.11 | 0 | 21.11 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 4.52 | 20
283 | HOOGHLY | SM/18109 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block | TSM/020535 | 40066215 | Retrofitting | MVS | GO2223017776PH | 27/03/2023 | 41.33 | 0 | 41.33 | Hooghly Division | Electrical Division | 6.03 | 0 | 0 | 0 | 6.03 | 6.03 | 0 | 0 | 0 | 6.03 | 14.59 | 20
284 | HOOGHLY | SM/18111 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Hasampur Water Supply Scheme Under Dhaniakhali Block | TSM/020538 | 40066224 | Retrofitting | MVS | GO2223017779PH | 27/03/2023 | 20.53 | 0 | 20.53 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
285 | HOOGHLY | SM/06763 | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | TSM/005631 | 7355421 | Retrofitting | MVS | GO2021001268PH | 18/09/2020 | 99.47 | 0 | 99.47 | Hooghly Division |  | 60.55 | 0 | 0 | 0 | 60.55 | 60.55 | 0 | 0 | 0 | 60.55 | 60.87 | 98
286 | HOOGHLY | SM/06766 | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | TSM/005639 | 8136198 | Retrofitting | MVS | GO2021001275PH | 18/09/2020 | 93.4 | 0 | 93.4 | Hooghly Division |  | 90.43 | 0 | 0 | 0.24 | 90.67 | 90.43 | 0 | 0 | 0.24 | 90.67 | 97.08 | 100
287 | HOOGHLY | SM/06757 | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 1374 nos Functional Household Tap Connection(FHTC) | TSM/005632 | 8136095 | Retrofitting | MVS | GO2021001278PH | 18/09/2020 | 99.73 | 0 | 99.73 | Hooghly Division |  | 7.58 | 0 | 0 | 0 | 7.58 | 7.58 | 0 | 0 | 0 | 7.58 | 7.6 | 100
288 | HOOGHLY | SM/06760 | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) | TSM/005633 | 8136095 | Retrofitting | MVS | GO2021001279PH | 18/09/2020 | 43.92 | 0 | 43.92 | Hooghly Division |  | 0 | 0 | 0 | 13.77 | 13.77 | 0 | 0 | 0 | 13.77 | 13.77 | 31.35 | 100
289 | HOOGHLY | SM/06761 | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | TSM/005634 | 8136095 | Retrofitting | MVS | GO2021001271PH | 18/09/2020 | 83.39 | 0 | 83.39 | Hooghly Division |  | 74.75 | 0 | 0 | 7.25 | 82 | 74.75 | 0 | 0 | 7.25 | 82 | 98.34 | 100
290 | HOOGHLY | SM/06765 | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | TSM/005642 | 8136209 | Retrofitting | MVS | GO2021001274PH | 18/09/2020 | 89.54 | 0 | 89.54 | Hooghly Division |  | 61.03 | 0 | 12.32 | 0 | 73.35 | 49.06 | 0 | 12.32 | 0 | 61.38 | 68.55 | 100
291 | HOOGHLY | SM/11004 | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | TSM/010297 | 7589585 | Retrofitting | MVS | GO2223003715PH | 01/06/2022 | 244.08 | 0 | 244.08 | Hooghly Division |  | 190.88 | 0 | 0 | 0 | 190.88 | 190.88 | 0 | 0 | 0 | 190.88 | 78.2 | 100
292 | HOOGHLY | SM/11003 | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010356 | 7355467 | Retrofitting | MVS | GO2223003717PH | 01/06/2022 | 51.92 | 0 | 51.92 | Hooghly Division |  | 2.43 | 0 | 12.32 | 0 | 14.75 | 2.43 | 0 | 12.32 | 0 | 14.75 | 28.42 | 100
293 | HOOGHLY | SM/11005 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | TSM/009992 | 40014757 | Retrofitting | MVS | GO2223003714PH | 01/06/2022 | 270.62 | 0 | 270.62 | Hooghly Division | Electrical Division | 219.67 | 0 | 11.4 | 0 | 231.07 | 219.67 | 0 | 11.4 | 0 | 231.07 | 85.39 | 100
294 | HOOGHLY | SM/11165 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | TSM/009991 | 40014663 | Retrofitting | MVS | GO2223003788PH | 02/06/2022 | 264.04 | 0 | 264.04 | Hooghly Division |  | 118.69 | 0 | 11.4 | 10.83 | 140.92 | 118.69 | 0 | 11.4 | 10.83 | 140.92 | 53.37 | 100
295 | HOOGHLY | SM/12001 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME | TSM/010987 | 7940575 | Retrofitting | MVS | GO2223006903PH | 01/09/2022 | 88.46 | 0 | 88.46 | Hooghly Division |  | 59.67 | 0 | 0 | 0 | 59.67 | 59.67 | 0 | 0 | 0 | 59.67 | 67.46 | 95
296 | HOOGHLY | SM/12000 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | TSM/011111 | 40026587 | Retrofitting | MVS | GO2223006904PH | 01/09/2022 | 148.75 | 0 | 148.75 | Hooghly Division |  | 40.78 | 0 | 0 | 0 | 40.78 | 40.78 | 0 | 0 | 0 | 40.78 | 27.42 | 100
297 | HOOGHLY | SM/11990 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | TSM/011098 | 40026375 | Retrofitting | MVS | GO2223006906PH | 01/09/2022 | 376.63 | 0 | 376.63 | Hooghly Division |  | 172.77 | 0 | 15.88 | 0 | 188.65 | 172.77 | 0 | 15.88 | 0 | 188.65 | 50.09 | 95
298 | HOOGHLY | SM/11002 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | TSM/009990 | 40014821 | Retrofitting | MVS | GO2223003718PH | 01/06/2022 | 371.11 | 0 | 371.11 | Hooghly Division |  | 139.89 | 0 | 5.7 | 0 | 145.59 | 139.89 | 0 | 5.7 | 0 | 145.59 | 39.23 | 100
299 | HOOGHLY | SM/11999 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BATANAL WATER SUPPLY SCHEME | TSM/011094 | 7940623 | Retrofitting | MVS | GO2223006907PH | 01/09/2022 | 218.68 | 0 | 218.68 | Hooghly Division |  | 73.68 | 0 | 0 | 0 | 73.68 | 73.68 | 0 | 0 | 0 | 73.68 | 33.69 | 100
300 | HOOGHLY | SM/12012 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) | TSM/010979 | 40021236 | Retrofitting | SVS | GO2223006908PH | 01/09/2022 | 47.77 | 0 | 47.77 | Hooghly Division |  | 45.38 | 0 | 0 | 0 | 45.38 | 45.38 | 0 | 0 | 0 | 45.38 | 95 | 100
301 | HOOGHLY | SM/12014 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | TSM/011091 | 7940552 | Retrofitting | MVS | GO2223006909PH | 01/09/2022 | 197.98 | 0 | 197.98 | Hooghly Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
302 | HOOGHLY | SM/11997 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | TSM/011090 | 40019990 | Retrofitting | MVS | GO2223006899PH | 01/09/2022 | 213.94 | 0 | 213.94 | Hooghly Division |  | 73.26 | 0 | 0 | 0 | 73.26 | 73.26 | 0 | 0 | 0 | 73.26 | 34.24 | 100
303 | HOOGHLY | SM/12015 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | TSM/010985 | 7940820 | Retrofitting | MVS | GO2223006911PH | 01/09/2022 | 163.75 | 0 | 163.75 | Hooghly Division |  | 117.86 | 0 | 0 | 0 | 117.86 | 117.86 | 0 | 0 | 0 | 117.86 | 71.97 | 97
304 | HOOGHLY | SM/11998 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME | TSM/010984 | 7573630 | Retrofitting | MVS | GO2223006914PH | 01/09/2022 | 140.93 | 0 | 140.93 | Hooghly Division |  | 25.49 | 0 | 0 | 0 | 25.49 | 25.49 | 0 | 0 | 0 | 25.49 | 18.09 | 100
305 | HOOGHLY | SM/12002 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | TSM/010980 | 7940671 | Retrofitting | MVS | GO2223006915PH | 01/09/2022 | 217.2 | 0 | 217.2 | Hooghly Division |  | 97.18 | 0 | 0 | 0 | 97.18 | 97.18 | 0 | 0 | 0 | 97.18 | 44.74 | 100
306 | HOOGHLY | SM/12013 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SRIPUR-BALAGARH WATER SUPPLY SCHEME | TSM/011088 | 40019969 | Retrofitting | MVS | GO2223006917PH | 01/09/2022 | 199.03 | 0 | 199.03 | Hooghly Division |  | 30.15 | 0 | 0 | 0 | 30.15 | 30.15 | 0 | 0 | 0 | 30.15 | 15.15 | 100
307 | HOOGHLY | SM/10135 | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | TSM/009771 | 40004908 | Retrofitting | MVS | GO2122009346PH | 08/02/2022 | 137.19 | 0 | 137.19 | Hooghly Division |  | 84.42 | 0 | 0 | 0 | 84.42 | 84.42 | 0 | 0 | 0 | 84.42 | 61.53 | 100
308 | HOOGHLY | SM/10134 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | TSM/009772 | 40004892 | Retrofitting | MVS | GO2122009358PH | 08/02/2022 | 88.95 | 0 | 88.95 | Hooghly Division |  | 57.55 | 0 | 0 | 0 | 57.55 | 57.55 | 0 | 0 | 0 | 57.55 | 64.7 | 100
309 | HOOGHLY | SM/10133 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | TSM/009778 | 40004896 | Retrofitting | MVS | GO2122009342PH | 08/02/2022 | 99.96 | 0 | 99.96 | Hooghly Division |  | 86.06 | 0 | 10.98 | 0 | 97.04 | 86.06 | 0 | 10.98 | 0 | 97.04 | 97.08 | 100
310 | HOOGHLY | SM/10132 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte | TSM/009779 | 40004906 | Retrofitting | MVS | GO2122009348PH | 08/02/2022 | 126.17 | 0 | 126.17 | Hooghly Division |  | 80.4 | 0 | 0 | 0 | 80.4 | 80.4 | 0 | 0 | 0 | 80.4 | 63.72 | 100
311 | HOOGHLY | SM/06764 | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | TSM/005636 | 8136191 | Retrofitting | MVS | GO2021001273PH | 18/09/2020 | 70.7 | 0 | 70.7 | Hooghly Division |  | 62.91 | 0 | 0 | 0 | 62.91 | 62.91 | 0 | 0 | 0 | 62.91 | 88.99 | 100
312 | HOOGHLY | SM/10136 | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | TSM/009766 | 40004909 | Retrofitting | MVS | GO2122009343PH | 08/02/2022 | 104.32 | 0 | 104.32 | Hooghly Division |  | 48.85 | 0 | 0 | 0 | 48.85 | 48.85 | 0 | 0 | 0 | 48.85 | 46.82 | 100
313 | HOOGHLY | SM/07540 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | TSM/006701 | 8199368 | Retrofitting | MVS | GO2021003919PH | 31/12/2020 | 66.84 | 0 | 66.84 | Hooghly Division |  | 50.2 | 0 | 0 | 10.28 | 60.48 | 45.15 | 0 | 0 | 10.28 | 55.44 | 82.94 | 100
314 | HOOGHLY | SM/09069 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. | TSM/008206 | 6865610 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 95.2 | 0 | 95.2 | Hooghly Division |  | 22.5 | 0 | 0 | 4.21 | 26.71 | 22.5 | 0 | 0 | 4.21 | 26.71 | 28.06 | 100
315 | HOOGHLY | SM/07442 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | TSM/006691 | 8191612 | Retrofitting | MVS | GO2021003865PH | 30/12/2020 | 123.87 | 0 | 123.87 | Hooghly Division |  | 90.58 | 0 | 0 | 23.55 | 114.13 | 90.58 | 0 | 0 | 23.55 | 114.13 | 92.13 | 100
316 | HOOGHLY | SM/07534 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | TSM/006676 | 8199398 | Retrofitting | MVS | GO2021003920PH | 31/12/2020 | 72.23 | 0 | 72.23 | Hooghly Division |  | 67.59 | 0 | 0 | 0 | 67.59 | 67.59 | 0 | 0 | 0 | 67.59 | 93.58 | 100
317 | HOOGHLY | SM/07946 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. | TSM/007127 | 7350475 | Retrofitting | MVS | GO2021004958PH | 21/01/2021 | 97.35 | 0 | 97.35 | Hooghly Division |  | 94.29 | 0 | 0 | 0 | 94.29 | 94.06 | 0 | 0 | 0 | 94.06 | 96.62 | 100
318 | HOOGHLY | SM/07957 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. | TSM/007137 | 8197306 | Retrofitting | MVS | GO2021004978PH | 21/01/2021 | 163.57 | 0 | 163.57 | Hooghly Division |  | 95.91 | 0 | 0 | 0 | 95.91 | 84.06 | 0 | 0 | 0 | 84.06 | 51.39 | 100
319 | HOOGHLY | SM/07958 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | TSM/007138 | 8197334 | Retrofitting | MVS | GO2021004969PH | 21/01/2021 | 119.68 | 0 | 119.68 | Hooghly Division |  | 109.14 | 0 | 0 | 0 | 109.14 | 109.14 | 0 | 0 | 0 | 109.14 | 91.19 | 100
320 | HOOGHLY | SM/08743 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | TSM/007483 | 7940653 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 147.07 | 0 | 147.07 | Hooghly Division |  | 72.1 | 0 | 0 | 0 | 72.1 | 58.28 | 0 | 0 | 0 | 58.28 | 39.63 | 100
321 | HOOGHLY | SM/08738 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | TSM/007386 | 7940555 | Retrofitting | SVS | GO2122003172PH | 09/09/2021 | 134.58 | 0 | 134.58 | Hooghly Division |  | 125.65 | 0 | 0 | 0 | 125.65 | 120.65 | 0 | 0 | 0 | 120.65 | 89.65 | 100
322 | HOOGHLY | SM/07948 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | TSM/007129 | 8196760 | Retrofitting | MVS | GO2021004957PH | 21/01/2021 | 98.47 | 0 | 98.47 | Hooghly Division |  | 95.26 | 0 | 0 | 0 | 95.26 | 95.07 | 0 | 0 | 0 | 95.07 | 96.56 | 100
323 | HOOGHLY | SM/09777 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008321 | 7747635 | Retrofitting | MVS | GO2122006245PH | 30/11/2021 | 131.1 | 0 | 131.1 | Hooghly Division |  | 89.15 | 0 | 0 | 0 | 89.15 | 89.15 | 0 | 0 | 0 | 89.15 | 68 | 100
324 | HOOGHLY | SM/08744 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BHANGAMORA WATER SUPPLY SCHEME. | TSM/007484 | 7733799 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 80.9 | 0 | 80.9 | Hooghly Division |  | 60.95 | 0 | 0 | 0 | 60.95 | 48.27 | 0 | 0 | 0 | 48.27 | 59.67 | 100
325 | HOOGHLY | SM/07537 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | TSM/006707 | 8199346 | Retrofitting | MVS | GO2021003916PH | 31/12/2020 | 95.57 | 0 | 95.57 | Hooghly Division |  | 70.99 | 0 | 0 | 14.56 | 85.55 | 70.99 | 0 | 0 | 14.56 | 85.55 | 89.52 | 100
326 | HOOGHLY | SM/07443 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | TSM/006693 | 6687858 | Retrofitting | MVS | GO2021003862PH | 30/12/2020 | 115.31 | 0 | 115.31 | Hooghly Division |  | 88.89 | 0 | 11 | 0 | 99.89 | 88.89 | 0 | 11 | 0 | 99.89 | 86.63 | 100
327 | HOOGHLY | SM/09072 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. | TSM/008211 | 8384696 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 42.14 | 0 | 42.14 | Hooghly Division | Electrical Division | 31.91 | 0 | 0 | 0 | 31.91 | 31.91 | 0 | 0 | 0 | 31.91 | 75.71 | 100
328 | HOOGHLY | SM/07542 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | TSM/006695 | 8197903 | Retrofitting | MVS | GO2021003913PH | 31/12/2020 | 95.57 | 0 | 95.57 | Hooghly Division |  | 72.98 | 0 | 0 | 0 | 72.98 | 69.44 | 0 | 0 | 0 | 69.44 | 72.66 | 100
329 | HOOGHLY | SM/09774 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008318 | 40003519 | Retrofitting | MVS | GO2122006246PH | 30/11/2021 | 166.04 | 0 | 166.04 | Hooghly Division |  | 9.65 | 0 | 0 | 0 | 9.65 | 9.65 | 0 | 0 | 0 | 9.65 | 5.81 | 100
330 | HOOGHLY | SM/07945 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | TSM/007126 | 7401878 | Retrofitting | MVS | GO2021004952PH | 21/01/2021 | 74.37 | 0 | 74.37 | Hooghly Division |  | 60.07 | 0 | 10.98 | 0 | 71.05 | 60.07 | 0 | 10.98 | 0 | 71.05 | 95.54 | 100
331 | HOOGHLY | SM/07955 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | TSM/007135 | 8197031 | Retrofitting | MVS | GO2021004962PH | 21/01/2021 | 166.55 | 0 | 166.55 | Hooghly Division |  | 141.44 | 0 | 0 | 0 | 141.44 | 141.43 | 0 | 0 | 0 | 141.43 | 84.92 | 100
332 | HOOGHLY | SM/07438 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. | TSM/006702 | 8192740 | Retrofitting | MVS | GO2021003877PH | 30/12/2020 | 272.67 | 0 | 272.67 | Hooghly Division |  | 0 | 0 | 0.08 | 0 | 0.08 | 0 | 0 | 0.08 | 0 | 0.08 | 0.03 | 100
333 | HOOGHLY | SM/07536 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | TSM/006708 | 8192815 | Retrofitting | MVS | GO2021003921PH | 31/12/2020 | 81.79 | 0 | 81.79 | Hooghly Division |  | 75.25 | 0 | 0 | 0 | 75.25 | 74.43 | 0 | 0 | 0 | 74.43 | 91.01 | 100
334 | HOOGHLY | SM/08741 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | TSM/007389 | 7747627 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 214.13 | 0 | 214.13 | Hooghly Division |  | 149.19 | 0 | 0 | 0 | 149.19 | 128.74 | 0 | 0 | 0 | 128.74 | 60.13 | 100
335 | HOOGHLY | SM/08742 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | TSM/007390 | 7940587 | Retrofitting | SVS | GO2122003172PH | 09/09/2021 | 176.84 | 0 | 176.84 | Hooghly Division |  | 154.03 | 0 | 10.43 | 0 | 164.46 | 154.03 | 0 | 10.43 | 0 | 164.46 | 93 | 100
336 | HOOGHLY | SM/07949 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | TSM/007130 | 8196833 | Retrofitting | MVS | GO2021004959PH | 21/01/2021 | 99.58 | 0 | 99.58 | Hooghly Division |  | 91.39 | 0 | 0 | 0 | 91.39 | 91.38 | 0 | 0 | 0 | 91.38 | 91.77 | 100
337 | HOOGHLY | SM/07952 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | TSM/007139 | 8197445 | Retrofitting | MVS | GO2021004979PH | 21/01/2021 | 212.07 | 0 | 212.07 | Hooghly Division |  | 191.4 | 0 | 0 | 14.43 | 205.83 | 191.4 | 0 | 0 | 14.43 | 205.83 | 97.06 | 100
338 | HOOGHLY | SM/08740 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | TSM/007388 | 7813939 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 230.84 | 0 | 230.84 | Hooghly Division |  | 218.11 | 0 | 0 | 0 | 218.11 | 200.4 | 0 | 0 | 0 | 200.4 | 86.81 | 100
339 | HOOGHLY | SM/07539 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. | TSM/006705 | 8199334 | Retrofitting | SVS | GO2021003915PH | 31/12/2020 | 35.08 | 0 | 35.08 | Hooghly Division |  | 32.42 | 0 | 2.66 | 0 | 35.08 | 32.42 | 0 | 2.66 | 0 | 35.08 | 100 | 100
340 | HOOGHLY | SM/09068 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | TSM/008204 | 7940560 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 80.21 | 0 | 80.21 | Hooghly Division |  | 14.88 | 0 | 0 | 0 | 14.88 | 14.88 | 0 | 0 | 0 | 14.88 | 18.55 | 100
341 | HOOGHLY | SM/09067 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | TSM/008203 | 7763276 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 131.23 | 0 | 131.23 | Hooghly Division |  | 52.39 | 0 | 0 | 0 | 52.39 | 52.39 | 0 | 0 | 0 | 52.39 | 39.92 | 100
342 | HOOGHLY | SM/07439 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | TSM/006697 | 8191751 | Retrofitting | MVS | GO2021003868PH | 30/12/2020 | 157.36 | 0 | 157.36 | Hooghly Division |  | 146.44 | 0 | 0 | 0 | 146.44 | 146.44 | 0 | 0 | 0 | 146.44 | 93.06 | 100
343 | HOOGHLY | SM/09775 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008319 | 7747555 | Retrofitting | MVS | GO2122006245PH | 30/11/2021 | 234.97 | 0 | 234.97 | Hooghly Division |  | 150.43 | 0 | 0 | 0 | 150.43 | 150.43 | 0 | 0 | 0 | 150.43 | 64.02 | 100
344 | HOOGHLY | SM/07436 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | TSM/006678 | 8190882 | Retrofitting | MVS | GO2021003878PH | 30/12/2020 | 288.46 | 0 | 288.46 | Hooghly Division |  | 268.81 | 0 | 0 | 11.25 | 280.06 | 268.77 | 0 | 0 | 11.25 | 280.02 | 97.07 | 100
345 | HOOGHLY | SM/07956 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | TSM/007136 | 8197040 | Retrofitting | MVS | GO2021004980PH | 21/01/2021 | 203.01 | 0 | 203.01 | Hooghly Division |  | 167.86 | 0 | 0.08 | 0 | 167.94 | 165.83 | 0 | 0.08 | 0 | 165.92 | 81.73 | 100
346 | HOOGHLY | SM/07535 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | TSM/006681 | 8197892 | Retrofitting | MVS | GO2021003912PH | 31/12/2020 | 57.39 | 0 | 57.39 | Hooghly Division |  | 55.68 | 0 | 0 | 0 | 55.68 | 55.68 | 0 | 0 | 0 | 55.68 | 97.02 | 100
347 | HOOGHLY | SM/07953 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | TSM/007133 | 7395830 | Retrofitting | MVS | GO2021004977PH | 21/01/2021 | 78.24 | 0 | 78.24 | Hooghly Division |  | 63.24 | 0 | 12.32 | 0 | 75.56 | 63.1 | 0 | 12.32 | 0 | 75.42 | 96.4 | 100
348 | HOOGHLY | SM/07441 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | TSM/006688 | 8191600 | Retrofitting | MVS | GO2021003855PH | 30/12/2020 | 128.62 | 0 | 128.62 | Hooghly Division |  | 115.23 | 0 | 10.98 | 0 | 126.21 | 95.47 | 0 | 10.98 | 0 | 106.45 | 82.77 | 100
349 | HOOGHLY | SM/09776 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008320 | 7362766 | Retrofitting | MVS | GO2122006245PH | 30/11/2021 | 130.24 | 0 | 130.24 | Hooghly Division |  | 70.61 | 0 | 0 | 0 | 70.61 | 70.61 | 0 | 0 | 0 | 70.61 | 54.22 | 98
350 | HOOGHLY | SM/09773 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008317 | 7401863 | Retrofitting | MVS | GO2122006246PH | 30/11/2021 | 95.96 | 0 | 95.96 | Hooghly Division |  | 58.52 | 0 | 0 | 0 | 58.52 | 56.59 | 0 | 0 | 0 | 56.59 | 58.97 | 100
351 | HOOGHLY | SM/07437 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. | TSM/006703 | 8192790 | Retrofitting | MVS | GO2021003872PH | 30/12/2020 | 278.22 | 0 | 278.22 | Hooghly Division |  | 157.54 | 0 | 10.98 | 0 | 168.52 | 156.14 | 0 | 10.98 | 0 | 167.12 | 60.07 | 100
352 | HOOGHLY | SM/07440 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | TSM/006686 | 8191532 | Retrofitting | MVS | GO2021003858PH | 30/12/2020 | 230.1 | 0 | 230.1 | Hooghly Division |  | 190.94 | 0 | 0 | 0 | 190.94 | 190.94 | 0 | 0 | 0 | 190.94 | 82.98 | 100
353 | HOOGHLY | SM/07538 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | TSM/006706 | 8199354 | Retrofitting | SVS | GO2021003917PH | 31/12/2020 | 32.62 | 0 | 32.62 | Hooghly Division |  | 21.83 | 0 | 0 | 0 | 21.83 | 21.83 | 0 | 0 | 0 | 21.83 | 66.91 | 100
354 | HOOGHLY | SM/08739 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | TSM/007387 | 7573681 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 197.26 | 0 | 197.26 | Hooghly Division |  | 101.84 | 0 | 0 | 0 | 101.84 | 101.84 | 0 | 0 | 0 | 101.84 | 51.62 | 100
355 | HOOGHLY | SM/07954 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | TSM/007134 | 8197021 | Retrofitting | MVS | GO2021004974PH | 21/01/2021 | 247.47 | 0 | 247.47 | Hooghly Division |  | 179.28 | 0 | 0 | 0 | 179.28 | 178.68 | 0 | 0 | 0 | 178.68 | 72.2 | 100
356 | HOOGHLY | SM/07950 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | TSM/007131 | 8196987 | Retrofitting | MVS | GO2021004961PH | 21/01/2021 | 99.37 | 0 | 99.37 | Hooghly Division |  | 99.34 | 0 | 0 | 0 | 99.34 | 99.34 | 0 | 0 | 0 | 99.34 | 99.96 | 100
357 | HOOGHLY | SM/07543 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | TSM/006684 | 8197868 | Retrofitting | MVS | GO2021003909PH | 31/12/2020 | 86.15 | 0 | 86.15 | Hooghly Division |  | 46.56 | 0 | 0 | 0 | 46.56 | 46.56 | 0 | 0 | 0 | 46.56 | 54.05 | 100
358 | HOOGHLY | SM/07951 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | TSM/007132 | 8196994 | Retrofitting | MVS | GO2021004975PH | 21/01/2021 | 99.86 | 0 | 99.86 | Hooghly Division |  | 96.94 | 0 | 0 | 0 | 96.94 | 96.94 | 0 | 0 | 0 | 96.94 | 97.08 | 100
359 | HOOGHLY | SM/07947 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. | TSM/007128 | 8196823 | Retrofitting | MVS | GO2021004971PH | 21/01/2021 | 83.61 | 0 | 83.61 | Hooghly Division |  | 51.7 | 0 | 5.7 | 0 | 57.4 | 51.7 | 0 | 5.7 | 0 | 57.4 | 68.65 | 100
360 | HOOGHLY | SM/07541 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME | TSM/006699 | 8197916 | Retrofitting | MVS | GO2021003914PH | 31/12/2020 | 56.68 | 0 | 56.68 | Hooghly Division |  | 52.12 | 0 | 0 | 0 | 52.12 | 52.12 | 0 | 0 | 0 | 52.12 | 91.96 | 100
361 | HOOGHLY | SM/09772 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008316 | 40002442 | Retrofitting | MVS | GO2122006246PH | 30/11/2021 | 337.05 | 0 | 337.05 | Hooghly Division |  | 229.22 | 0 | 0 | 56.76 | 285.98 | 228.29 | 0 | 0 | 56.76 | 285.06 | 84.57 | 100
362 | HOOGHLY | SM/08737 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. | TSM/007385 | 7940569 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 163.87 | 0 | 163.87 | Hooghly Division |  | 66.97 | 0 | 0 | 0 | 66.97 | 66.97 | 0 | 0 | 0 | 66.97 | 40.87 | 100
363 | HOOGHLY | SM/09070 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | TSM/008207 | 8390218 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 136.85 | 0 | 136.85 | Hooghly Division |  | 121.86 | 0 | 0 | 11 | 132.86 | 121.86 | 0 | 0 | 11 | 132.86 | 97.09 | 100
364 | HOOGHLY | SM/09071 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. | TSM/008209 | 8390229 | Retrofitting | SVS | GO2122004569PH | 28/10/2021 | 50.04 | 0 | 50.04 | Hooghly Division |  | 25.3 | 0 | 0 | 0 | 25.3 | 23.45 | 0 | 0 | 0 | 23.45 | 46.86 | 100
365 | HOOGHLY | SM/07944 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | TSM/007125 | 7597918 | Retrofitting | MVS | GO2021004973PH | 21/01/2021 | 48.29 | 0 | 48.29 | Hooghly Division |  | 33.53 | 0 | 0 | 0 | 33.53 | 33.53 | 0 | 0 | 0 | 33.53 | 69.43 | 100
366 | HOOGHLY | SM/06762 | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | TSM/005637 | 8136191 | Retrofitting | MVS | GO2021001272PH | 18/09/2020 | 87.72 | 0 | 87.72 | Hooghly Division |  | 58.51 | 0 | 0 | 0 | 58.51 | 58.51 | 0 | 0 | 0 | 58.51 | 66.7 | 100
367 | HOOGHLY | SM/09066 | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | TSM/008215 | 7401875 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 97.91 | 0 | 97.91 | Hooghly Division |  | 61.71 | 0 | 0 | 11.5 | 73.21 | 52.89 | 0 | 0 | 11.5 | 64.39 | 65.76 | 100
368 | HOOGHLY | SM/18110 | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | TSM/020534 | 40066205 | Retrofitting | MVS | GO2223017771PH | 27/03/2023 | 142.51 | 0 | 142.51 | Hooghly Division |  | 101.92 | 0 | 0 | 0 | 101.92 | 101.92 | 0 | 0 | 0 | 101.92 | 71.51 | 24
369 | HOOGHLY | SM/06767 | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | TSM/005641 | 8136209 | Retrofitting | MVS | GO2021001276PH | 18/09/2020 | 99.51 | 0 | 99.51 | Hooghly Division |  | 95.2 | 0 | 0 | 0 | 95.2 | 64.62 | 0 | 0 | 0 | 64.62 | 64.94 | 100
370 | HOOGHLY | SM/06759 | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme | TSM/005638 | 8136191 | Retrofitting | SVS | GO2021001270PH | 18/09/2020 | 40.46 | 0 | 40.46 | Hooghly Division |  | 39 | 0 | 0 | 0 | 39 | 39 | 0 | 0 | 0 | 39 | 96.38 | 99
371 | HOOGHLY | SM/06758 | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Rajarambati, Talandu, Taragun Mouza of Digsui-Heora (Zone-II) PWSS | TSM/005635 | 8136095 | Retrofitting | MVS | GO2021001269PH | 18/09/2020 | 74.68 | 0 | 74.68 | Hooghly Division |  | 29.43 | 0 | 0 | 0 | 29.43 | 29.43 | 0 | 0 | 0 | 29.43 | 39.41 | 100
372 | HOOGHLY | SM/10131 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME | TSM/009864 | 40004900 | Retrofitting | MVS | GO2122009347PH | 08/02/2022 | 83.52 | 0 | 83.52 | Hooghly Division |  | 52.06 | 0 | 0 | 0 | 52.06 | 52.06 | 0 | 0 | 0 | 52.06 | 62.33 | 100
373 | HOOGHLY | SM/13357 | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | TSM/010438 | 40027926 | Retrofitting | MVS | GO2223008944PH | 19/10/2022 | 38.98 | 0 | 38.98 | Hooghly Division |  | 31.74 | 0 | 0 | 0 | 31.74 | 31.74 | 0 | 0 | 0 | 31.74 | 81.45 | 100
374 | HOOGHLY | SM/06755 | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | TSM/005629 | 8136162 | Retrofitting | SVS | GO2021001280PH | 18/09/2020 | 99.95 | 0 | 99.95 | Hooghly Division |  | 97.04 | 0 | 2.92 | 0 | 99.95 | 97.04 | 0 | 2.92 | 0 | 99.95 | 100 | 100
375 | HOOGHLY | SM/06756 | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) | TSM/005630 | 7355467 | Retrofitting | MVS | GO2021001281PH | 18/09/2020 | 99.92 | 0 | 99.92 | Hooghly Division |  | 97 | 0 | 0 | 0 | 97 | 97 | 0 | 0 | 0 | 97 | 97.08 | 100
376 | HOOGHLY | SM/11001 | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010361 | 40014814 | Retrofitting | MVS | GO2223003716PH | 01/06/2022 | 128.04 | 0 | 128.04 | Hooghly Division | Electrical Division | 48.47 | 0 | 11.4 | 0 | 59.87 | 48.47 | 0 | 11.4 | 0 | 59.87 | 46.76 | 100
377 | HOOGHLY | SM/13356 | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | TSM/010441 | 40027945 | Retrofitting | MVS | GO2223008931PH | 19/10/2022 | 103.91 | 0 | 103.91 | Hooghly Division |  | 54.39 | 0 | 0 | 0 | 54.39 | 54.39 | 0 | 0 | 0 | 54.39 | 52.35 | 100
378 | HOOGHLY | SM/13355 | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010499 | 40027938 | Retrofitting | MVS | GO2223008941PH | 19/10/2022 | 139.24 | 0 | 139.24 | Hooghly Division |  | 0.7 | 0 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0.7 | 0.5 | 30
379 | HOOGHLY | SM/13354 | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010506 | 40027946 | Retrofitting | MVS | GO2223008937PH | 19/10/2022 | 295.6 | 0 | 295.6 | Hooghly Division |  | 80.33 | 0 | 0 | 0 | 80.33 | 80.33 | 0 | 0 | 0 | 80.33 | 27.17 | 19
380 | HOOGHLY | SM/12882 | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010507 | 40026588 | Retrofitting | MVS | GO2223008138PH | 23/09/2022 | 409.9 | 0 | 409.9 | Hooghly Division |  | 80 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 80 | 19.52 | 100
381 | HOOGHLY | SM/11225 | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010362 | 6865612 | Retrofitting | MVS | GO2223004151PH | 16/06/2022 | 271.91 | 0 | 271.91 | Hooghly Division |  | 44.6 | 0 | 0 | 0 | 44.6 | 44.6 | 0 | 0 | 0 | 44.6 | 16.4 | 100
382 | HOOGHLY | SM/13353 | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010508 | 40027922 | Retrofitting | MVS | GO2223008949PH | 19/10/2022 | 186.31 | 0 | 186.31 | Hooghly Division |  | 117.26 | 0 | 0 | 0 | 117.26 | 117.26 | 0 | 0 | 0 | 117.26 | 62.94 | 98
383 | HOOGHLY | SM/11006 | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010364 | 7544501 | Retrofitting | SVS | GO2223003712PH | 01/06/2022 | 77.49 | 0 | 77.49 | Hooghly Division |  | 4.69 | 0 | 0 | 0 | 4.69 | 4.69 | 0 | 0 | 0 | 4.69 | 6.05 | 100
384 | HOOGHLY | SM/12251 | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014296 | 40026984 | New | MVS | GO2223007138PH | 07/09/2022 | 550.65 | 54.66 | 605.31 | Hooghly Division | Electrical Division | 346.76 | 9.32 | 38.28 | 0 | 394.36 | 320.3 | 9.32 | 38.28 | 0 | 367.89 | 60.78 | 18
385 | HOOGHLY | SM/13501 | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/015414 | 40032755 | New | SVS | GO2223009249PH | 02/11/2022 | 328.64 | 49.03 | 377.67 | Hooghly Division | Electrical Division | 249.15 | 33.72 | 44.71 | 0 | 327.59 | 249.15 | 33.72 | 44.71 | 0 | 327.59 | 86.74 | 79
386 | HOOGHLY | SM/13556 | Saibana Mini Piped Water Supply Scheme | TSM/015648 | 40032975 | New | SVS | GO2223009337PH | 04/11/2022 | 32.95 | 8.75 | 41.7 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
387 | HOOGHLY | SM/16127 | SAMANTA KHANDA WATER SUPPLY SCHEME | TSM/014936 | 40033661 | New | MVS | GO2223014681PH | 22/02/2023 | 749.11 | 61.38 | 810.49 | Hooghly Division | Electrical Division | 163.07 | 7.76 | 66.78 | 0 | 237.61 | 163.07 | 7.76 | 66.78 | 0 | 237.61 | 29.32 | 22
388 | HOOGHLY | SM/15252 | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) | TSM/015867 | 40033651 | New | MVS | GO2223013450PH | 07/02/2023 | 667.44 | 59.55 | 726.99 | Hooghly Division | Electrical Division | 208.84 | 11.89 | 45.45 | 0 | 266.18 | 208.84 | 7.73 | 45.45 | 0 | 262.03 | 36.04 | 18
389 | HOOGHLY | SM/14685 | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) | TSM/015871 | 40033650 | New | MVS | GO2223012657PH | 31/01/2023 | 630.7 | 59.55 | 690.25 | Hooghly Division | Electrical Division | 241.58 | 31.18 | 5.53 | 0 | 278.29 | 241.58 | 31.18 | 5.53 | 0 | 278.29 | 40.32 | 17
390 | HOOGHLY | SM/13669 | Shripala Mini Piped Water Supply Scheme | TSM/015649 | 40029657 | New | SVS | GO2223009520PH | 09/11/2022 | 33.32 | 8.75 | 42.07 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
391 | HOOGHLY | SM/13337 | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014698 | 40028619 | New | MVS | GO2223008866PH | 17/10/2022 | 714.63 | 54.66 | 769.29 | Hooghly Division | Electrical Division | 174.03 | 0 | 37.86 | 0 | 211.89 | 174.03 | 0 | 37.86 | 0 | 211.89 | 27.54 | 22
392 | HOOGHLY | SM/13421 | Shyampur Mini Piped Water Supply Scheme | TSM/015675 | 40033654 | New | SVS | GO2223009165PH | 02/11/2022 | 33.47 | 8.75 | 42.22 | Hooghly Division | Electrical Division | 31.93 | 8.49 | 0.57 | 0 | 40.99 | 31.93 | 8.49 | 0.57 | 0 | 40.99 | 97.09 | 63
393 | HOOGHLY | SM/13412 | Shyamsundarpur Mini Piped Water Supply Scheme | TSM/015651 | 40032972 | New | SVS | GO2223009168PH | 02/11/2022 | 33.91 | 8.75 | 42.66 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
394 | HOOGHLY | SM/13668 | Sibpur Mini Piped Water Supply Scheme | TSM/015652 | 40029655 | New | SVS | GO2223009518PH | 09/11/2022 | 28.49 | 8.75 | 37.24 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
395 | HOOGHLY | SM/15889 | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | TSM/018131 | 40038024 | New | MVS | GO2223014271PH | 20/02/2023 | 842.16 | 42.78 | 884.94 | Hooghly Division | Electrical Division | 163.28 | 28.64 | 58.91 | 0 | 250.83 | 163.28 | 28.64 | 58.91 | 0 | 250.83 | 28.34 | 23
396 | HOOGHLY | SM/15888 | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | TSM/018116 | 40038032 | New | MVS | GO2223014272PH | 20/02/2023 | 472.81 | 42.78 | 515.59 | Hooghly Division | Electrical Division | 268.11 | 40.73 | 7.76 | 0 | 316.6 | 268.11 | 40.73 | 7.76 | 0 | 316.6 | 61.41 | 47
397 | HOOGHLY | SM/13661 | Sikil Beldiha Mini Piped Water Supply Scheme | TSM/015676 | 40029644 | New | SVS | GO2223009513PH | 09/11/2022 | 30.68 | 8.75 | 39.43 | Hooghly Division | Electrical Division | 29.38 | 8.49 | 0.4 | 0 | 38.28 | 29.38 | 8.49 | 0.4 | 0 | 38.28 | 97.09 | 62
398 | HOOGHLY | SM/12260 | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/014409 | 40026988 | New | MVS | GO2223007144PH | 07/09/2022 | 598.51 | 54.66 | 653.17 | Hooghly Division | Electrical Division | 343.85 | 12.27 | 21.66 | 0 | 377.79 | 292.8 | 12.27 | 21.66 | 0 | 326.73 | 50.02 | 26
399 | HOOGHLY | SM/18103 | SINHAL PATAN PIPED WATER SUPPLY SCHEME | TSM/020537 | 40066233 | New | SVS | GO2223017774PH | 27/03/2023 | 134.21 | 49.22 | 183.43 | Hooghly Division | Electrical Division | 2.53 | 11.85 | 1.42 | 0 | 15.8 | 2.53 | 14.6 | 1.42 | 0 | 18.55 | 10.11 | 18
400 | HOOGHLY | SM/11580 | SIRAZPUR PIPED WATER SUPPLY SCHEME | TSM/011542 | 40017466 | New | MVS | GO2223005431PH | 22/07/2022 | 755.19 | 56.53 | 811.72 | Hooghly Division | Electrical Division | 226.89 | 31.73 | 71.54 | 0 | 330.15 | 226.89 | 31.73 | 71.54 | 0 | 330.15 | 40.67 | 22
401 | HOOGHLY | SM/18980 | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK | TSM/020554 | 40067350 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 1.81 | 0 | 0 | 0 | 1.81 | 1.81 | 0 | 0 | 0 | 1.81 | 1.76 | 10
402 | HOOGHLY | SM/18943 | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/020550 | 40067437 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 52.61 | 32.82 | 85.43 | Hooghly Division | Electrical Division | 21.79 | 11.53 | 0 | 0 | 33.32 | 21.79 | 11.53 | 0 | 0 | 33.32 | 39 | 10
403 | HOOGHLY | SM/13346 | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/014980 | 40028614 | Augmentation | MVS | GO2223008467PH | 29/09/2022 | 152.36 | 62.29 | 214.65 | Hooghly Division | Electrical Division | 122.6 | 27.63 | 0 | 0 | 150.23 | 105.76 | 27.63 | 0 | 0 | 133.38 | 62.14 | 67
404 | HOOGHLY | SM/18950 | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | TSM/020465 | 40067407 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 6.57 | 9.1 | 0 | 0 | 15.66 | 6.57 | 9.1 | 0 | 0 | 15.66 | 10.22 | 10
405 | HOOGHLY | SM/09423 | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | TSM/008682 | 40033635 | Augmentation | MVS | GO2122005524PH | 17/11/2021 | 43.82 | 0 | 43.82 | Hooghly Division | Electrical Division | 6.73 | 15.28 | 0 | 12 | 34.01 | 6.73 | 15.28 | 0 | 12 | 34.01 | 77.61 | 96
406 | HOOGHLY | SM/16124 | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | TSM/020386 | 40053398 | Augmentation | MVS | GO2223014672PH | 22/02/2023 | 135.14 | 55.62 | 190.76 | Hooghly Division | Electrical Division | 0 | 2.8 | 0 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 2.8 | 1.47 | 52
407 | HOOGHLY | SM/18941 | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020552 | 40067440 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 17.08 | 4.01 | 0 | 0 | 21.09 | 17.08 | 4.01 | 0 | 0 | 21.09 | 11.19 | 10
408 | HOOGHLY | SM/18958 | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | TSM/020455 | 40067422 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 100.17 | 55.62 | 155.79 | Hooghly Division | Electrical Division | 0 | 9.55 | 0 | 0 | 9.55 | 0 | 9.55 | 0 | 0 | 9.55 | 6.13 | 10
409 | HOOGHLY | SM/15799 | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016328 | 40037221 | Augmentation | MVS | GO2223014258PH | 20/02/2023 | 139.28 | 62.29 | 201.57 | Hooghly Division | Electrical Division | 81.2 | 32.07 | 0 | 0 | 113.28 | 81.2 | 32.07 | 0 | 0 | 113.28 | 56.2 | 29
410 | HOOGHLY | SM/18944 | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020549 | 40067436 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 19.22 | 21.63 | 0 | 0 | 40.85 | 19.22 | 21.63 | 0 | 0 | 40.85 | 21.67 | 10
411 | HOOGHLY | SM/13344 | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/014984 | 40032981 | Augmentation | MVS | GO2223008474PH | 29/09/2022 | 173.39 | 62.29 | 235.69 | Hooghly Division | Electrical Division | 72.5 | 61.36 | 37.77 | 0 | 171.63 | 72.5 | 61.36 | 37.77 | 0 | 171.63 | 72.82 | 61
412 | HOOGHLY | SM/18961 | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | TSM/020451 | 40067468 | Augmentation | SVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 118.86 | 55.62 | 174.48 | Hooghly Division | Electrical Division | 26.32 | 13.62 | 0 | 0 | 39.95 | 26.32 | 13.62 | 0 | 0 | 39.95 | 22.89 | 11
413 | HOOGHLY | SM/19161 | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | TSM/011658 | 40067475 | Augmentation | SVS | PHE/IV/193/W-03/24 | 18/01/2024 | 24.95 | 26.27 | 51.21 | Hooghly Division | Electrical Division | 9.45 | 10.87 | 0 | 0 | 20.32 | 9.45 | 10.87 | 0 | 0 | 20.32 | 39.68 | 3
414 | HOOGHLY | SM/15803 | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | TSM/020252 | 40067472 | Augmentation | MVS | GO2223014181PH | 17/02/2023 | 35.39 | 27.81 | 63.2 | Hooghly Division | Electrical Division | 9.91 | 0 | 0 | 0 | 9.91 | 9.91 | 0 | 0 | 0 | 9.91 | 15.68 | 37
415 | HOOGHLY | SM/15794 | Source Augmentation of Bamonjol PWSS | TSM/018694 | 40039078 | Augmentation | MVS | GO2223014175PH | 17/02/2023 | 28.89 | 26.27 | 55.16 | Hooghly Division | Electrical Division | 11.12 | 11.84 | 0 | 0 | 22.96 | 11.12 | 11.84 | 0 | 0 | 22.96 | 41.62 | 13
416 | HOOGHLY | SM/18936 | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020666 | 40067458 | Augmentation | SVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 8.27 | 0 | 0 | 8.27 | 0 | 8.27 | 0 | 0 | 8.27 | 4.39 | 10
417 | HOOGHLY | SM/18973 | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020634 | 40067370 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 2.51 | 0 | 0 | 0 | 2.51 | 2.51 | 0 | 0 | 0 | 2.51 | 1.33 | 10
418 | HOOGHLY | SM/15813 | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | TSM/020241 | 40067473 | Augmentation | MVS | GO2223014295PH | 20/02/2023 | 44.42 | 27.81 | 72.23 | Hooghly Division | Electrical Division | 12.33 | 7.9 | 0 | 0 | 20.23 | 12.33 | 7.9 | 0 | 0 | 20.23 | 28.01 | 45
419 | HOOGHLY | SM/15800 | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/016351 | 40039172 | Augmentation | MVS | GO2223014190PH | 17/02/2023 | 116.4 | 62.29 | 178.69 | Hooghly Division | Electrical Division | 21.16 | 21.13 | 35.98 | 0 | 78.26 | 21.16 | 21.13 | 35.98 | 0 | 78.26 | 43.8 | 25
420 | HOOGHLY | SM/18968 | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | TSM/020439 | 40067346 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 27 | 18.23 | 45.23 | Hooghly Division | Electrical Division | 24.07 | 0 | 0 | 0 | 24.07 | 24.07 | 0 | 0 | 0 | 24.07 | 53.23 | 41
421 | HOOGHLY | SM/18940 | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020639 | 40067441 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 30.51 | 12.67 | 0 | 0 | 43.18 | 30.51 | 12.67 | 0 | 0 | 43.18 | 22.91 | 10
422 | HOOGHLY | SM/18966 | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | TSM/020442 | 40067397 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 352.41 | 55.62 | 408.03 | Hooghly Division | Electrical Division | 75.59 | 15.66 | 0 | 0 | 91.25 | 75.59 | 15.66 | 0 | 0 | 91.25 | 22.36 | 20
423 | HOOGHLY | SM/18967 | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | TSM/020441 | 40067395 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 96.57 | 27.81 | 124.38 | Hooghly Division | Electrical Division | 38.92 | 21.18 | 0 | 0 | 60.09 | 38.92 | 21.18 | 0 | 0 | 60.09 | 48.31 | 100
424 | HOOGHLY | SM/18937 | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020642 | 40067443 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 19.63 | 0 | 0 | 0 | 19.63 | 19.63 | 0 | 0 | 0 | 19.63 | 10.42 | 10
425 | HOOGHLY | SM/15812 | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | TSM/020237 | 6904467 | Augmentation | MVS | GO2223014182PH | 17/02/2023 | 48.06 | 27.81 | 75.87 | Hooghly Division | Electrical Division | 0 | 0 | 9.76 | 0 | 9.76 | 0 | 0 | 9.76 | 0 | 9.76 | 12.86 | 34
426 | HOOGHLY | SM/18975 | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/020632 | 40067369 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 45.23 | 34.82 | 0 | 0 | 80.05 | 45.23 | 34.82 | 0 | 0 | 80.05 | 42.47 | 9
427 | HOOGHLY | SM/18981 | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020553 | 40067348 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 0 | 9.56 | 0 | 0 | 9.56 | 0 | 9.56 | 0 | 0 | 9.56 | 9.28 | 10
428 | HOOGHLY | SM/18978 | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020629 | 40067355 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 34.59 | 22.66 | 0 | 0 | 57.25 | 34.59 | 22.66 | 0 | 0 | 57.25 | 30.38 | 10
429 | HOOGHLY | SM/13410 | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/015551 | 40030197 | Augmentation | MVS | GO2223009170PH | 02/11/2022 | 186.59 | 62.29 | 248.89 | Hooghly Division | Electrical Division | 67.16 | 35.22 | 37.77 | 0 | 140.15 | 67.16 | 35.22 | 37.77 | 0 | 140.15 | 56.31 | 53
430 | HOOGHLY | SM/16130 | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | TSM/020404 | 40053400 | Augmentation | MVS | GO2223014676PH | 22/02/2023 | 122.86 | 55.62 | 178.48 | Hooghly Division | Electrical Division | 23.17 | 11.02 | 0 | 0 | 34.19 | 23.17 | 11.02 | 0 | 0 | 34.19 | 19.16 | 37
431 | HOOGHLY | SM/18959 | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | TSM/020454 | 40067416 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 48.12 | 27.81 | 75.93 | Hooghly Division | Electrical Division | 0 | 8.76 | 0 | 0 | 8.76 | 0 | 8.76 | 0 | 0 | 8.76 | 11.54 | 10
432 | HOOGHLY | SM/13343 | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/014990 | 40032912 | Augmentation | MVS | GO2223008470PH | 29/09/2022 | 160.4 | 62.29 | 222.7 | Hooghly Division | Electrical Division | 47.98 | 40.5 | 0 | 0 | 88.48 | 47.98 | 40.5 | 0 | 0 | 88.48 | 39.73 | 50
433 | HOOGHLY | SM/18942 | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020551 | 40067439 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 31.61 | 8.83 | 0 | 0 | 40.44 | 31.61 | 8.83 | 0 | 0 | 40.44 | 39.25 | 11
434 | HOOGHLY | SM/18939 | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020640 | 40067442 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 9.61 | 0 | 0 | 9.61 | 0 | 9.61 | 0 | 0 | 9.61 | 5.1 | 10
435 | HOOGHLY | SM/18935 | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020671 | 40067451 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 11.82 | 11.08 | 0 | 0 | 22.9 | 11.82 | 11.08 | 0 | 0 | 22.9 | 12.15 | 10
436 | HOOGHLY | SM/15809 | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | TSM/020245 | 6904470 | Augmentation | MVS | GO2223014263PH | 20/02/2023 | 97.41 | 55.62 | 153.03 | Hooghly Division | Electrical Division | 13.26 | 3.31 | 12.16 | 0 | 28.73 | 13.26 | 3.31 | 12.16 | 0 | 28.73 | 18.77 | 34
437 | HOOGHLY | SM/18953 | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | TSM/020461 | 40067423 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 35.02 | 32.82 | 67.84 | Hooghly Division | Electrical Division | 28.8 | 12.57 | 0 | 0 | 41.36 | 28.8 | 12.57 | 0 | 0 | 41.36 | 60.97 | 8
438 | HOOGHLY | SM/18965 | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | TSM/020447 | 40067469 | Augmentation | SVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 119.06 | 55.62 | 174.68 | Hooghly Division | Electrical Division | 12.28 | 0 | 0 | 0 | 12.28 | 12.28 | 0 | 0 | 0 | 12.28 | 7.03 | 10
439 | HOOGHLY | SM/15801 | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK | TSM/016521 | 40037226 | Augmentation | MVS | GO2223014189PH | 17/02/2023 | 116.4 | 62.29 | 178.69 | Hooghly Division | Electrical Division | 53.97 | 23.16 | 35.71 | 0 | 112.84 | 53.97 | 23.16 | 35.71 | 0 | 112.84 | 63.15 | 17
440 | HOOGHLY | SM/18979 | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK | TSM/020555 | 40067353 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
441 | HOOGHLY | SM/15798 | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/018380 | 40039044 | Augmentation | MVS | GO2223014188PH | 17/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 29.04 | 21.4 | 37.77 | 0 | 88.21 | 29.04 | 21.4 | 37.77 | 0 | 88.21 | 77.17 | 26
442 | HOOGHLY | SM/18948 | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | TSM/020478 | 40067408 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 32.6 | 4.17 | 0 | 0 | 36.77 | 32.6 | 4.17 | 0 | 0 | 36.77 | 23.99 | 9
443 | HOOGHLY | SM/18964 | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | TSM/020448 | 40067410 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 138.89 | 55.62 | 194.51 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
444 | HOOGHLY | SM/18938 | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020641 | 40067356 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 26.29 | 26.95 | 0 | 0 | 53.25 | 26.29 | 26.95 | 0 | 0 | 53.25 | 28.25 | 10
445 | HOOGHLY | SM/18957 | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block | TSM/020456 | 40067470 | Augmentation | SVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 90.45 | 55.62 | 146.07 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
446 | HOOGHLY | SM/18956 | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | TSM/020457 | 40067420 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 35.02 | 32.82 | 67.84 | Hooghly Division | Electrical Division | 13.72 | 4.02 | 0 | 0 | 17.74 | 13.72 | 4.02 | 0 | 0 | 17.74 | 26.15 | 8
447 | HOOGHLY | SM/18960 | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | TSM/020452 | 40067471 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 117.26 | 55.62 | 172.88 | Hooghly Division | Electrical Division | 0 | 20.9 | 0 | 0 | 20.9 | 0 | 20.9 | 0 | 0 | 20.9 | 12.09 | 11
448 | HOOGHLY | SM/15815 | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | TSM/020228 | 0 | Augmentation | MVS | GO2223014279PH | 20/02/2023 | 40.05 | 27.81 | 67.86 | Hooghly Division | Electrical Division | 5.06 | 0 | 0 | 0 | 5.06 | 5.06 | 0 | 0 | 0 | 5.06 | 7.46 | 56
449 | HOOGHLY | SM/18934 | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020672 | 40067343 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 28.58 | 13.56 | 0 | 0 | 42.14 | 28.58 | 13.56 | 0 | 0 | 42.14 | 22.36 | 10
450 | HOOGHLY | SM/16122 | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | TSM/020384 | 40053403 | Augmentation | MVS | GO2223014674PH | 22/02/2023 | 143.25 | 55.62 | 198.87 | Hooghly Division | Electrical Division | 31.18 | 50.72 | 0 | 0 | 81.9 | 31.18 | 50.72 | 0 | 0 | 81.9 | 41.18 | 55
451 | HOOGHLY | SM/18945 | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020546 | 40067435 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 2.7 | 8.23 | 0 | 0 | 10.93 | 2.7 | 8.23 | 0 | 0 | 10.93 | 5.8 | 10
452 | HOOGHLY | SM/15808 | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | TSM/020246 | 40042900 | Augmentation | MVS | GO2223014183PH | 17/02/2023 | 49.98 | 27.81 | 77.79 | Hooghly Division | Electrical Division | 10.72 | 3.95 | 0 | 0 | 14.67 | 10.72 | 3.95 | 0 | 0 | 14.67 | 18.86 | 32
453 | HOOGHLY | SM/18974 | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020633 | 40067409 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 32.03 | 12.07 | 0 | 0 | 44.1 | 32.03 | 12.07 | 0 | 0 | 44.1 | 23.4 | 10
454 | HOOGHLY | SM/18972 | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020635 | 40067462 | Augmentation | SVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 4.12 | 0 | 0 | 4.12 | 0 | 4.12 | 0 | 0 | 4.12 | 2.18 | 10
455 | HOOGHLY | SM/15811 | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | TSM/020243 | 0 | Augmentation | MVS | GO2223014186PH | 17/02/2023 | 37.77 | 27.81 | 65.58 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
456 | HOOGHLY | SM/15814 | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | TSM/020242 | 40042968 | Augmentation | MVS | GO2223014282PH | 20/02/2023 | 73.89 | 55.62 | 129.51 | Hooghly Division | Electrical Division | 11.07 | 23.35 | 0 | 0 | 34.43 | 11.07 | 23.35 | 0 | 0 | 34.43 | 26.58 | 28
457 | HOOGHLY | SM/18955 | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | TSM/020458 | 40067391 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 35.02 | 32.82 | 67.84 | Hooghly Division | Electrical Division | 5.81 | 0 | 0 | 0 | 5.81 | 5.81 | 0 | 0 | 0 | 5.81 | 8.56 | 7
458 | HOOGHLY | SM/15802 | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | TSM/020250 | 40043401 | Augmentation | MVS | GO2223014257PH | 20/02/2023 | 38.61 | 27.81 | 66.42 | Hooghly Division | Electrical Division | 16.12 | 15.75 | 6.01 | 0 | 37.89 | 16.12 | 15.75 | 6.01 | 0 | 37.89 | 57.04 | 29
459 | HOOGHLY | SM/15899 | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/018192 | 40038980 | Augmentation | MVS | GO2223014278PH | 20/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 48.65 | 14.26 | 20.39 | 0 | 83.3 | 48.65 | 14.26 | 20.39 | 0 | 83.3 | 72.87 | 22
460 | HOOGHLY | SM/13345 | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/014975 | 40028612 | Augmentation | MVS | GO2223008486PH | 29/09/2022 | 163.29 | 62.29 | 225.59 | Hooghly Division | Electrical Division | 158.53 | 56.77 | 0 | 0 | 215.31 | 140.02 | 56.77 | 0 | 0 | 196.8 | 87.24 | 55
461 | HOOGHLY | SM/15796 | Source Augmentation of Malia PWSS | TSM/018687 | 40039057 | Augmentation | MVS | GO2223014286PH | 20/02/2023 | 28.89 | 26.27 | 55.16 | Hooghly Division | Electrical Division | 22.65 | 20.9 | 0 | 0 | 43.55 | 22.65 | 20.9 | 0 | 0 | 43.55 | 78.95 | 34
462 | HOOGHLY | SM/18977 | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020630 | 40067365 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 4.09 | 0 | 0 | 0 | 4.09 | 4.09 | 0 | 0 | 0 | 4.09 | 2.17 | 10
463 | HOOGHLY | SM/18954 | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | TSM/020460 | 40067400 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 18.76 | 47.32 | 0 | 0 | 66.08 | 18.76 | 47.32 | 0 | 0 | 66.08 | 43.11 | 9
464 | HOOGHLY | SM/18970 | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020637 | 40067345 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 13.22 | 24.14 | 0 | 0 | 37.37 | 13.22 | 24.14 | 0 | 0 | 37.37 | 19.83 | 10
465 | HOOGHLY | SM/18976 | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020631 | 40067456 | Augmentation | SVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 0.51 | 10
466 | HOOGHLY | SM/18933 | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020675 | 40067449 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 0.51 | 10
467 | HOOGHLY | SM/18963 | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block | TSM/020449 | 40067411 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 35.52 | 27.81 | 63.33 | Hooghly Division | Electrical Division | 17.73 | 10.8 | 0 | 0 | 28.53 | 17.73 | 10.8 | 0 | 0 | 28.53 | 45.05 | 9
468 | HOOGHLY | SM/18791 | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | TSM/011639 | 40037195 | Augmentation | MVS | PHE/IV/2693/W-387/23 | 07/09/2023 | 44.65 | 27.81 | 72.46 | Hooghly Division | Electrical Division | 0.38 | 21.09 | 0 | 0 | 21.47 | 0.38 | 21.09 | 0 | 0 | 21.47 | 29.63 | 10
469 | HOOGHLY | SM/18946 | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020544 | 40067460 | Augmentation | SVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 8.12 | 0 | 0 | 8.12 | 0 | 8.12 | 0 | 0 | 8.12 | 4.31 | 10
470 | HOOGHLY | SM/15795 | Source Augmentation of Paschim Joykrishnapur PWSS | TSM/018693 | 40039062 | Augmentation | MVS | GO2223014283PH | 20/02/2023 | 57.79 | 52.53 | 110.32 | Hooghly Division | Electrical Division | 26.48 | 34.57 | 26.06 | 0 | 87.11 | 26.48 | 34.57 | 26.06 | 0 | 87.11 | 78.96 | 18
471 | HOOGHLY | SM/15900 | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/018379 | 40039042 | Augmentation | MVS | GO2223014277PH | 20/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 25.61 | 17.08 | 1.85 | 0 | 44.54 | 25.61 | 17.08 | 1.85 | 0 | 44.54 | 38.96 | 22
472 | HOOGHLY | SM/15804 | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | TSM/020251 | 40043149 | Augmentation | MVS | GO2223014184PH | 17/02/2023 | 87.4 | 27.81 | 115.21 | Hooghly Division | Electrical Division | 9.95 | 3.55 | 6.01 | 0 | 19.52 | 9.95 | 3.55 | 6.01 | 0 | 19.52 | 16.94 | 50
473 | HOOGHLY | SM/18951 | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | TSM/020464 | 40067403 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 14.46 | 7.18 | 0 | 0 | 21.64 | 14.46 | 7.18 | 0 | 0 | 21.64 | 14.12 | 9
474 | HOOGHLY | SM/15807 | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | TSM/020247 | 40039157 | Augmentation | MVS | GO2223014187PH | 17/02/2023 | 73.34 | 55.62 | 128.96 | Hooghly Division | Electrical Division | 11.04 | 23.07 | 12.16 | 0 | 46.27 | 11.04 | 23.07 | 12.16 | 0 | 46.27 | 35.88 | 28
475 | HOOGHLY | SM/18952 | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | TSM/020462 | 40067402 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 46.79 | 15.74 | 0 | 0 | 62.53 | 46.79 | 15.74 | 0 | 0 | 62.53 | 40.8 | 9
476 | HOOGHLY | SM/15806 | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | TSM/020248 | 6904457 | Augmentation | MVS | GO2223014292PH | 20/02/2023 | 38 | 27.81 | 65.81 | Hooghly Division | Electrical Division | 0 | 0 | 6.32 | 0 | 6.32 | 0 | 0 | 6.32 | 0 | 6.32 | 9.6 | 100
477 | HOOGHLY | SM/15805 | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | TSM/020249 | 40043096 | Augmentation | MVS | GO2223014179PH | 17/02/2023 | 36.28 | 27.81 | 64.09 | Hooghly Division | Electrical Division | 18.4 | 13.48 | 0 | 0 | 31.89 | 18.4 | 13.48 | 0 | 0 | 31.89 | 49.75 | 49
478 | HOOGHLY | SM/13677 | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/014958 | 40032931 | Augmentation | MVS | GO2223008476PH | 29/09/2022 | 233.29 | 62.29 | 295.58 | Hooghly Division | Electrical Division | 97.45 | 38.34 | 0 | 0 | 135.79 | 97.45 | 38.34 | 0 | 0 | 135.79 | 45.94 | 100
479 | HOOGHLY | SM/18947 | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block | TSM/020492 | 40067434 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 85.29 | 55.62 | 140.91 | Hooghly Division | Electrical Division | 0 | 41.85 | 0 | 0 | 41.85 | 0 | 41.85 | 0 | 0 | 41.85 | 29.7 | 9
480 | HOOGHLY | SM/18971 | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020636 | 40067374 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 14.22 | 8.69 | 0 | 0 | 22.9 | 14.22 | 8.69 | 0 | 0 | 22.9 | 12.15 | 10
481 | HOOGHLY | SM/16121 | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | TSM/020378 | 40053407 | Augmentation | SVS | GO2223014679PH | 22/02/2023 | 108.04 | 55.62 | 163.66 | Hooghly Division | Electrical Division | 38.57 | 44 | 0 | 0 | 82.57 | 38.57 | 44 | 0 | 0 | 82.57 | 50.45 | 52
482 | HOOGHLY | SM/15797 | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/018201 | 40039009 | Augmentation | MVS | GO2223014260PH | 20/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 35.18 | 30.98 | 37.77 | 0 | 103.93 | 35.18 | 30.98 | 37.77 | 0 | 103.93 | 90.92 | 26
483 | HOOGHLY | SM/15793 | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | TSM/018794 | 40039084 | Augmentation | MVS | GO2223014176PH | 17/02/2023 | 26.02 | 26.27 | 52.29 | Hooghly Division | Electrical Division | 3.57 | 6.12 | 0 | 0 | 9.68 | 3.57 | 6.12 | 0 | 0 | 9.68 | 18.52 | 10
484 | HOOGHLY | SM/18962 | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | TSM/020450 | 40067413 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 137.06 | 55.62 | 192.68 | Hooghly Division | Electrical Division | 14.3 | 3.42 | 0 | 0 | 17.72 | 14.3 | 3.42 | 0 | 0 | 17.72 | 9.2 | 11
485 | HOOGHLY | SM/13409 | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/015548 | 40029480 | Augmentation | MVS | GO2223009172PH | 02/11/2022 | 139.28 | 62.29 | 201.57 | Hooghly Division | Electrical Division | 41.68 | 24.68 | 36.39 | 0 | 102.75 | 41.68 | 24.68 | 36.39 | 0 | 102.75 | 50.98 | 59
486 | HOOGHLY | SM/15810 | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | TSM/020244 | 7764511 | Augmentation | MVS | GO2223014185PH | 17/02/2023 | 36.55 | 27.81 | 64.36 | Hooghly Division | Electrical Division | 29.28 | 15.03 | 0 | 0 | 44.3 | 29.28 | 15.03 | 0 | 0 | 44.3 | 68.83 | 100
487 | HOOGHLY | SM/18969 | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020638 | 40067352 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 39.87 | 17.09 | 0 | 0 | 56.96 | 39.87 | 17.09 | 0 | 0 | 56.96 | 30.22 | 10
488 | HOOGHLY | SM/13411 | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/015549 | 40030029 | Augmentation | MVS | GO2223009171PH | 02/11/2022 | 134.88 | 62.29 | 197.18 | Hooghly Division | Electrical Division | 76.38 | 24.46 | 37.77 | 0 | 138.61 | 76.38 | 24.46 | 37.77 | 0 | 138.61 | 70.3 | 61
489 | HOOGHLY | SM/18932 | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020676 | 40067448 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 15.84 | 0 | 0 | 0 | 15.84 | 15.84 | 0 | 0 | 0 | 15.84 | 8.4 | 10
490 | HOOGHLY | SM/18949 | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | TSM/020467 | 40067427 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 79.13 | 65.63 | 144.76 | Hooghly Division | Electrical Division | 28.26 | 6.27 | 0 | 0 | 34.53 | 28.26 | 6.27 | 0 | 0 | 34.53 | 23.85 | 9
491 | HOOGHLY | SM/13593 | Sultangachha Mini Piped Water Supply Scheme | TSM/015667 | 40029782 | New | SVS | GO2223009482PH | 09/11/2022 | 32.06 | 8.75 | 40.81 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
492 | HOOGHLY | SM/18593 | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | TSM/017604 | 40033767 | New | MVS | 2151/PHE-28011/158/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1011.74 | 59.55 | 1071.3 | Hooghly Division | Electrical Division | 357.91 | 41.85 | 29.38 | 0 | 429.13 | 357.91 | 41.85 | 29.38 | 0 | 429.13 | 40.06 | 39
493 | HOOGHLY | SM/13594 | Surjyapur Mini Piped Water Supply Scheme | TSM/015681 | 40029743 | New | SVS | GO2223009475PH | 09/11/2022 | 33.22 | 8.75 | 41.97 | Hooghly Division | Electrical Division | 31.76 | 8.49 | 0.49 | 0 | 40.75 | 31.76 | 8.49 | 0.49 | 0 | 40.75 | 97.09 | 63
494 | HOOGHLY | SM/13599 | Telinipara Mini Piped Water Supply Scheme | TSM/015641 | 40029315 | New | SVS | GO2223009486PH | 09/11/2022 | 30.64 | 8.75 | 39.39 | Hooghly Division | Electrical Division | 29.33 | 8.49 | 0 | 0 | 37.82 | 29.33 | 8.49 | 0 | 0 | 37.82 | 96.02 | 38
495 | HOOGHLY | SM/18309 | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | TSM/017631 | 40033179 | New | MVS | 1657/PHE-28011/126/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 970.82 | 55.91 | 1026.73 | Hooghly Division | Electrical Division | 105.38 | 34.08 | 3.08 | 0 | 142.54 | 105.38 | 34.08 | 3.08 | 0 | 142.54 | 13.88 | 14
496 | HOOGHLY | SM/14121 | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016500 | 40032862 | New | MVS | GO2223011519PH | 02/01/2023 | 453.25 | 58.22 | 511.47 | Hooghly Division | Electrical Division | 203.85 | 11.06 | 35.58 | 0 | 250.48 | 203.85 | 11.06 | 35.58 | 0 | 250.48 | 48.97 | 35
497 | HOOGHLY | SM/14467 | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016744 | 40032860 | New | MVS | GO2223012348PH | 20/01/2023 | 733.87 | 79.02 | 812.88 | Hooghly Division | Electrical Division | 324.92 | 24.91 | 50.32 | 0 | 400.16 | 324.92 | 24.91 | 50.32 | 0 | 400.16 | 49.23 | 34
498 | HOOGHLY | SM/13663 | Uttar Hazipur Mini Piped Water Supply Scheme | TSM/015660 | 40029664 | New | SVS | GO2223009509PH | 09/11/2022 | 30.51 | 8.75 | 39.26 | Hooghly Division | Electrical Division | 29.62 | 8.49 | 0 | 0 | 38.11 | 29.62 | 8.49 | 0 | 0 | 38.11 | 97.09 | 62
Total | [9 empty] | 222269.73 | 19767.31 | 242037.04 |  |  | 84402.69 | 7887.38 | 10575.39 | 688.36 | 103553.83 | 83691.99 | 7896.13 | 10575.39 | 688.36 | 102851.87 | 42.49