## JJM Schemes Financial Status (B
JJM Schemes Financial Status (BANKURA) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | BANKURA | SM/17223 | Birsingpur Piped Water Supply Scheme. | TSM/018234 | 40059803 | New | MVS | GO2223016079PH | 15/03/2023 | 790.28 | 107.73 | 898.01 | Bankura Division | Bankura Mechanical Division | 182.45 | 20.09 | 24.3 | 0 | 226.84 | 182.45 | 16.4 | 0 | 0 | 198.85 | 22.14 | 39
2 | BANKURA | SM/18753 | Dhulai Piped Water Supply Scheme. | TSM/018195 | 40059793 | New | MVS | 2481/PHE-28011/190/2023-SCHM CELL-Dept. of PHE | 21/08/2023 | 1290.79 | 161.6 | 1452.39 | Bankura Division | Bankura Mechanical Division | 326.13 | 10.92 | 109.38 | 0 | 446.43 | 326.13 | 0 | 55.2 | 0 | 381.33 | 26.26 | 30
3 | BANKURA | SM/09924 | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas | TSM/005019 | 40036231 | Augmentation | MVS | GO2122006624PH | 10/12/2021 | 874.28 | 0 | 874.28 | Bankura Division | Bankura Mechanical Division | 199.42 | 0 | 23.75 | 0 | 223.17 | 188.6 | 0 | 23.75 | 0 | 212.36 | 24.29 | 37
4 | BANKURA | SM/17283 | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019231 | 40061289 | Augmentation | MVS | GO2223016309PH | 15/03/2023 | 572.46 | 187.38 | 759.85 | Bankura Division | Bankura Mechanical Division | 33.59 | 0 | 3.69 | 0 | 37.28 | 33.59 | 0 | 0 | 0 | 33.59 | 4.42 | 49
5 | BANKURA | SM/17435 | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019233 | 40061296 | Augmentation | MVS | GO2223017165PH | 18/03/2023 | 631.31 | 230.37 | 861.68 | Bankura Division | Bankura Mechanical Division | 143.19 | 0 | 4 | 0 | 147.19 | 142.61 | 0 | 0 | 0 | 142.61 | 16.55 | 73
6 | BANKURA | SM/16944 | Basudebpur Piped Water Supply Scheme. | TSM/018186 | 40059786 | New | MVS | GO2223016397PH | 16/03/2023 | 773.16 | 107.73 | 880.89 | Bankura Division | Bankura Mechanical Division | 0 | 19.17 | 0 | 0 | 19.17 | 0 | 19.17 | 0 | 0 | 19.17 | 2.18 | 8
7 | BANKURA | SM/17577 | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | TSM/011399 | 40061309 | New | SVS | GO2223017021PH | 18/03/2023 | 385.94 | 82.29 | 468.23 | Bankura Division | Bankura Mechanical Division | 3.46 | 23.52 | 0.91 | 0 | 27.89 | 3.46 | 18.79 | 0.91 | 0 | 23.16 | 4.95 | 10
8 | BANKURA | SM/16705 | Manik Bazar Piped Water Supply Scheme. | TSM/018138 | 40061525 | New | MVS | GO2223016010PH | 14/03/2023 | 469.2 | 96.1 | 565.3 | Bankura Division | Bankura Mechanical Division | 0 | 22.76 | 0 | 0 | 22.76 | 0 | 7.85 | 0 | 0 | 7.85 | 1.39 | 3
9 | BANKURA | SM/09322 | & commissiConstruction oning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Dighalgram-126) of Betanal (Zone - B) under | TSM/007425 | 5343948 | Retrofitting | SVS | GO2122005027PH | 08/11/2021 | 98.43 | 0 | 98.43 | Bankura Division |  | 57.57 | 0 | 0 | 0 | 57.57 | 57.57 | 0 | 0 | 0 | 57.57 | 58.49 | 55
10 | BANKURA | SM/17702 | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018938 | 40061092 | Augmentation | MVS | GO2223016737PH | 17/03/2023 | 429.46 | 280.12 | 709.58 | Bankura Division | Bankura Mechanical Division | 0 | 164.82 | 8.78 | 0 | 173.6 | 0 | 164.82 | 4.39 | 0 | 169.21 | 23.85 | 22
11 | BANKURA | SM/17700 | 'Augmentation works for Bikrampur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project).' | TSM/018958 | 40061217 | Augmentation | MVS | GO2223016825PH | 17/03/2023 | 170.76 | 91.68 | 262.44 | Bankura Division | Bankura Mechanical Division | 62.08 | 15.38 | 1.11 | 0 | 78.57 | 62.08 | 0 | 1.11 | 0 | 63.19 | 24.08 | 17
12 | BANKURA | SM/17704 | 'Augmentation works for Jamtora (Zone- G) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018944 | 40059944 | Augmentation | MVS | GO2223016746PH | 17/03/2023 | 235.52 | 0 | 235.52 | Bankura Division |  | 26.07 | 0 | 1.46 | 0 | 27.53 | 26.07 | 0 | 1.46 | 0 | 27.53 | 11.69 | 42
13 | BANKURA | SM/17249 | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018940 | 40059913 | Augmentation | MVS | GO2223016167PH | 15/03/2023 | 220.71 | 0 | 220.71 | Bankura Division |  | 21.22 | 0 | 5.41 | 0 | 26.63 | 21.22 | 0 | 2.7 | 0 | 23.92 | 10.84 | 28
14 | BANKURA | SM/17706 | 'Augmentation works for Keshra (Zone- I) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018947 | 5343948 | Augmentation | MVS | GO2223017211PH | 17/03/2023 | 255.52 | 0 | 255.52 | Bankura Division |  | 38.86 | 0 | 4.18 | 0 | 43.04 | 38.86 | 0 | 2.09 | 0 | 40.95 | 16.03 | 22
15 | BANKURA | SM/17250 | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | TSM/018942 | 40059936 | Augmentation | MVS | GO2223016084PH | 15/03/2023 | 177.09 | 0 | 177.09 | Bankura Division |  | 79.74 | 0 | 2.5 | 0 | 82.24 | 79.74 | 0 | 1.25 | 0 | 80.99 | 45.73 | 55
16 | BANKURA | SM/16942 | Adwaitabati Piped Water Supply Scheme | TSM/018268 | 40059800 | New | MVS | GO2223016396PH | 16/03/2023 | 873.52 | 125.54 | 999.06 | Bankura Division | Bankura Mechanical Division | 78.4 | 26.82 | 81.46 | 0 | 186.68 | 78.4 | 26.82 | 42.06 | 0 | 147.27 | 14.74 | 16
17 | BANKURA | SM/14000 | Atra Piped Water Supply Scheme | TSM/015426 | 40035942 | New | MVS | GO2223010526PH | 05/12/2022 | 787.61 | 125.54 | 913.15 | Bankura Division | Bankura Mechanical Division | 53.82 | 18.97 | 0 | 0 | 72.79 | 53.82 | 18.97 | 0 | 0 | 72.79 | 7.97 | 41
18 | BANKURA | SM/17254 | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | TSM/019213 | 40061484 | Augmentation | MVS | GO2223016295PH | 15/03/2023 | 382.11 | 189.59 | 571.7 | Bankura Division | Bankura Mechanical Division | 51.28 | 0 | 2.95 | 0 | 54.23 | 51.28 | 0 | 0 | 0 | 51.28 | 8.97 | 30
19 | BANKURA | SM/16953 | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | TSM/019123 | 40061175 | Augmentation | MVS | GO2223016411PH | 16/03/2023 | 183.46 | 0 | 183.46 | Bankura Division |  | 89.37 | 0 | 5.51 | 0 | 94.88 | 89.37 | 0 | 2.75 | 0 | 92.12 | 50.21 | 60
20 | BANKURA | SM/17120 | Augmentation for Gouripur Water Supply Scheme. | TSM/019130 | 40065926 | Augmentation | SVS | GO2223016512PH | 16/03/2023 | 87.47 | 28.77 | 116.24 | Bankura Division | Bankura Mechanical Division | 42.93 | 22.34 | 0.43 | 0 | 65.7 | 42.93 | 22.34 | 0.43 | 0 | 65.7 | 56.52 | 61
21 | BANKURA | SM/15007 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME | TSM/016326 | 40042613 | Augmentation | MVS | GO2223013071PH | 04/02/2023 | 325.29 | 36.79 | 362.07 | Bankura Division | Bankura Mechanical Division | 89.55 | 0 | 7.14 | 0 | 96.69 | 89.55 | 0 | 3.67 | 0 | 93.21 | 25.74 | 36
22 | BANKURA | SM/15001 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | TSM/016212 | 40037941 | Augmentation | MVS | GO2223013067PH | 04/02/2023 | 384.33 | 10.74 | 395.06 | Bankura Division | Bankura Mechanical Division | 3.72 | 0 | 5.44 | 0 | 9.15 | 3.72 | 0 | 5.44 | 0 | 9.15 | 2.32 | 19
23 | BANKURA | SM/15008 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | TSM/016329 | 40042745 | Augmentation | MVS | GO2223013069PH | 04/02/2023 | 417.32 | 36.79 | 454.11 | Bankura Division | Bankura Mechanical Division | 73.44 | 0 | 5.89 | 0 | 79.32 | 73.44 | 0 | 0 | 0 | 73.44 | 16.17 | 32
24 | BANKURA | SM/15002 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/B WATER SUPPLY SCHEME | TSM/016259 | 40039112 | Augmentation | MVS | GO2223013070PH | 04/02/2023 | 436.72 | 10.74 | 447.46 | Bankura Division | Bankura Mechanical Division | 39.18 | 0 | 6.17 | 0 | 45.36 | 39.18 | 0 | 0 | 0 | 39.18 | 8.76 | 20
25 | BANKURA | SM/15005 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | TSM/016303 | 40042425 | Augmentation | MVS | GO2223013075PH | 04/02/2023 | 637.58 | 10.74 | 648.32 | Bankura Division | Bankura Mechanical Division | 90.16 | 0 | 30.55 | 0 | 120.71 | 90.16 | 0 | 30.55 | 0 | 120.71 | 18.62 | 30
26 | BANKURA | SM/18495 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | TSM/016254 | 40038818 | Augmentation | MVS | 2034/PHE-28011/269/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 1115.26 | 10.74 | 1126 | Bankura Division | Bankura Mechanical Division | 4.46 | 0 | 24.58 | 0 | 29.05 | 4.46 | 0 | 24.58 | 0 | 29.05 | 2.58 | 15
27 | BANKURA | SM/15006 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | TSM/016323 | 40042546 | Augmentation | MVS | GO2223013072PH | 04/02/2023 | 235.69 | 10.74 | 246.43 | Bankura Division | Bankura Mechanical Division | 72.46 | 0 | 3.75 | 0 | 76.2 | 72.46 | 0 | 3.75 | 0 | 76.2 | 30.92 | 81
28 | BANKURA | SM/14091 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | TSM/016219 | 40037997 | Augmentation | MVS | GO2223010856PH | 12/12/2022 | 805.9 | 10.74 | 816.64 | Bankura Division | Bankura Mechanical Division | 4.27 | 0 | 0.25 | 0 | 4.53 | 4.27 | 0 | 0.25 | 0 | 4.53 | 0.55 | 8
29 | BANKURA | SM/15009 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/A WATER SUPPLY SCHEME | TSM/016332 | 40042995 | Augmentation | MVS | GO2223013073PH | 04/02/2023 | 439.41 | 10.74 | 450.15 | Bankura Division | Bankura Mechanical Division | 50.73 | 0 | 8.78 | 0 | 59.51 | 50.73 | 0 | 0 | 0 | 50.73 | 11.27 | 20
30 | BANKURA | SM/16935 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | TSM/016243 | 40038641 | Augmentation | MVS | GO2223016494PH | 16/03/2023 | 989.23 | 10.74 | 999.97 | Bankura Division | Bankura Mechanical Division | 4.66 | 0 | 146.2 | 0 | 150.86 | 4.66 | 0 | 146.2 | 0 | 150.86 | 15.09 | 5
31 | BANKURA | SM/14650 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | TSM/016337 | 40043300 | Augmentation | SVS | GO2223012701PH | 31/01/2023 | 78.26 | 10.74 | 89 | Bankura Division | Bankura Mechanical Division | 2.41 | 0 | 0 | 0 | 2.41 | 2.41 | 0 | 0 | 0 | 2.41 | 2.71 | 5
32 | BANKURA | SM/16936 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | TSM/016262 | 40042007 | Augmentation | MVS | GO2223016492PH | 16/03/2023 | 455.51 | 10.74 | 466.25 | Bankura Division | Bankura Mechanical Division | 48.22 | 0 | 6.81 | 0 | 55.03 | 48.22 | 0 | 0 | 0 | 48.22 | 10.34 | 20
33 | BANKURA | SM/15003 | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | TSM/016260 | 40041747 | Augmentation | MVS | GO2223013066PH | 04/02/2023 | 645.96 | 10.74 | 656.7 | Bankura Division | Bankura Mechanical Division | 143.96 | 0 | 0 | 0 | 143.96 | 143.96 | 0 | 0 | 0 | 143.96 | 21.92 | 36
34 | BANKURA | SM/09853 | Augmentation of Aguribandh-Punisole piped water supply scheme in Onda block of Bankura district under BRGF programme by relaying rising mains (DI K9) damaged due to various road widening programme and providing Functional Household Tap Connection (FHTC) t | TSM/008038 | 5343948 | Augmentation | SVS | GO2122006633PH | 03/12/2021 | 293.12 | 0 | 293.12 | Bankura Division |  | 213.02 | 0 | 19.44 | 0 | 232.46 | 213.02 | 0 | 19.44 | 0 | 232.46 | 79.31 | 99
35 | BANKURA | SM/17246 | Augmentation of Ajodhya Water Supply Scheme | TSM/019176 | 40060515 | Augmentation | MVS | GO2223016293PH | 15/03/2023 | 216.25 | 103.99 | 320.23 | Bankura Division | Bankura Mechanical Division | 67.38 | 48 | 0 | 0 | 115.38 | 67.38 | 32.83 | 0 | 0 | 100.21 | 31.29 | 44
36 | BANKURA | SM/16943 | Augmentation of Akui Zone-A Water Supply Scheme | TSM/018973 | 40060347 | Augmentation | MVS | GO2223016508PH | 16/03/2023 | 149.99 | 78.17 | 228.16 | Bankura Division | Bankura Mechanical Division | 38.79 | 1.41 | 0 | 0 | 40.2 | 0 | 0 | 0 | 0 | 0 | 0 | 13
37 | BANKURA | SM/17228 | Augmentation of Akui Zone-B Water Supply Scheme | TSM/019010 | 40059925 | Augmentation | MVS | GO2223016146PH | 15/03/2023 | 198.57 | 133.78 | 332.35 | Bankura Division | Bankura Mechanical Division | 49.81 | 49.9 | 0 | 0 | 99.71 | 49.81 | 46.82 | 0 | 0 | 96.63 | 29.07 | 32
38 | BANKURA | SM/17229 | Augmentation of Amrul Zone-A Water Supply Scheme | TSM/019154 | 40059940 | Augmentation | MVS | GO2223016089PH | 15/03/2023 | 182.8 | 114.54 | 297.35 | Bankura Division | Bankura Mechanical Division | 0 | 33.95 | 0 | 0 | 33.95 | 0 | 28.75 | 0 | 0 | 28.75 | 9.67 | 22
39 | BANKURA | SM/17230 | Augmentation of Amrul Zone-B Water Supply Scheme | TSM/019147 | 40059949 | Augmentation | MVS | GO2223016107PH | 15/03/2023 | 194.49 | 120.43 | 314.92 | Bankura Division | Bankura Mechanical Division | 78.08 | 2.6 | 0 | 0 | 80.68 | 78.08 | 0 | 0 | 0 | 78.08 | 24.79 | 32
40 | BANKURA | SM/17244 | Augmentation of Benda water supply scheme | TSM/019170 | 40060505 | Augmentation | MVS | GO2223016291PH | 15/03/2023 | 163.51 | 109.77 | 273.28 | Bankura Division | Bankura Mechanical Division | 0 | 39.69 | 0 | 0 | 39.69 | 0 | 39.69 | 0 | 0 | 39.69 | 14.52 | 17
41 | BANKURA | SM/17692 | Augmentation of Betanal Zone-A Water Supply Scheme | TSM/019158 | 40059976 | Augmentation | MVS | GO2223016813PH | 17/03/2023 | 177.48 | 90.27 | 267.76 | Bankura Division | Bankura Mechanical Division | 49.86 | 17.48 | 0 | 0 | 67.35 | 49.86 | 0 | 0 | 0 | 49.86 | 18.62 | 11
42 | BANKURA | SM/17418 | Augmentation of Betanal Zone-B Water Supply Scheme | TSM/019149 | 40059992 | Augmentation | MVS | GO2223017163PH | 18/03/2023 | 232.18 | 154.34 | 386.52 | Bankura Division | Bankura Mechanical Division | 0 | 7.48 | 0 | 0 | 7.48 | 0 | 0 | 0 | 0 | 0 | 0 | 5
43 | BANKURA | SM/17425 | Augmentation of Chakuparsole Zone-A Water Supply Scheme | TSM/019175 | 40060371 | Augmentation | MVS | GO2223017179PH | 18/03/2023 | 249.08 | 174.76 | 423.84 | Bankura Division | Bankura Mechanical Division | 106.67 | 0 | 0 | 0 | 106.67 | 106.67 | 0 | 0 | 0 | 106.67 | 25.17 | 18
44 | BANKURA | SM/17426 | Augmentation of Chakuparsole Zone-B Water Supply Scheme | TSM/019171 | 40060383 | Augmentation | MVS | GO2223017159PH | 18/03/2023 | 221.05 | 136.19 | 357.24 | Bankura Division | Bankura Mechanical Division | 49.8 | 0 | 0 | 0 | 49.8 | 49.8 | 0 | 0 | 0 | 49.8 | 13.94 | 9
45 | BANKURA | SM/17696 | Augmentation of Chuamasina Zone-A Water Supply Scheme | TSM/019173 | 40060397 | Augmentation | MVS | GO2223016843PH | 17/03/2023 | 257.92 | 132.91 | 390.83 | Bankura Division | Bankura Mechanical Division | 60.77 | 0 | 0 | 0 | 60.77 | 60.77 | 0 | 0 | 0 | 60.77 | 15.55 | 13
46 | BANKURA | SM/17427 | Augmentation of Chuamasina Zone-B Water Supply Scheme | TSM/019172 | 40060443 | Augmentation | MVS | GO2223017173PH | 18/03/2023 | 179.99 | 63.5 | 243.49 | Bankura Division | Bankura Mechanical Division | 41.21 | 47.23 | 0 | 0 | 88.45 | 0 | 47.23 | 0 | 0 | 47.23 | 19.4 | 16
47 | BANKURA | SM/17699 | Augmentation of Dhengasole Water Supply Scheme | TSM/019178 | 40060527 | Augmentation | MVS | GO2223016829PH | 17/03/2023 | 190.73 | 132.91 | 323.64 | Bankura Division | Bankura Mechanical Division | 83.22 | 7.74 | 0 | 0 | 90.96 | 83.22 | 0 | 0 | 0 | 83.22 | 25.71 | 39
48 | BANKURA | SM/09927 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | TSM/008990 | 40027145 | Augmentation | SVS | GO2122006613PH | 09/12/2021 | 282.49 | 26.43 | 308.91 | Bankura Division | Bankura Mechanical Division | 175.6 | 0 | 0 | 0 | 175.6 | 175.6 | 0 | 0 | 0 | 175.6 | 56.85 | 78
49 | BANKURA | SM/09454 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | TSM/008992 | 40017353 | Augmentation | MVS | GO2122005589PH | 19/11/2021 | 487.26 | 23.24 | 510.5 | Bankura Division | Bankura Mechanical Division | 325.5 | 15.18 | 53.41 | 0 | 394.09 | 325.5 | 12.06 | 53.41 | 0 | 390.97 | 76.59 | 75
50 | BANKURA | SM/09926 | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | TSM/008991 | 40027131 | Augmentation | SVS | GO2122006613PH | 09/12/2021 | 508.86 | 23.24 | 532.09 | Bankura Division | Bankura Mechanical Division | 307.91 | 10.79 | 0 | 0 | 318.7 | 307.91 | 0 | 0 | 0 | 307.91 | 57.87 | 76
51 | BANKURA | SM/12379 | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | TSM/014161 | 40047828 | Augmentation | MVS | GO2223007568PH | 13/09/2022 | 501.64 | 89.32 | 590.96 | Bankura Division | Bankura Mechanical Division | 137.86 | 0 | 0 | 0 | 137.86 | 137.86 | 0 | 0 | 0 | 137.86 | 23.33 | 59
52 | BANKURA | SM/17684 | Augmentation of Indas Water Supply Scheme | TSM/019132 | 40060275 | Augmentation | MVS | GO2223016864PH | 17/03/2023 | 135.26 | 42.94 | 178.2 | Bankura Division | Bankura Mechanical Division | 0 | 3.82 | 0 | 0 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 67
53 | BANKURA | SM/18036 | Augmentation of Indpur Piped Water Supply Scheme. Block- Bankura I, District- Bankura | TSM/017264 | 40061461 | Augmentation | MVS | GO2223016910PH | 17/03/2023 | 674.02 | 125.19 | 799.22 | Bankura Division | Bankura Mechanical Division | 3.46 | 0 | 85.22 | 0 | 88.68 | 3.46 | 0 | 4 | 0 | 7.46 | 0.93 | 0
54 | BANKURA | SM/18612 | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | TSM/019240 | 40061651 | Augmentation | MVS | 2157/PHE-28011/214/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 4616.1 | 510.91 | 5127.01 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 1186.93 | 0 | 1186.93 | 0 | 0 | 870.57 | 0 | 870.57 | 16.98 | 0
55 | BANKURA | SM/09880 | Augmentation of Jayrambati Piped Water Supply Scheme. | TSM/005083 | 40017339 | Augmentation | MVS | GO2122006585PH | 08/12/2021 | 0 | 0 | 0 | Bankura Division | Bankura Mechanical Division | 143.81 | 0 | 0 | 0 | 143.81 | 143.81 | 0 | 0 | 0 | 143.81 | 0 | 18
56 | BANKURA | SM/09878 | Augmentation of Joypur Piped Water Supply Scheme. | TSM/005084 | 40014162 | Augmentation | MVS | GO2122006584PH | 08/12/2021 | 726.64 | 96.07 | 822.71 | Bankura Division | Bankura Mechanical Division | 231.11 | 32.47 | 62.13 | 0 | 325.71 | 213.84 | 1.59 | 62.13 | 0 | 277.56 | 33.74 | 63
57 | BANKURA | SM/17419 | Augmentation of Karisunda Water Supply Scheme | TSM/019162 | 40060006 | Augmentation | MVS | GO2223017169PH | 18/03/2023 | 200.68 | 110.92 | 311.6 | Bankura Division | Bankura Mechanical Division | 26.02 | 45.35 | 0 | 0 | 71.37 | 26.02 | 40.16 | 0 | 0 | 66.18 | 21.24 | 40
58 | BANKURA | SM/09981 | Augmentation of Kotulpur Piped Water Supply Scheme. | TSM/005085 | 40017267 | Augmentation | MVS | GO2122006948PH | 16/12/2021 | 0 | 0 | 0 | Bankura Division | Bankura Mechanical Division | 421.77 | 34.16 | 25.01 | 0 | 480.94 | 396.98 | 34.16 | 25.01 | 0 | 456.16 | 0 | 29
59 | BANKURA | SM/17420 | Augmentation of Kushmuri Zone-A Water Supply Scheme | TSM/019165 | 40060045 | Augmentation | MVS | GO2223017149PH | 18/03/2023 | 169.83 | 119.15 | 288.97 | Bankura Division | Bankura Mechanical Division | 45.93 | 31.25 | 0 | 0 | 77.18 | 45.93 | 31.25 | 0 | 0 | 77.18 | 26.71 | 23
60 | BANKURA | SM/17682 | Augmentation of Kushmuri Zone-B Water Supply Scheme | TSM/019146 | 40060054 | Augmentation | MVS | GO2223016840PH | 17/03/2023 | 177.15 | 132.65 | 309.8 | Bankura Division | Bankura Mechanical Division | 33.35 | 33.7 | 0 | 0 | 67.05 | 33.35 | 0 | 0 | 0 | 33.35 | 10.77 | 35
61 | BANKURA | SM/17237 | Augmentation of Morar Zone-A Water Supply Scheme | TSM/019174 | 40060466 | Augmentation | MVS | GO2223016285PH | 15/03/2023 | 266.52 | 153.79 | 420.31 | Bankura Division | Bankura Mechanical Division | 119.14 | 34.26 | 0 | 0 | 153.4 | 119.14 | 34.26 | 0 | 0 | 153.4 | 36.5 | 36
62 | BANKURA | SM/17243 | Augmentation of Morar Zone-B Water Supply Scheme. | TSM/019179 | 0 | Augmentation | MVS | GO2223016284PH | 15/03/2023 | 244.48 | 194.79 | 439.27 | Bankura Division | Bankura Mechanical Division | 0 | 45.98 | 0 | 0 | 45.98 | 0 | 45.98 | 0 | 0 | 45.98 | 10.47 | 22
63 | BANKURA | SM/16260 | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VI WATER SUPPLY SCHEME | TSM/016333 | 40043140 | Augmentation | MVS | GO2223014859PH | 24/02/2023 | 372.88 | 10.74 | 383.62 | Bankura Division | Bankura Mechanical Division | 61.33 | 0 | 41.87 | 0 | 103.21 | 61.33 | 0 | 33.38 | 0 | 94.71 | 24.69 | 49
64 | BANKURA | SM/16261 | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | TSM/016343 | 40043815 | Augmentation | MVS | GO2223014858PH | 24/02/2023 | 472.86 | 36.79 | 509.65 | Bankura Division | Bankura Mechanical Division | 62.22 | 0 | 9.85 | 0 | 72.07 | 62.22 | 0 | 1.14 | 0 | 63.36 | 12.43 | 19
65 | BANKURA | SM/10290 | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | TSM/008518 | 40017361 | Augmentation | MVS | GO2122010175PH | 28/02/2022 | 926.41 | 78.13 | 1004.54 | Bankura Division | Bankura Mechanical Division | 357.23 | 38.4 | 28.91 | 0 | 424.54 | 357.23 | 38.4 | 28.91 | 0 | 424.54 | 42.26 | 47
66 | BANKURA | SM/17233 | Augmentation of Panchal Zone-I Water Supply Scheme | TSM/019138 | 40060293 | Augmentation | MVS | GO2223016310PH | 15/03/2023 | 23.84 | 0 | 23.84 | Bankura Division |  | 17.15 | 0 | 0 | 0 | 17.15 | 17.15 | 0 | 0 | 0 | 17.15 | 71.95 | 70
67 | BANKURA | SM/17423 | Augmentation of Panchal Zone-II Water Supply Scheme | TSM/019144 | 40060305 | Augmentation | MVS | GO2223017170PH | 18/03/2023 | 147.91 | 88.52 | 236.43 | Bankura Division | Bankura Mechanical Division | 32.5 | 21.44 | 0 | 0 | 53.93 | 32.5 | 16.61 | 0 | 0 | 49.1 | 20.77 | 56
68 | BANKURA | SM/09879 | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | TSM/005017 | 40063789 | Augmentation | MVS | GO2122006585PH | 08/12/2021 | 367.34 | 49.11 | 416.45 | Bankura Division | Bankura Mechanical Division | 63.52 | 0 | 0 | 0 | 63.52 | 63.52 | 0 | 0 | 0 | 63.52 | 15.25 | 9
69 | BANKURA | SM/09877 | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas | TSM/005016 | 40024753 | Augmentation | MVS | GO2122006583PH | 08/12/2021 | 537.93 | 118.34 | 656.27 | Bankura Division | Bankura Mechanical Division | 148.89 | 45.59 | 55.44 | 0 | 249.92 | 148.89 | 45.59 | 55.44 | 0 | 249.92 | 38.08 | 64
70 | BANKURA | SM/17441 | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | TSM/019125 | 40061291 | Augmentation | MVS | GO2223017027PH | 18/03/2023 | 183.86 | 42.77 | 226.63 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 1.32 | 0 | 1.32 | 0 | 0 | 1.32 | 0 | 1.32 | 0.58 | 15
71 | BANKURA | SM/17222 | Augmentation of Prakash Zone-A Water Supply Scheme | TSM/019131 | 40060354 | Augmentation | MVS | GO2223016150PH | 15/03/2023 | 185.96 | 0 | 185.96 | Bankura Division |  | 34.49 | 0 | 0 | 0 | 34.49 | 0 | 0 | 0 | 0 | 0 | 0 | 20
72 | BANKURA | SM/16945 | Augmentation of Prakash Zone-B Water Supply Scheme | TSM/019177 | 40060361 | Augmentation | MVS | GO2223016398PH | 16/03/2023 | 145.73 | 42.94 | 188.68 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
73 | BANKURA | SM/17690 | Augmentation of Radhanagar Zone-I Water Supply Scheme | TSM/019145 | 40060323 | Augmentation | MVS | GO2223016804PH | 17/03/2023 | 237.88 | 151.98 | 389.87 | Bankura Division | Bankura Mechanical Division | 41.29 | 22.96 | 0 | 0 | 64.24 | 41.29 | 22.96 | 0 | 0 | 64.24 | 16.48 | 41
74 | BANKURA | SM/17691 | Augmentation of Radhanagar Zone-II Water Supply Scheme | TSM/019169 | 40060335 | Augmentation | MVS | GO2223016838PH | 17/03/2023 | 133.28 | 86.33 | 219.61 | Bankura Division | Bankura Mechanical Division | 37.55 | 15.11 | 0 | 0 | 52.66 | 37.55 | 0 | 0 | 0 | 37.55 | 17.1 | 22
75 | BANKURA | SM/17693 | Augmentation of Rol Zone-A Water Supply Scheme | TSM/019121 | 40060059 | Augmentation | MVS | GO2223016834PH | 17/03/2023 | 124.6 | 41.11 | 165.71 | Bankura Division | Bankura Mechanical Division | 46.4 | 19.6 | 0 | 0 | 66 | 0 | 19.6 | 0 | 0 | 19.6 | 11.83 | 23
76 | BANKURA | SM/17683 | Augmentation of Rol Zone-B Water Supply Scheme | TSM/019094 | 40060084 | Augmentation | MVS | GO2223017188PH | 17/03/2023 | 206.72 | 135.1 | 341.82 | Bankura Division | Bankura Mechanical Division | 49.4 | 0 | 0 | 0 | 49.4 | 49.4 | 0 | 0 | 0 | 49.4 | 14.45 | 12
77 | BANKURA | SM/16950 | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | TSM/019127 | 40061126 | Augmentation | MVS | GO2223016487PH | 16/03/2023 | 246.4 | 0 | 246.4 | Bankura Division |  | 79.23 | 0 | 0.28 | 0 | 79.51 | 79.23 | 0 | 0.28 | 0 | 79.51 | 32.27 | 47
78 | BANKURA | SM/18114 | Augmentation of Sashpur Zone-A Water Supply Scheme | TSM/019166 | 40060103 | Augmentation | MVS | GO2223017141PH | 18/03/2023 | 226.76 | 135.1 | 361.86 | Bankura Division | Bankura Mechanical Division | 46.22 | 38.75 | 0 | 0 | 84.97 | 46.22 | 0 | 0 | 0 | 46.22 | 12.77 | 21
79 | BANKURA | SM/17421 | Augmentation of Sashpur Zone-B Water Supply Scheme | TSM/019015 | 40060267 | Augmentation | MVS | GO2223017151PH | 18/03/2023 | 209.7 | 135.1 | 344.8 | Bankura Division | Bankura Mechanical Division | 44.71 | 45.24 | 0 | 0 | 89.95 | 44.71 | 0 | 0 | 0 | 44.71 | 12.97 | 33
80 | BANKURA | SM/10294 | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | TSM/008341 | 40021233 | Augmentation | MVS | GO2122010200PH | 28/02/2022 | 1011.34 | 0 | 1011.34 | Bankura Division |  | 433.75 | 0 | 79.9 | 0 | 513.65 | 419.18 | 0 | 79.9 | 0 | 499.08 | 49.35 | 55
81 | BANKURA | SM/17579 | Augmentation of Somsar (BRGF) Water Supply Scheme | TSM/019167 | 40060272 | Augmentation | MVS | GO2223017036PH | 18/03/2023 | 69.11 | 35.23 | 104.34 | Bankura Division | Bankura Mechanical Division | 38.81 | 0 | 0 | 0 | 38.81 | 38.81 | 0 | 0 | 0 | 38.81 | 37.19 | 50
82 | BANKURA | SM/17422 | Augmentation of Somsar Water Supply Scheme | TSM/019134 | 40060289 | Augmentation | SVS | GO2223017162PH | 18/03/2023 | 96.37 | 55.78 | 152.16 | Bankura Division | Bankura Mechanical Division | 10.35 | 24.55 | 3.19 | 0 | 38.09 | 10.35 | 0 | 3.19 | 0 | 13.54 | 8.9 | 43
83 | BANKURA | SM/12382 | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | TSM/010931 | 5343948 | Augmentation | MVS | GO2223007572PH | 13/09/2022 | 451.85 | 148.2 | 600.05 | Bankura Division | Bankura Mechanical Division | 235.48 | 89.03 | 0 | 0 | 324.51 | 235.48 | 89.03 | 0 | 0 | 324.51 | 54.08 | 85
84 | BANKURA | SM/16952 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | TSM/019124 | 40061172 | Augmentation | MVS | GO2223016514PH | 16/03/2023 | 172.5 | 0 | 172.5 | Bankura Division |  | 2.04 | 0 | 0.64 | 0 | 2.68 | 2.04 | 0 | 0.64 | 0 | 2.68 | 1.56 | 8
85 | BANKURA | SM/10293 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | TSM/008339 | 40012806 | Augmentation | MVS | GO2122010178PH | 28/02/2022 | 1980.57 | 0 | 1980.57 | Bankura Division | Bankura Mechanical Division | 276.9 | 0 | 281.22 | 0 | 558.12 | 276.9 | 0 | 281.22 | 0 | 558.12 | 28.18 | 80
86 | BANKURA | SM/10292 | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | TSM/008338 | 40012785 | Augmentation | MVS | GO2122010198PH | 28/02/2022 | 3658.45 | 0 | 3658.45 | Bankura Division |  | 185.62 | 86.76 | 807.34 | 0 | 1079.72 | 185.62 | 0 | 807.34 | 0 | 992.96 | 27.14 | 20
87 | BANKURA | SM/12380 | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | TSM/011432 | 40034790 | Augmentation | MVS | GO2223007552PH | 13/09/2022 | 613.63 | 50.77 | 664.39 | Bankura Division | Bankura Mechanical Division | 190.2 | 4.46 | 92.2 | 0 | 286.87 | 190.2 | 0 | 92.2 | 0 | 282.4 | 42.51 | 19
88 | BANKURA | SM/17301 | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | TSM/019128 | 40061295 | Augmentation | MVS | GO2223016148PH | 15/03/2023 | 876.9 | 118.9 | 995.79 | Bankura Division | Bankura Mechanical Division | 353.18 | 31.01 | 0 | 0 | 384.18 | 353.18 | 31.01 | 0 | 0 | 384.18 | 38.58 | 37
89 | BANKURA | SM/08983 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) | TSM/008523 | 40024756 | Augmentation | MVS | GO2122004685PH | 29/10/2021 | 624.27 | 47.98 | 672.25 | Bankura Division | Bankura Mechanical Division | 225.85 | 11.59 | 0 | 0 | 237.44 | 225.85 | 11.59 | 0 | 0 | 237.44 | 35.32 | 67
90 | BANKURA | SM/16951 | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | TSM/019126 | 40061127 | Augmentation | MVS | GO2223016488PH | 16/03/2023 | 110.96 | 0 | 110.96 | Bankura Division |  | 0 | 0 | 35.74 | 0 | 35.74 | 0 | 0 | 35.74 | 0 | 35.74 | 32.21 | 10
91 | BANKURA | SM/12840 | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | TSM/014178 | 40066030 | Augmentation | MVS | GO2223008095PH | 22/09/2022 | 857.55 | 140.01 | 997.56 | Bankura Division | Bankura Mechanical Division | 83.25 | 0 | 12.44 | 0 | 95.69 | 83.25 | 0 | 6.22 | 0 | 89.47 | 8.97 | 100
92 | BANKURA | SM/17295 | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019151 | 40060516 | Augmentation | MVS | GO2223016304PH | 15/03/2023 | 608.47 | 181.86 | 790.33 | Bankura Division | Bankura Mechanical Division | 49.1 | 0 | 0 | 0 | 49.1 | 49.1 | 0 | 0 | 0 | 49.1 | 6.21 | 27
93 | BANKURA | SM/17434 | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019148 | 40061327 | Augmentation | MVS | GO2223017176PH | 18/03/2023 | 481.75 | 150.53 | 632.28 | Bankura Division | Bankura Mechanical Division | 37.9 | 0 | 0 | 0 | 37.9 | 37.9 | 0 | 0 | 0 | 37.9 | 5.99 | 19
94 | BANKURA | SM/17440 | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019188 | 40065474 | Augmentation | MVS | GO2223017154PH | 18/03/2023 | 755.14 | 230.37 | 985.52 | Bankura Division | Bankura Mechanical Division | 128.6 | 47.71 | 5.24 | 0 | 181.55 | 128.6 | 38.88 | 0 | 0 | 167.49 | 16.99 | 47
95 | BANKURA | SM/17288 | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019224 | 40060478 | Augmentation | MVS | GO2223016288PH | 15/03/2023 | 745.9 | 230.37 | 976.27 | Bankura Division | Bankura Mechanical Division | 100.79 | 57.93 | 4.8 | 0 | 163.52 | 100.79 | 47.77 | 0 | 0 | 148.57 | 15.22 | 41
96 | BANKURA | SM/12381 | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. | TSM/011121 | 40034629 | Augmentation | MVS | GO2223007548PH | 13/09/2022 | 206.2 | 0 | 206.2 | Bankura Division |  | 154.83 | 0 | 0 | 0 | 154.83 | 154.83 | 0 | 0 | 0 | 154.83 | 75.09 | 100
97 | BANKURA | SM/17302 | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019183 | 40060903 | Augmentation | MVS | GO2223016313PH | 15/03/2023 | 736.11 | 230.37 | 966.49 | Bankura Division | Bankura Mechanical Division | 378.81 | 7.97 | 0 | 0 | 386.78 | 378.81 | 0 | 0 | 0 | 378.81 | 39.19 | 57
98 | BANKURA | SM/18894 | Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020339 | 0 | Augmentation | MVS | PHE/IV/3034/W-661/23 | 05/10/2023 | 583.1 | 187.38 | 770.48 | Bankura Division | Bankura Mechanical Division | 0 | 2.43 | 0 | 0 | 2.43 | 0 | 0 | 0 | 0 | 0 | 0 | 6
99 | BANKURA | SM/18893 | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020340 | 0 | Augmentation | MVS | PHE/IV/3034/W-661/23 | 05/10/2023 | 313.47 | 150.53 | 464 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | BANKURA | SM/18895 | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020341 | 0 | Augmentation | MVS | PHE/IV/3034/W-661/23 | 05/10/2023 | 656.74 | 225.46 | 882.2 | Bankura Division | Bankura Mechanical Division | 0 | 3.44 | 0 | 0 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 3
101 | BANKURA | SM/18892 | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/020342 | 0 | Augmentation | MVS | PHE/IV/3034/W-661/23 | 05/10/2023 | 572.93 | 226.69 | 799.62 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
102 | BANKURA | SM/18119 | Augmentation works Chaknakaijuri and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | TSM/018959 | 40060373 | Augmentation | MVS | GO2223016098PH | 15/03/2023 | 280.17 | 106.93 | 387.1 | Bankura Division | Bankura Mechanical Division | 3.85 | 35.63 | 4.14 | 0 | 43.62 | 3.85 | 35.63 | 2.07 | 0 | 41.55 | 10.73 | 18
103 | BANKURA | SM/17252 | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018948 | 40059998 | Augmentation | MVS | GO2223016561PH | 15/03/2023 | 250.9 | 0 | 250.9 | Bankura Division |  | 10.3 | 0 | 1.86 | 0 | 12.16 | 10.3 | 0 | 1.86 | 0 | 12.16 | 4.85 | 25
104 | BANKURA | SM/17714 | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019227 | 40060416 | Augmentation | MVS | GO2223016869PH | 17/03/2023 | 653.73 | 209.47 | 863.2 | Bankura Division | Bankura Mechanical Division | 24.52 | 0 | 0 | 0 | 24.52 | 24.52 | 0 | 0 | 0 | 24.52 | 2.84 | 30
105 | BANKURA | SM/17236 | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018910 | 40060834 | Augmentation | MVS | GO2223016124PH | 15/03/2023 | 245.45 | 240.97 | 486.42 | Bankura Division | Bankura Mechanical Division | 17.67 | 163.88 | 1.03 | 0 | 182.59 | 17.67 | 20.73 | 1.03 | 0 | 39.44 | 8.11 | 44
106 | BANKURA | SM/18423 | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | TSM/018937 | 40061225 | Augmentation | MVS | 1922/PHE-28011/218/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 826.28 | 388.98 | 1215.26 | Bankura Division | Bankura Mechanical Division | 0 | 311.57 | 0 | 0 | 311.57 | 0 | 0 | 0 | 0 | 0 | 0 | 59
107 | BANKURA | SM/17253 | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018951 | 40060050 | Augmentation | MVS | GO2223016092PH | 15/03/2023 | 334.1 | 106.93 | 441.03 | Bankura Division | Bankura Mechanical Division | 103.16 | 35.89 | 5.92 | 0 | 144.98 | 103.16 | 35.89 | 2.96 | 0 | 142.02 | 32.2 | 34
108 | BANKURA | SM/17708 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018952 | 40060063 | Augmentation | MVS | GO2223016725PH | 17/03/2023 | 301.52 | 106.93 | 408.45 | Bankura Division | Bankura Mechanical Division | 115.56 | 22.84 | 1.11 | 0 | 139.5 | 81.31 | 22.84 | 1.11 | 0 | 105.26 | 25.77 | 43
109 | BANKURA | SM/17257 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018953 | 40060077 | Augmentation | MVS | GO2223016183PH | 15/03/2023 | 385.43 | 106.93 | 492.36 | Bankura Division | Bankura Mechanical Division | 104.7 | 29.29 | 1.5 | 0 | 135.49 | 104.7 | 0 | 1.5 | 0 | 106.2 | 21.57 | 28
110 | BANKURA | SM/17710 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | TSM/018954 | 40060105 | Augmentation | MVS | GO2223016782PH | 17/03/2023 | 516.34 | 115.21 | 631.55 | Bankura Division | Bankura Mechanical Division | 44.84 | 0 | 6.78 | 0 | 51.62 | 44.84 | 0 | 3.39 | 0 | 48.23 | 7.64 | 33
111 | BANKURA | SM/17258 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | TSM/018955 | 40060284 | Augmentation | MVS | GO2223016139PH | 15/03/2023 | 272.36 | 94.75 | 367.1 | Bankura Division | Bankura Mechanical Division | 67.54 | 0 | 1.29 | 0 | 68.83 | 67.54 | 0 | 1.29 | 0 | 68.83 | 18.75 | 23
112 | BANKURA | SM/17259 | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | TSM/018956 | 40060313 | Augmentation | SVS | GO2223016105PH | 15/03/2023 | 838.11 | 160.96 | 999.07 | Bankura Division | Bankura Mechanical Division | 340.07 | 0 | 28.98 | 0 | 369.04 | 340.07 | 0 | 28.98 | 0 | 369.04 | 36.94 | 34
113 | BANKURA | SM/17241 | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018925 | 40060899 | Augmentation | MVS | GO2223016115PH | 15/03/2023 | 376.35 | 123.5 | 499.85 | Bankura Division | Bankura Mechanical Division | 18.71 | 57.08 | 0.54 | 0 | 76.32 | 18.71 | 57.08 | 0.54 | 0 | 76.32 | 15.27 | 13
114 | BANKURA | SM/16972 | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018927 | 40060920 | Augmentation | MVS | GO2223016399PH | 16/03/2023 | 230.92 | 370.77 | 601.7 | Bankura Division | Bankura Mechanical Division | 28.88 | 98.15 | 0.36 | 0 | 127.38 | 28.88 | 0 | 0.36 | 0 | 29.23 | 4.86 | 26
115 | BANKURA | SM/16966 | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018919 | 40060896 | Augmentation | MVS | GO2223016407PH | 16/03/2023 | 367.01 | 111.53 | 478.54 | Bankura Division | Bankura Mechanical Division | 42.81 | 10.9 | 5.31 | 0 | 59.03 | 42.81 | 0 | 2.65 | 0 | 45.47 | 9.5 | 20
116 | BANKURA | SM/18231 | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019204 | 40061648 | Augmentation | MVS | PHE/IV/1404/W-604/23 | 05/06/2023 | 112.6 | 41.39 | 153.99 | Bankura Division | Bankura Mechanical Division | 19.32 | 0 | 0 | 0 | 19.32 | 19.32 | 0 | 0 | 0 | 19.32 | 12.55 | 50
117 | BANKURA | SM/17123 | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019237 | 40061654 | Augmentation | MVS | GO2223016513PH | 16/03/2023 | 189.14 | 41.39 | 230.53 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
118 | BANKURA | SM/17711 | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019211 | 40061356 | Augmentation | MVS | GO2223016809PH | 17/03/2023 | 274.98 | 189.59 | 464.57 | Bankura Division | Bankura Mechanical Division | 60.7 | 0 | 0 | 0 | 60.7 | 60.7 | 0 | 0 | 0 | 60.7 | 13.06 | 27
119 | BANKURA | SM/16974 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | TSM/018930 | 0 | Augmentation | MVS | GO2223016410PH | 16/03/2023 | 615.72 | 123.1 | 738.82 | Bankura Division | Bankura Mechanical Division | 199.55 | 0 | 0 | 0 | 199.55 | 115.27 | 0 | 0 | 0 | 115.27 | 15.6 | 30
120 | BANKURA | SM/17245 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). | TSM/018931 | 40061076 | Augmentation | MVS | GO2223016121PH | 15/03/2023 | 527.48 | 111.53 | 639.01 | Bankura Division | Bankura Mechanical Division | 48.35 | 21.68 | 1.86 | 0 | 71.89 | 48.35 | 21.68 | 1.86 | 0 | 71.89 | 11.25 | 10
121 | BANKURA | SM/17247 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | TSM/018932 | 40061077 | Augmentation | MVS | GO2223016160PH | 15/03/2023 | 463.27 | 123.1 | 586.37 | Bankura Division | Bankura Mechanical Division | 0 | 49.68 | 9.24 | 0 | 58.92 | 0 | 0 | 4.63 | 0 | 4.63 | 0.79 | 30
122 | BANKURA | SM/17428 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | TSM/018933 | 40061078 | Augmentation | MVS | GO2223017030PH | 18/03/2023 | 561.88 | 126.39 | 688.26 | Bankura Division | Bankura Mechanical Division | 44.06 | 21.69 | 7.07 | 0 | 72.82 | 44.06 | 21.69 | 3.54 | 0 | 69.29 | 10.07 | 16
123 | BANKURA | SM/17701 | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | TSM/018934 | 40061079 | Augmentation | MVS | GO2223016797PH | 17/03/2023 | 215.84 | 123.5 | 339.34 | Bankura Division | Bankura Mechanical Division | 57.81 | 0 | 1.18 | 0 | 58.98 | 57.81 | 0 | 1.18 | 0 | 58.98 | 17.38 | 24
124 | BANKURA | SM/17713 | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019150 | 40061278 | Augmentation | MVS | GO2223016831PH | 17/03/2023 | 556.01 | 187.38 | 743.39 | Bankura Division | Bankura Mechanical Division | 41.02 | 38.4 | 2.95 | 0 | 82.37 | 41.02 | 38.4 | 0 | 0 | 79.42 | 10.68 | 32
125 | BANKURA | SM/17292 | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | TSM/019153 | 40060485 | Augmentation | MVS | GO2223016298PH | 15/03/2023 | 560.17 | 192.29 | 752.47 | Bankura Division | Bankura Mechanical Division | 38.73 | 42.91 | 2.77 | 0 | 84.41 | 38.73 | 42.91 | 0 | 0 | 81.64 | 10.85 | 39
126 | BANKURA | SM/17303 | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | TSM/019129 | 40060829 | Augmentation | MVS | GO2223016154PH | 15/03/2023 | 230.94 | 54.74 | 285.68 | Bankura Division | Bankura Mechanical Division | 0 | 20.43 | 4.21 | 0 | 24.64 | 0 | 0 | 2.11 | 0 | 2.11 | 0.74 | 17
127 | BANKURA | SM/17730 | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019152 | 40060862 | Augmentation | MVS | GO2223016821PH | 17/03/2023 | 259.65 | 189.59 | 449.24 | Bankura Division | Bankura Mechanical Division | 35.67 | 0 | 2.34 | 0 | 38.01 | 35.67 | 0 | 2.34 | 0 | 38.01 | 8.46 | 36
128 | BANKURA | SM/17261 | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018957 | 40060345 | Augmentation | MVS | GO2223016174PH | 15/03/2023 | 332.4 | 106.93 | 439.33 | Bankura Division | Bankura Mechanical Division | 27.81 | 29.4 | 5.64 | 0 | 62.85 | 27.81 | 0 | 2.82 | 0 | 30.64 | 6.97 | 18
129 | BANKURA | SM/17291 | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | TSM/019122 | 40061268 | Augmentation | MVS | GO2223016080PH | 15/03/2023 | 140.58 | 103.65 | 244.22 | Bankura Division | Bankura Mechanical Division | 29.15 | 27.09 | 9.37 | 0 | 65.61 | 10.11 | 27.09 | 9.37 | 0 | 46.56 | 19.07 | 34
130 | BANKURA | SM/16980 | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019157 | 40061360 | Augmentation | MVS | GO2223016497PH | 16/03/2023 | 244.22 | 189.59 | 433.81 | Bankura Division | Bankura Mechanical Division | 36.29 | 0 | 0 | 0 | 36.29 | 36.29 | 0 | 0 | 0 | 36.29 | 8.37 | 39
131 | BANKURA | SM/16969 | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018923 | 40060876 | Augmentation | MVS | GO2223016483PH | 16/03/2023 | 528.87 | 111.53 | 640.4 | Bankura Division | Bankura Mechanical Division | 133.87 | 7.75 | 1.71 | 0 | 143.33 | 133.87 | 0 | 1.71 | 0 | 135.58 | 21.17 | 30
132 | BANKURA | SM/17698 | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018917 | 40060883 | Augmentation | MVS | GO2223016788PH | 17/03/2023 | 331.51 | 111.53 | 443.04 | Bankura Division | Bankura Mechanical Division | 91.84 | 0 | 1.95 | 0 | 93.79 | 86.21 | 0 | 1.95 | 0 | 88.16 | 19.9 | 25
133 | BANKURA | SM/16971 | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018926 | 40060913 | Augmentation | MVS | GO2223016414PH | 16/03/2023 | 472.89 | 135.07 | 607.96 | Bankura Division | Bankura Mechanical Division | 31.53 | 0 | 0.36 | 0 | 31.89 | 31.53 | 0 | 0.36 | 0 | 31.89 | 5.25 | 12
134 | BANKURA | SM/17697 | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018916 | 40060874 | Augmentation | MVS | GO2223016776PH | 17/03/2023 | 455.56 | 123.5 | 579.05 | Bankura Division | Bankura Mechanical Division | 137.31 | 60.95 | 1.92 | 0 | 200.18 | 137.2 | 0 | 1.92 | 0 | 139.12 | 24.03 | 30
135 | BANKURA | SM/17725 | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | TSM/019140 | 40060587 | Augmentation | MVS | GO2223016817PH | 17/03/2023 | 411.67 | 181.21 | 592.88 | Bankura Division | Bankura Mechanical Division | 91.65 | 0 | 0 | 0 | 91.65 | 91.65 | 0 | 0 | 0 | 91.65 | 15.46 | 69
136 | BANKURA | SM/17705 | Augmentation works for CHINABARI (Zone - H) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018946 | 40059961 | Augmentation | MVS | GO2223016814PH | 17/03/2023 | 271.86 | 0 | 271.86 | Bankura Division |  | 42.33 | 0 | 5.62 | 0 | 47.95 | 42.33 | 0 | 2.81 | 0 | 45.14 | 16.61 | 62
137 | BANKURA | SM/17235 | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018960 | 40061188 | Augmentation | MVS | GO2223016111PH | 15/03/2023 | 139.59 | 91.68 | 231.27 | Bankura Division | Bankura Mechanical Division | 3.74 | 10.2 | 0.82 | 0 | 14.76 | 3.74 | 0 | 0.82 | 0 | 4.56 | 1.97 | 5
138 | BANKURA | SM/17424 | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018908 | 40060799 | Augmentation | MVS | GO2223017033PH | 18/03/2023 | 281.25 | 111.53 | 392.78 | Bankura Division | Bankura Mechanical Division | 90.76 | 0 | 1.39 | 0 | 92.15 | 90.76 | 0 | 1.39 | 0 | 92.15 | 23.46 | 18
139 | BANKURA | SM/17297 | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | TSM/019155 | 40060545 | Augmentation | MVS | GO2223016299PH | 15/03/2023 | 660.35 | 209.47 | 869.82 | Bankura Division | Bankura Mechanical Division | 32.15 | 0 | 3.69 | 0 | 35.84 | 32.15 | 0 | 0 | 0 | 32.15 | 3.7 | 19
140 | BANKURA | SM/17281 | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | TSM/019143 | 40061305 | Augmentation | MVS | GO2223016301PH | 15/03/2023 | 704.47 | 225.46 | 929.93 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 42
141 | BANKURA | SM/17438 | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | TSM/019225 | 40060423 | Augmentation | MVS | GO2223017146PH | 18/03/2023 | 635.67 | 188.61 | 824.28 | Bankura Division | Bankura Mechanical Division | 69.47 | 0 | 2.77 | 0 | 72.23 | 69.47 | 0 | 0 | 0 | 69.47 | 8.43 | 31
142 | BANKURA | SM/16959 | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018909 | 40060819 | Augmentation | MVS | GO2223016480PH | 16/03/2023 | 265.4 | 111.53 | 376.93 | Bankura Division | Bankura Mechanical Division | 19.42 | 54.19 | 1.23 | 0 | 74.84 | 19.42 | 54.19 | 1.23 | 0 | 74.84 | 19.86 | 19
143 | BANKURA | SM/17703 | Augmentation works for HAPANIA (Zone - D) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018941 | 40059921 | Augmentation | MVS | GO2223016769PH | 17/03/2023 | 248.23 | 0 | 248.23 | Bankura Division |  | 19.85 | 0 | 7.47 | 0 | 27.32 | 19.85 | 0 | 3.74 | 0 | 23.59 | 9.5 | 10
144 | BANKURA | SM/16967 | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018920 | 40060818 | Augmentation | MVS | GO2223016481PH | 16/03/2023 | 623.26 | 125.86 | 749.13 | Bankura Division | Bankura Mechanical Division | 27.83 | 1.43 | 8.83 | 0 | 38.09 | 27.83 | 0 | 4.42 | 0 | 32.24 | 4.3 | 13
145 | BANKURA | SM/17430 | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | TSM/019206 | 40061456 | Augmentation | MVS | GO2223017178PH | 18/03/2023 | 267.97 | 189.59 | 457.56 | Bankura Division | Bankura Mechanical Division | 19.99 | 0 | 0 | 0 | 19.99 | 19.99 | 0 | 0 | 0 | 19.99 | 4.37 | 23
146 | BANKURA | SM/16970 | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018924 | 40060884 | Augmentation | MVS | GO2223016404PH | 16/03/2023 | 377.24 | 111.53 | 488.77 | Bankura Division | Bankura Mechanical Division | 38.7 | 21.68 | 1.79 | 0 | 62.17 | 20.95 | 21.68 | 1.79 | 0 | 44.42 | 9.09 | 8
147 | BANKURA | SM/17262 | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | TSM/018961 | 40060391 | Augmentation | MVS | GO2223016134PH | 15/03/2023 | 258.67 | 89.53 | 348.2 | Bankura Division | Bankura Mechanical Division | 0 | 22.22 | 2.07 | 0 | 24.28 | 0 | 0 | 1.03 | 0 | 1.03 | 0.3 | 11
148 | BANKURA | SM/17432 | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) | TSM/019189 | 40061439 | Augmentation | MVS | GO2223017161PH | 18/03/2023 | 246.61 | 189.59 | 436.2 | Bankura Division | Bankura Mechanical Division | 27.58 | 0 | 0 | 0 | 27.58 | 27.58 | 0 | 0 | 0 | 27.58 | 6.32 | 35
149 | BANKURA | SM/16976 | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018939 | 40059901 | Augmentation | MVS | GO2223016585PH | 16/03/2023 | 306.48 | 0 | 306.48 | Bankura Division |  | 57.84 | 0 | 7.02 | 0 | 64.87 | 57.84 | 0 | 3.51 | 0 | 61.35 | 20.02 | 90
150 | BANKURA | SM/17694 | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018913 | 40060860 | Augmentation | MVS | GO2223016780PH | 17/03/2023 | 344.81 | 129.15 | 473.96 | Bankura Division | Bankura Mechanical Division | 13.13 | 29.18 | 5.08 | 0 | 47.39 | 13.13 | 29.18 | 2.54 | 0 | 44.85 | 9.46 | 13
151 | BANKURA | SM/16961 | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018912 | 40060850 | Augmentation | MVS | GO2223016400PH | 16/03/2023 | 345.39 | 111.53 | 456.92 | Bankura Division | Bankura Mechanical Division | 29.77 | 0 | 1.93 | 0 | 31.7 | 29.77 | 0 | 1.93 | 0 | 31.7 | 6.94 | 5
152 | BANKURA | SM/17433 | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019218 | 40061419 | Augmentation | MVS | GO2223017156PH | 18/03/2023 | 299.63 | 189.59 | 489.22 | Bankura Division | Bankura Mechanical Division | 26.3 | 0 | 0 | 0 | 26.3 | 26.3 | 0 | 0 | 0 | 26.3 | 5.38 | 18
153 | BANKURA | SM/16958 | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018962 | 40061185 | Augmentation | MVS | GO2223016584PH | 16/03/2023 | 187.97 | 101.62 | 289.59 | Bankura Division | Bankura Mechanical Division | 68.91 | 40.79 | 1 | 0 | 110.69 | 68.91 | 0 | 1 | 0 | 69.9 | 24.14 | 19
154 | BANKURA | SM/16957 | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018963 | 40061182 | Augmentation | MVS | GO2223016509PH | 16/03/2023 | 191.97 | 101.62 | 293.59 | Bankura Division | Bankura Mechanical Division | 11.73 | 0 | 1.48 | 0 | 13.21 | 11.73 | 0 | 1.48 | 0 | 13.21 | 4.5 | 5
155 | BANKURA | SM/16956 | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018907 | 40060788 | Augmentation | MVS | GO2223016416PH | 16/03/2023 | 503.01 | 129.15 | 632.16 | Bankura Division | Bankura Mechanical Division | 78.05 | 49.66 | 6.64 | 0 | 134.34 | 78.05 | 0 | 3.32 | 0 | 81.37 | 12.87 | 20
156 | BANKURA | SM/16968 | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018921 | 40060835 | Augmentation | MVS | GO2223016484PH | 16/03/2023 | 323.82 | 123.5 | 447.32 | Bankura Division | Bankura Mechanical Division | 23.23 | 14.53 | 1.54 | 0 | 39.3 | 23.23 | 0 | 1.54 | 0 | 24.77 | 5.54 | 18
157 | BANKURA | SM/17429 | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019244 | 40061538 | Augmentation | MVS | GO2223017167PH | 18/03/2023 | 274.59 | 189.99 | 464.58 | Bankura Division | Bankura Mechanical Division | 30.85 | 0 | 0 | 0 | 30.85 | 30.85 | 0 | 0 | 0 | 30.85 | 6.64 | 18
158 | BANKURA | SM/17695 | Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018915 | 40060867 | Augmentation | MVS | GO2223016774PH | 17/03/2023 | 570.07 | 111.53 | 681.6 | Bankura Division | Bankura Mechanical Division | 32.2 | 0 | 4.67 | 0 | 36.87 | 32.2 | 0 | 2.33 | 0 | 34.53 | 5.07 | 3
159 | BANKURA | SM/16955 | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018906 | 40060556 | Augmentation | MVS | GO2223016489PH | 16/03/2023 | 366.95 | 111.53 | 478.49 | Bankura Division | Bankura Mechanical Division | 36.87 | 49.68 | 6.86 | 0 | 93.41 | 36.87 | 0 | 3.43 | 0 | 40.31 | 8.42 | 35
160 | BANKURA | SM/17242 | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018928 | 40060971 | Augmentation | MVS | GO2223016156PH | 15/03/2023 | 379.81 | 123.5 | 503.31 | Bankura Division | Bankura Mechanical Division | 23.94 | 0 | 0.36 | 0 | 24.3 | 23.94 | 0 | 0.36 | 0 | 24.3 | 4.83 | 3
161 | BANKURA | SM/16984 | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019159 | 40065465 | Augmentation | MVS | GO2223016490PH | 16/03/2023 | 310.6 | 189.59 | 500.19 | Bankura Division | Bankura Mechanical Division | 93.99 | 0 | 0 | 0 | 93.99 | 93.99 | 0 | 0 | 0 | 93.99 | 18.79 | 19
162 | BANKURA | SM/17313 | Augmentation works for Lakshmanpur (Zone L) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018950 | 40060043 | Augmentation | MVS | GO2223016141PH | 15/03/2023 | 347.79 | 0 | 347.79 | Bankura Division |  | 75.64 | 0 | 10.71 | 0 | 86.35 | 75.64 | 0 | 5.36 | 0 | 81 | 23.29 | 45
163 | BANKURA | SM/17251 | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019241 | 40061529 | Augmentation | MVS | GO2223016283PH | 15/03/2023 | 265.29 | 189.99 | 455.28 | Bankura Division | Bankura Mechanical Division | 30.31 | 0 | 0 | 0 | 30.31 | 30.31 | 0 | 0 | 0 | 30.31 | 6.66 | 17
164 | BANKURA | SM/17234 | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018902 | 40060529 | Augmentation | MVS | GO2223016180PH | 15/03/2023 | 368.95 | 111.53 | 480.48 | Bankura Division | Bankura Mechanical Division | 49.87 | 0 | 6.93 | 0 | 56.8 | 49.87 | 0 | 3.47 | 0 | 53.34 | 11.1 | 8
165 | BANKURA | SM/17729 | Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019163 | 40060929 | Augmentation | MVS | GO2223016859PH | 17/03/2023 | 269.67 | 189.59 | 459.25 | Bankura Division | Bankura Mechanical Division | 93.34 | 0 | 3.81 | 0 | 97.15 | 93.34 | 0 | 0 | 0 | 93.34 | 20.32 | 23
166 | BANKURA | SM/16977 | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | TSM/018949 | 40060007 | Augmentation | MVS | GO2223016583PH | 16/03/2023 | 234.93 | 0 | 234.93 | Bankura Division |  | 28.12 | 0 | 1.72 | 0 | 29.85 | 28.12 | 0 | 1.72 | 0 | 29.85 | 12.71 | 28
167 | BANKURA | SM/17304 | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019161 | 40060993 | Augmentation | MVS | GO2223016281PH | 15/03/2023 | 296.07 | 189.59 | 485.66 | Bankura Division | Bankura Mechanical Division | 74.06 | 0 | 2.58 | 0 | 76.64 | 74.06 | 0 | 0 | 0 | 74.06 | 15.25 | 32
168 | BANKURA | SM/17280 | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018964 | 40060474 | Augmentation | MVS | GO2223016085PH | 15/03/2023 | 226.17 | 101.62 | 327.8 | Bankura Division | Bankura Mechanical Division | 13.44 | 36.53 | 1.5 | 0 | 51.47 | 13.44 | 0 | 1.5 | 0 | 14.94 | 4.56 | 6
169 | BANKURA | SM/17712 | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018965 | 40060482 | Augmentation | MVS | GO2223016764PH | 17/03/2023 | 245.51 | 101.62 | 347.13 | Bankura Division | Bankura Mechanical Division | 59.25 | 0 | 4.17 | 0 | 63.43 | 59.25 | 0 | 2.09 | 0 | 61.34 | 17.67 | 13
170 | BANKURA | SM/16954 | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | TSM/018966 | 40061178 | Augmentation | SVS | GO2223016511PH | 16/03/2023 | 96.8 | 30.81 | 127.61 | Bankura Division | Bankura Mechanical Division | 22.93 | 17.53 | 6.43 | 0 | 46.9 | 12.04 | 0 | 3.22 | 0 | 15.26 | 11.96 | 12
171 | BANKURA | SM/16973 | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | TSM/018929 | 40060979 | Augmentation | MVS | GO2223016402PH | 16/03/2023 | 310.2 | 106.93 | 417.13 | Bankura Division | Bankura Mechanical Division | 112.75 | 33.16 | 4.5 | 0 | 150.41 | 112.75 | 33.16 | 2.25 | 0 | 148.16 | 35.52 | 29
172 | BANKURA | SM/18424 | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | TSM/019230 | 40061498 | Augmentation | MVS | 1922/PHE-28011/218/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 676.73 | 416.18 | 1092.92 | Bankura Division | Bankura Mechanical Division | 35.43 | 6.19 | 2.03 | 0 | 43.65 | 35.43 | 0 | 2.03 | 0 | 37.46 | 3.43 | 10
173 | BANKURA | SM/17707 | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | TSM/019235 | 40061515 | Augmentation | MVS | GO2223016841PH | 17/03/2023 | 467.73 | 208.09 | 675.82 | Bankura Division | Bankura Mechanical Division | 48.49 | 0 | 0 | 0 | 48.49 | 48.49 | 0 | 0 | 0 | 48.49 | 7.17 | 14
174 | BANKURA | SM/17282 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018967 | 40060488 | Augmentation | MVS | GO2223016096PH | 15/03/2023 | 456.38 | 94.97 | 551.35 | Bankura Division | Bankura Mechanical Division | 107.76 | 0 | 5.69 | 0 | 113.46 | 107.76 | 0 | 2.85 | 0 | 110.61 | 20.06 | 29
175 | BANKURA | SM/17284 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018968 | 40060525 | Augmentation | MVS | GO2223016087PH | 15/03/2023 | 460.82 | 94.97 | 555.78 | Bankura Division | Bankura Mechanical Division | 149.01 | 41.99 | 1.8 | 0 | 192.8 | 149.01 | 0 | 1.8 | 0 | 150.81 | 27.13 | 49
176 | BANKURA | SM/17285 | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | TSM/018969 | 40060548 | Augmentation | MVS | GO2223016091PH | 15/03/2023 | 579.35 | 42.77 | 622.12 | Bankura Division | Bankura Mechanical Division | 148.32 | 0 | 25.33 | 0 | 173.65 | 148.22 | 0 | 12.66 | 0 | 160.89 | 25.86 | 49
177 | BANKURA | SM/17286 | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | TSM/018970 | 40060584 | Augmentation | MVS | GO2223016102PH | 15/03/2023 | 207.73 | 54.74 | 262.47 | Bankura Division | Bankura Mechanical Division | 98.47 | 25.39 | 1.8 | 0 | 125.65 | 98.47 | 25.39 | 1.8 | 0 | 125.65 | 47.87 | 44
178 | BANKURA | SM/17287 | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | TSM/018971 | 40061261 | Augmentation | MVS | GO2223016118PH | 15/03/2023 | 206.04 | 54.74 | 260.78 | Bankura Division | Bankura Mechanical Division | 69.22 | 21.09 | 1.86 | 0 | 92.16 | 69.22 | 21.09 | 1.86 | 0 | 92.16 | 35.34 | 31
179 | BANKURA | SM/16975 | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | TSM/018936 | 40061087 | Augmentation | MVS | GO2223016516PH | 16/03/2023 | 282.39 | 0 | 282.39 | Bankura Division |  | 91.52 | 0 | 1.7 | 0 | 93.22 | 91.52 | 0 | 1.7 | 0 | 93.22 | 33.01 | 55
180 | BANKURA | SM/17248 | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | TSM/018935 | 40061085 | Augmentation | MVS | GO2223016171PH | 15/03/2023 | 394.85 | 0 | 394.85 | Bankura Division |  | 104.56 | 0 | 5.91 | 0 | 110.47 | 104.56 | 0 | 2.96 | 0 | 107.51 | 27.23 | 50
181 | BANKURA | SM/16960 | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018911 | 40060843 | Augmentation | MVS | GO2223016409PH | 16/03/2023 | 537.13 | 141.11 | 678.24 | Bankura Division | Bankura Mechanical Division | 8.24 | 54.14 | 5.64 | 0 | 68.02 | 8.24 | 54.14 | 2.82 | 0 | 65.2 | 9.61 | 11
182 | BANKURA | SM/17240 | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018922 | 40060865 | Augmentation | MVS | GO2223016187PH | 15/03/2023 | 436.17 | 111.53 | 547.7 | Bankura Division | Bankura Mechanical Division | 71.97 | 0 | 1.23 | 0 | 73.2 | 30.5 | 0 | 1.23 | 0 | 31.73 | 5.79 | 6
183 | BANKURA | SM/16964 | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | TSM/018918 | 40060889 | Augmentation | MVS | GO2223016486PH | 16/03/2023 | 324.82 | 369.19 | 694.01 | Bankura Division | Bankura Mechanical Division | 86.86 | 0 | 5.34 | 0 | 92.2 | 86.86 | 0 | 2.67 | 0 | 89.53 | 12.9 | 7
184 | BANKURA | SM/17731 | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019156 | 40061351 | Augmentation | MVS | GO2223016792PH | 17/03/2023 | 294.59 | 189.59 | 484.18 | Bankura Division | Bankura Mechanical Division | 61.4 | 0 | 26 | 0 | 87.41 | 61.4 | 0 | 0 | 0 | 61.4 | 12.68 | 30
185 | BANKURA | SM/17260 | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019215 | 40061407 | Augmentation | MVS | GO2223016307PH | 15/03/2023 | 247.03 | 189.59 | 436.62 | Bankura Division | Bankura Mechanical Division | 30.69 | 0 | 0 | 0 | 30.69 | 30.69 | 0 | 0 | 0 | 30.69 | 7.03 | 45
186 | BANKURA | SM/18403 | Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | TSM/019164 | 40060911 | Augmentation | MVS | 1851/PHE-28011/218/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 1610.42 | 1137.54 | 2747.96 | Bankura Division | Bankura Mechanical Division | 475.78 | 0 | 18.48 | 0 | 494.26 | 313.29 | 0 | 18.48 | 0 | 331.77 | 12.07 | 21
187 | BANKURA | SM/18305 | Bagdoba Piped Water Supply Scheme | TSM/014781 | 40041763 | New | MVS | 1659/PHE-28011/184/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 1063.63 | 125.54 | 1189.17 | Bankura Division | Bankura Mechanical Division | 177.44 | 33.26 | 141.04 | 0 | 351.75 | 177.44 | 33.26 | 141.04 | 0 | 351.75 | 29.58 | 34
188 | BANKURA | SM/14525 | Banna Piped Water Supply Scheme | TSM/014200 | 40035012 | New | MVS | GO2223012617PH | 30/01/2023 | 1274.74 | 149.6 | 1424.34 | Bankura Division | Bankura Mechanical Division | 33.71 | 18.17 | 110.53 | 0 | 162.4 | 12.31 | 4.96 | 110.53 | 0 | 127.8 | 8.97 | 5
189 | BANKURA | SM/18789 | Baragaria Piped Water Supply Scheme | TSM/018204 | 40059775 | New | MVS | 2692/PHE-28011/187/2023-SCHM CELL-Dept. of PHE | 07/09/2023 | 1367.96 | 161.04 | 1529 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 96.69 | 0 | 96.69 | 0 | 0 | 96.69 | 0 | 96.69 | 6.32 | 13
190 | BANKURA | SM/12424 | Basantapur Piped Water Supply Scheme | TSM/014203 | 40034950 | New | MVS | GO2223007567PH | 13/09/2022 | 774.48 | 108.47 | 882.95 | Bankura Division | Bankura Mechanical Division | 10.88 | 4.47 | 41.93 | 0 | 57.28 | 1.08 | 4.47 | 41.93 | 0 | 47.49 | 5.38 | 3
191 | BANKURA | SM/12416 | Bhat Pushkarini Piped Water Supply Scheme | TSM/014586 | 40041261 | New | MVS | GO2223007570PH | 13/09/2022 | 852.55 | 96.1 | 948.65 | Bankura Division | Bankura Mechanical Division | 123.23 | 27.75 | 153.06 | 0 | 304.04 | 123.23 | 27.75 | 143.3 | 0 | 294.29 | 31.02 | 33
192 | BANKURA | SM/16700 | Bhubut Piped Water Supply Scheme | TSM/018244 | 40061485 | New | MVS | GO2223016014PH | 14/03/2023 | 450.47 | 67.83 | 518.29 | Bankura Division | Bankura Mechanical Division | 48.13 | 0 | 0 | 0 | 48.13 | 48.13 | 0 | 0 | 0 | 48.13 | 9.29 | 13
193 | BANKURA | SM/18340 | Binod Nagar Piped Water Supply Scheme | TSM/015427 | 40043942 | New | MVS | 1737/PHE-28011/45/2023-SCHM CELL-Dept. of PHE | 04/07/2023 | 979.86 | 133.23 | 1113.09 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
194 | BANKURA | SM/18754 | Biur Piped Water Supply Scheme | TSM/017778 | 40061281 | New | MVS | 2481/PHE-28011/190/2023-SCHM CELL-Dept. of PHE | 21/08/2023 | 1156.3 | 178.15 | 1334.45 | Bankura Division | Bankura Mechanical Division | 0 | 3.28 | 43.55 | 0 | 46.82 | 0 | 0 | 0 | 0 | 0 | 0 | 1
195 | BANKURA | SM/18437 | Brindabanpur Piped Water Supply Scheme | TSM/015157 | 40034995 | New | MVS | 1932/PHE-28011/232/2022-SCHM CELL-Dept. of PHE | 18/07/2023 | 1487.44 | 161.6 | 1649.04 | Bankura Division | Bankura Mechanical Division | 8.84 | 0 | 64.36 | 0 | 73.2 | 8.84 | 0 | 64.36 | 0 | 73.2 | 4.44 | 15
196 | BANKURA | SM/18401 | Chak Patrasaer Piped Water Supply Scheme | TSM/015946 | 40044167 | New | MVS | 1849/PHE-28011/27/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 1109.9 | 170.12 | 1280.02 | Bankura Division | Bankura Mechanical Division | 0.1 | 29.12 | 61.79 | 0 | 91.02 | 0 | 18.8 | 61.79 | 0 | 80.6 | 6.3 | 28
197 | BANKURA | SM/14245 | Chakai Piped Water Supply Scheme | TSM/015173 | 40034875 | New | MVS | GO2223011829PH | 16/01/2023 | 1035.16 | 107.73 | 1142.89 | Bankura Division | Bankura Mechanical Division | 85.33 | 29.11 | 111.05 | 0 | 225.49 | 85.33 | 0 | 111.05 | 0 | 196.38 | 17.18 | 17
198 | BANKURA | SM/13999 | Chandal Bandi Piped Water Supply Scheme | TSM/015424 | 40035933 | New | MVS | GO2223010521PH | 05/12/2022 | 508.82 | 94.21 | 603.03 | Bankura Division | Bankura Mechanical Division | 0 | 16.49 | 0 | 0 | 16.49 | 0 | 0 | 0 | 0 | 0 | 0 | 27
199 | BANKURA | SM/09317 | Construction & commissioning d of FHTC by Retrofitting of completeand commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Kunjapur-112 & Bahalalpur-114) of Betanal | TSM/007422 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 97.49 | 0 | 97.49 | Bankura Division |  | 52.08 | 0 | 0 | 0 | 52.08 | 52.08 | 0 | 0 | 0 | 52.08 | 53.42 | 54
200 | BANKURA | SM/07255 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Talanjuri) of Talanjuri (Zone - F) under Bankura - I,II & Bar | TSM/005922 | 5343948 | Retrofitting | SVS | GO2021003119PH | 08/12/2020 | 98.39 | 0 | 98.39 | Bankura Division |  | 88.39 | 0 | 0 | 0 | 88.39 | 88.39 | 0 | 0 | 0 | 88.39 | 89.83 | 100
201 | BANKURA | SM/07312 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Ladna, Mathana, Kodalia) of Joytunga (Zone - H) under Banku | TSM/005999 | 5343948 | Retrofitting | MVS | GO2021003272PH | 10/12/2020 | 85.93 | 0 | 85.93 | Bankura Division |  | 85.93 | 0 | 0 | 0 | 85.93 | 85.93 | 0 | 0 | 0 | 85.93 | 100 | 100
202 | BANKURA | SM/07313 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bara Bendya, Joytunga, Kostia & Khemua) of Joytunga (Zone - | TSM/005998 | 5343948 | Retrofitting | MVS | GO2021003265PH | 10/12/2020 | 97.22 | 0 | 97.22 | Bankura Division |  | 94.39 | 0 | 0 | 0 | 94.39 | 93.55 | 0 | 0 | 0 | 93.55 | 96.23 | 100
203 | BANKURA | SM/07259 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Koskunda, Kanchanpur, Kalapani & Nirshce) of Kanchanpur (Zo | TSM/005926 | 5343948 | Retrofitting | MVS | GO2021003159PH | 08/12/2020 | 86.91 | 0 | 86.91 | Bankura Division |  | 86.91 | 0 | 0 | 0 | 86.91 | 86.91 | 0 | 0 | 0 | 86.91 | 100 | 100
204 | BANKURA | SM/07328 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Ramchandrapur, Paschim Brindabanpur, Palsana & Saluka) of Jo | TSM/005965 | 5343948 | Retrofitting | MVS | GO2021003264PH | 10/12/2020 | 95.32 | 0 | 95.32 | Bankura Division |  | 92.54 | 0 | 0 | 0 | 92.54 | 92.54 | 0 | 0 | 0 | 92.54 | 97.09 | 100
205 | BANKURA | SM/07258 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Shitla, Manjumara, Monoharbati & Pabaya) of Kanchanpur (Zone - | TSM/005925 | 5343948 | Retrofitting | MVS | GO2021003106PH | 08/12/2020 | 86.63 | 0 | 86.63 | Bankura Division |  | 84.1 | 0 | 0 | 0 | 84.1 | 84.1 | 0 | 0 | 0 | 84.1 | 97.09 | 100
206 | BANKURA | SM/07314 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Bandarkhola, Ramharipur, Katapesia, Kolaberia & Maitha Gopinat | TSM/005997 | 5343948 | Retrofitting | MVS | GO2021003220PH | 10/12/2020 | 91.63 | 0 | 91.63 | Bankura Division |  | 88.96 | 0 | 0 | 0 | 88.96 | 88.96 | 0 | 0 | 0 | 88.96 | 97.09 | 100
207 | BANKURA | SM/07260 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Dakaisini, Khandari, Bansol, Dhwajmonipur & Damodarpur) of | TSM/005927 | 5343948 | Retrofitting | MVS | GO2021003158PH | 08/12/2020 | 89.89 | 0 | 89.89 | Bankura Division |  | 87.27 | 0 | 0 | 0 | 87.27 | 87.27 | 0 | 0 | 0 | 87.27 | 97.09 | 100
208 | BANKURA | SM/07317 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gou | TSM/005992 | 5343948 | Retrofitting | MVS | GO2021003235PH | 10/12/2020 | 85.51 | 0 | 85.51 | Bankura Division |  | 83.02 | 0 | 0 | 0 | 83.02 | 83.02 | 0 | 0 | 0 | 83.02 | 97.09 | 100
209 | BANKURA | SM/07339 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorshal, Dhenga kend, Kushma, Golhati & Bonomadhavpur) of J | TSM/006000 | 5343948 | Retrofitting | MVS | GO2021003356PH | 11/12/2020 | 81.28 | 0 | 81.28 | Bankura Division |  | 78.79 | 0 | 0 | 0 | 78.79 | 78.79 | 0 | 0 | 0 | 78.79 | 96.94 | 100
210 | BANKURA | SM/07261 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kurulia, Majdangra, Gadardihi Balarampur, Gadardihi & Gobindap | TSM/005928 | 5343948 | Retrofitting | MVS | GO2021003157PH | 08/12/2020 | 83.44 | 0 | 83.44 | Bankura Division |  | 81.01 | 0 | 0 | 0 | 81.01 | 81.01 | 0 | 0 | 0 | 81.01 | 97.09 | 100
211 | BANKURA | SM/07243 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kusum Goria, Tajpur Rampur, Rajmadhavtir, Kotalpukur & Mahidar | TSM/005984 | 5343948 | Retrofitting | MVS | GO2021003150PH | 08/12/2020 | 77.66 | 0 | 77.66 | Bankura Division |  | 74.71 | 0 | 0 | 0 | 74.71 | 74.71 | 0 | 0 | 0 | 74.71 | 96.21 | 100
212 | BANKURA | SM/07256 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Purunia, sangrampur, Laxminarayanpur, Baharkhulia & Gangadarpu | TSM/005923 | 5343948 | Retrofitting | MVS | GO2021003112PH | 08/12/2020 | 98.92 | 0 | 98.92 | Bankura Division |  | 93.33 | 0 | 0 | 0 | 93.33 | 93.33 | 0 | 0 | 0 | 93.33 | 94.35 | 100
213 | BANKURA | SM/07251 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)} o | TSM/005961 | 5343948 | Retrofitting | MVS | GO2021003135PH | 08/12/2020 | 99.13 | 0 | 99.13 | Bankura Division |  | 96.25 | 0 | 0 | 0 | 96.25 | 96.25 | 0 | 0 | 0 | 96.25 | 97.09 | 100
214 | BANKURA | SM/07263 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouza (Bandarkoda, Bhairabdanga, Barkura, Radhakantapur, Kantabesa, Ni | TSM/005931 | 5343948 | Retrofitting | MVS | GO2021003151PH | 08/12/2020 | 99.4 | 0 | 99.4 | Bankura Division |  | 96.51 | 0 | 0 | 0 | 96.51 | 96.51 | 0 | 0 | 0 | 96.51 | 97.09 | 100
215 | BANKURA | SM/07327 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Phulberia , Bahadurpur , Ratganj Madhavpur , Oltara, Sirsa & J | TSM/005960 | 5343948 | Retrofitting | MVS | GO2021003262PH | 10/12/2020 | 66.26 | 0 | 66.26 | Bankura Division |  | 64.33 | 0 | 0 | 0 | 64.33 | 64.29 | 0 | 0 | 0 | 64.29 | 97.03 | 100
216 | BANKURA | SM/07345 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouza (Talanda, Cahndanpur, Swargabati, Harishpur, Gopinathpur, Brinda | TSM/005930 | 5343948 | Retrofitting | MVS | GO2021003333PH | 11/12/2020 | 85.97 | 0 | 85.97 | Bankura Division |  | 83.47 | 0 | 0 | 0 | 83.47 | 83.47 | 0 | 0 | 0 | 83.47 | 97.09 | 100
217 | BANKURA | SM/07305 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hare Krishnapur , Dadimukha , Gopbandh , Bankuradanga, Belut , | TSM/006002 | 5343948 | Retrofitting | MVS | GO2021003238PH | 10/12/2020 | 96.08 | 0 | 96.08 | Bankura Division |  | 93.29 | 0 | 0 | 0 | 93.29 | 93.29 | 0 | 0 | 0 | 93.29 | 97.09 | 100
218 | BANKURA | SM/07257 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Narricha, Bhabanipur, Namonahar, Barapukura, Baliguma, Sapkrra | TSM/005924 | 5343948 | Retrofitting | MVS | GO2021003110PH | 08/12/2020 | 94.9 | 0 | 94.9 | Bankura Division |  | 92.13 | 0 | 0 | 0 | 92.13 | 92.13 | 0 | 0 | 0 | 92.13 | 97.09 | 100
219 | BANKURA | SM/07306 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Kantabandh, Elianarayan pur, Radharamanpur, Birsingpur, Saldan | TSM/006001 | 5343948 | Retrofitting | MVS | GO2021003237PH | 10/12/2020 | 96.39 | 0 | 96.39 | Bankura Division |  | 93.58 | 0 | 0 | 0 | 93.58 | 93.58 | 0 | 0 | 0 | 93.58 | 97.09 | 100
220 | BANKURA | SM/07248 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Basuda, Rajprasadpur, Saldanga, Managram, Dewangrya, Numuigary | TSM/005989 | 5343948 | Retrofitting | MVS | GO2021003149PH | 08/12/2020 | 83.6 | 0 | 83.6 | Bankura Division |  | 71.35 | 0 | 0 | 0 | 71.35 | 71.35 | 0 | 0 | 0 | 71.35 | 85.35 | 100
221 | BANKURA | SM/07346 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Shyamdaspur, Amthia, Krishnapur, Benachapra, Mathurberia, Math | TSM/005932 | 5343948 | Retrofitting | MVS | GO2021003343PH | 11/12/2020 | 99.61 | 0 | 99.61 | Bankura Division |  | 96.71 | 0 | 0 | 0 | 96.71 | 96.71 | 0 | 0 | 0 | 96.71 | 97.09 | 100
222 | BANKURA | SM/07262 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 12 Nos. Mouzas (Enayetpur, Kaleberia, Namoghansara, Kururia Balarampur, Malkur | TSM/005929 | 5343948 | Retrofitting | MVS | GO2021003156PH | 08/12/2020 | 80.43 | 0 | 80.43 | Bankura Division |  | 78.09 | 0 | 0 | 0 | 78.09 | 78.08 | 0 | 0 | 0 | 78.08 | 97.08 | 100
223 | BANKURA | SM/07309 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - I) of MALIARA (Zone - A) under Bankura - I, II | TSM/006003 | 5343948 | Retrofitting | SVS | GO2021003241PH | 10/12/2020 | 84.49 | 0 | 84.49 | Bankura Division |  | 82.03 | 0 | 0 | 0 | 82.03 | 82.03 | 0 | 0 | 0 | 82.03 | 97.09 | 100
224 | BANKURA | SM/07307 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 01 No. Mouza (Maliara Part - II) of MALIARA (Zone - A) under Bankura - I,II & | TSM/006006 | 5343948 | Retrofitting | SVS | GO2021003239PH | 10/12/2020 | 84.49 | 0 | 84.49 | Bankura Division |  | 82.03 | 0 | 0 | 0 | 82.03 | 82.03 | 0 | 0 | 0 | 82.03 | 97.09 | 100
225 | BANKURA | SM/07308 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 02 Nos. Mouzas (Pinguri & Tentulpoha) of MALIARA (Zone - A) under Bankura - I, | TSM/006004 | 5343948 | Retrofitting | MVS | GO2021003242PH | 10/12/2020 | 85.15 | 0 | 85.15 | Bankura Division |  | 82.67 | 0 | 0 | 0 | 82.67 | 82.67 | 0 | 0 | 0 | 82.67 | 97.09 | 100
226 | BANKURA | SM/09304 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha , Napra, Bagulia) of MALIARA (Zone - A) under Bankur | TSM/006005 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 85.58 | 0 | 85.58 | Bankura Division |  | 83.08 | 0 | 0 | 0 | 83.08 | 81.12 | 0 | 0 | 0 | 81.12 | 94.79 | 90
227 | BANKURA | SM/07252 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jhunka, Shushunia parasibana, Paharbedia, Bharatpur, Kendua) | TSM/005970 | 5343948 | Retrofitting | MVS | GO2021003136PH | 08/12/2020 | 90.97 | 0 | 90.97 | Bankura Division |  | 88.32 | 0 | 0 | 0 | 88.32 | 88.32 | 0 | 0 | 0 | 88.32 | 97.09 | 90
228 | BANKURA | SM/09305 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | TSM/005972 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 95.96 | 0 | 95.96 | Bankura Division |  | 61.84 | 0 | 0 | 0 | 61.84 | 61.84 | 0 | 0 | 0 | 61.84 | 64.45 | 100
229 | BANKURA | SM/07254 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Kalipur, Housibad, Parulia, Biskodar, Joljolia Banshal) of K | TSM/005921 | 5343948 | Retrofitting | MVS | GO2021003121PH | 08/12/2020 | 74.43 | 0 | 74.43 | Bankura Division |  | 61.71 | 0 | 0 | 0 | 61.71 | 61.71 | 0 | 0 | 0 | 61.71 | 82.91 | 66
230 | BANKURA | SM/07310 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Jorhira, Sanpura, Arajuri, Kalipahari, Parasia) of JOR | TSM/006007 | 5343948 | Retrofitting | MVS | GO2021003243PH | 10/12/2020 | 90.97 | 0 | 90.97 | Bankura Division |  | 88.32 | 0 | 0 | 0 | 88.32 | 87.98 | 0 | 0 | 0 | 87.98 | 96.72 | 100
231 | BANKURA | SM/09306 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Kumirdoha, Gairabad, Fulberia, Dhaban, Bhabanipur, Upargara) | TSM/005974 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 97.18 | 0 | 97.18 | Bankura Division |  | 77.29 | 0 | 0 | 0 | 77.29 | 75.04 | 0 | 0 | 0 | 75.04 | 77.21 | 90
232 | BANKURA | SM/07340 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Hatasora, Susunia, Jirrakelai, Ethani, Sirpura, Sihika, Tulsa | TSM/005937 | 5343948 | Retrofitting | MVS | GO2021003342PH | 11/12/2020 | 88.31 | 0 | 88.31 | Bankura Division |  | 61.23 | 0 | 0 | 0 | 61.23 | 61.23 | 0 | 0 | 0 | 61.23 | 69.34 | 75
233 | BANKURA | SM/07341 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo | TSM/005938 | 5343948 | Retrofitting | MVS | GO2021003341PH | 11/12/2020 | 85.33 | 0 | 85.33 | Bankura Division |  | 82.51 | 0 | 0 | 0 | 82.51 | 82.51 | 0 | 0 | 0 | 82.51 | 96.7 | 96
234 | BANKURA | SM/07240 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyalda | TSM/005975 | 5343948 | Retrofitting | MVS | GO2021003141PH | 08/12/2020 | 83.76 | 0 | 83.76 | Bankura Division |  | 81.32 | 0 | 0 | 0 | 81.32 | 81.32 | 0 | 0 | 0 | 81.32 | 97.09 | 100
235 | BANKURA | SM/07241 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 08 Nos. Mouzas (Barsi, Malbedya, Narasinghapur, Arrah, Barabanagram, Khudra b | TSM/005980 | 5343948 | Retrofitting | MVS | GO2021003143PH | 08/12/2020 | 96.76 | 0 | 96.76 | Bankura Division |  | 92.03 | 0 | 0 | 0 | 92.03 | 92.03 | 0 | 0 | 0 | 92.03 | 95.11 | 100
236 | BANKURA | SM/07253 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Nangla, Agaya, Gidhuria, Pachasimul, Mechabaid, Banjurya, Har | TSM/005971 | 5343948 | Retrofitting | MVS | GO2021003138PH | 08/12/2020 | 90.95 | 0 | 90.95 | Bankura Division |  | 69.75 | 0 | 0 | 0 | 69.75 | 69.75 | 0 | 0 | 0 | 69.75 | 76.69 | 91
237 | BANKURA | SM/07239 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 Nos. Mouzas (Narasole, Radhaballavpur, Gopinathdihi, Taljhoria, Namabad, K | TSM/005973 | 5343948 | Retrofitting | MVS | GO2021003133PH | 08/12/2020 | 96.29 | 0 | 96.29 | Bankura Division |  | 93.48 | 0 | 0 | 0 | 93.48 | 93.48 | 0 | 0 | 0 | 93.48 | 97.09 | 100
238 | BANKURA | SM/07325 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Brindajam, Kaminbedia, Sihikapahari, Hatjore, Simulbedia, Moy | TSM/005958 | 5343948 | Retrofitting | MVS | GO2021003270PH | 10/12/2020 | 88.06 | 0 | 88.06 | Bankura Division |  | 76.94 | 0 | 0 | 0 | 76.94 | 76.94 | 0 | 0 | 0 | 76.94 | 87.37 | 100
239 | BANKURA | SM/07311 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 Nos. Mouzas (Rangametya, Kuladabar, Burat, Deulberia, Murgathol, Ampahari, | TSM/006008 | 5343948 | Retrofitting | MVS | GO2021003245PH | 10/12/2020 | 88.11 | 0 | 88.11 | Bankura Division |  | 85.2 | 0 | 0 | 0 | 85.2 | 85.2 | 0 | 0 | 0 | 85.2 | 96.69 | 100
240 | BANKURA | SM/07324 | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 Nos. Mouzas (Malpara, Harokabedy, Mangalda, Palsora, Kalai, Amdiha, Parasi | TSM/005956 | 5343948 | Retrofitting | MVS | GO2021003258PH | 10/12/2020 | 96.55 | 0 | 96.55 | Bankura Division |  | 70.14 | 0 | 0 | 0 | 70.14 | 70.14 | 0 | 0 | 0 | 70.14 | 72.64 | 100
241 | BANKURA | SM/09326 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Ajodhya (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Sancha - 6,Patalpur -8, Loharara - 9, Ajodhya -10 | TSM/007473 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 291.93 | 0 | 291.93 | Bankura Division |  | 168.44 | 0 | 0 | 0 | 168.44 | 168.44 | 0 | 0 | 0 | 168.44 | 57.7 | 52
242 | BANKURA | SM/09621 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | TSM/007402 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 211.82 | 0 | 211.82 | Bankura Division |  | 205.65 | 0 | 2.87 | 0 | 208.52 | 205.65 | 0 | 2.87 | 0 | 208.52 | 98.44 | 90
243 | BANKURA | SM/09622 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Jhiknara-119 & Kharsi-121, Narra-120, Ratra-1 | TSM/007403 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 193.98 | 0 | 193.98 | Bankura Division |  | 152.22 | 0 | 0 | 0 | 152.22 | 152.22 | 0 | 0 | 0 | 152.22 | 78.47 | 65
244 | BANKURA | SM/09628 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Gangabati-32, Maurui-33, Bhagabanbati-34, Nu | TSM/007469 | 5343948 | Retrofitting | MVS | GO2122005837PH | 24/11/2021 | 241.81 | 0 | 241.81 | Bankura Division |  | 169.21 | 0 | 0 | 0 | 169.21 | 169.21 | 0 | 0 | 0 | 169.21 | 69.97 | 70
245 | BANKURA | SM/09323 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Amrul Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Srikara-31, Padua-11, Adpara Kumrul-12, Srip | TSM/007470 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 206.18 | 0 | 206.18 | Bankura Division |  | 200.17 | 0 | 0 | 0 | 200.17 | 200.17 | 0 | 0 | 0 | 200.17 | 97.09 | 69
246 | BANKURA | SM/12839 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under Jal Jeevan Mission (JJM) for 04 nos, Kharigara (302), Dhonara (303), Chingragoalaso | TSM/010428 | 5343948 | Retrofitting | MVS | GO2223008091PH | 22/09/2022 | 115.16 | 0 | 115.16 | Bankura Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
247 | BANKURA | SM/06817 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mouzas (Junbedia) of HARIALGORA (Z | TSM/005738 | 5343948 | Retrofitting | SVS | GO2021001436PH | 23/09/2020 | 78.79 | 0 | 78.79 | Bankura Division |  | 78.79 | 0 | 0 | 0 | 78.79 | 78.79 | 0 | 0 | 0 | 78.79 | 100 | 100
248 | BANKURA | SM/11822 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I Project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos, Baramasia & Mukundapur (PIRRAGARI | TSM/010429 | 5343948 | Retrofitting | MVS | GO2223006293PH | 16/08/2022 | 33.27 | 0 | 33.27 | Bankura Division |  | 26.32 | 0 | 0 | 0 | 26.32 | 26.32 | 0 | 0 | 0 | 26.32 | 79.1 | 93
249 | BANKURA | SM/06812 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mouzas (Bhangaria, Magra and Sonad | TSM/005743 | 5343948 | Retrofitting | MVS | GO2021001428PH | 23/09/2020 | 60.55 | 0 | 60.55 | Bankura Division |  | 60.55 | 0 | 0 | 0 | 60.55 | 60.55 | 0 | 0 | 0 | 60.55 | 100 | 100
250 | BANKURA | SM/07246 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas ( Balia, Barabagan, Kasibed | TSM/005987 | 5343948 | Retrofitting | MVS | GO2021003144PH | 08/12/2020 | 96.56 | 0 | 96.56 | Bankura Division |  | 72.68 | 0 | 0 | 0 | 72.68 | 72.68 | 0 | 0 | 0 | 72.68 | 75.27 | 59
251 | BANKURA | SM/07249 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Anchuri, Dhulkumari, Patha | TSM/005990 | 5343948 | Retrofitting | MVS | GO2021003155PH | 08/12/2020 | 85.75 | 0 | 85.75 | Bankura Division |  | 44.68 | 0 | 0 | 0 | 44.68 | 44.68 | 0 | 0 | 0 | 44.68 | 52.1 | 51
252 | BANKURA | SM/07318 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Aralbasi, Bansi, Patakola | TSM/005983 | 5343948 | Retrofitting | MVS | GO2021003251PH | 10/12/2020 | 80.74 | 0 | 80.74 | Bankura Division |  | 69.14 | 0 | 0 | 0 | 69.14 | 69.11 | 0 | 0 | 0 | 69.11 | 85.6 | 100
253 | BANKURA | SM/07245 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dadhimukha, Jamboni,Jagdal | TSM/005986 | 5343948 | Retrofitting | MVS | GO2021003147PH | 08/12/2020 | 81.76 | 0 | 81.76 | Bankura Division |  | 79.37 | 0 | 0 | 0 | 79.37 | 79.37 | 0 | 0 | 0 | 79.37 | 97.09 | 100
254 | BANKURA | SM/07242 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mousas (Dhaldanga, Chak dhaldanga, | TSM/005982 | 5343948 | Retrofitting | MVS | GO2021003148PH | 08/12/2020 | 79.81 | 0 | 79.81 | Bankura Division |  | 68.17 | 0 | 0 | 0 | 68.17 | 68.17 | 0 | 0 | 0 | 68.17 | 85.43 | 100
255 | BANKURA | SM/06808 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos mouzas (Kanchanpur, Dhansimla, Pas | TSM/005736 | 5343948 | Retrofitting | MVS | GO2021001434PH | 23/09/2020 | 88 | 0 | 88 | Bankura Division |  | 86.73 | 0 | 0 | 0 | 86.73 | 86.73 | 0 | 0 | 0 | 86.73 | 98.56 | 100
256 | BANKURA | SM/07264 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas ( Patalkuri, Nandigram, Dam | TSM/005936 | 5343948 | Retrofitting | MVS | GO2021003142PH | 08/12/2020 | 83.94 | 0 | 83.94 | Bankura Division |  | 8.78 | 0 | 0 | 0 | 8.78 | 8.78 | 0 | 0 | 0 | 8.78 | 10.46 | 90
257 | BANKURA | SM/07316 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bamdhantur, Nabada, Sibara | TSM/005993 | 5343948 | Retrofitting | MVS | GO2021003263PH | 10/12/2020 | 99.71 | 0 | 99.71 | Bankura Division |  | 96.8 | 0 | 0 | 0 | 96.8 | 96.8 | 0 | 0 | 0 | 96.8 | 97.09 | 100
258 | BANKURA | SM/07237 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Kesekol, Domanbandhi, Kumu | TSM/005996 | 5343948 | Retrofitting | MVS | GO2021003152PH | 08/12/2020 | 75.94 | 0 | 75.94 | Bankura Division |  | 75.94 | 0 | 0 | 0 | 75.94 | 75.94 | 0 | 0 | 0 | 75.94 | 100 | 100
259 | BANKURA | SM/06807 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gaira, Arjunpur, Pairasol, | TSM/005735 | 5343948 | Retrofitting | MVS | GO2021001433PH | 23/09/2020 | 99.9 | 0 | 99.9 | Bankura Division |  | 99.9 | 0 | 0 | 0 | 99.9 | 99.9 | 0 | 0 | 0 | 99.9 | 100 | 100
260 | BANKURA | SM/06818 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Gourangadihi, Ledadihi, Ra | TSM/005740 | 5343948 | Retrofitting | MVS | GO2021001439PH | 23/09/2020 | 78.36 | 0 | 78.36 | Bankura Division |  | 76.08 | 0 | 0 | 0 | 76.08 | 76.08 | 0 | 0 | 0 | 76.08 | 97.09 | 100
261 | BANKURA | SM/06816 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mouzas (Kulpat, Kesia, Bhedua, Bad | TSM/005739 | 5343948 | Retrofitting | MVS | GO2021001438PH | 23/09/2020 | 80.94 | 0 | 80.94 | Bankura Division |  | 78.58 | 0 | 0 | 0 | 78.58 | 78.58 | 0 | 0 | 0 | 78.58 | 97.09 | 100
262 | BANKURA | SM/07344 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas ( Bhalukbasa, Hrtyasol, Kus | TSM/005967 | 5343948 | Retrofitting | MVS | GO2021003339PH | 11/12/2020 | 95.35 | 0 | 95.35 | Bankura Division |  | 46.94 | 0 | 0 | 0 | 46.94 | 46.94 | 0 | 0 | 0 | 46.94 | 49.23 | 100
263 | BANKURA | SM/07238 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Mouladanga, Mithila, Jagan | TSM/005995 | 5343948 | Retrofitting | MVS | GO2021003153PH | 08/12/2020 | 76.09 | 0 | 76.09 | Bankura Division |  | 74.38 | 0 | 0 | 0 | 74.38 | 74.38 | 0 | 0 | 0 | 74.38 | 97.75 | 100
264 | BANKURA | SM/09320 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | TSM/007466 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 146.29 | 0 | 146.29 | Bankura Division |  | 142.03 | 0 | 0 | 0 | 142.03 | 138.96 | 0 | 0 | 0 | 138.96 | 94.99 | 90
265 | BANKURA | SM/06802 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Akurbad, Banki, Matranga, | TSM/005732 | 5343948 | Retrofitting | MVS | GO2021001431PH | 23/09/2020 | 94.88 | 0 | 94.88 | Bankura Division |  | 92.44 | 0 | 0 | 0 | 92.44 | 92.44 | 0 | 0 | 0 | 92.44 | 97.43 | 100
266 | BANKURA | SM/06809 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Khejurbedia, Upardihi, Rad | TSM/005737 | 5343948 | Retrofitting | MVS | GO2021001435PH | 23/09/2020 | 99.97 | 0 | 99.97 | Bankura Division |  | 97.06 | 0 | 0 | 0 | 97.06 | 97.06 | 0 | 0 | 0 | 97.06 | 97.09 | 100
267 | BANKURA | SM/06803 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Mobarakpur, Chaptara, Send | TSM/005731 | 5343948 | Retrofitting | MVS | GO2021001429PH | 23/09/2020 | 94.04 | 0 | 94.04 | Bankura Division |  | 94.04 | 0 | 0 | 0 | 94.04 | 94.04 | 0 | 0 | 0 | 94.04 | 100 | 100
268 | BANKURA | SM/06805 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mouzas (Patna Joykrishnapur, Kunja | TSM/005734 | 5343948 | Retrofitting | MVS | GO2021001432PH | 23/09/2020 | 78.14 | 0 | 78.14 | Bankura Division |  | 78.14 | 0 | 0 | 0 | 78.14 | 78.14 | 0 | 0 | 0 | 78.14 | 100 | 100
269 | BANKURA | SM/06815 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kendboni, Kantaboni, Mamur | TSM/005742 | 5343948 | Retrofitting | MVS | GO2021001427PH | 23/09/2020 | 86.39 | 0 | 86.39 | Bankura Division |  | 83.88 | 0 | 0 | 0 | 83.88 | 83.84 | 0 | 0 | 0 | 83.84 | 97.04 | 100
270 | BANKURA | SM/06810 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Kulpat Bonkati, Gourangadi | TSM/005745 | 5343948 | Retrofitting | MVS | GO2021001444PH | 23/09/2020 | 90.12 | 0 | 90.12 | Bankura Division |  | 87.5 | 0 | 0 | 0 | 87.5 | 87.5 | 0 | 0 | 0 | 87.5 | 97.09 | 100
271 | BANKURA | SM/06806 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mouzas (Taldanga, Upar Narrah, Khe | TSM/005733 | 5343948 | Retrofitting | MVS | GO2021001430PH | 23/09/2020 | 78.26 | 0 | 78.26 | Bankura Division |  | 75.41 | 0 | 0 | 0 | 75.41 | 75.41 | 0 | 0 | 0 | 75.41 | 96.35 | 100
272 | BANKURA | SM/07244 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas ( Duldihi, Kamlagora, Kalap | TSM/005985 | 5343948 | Retrofitting | MVS | GO2021003145PH | 08/12/2020 | 77.31 | 0 | 77.31 | Bankura Division |  | 24.25 | 0 | 0 | 0 | 24.25 | 24.25 | 0 | 0 | 0 | 24.25 | 31.37 | 90
273 | BANKURA | SM/07247 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mousas (Dhaboagram, Tantkanali, Ni | TSM/005988 | 5343948 | Retrofitting | MVS | GO2021003146PH | 08/12/2020 | 85.75 | 0 | 85.75 | Bankura Division |  | 83.25 | 0 | 0 | 0 | 83.25 | 83.25 | 0 | 0 | 0 | 83.25 | 97.09 | 100
274 | BANKURA | SM/06813 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos mouzas (Bagapatal, Parasia bad, Ba | TSM/005744 | 5343948 | Retrofitting | MVS | GO2021001441PH | 23/09/2020 | 60.4 | 0 | 60.4 | Bankura Division |  | 58.64 | 0 | 0 | 0 | 58.64 | 58.64 | 0 | 0 | 0 | 58.64 | 97.09 | 100
275 | BANKURA | SM/07349 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas ( Bhagabanpur,Baindhka, Bha | TSM/005935 | 5343948 | Retrofitting | MVS | GO2021003338PH | 11/12/2020 | 95.93 | 0 | 95.93 | Bankura Division |  | 10.72 | 0 | 0 | 0 | 10.72 | 10.72 | 0 | 0 | 0 | 10.72 | 11.18 | 31
276 | BANKURA | SM/07326 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam | TSM/005959 | 5343948 | Retrofitting | MVS | GO2021003271PH | 10/12/2020 | 72.12 | 0 | 72.12 | Bankura Division |  | 70.02 | 0 | 0 | 0 | 70.02 | 70.02 | 0 | 0 | 0 | 70.02 | 97.09 | 100
277 | BANKURA | SM/07343 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Chhendua, Chamkara, Fengab | TSM/005963 | 5343948 | Retrofitting | MVS | GO2021003340PH | 11/12/2020 | 99.07 | 0 | 99.07 | Bankura Division |  | 96.18 | 0 | 0 | 0 | 96.18 | 96.17 | 0 | 0 | 0 | 96.17 | 97.07 | 100
278 | BANKURA | SM/07347 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Dhobagram, Chila bakra, Na | TSM/005933 | 5343948 | Retrofitting | MVS | GO2021003335PH | 11/12/2020 | 93.49 | 0 | 93.49 | Bankura Division |  | 79.81 | 0 | 0 | 0 | 79.81 | 79.81 | 0 | 0 | 0 | 79.81 | 85.37 | 100
279 | BANKURA | SM/07315 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Patradanga, Brindabanpur, | TSM/005994 | 5343948 | Retrofitting | MVS | GO2021003267PH | 10/12/2020 | 98.56 | 0 | 98.56 | Bankura Division |  | 96.63 | 0 | 0 | 0 | 96.63 | 96.63 | 0 | 0 | 0 | 96.63 | 98.05 | 100
280 | BANKURA | SM/06814 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Karanjora, Lapuria, Dulal | TSM/005741 | 5343948 | Retrofitting | MVS | GO2021001440PH | 23/09/2020 | 86.25 | 0 | 86.25 | Bankura Division |  | 83.74 | 0 | 0 | 0 | 83.74 | 83.74 | 0 | 0 | 0 | 83.74 | 97.09 | 100
281 | BANKURA | SM/06804 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mouzas (Nabagram, Vidyadharpur, Ai | TSM/005730 | 5343948 | Retrofitting | MVS | GO2021001451PH | 23/09/2020 | 92.61 | 0 | 92.61 | Bankura Division |  | 92.61 | 0 | 0 | 0 | 92.61 | 92.61 | 0 | 0 | 0 | 92.61 | 99.99 | 100
282 | BANKURA | SM/07329 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas ( Baraleddya, Dhagoria, Ban | TSM/005969 | 5343948 | Retrofitting | MVS | GO2021003256PH | 10/12/2020 | 96.08 | 0 | 96.08 | Bankura Division |  | 61.96 | 0 | 0 | 0 | 61.96 | 61.96 | 0 | 0 | 0 | 61.96 | 64.49 | 100
283 | BANKURA | SM/07250 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos mousas (Kapista, Domnageria, Darpa | TSM/005991 | 5343948 | Retrofitting | MVS | GO2021003154PH | 08/12/2020 | 88.19 | 0 | 88.19 | Bankura Division |  | 85.63 | 0 | 0 | 0 | 85.63 | 85.63 | 0 | 0 | 0 | 85.63 | 97.09 | 100
284 | BANKURA | SM/06811 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria | TSM/005746 | 5343948 | Retrofitting | MVS | GO2021001425PH | 23/09/2020 | 90.1 | 0 | 90.1 | Bankura Division |  | 73.15 | 0 | 0 | 0 | 73.15 | 73.15 | 0 | 0 | 0 | 73.15 | 81.19 | 100
285 | BANKURA | SM/07348 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos mousas (Helna, Fagua kanali, Dumur | TSM/005934 | 5343948 | Retrofitting | MVS | GO2021003337PH | 11/12/2020 | 93.87 | 0 | 93.87 | Bankura Division |  | 58.16 | 0 | 0 | 0 | 58.16 | 58.16 | 0 | 0 | 0 | 58.16 | 61.96 | 100
286 | BANKURA | SM/09240 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Abantika- 88 , Belthya- 89 & Deuli- 91) of BENDA u | TSM/007416 | 5343948 | Retrofitting | MVS | GO2122000772PH | 25/05/2021 | 73.17 | 0 | 73.17 | Bankura Division |  | 43.68 | 0 | 1.11 | 0 | 44.79 | 43.68 | 0 | 1.11 | 0 | 44.79 | 61.22 | 50
287 | BANKURA | SM/09239 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54 | TSM/007415 | 5343948 | Retrofitting | MVS | GO2122000774PH | 25/05/2021 | 76.06 | 0 | 76.06 | Bankura Division |  | 26.19 | 0 | 4.53 | 0 | 30.72 | 26.19 | 0 | 4.53 | 0 | 30.72 | 40.38 | 50
288 | BANKURA | SM/09631 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, | TSM/007408 | 5343948 | Retrofitting | MVS | GO2122005838PH | 24/11/2021 | 427.7 | 0 | 427.7 | Bankura Division |  | 275.8 | 0 | 0 | 0 | 275.8 | 265.99 | 0 | 0 | 0 | 265.99 | 62.19 | 65
289 | BANKURA | SM/09331 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Bamania-113) of Betanal (Zone - B) under In | TSM/007423 | 5343948 | Retrofitting | SVS | GO2122005027PH | 08/11/2021 | 92.06 | 0 | 92.06 | Bankura Division |  | 40 | 0 | 0 | 0 | 40 | 39.78 | 0 | 0 | 0 | 39.78 | 43.22 | 50
290 | BANKURA | SM/09332 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Kenjera-129, Chattrakhanda-130 & Nagatentu | TSM/007426 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 85.14 | 0 | 85.14 | Bankura Division |  | 46.71 | 0 | 0 | 0 | 46.71 | 41.71 | 0 | 0 | 0 | 41.71 | 49 | 50
291 | BANKURA | SM/08294 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Mamudpur-124, Barabaikunthapur-125, Habish | TSM/007424 | 5343948 | Retrofitting | MVS | GO2021007624PH | 26/02/2021 | 80.95 | 0 | 80.95 | Bankura Division |  | 42.21 | 0 | 0 | 0 | 42.21 | 42.21 | 0 | 0 | 0 | 42.21 | 52.15 | 52
292 | BANKURA | SM/09636 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 no. mouza (Majuria-135) of CHAKUPARSOLE (Zone - A) | TSM/007409 | 5343948 | Retrofitting | SVS | GO2122005834PH | 24/11/2021 | 86.9 | 0 | 86.9 | Bankura Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
293 | BANKURA | SM/09638 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Baramara-149 & Kulaijuri-134) of CHAK | TSM/007412 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 78.32 | 0 | 78.32 | Bankura Division |  | 60.62 | 0 | 0 | 0 | 60.62 | 60.62 | 0 | 0 | 0 | 60.62 | 77.4 | 50
294 | BANKURA | SM/09619 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | TSM/007411 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 73.06 | 0 | 73.06 | Bankura Division |  | 70.93 | 0 | 0 | 0 | 70.93 | 70.93 | 0 | 0 | 0 | 70.93 | 97.09 | 56
295 | BANKURA | SM/09637 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Dhabani-136, Chitrang-137, Baliguma-1 | TSM/007410 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 86.89 | 0 | 86.89 | Bankura Division |  | 84.36 | 0 | 0 | 0 | 84.36 | 84.36 | 0 | 0 | 0 | 84.36 | 97.09 | 50
296 | BANKURA | SM/09321 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Layak Bandh - 13 & Chua Masina - 17) of | TSM/007468 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 210.06 | 0 | 210.06 | Bankura Division |  | 203.94 | 0 | 0 | 0 | 203.94 | 203.41 | 0 | 0 | 0 | 203.41 | 96.83 | 53
297 | BANKURA | SM/09624 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, | TSM/007467 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 139.57 | 0 | 139.57 | Bankura Division |  | 61.78 | 0 | 5.56 | 0 | 67.34 | 61.78 | 0 | 5.56 | 0 | 67.34 | 48.25 | 55
298 | BANKURA | SM/08290 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | TSM/007417 | 5343948 | Retrofitting | MVS | GO2021007631PH | 26/02/2021 | 78.52 | 0 | 78.52 | Bankura Division |  | 76.23 | 0 | 0 | 0 | 76.23 | 76.23 | 0 | 0 | 0 | 76.23 | 97.09 | 59
299 | BANKURA | SM/08291 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Tentulara-20, Saluka-21, Dharampur-22, | TSM/007418 | 5343948 | Retrofitting | MVS | GO2021007629PH | 26/02/2021 | 78.23 | 0 | 78.23 | Bankura Division |  | 58.35 | 0 | 0 | 0 | 58.35 | 58.35 | 0 | 0 | 0 | 58.35 | 74.59 | 50
300 | BANKURA | SM/09308 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Nangalbhanga-18, Chwak Chuamosina-19, B | TSM/007419 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 67.34 | 0 | 67.34 | Bankura Division |  | 55.84 | 0 | 0 | 0 | 55.84 | 55.43 | 0 | 0 | 0 | 55.43 | 82.31 | 51
301 | BANKURA | SM/09644 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | TSM/007413 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 92.7 | 0 | 92.7 | Bankura Division |  | 65.01 | 0 | 0 | 0 | 65.01 | 64.99 | 0 | 0 | 0 | 64.99 | 70.11 | 65
302 | BANKURA | SM/09238 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Khuliamuri-126, Harabati-127, Dhengasole-128, | TSM/007414 | 5343948 | Retrofitting | MVS | GO2122000755PH | 25/05/2021 | 80.74 | 0 | 80.74 | Bankura Division |  | 66.05 | 0 | 0 | 0 | 66.05 | 66.05 | 0 | 0 | 0 | 66.05 | 81.81 | 60
303 | BANKURA | SM/09627 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | TSM/007407 | 5343948 | Retrofitting | MVS | GO2122005837PH | 24/11/2021 | 280.67 | 0 | 280.67 | Bankura Division |  | 103.55 | 0 | 14.27 | 0 | 117.82 | 103.55 | 0 | 14.27 | 0 | 117.82 | 41.98 | 54
304 | BANKURA | SM/09623 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Sanpura-57, Jagaldwip-58, Dasarathbati-61 | TSM/007404 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 190.01 | 0 | 190.01 | Bankura Division |  | 184.48 | 0 | 0 | 0 | 184.48 | 184.48 | 0 | 0 | 0 | 184.48 | 97.09 | 81
305 | BANKURA | SM/09625 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | TSM/007405 | 5343948 | Retrofitting | MVS | GO2122005837PH | 24/11/2021 | 184.53 | 0 | 184.53 | Bankura Division |  | 163.1 | 0 | 16.05 | 0 | 179.15 | 163.1 | 0 | 16.05 | 0 | 179.15 | 97.09 | 95
306 | BANKURA | SM/09626 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | TSM/007406 | 5343948 | Retrofitting | MVS | GO2122005837PH | 24/11/2021 | 202.38 | 0 | 202.38 | Bankura Division |  | 196.49 | 0 | 5.89 | 0 | 202.38 | 196.49 | 0 | 5.89 | 0 | 202.38 | 100 | 93
307 | BANKURA | SM/08293 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | TSM/007421 | 5343948 | Retrofitting | MVS | GO2021007627PH | 26/02/2021 | 73.3 | 0 | 73.3 | Bankura Division |  | 71.17 | 0 | 0 | 0 | 71.17 | 70 | 0 | 0 | 0 | 70 | 95.5 | 65
308 | BANKURA | SM/08292 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Mathurabihari-28, Ramchandrapur-30, Matukp | TSM/007420 | 5343948 | Retrofitting | MVS | GO2021007628PH | 26/02/2021 | 70.88 | 0 | 70.88 | Bankura Division |  | 64.06 | 0 | 0 | 0 | 64.06 | 63.72 | 0 | 0 | 0 | 63.72 | 89.9 | 80
309 | BANKURA | SM/08297 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | TSM/007427 | 5343948 | Retrofitting | MVS | GO2021007625PH | 26/02/2021 | 84.54 | 0 | 84.54 | Bankura Division |  | 82.07 | 0 | 0 | 0 | 82.07 | 82.07 | 0 | 0 | 0 | 82.07 | 97.09 | 51
310 | BANKURA | SM/08298 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Du | TSM/007428 | 5343948 | Retrofitting | MVS | GO2021007623PH | 26/02/2021 | 75.69 | 0 | 75.69 | Bankura Division |  | 52.4 | 0 | 1.08 | 0 | 53.48 | 52.4 | 0 | 1.08 | 0 | 53.48 | 70.65 | 50
311 | BANKURA | SM/09318 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Birasimul-70, Shakrul-71, Suripuskarini-72 & D | TSM/007429 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 99.95 | 0 | 99.95 | Bankura Division |  | 79.13 | 0 | 0 | 0 | 79.13 | 79.07 | 0 | 0 | 0 | 79.07 | 79.1 | 80
312 | BANKURA | SM/08299 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | TSM/007430 | 5343948 | Retrofitting | MVS | GO2021007626PH | 26/02/2021 | 87.68 | 0 | 87.68 | Bankura Division |  | 85.12 | 0 | 0 | 0 | 85.12 | 85.12 | 0 | 0 | 0 | 85.12 | 97.09 | 72
313 | BANKURA | SM/09324 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Shashpur-75, Narayanpur-82, Thakuranidighi | TSM/007471 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 187.99 | 0 | 187.99 | Bankura Division |  | 158.97 | 0 | 13.92 | 0 | 172.89 | 158.97 | 0 | 13.92 | 0 | 172.89 | 91.97 | 75
314 | BANKURA | SM/09325 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Banki-85, Chotogobindapur-86, Adilpur-87 & | TSM/007472 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 226.6 | 0 | 226.6 | Bankura Division |  | 205.48 | 0 | 14.51 | 0 | 220 | 205.48 | 0 | 14.51 | 0 | 220 | 97.09 | 68
315 | BANKURA | SM/10041 | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Somsar (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos Mouza Bhagabatipur - 01, Palashdanga - 03, Kumna - 04 of | TSM/009450 | 40002257 | Retrofitting | MVS | GO2122008429PH | 19/01/2022 | 83.4 | 0 | 83.4 | Bankura Division |  | 20.92 | 0 | 0 | 0 | 20.92 | 20.92 | 0 | 0 | 0 | 20.92 | 25.09 | 45
316 | BANKURA | SM/07319 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Mantumra, Kamalpur, Patjuri Agaya)of Chinabari (Zone- H) under | TSM/005940 | 5343948 | Retrofitting | MVS | GO2021003254PH | 10/12/2020 | 77.62 | 0 | 77.62 | Bankura Division |  | 75.35 | 0 | 0 | 0 | 75.35 | 75.35 | 0 | 0 | 0 | 75.35 | 97.09 | 50
317 | BANKURA | SM/07320 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahara, Rangametia, Chhatapathor, Kunkhri Basa) of Chinabari (Z | TSM/005941 | 5343948 | Retrofitting | MVS | GO2021003253PH | 10/12/2020 | 77.52 | 0 | 77.52 | Bankura Division |  | 53.16 | 0 | 0 | 0 | 53.16 | 53.16 | 0 | 0 | 0 | 53.16 | 68.57 | 100
318 | BANKURA | SM/07322 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Subarda, Simla, Shalchura, Bank simul, Nekrakuada) of Chinabari | TSM/005944 | 5343948 | Retrofitting | MVS | GO2021003252PH | 10/12/2020 | 78.19 | 0 | 78.19 | Bankura Division |  | 75.91 | 0 | 0 | 0 | 75.91 | 75.91 | 0 | 0 | 0 | 75.91 | 97.09 | 100
319 | BANKURA | SM/07321 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Bahirdya, Fulkusma, Jambede, Nabagram)of Nabagram (Zon - K) unde | TSM/005942 | 5343948 | Retrofitting | MVS | GO2021003269PH | 10/12/2020 | 97.45 | 0 | 97.45 | Bankura Division |  | 45 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 45 | 46.18 | 100
320 | BANKURA | SM/09311 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 nos. Mouzas (Kastara, Rangamati, Kendana, Sat-deuli) of pipe water supply sc | TSM/007479 | 4696991 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 55.5 | 0 | 55.5 | Bankura Division |  | 53.88 | 0 | 0 | 0 | 53.88 | 53.88 | 0 | 0 | 0 | 53.88 | 97.09 | 90
321 | BANKURA | SM/07323 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 04 Nos. Mouzas (Nabanda, Karkai, Haridi, Kantapahari) of Nabagram, (Zone- K) und | TSM/005954 | 5343948 | Retrofitting | MVS | GO2021003255PH | 10/12/2020 | 89.87 | 0 | 89.87 | Bankura Division |  | 69.76 | 0 | 0 | 0 | 69.76 | 69.76 | 0 | 0 | 0 | 69.76 | 77.62 | 100
322 | BANKURA | SM/07342 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 Nos. Mouzas (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala) of Nabagr | TSM/005939 | 5343948 | Retrofitting | MVS | GO2021003334PH | 11/12/2020 | 98.67 | 0 | 98.67 | Bankura Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
323 | BANKURA | SM/09630 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | TSM/007465 | 5343948 | Retrofitting | MVS | GO2122005838PH | 24/11/2021 | 184.06 | 0 | 184.06 | Bankura Division |  | 94.67 | 0 | 0 | 0 | 94.67 | 94.67 | 0 | 0 | 0 | 94.67 | 51.44 | 90
324 | BANKURA | SM/09314 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | TSM/007481 | 40027420 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 143.98 | 25.3 | 169.28 | Bankura Division |  | 127.44 | 0 | 0 | 0 | 127.44 | 116.23 | 0 | 0 | 0 | 116.23 | 68.66 | 79
325 | BANKURA | SM/09629 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | TSM/007464 | 5343948 | Retrofitting | MVS | GO2122005838PH | 24/11/2021 | 159.63 | 0 | 159.63 | Bankura Division |  | 130.51 | 0 | 0 | 0 | 130.51 | 130.51 | 0 | 0 | 0 | 130.51 | 81.75 | 90
326 | BANKURA | SM/09319 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | TSM/007463 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 254.76 | 0 | 254.76 | Bankura Division |  | 175.3 | 0 | 0 | 0 | 175.3 | 175.3 | 0 | 0 | 0 | 175.3 | 68.81 | 90
327 | BANKURA | SM/09316 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | TSM/007459 | 4696991 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 272.68 | 0 | 272.68 | Bankura Division |  | 264.73 | 0 | 0 | 0 | 264.73 | 264.73 | 0 | 0 | 0 | 264.73 | 97.09 | 90
328 | BANKURA | SM/07765 | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1)under S | TSM/005955 | 5343948 | Retrofitting | MVS | GO2021004407PH | 11/01/2021 | 1524.36 | 0 | 1524.36 | Bankura Division |  | 1395.56 | 0 | 0 | 0 | 1395.56 | 1395.42 | 0 | 0 | 0 | 1395.42 | 91.54 | 96
329 | BANKURA | SM/09310 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Ekteswar (Part, 70%) & Sankarhati) of pipe water supply scheme for E | TSM/007478 | 40042529 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 32.92 | 0 | 32.92 | Bankura Division |  | 31.96 | 0 | 0 | 0 | 31.96 | 31.54 | 0 | 0 | 0 | 31.54 | 95.8 | 90
330 | BANKURA | SM/09309 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply s | TSM/007477 | 40023343 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 30.33 | 5.87 | 36.21 | Bankura Division |  | 35.14 | 0 | 0 | 0 | 35.14 | 35.14 | 0 | 0 | 0 | 35.14 | 97.05 | 75
331 | BANKURA | SM/09315 | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | TSM/007482 | 40017094 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 230.75 | 0 | 230.75 | Bankura Division |  | 224.03 | 0 | 2.75 | 0 | 226.77 | 224.03 | 0 | 2.75 | 0 | 226.77 | 98.28 | 90
332 | BANKURA | SM/07367 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Arjunda (65), Tirsulia (66), Barkania (69), Dhairapara (70), Jamdahara (71), Tilabani (72), Dhanga Dungri (74), Mirgi (75), Basudebpur (79), Jhat Pukhuria (80) & Patasimul (1 | TSM/005916 | 5343948 | Retrofitting | MVS | GO2021003351PH | 11/12/2020 | 99.39 | 0 | 99.39 | Bankura Division |  | 96.49 | 0 | 0 | 0 | 96.49 | 146.48 | 0 | 0 | 0 | 146.48 | 147.38 | 100
333 | BANKURA | SM/07269 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bara Gajra (103), Asberya (104), Kaliahuta (105), Jadurbankata (106), Nischintapur (107), Kankata (127), Dharra Muli (128) & Bagaldhara (129) mouzas by retrofitting Zone-F (M | TSM/005906 | 5343948 | Retrofitting | MVS | GO2021003128PH | 08/12/2020 | 89.36 | 0 | 89.36 | Bankura Division |  | 25.9 | 0 | 0 | 0 | 25.9 | 25.9 | 0 | 0 | 0 | 25.9 | 28.98 | 100
334 | BANKURA | SM/09503 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baradi Kalapathar (15), Baradi (16), Dalambhija (17), Balguma (18), Chuagara (19), Bhangadeuli (20), Shushunia (21), Maukura (22), Belatikri (23), Guniada (24), Panchur (25), | TSM/008410 | 5343948 | Retrofitting | MVS | GO2122005581PH | 19/11/2021 | 239.83 | 0 | 239.83 | Bankura Division |  | 116.6 | 0 | 0 | 0 | 116.6 | 116.38 | 0 | 0 | 0 | 116.38 | 48.53 | 90
335 | BANKURA | SM/09534 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma | TSM/008648 | 5343948 | Retrofitting | MVS | GO2122005573PH | 19/11/2021 | 197.45 | 0 | 197.45 | Bankura Division |  | 115.73 | 0 | 14.41 | 0 | 130.13 | 115.73 | 0 | 14.41 | 0 | 130.13 | 65.91 | 90
336 | BANKURA | SM/07362 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Batikara (12), Nanda (15), Kadia (17), Pakhuria (18), Khayer Kundi (19), Aralbara (20) & Damodarpur (21) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Raniban | TSM/005905 | 5343948 | Retrofitting | MVS | GO2021003332PH | 11/12/2020 | 77.85 | 0 | 77.85 | Bankura Division |  | 75.59 | 0 | 0 | 0 | 75.59 | 75.59 | 0 | 0 | 0 | 75.59 | 97.09 | 100
337 | BANKURA | SM/09522 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (2 | TSM/008588 | 5343948 | Retrofitting | MVS | GO2122005576PH | 19/11/2021 | 101.77 | 0 | 101.77 | Bankura Division |  | 36.52 | 0 | 6.45 | 0 | 42.97 | 36.52 | 0 | 6.45 | 0 | 42.97 | 42.23 | 38
338 | BANKURA | SM/09230 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368), Deuli (369) & Majura (372) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF | TSM/007300 | 5343948 | Retrofitting | MVS | GO2122000780PH | 25/05/2021 | 89 | 0 | 89 | Bankura Division |  | 76.31 | 0 | 0 | 0 | 76.31 | 76.31 | 0 | 0 | 0 | 76.31 | 85.74 | 78
339 | BANKURA | SM/07360 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurul Pahari (238), Sindurpeti (239), Baurisol (240), Tiring (244), Parashi Danga (247), Khayerbani (248) & Bagakhulia (249) mouzas by retrofitting Z | TSM/005899 | 5343948 | Retrofitting | MVS | GO2021003314PH | 11/12/2020 | 99.9 | 0 | 99.9 | Bankura Division |  | 96.99 | 0 | 0 | 0 | 96.99 | 96.99 | 0 | 0 | 0 | 96.99 | 97.09 | 98
340 | BANKURA | SM/09535 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza | TSM/008654 | 5343948 | Retrofitting | MVS | GO2122005573PH | 19/11/2021 | 152.7 | 0 | 152.7 | Bankura Division |  | 43.7 | 0 | 1.24 | 0 | 44.94 | 43.7 | 0 | 1.24 | 0 | 44.94 | 29.43 | 18
341 | BANKURA | SM/09551 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benjtabani (51), Benrebati (52), Tilbari (53), Sarasbakra (55), Pukhuria (56), Birsingpur (57), Bikrampur (58), Krishnapur (59), Kathjuria (60), Nuniabad (61), Harintuli (62) | TSM/008983 | 5343948 | Retrofitting | MVS | GO2122005593PH | 19/11/2021 | 264.94 | 0 | 264.94 | Bankura Division |  | 93.9 | 0 | 12.97 | 0 | 106.88 | 93.9 | 0 | 12.97 | 0 | 106.88 | 40.34 | 70
342 | BANKURA | SM/09480 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhanga Bandh (91), Bheduasol (92), Kamalpur (93), Sayer Bankra (99), Kotalpur (100), Ramnagar (101), Dhabani (102), Manipur (105), Guinandi (106), Itapanchira (107), Paharpur | TSM/008575 | 5343948 | Retrofitting | MVS | GO2122005577PH | 19/11/2021 | 207.69 | 0 | 207.69 | Bankura Division |  | 135.87 | 0 | 4.06 | 0 | 139.93 | 135.87 | 0 | 4.06 | 0 | 139.93 | 67.37 | 82
343 | BANKURA | SM/07354 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pita Dungri (275) & Kuchiar Mahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | TSM/005893 | 5343948 | Retrofitting | MVS | GO2021003355PH | 11/12/2020 | 67.76 | 0 | 67.76 | Bankura Division |  | 65.79 | 0 | 0 | 0 | 65.79 | 65.79 | 0 | 0 | 0 | 65.79 | 97.09 | 100
344 | BANKURA | SM/09552 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | TSM/008984 | 5343948 | Retrofitting | MVS | GO2122005593PH | 19/11/2021 | 161.82 | 0 | 161.82 | Bankura Division |  | 108.26 | 0 | 0 | 0 | 108.26 | 108.26 | 0 | 0 | 0 | 108.26 | 66.9 | 100
345 | BANKURA | SM/07336 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Biradihi (39), Diktor (40) & Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Banku | TSM/005918 | 5343948 | Retrofitting | MVS | GO2021003250PH | 10/12/2020 | 63.54 | 0 | 63.54 | Bankura Division |  | 61.69 | 0 | 0 | 0 | 61.69 | 61.69 | 0 | 0 | 0 | 61.69 | 97.09 | 100
346 | BANKURA | SM/09478 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | TSM/008452 | 5343948 | Retrofitting | SVS | GO2122005577PH | 19/11/2021 | 212.48 | 0 | 212.48 | Bankura Division |  | 40.63 | 0 | 165.66 | 0 | 206.29 | 40.63 | 0 | 165.66 | 0 | 206.29 | 97.09 | 57
347 | BANKURA | SM/07335 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chakadoba (73), Balarampur (138), Kubasol (139), Ban Pukhuria (140), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas | TSM/005917 | 5343948 | Retrofitting | MVS | GO2021003247PH | 10/12/2020 | 99.02 | 0 | 99.02 | Bankura Division |  | 96.13 | 0 | 0 | 0 | 96.13 | 139.11 | 0 | 0 | 0 | 139.11 | 140.49 | 100
348 | BANKURA | SM/09549 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | TSM/008981 | 5343948 | Retrofitting | MVS | GO2122005593PH | 19/11/2021 | 286.81 | 0 | 286.81 | Bankura Division |  | 167.57 | 0 | 0 | 0 | 167.57 | 167.57 | 0 | 0 | 0 | 167.57 | 58.43 | 52
349 | BANKURA | SM/07356 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dahala (250) & Bahadurpur (251) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under | TSM/005895 | 5343948 | Retrofitting | MVS | GO2021003360PH | 11/12/2020 | 64.72 | 0 | 64.72 | Bankura Division |  | 54.05 | 0 | 0 | 0 | 54.05 | 54.05 | 0 | 0 | 0 | 54.05 | 83.52 | 98
350 | BANKURA | SM/09524 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Su | TSM/008619 | 5343948 | Retrofitting | MVS | GO2122005576PH | 19/11/2021 | 142.09 | 0 | 142.09 | Bankura Division |  | 25.35 | 0 | 10.84 | 0 | 36.18 | 25.35 | 0 | 10.84 | 0 | 36.18 | 25.46 | 36
351 | BANKURA | SM/09530 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarbati (228), Jamdoba (229), Singar Garia (232), Baruipara (236), Sundarpur (237), Teliberia (238), Puncha (239), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by | TSM/008626 | 5343948 | Retrofitting | MVS | GO2122005575PH | 19/11/2021 | 251.99 | 0 | 251.99 | Bankura Division |  | 164.23 | 0 | 17.29 | 0 | 181.52 | 164.23 | 0 | 17.29 | 0 | 181.52 | 72.03 | 90
352 | BANKURA | SM/07359 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Damodarpur (122), Simla (123), Arkama (124), Rangi Bari (125), Hazamdihi (233) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Su | TSM/005898 | 5343948 | Retrofitting | MVS | GO2021003361PH | 11/12/2020 | 99.99 | 0 | 99.99 | Bankura Division |  | 97.08 | 0 | 0 | 0 | 97.08 | 97.08 | 0 | 0 | 0 | 97.08 | 97.09 | 100
353 | BANKURA | SM/09642 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dangarpara (293), Jamrepara (295), Debgram (296), Agaya (350), Ampata (351) & Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjo | TSM/007290 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 84.2 | 0 | 84.2 | Bankura Division |  | 49.07 | 0 | 0 | 0 | 49.07 | 48.88 | 0 | 0 | 0 | 48.88 | 58.05 | 100
354 | BANKURA | SM/07363 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhajamanipur (87), Topabari (88), Kaliapathar (89), Shyampur (90), Baharamuri (91), Jibanpur (92) & Uparhir (99) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-R | TSM/005912 | 5343948 | Retrofitting | MVS | GO2021003354PH | 11/12/2020 | 97.85 | 0 | 97.85 | Bankura Division |  | 74.97 | 0 | 0 | 0 | 74.97 | 74.92 | 0 | 0 | 0 | 74.92 | 76.57 | 100
355 | BANKURA | SM/09236 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Doldere (147), Bankata (148), Arjjunia (149), Kayma (150), Rosana (151), Mukundapur (152), Jaleswar (153), Lakshmanpur (154), Mathurakata (155), Jambedia (179), Baricha (180) | TSM/007319 | 5343948 | Retrofitting | MVS | GO2122000777PH | 25/05/2021 | 271.55 | 0 | 271.55 | Bankura Division |  | 263.64 | 0 | 0 | 0 | 263.64 | 261.86 | 0 | 0 | 0 | 261.86 | 96.43 | 100
356 | BANKURA | SM/06791 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dulaparar (231), Asarda (232), Chandpara (233), Luapara (269), Kemduadangri (273), Benasuli (275), Phulberia (278), Danara (279) mouzas by retrofitting of Piped Water Supply | TSM/005749 | 8129955 | Retrofitting | MVS | GO2021001426PH | 23/09/2020 | 85.04 | 0 | 85.04 | Bankura Division |  | 76.25 | 0 | 0 | 0 | 76.25 | 76.25 | 0 | 0 | 0 | 76.25 | 89.66 | 100
357 | BANKURA | SM/09523 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retr | TSM/008597 | 5343948 | Retrofitting | MVS | GO2122005576PH | 19/11/2021 | 137.57 | 0 | 137.57 | Bankura Division |  | 41.6 | 0 | 8.76 | 0 | 50.36 | 41.6 | 0 | 8.76 | 0 | 50.36 | 36.61 | 68
358 | BANKURA | SM/09234 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S | TSM/007315 | 5343948 | Retrofitting | MVS | GO2122000402PH | 25/05/2021 | 82.8 | 0 | 82.8 | Bankura Division |  | 76.31 | 0 | 0 | 0 | 76.31 | 76.31 | 0 | 0 | 0 | 76.31 | 92.16 | 100
359 | BANKURA | SM/09528 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gamidya (192), Amla Tara (196), Angaria (197), Madan Mohanpur (198), Kheruashol (199), Betajora (200), Bhaluk Khulya (201), Brindabanpur (202), Shirsha (203), Siara (204), Ku | TSM/008621 | 5343948 | Retrofitting | MVS | GO2122005575PH | 19/11/2021 | 148.3 | 0 | 148.3 | Bankura Division |  | 62.98 | 0 | 10.24 | 0 | 73.22 | 62.98 | 0 | 10.24 | 0 | 73.22 | 49.37 | 90
360 | BANKURA | SM/07364 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (6 | TSM/005913 | 5343948 | Retrofitting | MVS | GO2021003352PH | 11/12/2020 | 69.9 | 0 | 69.9 | Bankura Division |  | 67.86 | 0 | 0 | 0 | 67.86 | 67.86 | 0 | 0 | 0 | 67.86 | 97.09 | 100
361 | BANKURA | SM/06794 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gotkanali (45), Bankhola (54), Jarisa (89) & Harinyaguri (90) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | TSM/005757 | 8130042 | Retrofitting | MVS | GO2021001449PH | 23/09/2020 | 86.48 | 0 | 86.48 | Bankura Division |  | 28.99 | 0 | 0 | 0 | 28.99 | 28.83 | 0 | 0 | 0 | 28.83 | 33.34 | 100
362 | BANKURA | SM/07266 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Guniada (1), Chalka (2), Chatanibaid (3), Bangopalpur (4) & Harirampur (6) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph | TSM/005902 | 5343948 | Retrofitting | MVS | GO2021003132PH | 08/12/2020 | 71.22 | 0 | 71.22 | Bankura Division |  | 35.73 | 0 | 0 | 0 | 35.73 | 35.73 | 0 | 0 | 0 | 35.73 | 50.17 | 98
363 | BANKURA | SM/09500 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | TSM/008196 | 5343948 | Retrofitting | MVS | GO2122005581PH | 19/11/2021 | 297.84 | 0 | 297.84 | Bankura Division |  | 261.53 | 0 | 0 | 0 | 261.53 | 259.7 | 0 | 0 | 0 | 259.7 | 87.19 | 100
364 | BANKURA | SM/09635 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gurighati (25), Penruabaid (26) & Parsola (28) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme ( | TSM/007282 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 69.48 | 0 | 69.48 | Bankura Division |  | 67.46 | 0 | 0 | 0 | 67.46 | 67.46 | 0 | 0 | 0 | 67.46 | 97.09 | 100
365 | BANKURA | SM/09476 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Handulia (1), Metyaldoba (2), Lakhyatapal (3), Budhadhara (4), Kharkhari (6), Kharjuria (7), Peripathar (8) & Ramgar (33) mouzas by retrofitting of Water Supply Scheme for Pa | TSM/008191 | 5343948 | Retrofitting | MVS | GO2122005583PH | 19/11/2021 | 56.84 | 0 | 56.84 | Bankura Division |  | 37.2 | 0 | 0 | 0 | 37.2 | 37.2 | 0 | 0 | 0 | 37.2 | 65.45 | 100
366 | BANKURA | SM/09531 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting | TSM/008629 | 5343948 | Retrofitting | MVS | GO2122005575PH | 19/11/2021 | 170.99 | 0 | 170.99 | Bankura Division |  | 98.44 | 0 | 12.42 | 0 | 110.87 | 98.44 | 0 | 12.42 | 0 | 110.87 | 64.84 | 90
367 | BANKURA | SM/07365 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Itamara (60), Jambeda (64), Gobarda (152), Deulagara (153), Domohani (154) & Khandarani (155) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supp | TSM/005914 | 5343948 | Retrofitting | MVS | GO2021003353PH | 11/12/2020 | 65.48 | 0 | 65.48 | Bankura Division |  | 63.57 | 0 | 0 | 0 | 63.57 | 63.57 | 0 | 0 | 0 | 63.57 | 97.09 | 100
368 | BANKURA | SM/09481 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jaba Balarampur (68), Bagjata (78), Debagram (79), Baidyanathpur (80), Mankhamar (81), Bhatgram (82), Banamalipur (83), Mukundabati (84), Lodna (89) & Madanpur (90) mouzas by | TSM/008576 | 5343948 | Retrofitting | MVS | GO2122005577PH | 19/11/2021 | 164.78 | 0 | 164.78 | Bankura Division |  | 120.54 | 0 | 11 | 0 | 131.54 | 120.54 | 0 | 11 | 0 | 131.54 | 79.83 | 100
369 | BANKURA | SM/07357 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh W | TSM/005896 | 5343948 | Retrofitting | MVS | GO2021003359PH | 11/12/2020 | 88.45 | 0 | 88.45 | Bankura Division |  | 76.89 | 0 | 0 | 0 | 76.89 | 76.89 | 0 | 0 | 0 | 76.89 | 86.94 | 85
370 | BANKURA | SM/06795 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamda (38), Tilabani (39), Jhikri (40), Kusumkanali (41) , Baurisol (42) and Maidhara (46) mouzas by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its | TSM/005758 | 8130050 | Retrofitting | MVS | GO2021001450PH | 23/09/2020 | 88.07 | 0 | 88.07 | Bankura Division |  | 85.5 | 0 | 0 | 0 | 85.5 | 80.88 | 0 | 0 | 0 | 80.88 | 91.84 | 100
371 | BANKURA | SM/09232 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B a | TSM/007311 | 5343948 | Retrofitting | MVS | GO2122000783PH | 25/05/2021 | 82.52 | 0 | 82.52 | Bankura Division |  | 75.27 | 0 | 0 | 0 | 75.27 | 75.27 | 0 | 0 | 0 | 75.27 | 91.21 | 100
372 | BANKURA | SM/09554 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jhumka (156) Nutangram (157), Ghaghrakhulia (169), Ekaria Jambani (170), Krishnabati (171), Chandpur (172), Putiadaha (173), Pithabakra (174), Bagnada (175) & Nekratapal (176 | TSM/008989 | 5343948 | Retrofitting | MVS | GO2122005590PH | 19/11/2021 | 112.59 | 0 | 112.59 | Bankura Division |  | 68.17 | 0 | 0 | 0 | 68.17 | 68.17 | 0 | 0 | 0 | 68.17 | 60.54 | 70
373 | BANKURA | SM/09643 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | TSM/007294 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 79.61 | 0 | 79.61 | Bankura Division |  | 58.63 | 0 | 0 | 0 | 58.63 | 58.63 | 0 | 0 | 0 | 58.63 | 73.64 | 100
374 | BANKURA | SM/09640 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kadamara (9), Pukhuria (10), Baranimdiha (13), Rengurbandh (14) & Rajabandh (15) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas un | TSM/007286 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 90.02 | 0 | 90.02 | Bankura Division |  | 87.4 | 0 | 0 | 0 | 87.4 | 87.4 | 0 | 0 | 0 | 87.4 | 97.09 | 100
375 | BANKURA | SM/09498 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | TSM/008195 | 5343948 | Retrofitting | MVS | GO2122005582PH | 19/11/2021 | 247.99 | 0 | 247.99 | Bankura Division |  | 92.15 | 0 | 16.1 | 0 | 108.25 | 92.15 | 0 | 16.1 | 0 | 108.25 | 43.65 | 90
376 | BANKURA | SM/09533 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | TSM/008636 | 5343948 | Retrofitting | MVS | GO2122005573PH | 19/11/2021 | 198.8 | 0 | 198.8 | Bankura Division |  | 23.93 | 0 | 13.98 | 0 | 37.92 | 23.93 | 0 | 13.98 | 0 | 37.92 | 19.07 | 20
377 | BANKURA | SM/07361 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kasipur (230), Indkucha (231), Dhanara (234), Nekra Sonda (246), Sabudad (253), Dumuria (254), Dhargram (255), Sial Pahari (256) & Dhabani (257) mouzas by retrofitting Zone-H | TSM/005900 | 5343948 | Retrofitting | MVS | GO2021003364PH | 11/12/2020 | 99.88 | 0 | 99.88 | Bankura Division |  | 35.03 | 0 | 0 | 0 | 35.03 | 35.03 | 0 | 0 | 0 | 35.03 | 35.07 | 100
378 | BANKURA | SM/09231 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjo | TSM/007306 | 5343948 | Retrofitting | MVS | GO2122000779PH | 25/05/2021 | 99.3 | 0 | 99.3 | Bankura Division |  | 71.91 | 0 | 0 | 0 | 71.91 | 71.91 | 0 | 0 | 0 | 71.91 | 72.42 | 80
379 | BANKURA | SM/09550 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | TSM/008976 | 5343948 | Retrofitting | MVS | GO2122005593PH | 19/11/2021 | 234.05 | 0 | 234.05 | Bankura Division |  | 183.91 | 0 | 0 | 0 | 183.91 | 183.91 | 0 | 0 | 0 | 183.91 | 78.58 | 55
380 | BANKURA | SM/09475 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kharika (27), Khapmayna (29), Mayna (30), Bankata (31) & Kumarsol (49) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlap | TSM/008190 | 5343948 | Retrofitting | MVS | GO2122005583PH | 19/11/2021 | 57.03 | 0 | 57.03 | Bankura Division |  | 42.98 | 0 | 0 | 0 | 42.98 | 42.98 | 0 | 0 | 0 | 42.98 | 75.37 | 100
381 | BANKURA | SM/06799 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kotalsol (108), Chiltore (109), Jhola (110), Dhepua (111), Chaknara (112), Deuli (113), Narayanpur (114) & Dharmapur (133) mouzas by retrofitting of Piped Water Supply Scheme | TSM/005747 | 8130008 | Retrofitting | MVS | GO2021001445PH | 23/09/2020 | 91.99 | 0 | 91.99 | Bankura Division |  | 78.13 | 0 | 0 | 0 | 78.13 | 78.13 | 0 | 0 | 0 | 78.13 | 84.93 | 100
382 | BANKURA | SM/06797 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kukrajuri (270), Madhupur (271), Saltora (272), Babaida (274), Jadabpur (276), Nahilya (277), Gopalpur (301), Raghunathpur (303), Sahajpur (341) and salbani (342) mouzas by r | TSM/005751 | 8129944 | Retrofitting | MVS | GO2021001424PH | 23/09/2020 | 62 | 15.86 | 77.86 | Bankura Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
383 | BANKURA | SM/07337 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kundurka (43), Paira (44), Simlabandh (45), Bhedua (46) & Lutia (47) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at | TSM/005919 | 5343948 | Retrofitting | MVS | GO2021003246PH | 10/12/2020 | 56.54 | 0 | 56.54 | Bankura Division |  | 54.9 | 0 | 0 | 0 | 54.9 | 54.87 | 0 | 0 | 0 | 54.87 | 97.04 | 100
384 | BANKURA | SM/07338 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lachaipur (9), Fetapur (10), Gopalpur (11), Tilabad (13) & Jharia Kucha (14) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF | TSM/005920 | 5343948 | Retrofitting | MVS | GO2021003248PH | 10/12/2020 | 89.1 | 0 | 89.1 | Bankura Division |  | 63.73 | 0 | 0 | 0 | 63.73 | 113.73 | 0 | 0 | 0 | 113.73 | 127.65 | 100
385 | BANKURA | SM/09553 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | TSM/008985 | 5343948 | Retrofitting | MVS | GO2122005590PH | 19/11/2021 | 279 | 0 | 279 | Bankura Division |  | 123.92 | 0 | 11.42 | 0 | 135.34 | 123.92 | 0 | 11.42 | 0 | 135.34 | 48.51 | 75
386 | BANKURA | SM/06796 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | TSM/005754 | 8130034 | Retrofitting | SVS | GO2021001448PH | 23/09/2020 | 66.43 | 33.51 | 99.94 | Bankura Division |  | 99.94 | 0 | 0 | 0 | 99.94 | 99.94 | 0 | 0 | 0 | 99.94 | 100 | 100
387 | BANKURA | SM/09227 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | TSM/007280 | 5343948 | Retrofitting | MVS | GO2122000645PH | 25/05/2021 | 51.96 | 0 | 51.96 | Bankura Division |  | 50.44 | 0 | 0 | 0 | 50.44 | 48.32 | 0 | 0 | 0 | 48.32 | 93 | 100
388 | BANKURA | SM/07355 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (252), Labda Para (265), Birkham (266), Jharia (267), Dakai (268), Karra (269), Kapila (270) & Hetiasol (271) mouzas by retrofitting Zone-IIB (Hetiasol) of Khatra-H | TSM/005894 | 5343948 | Retrofitting | MVS | GO2021003357PH | 11/12/2020 | 61.82 | 0 | 61.82 | Bankura Division |  | 60.02 | 0 | 0 | 0 | 60.02 | 60.02 | 0 | 0 | 0 | 60.02 | 97.09 | 100
389 | BANKURA | SM/07334 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis | TSM/005911 | 5343948 | Retrofitting | MVS | GO2021003261PH | 10/12/2020 | 99.12 | 0 | 99.12 | Bankura Division |  | 96.24 | 0 | 0 | 0 | 96.24 | 96.24 | 0 | 0 | 0 | 96.24 | 97.09 | 100
390 | BANKURA | SM/09639 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | TSM/007284 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 74.39 | 0 | 74.39 | Bankura Division |  | 72.23 | 0 | 0 | 0 | 72.23 | 72.23 | 0 | 0 | 0 | 72.23 | 97.09 | 90
391 | BANKURA | SM/09529 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mandiha (175), Mouleswar (176), Medinipur (177), Datina (178), Krishna Nagar (179), Kalla (180), Shima Baid (181), Gogra (184), Prajabad (185), Kushte (186), Jamra Madhabpur | TSM/008624 | 5343948 | Retrofitting | MVS | GO2122005575PH | 19/11/2021 | 228.15 | 0 | 228.15 | Bankura Division |  | 106.56 | 0 | 23.42 | 0 | 129.98 | 106.56 | 0 | 23.42 | 0 | 129.98 | 56.97 | 85
392 | BANKURA | SM/09620 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | TSM/007320 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 75.16 | 0 | 75.16 | Bankura Division |  | 70.24 | 0 | 0 | 0 | 70.24 | 70.24 | 0 | 0 | 0 | 70.24 | 93.46 | 100
393 | BANKURA | SM/09641 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | TSM/007288 | 5343948 | Retrofitting | MVS | GO2122005834PH | 24/11/2021 | 237.71 | 0 | 237.71 | Bankura Division |  | 161.49 | 0 | 5.09 | 0 | 166.58 | 161.49 | 0 | 5.09 | 0 | 166.58 | 70.08 | 100
394 | BANKURA | SM/09237 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | TSM/007322 | 5343948 | Retrofitting | MVS | GO2122000784PH | 25/05/2021 | 299.8 | 0 | 299.8 | Bankura Division |  | 165.84 | 0 | 5.1 | 0 | 170.95 | 165.84 | 0 | 5.1 | 0 | 170.95 | 57.02 | 100
395 | BANKURA | SM/09228 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | TSM/007289 | 5343948 | Retrofitting | MVS | GO2122000781PH | 25/05/2021 | 255.23 | 0 | 255.23 | Bankura Division |  | 161.67 | 0 | 5.07 | 0 | 166.74 | 161.67 | 0 | 5.07 | 0 | 166.74 | 65.33 | 100
396 | BANKURA | SM/11823 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | TSM/011376 | 40034377 | Retrofitting | MVS | GO2223006293PH | 16/08/2022 | 513.85 | 0 | 513.85 | Bankura Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
397 | BANKURA | SM/09477 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Dhemushunya (Zone-IV) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | TSM/008192 | 5343948 | Retrofitting | MVS | GO2122005583PH | 19/11/2021 | 197.45 | 0 | 197.45 | Bankura Division |  | 110.55 | 0 | 0 | 0 | 110.55 | 109.28 | 0 | 0 | 0 | 109.28 | 55.34 | 80
398 | BANKURA | SM/16940 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | TSM/015536 | 40061271 | Retrofitting | MVS | GO2223016495PH | 16/03/2023 | 659.22 | 0 | 659.22 | Bankura Division |  | 184.5 | 0 | 27.58 | 0 | 212.08 | 184.5 | 0 | 27.58 | 0 | 212.08 | 32.17 | 75
399 | BANKURA | SM/14491 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | TSM/015535 | 40035881 | Retrofitting | MVS | GO2223012342PH | 20/01/2023 | 483.88 | 0 | 483.88 | Bankura Division |  | 85.35 | 0 | 23.21 | 0 | 108.56 | 85.35 | 0 | 23.21 | 0 | 108.56 | 22.44 | 30
400 | BANKURA | SM/09496 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | TSM/008193 | 5343948 | Retrofitting | MVS | GO2122005582PH | 19/11/2021 | 234.6 | 0 | 234.6 | Bankura Division |  | 167.89 | 0 | 0 | 0 | 167.89 | 167.89 | 0 | 0 | 0 | 167.89 | 71.57 | 100
401 | BANKURA | SM/09497 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | TSM/008194 | 5343948 | Retrofitting | MVS | GO2122005582PH | 19/11/2021 | 272.39 | 0 | 272.39 | Bankura Division |  | 171.75 | 0 | 0 | 0 | 171.75 | 171.75 | 0 | 0 | 0 | 171.75 | 63.05 | 100
402 | BANKURA | SM/14126 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Water supply scheme for Left out Mouzas of Raipur Block under Jal Swapna & Jal Jeevan Mission Programme. | TSM/011369 | 40034334 | Retrofitting | MVS | GO2223011513PH | 02/01/2023 | 551.14 | 0 | 551.14 | Bankura Division |  | 83.81 | 0 | 0 | 0 | 83.81 | 83.81 | 0 | 0 | 0 | 83.81 | 15.21 | 45
403 | BANKURA | SM/07766 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | TSM/005901 | 5343948 | Retrofitting | MVS | GO2021004408PH | 11/01/2021 | 1310.43 | 0 | 1310.43 | Bankura Division |  | 1200.02 | 0 | 87.84 | 0 | 1287.86 | 1199.83 | 0 | 87.84 | 0 | 1287.67 | 98.26 | 82
404 | BANKURA | SM/07333 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Nipania (32), Ranga (35), Ashatara (36), Nowadihi (37), Jibanpur (38) & Rangametia (41) mouzas by retrofitting Zone-CE (Ashatara) of Khatra-Hirbandh-Ranibandh Water Supply Sc | TSM/005910 | 5343948 | Retrofitting | MVS | GO2021003260PH | 10/12/2020 | 61.29 | 0 | 61.29 | Bankura Division |  | 42.75 | 0 | 0 | 0 | 42.75 | 42.75 | 0 | 0 | 0 | 42.75 | 69.75 | 100
405 | BANKURA | SM/09536 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | TSM/008656 | 5343948 | Retrofitting | MVS | GO2122005573PH | 19/11/2021 | 34.65 | 0 | 34.65 | Bankura Division |  | 16.56 | 0 | 2.67 | 0 | 19.23 | 13.12 | 0 | 2.67 | 0 | 15.79 | 45.57 | 90
406 | BANKURA | SM/07332 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Paharapatpur (117), Bhaluka (120), Kadra (121), Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Raniban | TSM/005909 | 5343948 | Retrofitting | MVS | GO2021003259PH | 10/12/2020 | 86.55 | 0 | 86.55 | Bankura Division |  | 67.56 | 0 | 0 | 0 | 67.56 | 67.56 | 0 | 0 | 0 | 67.56 | 78.05 | 100
407 | BANKURA | SM/07353 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Parkul (217), Mashara (218), Goala Danga (219), Chandanpur (261), Benia Baid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh | TSM/005891 | 5343948 | Retrofitting | MVS | GO2021003358PH | 11/12/2020 | 66.76 | 0 | 66.76 | Bankura Division |  | 59.29 | 0 | 0 | 0 | 59.29 | 42.54 | 0 | 0 | 0 | 42.54 | 63.72 | 100
408 | BANKURA | SM/09521 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina | TSM/008583 | 5343948 | Retrofitting | MVS | GO2122005576PH | 19/11/2021 | 135.75 | 0 | 135.75 | Bankura Division |  | 34.3 | 0 | 9.3 | 0 | 43.6 | 34.3 | 0 | 9.3 | 0 | 43.6 | 32.12 | 55
409 | BANKURA | SM/07265 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patpur (214), Maharadihi (215), Dharampur (216), Bara Gari (220), Data Rampur (221), Pitha Baid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Bara | TSM/005892 | 5343948 | Retrofitting | MVS | GO2021003123PH | 08/12/2020 | 75.82 | 0 | 75.82 | Bankura Division |  | 73.61 | 0 | 0 | 0 | 73.61 | 72.7 | 0 | 0 | 0 | 72.7 | 95.89 | 100
410 | BANKURA | SM/06798 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Penchakola (298), Dubli (299), Kharkasuli (300), Marosol (302), Katalda (343), Baherbani (344) and Thakurabada (360) mouzas by retrofitting Piped Water Supply Scheme for Dhan | TSM/005750 | 8130029 | Retrofitting | MVS | GO2021001447PH | 23/09/2020 | 63.56 | 27.97 | 91.53 | Bankura Division |  | 73.38 | 0 | 0 | 0 | 73.38 | 73.38 | 0 | 0 | 0 | 73.38 | 80.17 | 100
411 | BANKURA | SM/06792 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas | TSM/005755 | 8130065 | Retrofitting | MVS | GO2021001453PH | 23/09/2020 | 74.89 | 0 | 74.89 | Bankura Division |  | 51.31 | 0 | 0 | 0 | 51.31 | 25.22 | 0 | 0 | 0 | 25.22 | 33.68 | 100
412 | BANKURA | SM/07358 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (108), Shyam Bazar (109), Ban Bedia (111), Baidyanathpur (118) & Jasara (119) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme | TSM/005897 | 5343948 | Retrofitting | MVS | GO2021003363PH | 11/12/2020 | 79.04 | 0 | 79.04 | Bankura Division |  | 74.32 | 0 | 0 | 0 | 74.32 | 73.76 | 0 | 0 | 0 | 73.76 | 93.31 | 100
413 | BANKURA | SM/09532 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Mandar Bani (38), Pitambarpur (39), Benachapra (40) mouzas by retrofitting Ratanpur and adjo | TSM/008634 | 5343948 | Retrofitting | MVS | GO2122005575PH | 19/11/2021 | 177.6 | 0 | 177.6 | Bankura Division |  | 98.8 | 0 | 12.81 | 0 | 111.61 | 98.8 | 0 | 12.81 | 0 | 111.61 | 62.84 | 90
414 | BANKURA | SM/09520 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rautara (41), Kawabasa (42), Panbaraj (43), Kiabati (44), Bhulanpur (45), Palash Bani (46), Gengari (47), Pratappur (48), Gopalpur (49), Dhabani (50), Metyala (51), Jamjuri ( | TSM/008582 | 5343948 | Retrofitting | MVS | GO2122005576PH | 19/11/2021 | 266.81 | 0 | 266.81 | Bankura Division |  | 229.03 | 0 | 18.51 | 0 | 247.54 | 229.03 | 0 | 18.51 | 0 | 247.54 | 92.78 | 75
415 | BANKURA | SM/09618 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and | TSM/007303 | 5343948 | Retrofitting | MVS | GO2122005836PH | 24/11/2021 | 99.94 | 0 | 99.94 | Bankura Division |  | 87.36 | 0 | 0 | 0 | 87.36 | 87.36 | 0 | 0 | 0 | 87.36 | 87.41 | 92
416 | BANKURA | SM/07268 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Salapahari (5), Elora (7), Dhanarangi (8) & Bansol (16) mouzas by retrofitting Zone-D (Lachiapur) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirba | TSM/005904 | 5343948 | Retrofitting | MVS | GO2021003127PH | 08/12/2020 | 77.68 | 0 | 77.68 | Bankura Division |  | 73.58 | 0 | 0 | 0 | 73.58 | 73.58 | 0 | 0 | 0 | 73.58 | 94.72 | 100
417 | BANKURA | SM/09233 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | TSM/007313 | 5343948 | Retrofitting | MVS | GO2122000785PH | 25/05/2021 | 99.93 | 0 | 99.93 | Bankura Division |  | 60.3 | 0 | 0 | 0 | 60.3 | 60.3 | 0 | 0 | 0 | 60.3 | 60.34 | 93
418 | BANKURA | SM/07270 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shyamnagar (22), Aral Chhota (28), Naria (29), Benagaria (30), Hirakhon (31), Brahma Danga (33), Mahal Danga (34), Simul Kundi (77) & Chanpasol (78) mouzas by retrofitting Zo | TSM/005908 | 5343948 | Retrofitting | MVS | GO2021003125PH | 08/12/2020 | 100 | 0 | 100 | Bankura Division |  | 89.61 | 0 | 0 | 0 | 89.61 | 82.25 | 0 | 0 | 0 | 82.25 | 82.25 | 100
419 | BANKURA | SM/06793 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sinyajora (32), Bhelaidiha (36), Korkhi (37) , Shyampur (44), Jugidangra (47), Rasikpur (48) and Sarenga (50) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for L | TSM/005756 | 8129932 | Retrofitting | MVS | GO2021001420PH | 23/09/2020 | 67.66 | 0 | 67.66 | Bankura Division |  | 45.48 | 0 | 0 | 0 | 45.48 | 45.48 | 0 | 0 | 0 | 45.48 | 67.23 | 100
420 | BANKURA | SM/09479 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | TSM/008569 | 5343948 | Retrofitting | MVS | GO2122005577PH | 19/11/2021 | 181.27 | 0 | 181.27 | Bankura Division |  | 127.77 | 0 | 12.47 | 0 | 140.24 | 127.77 | 0 | 12.47 | 0 | 140.24 | 77.36 | 90
421 | BANKURA | SM/09229 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | TSM/007297 | 5343948 | Retrofitting | MVS | GO2122000778PH | 25/05/2021 | 89.49 | 0 | 89.49 | Bankura Division |  | 64.84 | 0 | 0 | 0 | 64.84 | 64.43 | 0 | 0 | 0 | 64.43 | 72 | 100
422 | BANKURA | SM/07267 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Talgaria (93), Itamara (94), Uganpathar (95), Benagaria (96), Pathardihi (97), Jambedya (98), Bhubandihi (100), Maiti Bandh (101), Dias Dihi (102), Mirgi Pahari (130), Rangam | TSM/005903 | 5343948 | Retrofitting | MVS | GO2021003130PH | 08/12/2020 | 96.51 | 0 | 96.51 | Bankura Division |  | 93.7 | 0 | 0 | 0 | 93.7 | 93.7 | 0 | 0 | 0 | 93.7 | 97.09 | 100
423 | BANKURA | SM/09235 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by | TSM/007317 | 5343948 | Retrofitting | MVS | GO2122000782PH | 25/05/2021 | 79.85 | 0 | 79.85 | Bankura Division |  | 62.57 | 0 | 0 | 0 | 62.57 | 62.57 | 0 | 0 | 0 | 62.57 | 78.36 | 100
424 | BANKURA | SM/07331 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tentulia (27), Bhelai Diha (81), Jagatpur (82), Husum Danga (83), Bhogra (84), Dighi (85) & Debidia (86) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Wa | TSM/005907 | 5343948 | Retrofitting | MVS | GO2021003258PH | 10/12/2020 | 99.99 | 0 | 99.99 | Bankura Division |  | 97.08 | 0 | 0 | 0 | 97.08 | 97.08 | 0 | 0 | 0 | 97.08 | 97.09 | 100
425 | BANKURA | SM/07366 | Construction and commissioning of FHTC (Functional House Hold Tap Connection) Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (1 | TSM/005915 | 5343948 | Retrofitting | MVS | GO2021003350PH | 11/12/2020 | 79.75 | 0 | 79.75 | Bankura Division |  | 57.04 | 0 | 0 | 0 | 57.04 | 56.93 | 0 | 0 | 0 | 56.93 | 71.39 | 100
426 | BANKURA | SM/06790 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Dhabani (195), Chhota Amjur (196), Kuchalghati (197), Sitalpur (198), Phulberia (199), Makalrangi (200), Danarkini (208), Kumarpur (209), Bansi (225), Nimdangra (226), Chhota | TSM/005752 | 8130063 | Retrofitting | MVS | GO2021001452PH | 23/09/2020 | 86.99 | 0 | 86.99 | Bankura Division |  | 64.66 | 0 | 0 | 0 | 64.66 | 64.66 | 0 | 0 | 0 | 64.66 | 74.34 | 100
427 | BANKURA | SM/06801 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Katgara (134), Basudebpur (135), Bbagjanta (136) and Sidi (137) mouzas by retrofitting of Piped Water Supply Scheme for Chiltore & Its Adjoining Mouzas | TSM/005748 | 8130022 | Retrofitting | MVS | GO2021001446PH | 23/09/2020 | 48.55 | 0 | 48.55 | Bankura Division |  | 46.92 | 0 | 0 | 0 | 46.92 | 46.92 | 0 | 0 | 0 | 46.92 | 96.64 | 100
428 | BANKURA | SM/06800 | Construction and commissioning of FHTC (Functional Household Tap Connection) in Kayerpara (206), Harinarayanpur (207), Murku (210) and Ganganala (230) mouzas by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas | TSM/005753 | 8129934 | Retrofitting | MVS | GO2021001421PH | 23/09/2020 | 60.74 | 0 | 60.74 | Bankura Division |  | 54.16 | 0 | 0 | 0 | 54.16 | 54.16 | 0 | 0 | 0 | 54.16 | 89.15 | 100
429 | BANKURA | SM/09504 | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | TSM/008411 | 5343948 | Retrofitting | SVS | GO2122005581PH | 19/11/2021 | 80.23 | 0 | 80.23 | Bankura Division |  | 71.21 | 0 | 0 | 0 | 71.21 | 71.21 | 0 | 0 | 0 | 71.21 | 88.75 | 58
430 | BANKURA | SM/09502 | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | TSM/008409 | 5343948 | Retrofitting | MVS | GO2122005581PH | 19/11/2021 | 198.36 | 0 | 198.36 | Bankura Division |  | 191.11 | 0 | 0 | 0 | 191.11 | 191.11 | 0 | 0 | 0 | 191.11 | 96.35 | 90
431 | BANKURA | SM/10296 | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | TSM/008344 | 5343948 | Augmentation | SVS | GO2122010204PH | 28/02/2022 | 2502.19 | 0 | 2502.19 | Bankura Division | Bankura Mechanical Division | 308.24 | 0 | 1021.19 | 0 | 1329.43 | 308.24 | 0 | 1021.19 | 0 | 1329.43 | 53.13 | 58
432 | BANKURA | SM/14523 | Danga Makarandapur Piped Water Supply Scheme | TSM/014201 | 40034921 | New | MVS | GO2223012616PH | 30/01/2023 | 1049.88 | 149.6 | 1199.48 | Bankura Division | Bankura Mechanical Division | 277.47 | 6.43 | 109.03 | 0 | 392.93 | 277.47 | 6.43 | 63.63 | 0 | 347.53 | 28.97 | 49
433 | BANKURA | SM/18302 | Danna Piped Water Supply Scheme. | TSM/015928 | 40037815 | New | MVS | 1663/PHE-28011/274/2022-SCHM CELL-Dept. of PHE | 26/06/2023 | 1127.14 | 178.15 | 1305.29 | Bankura Division | Bankura Mechanical Division | 91.84 | 28.78 | 251.82 | 0 | 372.43 | 0 | 28.78 | 210.75 | 0 | 239.53 | 18.35 | 28
434 | BANKURA | SM/14246 | Deshra Piped Water Supply Scheme | TSM/014824 | 40041880 | New | MVS | GO2223011828PH | 16/01/2023 | 1421.7 | 170.12 | 1591.82 | Bankura Division | Bankura Mechanical Division | 58.47 | 0 | 67.45 | 0 | 125.92 | 58.47 | 0 | 44.9 | 0 | 103.37 | 6.49 | 3
435 | BANKURA | SM/15023 | Dhagaria Piped Water Supply Scheme | TSM/015425 | 40043875 | New | MVS | GO2223013093PH | 04/02/2023 | 787.72 | 120.28 | 908 | Bankura Division | Bankura Mechanical Division | 43.95 | 46.23 | 17.26 | 0 | 107.44 | 0 | 27.72 | 17.26 | 0 | 44.98 | 4.95 | 34
436 | BANKURA | SM/16706 | Dhan Simla Piped Water Supply Scheme. | TSM/018459 | 40065462 | New | SVS | GO2223016006PH | 14/03/2023 | 158.96 | 72.25 | 231.21 | Bankura Division | Bankura Mechanical Division | 11.63 | 39.12 | 0 | 0 | 50.75 | 11.63 | 30.52 | 0 | 0 | 42.15 | 18.23 | 69
437 | BANKURA | SM/14176 | Dhula Danga Piped Water Supply Scheme | TSM/014770 | 40041733 | New | MVS | GO2223011646PH | 09/01/2023 | 1037.66 | 125.54 | 1163.2 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 21.35 | 0 | 21.35 | 0 | 0 | 0 | 0 | 0 | 0 | 4
438 | BANKURA | SM/17224 | Dwarika Pipe Water Supply Scheme | TSM/018289 | 40059906 | New | MVS | GO2223016130PH | 15/03/2023 | 650.79 | 82.78 | 733.57 | Bankura Division | Bankura Mechanical Division | 105.44 | 8.76 | 0 | 0 | 114.2 | 105.44 | 0 | 0 | 0 | 105.44 | 14.37 | 28
439 | BANKURA | SM/12426 | Ghagara Piped Water Supply Scheme | TSM/014207 | 40035594 | New | MVS | GO2223007571PH | 13/09/2022 | 379.52 | 78.02 | 457.53 | Bankura Division | Bankura Mechanical Division | 91.74 | 14.38 | 4.05 | 0 | 110.17 | 70.63 | 14.38 | 0 | 0 | 85.01 | 18.58 | 14
440 | BANKURA | SM/18611 | Ghora Danga Piped Water Supply Scheme | TSM/018446 | 40061511 | New | MVS | 2157/PHE-28011/214/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 965.03 | 120.28 | 1085.31 | Bankura Division | Bankura Mechanical Division | 19.1 | 0 | 126.94 | 0 | 146.04 | 0 | 0 | 126.94 | 0 | 126.94 | 11.7 | 13
441 | BANKURA | SM/14001 | Goala Danga Piped Water Supply Scheme. | TSM/015440 | 40035954 | New | MVS | GO2223010525PH | 05/12/2022 | 394.12 | 84.76 | 478.88 | Bankura Division | Bankura Mechanical Division | 93.36 | 13.41 | 0 | 0 | 106.77 | 93.36 | 0 | 0 | 0 | 93.36 | 19.49 | 38
442 | BANKURA | SM/16698 | Gopalpur Piped Water Supply Scheme. | TSM/018122 | 40061471 | New | MVS | GO2223016016PH | 14/03/2023 | 838.57 | 107.36 | 945.93 | Bankura Division | Bankura Mechanical Division | 198.15 | 18.44 | 80.01 | 0 | 296.6 | 198.15 | 4.11 | 80.01 | 0 | 282.27 | 29.84 | 31
443 | BANKURA | SM/11923 | Ground water based Diga pipe water supply scheme, under Bankura Division, Block -Onda, Dist - Bankura. | TSM/011392 | 40034906 | New | MVS | GO2223006608PH | 22/08/2022 | 458.83 | 82.29 | 541.12 | Bankura Division | Bankura Mechanical Division | 10.48 | 15.1 | 6.86 | 0 | 32.45 | 10.48 | 0 | 3.43 | 0 | 13.91 | 2.57 | 14
444 | BANKURA | SM/16696 | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | TSM/013114 | 40061448 | New | MVS | GO2223016008PH | 14/03/2023 | 538.88 | 82.78 | 621.66 | Bankura Division | Bankura Mechanical Division | 5.22 | 13.7 | 10.42 | 0 | 29.34 | 5.22 | 0 | 5.21 | 0 | 10.43 | 1.68 | 7
445 | BANKURA | SM/16694 | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. | TSM/013109 | 40061417 | New | MVS | GO2223016021PH | 14/03/2023 | 287.45 | 82.78 | 370.23 | Bankura Division | Bankura Mechanical Division | 24.58 | 22.49 | 2.56 | 0 | 49.63 | 24.58 | 18.15 | 2.56 | 0 | 45.29 | 12.23 | 18
446 | BANKURA | SM/16697 | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | TSM/013115 | 40061453 | New | MVS | GO2223016020PH | 14/03/2023 | 515.8 | 82.78 | 598.58 | Bankura Division | Bankura Mechanical Division | 4.25 | 15.54 | 9.13 | 0 | 28.92 | 4.25 | 15.54 | 4.56 | 0 | 24.36 | 4.07 | 8
447 | BANKURA | SM/16695 | Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | TSM/013112 | 40061427 | New | MVS | GO2223016018PH | 14/03/2023 | 113.23 | 82.78 | 196.01 | Bankura Division | Bankura Mechanical Division | 1.43 | 16.2 | 1.14 | 0 | 18.77 | 1.43 | 16.2 | 1.14 | 0 | 18.77 | 9.58 | 22
448 | BANKURA | SM/12422 | Harinashuli Piped Water Supply Scheme | TSM/014205 | 40035102 | New | MVS | GO2223007550PH | 13/09/2022 | 832.85 | 113.98 | 946.83 | Bankura Division | Bankura Mechanical Division | 202.2 | 8.24 | 130.5 | 0 | 340.94 | 202.2 | 8.24 | 130.5 | 0 | 340.94 | 36.01 | 36
449 | BANKURA | SM/12425 | Hetia Piped Water Supply Scheme | TSM/014202 | 40034929 | New | MVS | GO2223007543PH | 13/09/2022 | 701.51 | 113.98 | 815.5 | Bankura Division | Bankura Mechanical Division | 121.37 | 4.02 | 14.49 | 0 | 139.88 | 121.37 | 4.02 | 14.49 | 0 | 139.88 | 17.15 | 14
450 | BANKURA | SM/12418 | Hirapur Piped Water Supply Scheme | TSM/014583 | 40041350 | New | MVS | GO2223007554PH | 13/09/2022 | 815.88 | 86.71 | 902.58 | Bankura Division | Bankura Mechanical Division | 22.3 | 4.45 | 118.58 | 0 | 145.33 | 22.3 | 4.45 | 64.44 | 0 | 91.19 | 10.1 | 4
451 | BANKURA | SM/14527 | Jadabnagar Piped Water Supply Scheme | TSM/014206 | 40035116 | New | MVS | GO2223012618PH | 30/01/2023 | 1075.44 | 149.6 | 1225.04 | Bankura Division | Bankura Mechanical Division | 315.49 | 40.76 | 68.3 | 0 | 424.55 | 315.49 | 40.76 | 68.3 | 0 | 424.55 | 34.66 | 58
452 | BANKURA | SM/14007 | Jamkuri Piped Water Supply Scheme | TSM/015750 | 40036185 | New | MVS | GO2223010516PH | 05/12/2022 | 824.6 | 125.54 | 950.14 | Bankura Division | Bankura Mechanical Division | 57.59 | 7.94 | 24.08 | 0 | 89.6 | 57.59 | 0 | 24.08 | 0 | 81.67 | 8.6 | 23
453 | BANKURA | SM/18037 | Jamuna Band Pipe Water Supply Scheme | TSM/017801 | 5343948 | New | MVS | GO2223016898PH | 17/03/2023 | 481.07 | 82.78 | 563.85 | Bankura Division | Bankura Mechanical Division | 152.69 | 20.14 | 0 | 0 | 172.83 | 152.69 | 0 | 0 | 0 | 152.69 | 27.08 | 30
454 | BANKURA | SM/15018 | Jibta Piped Water Supply Scheme | TSM/015757 | 40035898 | New | MVS | GO2223013074PH | 04/02/2023 | 585.71 | 84.76 | 670.46 | Bankura Division | Bankura Mechanical Division | 132.14 | 27.69 | 14.45 | 0 | 174.27 | 132.14 | 27.69 | 14.45 | 0 | 174.27 | 25.99 | 49
455 | BANKURA | SM/16701 | Kaktia Piped Water Supply Scheme. | TSM/018274 | 40061496 | New | MVS | GO2223016015PH | 14/03/2023 | 836.48 | 127.97 | 964.45 | Bankura Division | Bankura Mechanical Division | 19.17 | 0 | 44.17 | 0 | 63.33 | 0 | 0 | 44.17 | 0 | 44.17 | 4.58 | 17
456 | BANKURA | SM/14010 | Kalyanpur Piped Water Supply Scheme | TSM/015704 | 40036669 | New | MVS | GO2223010506PH | 05/12/2022 | 507.91 | 86.71 | 594.62 | Bankura Division | Bankura Mechanical Division | 79.63 | 18.25 | 0 | 0 | 97.88 | 0 | 18.25 | 0 | 0 | 18.25 | 3.07 | 13
457 | BANKURA | SM/12420 | Karachmani Khayarsol Piped Water Supply Scheme | TSM/014581 | 40038950 | New | MVS | GO2223007553PH | 13/09/2022 | 335.43 | 82.2 | 417.62 | Bankura Division | Bankura Mechanical Division | 70.32 | 17.28 | 22.18 | 0 | 109.78 | 70.32 | 17.28 | 0 | 0 | 87.6 | 20.98 | 33
458 | BANKURA | SM/16702 | Karajbani Piped Water Supply Scheme | TSM/018423 | 40061504 | New | MVS | GO2223016011PH | 14/03/2023 | 437.95 | 67.83 | 505.78 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | BANKURA | SM/14247 | Karak Berya Piped Water Supply Scheme | TSM/014783 | 40042371 | New | MVS | GO2223011830PH | 16/01/2023 | 901.97 | 107.36 | 1009.33 | Bankura Division | Bankura Mechanical Division | 21.61 | 0 | 59.48 | 0 | 81.09 | 0 | 0 | 59.48 | 0 | 59.48 | 5.89 | 3
460 | BANKURA | SM/14526 | Kataban Piped Water Supply Scheme | TSM/014204 | 40035000 | New | MVS | GO2223012615PH | 30/01/2023 | 913.38 | 108.47 | 1021.84 | Bankura Division | Bankura Mechanical Division | 136.15 | 4.35 | 40.84 | 0 | 181.35 | 125.91 | 0 | 27.08 | 0 | 152.99 | 14.97 | 13
461 | BANKURA | SM/18436 | Khiri Piped Water Supply Scheme | TSM/014798 | 40041828 | New | MVS | 1932/PHE-28011/232/2022-SCHM CELL-Dept. of PHE | 18/07/2023 | 1011.16 | 107.36 | 1118.52 | Bankura Division | Bankura Mechanical Division | 21.36 | 0 | 87.77 | 0 | 109.13 | 0 | 0 | 87.77 | 0 | 87.77 | 7.85 | 3
462 | BANKURA | SM/14482 | Khundanga Piped Water Supply Scheme | TSM/014843 | 40042652 | New | MVS | GO2223012317PH | 20/01/2023 | 669.96 | 94.21 | 764.18 | Bankura Division | Bankura Mechanical Division | 177.44 | 21.78 | 9.9 | 0 | 209.13 | 177.44 | 21.78 | 9.9 | 0 | 209.13 | 27.37 | 25
463 | BANKURA | SM/14008 | Kubir Bandh Piped Water Supply Scheme | TSM/015439 | 40036480 | New | MVS | GO2223010511PH | 05/12/2022 | 545.58 | 178.97 | 724.55 | Bankura Division | Bankura Mechanical Division | 31.78 | 40.04 | 0 | 0 | 71.82 | 31.78 | 33.53 | 0 | 0 | 65.3 | 9.01 | 32
464 | BANKURA | SM/15266 | Kushadwip Piped Water Supply Scheme | TSM/015399 | 40044103 | New | MVS | GO2223013460PH | 07/02/2023 | 627.62 | 125.54 | 753.15 | Bankura Division | Bankura Mechanical Division | 84.12 | 3.42 | 32.57 | 0 | 120.12 | 84.12 | 0 | 10.29 | 0 | 94.41 | 12.54 | 52
465 | BANKURA | SM/15022 | Lankajol Piped Water Supply Scheme. | TSM/015918 | 40044241 | New | MVS | GO2223013167PH | 04/02/2023 | 866.15 | 133.23 | 999.38 | Bankura Division | Bankura Mechanical Division | 59.92 | 3.9 | 35.76 | 0 | 99.58 | 59.92 | 3.9 | 35.76 | 0 | 99.58 | 9.96 | 14
466 | BANKURA | SM/18438 | Laugram Piped Water Supply Scheme | TSM/014861 | 40043287 | New | MVS | 1932/PHE-28011/232/2022-SCHM CELL-Dept. of PHE | 18/07/2023 | 1258.96 | 133.23 | 1392.19 | Bankura Division | Bankura Mechanical Division | 12.47 | 0 | 37.4 | 0 | 49.87 | 0 | 0 | 37.4 | 0 | 37.4 | 2.69 | 1
467 | BANKURA | SM/09852 | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Hirbandh & Adjoining Mouzas Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | TSM/008343 | 7708183 | Augmentation | MVS | GO2122006633PH | 03/12/2021 | 580.47 | 0 | 580.47 | Bankura Division | Bankura Mechanical Division | 127.33 | 0 | 22.02 | 0 | 149.35 | 127.33 | 0 | 11.02 | 0 | 138.35 | 23.83 | 22
468 | BANKURA | SM/10295 | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | TSM/008342 | 7615546 | Augmentation | MVS | GO2122010202PH | 28/02/2022 | 1828.18 | 0 | 1828.18 | Bankura Division | Bankura Mechanical Division | 629.42 | 0 | 0 | 0 | 629.42 | 629.42 | 0 | 0 | 0 | 629.42 | 34.43 | 31
469 | BANKURA | SM/18390 | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | TSM/011428 | 40034477 | Augmentation | MVS | 1813/PHE-28011/32/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 1966.1 | 572.14 | 2538.24 | Bankura Division | Bankura Mechanical Division | 140.04 | 177.09 | 370.45 | 0 | 687.58 | 140.04 | 177.09 | 237.51 | 0 | 554.64 | 21.85 | 33
470 | BANKURA | SM/14177 | Lego Piped Water Supply Scheme | TSM/014855 | 40042716 | New | MVS | GO2223011647PH | 09/01/2023 | 941.65 | 107.36 | 1049.01 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | BANKURA | SM/14522 | Madhab Bati Piped Water Supply Scheme | TSM/014209 | 40035621 | New | MVS | GO2223012614PH | 30/01/2023 | 1019.81 | 138.07 | 1157.88 | Bankura Division | Bankura Mechanical Division | 11.3 | 5.2 | 13.2 | 0 | 29.69 | 1.08 | 2.7 | 13.2 | 0 | 16.98 | 1.47 | 7
472 | BANKURA | SM/18318 | Mahaldanga Piped Water Supply Scheme | TSM/014764 | 40034387 | New | MVS | 1656/PHE-28011/33/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1380.01 | 161.48 | 1541.49 | Bankura Division | Bankura Mechanical Division | 67.16 | 29.5 | 254.76 | 0 | 351.42 | 67.16 | 6.57 | 254.76 | 0 | 328.48 | 21.31 | 50
473 | BANKURA | SM/14520 | Makarandapur Piped Water Supply Scheme | TSM/014566 | 40041393 | New | MVS | GO2223012612PH | 30/01/2023 | 1039.26 | 114.28 | 1153.54 | Bankura Division | Bankura Mechanical Division | 12.89 | 7.14 | 59.4 | 0 | 79.44 | 12.89 | 0 | 59.4 | 0 | 72.29 | 6.27 | 7
474 | BANKURA | SM/12417 | Mathurabati Piped Water Supply Scheme | TSM/014588 | 40041296 | New | MVS | GO2223007555PH | 13/09/2022 | 595.54 | 96.1 | 691.64 | Bankura Division | Bankura Mechanical Division | 0 | 18.3 | 29.08 | 0 | 47.38 | 0 | 18.3 | 20.48 | 0 | 38.79 | 5.61 | 8
475 | BANKURA | SM/11688 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Adhakata, House Hold No.: 51) | TSM/012141 | 40020005 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 62.99 | 72
476 | BANKURA | SM/11683 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bagsara, House Hold No.: 25) | TSM/012159 | 40020053 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 70.51 | 91
477 | BANKURA | SM/11687 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Barakura, House Hold No.: 61) | TSM/012144 | 40020048 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 62.99 | 72
478 | BANKURA | SM/11678 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) | TSM/012177 | 40029030 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 10.13 | 0 | 0 | 0 | 10.13 | 10 | 0 | 0 | 0 | 10 | 25.08 | 31
479 | BANKURA | SM/11695 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bhabanipur, House Hold No.: 60) | TSM/012121 | 40019979 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30.12 | 0 | 0 | 0 | 30.12 | 75.52 | 82
480 | BANKURA | SM/11679 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Bhandarya, House Hold No.: 72) | TSM/012174 | 40065999 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 0.13 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 13
481 | BANKURA | SM/11694 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Birampur, House Hold No.: 57) | TSM/012123 | 40019988 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 22 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 22 | 55.17 | 75
482 | BANKURA | SM/11681 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Borajpota, House Hold No.: 33) | TSM/012167 | 40030370 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 30.11 | 0 | 0 | 0 | 30.11 | 30.11 | 0 | 0 | 0 | 30.11 | 75.51 | 88
483 | BANKURA | SM/11675 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chakchuamasina, House Hold No.: 75) | TSM/012183 | 40066051 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 10.13 | 0 | 0 | 0 | 10.13 | 10 | 0 | 0 | 0 | 10 | 25.08 | 31
484 | BANKURA | SM/11686 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chandabil, House Hold No.: 93) | TSM/012149 | 40020050 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 70.51 | 81
485 | BANKURA | SM/11693 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Chhatina, House Hold No.: 80) | TSM/012125 | 40019994 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 73.02 | 91
486 | BANKURA | SM/11685 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Danga Makarandapur, House Hold No.: 90) | TSM/012151 | 40020051 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 62.99 | 72
487 | BANKURA | SM/11684 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Dharisyer, House Hold No.: 25) | TSM/012155 | 40020052 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 70.51 | 82
488 | BANKURA | SM/11677 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Dumohani, House Hold No.: 51) | TSM/012178 | 40029027 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 10.13 | 0 | 0 | 0 | 10.13 | 10 | 0 | 0 | 0 | 10 | 25.08 | 21
489 | BANKURA | SM/11676 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Khanabari, House Hold No.: 53) | TSM/012180 | 40029024 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 0.13 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 11
490 | BANKURA | SM/11680 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Kushtara , House Hold No.: 21 ) | TSM/012169 | 40066069 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 0.13 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 23
491 | BANKURA | SM/11692 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Madhurpur, House Hold No.: 93) | TSM/012127 | 40019995 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 73.02 | 93
492 | BANKURA | SM/11682 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Maheshpur , House Hold No.: 84) | TSM/012162 | 40029038 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 73.02 | 87
493 | BANKURA | SM/11691 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Mohishkhoar, House Hold No.: 78) | TSM/012130 | 40019997 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30 | 0 | 0 | 0 | 30 | 75.23 | 92
494 | BANKURA | SM/11672 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Narayanpur, House Hold No.: 53) | TSM/012189 | 40029019 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 25.25 | 0 | 0 | 0 | 25.25 | 25.12 | 0 | 0 | 0 | 25.12 | 62.99 | 33
495 | BANKURA | SM/11690 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Narayanpur, House Hold No.: 60) | TSM/012134 | 40020000 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 29 | 0 | 0 | 0 | 29 | 29 | 0 | 0 | 0 | 29 | 72.72 | 91
496 | BANKURA | SM/11689 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Parashe, House Hold No.: 90) | TSM/012136 | 40020003 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 73.02 | 91
497 | BANKURA | SM/11673 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Pirragara, House Hold No.: 75) | TSM/012188 | 40029020 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 10.13 | 0 | 0 | 0 | 10.13 | 10 | 0 | 0 | 0 | 10 | 25.08 | 16
498 | BANKURA | SM/11674 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Purba Nischintapur, House Hold No.: 81) | TSM/012185 | 40066053 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 0.13 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 21
499 | BANKURA | SM/11671 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Ramnagar, House Hold No.: 88) | TSM/012192 | 40029016 | New | SVS | GO2223003668PH | 30/05/2022 | 39.88 | 0 | 39.88 | Bankura Division | Bankura Mechanical Division | 10.13 | 0 | 0 | 0 | 10.13 | 10 | 0 | 0 | 0 | 10 | 25.08 | 33
500 | BANKURA | SM/11190 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Akharashal, House Hold No.: 35) | TSM/012206 | 40029037 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 64.7 | 85
501 | BANKURA | SM/11173 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Amlasol, House Hold No.: 69) | TSM/012239 | 40020088 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.6 | 88
502 | BANKURA | SM/11181 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Basantapur, House Hold No.: 62) | TSM/012226 | 40020067 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 80.54 | 92
503 | BANKURA | SM/11195 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Bhalukgere, House Hold No.: 48) | TSM/012196 | 40029060 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 23.12 | 0 | 0 | 0 | 23.12 | 23.12 | 0 | 0 | 0 | 23.12 | 59.83 | 72
504 | BANKURA | SM/11193 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Bhelaighata, House Hold No.: 32) | TSM/012200 | 40029050 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 69.15 | 78
505 | BANKURA | SM/11180 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Brindabanpur, House Hold No.: 95) | TSM/012227 | 40020071 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 75.36 | 93
506 | BANKURA | SM/11189 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chaknayan, House Hold No.: 29) | TSM/012209 | 40029034 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 24.12 | 0 | 0 | 0 | 24.12 | 24.12 | 0 | 0 | 0 | 24.12 | 62.42 | 75
507 | BANKURA | SM/11179 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Chanpatala, House Hold No.: 63) | TSM/012229 | 40020074 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 85
508 | BANKURA | SM/11178 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Digrya, House Hold No.: 64) | TSM/012231 | 40020077 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 80.54 | 92
509 | BANKURA | SM/11192 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Durgabati, House Hold No.: 20) | TSM/012202 | 40029039 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.28 | 0 | 0 | 0 | 25.28 | 25.28 | 0 | 0 | 0 | 25.28 | 65.43 | 74
510 | BANKURA | SM/11185 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Gaighata, House Hold No.: 84) | TSM/012216 | 40020054 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 23.18 | 0 | 0 | 0 | 23.18 | 23.01 | 0 | 0 | 0 | 23.01 | 59.55 | 75
511 | BANKURA | SM/11175 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) | TSM/012236 | 40020084 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 82
512 | BANKURA | SM/11177 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Hajipur, House Hold No.: 87) | TSM/012232 | 40020080 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 75.36 | 90
513 | BANKURA | SM/11188 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Jhero, House Hold No.: 21) | TSM/012210 | 40029031 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 74
514 | BANKURA | SM/11176 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Kumardubi, House Hold No.: 50) | TSM/012234 | 40020083 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 80.54 | 95
515 | BANKURA | SM/11183 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Mahishabandi, House Hold No.: 93) | TSM/012221 | 40020064 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 22.12 | 0 | 0 | 0 | 22.12 | 22.12 | 0 | 0 | 0 | 22.12 | 57.25 | 80
516 | BANKURA | SM/11172 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nachur, House Hold No.: 59) | TSM/012241 | 40020090 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 72.77 | 82
517 | BANKURA | SM/11174 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nutangram Radhamohanpur, House Hold No.: 88) | TSM/012237 | 40020087 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 80
518 | BANKURA | SM/11182 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Nutangram, House Hold No.: 81) | TSM/012223 | 40020066 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 80
519 | BANKURA | SM/11186 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Parbatipur, House Hold No.: 50) | TSM/012215 | 40029025 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 74
520 | BANKURA | SM/11194 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Piritchak, House Hold No.: 39) | TSM/012198 | 40027952 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.01 | 73
521 | BANKURA | SM/11171 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Radhanagar, House Hold No.: 97) | TSM/012242 | 40020095 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 54.66 | 82
522 | BANKURA | SM/11191 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ramchandrapur, House Hold No.: 45) | TSM/012204 | 40030387 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.24 | 0 | 0 | 0 | 25.24 | 25.24 | 0 | 0 | 0 | 25.24 | 65.32 | 74
523 | BANKURA | SM/11184 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Shibdanga, House Hold No.: 74) | TSM/012218 | 40020062 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 27.12 | 0 | 0 | 0 | 27.12 | 27.12 | 0 | 0 | 0 | 27.12 | 70.19 | 80
524 | BANKURA | SM/11187 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Tentulia, House Hold No.: 23) | TSM/012213 | 40029028 | New | SVS | GO2223003666PH | 30/05/2022 | 38.64 | 0 | 38.64 | Bankura Division | Bankura Mechanical Division | 25.72 | 0 | 0 | 0 | 25.72 | 25.72 | 0 | 0 | 0 | 25.72 | 66.56 | 74
525 | BANKURA | SM/11158 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Akargarya, House Hold No.: 94) | TSM/012245 | 40030077 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 63.29 | 72
526 | BANKURA | SM/11146 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Baragopinathpur, House Hold No.: 90) | TSM/012257 | 40027975 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 67.32 | 78
527 | BANKURA | SM/11157 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) | TSM/012246 | 40030074 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 63.29 | 74
528 | BANKURA | SM/11144 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Mahammad, House Hold No.: 83) | TSM/012259 | 40027966 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 63.29 | 82
529 | BANKURA | SM/11142 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chandipur, House Hold No.: 97) | TSM/012261 | 40027962 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.6 | 0 | 0 | 0 | 26.6 | 26.6 | 0 | 0 | 0 | 26.6 | 67.02 | 77
530 | BANKURA | SM/11140 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Dhanjoga, House Hold No.: 56) | TSM/012263 | 40027959 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 63.29 | 82
531 | BANKURA | SM/11155 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Enayet Chak, House Hold No.: 85) | TSM/012248 | 40028010 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 63.29 | 78
532 | BANKURA | SM/11137 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Jemo, House Hold No.: 54) | TSM/012266 | 40027930 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 63.29 | 74
533 | BANKURA | SM/11153 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Metelsair, House Hold No.: 93) | TSM/012250 | 40028007 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 30 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 30 | 75.58 | 86
534 | BANKURA | SM/11135 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Mohanchak, House Hold No.: 96) | TSM/012268 | 40027918 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 27 | 0 | 0 | 0 | 27 | 27 | 0 | 0 | 0 | 27 | 68.03 | 74
535 | BANKURA | SM/11150 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Pal Puskarini, House Hold No.: 79) | TSM/012253 | 40027983 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 27.12 | 0 | 0 | 0 | 27.12 | 27.12 | 0 | 0 | 0 | 27.12 | 68.32 | 78
536 | BANKURA | SM/11148 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Rohimchak, House Hold No.: 78) | TSM/012255 | 40027979 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.24 | 0 | 0 | 0 | 26.24 | 26.24 | 0 | 0 | 0 | 26.24 | 66.1 | 82
537 | BANKURA | SM/11141 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Angazrasol, House Hold:42) | TSM/012262 | 40027960 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.62 | 0 | 0 | 0 | 26.62 | 26.62 | 0 | 0 | 0 | 26.62 | 67.07 | 78
538 | BANKURA | SM/11147 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balananda, House Hold:42) | TSM/012256 | 40027977 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 32.33 | 0 | 0 | 0 | 32.33 | 30 | 0 | 0 | 0 | 30 | 75.58 | 88
539 | BANKURA | SM/11149 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Balaramp[ur, House Hold:49) | TSM/012254 | 40027981 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 29.67 | 0 | 0 | 0 | 29.67 | 29.67 | 0 | 0 | 0 | 29.67 | 74.75 | 87
540 | BANKURA | SM/11151 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) | TSM/012252 | 40027989 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 27.12 | 0 | 0 | 0 | 27.12 | 27.12 | 0 | 0 | 0 | 27.12 | 68.32 | 89
541 | BANKURA | SM/11134 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Fatepur, House Hold:88) | TSM/012269 | 40027893 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 27.72 | 0 | 0 | 0 | 27.72 | 27.72 | 0 | 0 | 0 | 27.72 | 69.84 | 74
542 | BANKURA | SM/11136 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) | TSM/012267 | 40027923 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 14.12 | 0 | 0 | 0 | 14.12 | 14.12 | 0 | 0 | 0 | 14.12 | 35.57 | 74
543 | BANKURA | SM/11143 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Jamsala, House Hold:60) | TSM/012260 | 40030080 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 67.32 | 82
544 | BANKURA | SM/11152 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kendgara, House Hold:27) | TSM/012251 | 40028006 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 30.55 | 0 | 0 | 0 | 30.55 | 30.55 | 0 | 0 | 0 | 30.55 | 76.96 | 87
545 | BANKURA | SM/11154 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) | TSM/012249 | 40028009 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30.12 | 0 | 0 | 0 | 30.12 | 75.88 | 87
546 | BANKURA | SM/11156 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) | TSM/012247 | 40030071 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 30 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 30 | 75.58 | 88
547 | BANKURA | SM/11145 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) | TSM/012258 | 40027973 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 65.81 | 82
548 | BANKURA | SM/11138 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Shyampur, House Hold:42) | TSM/012265 | 40027947 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 67.32 | 72
549 | BANKURA | SM/11139 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sri Rampur, House Hold:46) | TSM/012264 | 40027956 | New | SVS | GO2223003667PH | 30/05/2022 | 39.69 | 0 | 39.69 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 65.81 | 74
550 | BANKURA | SM/11099 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Adwaitabati, House Hold No.: 50) | TSM/012087 | 40029428 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 69.39 | 74
551 | BANKURA | SM/11102 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Asude, House Hold No.: 35) | TSM/012083 | 40029406 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 73.03 | 82
552 | BANKURA | SM/11105 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) | TSM/012078 | 40029394 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.24 | 74
553 | BANKURA | SM/11108 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | TSM/012066 | 40029274 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 25.24 | 0 | 0 | 0 | 25.24 | 25.24 | 0 | 0 | 0 | 25.24 | 65.55 | 78
554 | BANKURA | SM/11101 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) | TSM/012084 | 40029416 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 73.03 | 82
555 | BANKURA | SM/11092 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bramhanairi, House Hold No.: 67) | TSM/012099 | 40029396 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 73.03 | 82
556 | BANKURA | SM/11091 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) | TSM/012101 | 40029388 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 75
557 | BANKURA | SM/11097 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) | TSM/012091 | 40029425 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 30.72 | 0 | 0 | 0 | 30.72 | 30.72 | 0 | 0 | 0 | 30.72 | 79.78 | 82
558 | BANKURA | SM/11095 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) | TSM/012094 | 40029417 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 75
559 | BANKURA | SM/11096 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dashere, House Hold No.: 75) | TSM/012092 | 40029422 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 69.39 | 78
560 | BANKURA | SM/11088 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dehuabani, House Hold No.: 61) | TSM/012106 | 40027985 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 73
561 | BANKURA | SM/11087 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dharapat, House Hold No.: 65) | TSM/012109 | 40027974 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 72
562 | BANKURA | SM/11107 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Haldar Chak, House Hold No.: 40) | TSM/012075 | 40029276 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 74
563 | BANKURA | SM/11086 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Jaljala, House Hold No.: 84) | TSM/012112 | 40027968 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.62 | 0 | 0 | 0 | 26.62 | 26.62 | 0 | 0 | 0 | 26.62 | 69.14 | 75
564 | BANKURA | SM/11104 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Kachara , House Hold No.: 25) | TSM/012080 | 40029397 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.24 | 75
565 | BANKURA | SM/11090 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Kankara, House Hold No.: 69) | TSM/012102 | 40029419 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 75
566 | BANKURA | SM/11103 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Lalgara, House Hold No.: 34) | TSM/012081 | 40029402 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 64.93 | 75
567 | BANKURA | SM/11094 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Mukha, House Hold No.: 93) | TSM/012096 | 40029403 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 75
568 | BANKURA | SM/11089 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Napukur, House Hold No.: 89) | TSM/012104 | 40027994 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.24 | 78
569 | BANKURA | SM/11085 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) | TSM/012114 | 40027952 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.62 | 0 | 0 | 0 | 26.62 | 26.62 | 0 | 0 | 0 | 26.62 | 69.14 | 75
570 | BANKURA | SM/11098 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Ram Bakhra, House Hold No.: 63) | TSM/012089 | 40029429 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 75
571 | BANKURA | SM/11100 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Rampur, House Hold No.:65) | TSM/012086 | 40030061 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 74
572 | BANKURA | SM/11084 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) | TSM/012116 | 40027914 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.84 | 78
573 | BANKURA | SM/11093 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Shimdal, House Hold No.: 50) | TSM/012098 | 40029400 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.24 | 75
574 | BANKURA | SM/11106 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Siringa, House Hold No.: 21) | TSM/012076 | 40029393 | New | SVS | GO2223003661PH | 30/05/2022 | 38.5 | 0 | 38.5 | Bankura Division | Bankura Mechanical Division | 26.72 | 0 | 0 | 0 | 26.72 | 26.72 | 0 | 0 | 0 | 26.72 | 69.39 | 74
575 | BANKURA | SM/11440 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:66) | TSM/012214 | 40029191 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87
576 | BANKURA | SM/11435 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) | TSM/012228 | 40029191 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 21.2 | 0 | 0 | 0 | 21.2 | 21.2 | 0 | 0 | 0 | 21.2 | 54.49 | 87
577 | BANKURA | SM/11434 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) | TSM/012230 | 40029189 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 19.72 | 0 | 0 | 0 | 19.72 | 19.72 | 0 | 0 | 0 | 19.72 | 50.67 | 90
578 | BANKURA | SM/11439 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Dihilapur, House Hold:52) | TSM/012217 | 40029217 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 25.72 | 0 | 0 | 0 | 25.72 | 25.72 | 0 | 0 | 0 | 25.72 | 66.09 | 85
579 | BANKURA | SM/11438 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Goala Danga, House Hold:96) | TSM/012219 | 40029213 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 18.72 | 0 | 0 | 0 | 18.72 | 18.72 | 0 | 0 | 0 | 18.72 | 48.1 | 86
580 | BANKURA | SM/11429 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Goppdanga, House Hold:36) | TSM/012243 | 40029096 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 15.12 | 0 | 0 | 0 | 15.12 | 15.12 | 0 | 0 | 0 | 15.12 | 38.85 | 40
581 | BANKURA | SM/11431 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Hurhrjangar, House Hold:45) | TSM/012238 | 40029182 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.55 | 60
582 | BANKURA | SM/11437 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Kamar Bera, House Hold:81) | TSM/012222 | 40029205 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 20.84 | 0 | 0 | 0 | 20.84 | 20.84 | 0 | 0 | 0 | 20.84 | 53.55 | 89
583 | BANKURA | SM/11433 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Paschim Nabasan, House Hold:33) | TSM/012233 | 40029185 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.55 | 80
584 | BANKURA | SM/11432 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Radhakrishnapur, House Hold:22) | TSM/012235 | 40029184 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 19 | 0 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | 19 | 48.83 | 60
585 | BANKURA | SM/11441 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Shalkota, House Hold:75) | TSM/012212 | 40029229 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 20.6 | 0 | 0 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 20.6 | 52.94 | 88
586 | BANKURA | SM/11436 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Shankarpur, House Hold:52) | TSM/012224 | 40029201 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 20.72 | 0 | 0 | 0 | 20.72 | 20.72 | 0 | 0 | 0 | 20.72 | 53.24 | 88
587 | BANKURA | SM/11428 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Siltya(P), House Hold:22) | TSM/012244 | 40029080 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 15.14 | 0 | 0 | 0 | 15.14 | 15.14 | 0 | 0 | 0 | 15.14 | 38.9 | 65
588 | BANKURA | SM/11430 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Tulardihi, House Hold:21) | TSM/012240 | 40029133 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 19.24 | 0 | 0 | 0 | 19.24 | 19.12 | 0 | 0 | 0 | 19.12 | 49.13 | 65
589 | BANKURA | SM/11446 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name : Radha Damodarpur, House Hold:79 | TSM/012191 | 40044811 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 18.6 | 0 | 0 | 0 | 18.6 | 18.6 | 0 | 0 | 0 | 18.6 | 47.8 | 86
590 | BANKURA | SM/11442 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Barika Bhanupur, House Hold:53 | TSM/012208 | 40044744 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 64.25 | 86
591 | BANKURA | SM/11449 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Bhetia, House Hold:78 | TSM/012181 | 40029266 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 19.12 | 0 | 0 | 0 | 19.12 | 19.12 | 0 | 0 | 0 | 19.12 | 49.13 | 87
592 | BANKURA | SM/11445 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Brindabanpur, House Hold:60 | TSM/012193 | 40029243 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 19.44 | 0 | 0 | 0 | 19.44 | 19.44 | 0 | 0 | 0 | 19.44 | 49.95 | 85
593 | BANKURA | SM/11447 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Dumni, House Hold:67 | TSM/012187 | 40029251 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 67.12 | 86
594 | BANKURA | SM/11448 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Gosai Gram, House Hold:59 | TSM/012184 | 40029265 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 25.42 | 0 | 0 | 0 | 25.42 | 25.42 | 0 | 0 | 0 | 25.42 | 65.34 | 89
595 | BANKURA | SM/11450 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Haira bandh, House Hold:54 | TSM/012179 | 40029268 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 18.72 | 0 | 0 | 0 | 18.72 | 18.72 | 0 | 0 | 0 | 18.72 | 48.1 | 86
596 | BANKURA | SM/11452 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Karajbani , House Hold:74 | TSM/012170 | 40029271 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 18.54 | 0 | 0 | 0 | 18.54 | 18.54 | 0 | 0 | 0 | 18.54 | 47.64 | 90
597 | BANKURA | SM/11444 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Khamardihi, House Hold:92 | TSM/012201 | 40029242 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 19.12 | 0 | 0 | 0 | 19.12 | 19.12 | 0 | 0 | 0 | 19.12 | 49.13 | 88
598 | BANKURA | SM/11443 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Parashia, House Hold:71 | TSM/012205 | 40029238 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 51.7 | 90
599 | BANKURA | SM/11451 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Thakurhati , House Hold: 74 | TSM/012175 | 40029269 | New | SVS | GO2223003655PH | 30/05/2022 | 38.91 | 0 | 38.91 | Bankura Division | Bankura Mechanical Division | 18.72 | 0 | 0 | 0 | 18.72 | 18.72 | 0 | 0 | 0 | 18.72 | 48.1 | 88
600 | BANKURA | SM/11418 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) | TSM/012097 | 40029108 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30.12 | 0 | 0 | 0 | 30.12 | 77.01 | 80
601 | BANKURA | SM/11426 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name -Aligang, House Hold-91) | TSM/012077 | 40029141 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 19.12 | 0 | 0 | 0 | 19.12 | 19.12 | 0 | 0 | 0 | 19.12 | 48.88 | 80
602 | BANKURA | SM/11422 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Bara Naryanpur, Household-73) | TSM/012088 | 40029119 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 70
603 | BANKURA | SM/11407 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Chhota Narayanpur, Household-24) | TSM/012129 | 40029063 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 40
604 | BANKURA | SM/11405 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Dakshinsol, Household-36) | TSM/012137 | 40029059 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 19.12 | 0 | 0 | 0 | 19.12 | 19.12 | 0 | 0 | 0 | 19.12 | 48.88 | 60
605 | BANKURA | SM/11419 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Mach Doba, Household-67) | TSM/012095 | 40029112 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 51.44 | 60
606 | BANKURA | SM/11421 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Mathurabati, Household-54) | TSM/012090 | 40029117 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 21.01 | 0 | 0 | 0 | 21.01 | 21.01 | 0 | 0 | 0 | 21.01 | 53.71 | 65
607 | BANKURA | SM/11414 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) | TSM/012108 | 40029101 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 65
608 | BANKURA | SM/11416 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) | TSM/012103 | 40029105 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0 | 0 | 0 | 29.12 | 74.45 | 80
609 | BANKURA | SM/11406 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name- Samanta Bandi, Household-39) | TSM/012133 | 40030433 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 19.12 | 0 | 0 | 0 | 19.12 | 19.12 | 0 | 0 | 0 | 19.12 | 48.88 | 65
610 | BANKURA | SM/11420 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Tiura, Household-95) | TSM/012093 | 40029115 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 19.12 | 0 | 0 | 0 | 19.12 | 19.12 | 0 | 0 | 0 | 19.12 | 48.88 | 40
611 | BANKURA | SM/11410 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Amghata, Household-22) | TSM/012122 | 40029068 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 60
612 | BANKURA | SM/11409 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village name-Chakdhoyakure, household-36) | TSM/012124 | 40029066 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 80
613 | BANKURA | SM/11417 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Chaulya, Household-71) | TSM/012100 | 40029107 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 80
614 | BANKURA | SM/11404 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Jaypur, Household-22) | TSM/012142 | 40029058 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 19 | 0 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | 19 | 48.58 | 60
615 | BANKURA | SM/11403 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Kubir Bandh, Household-43) | TSM/012147 | 40029055 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 19 | 0 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | 19 | 48.58 | 60
616 | BANKURA | SM/11423 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Maitya, Household-74) | TSM/012085 | 40029136 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 51.44 | 80
617 | BANKURA | SM/11425 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Nachanhati, Household-84) | TSM/012079 | 40029140 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 80
618 | BANKURA | SM/11413 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Nischintapur, Household-81) | TSM/012111 | 40029099 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 16 | 40.91 | 65
619 | BANKURA | SM/11424 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) | TSM/012082 | 40029138 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 21.63 | 0 | 0 | 0 | 21.63 | 21.63 | 0 | 0 | 0 | 21.63 | 55.29 | 65
620 | BANKURA | SM/11411 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rupuisar, Household-85) | TSM/012120 | 40029090 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 21.14 | 0 | 0 | 0 | 21.14 | 21.14 | 0 | 0 | 0 | 21.14 | 54.04 | 60
621 | BANKURA | SM/11412 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Salda, Household-77) | TSM/012119 | 40029097 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.24 | 0 | 0 | 0 | 25.24 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 80
622 | BANKURA | SM/11408 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (village Name-Sapuradihi, household-25) | TSM/012126 | 40029065 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 60
623 | BANKURA | SM/11415 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Shibdanga, Household-82) | TSM/012105 | 40029102 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 64.22 | 70
624 | BANKURA | SM/11427 | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name: Indkata, House Hold- 93) | TSM/012074 | 40029142 | New | SVS | GO2223003665PH | 30/05/2022 | 39.11 | 0 | 39.11 | Bankura Division | Bankura Mechanical Division | 15.12 | 0 | 0 | 0 | 15.12 | 15.12 | 0 | 0 | 0 | 15.12 | 38.66 | 65
625 | BANKURA | SM/10926 | MINI PIPED WATER SUPPLY SCHEME FOR AMALA DIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012383 | 40026022 | New | SVS | GO2223003674PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
626 | BANKURA | SM/10977 | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012459 | 40020109 | New | SVS | GO2223003672PH | 30/05/2022 | 44.04 | 0 | 44.04 | Bankura Division | Bankura Mechanical Division | 31 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 31 | 70.4 | 50
627 | BANKURA | SM/10878 | MINI PIPED WATER SUPPLY SCHEME FOR AMDANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012435 | 40020019 | New | SVS | GO2223003669PH | 30/05/2022 | 34.46 | 0 | 34.46 | Bankura Division | Bankura Mechanical Division | 26.12 | 0 | 0 | 0 | 26.12 | 26.12 | 0 | 0 | 0 | 26.12 | 75.8 | 70
628 | BANKURA | SM/10945 | MINI PIPED WATER SUPPLY SCHEME FOR ASAN CHUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012402 | 40026029 | New | SVS | GO2223003674PH | 30/05/2022 | 42.08 | 0 | 42.08 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.28 | 75
629 | BANKURA | SM/11045 | MINI PIPED WATER SUPPLY SCHEME FOR ASNASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012364 | 40027301 | New | SVS | GO2223003657PH | 30/05/2022 | 43.45 | 0 | 43.45 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 46.03 | 60
630 | BANKURA | SM/11074 | MINI PIPED WATER SUPPLY SCHEME FOR ASNASUNDARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012337 | 40065449 | New | SVS | GO2223003663PH | 30/05/2022 | 35.46 | 0 | 35.46 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
631 | BANKURA | SM/10929 | MINI PIPED WATER SUPPLY SCHEME FOR ATARYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012386 | 40026041 | New | SVS | GO2223003674PH | 30/05/2022 | 35.21 | 0 | 35.21 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
632 | BANKURA | SM/11073 | MINI PIPED WATER SUPPLY SCHEME FOR AULIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012336 | 0 | New | SVS | GO2223003663PH | 30/05/2022 | 34.46 | 0 | 34.46 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
633 | BANKURA | SM/11110 | MINI PIPED WATER SUPPLY SCHEME FOR BAGDUBI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012298 | 40066029 | New | SVS | GO2223003670PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 10 | 26.52 | 20
634 | BANKURA | SM/11059 | MINI PIPED WATER SUPPLY SCHEME FOR BAGNADA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012322 | 40066026 | New | SVS | GO2223003663PH | 30/05/2022 | 34.46 | 0 | 34.46 | Bankura Division | Bankura Mechanical Division | 15 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 43.53 | 25
635 | BANKURA | SM/11075 | MINI PIPED WATER SUPPLY SCHEME FOR BAHARAGARYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012338 | 40065455 | New | SVS | GO2223003663PH | 30/05/2022 | 31.49 | 0 | 31.49 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 50
636 | BANKURA | SM/10983 | MINI PIPED WATER SUPPLY SCHEME FOR BAJORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012465 | 40020147 | New | SVS | GO2223003672PH | 30/05/2022 | 43.06 | 0 | 43.06 | Bankura Division | Bankura Mechanical Division | 22.5 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 22.5 | 52.25 | 70
637 | BANKURA | SM/11053 | MINI PIPED WATER SUPPLY SCHEME FOR BALARAMPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012372 | 40027369 | New | SVS | GO2223003657PH | 30/05/2022 | 39.05 | 0 | 39.05 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25 | 0 | 0 | 0 | 25 | 64.02 | 62
638 | BANKURA | SM/11129 | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012317 | 40066009 | New | SVS | GO2223003670PH | 30/05/2022 | 36.21 | 0 | 36.21 | Bankura Division | Bankura Mechanical Division | 16.11 | 0 | 0 | 0 | 16.11 | 16.11 | 0 | 0 | 0 | 16.11 | 44.48 | 50
639 | BANKURA | SM/11080 | MINI PIPED WATER SUPPLY SCHEME FOR BALI BANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012343 | 40065458 | New | SVS | GO2223003663PH | 30/05/2022 | 32.56 | 0 | 32.56 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 25
640 | BANKURA | SM/10852 | MINI PIPED WATER SUPPLY SCHEME FOR BALIKHUN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012409 | 40026251 | New | SVS | GO2223003673PH | 30/05/2022 | 45.01 | 0 | 45.01 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
641 | BANKURA | SM/11127 | MINI PIPED WATER SUPPLY SCHEME FOR BAMNISHALA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012315 | 40066024 | New | SVS | GO2223003670PH | 30/05/2022 | 40.68 | 0 | 40.68 | Bankura Division | Bankura Mechanical Division | 15.12 | 0 | 0 | 0 | 15.12 | 15.12 | 0 | 0 | 0 | 15.12 | 37.17 | 25
642 | BANKURA | SM/11070 | MINI PIPED WATER SUPPLY SCHEME FOR BAMUN PATHRI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012333 | 40065980 | New | SVS | GO2223003663PH | 30/05/2022 | 42.47 | 0 | 42.47 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21 | 0 | 0 | 0 | 21 | 49.44 | 50
643 | BANKURA | SM/10853 | MINI PIPED WATER SUPPLY SCHEME FOR BAMUNDIHA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012410 | 40026254 | New | SVS | GO2223003673PH | 30/05/2022 | 41.5 | 0 | 41.5 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
644 | BANKURA | SM/10915 | MINI PIPED WATER SUPPLY SCHEME FOR BANAGRAM VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012161 | 40032279 | New | SVS | GO2223003656PH | 30/05/2022 | 41.37 | 0 | 41.37 | Bankura Division | Bankura Mechanical Division | 12.62 | 0 | 0 | 0 | 12.62 | 12.62 | 0 | 0 | 0 | 12.62 | 30.5 | 25
645 | BANKURA | SM/10949 | MINI PIPED WATER SUPPLY SCHEME FOR BANDARKONDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012481 | 40065716 | New | SVS | GO2223003664PH | 30/05/2022 | 32.56 | 0 | 32.56 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 61.78 | 70
646 | BANKURA | SM/10872 | MINI PIPED WATER SUPPLY SCHEME FOR BANGRAM VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012429 | 40019993 | New | SVS | GO2223003669PH | 30/05/2022 | 34.45 | 0 | 34.45 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 61.31 | 70
647 | BANKURA | SM/13274 | MINI PIPED WATER SUPPLY SCHEME FOR BANKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012220 | 40028547 | New | SVS | GO2223003658PH | 30/05/2022 | 41.69 | 0 | 41.69 | Bankura Division | Bankura Mechanical Division | 15.12 | 0 | 0 | 0 | 15.12 | 15 | 0 | 0 | 0 | 15 | 35.98 | 30
648 | BANKURA | SM/10955 | MINI PIPED WATER SUPPLY SCHEME FOR BANKATI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012487 | 40026069 | New | SVS | GO2223003664PH | 30/05/2022 | 40.91 | 0 | 40.91 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 44.29 | 50
649 | BANKURA | SM/11076 | MINI PIPED WATER SUPPLY SCHEME FOR BANKTOR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012339 | 40065420 | New | SVS | GO2223003663PH | 30/05/2022 | 36.21 | 0 | 36.21 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
650 | BANKURA | SM/11029 | MINI PIPED WATER SUPPLY SCHEME FOR BANPUKHURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012292 | 40026359 | New | SVS | GO2223003671PH | 30/05/2022 | 34.45 | 0 | 34.45 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18 | 0 | 0 | 0 | 18 | 52.26 | 55
651 | BANKURA | SM/10885 | MINI PIPED WATER SUPPLY SCHEME FOR BANSHKETYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012442 | 40020063 | New | SVS | GO2223003669PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 12.62 | 0 | 0 | 0 | 12.62 | 12.5 | 0 | 0 | 0 | 12.5 | 28.26 | 50
652 | BANKURA | SM/10957 | MINI PIPED WATER SUPPLY SCHEME FOR BANSNALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012489 | 40026077 | New | SVS | GO2223003664PH | 30/05/2022 | 42.3 | 0 | 42.3 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 42.83 | 52
653 | BANKURA | SM/11009 | MINI PIPED WATER SUPPLY SCHEME FOR BARAKHARANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012272 | 40020027 | New | SVS | GO2223003671PH | 30/05/2022 | 43.45 | 0 | 43.45 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 46.3 | 75
654 | BANKURA | SM/10911 | MINI PIPED WATER SUPPLY SCHEME FOR BARAMASIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012153 | 40019351 | New | SVS | GO2223003656PH | 30/05/2022 | 42.28 | 0 | 42.28 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
655 | BANKURA | SM/11115 | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012303 | 40027156 | New | SVS | GO2223003670PH | 30/05/2022 | 41.6 | 0 | 41.6 | Bankura Division | Bankura Mechanical Division | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 0 | 0 | 0 | 12.6 | 30.28 | 26
656 | BANKURA | SM/11062 | MINI PIPED WATER SUPPLY SCHEME FOR BARISOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012325 | 40026912 | New | SVS | GO2223003663PH | 30/05/2022 | 37.21 | 0 | 37.21 | Bankura Division | Bankura Mechanical Division | 19.5 | 0 | 0 | 0 | 19.5 | 19.5 | 0 | 0 | 0 | 19.5 | 52.4 | 50
657 | BANKURA | SM/11030 | MINI PIPED WATER SUPPLY SCHEME FOR BARUNIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012293 | 40066042 | New | SVS | GO2223003671PH | 30/05/2022 | 35.71 | 0 | 35.71 | Bankura Division | Bankura Mechanical Division | 15.12 | 0 | 0 | 0 | 15.12 | 15 | 0 | 0 | 0 | 15 | 42.01 | 55
658 | BANKURA | SM/10927 | MINI PIPED WATER SUPPLY SCHEME FOR BELARMARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012384 | 40026028 | New | SVS | GO2223003674PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
659 | BANKURA | SM/10992 | MINI PIPED WATER SUPPLY SCHEME FOR BELARUMA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012474 | 40020170 | New | SVS | GO2223003672PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 27.5 | 0 | 0 | 0 | 27.5 | 27.5 | 0 | 0 | 0 | 27.5 | 61.63 | 70
660 | BANKURA | SM/13251 | MINI PIPED WATER SUPPLY SCHEME FOR BENAGARYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012067 | 40028629 | New | SVS | GO2223003658PH | 30/05/2022 | 37.89 | 0 | 37.89 | Bankura Division | Bankura Mechanical Division | 22.6 | 0 | 0 | 0 | 22.6 | 22.6 | 0 | 0 | 0 | 22.6 | 59.64 | 40
661 | BANKURA | SM/10879 | MINI PIPED WATER SUPPLY SCHEME FOR BENAGERIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012436 | 40020023 | New | SVS | GO2223003669PH | 30/05/2022 | 33.1 | 0 | 33.1 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18 | 0 | 0 | 0 | 18 | 54.38 | 75
662 | BANKURA | SM/10958 | MINI PIPED WATER SUPPLY SCHEME FOR BENAKANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012490 | 40026099 | New | SVS | GO2223003664PH | 30/05/2022 | 36.21 | 0 | 36.21 | Bankura Division | Bankura Mechanical Division | 20.6 | 0 | 0 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 20.6 | 56.89 | 30
663 | BANKURA | SM/10964 | MINI PIPED WATER SUPPLY SCHEME FOR BENATHOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME+B20:B21 | TSM/012496 | 40026139 | New | SVS | GO2223003664PH | 30/05/2022 | 43.45 | 0 | 43.45 | Bankura Division | Bankura Mechanical Division | 32 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 32 | 73.65 | 75
664 | BANKURA | SM/13266 | MINI PIPED WATER SUPPLY SCHEME FOR BERA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012190 | 40028707 | New | SVS | GO2223003658PH | 30/05/2022 | 43.58 | 0 | 43.58 | Bankura Division | Bankura Mechanical Division | 25.72 | 0 | 0 | 0 | 25.72 | 25.72 | 0 | 0 | 0 | 25.72 | 59.01 | 75
665 | BANKURA | SM/11131 | MINI PIPED WATER SUPPLY SCHEME FOR BERUABAID VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012319 | 40066000 | New | SVS | GO2223003670PH | 30/05/2022 | 43.25 | 0 | 43.25 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
666 | BANKURA | SM/10965 | MINI PIPED WATER SUPPLY SCHEME FOR BHABANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012497 | 40026142 | New | SVS | GO2223003664PH | 30/05/2022 | 41.37 | 0 | 41.37 | Bankura Division | Bankura Mechanical Division | 19 | 0 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | 19 | 45.92 | 50
667 | BANKURA | SM/11024 | MINI PIPED WATER SUPPLY SCHEME FOR BHADLI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012287 | 40020098 | New | SVS | GO2223003671PH | 30/05/2022 | 42.47 | 0 | 42.47 | Bankura Division | Bankura Mechanical Division | 20.72 | 0 | 0 | 0 | 20.72 | 20.72 | 0 | 0 | 0 | 20.72 | 48.78 | 50
668 | BANKURA | SM/11065 | MINI PIPED WATER SUPPLY SCHEME FOR BHADULDOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012328 | 40027080 | New | SVS | GO2223003663PH | 30/05/2022 | 37.66 | 0 | 37.66 | Bankura Division | Bankura Mechanical Division | 19.62 | 0 | 0 | 0 | 19.62 | 19.5 | 0 | 0 | 0 | 19.5 | 51.78 | 50
669 | BANKURA | SM/10948 | MINI PIPED WATER SUPPLY SCHEME FOR BHALAIDIHA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012480 | 40026010 | New | SVS | GO2223003664PH | 30/05/2022 | 31.76 | 0 | 31.76 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 57.05 | 50
670 | BANKURA | SM/11077 | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012340 | 40065419 | New | SVS | GO2223003663PH | 30/05/2022 | 36.71 | 0 | 36.71 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
671 | BANKURA | SM/10935 | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKATHOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012392 | 40026150 | New | SVS | GO2223003674PH | 30/05/2022 | 41.84 | 0 | 41.84 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
672 | BANKURA | SM/10891 | MINI PIPED WATER SUPPLY SCHEME FOR BHALUKBASA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012448 | 40020086 | New | SVS | GO2223003669PH | 30/05/2022 | 37.43 | 0 | 37.43 | Bankura Division | Bankura Mechanical Division | 22.5 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 22.5 | 60.11 | 70
673 | BANKURA | SM/11054 | MINI PIPED WATER SUPPLY SCHEME FOR BHANDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012373 | 40027377 | New | SVS | GO2223003657PH | 30/05/2022 | 40.52 | 0 | 40.52 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 49.36 | 60
674 | BANKURA | SM/11041 | MINI PIPED WATER SUPPLY SCHEME FOR BHEDUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012360 | 40027293 | New | SVS | GO2223003657PH | 30/05/2022 | 41.11 | 0 | 41.11 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 48.65 | 50
675 | BANKURA | SM/10846 | MINI PIPED WATER SUPPLY SCHEME FOR BHIRINGI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012403 | 40022102 | New | SVS | GO2223003673PH | 30/05/2022 | 40.52 | 0 | 40.52 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.3 | 75
676 | BANKURA | SM/10959 | MINI PIPED WATER SUPPLY SCHEME FOR BHULUI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012491 | 40026102 | New | SVS | GO2223003664PH | 30/05/2022 | 36.71 | 0 | 36.71 | Bankura Division | Bankura Mechanical Division | 20.5 | 0 | 0 | 0 | 20.5 | 20.5 | 0 | 0 | 0 | 20.5 | 55.84 | 30
677 | BANKURA | SM/10865 | MINI PIPED WATER SUPPLY SCHEME FOR BINODPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012422 | 40026297 | New | SVS | GO2223003673PH | 30/05/2022 | 31.49 | 0 | 31.49 | Bankura Division | Bankura Mechanical Division | 25.62 | 0 | 0 | 0 | 25.62 | 25.5 | 0 | 0 | 0 | 25.5 | 80.98 | 70
678 | BANKURA | SM/11111 | MINI PIPED WATER SUPPLY SCHEME FOR BIRBHANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012299 | 40026919 | New | SVS | GO2223003670PH | 30/05/2022 | 37.66 | 0 | 37.66 | Bankura Division | Bankura Mechanical Division | 25.11 | 0 | 0 | 0 | 25.11 | 25.11 | 0 | 0 | 0 | 25.11 | 66.69 | 40
679 | BANKURA | SM/13267 | MINI PIPED WATER SUPPLY SCHEME FOR BIRUDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012194 | 40028708 | New | SVS | GO2223003658PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 18.06 | 0 | 0 | 0 | 18.06 | 18.06 | 0 | 0 | 0 | 18.06 | 49.54 | 40
680 | BANKURA | SM/10895 | MINI PIPED WATER SUPPLY SCHEME FOR BOTKULA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012452 | 40020099 | New | SVS | GO2223003669PH | 30/05/2022 | 42.47 | 0 | 42.47 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 66.2 | 70
681 | BANKURA | SM/11055 | MINI PIPED WATER SUPPLY SCHEME FOR BRAHMANDHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012374 | 40027386 | New | SVS | GO2223003657PH | 30/05/2022 | 41.6 | 0 | 41.6 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
682 | BANKURA | SM/10930 | MINI PIPED WATER SUPPLY SCHEME FOR BRINDABANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012387 | 40026052 | New | SVS | GO2223003674PH | 30/05/2022 | 32.83 | 0 | 32.83 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
683 | BANKURA | SM/11026 | MINI PIPED WATER SUPPLY SCHEME FOR BUCHI BURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012289 | 40065693 | New | SVS | GO2223003671PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 15 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 40.04 | 25
684 | BANKURA | SM/11117 | MINI PIPED WATER SUPPLY SCHEME FOR BURISAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012305 | 40027184 | New | SVS | GO2223003670PH | 30/05/2022 | 39.98 | 0 | 39.98 | Bankura Division | Bankura Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 45.31 | 70
685 | BANKURA | SM/10857 | MINI PIPED WATER SUPPLY SCHEME FOR CHAITANDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012414 | 40026276 | New | SVS | GO2223003673PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 59.45 | 75
686 | BANKURA | SM/13258 | MINI PIPED WATER SUPPLY SCHEME FOR CHAK KRISHNASINGHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012154 | 40066077 | New | SVS | GO2223003658PH | 30/05/2022 | 42.51 | 0 | 42.51 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
687 | BANKURA | SM/10921 | MINI PIPED WATER SUPPLY SCHEME FOR CHAK RANGA METYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012378 | 40025955 | New | SVS | GO2223003674PH | 30/05/2022 | 32.03 | 0 | 32.03 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
688 | BANKURA | SM/11058 | MINI PIPED WATER SUPPLY SCHEME FOR CHAKJAMBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012377 | 40027402 | New | SVS | GO2223003657PH | 30/05/2022 | 41.14 | 0 | 41.14 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
689 | BANKURA | SM/10934 | MINI PIPED WATER SUPPLY SCHEME FOR CHANDIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012391 | 40026075 | New | SVS | GO2223003674PH | 30/05/2022 | 34.46 | 0 | 34.46 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.35 | 75
690 | BANKURA | SM/10993 | MINI PIPED WATER SUPPLY SCHEME FOR CHANDRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012475 | 40020173 | New | SVS | GO2223003672PH | 30/05/2022 | 43.84 | 0 | 43.84 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 70.98 | 70
691 | BANKURA | SM/10847 | MINI PIPED WATER SUPPLY SCHEME FOR CHARADIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012404 | 40022106 | New | SVS | GO2223003673PH | 30/05/2022 | 41.3 | 0 | 41.3 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
692 | BANKURA | SM/11010 | MINI PIPED WATER SUPPLY SCHEME FOR CHATURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012273 | 40020031 | New | SVS | GO2223003671PH | 30/05/2022 | 43.84 | 0 | 43.84 | Bankura Division | Bankura Mechanical Division | 30.24 | 0 | 0 | 0 | 30.24 | 30.24 | 0 | 0 | 0 | 30.24 | 68.97 | 75
693 | BANKURA | SM/13268 | MINI PIPED WATER SUPPLY SCHEME FOR CHATURIKALAPATHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012195 | 40028709 | New | SVS | GO2223003658PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 68.57 | 75
694 | BANKURA | SM/11046 | MINI PIPED WATER SUPPLY SCHEME FOR CHENCHURYA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012365 | 40027323 | New | SVS | GO2223003657PH | 30/05/2022 | 37.66 | 0 | 37.66 | Bankura Division | Bankura Mechanical Division | 17.12 | 0 | 0 | 0 | 17.12 | 17 | 0 | 0 | 0 | 17 | 45.14 | 50
695 | BANKURA | SM/10984 | MINI PIPED WATER SUPPLY SCHEME FOR CHHATRABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012466 | 40020148 | New | SVS | GO2223003672PH | 30/05/2022 | 40.91 | 0 | 40.91 | Bankura Division | Bankura Mechanical Division | 22.62 | 0 | 0 | 0 | 22.62 | 22.62 | 0 | 0 | 0 | 22.62 | 55.29 | 45
696 | BANKURA | SM/10882 | MINI PIPED WATER SUPPLY SCHEME FOR CHHELEBAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012439 | 40020057 | New | SVS | GO2223003669PH | 30/05/2022 | 34.21 | 0 | 34.21 | Bankura Division | Bankura Mechanical Division | 26.62 | 0 | 0 | 0 | 26.62 | 26.62 | 0 | 0 | 0 | 26.62 | 77.82 | 70
697 | BANKURA | SM/10932 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOLA BAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012389 | 40026066 | New | SVS | GO2223003674PH | 30/05/2022 | 34.46 | 0 | 34.46 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
698 | BANKURA | SM/11133 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA GOALDANGRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012321 | 40065984 | New | SVS | GO2223003670PH | 30/05/2022 | 41.89 | 0 | 41.89 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
699 | BANKURA | SM/10944 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA KUMIRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012401 | 40026180 | New | SVS | GO2223003674PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
700 | BANKURA | SM/10933 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012390 | 40026073 | New | SVS | GO2223003674PH | 30/05/2022 | 34.96 | 0 | 34.96 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
701 | BANKURA | SM/10866 | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTAKEEHANDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012423 | 40026301 | New | SVS | GO2223003673PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 75.06 | 70
702 | BANKURA | SM/10910 | MINI PIPED WATER SUPPLY SCHEME FOR CHINGRAGOALASOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012152 | 40066059 | New | SVS | GO2223003656PH | 30/05/2022 | 32.83 | 0 | 32.83 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 18 | 54.82 | 25
703 | BANKURA | SM/10916 | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012164 | 40032332 | New | SVS | GO2223003656PH | 30/05/2022 | 43.84 | 0 | 43.84 | Bankura Division | Bankura Mechanical Division | 22.72 | 0 | 0 | 0 | 22.72 | 22.72 | 0 | 0 | 0 | 22.72 | 51.82 | 45
704 | BANKURA | SM/13263 | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012176 | 40066006 | New | SVS | GO2223003658PH | 30/05/2022 | 40.26 | 0 | 40.26 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
705 | BANKURA | SM/11042 | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012361 | 40027296 | New | SVS | GO2223003657PH | 30/05/2022 | 39.29 | 0 | 39.29 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
706 | BANKURA | SM/10886 | MINI PIPED WATER SUPPLY SCHEME FOR CHURAMANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012443 | 40020065 | New | SVS | GO2223003669PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
707 | BANKURA | SM/10994 | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHIN KAMALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012476 | 40020177 | New | SVS | GO2223003672PH | 30/05/2022 | 37.43 | 0 | 37.43 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 67.11 | 75
708 | BANKURA | SM/10862 | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHINASANBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012419 | 40026287 | New | SVS | GO2223003673PH | 30/05/2022 | 34.46 | 0 | 34.46 | Bankura Division | Bankura Mechanical Division | 19.5 | 0 | 0 | 0 | 19.5 | 19.5 | 0 | 0 | 0 | 19.5 | 56.59 | 65
709 | BANKURA | SM/10873 | MINI PIPED WATER SUPPLY SCHEME FOR DAKSHINKENDBANA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012430 | 40019998 | New | SVS | GO2223003669PH | 30/05/2022 | 30.68 | 0 | 30.68 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 65.57 | 80
710 | BANKURA | SM/13257 | MINI PIPED WATER SUPPLY SCHEME FOR DALI MAHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012150 | 40066062 | New | SVS | GO2223003658PH | 30/05/2022 | 36.7 | 0 | 36.7 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
711 | BANKURA | SM/10918 | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012168 | 40032315 | New | SVS | GO2223003656PH | 30/05/2022 | 43.65 | 0 | 43.65 | Bankura Division | Bankura Mechanical Division | 30.5 | 0 | 0 | 0 | 30.5 | 30.5 | 0 | 0 | 0 | 30.5 | 69.88 | 56
712 | BANKURA | SM/10963 | MINI PIPED WATER SUPPLY SCHEME FOR DAMODAR MOHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012495 | 40026111 | New | SVS | GO2223003664PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 66.74 | 75
713 | BANKURA | SM/10985 | MINI PIPED WATER SUPPLY SCHEME FOR DAMODARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012467 | 40020154 | New | SVS | GO2223003672PH | 30/05/2022 | 40.52 | 0 | 40.52 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 52.12 | 80
714 | BANKURA | SM/10956 | MINI PIPED WATER SUPPLY SCHEME FOR DAMODARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012488 | 40026074 | New | SVS | GO2223003664PH | 30/05/2022 | 38.13 | 0 | 38.13 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 65.89 | 77
715 | BANKURA | SM/10936 | MINI PIPED WATER SUPPLY SCHEME FOR DAMRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012393 | 40026151 | New | SVS | GO2223003674PH | 30/05/2022 | 43.84 | 0 | 43.84 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.27 | 75
716 | BANKURA | SM/11025 | MINI PIPED WATER SUPPLY SCHEME FOR DANGARSAI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012288 | 40065697 | New | SVS | GO2223003671PH | 30/05/2022 | 44.43 | 0 | 44.43 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30.12 | 0 | 0 | 0 | 30.12 | 67.8 | 50
717 | BANKURA | SM/10986 | MINI PIPED WATER SUPPLY SCHEME FOR DEUL BHIRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012468 | 40020158 | New | SVS | GO2223003672PH | 30/05/2022 | 43.06 | 0 | 43.06 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 72.27 | 70
718 | BANKURA | SM/10961 | MINI PIPED WATER SUPPLY SCHEME FOR DHANDORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012493 | 40026107 | New | SVS | GO2223003664PH | 30/05/2022 | 32.3 | 0 | 32.3 | Bankura Division | Bankura Mechanical Division | 22.6 | 0 | 0 | 0 | 22.6 | 22.6 | 0 | 0 | 0 | 22.6 | 69.98 | 50
719 | BANKURA | SM/11112 | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012300 | 40026953 | New | SVS | GO2223003670PH | 30/05/2022 | 37.2 | 0 | 37.2 | Bankura Division | Bankura Mechanical Division | 25.11 | 0 | 0 | 0 | 25.11 | 25.11 | 0 | 0 | 0 | 25.11 | 67.52 | 55
720 | BANKURA | SM/11130 | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012318 | 40066003 | New | SVS | GO2223003670PH | 30/05/2022 | 43.06 | 0 | 43.06 | Bankura Division | Bankura Mechanical Division | 15 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 34.84 | 25
721 | BANKURA | SM/10880 | MINI PIPED WATER SUPPLY SCHEME FOR DHOBAGERE VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012437 | 40020035 | New | SVS | GO2223003669PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 12.5 | 0 | 0 | 0 | 12.5 | 12.5 | 0 | 0 | 0 | 12.5 | 34.28 | 25
722 | BANKURA | SM/11039 | MINI PIPED WATER SUPPLY SCHEME FOR DHUAKAKI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012358 | 40027292 | New | SVS | GO2223003657PH | 30/05/2022 | 41.3 | 0 | 41.3 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
723 | BANKURA | SM/11203 | MINI PIPED WATER SUPPLY SCHEME FOR DOMAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012351 | 40027456 | New | SVS | GO2223003662PH | 30/05/2022 | 39.29 | 0 | 39.29 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 25
724 | BANKURA | SM/11072 | MINI PIPED WATER SUPPLY SCHEME FOR DUDHIA DOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012335 | 40065451 | New | SVS | GO2223003663PH | 30/05/2022 | 40.44 | 0 | 40.44 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
725 | BANKURA | SM/11199 | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012347 | 40027431 | New | SVS | GO2223003662PH | 30/05/2022 | 43.06 | 0 | 43.06 | Bankura Division | Bankura Mechanical Division | 21.24 | 0 | 0 | 0 | 21.24 | 21.12 | 0 | 0 | 0 | 21.12 | 49.05 | 50
726 | BANKURA | SM/10892 | MINI PIPED WATER SUPPLY SCHEME FOR GANDLUGARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012449 | 40020091 | New | SVS | GO2223003669PH | 30/05/2022 | 44.04 | 0 | 44.04 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 70.67 | 70
727 | BANKURA | SM/10975 | MINI PIPED WATER SUPPLY SCHEME FOR GANGPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012457 | 40020107 | New | SVS | GO2223003672PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 66.61 | 78
728 | BANKURA | SM/11050 | MINI PIPED WATER SUPPLY SCHEME FOR GHAGAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012369 | 40027342 | New | SVS | GO2223003657PH | 30/05/2022 | 40.72 | 0 | 40.72 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25 | 0 | 0 | 0 | 25 | 61.4 | 62
729 | BANKURA | SM/11031 | MINI PIPED WATER SUPPLY SCHEME FOR GHOLKURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012294 | 40066036 | New | SVS | GO2223003671PH | 30/05/2022 | 36.71 | 0 | 36.71 | Bankura Division | Bankura Mechanical Division | 16.11 | 0 | 0 | 0 | 16.11 | 16.11 | 0 | 0 | 0 | 16.11 | 43.9 | 40
730 | BANKURA | SM/10903 | MINI PIPED WATER SUPPLY SCHEME FOR GHUGUJAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012131 | 40019330 | New | SVS | GO2223003656PH | 30/05/2022 | 37.43 | 0 | 37.43 | Bankura Division | Bankura Mechanical Division | 20.61 | 0 | 0 | 0 | 20.61 | 20.5 | 0 | 0 | 0 | 20.5 | 54.77 | 80
731 | BANKURA | SM/10883 | MINI PIPED WATER SUPPLY SCHEME FOR GHUTIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012440 | 40020059 | New | SVS | GO2223003669PH | 30/05/2022 | 34.45 | 0 | 34.45 | Bankura Division | Bankura Mechanical Division | 21 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 21 | 60.97 | 75
732 | BANKURA | SM/10978 | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012460 | 40020110 | New | SVS | GO2223003672PH | 30/05/2022 | 39.98 | 0 | 39.98 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 77.83 | 40
733 | BANKURA | SM/11040 | MINI PIPED WATER SUPPLY SCHEME FOR GOALKPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012359 | 40027295 | New | SVS | GO2223003657PH | 30/05/2022 | 40.91 | 0 | 40.91 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18 | 0 | 0 | 0 | 18 | 44 | 50
734 | BANKURA | SM/11118 | MINI PIPED WATER SUPPLY SCHEME FOR GOALMURI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012306 | 40027329 | New | SVS | GO2223003670PH | 30/05/2022 | 38.36 | 0 | 38.36 | Bankura Division | Bankura Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 47.23 | 70
735 | BANKURA | SM/10922 | MINI PIPED WATER SUPPLY SCHEME FOR GOBINDAPURBAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012379 | 40025963 | New | SVS | GO2223003674PH | 30/05/2022 | 31.49 | 0 | 31.49 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
736 | BANKURA | SM/11124 | MINI PIPED WATER SUPPLY SCHEME FOR GORADIHI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012312 | 40027376 | New | SVS | GO2223003670PH | 30/05/2022 | 31.22 | 0 | 31.22 | Bankura Division | Bankura Mechanical Division | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 10 | 32.03 | 25
737 | BANKURA | SM/11011 | MINI PIPED WATER SUPPLY SCHEME FOR GUMKIHATA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012274 | 40020039 | New | SVS | GO2223003671PH | 30/05/2022 | 40.91 | 0 | 40.91 | Bankura Division | Bankura Mechanical Division | 12.5 | 0 | 0 | 0 | 12.5 | 12.5 | 0 | 0 | 0 | 12.5 | 30.55 | 25
738 | BANKURA | SM/10919 | MINI PIPED WATER SUPPLY SCHEME FOR HARIDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012171 | 40032342 | New | SVS | GO2223003656PH | 30/05/2022 | 39.29 | 0 | 39.29 | Bankura Division | Bankura Mechanical Division | 30.63 | 0 | 0 | 0 | 30.63 | 30.63 | 0 | 0 | 0 | 30.63 | 77.97 | 61
739 | BANKURA | SM/10867 | MINI PIPED WATER SUPPLY SCHEME FOR HARISHCHANDRAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012424 | 40026307 | New | SVS | GO2223003673PH | 30/05/2022 | 33.91 | 0 | 33.91 | Bankura Division | Bankura Mechanical Division | 20 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 20 | 58.98 | 75
740 | BANKURA | SM/13254 | MINI PIPED WATER SUPPLY SCHEME FOR HATIBAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012270 | 40066031 | New | SVS | GO2223003658PH | 30/05/2022 | 33.92 | 0 | 33.92 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
741 | BANKURA | SM/10966 | MINI PIPED WATER SUPPLY SCHEME FOR INDARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012498 | 40026149 | New | SVS | GO2223003664PH | 30/05/2022 | 37.89 | 0 | 37.89 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 65.98 | 50
742 | BANKURA | SM/13275 | MINI PIPED WATER SUPPLY SCHEME FOR INDRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012225 | 40066082 | New | SVS | GO2223003658PH | 30/05/2022 | 37.43 | 0 | 37.43 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
743 | BANKURA | SM/10941 | MINI PIPED WATER SUPPLY SCHEME FOR ITA DANGRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012398 | 40026168 | New | SVS | GO2223003674PH | 30/05/2022 | 42.07 | 0 | 42.07 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.28 | 75
744 | BANKURA | SM/11020 | MINI PIPED WATER SUPPLY SCHEME FOR JAGANNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012283 | 40020089 | New | SVS | GO2223003671PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 25.72 | 0 | 0 | 0 | 25.72 | 25.72 | 0 | 0 | 0 | 25.72 | 68.2 | 75
745 | BANKURA | SM/10887 | MINI PIPED WATER SUPPLY SCHEME FOR JAGATDEULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012444 | 40020069 | New | SVS | GO2223003669PH | 30/05/2022 | 41.3 | 0 | 41.3 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 68.08 | 70
746 | BANKURA | SM/10874 | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012431 | 40020004 | New | SVS | GO2223003669PH | 30/05/2022 | 33.91 | 0 | 33.91 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 62.28 | 80
747 | BANKURA | SM/11012 | MINI PIPED WATER SUPPLY SCHEME FOR JALJURA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012275 | 40020068 | New | SVS | GO2223003671PH | 30/05/2022 | 38.13 | 0 | 38.13 | Bankura Division | Bankura Mechanical Division | 12.5 | 0 | 0 | 0 | 12.5 | 12.5 | 0 | 0 | 0 | 12.5 | 32.79 | 25
748 | BANKURA | SM/10904 | MINI PIPED WATER SUPPLY SCHEME FOR JAMARADIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012135 | 40019333 | New | SVS | GO2223003656PH | 30/05/2022 | 43.06 | 0 | 43.06 | Bankura Division | Bankura Mechanical Division | 30.11 | 0 | 0 | 0 | 30.11 | 30 | 0 | 0 | 0 | 30 | 69.67 | 85
749 | BANKURA | SM/11200 | MINI PIPED WATER SUPPLY SCHEME FOR JAMBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012348 | 40027435 | New | SVS | GO2223003662PH | 30/05/2022 | 40.91 | 0 | 40.91 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
750 | BANKURA | SM/13264 | MINI PIPED WATER SUPPLY SCHEME FOR JAMRA MADHABPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012182 | 40066021 | New | SVS | GO2223003658PH | 30/05/2022 | 43.19 | 0 | 43.19 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
751 | BANKURA | SM/10854 | MINI PIPED WATER SUPPLY SCHEME FOR JAMSHALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012411 | 40026263 | New | SVS | GO2223003673PH | 30/05/2022 | 41.6 | 0 | 41.6 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
752 | BANKURA | SM/11021 | MINI PIPED WATER SUPPLY SCHEME FOR JARKA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012284 | 40020092 | New | SVS | GO2223003671PH | 30/05/2022 | 37.89 | 0 | 37.89 | Bankura Division | Bankura Mechanical Division | 20.72 | 0 | 0 | 0 | 20.72 | 20.72 | 0 | 0 | 0 | 20.72 | 54.68 | 50
753 | BANKURA | SM/11047 | MINI PIPED WATER SUPPLY SCHEME FOR JASHODANANDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012366 | 40027326 | New | SVS | GO2223003657PH | 30/05/2022 | 45.01 | 0 | 45.01 | Bankura Division | Bankura Mechanical Division | 10.12 | 0 | 0 | 0 | 10.12 | 10 | 0 | 0 | 0 | 10 | 22.22 | 50
754 | BANKURA | SM/11121 | MINI PIPED WATER SUPPLY SCHEME FOR JAVI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012309 | 40027351 | New | SVS | GO2223003670PH | 30/05/2022 | 43.65 | 0 | 43.65 | Bankura Division | Bankura Mechanical Division | 25.11 | 0 | 0 | 0 | 25.11 | 25.11 | 0 | 0 | 0 | 25.11 | 57.54 | 42
755 | BANKURA | SM/11081 | MINI PIPED WATER SUPPLY SCHEME FOR JEMUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012344 | 40065421 | New | SVS | GO2223003663PH | 30/05/2022 | 33.37 | 0 | 33.37 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 50
756 | BANKURA | SM/11078 | MINI PIPED WATER SUPPLY SCHEME FOR JIAKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012341 | 0 | New | SVS | GO2223003663PH | 30/05/2022 | 33.91 | 0 | 33.91 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
757 | BANKURA | SM/10896 | MINI PIPED WATER SUPPLY SCHEME FOR JIRABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012073 | 40019308 | New | SVS | GO2223003656PH | 30/05/2022 | 32.83 | 0 | 32.83 | Bankura Division | Bankura Mechanical Division | 30.49 | 0 | 0 | 0 | 30.49 | 30.38 | 0 | 0 | 0 | 30.38 | 92.52 | 85
758 | BANKURA | SM/10863 | MINI PIPED WATER SUPPLY SCHEME FOR KALACHANDPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012420 | 40026289 | New | SVS | GO2223003673PH | 30/05/2022 | 34.18 | 0 | 34.18 | Bankura Division | Bankura Mechanical Division | 20.2 | 0 | 0 | 0 | 20.2 | 20.2 | 0 | 0 | 0 | 20.2 | 59.11 | 55
759 | BANKURA | SM/11013 | MINI PIPED WATER SUPPLY SCHEME FOR KALAPATHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012276 | 40020070 | New | SVS | GO2223003671PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 30.72 | 0 | 0 | 0 | 30.72 | 30.72 | 0 | 0 | 0 | 30.72 | 69.45 | 75
760 | BANKURA | SM/11022 | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012285 | 40020094 | New | SVS | GO2223003671PH | 30/05/2022 | 44.43 | 0 | 44.43 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 56.54 | 75
761 | BANKURA | SM/10976 | MINI PIPED WATER SUPPLY SCHEME FOR KALIAPATHAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012458 | 40020108 | New | SVS | GO2223003672PH | 30/05/2022 | 41.14 | 0 | 41.14 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 68.35 | 70
762 | BANKURA | SM/10979 | MINI PIPED WATER SUPPLY SCHEME FOR KALIPAHARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012461 | 40020111 | New | SVS | GO2223003672PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21 | 0 | 0 | 0 | 21 | 55.69 | 85
763 | BANKURA | SM/10937 | MINI PIPED WATER SUPPLY SCHEME FOR KALIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012394 | 40026153 | New | SVS | GO2223003674PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.27 | 75
764 | BANKURA | SM/13255 | MINI PIPED WATER SUPPLY SCHEME FOR KALLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012139 | 40020072 | New | SVS | GO2223003658PH | 30/05/2022 | 32.57 | 0 | 32.57 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
765 | BANKURA | SM/10905 | MINI PIPED WATER SUPPLY SCHEME FOR KALUDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012138 | 40019336 | New | SVS | GO2223003656PH | 30/05/2022 | 39.52 | 0 | 39.52 | Bankura Division | Bankura Mechanical Division | 30.62 | 0 | 0 | 0 | 30.62 | 30.62 | 0 | 0 | 0 | 30.62 | 77.48 | 80
766 | BANKURA | SM/13269 | MINI PIPED WATER SUPPLY SCHEME FOR KALYANSAER VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012197 | 40028710 | New | SVS | GO2223003658PH | 30/05/2022 | 35.71 | 0 | 35.71 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 70.34 | 75
767 | BANKURA | SM/10893 | MINI PIPED WATER SUPPLY SCHEME FOR KAMLABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012450 | 40020093 | New | SVS | GO2223003669PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 22.5 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 22.5 | 50.42 | 70
768 | BANKURA | SM/11201 | MINI PIPED WATER SUPPLY SCHEME FOR KANAIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012349 | 40027440 | New | SVS | GO2223003662PH | 30/05/2022 | 39.05 | 0 | 39.05 | Bankura Division | Bankura Mechanical Division | 10.12 | 0 | 0 | 0 | 10.12 | 10 | 0 | 0 | 0 | 10 | 25.61 | 30
769 | BANKURA | SM/11066 | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012329 | 40027129 | New | SVS | GO2223003663PH | 30/05/2022 | 41.37 | 0 | 41.37 | Bankura Division | Bankura Mechanical Division | 12.62 | 0 | 0 | 0 | 12.62 | 12.5 | 0 | 0 | 0 | 12.5 | 30.21 | 25
770 | BANKURA | SM/10902 | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012118 | 40019323 | New | SVS | GO2223003656PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 20.62 | 0 | 0 | 0 | 20.62 | 20.62 | 0 | 0 | 0 | 20.62 | 61.29 | 85
771 | BANKURA | SM/10987 | MINI PIPED WATER SUPPLY SCHEME FOR KANTAKULI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012469 | 40020161 | New | SVS | GO2223003672PH | 30/05/2022 | 39.05 | 0 | 39.05 | Bankura Division | Bankura Mechanical Division | 22.5 | 0 | 0 | 0 | 22.5 | 22.5 | 0 | 0 | 0 | 22.5 | 57.61 | 70
772 | BANKURA | SM/11014 | MINI PIPED WATER SUPPLY SCHEME FOR KARAMARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012277 | 40020072 | New | SVS | GO2223003671PH | 30/05/2022 | 39.29 | 0 | 39.29 | Bankura Division | Bankura Mechanical Division | 27.72 | 0 | 0 | 0 | 27.72 | 27.72 | 0 | 0 | 0 | 27.72 | 70.56 | 75
773 | BANKURA | SM/10913 | MINI PIPED WATER SUPPLY SCHEME FOR KARRASOL VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012157 | 40032034 | New | SVS | GO2223003656PH | 30/05/2022 | 32.3 | 0 | 32.3 | Bankura Division | Bankura Mechanical Division | 25.5 | 0 | 0 | 0 | 25.5 | 25.5 | 0 | 0 | 0 | 25.5 | 78.96 | 57
774 | BANKURA | SM/10950 | MINI PIPED WATER SUPPLY SCHEME FOR KATAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012482 | 40026013 | New | SVS | GO2223003664PH | 30/05/2022 | 42.08 | 0 | 42.08 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 43.05 | 55
775 | BANKURA | SM/11109 | MINI PIPED WATER SUPPLY SCHEME FOR KAWA TANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012297 | 40026882 | New | SVS | GO2223003670PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 12.71 | 0 | 0 | 0 | 12.71 | 12.71 | 0 | 0 | 0 | 12.71 | 33.94 | 25
776 | BANKURA | SM/10938 | MINI PIPED WATER SUPPLY SCHEME FOR KELAI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012395 | 40026158 | New | SVS | GO2223003674PH | 30/05/2022 | 45.01 | 0 | 45.01 | Bankura Division | Bankura Mechanical Division | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 75
777 | BANKURA | SM/10894 | MINI PIPED WATER SUPPLY SCHEME FOR KELERA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012451 | 40020096 | New | SVS | GO2223003669PH | 30/05/2022 | 42.76 | 0 | 42.76 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 65.75 | 40
778 | BANKURA | SM/10864 | MINI PIPED WATER SUPPLY SCHEME FOR KENDBANADHAGRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012421 | 40026292 | New | SVS | GO2223003673PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 25.62 | 0 | 0 | 0 | 25.62 | 25.62 | 0 | 0 | 0 | 25.62 | 76.16 | 70
779 | BANKURA | SM/10967 | MINI PIPED WATER SUPPLY SCHEME FOR KENDUT VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012499 | 40026163 | New | SVS | GO2223003664PH | 30/05/2022 | 44.43 | 0 | 44.43 | Bankura Division | Bankura Mechanical Division | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 10 | 22.51 | 25
780 | BANKURA | SM/10939 | MINI PIPED WATER SUPPLY SCHEME FOR KENTHALYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012396 | 40026160 | New | SVS | GO2223003674PH | 30/05/2022 | 41.6 | 0 | 41.6 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.29 | 75
781 | BANKURA | SM/10920 | MINI PIPED WATER SUPPLY SCHEME FOR KHAERBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012173 | 40032347 | New | SVS | GO2223003656PH | 30/05/2022 | 41.6 | 0 | 41.6 | Bankura Division | Bankura Mechanical Division | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 0 | 0 | 0 | 12.6 | 30.28 | 25
782 | BANKURA | SM/10968 | MINI PIPED WATER SUPPLY SCHEME FOR KHAERBANI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012500 | 40026167 | New | SVS | GO2223003664PH | 30/05/2022 | 38.13 | 0 | 38.13 | Bankura Division | Bankura Mechanical Division | 22.6 | 0 | 0 | 0 | 22.6 | 22.6 | 0 | 0 | 0 | 22.6 | 59.28 | 50
783 | BANKURA | SM/10855 | MINI PIPED WATER SUPPLY SCHEME FOR KHAJURI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012412 | 40026267 | New | SVS | GO2223003673PH | 30/05/2022 | 43.45 | 0 | 43.45 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
784 | BANKURA | SM/10951 | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012483 | 40026014 | New | SVS | GO2223003664PH | 30/05/2022 | 42.07 | 0 | 42.07 | Bankura Division | Bankura Mechanical Division | 22.62 | 0 | 0 | 0 | 22.62 | 22.62 | 0 | 0 | 0 | 22.62 | 53.77 | 50
785 | BANKURA | SM/11015 | MINI PIPED WATER SUPPLY SCHEME FOR KHALPARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012278 | 40020075 | New | SVS | GO2223003671PH | 30/05/2022 | 40.21 | 0 | 40.21 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 18 | 44.76 | 25
786 | BANKURA | SM/10869 | MINI PIPED WATER SUPPLY SCHEME FOR KHAPKATA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012426 | 40026320 | New | SVS | GO2223003673PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 15 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 41.14 | 55
787 | BANKURA | SM/10888 | MINI PIPED WATER SUPPLY SCHEME FOR KHARAKANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012445 | 40020073 | New | SVS | GO2223003669PH | 30/05/2022 | 37.2 | 0 | 37.2 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
788 | BANKURA | SM/11119 | MINI PIPED WATER SUPPLY SCHEME FOR KHATA-AM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012307 | 40027337 | New | SVS | GO2223003670PH | 30/05/2022 | 40.72 | 0 | 40.72 | Bankura Division | Bankura Mechanical Division | 25.11 | 0 | 0 | 0 | 25.11 | 25.11 | 0 | 0 | 0 | 25.11 | 61.68 | 40
789 | BANKURA | SM/13270 | MINI PIPED WATER SUPPLY SCHEME FOR KHATANGA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012199 | 40028711 | New | SVS | GO2223003658PH | 30/05/2022 | 32.83 | 0 | 32.83 | Bankura Division | Bankura Mechanical Division | 23 | 0 | 0 | 0 | 23 | 23 | 0 | 0 | 0 | 23 | 70.05 | 40
790 | BANKURA | SM/11016 | MINI PIPED WATER SUPPLY SCHEME FOR KHEJURBEDIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012279 | 40020078 | New | SVS | GO2223003671PH | 30/05/2022 | 38.36 | 0 | 38.36 | Bankura Division | Bankura Mechanical Division | 22.62 | 0 | 0 | 0 | 22.62 | 22.62 | 0 | 0 | 0 | 22.62 | 58.97 | 75
791 | BANKURA | SM/11082 | MINI PIPED WATER SUPPLY SCHEME FOR KOLSULI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012345 | 40065450 | New | SVS | GO2223003663PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 25
792 | BANKURA | SM/11064 | MINI PIPED WATER SUPPLY SCHEME FOR KORKHI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012327 | 40065978 | New | SVS | GO2223003663PH | 30/05/2022 | 37.43 | 0 | 37.43 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
793 | BANKURA | SM/10848 | MINI PIPED WATER SUPPLY SCHEME FOR KOT MADAN MOHANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012405 | 40022107 | New | SVS | GO2223003673PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
794 | BANKURA | SM/11060 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNABATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012323 | 40026888 | New | SVS | GO2223003663PH | 30/05/2022 | 31.76 | 0 | 31.76 | Bankura Division | Bankura Mechanical Division | 20.5 | 0 | 0 | 0 | 20.5 | 20.5 | 0 | 0 | 0 | 20.5 | 64.55 | 50
795 | BANKURA | SM/10907 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012143 | 40019340 | New | SVS | GO2223003656PH | 30/05/2022 | 38.59 | 0 | 38.59 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28.12 | 0 | 0 | 0 | 28.12 | 72.87 | 85
796 | BANKURA | SM/10988 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012470 | 40020163 | New | SVS | GO2223003672PH | 30/05/2022 | 41.37 | 0 | 41.37 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 48.34 | 40
797 | BANKURA | SM/11122 | MINI PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012310 | 40065975 | New | SVS | GO2223003670PH | 30/05/2022 | 36.96 | 0 | 36.96 | Bankura Division | Bankura Mechanical Division | 10.12 | 0 | 0 | 0 | 10.12 | 10.12 | 0 | 0 | 0 | 10.12 | 27.38 | 30
798 | BANKURA | SM/11023 | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012286 | 40065723 | New | SVS | GO2223003671PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 45.49 | 75
799 | BANKURA | SM/10923 | MINI PIPED WATER SUPPLY SCHEME FOR KUDRA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012380 | 40025984 | New | SVS | GO2223003674PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
800 | BANKURA | SM/11202 | MINI PIPED WATER SUPPLY SCHEME FOR KUKUTIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012350 | 40027449 | New | SVS | GO2223003662PH | 30/05/2022 | 39.52 | 0 | 39.52 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
801 | BANKURA | SM/10875 | MINI PIPED WATER SUPPLY SCHEME FOR KUMIR PATHAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012432 | 40020008 | New | SVS | GO2223003669PH | 30/05/2022 | 36.96 | 0 | 36.96 | Bankura Division | Bankura Mechanical Division | 22.62 | 0 | 0 | 0 | 22.62 | 22.5 | 0 | 0 | 0 | 22.5 | 60.88 | 55
802 | BANKURA | SM/10884 | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012441 | 40020061 | New | SVS | GO2223003669PH | 30/05/2022 | 32.56 | 0 | 32.56 | Bankura Division | Bankura Mechanical Division | 25.62 | 0 | 0 | 0 | 25.62 | 25.62 | 0 | 0 | 0 | 25.62 | 78.67 | 78
803 | BANKURA | SM/10971 | MINI PIPED WATER SUPPLY SCHEME FOR KURUSTHALIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012453 | 40020103 | New | SVS | GO2223003672PH | 30/05/2022 | 42.28 | 0 | 42.28 | Bankura Division | Bankura Mechanical Division | 22.62 | 0 | 0 | 0 | 22.62 | 22.62 | 0 | 0 | 0 | 22.62 | 53.5 | 70
804 | BANKURA | SM/11114 | MINI PIPED WATER SUPPLY SCHEME FOR KUSUM KHUNDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012302 | 40065966 | New | SVS | GO2223003670PH | 30/05/2022 | 42.08 | 0 | 42.08 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18 | 0 | 0 | 0 | 18 | 42.77 | 40
805 | BANKURA | SM/11017 | MINI PIPED WATER SUPPLY SCHEME FOR LACHHIPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012280 | 40020081 | New | SVS | GO2223003671PH | 30/05/2022 | 43.65 | 0 | 43.65 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30.12 | 0 | 0 | 0 | 30.12 | 69.01 | 75
806 | BANKURA | SM/10942 | MINI PIPED WATER SUPPLY SCHEME FOR LAKHYARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012399 | 40026172 | New | SVS | GO2223003674PH | 30/05/2022 | 42.86 | 0 | 42.86 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.28 | 75
807 | BANKURA | SM/11116 | MINI PIPED WATER SUPPLY SCHEME FOR LEDAPAKUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012304 | 40027174 | New | SVS | GO2223003670PH | 30/05/2022 | 40.44 | 0 | 40.44 | Bankura Division | Bankura Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 44.79 | 70
808 | BANKURA | SM/11048 | MINI PIPED WATER SUPPLY SCHEME FOR MACHLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012367 | 40027336 | New | SVS | GO2223003657PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 45.22 | 75
809 | BANKURA | SM/11018 | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012281 | 40020082 | New | SVS | GO2223003671PH | 30/05/2022 | 40.52 | 0 | 40.52 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 61.7 | 45
810 | BANKURA | SM/11033 | MINI PIPED WATER SUPPLY SCHEME FOR MAHADEBSINAM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012296 | 40066025 | New | SVS | GO2223003671PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 0.11 | 0 | 0 | 0 | 0.11 | 0.11 | 0 | 0 | 0 | 0.11 | 0.31 | 0
811 | BANKURA | SM/11083 | MINI PIPED WATER SUPPLY SCHEME FOR MAHISHAKANALI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012346 | 40065459 | New | SVS | GO2223003663PH | 30/05/2022 | 32.56 | 0 | 32.56 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
812 | BANKURA | SM/10900 | MINI PIPED WATER SUPPLY SCHEME FOR MAKARKENDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012115 | 40019320 | New | SVS | GO2223003656PH | 30/05/2022 | 35.21 | 0 | 35.21 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 71.34 | 85
813 | BANKURA | SM/10912 | MINI PIPED WATER SUPPLY SCHEME FOR MALIN DASI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- II BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012156 | 40066064 | New | SVS | GO2223003656PH | 30/05/2022 | 41.37 | 0 | 41.37 | Bankura Division | Bankura Mechanical Division | 30.12 | 0 | 0 | 0 | 30.12 | 30.12 | 0 | 0 | 0 | 30.12 | 72.8 | 75
814 | BANKURA | SM/10943 | MINI PIPED WATER SUPPLY SCHEME FOR MALLIKDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012400 | 40026177 | New | SVS | GO2223003674PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
815 | BANKURA | SM/10928 | MINI PIPED WATER SUPPLY SCHEME FOR MANDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012385 | 40026034 | New | SVS | GO2223003674PH | 30/05/2022 | 36.71 | 0 | 36.71 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
816 | BANKURA | SM/11019 | MINI PIPED WATER SUPPLY SCHEME FOR MANHARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012282 | 40020085 | New | SVS | GO2223003671PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 25.72 | 0 | 0 | 0 | 25.72 | 25.72 | 0 | 0 | 0 | 25.72 | 68.2 | 75
817 | BANKURA | SM/10908 | MINI PIPED WATER SUPPLY SCHEME FOR MANJURA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012145 | 40019342 | New | SVS | GO2223003656PH | 30/05/2022 | 41.14 | 0 | 41.14 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.29 | 75
818 | BANKURA | SM/11051 | MINI PIPED WATER SUPPLY SCHEME FOR MARASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012370 | 40027362 | New | SVS | GO2223003657PH | 30/05/2022 | 40.21 | 0 | 40.21 | Bankura Division | Bankura Mechanical Division | 10.12 | 0 | 0 | 0 | 10.12 | 10 | 0 | 0 | 0 | 10 | 24.87 | 25
819 | BANKURA | SM/11061 | MINI PIPED WATER SUPPLY SCHEME FOR MEMOULI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012324 | 40026899 | New | SVS | GO2223003663PH | 30/05/2022 | 33.37 | 0 | 33.37 | Bankura Division | Bankura Mechanical Division | 19.62 | 0 | 0 | 0 | 19.62 | 19.5 | 0 | 0 | 0 | 19.5 | 58.44 | 50
820 | BANKURA | SM/10889 | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012446 | 40020076 | New | SVS | GO2223003669PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 70.36 | 70
821 | BANKURA | SM/13256 | MINI PIPED WATER SUPPLY SCHEME FOR MOULESWAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012146 | 40020075 | New | SVS | GO2223003658PH | 30/05/2022 | 30.69 | 0 | 30.69 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
822 | BANKURA | SM/10858 | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012415 | 40026282 | New | SVS | GO2223003673PH | 30/05/2022 | 34.21 | 0 | 34.21 | Bankura Division | Bankura Mechanical Division | 25.5 | 0 | 0 | 0 | 25.5 | 25.5 | 0 | 0 | 0 | 25.5 | 74.55 | 92
823 | BANKURA | SM/13252 | MINI PIPED WATER SUPPLY SCHEME FOR MUKUNDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012072 | 40028635 | New | SVS | GO2223003658PH | 30/05/2022 | 44.62 | 0 | 44.62 | Bankura Division | Bankura Mechanical Division | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 0 | 0 | 0 | 12.6 | 28.24 | 25
824 | BANKURA | SM/11113 | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012301 | 40027123 | New | SVS | GO2223003670PH | 30/05/2022 | 42.08 | 0 | 42.08 | Bankura Division | Bankura Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 43.04 | 40
825 | BANKURA | SM/13253 | MINI PIPED WATER SUPPLY SCHEME FOR MURRA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012128 | 40028639 | New | SVS | GO2223003658PH | 30/05/2022 | 39.29 | 0 | 39.29 | Bankura Division | Bankura Mechanical Division | 22.6 | 0 | 0 | 0 | 22.6 | 22.6 | 0 | 0 | 0 | 22.6 | 57.53 | 50
826 | BANKURA | SM/11052 | MINI PIPED WATER SUPPLY SCHEME FOR NABAGRAM VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012371 | 40027365 | New | SVS | GO2223003657PH | 30/05/2022 | 40.72 | 0 | 40.72 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25 | 0 | 0 | 0 | 25 | 61.4 | 50
827 | BANKURA | SM/10962 | MINI PIPED WATER SUPPLY SCHEME FOR NABASHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012494 | 40026109 | New | SVS | GO2223003664PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 0 | 0 | 0 | 12.6 | 33.63 | 30
828 | BANKURA | SM/11043 | MINI PIPED WATER SUPPLY SCHEME FOR NACHNA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012362 | 40027299 | New | SVS | GO2223003657PH | 30/05/2022 | 41.14 | 0 | 41.14 | Bankura Division | Bankura Mechanical Division | 10.12 | 0 | 0 | 0 | 10.12 | 10 | 0 | 0 | 0 | 10 | 24.31 | 25
829 | BANKURA | SM/10890 | MINI PIPED WATER SUPPLY SCHEME FOR NADUSENARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012447 | 40020079 | New | SVS | GO2223003669PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21 | 0 | 0 | 0 | 21 | 55.69 | 80
830 | BANKURA | SM/11063 | MINI PIPED WATER SUPPLY SCHEME FOR NAMADUDHIA DOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012326 | 40026915 | New | SVS | GO2223003663PH | 30/05/2022 | 31.49 | 0 | 31.49 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
831 | BANKURA | SM/10924 | MINI PIPED WATER SUPPLY SCHEME FOR NARAYANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012381 | 40025989 | New | SVS | GO2223003674PH | 30/05/2022 | 32.3 | 0 | 32.3 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
832 | BANKURA | SM/10969 | MINI PIPED WATER SUPPLY SCHEME FOR NATSHALA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012501 | 40026170 | New | SVS | GO2223003664PH | 30/05/2022 | 40.52 | 0 | 40.52 | Bankura Division | Bankura Mechanical Division | 20.6 | 0 | 0 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 20.6 | 50.84 | 30
833 | BANKURA | SM/10946 | MINI PIPED WATER SUPPLY SCHEME FOR NEKRAKONDA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012478 | 40025999 | New | SVS | GO2223003664PH | 30/05/2022 | 41.5 | 0 | 41.5 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 18 | 43.38 | 25
834 | BANKURA | SM/10972 | MINI PIPED WATER SUPPLY SCHEME FOR NISCHINTAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012454 | 40020104 | New | SVS | GO2223003672PH | 30/05/2022 | 43.25 | 0 | 43.25 | Bankura Division | Bankura Mechanical Division | 28.24 | 0 | 0 | 0 | 28.24 | 28.24 | 0 | 0 | 0 | 28.24 | 65.28 | 40
835 | BANKURA | SM/10859 | MINI PIPED WATER SUPPLY SCHEME FOR NISHCHINTAPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012416 | 40020104 | New | SVS | GO2223003673PH | 30/05/2022 | 34.21 | 0 | 34.21 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
836 | BANKURA | SM/10876 | MINI PIPED WATER SUPPLY SCHEME FOR NIYASA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012433 | 40020011 | New | SVS | GO2223003669PH | 30/05/2022 | 36.71 | 0 | 36.71 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 57.53 | 80
837 | BANKURA | SM/10989 | MINI PIPED WATER SUPPLY SCHEME FOR NUNIABAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012471 | 40020166 | New | SVS | GO2223003672PH | 30/05/2022 | 41.69 | 0 | 41.69 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 50.65 | 85
838 | BANKURA | SM/11126 | MINI PIPED WATER SUPPLY SCHEME FOR PAHARBERA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012314 | 40027389 | New | SVS | GO2223003670PH | 30/05/2022 | 44.04 | 0 | 44.04 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 45.69 | 10
839 | BANKURA | SM/10897 | MINI PIPED WATER SUPPLY SCHEME FOR PAHARIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012107 | 40019309 | New | SVS | GO2223003656PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 27.62 | 0 | 0 | 0 | 27.62 | 27.62 | 0 | 0 | 0 | 27.62 | 75.75 | 70
840 | BANKURA | SM/10990 | MINI PIPED WATER SUPPLY SCHEME FOR PAHARPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012472 | 40020167 | New | SVS | GO2223003672PH | 30/05/2022 | 42.47 | 0 | 42.47 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 49.72 | 80
841 | BANKURA | SM/11036 | MINI PIPED WATER SUPPLY SCHEME FOR PAINADA MODARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012355 | 40027216 | New | SVS | GO2223003657PH | 30/05/2022 | 34.45 | 0 | 34.45 | Bankura Division | Bankura Mechanical Division | 17.62 | 0 | 0 | 0 | 17.62 | 17.5 | 0 | 0 | 0 | 17.5 | 50.81 | 53
842 | BANKURA | SM/10917 | MINI PIPED WATER SUPPLY SCHEME FOR PANCHPUKHURIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012165 | 40032312 | New | SVS | GO2223003656PH | 30/05/2022 | 42.28 | 0 | 42.28 | Bankura Division | Bankura Mechanical Division | 31.29 | 0 | 0 | 0 | 31.29 | 31.29 | 0 | 0 | 0 | 31.29 | 74.01 | 56
843 | BANKURA | SM/10931 | MINI PIPED WATER SUPPLY SCHEME FOR PANKUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012388 | 40026056 | New | SVS | GO2223003674PH | 30/05/2022 | 34.96 | 0 | 34.96 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
844 | BANKURA | SM/10925 | MINI PIPED WATER SUPPLY SCHEME FOR PARAMANIK KUNRI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012382 | 40025995 | New | SVS | GO2223003674PH | 30/05/2022 | 33.37 | 0 | 33.37 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 75
845 | BANKURA | SM/10953 | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012485 | 40026059 | New | SVS | GO2223003664PH | 30/05/2022 | 41.69 | 0 | 41.69 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 43.46 | 50
846 | BANKURA | SM/11032 | MINI PIPED WATER SUPPLY SCHEME FOR PARESNATH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012295 | 40026365 | New | SVS | GO2223003671PH | 30/05/2022 | 37.21 | 0 | 37.21 | Bankura Division | Bankura Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 48.68 | 70
847 | BANKURA | SM/10973 | MINI PIPED WATER SUPPLY SCHEME FOR PATIJANARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012455 | 40020105 | New | SVS | GO2223003672PH | 30/05/2022 | 42.07 | 0 | 42.07 | Bankura Division | Bankura Mechanical Division | 31.12 | 0 | 0 | 0 | 31.12 | 31.12 | 0 | 0 | 0 | 31.12 | 73.97 | 70
848 | BANKURA | SM/13265 | MINI PIPED WATER SUPPLY SCHEME FOR PATRA HATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012186 | 40028692 | New | SVS | GO2223003658PH | 30/05/2022 | 39.95 | 0 | 39.95 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
849 | BANKURA | SM/13259 | MINI PIPED WATER SUPPLY SCHEME FOR PECHARAH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012160 | 40066079 | New | SVS | GO2223003658PH | 30/05/2022 | 40.88 | 0 | 40.88 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
850 | BANKURA | SM/11056 | MINI PIPED WATER SUPPLY SCHEME FOR PEDDAA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012375 | 40027391 | New | SVS | GO2223003657PH | 30/05/2022 | 44.23 | 0 | 44.23 | Bankura Division | Bankura Mechanical Division | 11.12 | 0 | 0 | 0 | 11.12 | 11 | 0 | 0 | 0 | 11 | 24.87 | 25
851 | BANKURA | SM/11027 | MINI PIPED WATER SUPPLY SCHEME FOR PHULJHOR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012290 | 40026326 | New | SVS | GO2223003671PH | 30/05/2022 | 35.46 | 0 | 35.46 | Bankura Division | Bolpur Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 51.09 | 40
852 | BANKURA | SM/11049 | MINI PIPED WATER SUPPLY SCHEME FOR PUNESA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012368 | 40027356 | New | SVS | GO2223003657PH | 30/05/2022 | 42.86 | 0 | 42.86 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
853 | BANKURA | SM/10960 | MINI PIPED WATER SUPPLY SCHEME FOR PURBATOR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012492 | 40026103 | New | SVS | GO2223003664PH | 30/05/2022 | 33.91 | 0 | 33.91 | Bankura Division | Bankura Mechanical Division | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 0 | 0 | 0 | 12.6 | 37.16 | 25
854 | BANKURA | SM/10980 | MINI PIPED WATER SUPPLY SCHEME FOR RADHANAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012462 | 40020112 | New | SVS | GO2223003672PH | 30/05/2022 | 40.72 | 0 | 40.72 | Bankura Division | Bankura Mechanical Division | 28.12 | 0 | 0 | 0 | 28.12 | 28 | 0 | 0 | 0 | 28 | 68.77 | 40
855 | BANKURA | SM/10849 | MINI PIPED WATER SUPPLY SCHEME FOR RADHASHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012406 | 40022108 | New | SVS | GO2223003673PH | 30/05/2022 | 41.14 | 0 | 41.14 | Bankura Division | Bankura Mechanical Division | 20 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 20 | 48.61 | 50
856 | BANKURA | SM/10877 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012434 | 40020015 | New | SVS | GO2223003669PH | 30/05/2022 | 30.68 | 0 | 30.68 | Bankura Division | Bankura Mechanical Division | 21.12 | 0 | 0 | 0 | 21.12 | 21.12 | 0 | 0 | 0 | 21.12 | 68.83 | 80
857 | BANKURA | SM/13262 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012172 | 40066057 | New | SVS | GO2223003658PH | 30/05/2022 | 40.19 | 0 | 40.19 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
858 | BANKURA | SM/11132 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012320 | 40065976 | New | SVS | GO2223003670PH | 30/05/2022 | 43.84 | 0 | 43.84 | Bankura Division | Bankura Mechanical Division | 15 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 34.22 | 25
859 | BANKURA | SM/10868 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012425 | 40026312 | New | SVS | GO2223003673PH | 30/05/2022 | 32.83 | 0 | 32.83 | Bankura Division | Bankura Mechanical Division | 20.24 | 0 | 0 | 0 | 20.24 | 20.24 | 0 | 0 | 0 | 20.24 | 61.64 | 40
860 | BANKURA | SM/10947 | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012479 | 40026002 | New | SVS | GO2223003664PH | 30/05/2022 | 44.82 | 0 | 44.82 | Bankura Division | Bankura Mechanical Division | 20 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 20 | 44.63 | 50
861 | BANKURA | SM/10909 | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012148 | 40019344 | New | SVS | GO2223003656PH | 30/05/2022 | 42.28 | 0 | 42.28 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.28 | 60
862 | BANKURA | SM/11123 | MINI PIPED WATER SUPPLY SCHEME FOR RAJPURA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012311 | 40027366 | New | SVS | GO2223003670PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 24.12 | 0 | 0 | 0 | 24.12 | 24.12 | 0 | 0 | 0 | 24.12 | 71.7 | 75
863 | BANKURA | SM/10850 | MINI PIPED WATER SUPPLY SCHEME FOR RAMNAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012407 | 40023386 | New | SVS | GO2223003673PH | 30/05/2022 | 37.2 | 0 | 37.2 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
864 | BANKURA | SM/13271 | MINI PIPED WATER SUPPLY SCHEME FOR RAUTKHANA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012203 | 40028555 | New | SVS | GO2223003658PH | 30/05/2022 | 35.96 | 0 | 35.96 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 69.85 | 75
865 | BANKURA | SM/11071 | MINI PIPED WATER SUPPLY SCHEME FOR RENGURBANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012334 | 40065453 | New | SVS | GO2223003663PH | 30/05/2022 | 39.98 | 0 | 39.98 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
866 | BANKURA | SM/11037 | MINI PIPED WATER SUPPLY SCHEME FOR RESIAGARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012356 | 40027243 | New | SVS | GO2223003657PH | 30/05/2022 | 32.03 | 0 | 32.03 | Bankura Division | Bankura Mechanical Division | 16.23 | 0 | 0 | 0 | 16.23 | 16.12 | 0 | 0 | 0 | 16.12 | 50.32 | 76
867 | BANKURA | SM/10954 | MINI PIPED WATER SUPPLY SCHEME FOR SABUDAD VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012486 | 40026061 | New | SVS | GO2223003664PH | 30/05/2022 | 42.86 | 0 | 42.86 | Bankura Division | Bankura Mechanical Division | 22.62 | 0 | 0 | 0 | 22.62 | 22.5 | 0 | 0 | 0 | 22.5 | 52.49 | 50
868 | BANKURA | SM/11079 | MINI PIPED WATER SUPPLY SCHEME FOR SAHARGHATI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012342 | 0 | New | SVS | GO2223003663PH | 30/05/2022 | 34.71 | 0 | 34.71 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
869 | BANKURA | SM/10870 | MINI PIPED WATER SUPPLY SCHEME FOR SALGERYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012427 | 40026321 | New | SVS | GO2223003673PH | 30/05/2022 | 31.49 | 0 | 31.49 | Bankura Division | Bankura Mechanical Division | 23.12 | 0 | 0 | 0 | 23.12 | 23.12 | 0 | 0 | 0 | 23.12 | 73.42 | 60
870 | BANKURA | SM/10981 | MINI PIPED WATER SUPPLY SCHEME FOR SALUKDANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012463 | 40020143 | New | SVS | GO2223003672PH | 30/05/2022 | 38.36 | 0 | 38.36 | Bankura Division | Bankura Mechanical Division | 12.5 | 0 | 0 | 0 | 12.5 | 12.5 | 0 | 0 | 0 | 12.5 | 32.59 | 25
871 | BANKURA | SM/10851 | MINI PIPED WATER SUPPLY SCHEME FOR SANKARARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012408 | 40026248 | New | SVS | GO2223003673PH | 30/05/2022 | 43.45 | 0 | 43.45 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
872 | BANKURA | SM/10970 | MINI PIPED WATER SUPPLY SCHEME FOR SHALTORA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012502 | 40026176 | New | SVS | GO2223003664PH | 30/05/2022 | 41.14 | 0 | 41.14 | Bankura Division | Bankura Mechanical Division | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 25 | 60.77 | 70
873 | BANKURA | SM/10860 | MINI PIPED WATER SUPPLY SCHEME FOR SHALUKA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012417 | 40026283 | New | SVS | GO2223003673PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20 | 0 | 0 | 0 | 20 | 53.39 | 65
874 | BANKURA | SM/10871 | MINI PIPED WATER SUPPLY SCHEME FOR SHIBARAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012428 | 40019987 | New | SVS | GO2223003669PH | 30/05/2022 | 36.46 | 0 | 36.46 | Bankura Division | Bankura Mechanical Division | 23.12 | 0 | 0 | 0 | 23.12 | 23.12 | 0 | 0 | 0 | 23.12 | 63.41 | 60
875 | BANKURA | SM/13250 | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012063 | 40028590 | New | SVS | GO2223003658PH | 30/05/2022 | 39.05 | 0 | 39.05 | Bankura Division | Bankura Mechanical Division | 18 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 18 | 46.09 | 50
876 | BANKURA | SM/10856 | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012413 | 40026274 | New | SVS | GO2223003673PH | 30/05/2022 | 31.22 | 0 | 31.22 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.38 | 70
877 | BANKURA | SM/11038 | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMSUNDARPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012357 | 40027287 | New | SVS | GO2223003657PH | 30/05/2022 | 36.96 | 0 | 36.96 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 49.02 | 75
878 | BANKURA | SM/11128 | MINI PIPED WATER SUPPLY SCHEME FOR SIAKULDOBA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012316 | 40066018 | New | SVS | GO2223003670PH | 30/05/2022 | 40.44 | 0 | 40.44 | Bankura Division | Bankura Mechanical Division | 20.12 | 0 | 0 | 0 | 20.12 | 20.12 | 0 | 0 | 0 | 20.12 | 49.74 | 30
879 | BANKURA | SM/10898 | MINI PIPED WATER SUPPLY SCHEME FOR SIARBADA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012110 | 40019313 | New | SVS | GO2223003656PH | 30/05/2022 | 33.64 | 0 | 33.64 | Bankura Division | Bankura Mechanical Division | 22.72 | 0 | 0 | 0 | 22.72 | 22.72 | 0 | 0 | 0 | 22.72 | 67.54 | 85
880 | BANKURA | SM/10901 | MINI PIPED WATER SUPPLY SCHEME FOR SIBARAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012117 | 40019322 | New | SVS | GO2223003656PH | 30/05/2022 | 36.96 | 0 | 36.96 | Bankura Division | Bankura Mechanical Division | 30.62 | 0 | 0 | 0 | 30.62 | 30.62 | 0 | 0 | 0 | 30.62 | 82.84 | 85
881 | BANKURA | SM/10952 | MINI PIPED WATER SUPPLY SCHEME FOR SIMCHAKA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012484 | 40026015 | New | SVS | GO2223003664PH | 30/05/2022 | 41.69 | 0 | 41.69 | Bankura Division | Bankura Mechanical Division | 18.12 | 0 | 0 | 0 | 18.12 | 18.12 | 0 | 0 | 0 | 18.12 | 43.46 | 42
882 | BANKURA | SM/10991 | MINI PIPED WATER SUPPLY SCHEME FOR SIROMANIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012473 | 40020168 | New | SVS | GO2223003672PH | 30/05/2022 | 43.45 | 0 | 43.45 | Bankura Division | Bankura Mechanical Division | 12.5 | 0 | 0 | 0 | 12.5 | 12.5 | 0 | 0 | 0 | 12.5 | 28.77 | 25
883 | BANKURA | SM/11067 | MINI PIPED WATER SUPPLY SCHEME FOR SONAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012330 | 40027175 | New | SVS | GO2223003663PH | 30/05/2022 | 42.86 | 0 | 42.86 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
884 | BANKURA | SM/10940 | MINI PIPED WATER SUPPLY SCHEME FOR SUDARSHANPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012397 | 40026164 | New | SVS | GO2223003674PH | 30/05/2022 | 41.89 | 0 | 41.89 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0.12 | 0 | 0 | 0 | 0.12 | 0.29 | 75
885 | BANKURA | SM/11068 | MINI PIPED WATER SUPPLY SCHEME FOR SUKNABAD VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012331 | 40027180 | New | SVS | GO2223003663PH | 30/05/2022 | 37.71 | 0 | 37.71 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
886 | BANKURA | SM/11028 | MINI PIPED WATER SUPPLY SCHEME FOR SUKNI BASA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012291 | 40026327 | New | SVS | GO2223003671PH | 30/05/2022 | 37.21 | 0 | 37.21 | Bankura Division | Bankura Mechanical Division | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 0 | 0 | 0 | 12.6 | 33.86 | 25
887 | BANKURA | SM/10899 | MINI PIPED WATER SUPPLY SCHEME FOR SUPURDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012113 | 40019315 | New | SVS | GO2223003656PH | 30/05/2022 | 30.41 | 0 | 30.41 | Bankura Division | Bankura Mechanical Division | 22.72 | 0 | 0 | 0 | 22.72 | 22.72 | 0 | 0 | 0 | 22.72 | 74.7 | 85
888 | BANKURA | SM/11057 | MINI PIPED WATER SUPPLY SCHEME FOR SURBHAGAB BAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012376 | 40027400 | New | SVS | GO2223003657PH | 30/05/2022 | 42.86 | 0 | 42.86 | Bankura Division | Bankura Mechanical Division | 10.12 | 0 | 0 | 0 | 10.12 | 10 | 0 | 0 | 0 | 10 | 23.33 | 25
889 | BANKURA | SM/11034 | MINI PIPED WATER SUPPLY SCHEME FOR SUSHUNIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012353 | 40027181 | New | SVS | GO2223003657PH | 30/05/2022 | 31.76 | 0 | 31.76 | Bankura Division | Bankura Mechanical Division | 22.12 | 0 | 0 | 0 | 22.12 | 22 | 0 | 0 | 0 | 22 | 69.27 | 50
890 | BANKURA | SM/11120 | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012308 | 40027345 | New | SVS | GO2223003670PH | 30/05/2022 | 42.07 | 0 | 42.07 | Bankura Division | Bankura Mechanical Division | 18.11 | 0 | 0 | 0 | 18.11 | 18.11 | 0 | 0 | 0 | 18.11 | 43.06 | 70
891 | BANKURA | SM/11044 | MINI PIPED WATER SUPPLY SCHEME FOR TALTALA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012363 | 40027300 | New | SVS | GO2223003657PH | 30/05/2022 | 42.07 | 0 | 42.07 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25 | 0 | 0 | 0 | 25 | 59.43 | 50
892 | BANKURA | SM/11069 | MINI PIPED WATER SUPPLY SCHEME FOR TAPUBAID VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012332 | 40063555 | New | SVS | GO2223003663PH | 30/05/2022 | 43.65 | 0 | 43.65 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
893 | BANKURA | SM/10906 | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012140 | 40019338 | New | SVS | GO2223003656PH | 30/05/2022 | 40.52 | 0 | 40.52 | Bankura Division | Bankura Mechanical Division | 25.68 | 0 | 0 | 0 | 25.68 | 25.68 | 0 | 0 | 0 | 25.68 | 63.37 | 85
894 | BANKURA | SM/10881 | MINI PIPED WATER SUPPLY SCHEME FOR TARKAJOR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012438 | 0 | New | SVS | GO2223003669PH | 30/05/2022 | 36.71 | 0 | 36.71 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
895 | BANKURA | SM/11204 | MINI PIPED WATER SUPPLY SCHEME FOR TELANBANDI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012352 | 40027454 | New | SVS | GO2223003662PH | 30/05/2022 | 37.66 | 0 | 37.66 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1
896 | BANKURA | SM/13260 | MINI PIPED WATER SUPPLY SCHEME FOR TELLA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012163 | 40066066 | New | SVS | GO2223003658PH | 30/05/2022 | 43.39 | 0 | 43.39 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
897 | BANKURA | SM/10914 | MINI PIPED WATER SUPPLY SCHEME FOR TENTUL BERIA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012158 | 40032068 | New | SVS | GO2223003656PH | 30/05/2022 | 35.96 | 0 | 35.96 | Bankura Division | Bankura Mechanical Division | 20.5 | 0 | 0 | 0 | 20.5 | 20.5 | 0 | 0 | 0 | 20.5 | 57.01 | 57
898 | BANKURA | SM/11125 | MINI PIPED WATER SUPPLY SCHEME FOR THANA DUMAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SALTORA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012313 | 40065995 | New | SVS | GO2223003670PH | 30/05/2022 | 37.46 | 0 | 37.46 | Bankura Division | Bankura Mechanical Division | 15.12 | 0 | 0 | 0 | 15.12 | 15.12 | 0 | 0 | 0 | 15.12 | 40.36 | 25
899 | BANKURA | SM/13273 | MINI PIPED WATER SUPPLY SCHEME FOR TIKARPARA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012211 | 40028550 | New | SVS | GO2223003658PH | 30/05/2022 | 34.21 | 0 | 34.21 | Bankura Division | Bankura Mechanical Division | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 10 | 29.23 | 25
900 | BANKURA | SM/11035 | MINI PIPED WATER SUPPLY SCHEME FOR TILABAI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012354 | 40027207 | New | SVS | GO2223003657PH | 30/05/2022 | 30.68 | 0 | 30.68 | Bankura Division | Bankura Mechanical Division | 12.62 | 0 | 0 | 0 | 12.62 | 12.5 | 0 | 0 | 0 | 12.5 | 40.74 | 52
901 | BANKURA | SM/13261 | MINI PIPED WATER SUPPLY SCHEME FOR TOL CHANDRAKONA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012166 | 40066074 | New | SVS | GO2223003658PH | 30/05/2022 | 40.42 | 0 | 40.42 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
902 | BANKURA | SM/10861 | MINI PIPED WATER SUPPLY SCHEME FOR TUNAMARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012418 | 40026285 | New | SVS | GO2223003673PH | 30/05/2022 | 34.96 | 0 | 34.96 | Bankura Division | Bankura Mechanical Division | 20.62 | 0 | 0 | 0 | 20.62 | 20.5 | 0 | 0 | 0 | 20.5 | 58.64 | 65
903 | BANKURA | SM/13272 | MINI PIPED WATER SUPPLY SCHEME FOR TURUBANDH VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | TSM/012207 | 40066081 | New | SVS | GO2223003658PH | 30/05/2022 | 30.41 | 0 | 30.41 | Bankura Division | Bankura Mechanical Division | 25.12 | 0 | 0 | 0 | 25.12 | 25.12 | 0 | 0 | 0 | 25.12 | 82.59 | 75
904 | BANKURA | SM/10974 | MINI PIPED WATER SUPPLY SCHEME FOR UPARGERYAKULA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012456 | 40020106 | New | SVS | GO2223003672PH | 30/05/2022 | 39.75 | 0 | 39.75 | Bankura Division | Bankura Mechanical Division | 0.12 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 80
905 | BANKURA | SM/10982 | MINI PIPED WATER SUPPLY SCHEME FOR UTTAR KENDBANA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/012464 | 40020144 | New | SVS | GO2223003672PH | 30/05/2022 | 42.53 | 0 | 42.53 | Bankura Division | Bankura Mechanical Division | 12.62 | 0 | 0 | 0 | 12.62 | 12.5 | 0 | 0 | 0 | 12.5 | 29.39 | 25
906 | BANKURA | SM/14006 | Mukundapur Piped Water Supply Scheme | TSM/015734 | 40035986 | New | MVS | GO2223010513PH | 05/12/2022 | 602.61 | 94.21 | 696.82 | Bankura Division | Bankura Mechanical Division | 61.79 | 11.76 | 7.99 | 0 | 81.54 | 61.79 | 0 | 0 | 0 | 61.79 | 8.87 | 27
907 | BANKURA | SM/13874 | Nabasan Piped Water Supply Scheme | TSM/014758 | 40034332 | New | MVS | GO2223010074PH | 25/11/2022 | 831.04 | 94.21 | 925.26 | Bankura Division | Bankura Mechanical Division | 22.62 | 7.95 | 92.93 | 0 | 123.51 | 12.31 | 3.33 | 92.93 | 0 | 108.57 | 11.73 | 5
908 | BANKURA | SM/19178 | Nanda Mohanpur Piped Water Supply Scheme | TSM/015172 | 40035818 | New | MVS | 448/PHE-28011/232/2022-SCHM CELL-Dept. of PHE | 16/02/2024 | 1281.53 | 161.6 | 1443.13 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
909 | BANKURA | SM/14248 | Nandagram Piped Water Supply Scheme | TSM/014862 | 40042088 | New | MVS | GO2223011827PH | 16/01/2023 | 1295.15 | 170.12 | 1465.27 | Bankura Division | Bankura Mechanical Division | 94.86 | 18.36 | 87.53 | 0 | 200.75 | 94.86 | 18.36 | 87.53 | 0 | 200.75 | 13.7 | 6
910 | BANKURA | SM/18252 | Nandur Piped Water Supply Scheme | TSM/015740 | 40044037 | New | MVS | 1563/PHE-28011/83/2023-ESTT CELL-Dept. of PHE | 16/06/2023 | 1292.37 | 170.12 | 1462.49 | Bankura Division | Bankura Mechanical Division | 12.59 | 0 | 128.82 | 0 | 141.42 | 12.59 | 0 | 128.82 | 0 | 141.42 | 9.67 | 3
911 | BANKURA | SM/14178 | Narayanpur Piped Water Supply Scheme | TSM/014854 | 40042005 | New | MVS | GO2223011631PH | 09/01/2023 | 936.49 | 107.36 | 1043.85 | Bankura Division | Bankura Mechanical Division | 0 | 9.1 | 24.51 | 0 | 33.61 | 0 | 9.1 | 24.51 | 0 | 33.61 | 3.22 | 4
912 | BANKURA | SM/13789 | Naruala Piped Water Supply Scheme | TSM/015168 | 40034660 | New | MVS | GO2223009886PH | 18/11/2022 | 546.62 | 86.71 | 633.32 | Bankura Division | Bankura Mechanical Division | 49.12 | 8.27 | 0 | 0 | 57.38 | 49.12 | 0 | 0 | 0 | 49.12 | 7.76 | 13
913 | BANKURA | SM/09633 | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Bl | TSM/007461 | 5343948 | Retrofitting | SVS | GO2122005839PH | 24/11/2021 | 295.14 | 0 | 295.14 | Bankura Division |  | 184.79 | 0 | 0 | 0 | 184.79 | 184.79 | 0 | 0 | 0 | 184.79 | 62.61 | 90
914 | BANKURA | SM/09634 | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora B | TSM/007462 | 5343948 | Retrofitting | SVS | GO2122005839PH | 24/11/2021 | 294.27 | 0 | 294.27 | Bankura Division |  | 179.8 | 0 | 0 | 0 | 179.8 | 179.8 | 0 | 0 | 0 | 179.8 | 61.1 | 90
915 | BANKURA | SM/09632 | New pipe line with Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 03 nos. Mouzas (Kadasole , Kamarsol ,Ghutgaria) of BARJORA Water Supply Scheme(Left out mouzas | TSM/007460 | 5343948 | Retrofitting | MVS | GO2122005839PH | 24/11/2021 | 294.2 | 0 | 294.2 | Bankura Division |  | 197.71 | 0 | 87.92 | 0 | 285.63 | 197.71 | 0 | 87.92 | 0 | 285.63 | 97.09 | 90
916 | BANKURA | SM/18790 | Panahar Piped Water Supply Scheme | TSM/018129 | 40059758 | New | MVS | 2692/PHE-28011/187/2023-SCHM CELL-Dept. of PHE | 07/09/2023 | 1163.38 | 161.04 | 1324.42 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 35.48 | 0 | 35.48 | 0 | 0 | 35.48 | 0 | 35.48 | 2.68 | 9
917 | BANKURA | SM/12427 | Pankhai Piped Water Supply Scheme | TSM/014210 | 40036227 | New | MVS | GO2223007537PH | 13/09/2022 | 724.66 | 100.78 | 825.44 | Bankura Division | Bankura Mechanical Division | 157.79 | 10.86 | 27.27 | 0 | 195.92 | 147.05 | 7.68 | 27.27 | 0 | 182 | 22.05 | 12
918 | BANKURA | SM/14009 | Pathara Piped Water Supply Scheme | TSM/015700 | 40036652 | New | MVS | GO2223010509PH | 05/12/2022 | 427.73 | 82.81 | 510.54 | Bankura Division | Bankura Mechanical Division | 0 | 35.88 | 0 | 0 | 35.88 | 0 | 14.56 | 0 | 0 | 14.56 | 2.85 | 8
919 | BANKURA | SM/14012 | Patrabandh Piped Water Supply Scheme | TSM/015915 | 40036824 | New | MVS | GO2223010508PH | 05/12/2022 | 871.35 | 107.36 | 978.71 | Bankura Division | Bankura Mechanical Division | 10.55 | 0 | 0 | 0 | 10.55 | 10.55 | 0 | 0 | 0 | 10.55 | 1.08 | 3
920 | BANKURA | SM/14011 | Patsol Piped Water Supply Scheme | TSM/015708 | 40036819 | New | MVS | GO2223010515PH | 05/12/2022 | 166.91 | 84.76 | 251.67 | Bankura Division | Bankura Mechanical Division | 31.82 | 10.74 | 0 | 0 | 42.55 | 31.82 | 0 | 0 | 0 | 31.82 | 12.64 | 13
921 | BANKURA | SM/15019 | Pratappur Piped Water Supply Scheme. | TSM/015766 | 40035900 | New | MVS | GO2223013068PH | 04/02/2023 | 855.81 | 107.36 | 963.17 | Bankura Division | Bankura Mechanical Division | 26.46 | 0 | 61.85 | 0 | 88.31 | 26.46 | 0 | 47.99 | 0 | 74.45 | 7.73 | 2
922 | BANKURA | SM/18038 | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | TSM/018000 | 40061567 | New | MVS | GO2223016904PH | 17/03/2023 | 183.26 | 41.39 | 224.65 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 2.92 | 0 | 2.92 | 0 | 0 | 2.92 | 0 | 2.92 | 1.3 | 8
923 | BANKURA | SM/18039 | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | TSM/017979 | 40061588 | New | MVS | GO2223016902PH | 17/03/2023 | 542.2 | 82.78 | 624.98 | Bankura Division | Bankura Mechanical Division | 60.53 | 0 | 0 | 0 | 60.53 | 60.53 | 0 | 0 | 0 | 60.53 | 9.69 | 13
924 | BANKURA | SM/17578 | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | TSM/011406 | 40065964 | New | SVS | GO2223017018PH | 18/03/2023 | 408.29 | 82.29 | 490.58 | Bankura Division | Bankura Mechanical Division | 87.32 | 0 | 2.09 | 0 | 89.42 | 87.32 | 0 | 2.09 | 0 | 89.42 | 18.23 | 14
925 | BANKURA | SM/18041 | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | TSM/018452 | 40061557 | New | MVS | GO2223016907PH | 17/03/2023 | 413.83 | 83.82 | 497.65 | Bankura Division | Bankura Mechanical Division | 58.79 | 14.17 | 7.98 | 0 | 80.93 | 58.79 | 0 | 3.99 | 0 | 62.78 | 12.62 | 42
926 | BANKURA | SM/18040 | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | TSM/017961 | 40061593 | New | MVS | GO2223016890PH | 17/03/2023 | 274.89 | 82.78 | 357.67 | Bankura Division | Bankura Mechanical Division | 0 | 24.98 | 4.95 | 0 | 29.94 | 0 | 0 | 4.95 | 0 | 4.95 | 1.38 | 11
927 | BANKURA | SM/17231 | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | TSM/018450 | 40061125 | New | MVS | GO2223016128PH | 15/03/2023 | 570.75 | 83.82 | 654.57 | Bankura Division | Bankura Mechanical Division | 0 | 17.17 | 98.52 | 0 | 115.69 | 0 | 17.17 | 98.52 | 0 | 115.69 | 17.67 | 6
928 | BANKURA | SM/18043 | Proposed sub surface water based Parashibana pipe water supply scheme under Bankura Division, Block Chhatna, District: Bankura. | TSM/018449 | 40061586 | New | MVS | GO2223016915PH | 17/03/2023 | 589.01 | 83.82 | 672.83 | Bankura Division | Bankura Mechanical Division | 6.78 | 27.93 | 78.37 | 0 | 113.08 | 0 | 0 | 72.99 | 0 | 72.99 | 10.85 | 5
929 | BANKURA | SM/18042 | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | TSM/017903 | 40061600 | New | MVS | GO2223016900PH | 17/03/2023 | 356.1 | 82.78 | 438.88 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 59.17 | 0 | 59.17 | 0 | 0 | 53.11 | 0 | 53.11 | 12.1 | 4
930 | BANKURA | SM/17227 | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | TSM/018014 | 40059915 | New | MVS | GO2223016129PH | 15/03/2023 | 683.88 | 82.78 | 766.66 | Bankura Division | Bankura Mechanical Division | 0 | 2.93 | 15.5 | 0 | 18.43 | 0 | 0 | 15.5 | 0 | 15.5 | 2.02 | 1
931 | BANKURA | SM/18044 | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | TSM/019239 | 40061643 | New | MVS | GO2223016912PH | 17/03/2023 | 296.31 | 82.78 | 379.09 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 28.14 | 0 | 28.14 | 0 | 0 | 28.14 | 0 | 28.14 | 7.42 | 9
932 | BANKURA | SM/08310 | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | TSM/007339 | 5343948 | Retrofitting | MVS | GO2021007606PH | 26/02/2021 | 295.5 | 0 | 295.5 | Bankura Division |  | 87.99 | 0 | 0 | 0 | 87.99 | 87.99 | 0 | 0 | 0 | 87.99 | 29.78 | 50
933 | BANKURA | SM/08311 | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District | TSM/007338 | 5343948 | Retrofitting | MVS | GO2021007633PH | 26/02/2021 | 298.3 | 0 | 298.3 | Bankura Division |  | 164.2 | 0 | 22.13 | 0 | 186.33 | 152.4 | 0 | 22.13 | 0 | 174.53 | 58.51 | 76
934 | BANKURA | SM/14005 | Ramnagar Piped Water Supply Scheme | TSM/015728 | 40035971 | New | MVS | GO2223010514PH | 05/12/2022 | 866.11 | 125.54 | 991.65 | Bankura Division | Bankura Mechanical Division | 0 | 23.88 | 54.68 | 0 | 78.56 | 0 | 18.92 | 54.68 | 0 | 73.6 | 7.42 | 27
935 | BANKURA | SM/18349 | Rampur Piped Water Supply Scheme | TSM/018166 | 40059591 | New | MVS | 1767/PHE-28011/190/2023-SCHM CELL-Dept. of PHE | 06/07/2023 | 1168.6 | 170.12 | 1338.73 | Bankura Division | Bankura Mechanical Division | 93.2 | 23.1 | 0 | 0 | 116.31 | 93.2 | 0 | 0 | 0 | 93.2 | 6.96 | 44
936 | BANKURA | SM/12415 | Rani Bandh Piped Water Supply Scheme | TSM/014587 | 40039114 | New | MVS | GO2223007569PH | 13/09/2022 | 828 | 96.1 | 924.1 | Bankura Division | Bankura Mechanical Division | 240.9 | 20.2 | 60.42 | 0 | 321.52 | 240.9 | 20.2 | 60.42 | 0 | 321.52 | 34.79 | 42
937 | BANKURA | SM/14519 | Ranpur Piped Water Supply Scheme | TSM/014589 | 40036241 | New | MVS | GO2223012611PH | 30/01/2023 | 1374.16 | 160.28 | 1534.45 | Bankura Division | Bankura Mechanical Division | 18.74 | 4.2 | 60.28 | 0 | 83.23 | 18.74 | 0 | 60.28 | 0 | 79.02 | 5.15 | 8
938 | BANKURA | SM/14521 | Rautara Piped Water Supply Scheme | TSM/014579 | 40038902 | New | MVS | GO2223012613PH | 30/01/2023 | 908.26 | 114.28 | 1022.54 | Bankura Division | Bankura Mechanical Division | 0 | 0 | 54.75 | 0 | 54.75 | 0 | 0 | 54.75 | 0 | 54.75 | 5.35 | 1
939 | BANKURA | SM/14524 | Rautkhanda Piped Water Supply Scheme | TSM/014208 | 40035606 | New | MVS | GO2223012619PH | 30/01/2023 | 1284.24 | 157.87 | 1442.11 | Bankura Division | Bankura Mechanical Division | 128.17 | 5.94 | 32.39 | 0 | 166.49 | 128.17 | 2.6 | 32.39 | 0 | 163.15 | 11.31 | 10
940 | BANKURA | SM/09330 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Schem | TSM/007456 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 211.32 | 0 | 211.32 | Bankura Division |  | 205.16 | 0 | 0 | 0 | 205.16 | 204.63 | 0 | 0 | 0 | 204.63 | 96.84 | 90
941 | BANKURA | SM/09329 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S | TSM/007476 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 160.36 | 0 | 160.36 | Bankura Division |  | 153.17 | 0 | 0 | 0 | 153.17 | 153.17 | 0 | 0 | 0 | 153.17 | 95.51 | 90
942 | BANKURA | SM/09312 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur) of BARJORA Water Su | TSM/007457 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 206.86 | 0 | 206.86 | Bankura Division |  | 200.84 | 0 | 0 | 0 | 200.84 | 200.63 | 0 | 0 | 0 | 200.63 | 96.99 | 90
943 | BANKURA | SM/09328 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 09 nos. Mouzas (Pakhnna, Kamalpur, Tajpur, Pakhanna Bharabpur, Gopalpur, Radhakantapur, Pakhanna Pratap pur, P | TSM/007475 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 236.78 | 0 | 236.78 | Bankura Division |  | 229.89 | 0 | 0 | 0 | 229.89 | 229.89 | 0 | 0 | 0 | 229.89 | 97.09 | 90
944 | BANKURA | SM/09327 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishn | TSM/007474 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 254.63 | 0 | 254.63 | Bankura Division |  | 230.08 | 0 | 0 | 0 | 230.08 | 229.86 | 0 | 0 | 0 | 229.86 | 90.27 | 90
945 | BANKURA | SM/09313 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Hariramp | TSM/007458 | 5343948 | Retrofitting | MVS | GO2122005027PH | 08/11/2021 | 262.33 | 0 | 262.33 | Bankura Division |  | 254.69 | 0 | 0 | 0 | 254.69 | 254.69 | 0 | 0 | 0 | 254.69 | 97.09 | 90
946 | BANKURA | SM/09499 | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | TSM/008407 | 5343948 | Retrofitting | MVS | GO2122005582PH | 19/11/2021 | 231.41 | 0 | 231.41 | Bankura Division |  | 224.67 | 0 | 0 | 0 | 224.67 | 224.67 | 0 | 0 | 0 | 224.67 | 97.09 | 90
947 | BANKURA | SM/07372 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-A) | TSM/006020 | 5343948 | Retrofitting | MVS | GO2021003348PH | 11/12/2020 | 75.12 | 0 | 75.12 | Bankura Division |  | 64.78 | 0 | 0 | 0 | 64.78 | 64.78 | 0 | 0 | 0 | 64.78 | 86.24 | 56
948 | BANKURA | SM/07373 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-B) | TSM/006021 | 5343948 | Retrofitting | MVS | GO2021003328PH | 11/12/2020 | 96.11 | 0 | 96.11 | Bankura Division |  | 62.94 | 0 | 0 | 0 | 62.94 | 62.94 | 0 | 0 | 0 | 62.94 | 65.48 | 58
949 | BANKURA | SM/07374 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - B W/S Scheme (BRGF ph - I project) (Part-C) | TSM/006022 | 5343948 | Retrofitting | MVS | GO2021003349PH | 11/12/2020 | 97.77 | 0 | 97.77 | Bankura Division |  | 67.23 | 0 | 0 | 0 | 67.23 | 67.23 | 0 | 0 | 0 | 67.23 | 68.76 | 55
950 | BANKURA | SM/07272 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) | TSM/006016 | 8147050 | Retrofitting | MVS | GO2021003140PH | 08/12/2020 | 88.11 | 0 | 88.11 | Bankura Division |  | 83.64 | 0 | 1.9 | 0 | 85.54 | 83.64 | 0 | 1.9 | 0 | 85.54 | 97.09 | 86
951 | BANKURA | SM/07370 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) | TSM/006017 | 8147060 | Retrofitting | MVS | GO2021003331PH | 11/12/2020 | 98.13 | 0 | 98.13 | Bankura Division |  | 78.61 | 0 | 16.67 | 0 | 95.27 | 78.61 | 0 | 16.67 | 0 | 95.27 | 97.09 | 59
952 | BANKURA | SM/07371 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-C) | TSM/006018 | 8147068 | Retrofitting | MVS | GO2021003347PH | 11/12/2020 | 78.33 | 0 | 78.33 | Bankura Division |  | 69.32 | 0 | 6.73 | 0 | 76.05 | 69.32 | 0 | 6.73 | 0 | 76.05 | 97.09 | 52
953 | BANKURA | SM/07330 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) (Part-A) | TSM/006009 | 8146588 | Retrofitting | MVS | GO2021003217PH | 10/12/2020 | 67.6 | 0 | 67.6 | Bankura Division |  | 38.42 | 0 | 0 | 0 | 38.42 | 38.42 | 0 | 0 | 0 | 38.42 | 56.84 | 65
954 | BANKURA | SM/07350 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-A) | TSM/006010 | 8146616 | Retrofitting | SVS | GO2021003344PH | 11/12/2020 | 58.68 | 0 | 58.68 | Bankura Division |  | 58.68 | 0 | 0 | 0 | 58.68 | 58.68 | 0 | 0 | 0 | 58.68 | 100 | 52
955 | BANKURA | SM/07351 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone-II) (Part-B) | TSM/006011 | 8146657 | Retrofitting | MVS | GO2021003329PH | 11/12/2020 | 61.18 | 0 | 61.18 | Bankura Division |  | 59.4 | 0 | 0 | 0 | 59.4 | 59.4 | 0 | 0 | 0 | 59.4 | 97.09 | 89
956 | BANKURA | SM/07271 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) | TSM/006014 | 8160407 | Retrofitting | MVS | GO2021003139PH | 08/12/2020 | 96.39 | 0 | 96.39 | Bankura Division |  | 90.54 | 0 | 0 | 0 | 90.54 | 90.54 | 0 | 0 | 0 | 90.54 | 93.94 | 54
957 | BANKURA | SM/07352 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - I) (Part-A) | TSM/006012 | 8160401 | Retrofitting | SVS | GO2021003345PH | 11/12/2020 | 99.63 | 0 | 99.63 | Bankura Division |  | 83.47 | 0 | 0 | 0 | 83.47 | 83.47 | 0 | 0 | 0 | 83.47 | 83.78 | 53
958 | BANKURA | SM/07368 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I) (Part-B) | TSM/006013 | 8160413 | Retrofitting | MVS | GO2021003330PH | 11/12/2020 | 86.28 | 0 | 86.28 | Bankura Division |  | 72.06 | 0 | 0 | 0 | 72.06 | 69.64 | 0 | 0 | 0 | 69.64 | 80.71 | 50
959 | BANKURA | SM/07369 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-II) (Part-B) | TSM/006015 | 8160424 | Retrofitting | MVS | GO2021003346PH | 11/12/2020 | 94.58 | 0 | 94.58 | Bankura Division |  | 68 | 0 | 0 | 0 | 68 | 67.56 | 0 | 0 | 0 | 67.56 | 71.43 | 55
960 | BANKURA | SM/09501 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | TSM/008197 | 5343948 | Retrofitting | MVS | GO2122005581PH | 19/11/2021 | 92.18 | 0 | 92.18 | Bankura Division |  | 89.5 | 0 | 0 | 0 | 89.5 | 89.5 | 0 | 0 | 0 | 89.5 | 97.09 | 90
961 | BANKURA | SM/09473 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | TSM/008188 | 5343948 | Retrofitting | SVS | GO2122005583PH | 19/11/2021 | 189.75 | 0 | 189.75 | Bankura Division |  | 166.86 | 0 | 3.84 | 0 | 170.7 | 166.86 | 0 | 3.84 | 0 | 170.7 | 89.96 | 56
962 | BANKURA | SM/09472 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | TSM/008187 | 5343948 | Retrofitting | MVS | GO2122005583PH | 19/11/2021 | 278.21 | 0 | 278.21 | Bankura Division |  | 156.6 | 0 | 103.06 | 0 | 259.66 | 156.6 | 0 | 103.06 | 0 | 259.66 | 93.33 | 65
963 | BANKURA | SM/09474 | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | TSM/008189 | 5343948 | Retrofitting | MVS | GO2122005583PH | 19/11/2021 | 208.88 | 0 | 208.88 | Bankura Division |  | 151.87 | 0 | 0 | 0 | 151.87 | 151.87 | 0 | 0 | 0 | 151.87 | 72.71 | 75
964 | BANKURA | SM/14003 | Salkhara Piped Water Supply Scheme | TSM/015725 | 40035962 | New | MVS | GO2223010524PH | 05/12/2022 | 377.59 | 84.76 | 462.35 | Bankura Division | Bankura Mechanical Division | 58.47 | 15.39 | 0 | 0 | 73.86 | 0 | 15.39 | 0 | 0 | 15.39 | 3.33 | 29
965 | BANKURA | SM/11980 | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | TSM/011427 | 40048181 | Augmentation | MVS | GO2223006840PH | 31/08/2022 | 984.62 | 59.19 | 1043.82 | Bankura Division | Bankura Mechanical Division | 356.44 | 15.98 | 248.63 | 0 | 621.04 | 356.44 | 8.45 | 248.63 | 0 | 613.51 | 58.78 | 65
966 | BANKURA | SM/13711 | Telrui Piped Water Supply Scheme | TSM/015147 | 40034953 | New | MVS | GO2223009715PH | 14/11/2022 | 587.73 | 86.71 | 674.44 | Bankura Division | Bankura Mechanical Division | 2.97 | 4.43 | 71.6 | 0 | 79.01 | 2.97 | 0 | 71.6 | 0 | 74.57 | 11.06 | 26
Total | [9 empty] | 207288.33 | 30993.94 | 238282.27 |  |  | 54316.61 | 4308.93 | 10014.86 | 0 | 68640.4 | 52941.18 | 2385.53 | 8767.7 | 0 | 64094.41 | 26.9