## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PURULIA) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PURULIA | SM/18333 | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | TSM/011448 | 40032558 | New | MVS | 1712/PHE-28011/46/2023-SCHM CELL-Dept. of PHE | 30/06/2023 | 9898.87 | 380.98 | 10279.85 | Purulia Division | Purulia Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2 | PURULIA | SM/06826 | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | TSM/005788 | 8136128 | New | SVS | GO2021001718PH | 06/10/2020 | 81.48 | 0 | 81.48 | Purulia Division |  | 81.48 | 0 | 0 | 0 | 81.48 | 76.66 | 0 | 0 | 0 | 76.66 | 94.08 | 100
3 | PURULIA | SM/09578 | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008379 | 40009510 | Augmentation | MVS | GO2122005677PH | 22/11/2021 | 609.32 | 176.21 | 785.53 | Purulia Division | Purulia Mechanical Division | 378.67 | 89.84 | 19.43 | 0 | 487.94 | 378.67 | 89.84 | 19.43 | 0 | 487.94 | 62.12 | 79
4 | PURULIA | SM/16414 | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | TSM/019726 | 40065304 | Augmentation | MVS | GO2223015014PH | 28/02/2023 | 0 | 717.4 | 717.4 |  | Purulia Mechanical Division | 0 | 311.52 | 0 | 0 | 311.52 | 0 | 311.52 | 0 | 0 | 311.52 | 43.42 | 85
5 | PURULIA | SM/09217 | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | TSM/008389 | 40009347 | Augmentation | SVS | GO2122004732PH | 30/10/2021 | 236.63 | 149.46 | 386.08 | Purulia Division | Purulia Mechanical Division | 185.13 | 92.99 | 0 | 0 | 278.12 | 141.7 | 92.96 | 0 | 0 | 234.66 | 60.78 | 58
6 | PURULIA | SM/09580 | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | TSM/009008 | 40008783 | Augmentation | MVS | GO2122005676PH | 22/11/2021 | 274.67 | 229.81 | 504.47 | Purulia Division | Purulia Mechanical Division | 145.71 | 152.54 | 40.3 | 0 | 338.55 | 145.37 | 152.54 | 40.3 | 0 | 338.2 | 67.04 | 57
7 | PURULIA | SM/09215 | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008392 | 40008870 | Augmentation | MVS | GO2122004727PH | 30/10/2021 | 378.39 | 136.23 | 514.62 | Purulia Division | Purulia Mechanical Division | 265.81 | 111.07 | 82.04 | 0 | 458.91 | 262.24 | 108.85 | 82.04 | 0 | 453.12 | 88.05 | 71
8 | PURULIA | SM/10046 | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008456 | 40008872 | Augmentation | SVS | GO2122008500PH | 24/01/2022 | 1982.8 | 348.13 | 2330.93 | Purulia Division | Purulia Mechanical Division | 810.38 | 144.75 | 46.12 | 0 | 1001.25 | 632.43 | 144.75 | 46.12 | 0 | 823.3 | 35.32 | 73
9 | PURULIA | SM/09214 | Augmentation of Balitora & its adjoining mouzas water supply scheme | TSM/008393 | 40007341 | Augmentation | MVS | GO2122004727PH | 30/10/2021 | 372.89 | 90.87 | 463.76 | Purulia Division | Purulia Mechanical Division | 148.43 | 72.53 | 157.35 | 0 | 378.3 | 137.19 | 23.96 | 157.35 | 0 | 318.49 | 68.68 | 91
10 | PURULIA | SM/09209 | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008431 | 40008885 | Augmentation | SVS | GO2122004724PH | 30/10/2021 | 458.78 | 131.26 | 590.04 | Purulia Division | Purulia Mechanical Division | 258.11 | 75.56 | 6.96 | 0 | 340.63 | 245.48 | 74.07 | 6.96 | 0 | 326.51 | 55.34 | 74
11 | PURULIA | SM/09213 | Augmentation of Baram Water Supply Scheme | TSM/008385 | 40007338 | Augmentation | MVS | GO2122004734PH | 30/10/2021 | 87.94 | 107.52 | 195.46 | Purulia Division | Purulia Mechanical Division | 56.72 | 53.29 | 0 | 0 | 110.01 | 54.3 | 44.04 | 0 | 0 | 98.34 | 50.31 | 52
12 | PURULIA | SM/09211 | Augmentation of Bathanbari W/S Scheme | TSM/008398 | 40008779 | Augmentation | MVS | GO2122004734PH | 30/10/2021 | 69.97 | 97.12 | 167.09 | Purulia Division | Purulia Mechanical Division | 67.94 | 70.06 | 0 | 0 | 138 | 52.95 | 67.57 | 0 | 0 | 120.52 | 72.13 | 49
13 | PURULIA | SM/09218 | Augmentation of Beldi Water Supply Scheme | TSM/008386 | 40007323 | Augmentation | MVS | GO2122004732PH | 30/10/2021 | 60.7 | 67.9 | 128.6 | Purulia Division | Purulia Mechanical Division | 27.65 | 51.41 | 0 | 0 | 79.06 | 27.24 | 48.21 | 0 | 0 | 75.45 | 58.67 | 54
14 | PURULIA | SM/10395 | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008461 | 40021204 | Augmentation | MVS | GO2122011545PH | 29/03/2022 | 1706.86 | 243.04 | 1949.9 | Purulia Division | Purulia Mechanical Division | 285.45 | 88.11 | 0 | 0 | 373.56 | 258.88 | 88.11 | 0 | 0 | 346.99 | 17.8 | 64
15 | PURULIA | SM/10198 | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/009014 | 40009103 | Augmentation | MVS | GO2122009823PH | 22/02/2022 | 1206.75 | 248.79 | 1455.54 | Purulia Division | Purulia Mechanical Division | 523.64 | 164.7 | 209.08 | 0 | 897.43 | 504.3 | 164.7 | 169.21 | 0 | 838.21 | 57.59 | 75
16 | PURULIA | SM/09216 | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008390 | 40007361 | Augmentation | SVS | GO2122004732PH | 30/10/2021 | 260.66 | 163.56 | 424.22 | Purulia Division | Purulia Mechanical Division | 162.42 | 127.17 | 14.87 | 0 | 304.46 | 146.49 | 117.85 | 14.87 | 0 | 279.2 | 65.82 | 59
17 | PURULIA | SM/14460 | Augmentation of Dubra Pipe Water Supply Scheme PWSS | TSM/016045 | 40032506 | Augmentation | MVS | GO2223012295PH | 20/01/2023 | 567.66 | 92.39 | 660.04 | Purulia Division | Purulia Mechanical Division | 379.16 | 25.09 | 0 | 0 | 404.25 | 371.01 | 25.09 | 0 | 0 | 396.1 | 60.01 | 36
18 | PURULIA | SM/10045 | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | TSM/008462 | 40008838 | Augmentation | SVS | GO2122008500PH | 24/01/2022 | 1309.81 | 267.45 | 1577.26 | Purulia Division | Purulia Mechanical Division | 875.68 | 163.77 | 144.33 | 0 | 1183.78 | 829.04 | 163.77 | 144.33 | 0 | 1137.14 | 72.1 | 55
19 | PURULIA | SM/09037 | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008388 | 40007364 | Augmentation | MVS | GO2122004733PH | 30/10/2021 | 477.62 | 206.7 | 684.31 | Purulia Division | Purulia Mechanical Division | 292.41 | 86.49 | 18.98 | 0 | 397.88 | 289.23 | 86.28 | 18.98 | 0 | 394.5 | 57.65 | 69
20 | PURULIA | SM/10722 | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | TSM/009004 | 40015229 | Augmentation | MVS | GO2223002004PH | 18/05/2022 | 1948.46 | 247.24 | 2195.7 | Purulia Division | Purulia Mechanical Division | 566.09 | 141.43 | 465.46 | 0 | 1172.97 | 558.78 | 141.43 | 465.46 | 0 | 1165.66 | 53.09 | 62
21 | PURULIA | SM/09581 | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | TSM/009005 | 40008774 | Augmentation | MVS | GO2122005675PH | 22/11/2021 | 178.97 | 109.52 | 288.49 | Purulia Division | Purulia Mechanical Division | 167.89 | 94.52 | 0 | 0 | 262.41 | 124.08 | 94.52 | 0 | 0 | 218.61 | 75.78 | 65
22 | PURULIA | SM/11453 | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | TSM/008399 | 40018950 | Augmentation | MVS | GO2223004998PH | 12/07/2022 | 2133.73 | 233.82 | 2367.56 | Purulia Division | Purulia Mechanical Division | 919.95 | 130.62 | 528.8 | 0 | 1579.38 | 837.31 | 130.62 | 528.8 | 0 | 1496.73 | 63.22 | 40
23 | PURULIA | SM/10047 | Augmentation of Kashipur Piped Water Supply Scheme | TSM/008394 | 40008839 | Augmentation | SVS | GO2122008500PH | 24/01/2022 | 903.79 | 184.58 | 1088.37 | Purulia Division | Purulia Mechanical Division | 504.12 | 116.63 | 12.4 | 0 | 633.14 | 504.12 | 116.63 | 12.4 | 0 | 633.14 | 58.17 | 83
24 | PURULIA | SM/10723 | Augmentation of Kotshila Water Supply Scheme. | TSM/009003 | 40015237 | Augmentation | MVS | GO2223002065PH | 18/05/2022 | 1912.63 | 178.77 | 2091.4 | Purulia Division | Purulia Mechanical Division | 1320.57 | 83.67 | 0 | 0 | 1404.24 | 1173.7 | 73.3 | 0 | 0 | 1247 | 59.63 | 67
25 | PURULIA | SM/09212 | Augmentation of Lachhyara Piped Water Supply Scheme | TSM/008395 | 40008863 | Augmentation | MVS | GO2122004734PH | 30/10/2021 | 225.73 | 129.18 | 354.91 | Purulia Division | Purulia Mechanical Division | 135.58 | 53.45 | 39.18 | 0 | 228.21 | 132.43 | 53.45 | 39.18 | 0 | 225.06 | 63.41 | 47
26 | PURULIA | SM/09036 | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008391 | 40008862 | Augmentation | SVS | GO2122004731PH | 30/10/2021 | 780.8 | 184.96 | 965.77 | Purulia Division | Purulia Mechanical Division | 360.7 | 90.05 | 47.61 | 0 | 498.36 | 351.87 | 86.84 | 47.61 | 0 | 486.33 | 50.36 | 79
27 | PURULIA | SM/10719 | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/009013 | 40015227 | Augmentation | MVS | GO2223002001PH | 18/05/2022 | 1367.82 | 201.76 | 1569.58 | Purulia Division | Purulia Mechanical Division | 566.87 | 108.79 | 210.76 | 0 | 886.42 | 546.27 | 108.79 | 152.19 | 0 | 807.25 | 51.43 | 62
28 | PURULIA | SM/15936 | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | TSM/010889 | 40061242 | Augmentation | MVS | GO2223014613PH | 22/02/2023 | 999.41 | 0 | 999.41 | Purulia Division |  | 187.4 | 0 | 641.37 | 0 | 828.77 | 177.07 | 0 | 641.37 | 0 | 818.43 | 81.89 | 23
29 | PURULIA | SM/09943 | Augmentation of Manguria-Lalpur W/S Scheme | TSM/008396 | 40007352 | Augmentation | MVS | GO2122006799PH | 14/12/2021 | 255.1 | 115.98 | 371.08 | Purulia Division | Purulia Mechanical Division | 194.52 | 112.6 | 52.55 | 0 | 359.67 | 194.52 | 102.28 | 52.55 | 0 | 349.35 | 94.14 | 70
30 | PURULIA | SM/10718 | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | TSM/009015 | 40015228 | Augmentation | MVS | GO2223001981PH | 18/05/2022 | 1502.88 | 167.15 | 1670.03 | Purulia Division | Purulia Mechanical Division | 872.23 | 78.56 | 181.64 | 0 | 1132.42 | 824.26 | 78.56 | 181.64 | 0 | 1084.45 | 64.94 | 78
31 | PURULIA | SM/09583 | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | TSM/009000 | 40008786 | Augmentation | MVS | GO2122005675PH | 22/11/2021 | 32.96 | 70.6 | 103.56 | Purulia Division | Purulia Mechanical Division | 12.38 | 38.29 | 0 | 0 | 50.67 | 10.64 | 38.29 | 0 | 0 | 48.93 | 47.25 | 37
32 | PURULIA | SM/10048 | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008384 | 40009098 | Augmentation | SVS | GO2122008500PH | 24/01/2022 | 1252.58 | 224.48 | 1477.06 | Purulia Division | Purulia Mechanical Division | 931.62 | 135.04 | 308.96 | 0 | 1375.62 | 906.79 | 135.04 | 308.96 | 0 | 1350.79 | 91.45 | 77
33 | PURULIA | SM/14669 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | TSM/016035 | 40032407 | Augmentation | MVS | GO2223012689PH | 31/01/2023 | 940.08 | 29.33 | 969.41 | Purulia Division | Purulia Mechanical Division | 223.23 | 17.66 | 13.71 | 0 | 254.6 | 164.15 | 17.66 | 0 | 0 | 181.81 | 18.75 | 32
34 | PURULIA | SM/18250 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | TSM/016036 | 40032409 | Augmentation | MVS | 1561/PHE-28011/18/2023-ESTT CELL-Dept. of PHE | 16/06/2023 | 1048.66 | 29.33 | 1077.99 | Purulia Division | Purulia Mechanical Division | 236.18 | 21.31 | 0 | 0 | 257.5 | 137.62 | 21.31 | 0 | 0 | 158.93 | 14.74 | 5
35 | PURULIA | SM/14024 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | TSM/016037 | 40034808 | Augmentation | MVS | GO2223010504PH | 05/12/2022 | 752.92 | 29.33 | 782.25 | Purulia Division | Purulia Mechanical Division | 395.7 | 14.85 | 0 | 0 | 410.55 | 319.47 | 14.85 | 0 | 0 | 334.31 | 42.74 | 51
36 | PURULIA | SM/14025 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | TSM/016038 | 40032470 | Augmentation | MVS | GO2223010505PH | 05/12/2022 | 538.16 | 0.25 | 538.41 | Purulia Division | Purulia Mechanical Division | 169.63 | 0 | 0 | 0 | 169.63 | 169.63 | 0 | 0 | 0 | 169.63 | 31.51 | 53
37 | PURULIA | SM/14670 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | TSM/016039 | 40032476 | Augmentation | MVS | GO2223012694PH | 31/01/2023 | 955.25 | 29.08 | 984.33 | Purulia Division | Purulia Mechanical Division | 207.12 | 16.03 | 79.43 | 0 | 302.57 | 165.31 | 16.03 | 79.43 | 0 | 260.77 | 26.49 | 44
38 | PURULIA | SM/18306 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | TSM/016040 | 40032479 | Augmentation | MVS | 1658/PHE-28011/41/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 985.41 | 29.33 | 1014.74 | Purulia Division | Purulia Mechanical Division | 57.92 | 0 | 0 | 0 | 57.92 | 57.92 | 0 | 0 | 0 | 57.92 | 5.71 | 10
39 | PURULIA | SM/14022 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | TSM/016041 | 40032486 | Augmentation | MVS | GO2223010503PH | 05/12/2022 | 559.22 | 0.25 | 559.47 | Purulia Division | Purulia Mechanical Division | 53.17 | 0 | 0 | 0 | 53.17 | 51.98 | 0 | 0 | 0 | 51.98 | 9.29 | 35
40 | PURULIA | SM/16379 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | TSM/016042 | 40062835 | Augmentation | MVS | GO2223015017PH | 28/02/2023 | 785.64 | 29.08 | 814.73 | Purulia Division | Purulia Mechanical Division | 380.79 | 13.19 | 0 | 0 | 393.98 | 303.68 | 13.19 | 0 | 0 | 316.87 | 38.89 | 58
41 | PURULIA | SM/14023 | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | TSM/016044 | 40032489 | Augmentation | MVS | GO2223010502PH | 05/12/2022 | 663.92 | 57.31 | 721.23 | Purulia Division | Purulia Mechanical Division | 213.81 | 21.57 | 0 | 0 | 235.38 | 46.1 | 21.57 | 0 | 0 | 67.67 | 9.38 | 16
42 | PURULIA | SM/09582 | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | TSM/009002 | 40007346 | Augmentation | MVS | GO2122005675PH | 22/11/2021 | 94.65 | 109.21 | 203.85 | Purulia Division | Purulia Mechanical Division | 71.53 | 82.04 | 14.97 | 0 | 168.54 | 71.53 | 77.83 | 14.97 | 0 | 164.33 | 80.61 | 50
43 | PURULIA | SM/10721 | Augmentation of Saltore-Hijuli Water Supply Scheme | TSM/009011 | 40015232 | Augmentation | SVS | GO2223002003PH | 18/05/2022 | 865.97 | 179.4 | 1045.37 | Purulia Division | Purulia Mechanical Division | 343.06 | 114.28 | 318.74 | 0 | 776.08 | 338.93 | 114.28 | 318.74 | 0 | 771.95 | 73.84 | 76
44 | PURULIA | SM/14459 | Augmentation of Santuri Pipe Water Supply Scheme PWSS | TSM/016080 | 40032524 | Augmentation | SVS | GO2223012293PH | 20/01/2023 | 289.94 | 74 | 363.94 | Purulia Division | Purulia Mechanical Division | 157.11 | 32.49 | 0 | 0 | 189.6 | 128.49 | 32.49 | 0 | 0 | 160.98 | 44.23 | 67
45 | PURULIA | SM/09038 | Augmentation of Satra Water Supply Scheme | TSM/008387 | 40008755 | Augmentation | MVS | GO2122004726PH | 30/10/2021 | 260.06 | 129.15 | 389.21 | Purulia Division | Purulia Mechanical Division | 157.99 | 110.99 | 51.55 | 0 | 320.53 | 157.99 | 110.67 | 51.55 | 0 | 320.2 | 82.27 | 63
46 | PURULIA | SM/10347 | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008455 | 40010665 | Augmentation | MVS | GO2122010915PH | 16/03/2022 | 740.87 | 199.39 | 940.26 | Purulia Division | Purulia Mechanical Division | 238.81 | 83.8 | 0 | 0 | 322.61 | 224.37 | 83.8 | 0 | 0 | 308.17 | 32.77 | 46
47 | PURULIA | SM/09210 | Augmentation of Sonathali W/S Scheme | TSM/008397 | 40007343 | Augmentation | MVS | GO2122004724PH | 30/10/2021 | 258.83 | 143.05 | 401.87 | Purulia Division | Purulia Mechanical Division | 146.32 | 39.92 | 59.12 | 0 | 245.36 | 142.34 | 35.62 | 59.12 | 0 | 237.08 | 58.99 | 67
48 | PURULIA | SM/09579 | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | TSM/009009 | 40007355 | Augmentation | MVS | GO2122005676PH | 22/11/2021 | 261.84 | 201.19 | 463.03 | Purulia Division | Purulia Mechanical Division | 169.15 | 145.01 | 69.92 | 0 | 384.08 | 163.55 | 145.01 | 69.92 | 0 | 378.48 | 81.74 | 59
49 | PURULIA | SM/18779 | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | TSM/017383 | 40032542 | Augmentation | MVS | 2585/PHE-28011/216/2023-ESTT CELL-Dept. of PHE | 28/08/2023 | 3300.21 | 1384.9 | 4685.1 | Purulia Division | Purulia Mechanical Division | 0 | 40.45 | 1218.95 | 0 | 1259.4 | 0 | 40.45 | 841.31 | 0 | 881.76 | 18.82 | 9
50 | PURULIA | SM/08718 | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | TSM/005223 | 40008845 | New | MVS | GO2122002848PH | 03/09/2021 | 552.02 | 0 | 552.02 | Purulia Division |  | 475.49 | 0 | 0 | 0 | 475.49 | 360.51 | 0 | 0 | 0 | 360.51 | 65.31 | 16
51 | PURULIA | SM/18319 | Left out Mouzas of Barabazar pipe water supply scheme | TSM/011442 | 40035831 | New | MVS | 1681/PHE-28011/51/2023-SCHM CELL-Dept. of PHE | 27/06/2023 | 5404.98 | 730.4 | 6135.38 | Project Management Unit,WBPWSP,Purulia | Purulia Mechanical Division | 692.79 | 0 | 2403.07 | 0 | 3095.86 | 0 | 0 | 2316.05 | 0 | 2316.05 | 37.75 | 3
52 | PURULIA | SM/16091 | MINI PIPED WATER SUPPLY SCHEME FOR ANKDUAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER JAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013718 | 40061495 | New | SVS | GO2223014618PH | 22/02/2023 | 28.64 | 8.75 | 37.39 | Purulia Division | Purulia Mechanical Division | 2.84 | 0 | 0 | 0 | 2.84 | 2.84 | 0 | 0 | 0 | 2.84 | 7.61 | 2
53 | PURULIA | SM/14251 | MINI PIPED WATER SUPPLY SCHEME FOR BAMANDIHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MANBAZAR-I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013873 | 40034679 | New | SVS | GO2223012287PH | 20/01/2023 | 20.49 | 8.75 | 29.24 | Purulia Division | Purulia Mechanical Division | 4.33 | 0 | 0 | 0 | 4.33 | 4.33 | 0 | 0 | 0 | 4.33 | 14.83 | 1
54 | PURULIA | SM/16570 | MINI PIPED WATER SUPPLY SCHEME FOR BAMNI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ARSHA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013556 | 40030168 | New | SVS | GO2223015436PH | 09/03/2023 | 21.56 | 8.75 | 30.31 | Purulia Division | Purulia Mechanical Division | 2.28 | 0 | 0 | 0 | 2.28 | 2.28 | 0 | 0 | 0 | 2.28 | 7.51 | 1
55 | PURULIA | SM/15380 | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013606 | 40032979 | New | SVS | GO2223013402PH | 07/02/2023 | 24.09 | 8.75 | 32.84 | Purulia Division | Purulia Mechanical Division | 3.49 | 0 | 0 | 0 | 3.49 | 3.49 | 0 | 0 | 0 | 3.49 | 10.64 | 1
56 | PURULIA | SM/07764 | Piped Water Supply Scheme from Marble Lake to adjoining areas. | TSM/005481 | 8178268 | New | MVS | GO2021001828PH | 04/11/2020 | 686.88 | 72.14 | 759.01 | Purulia Division | Purulia Mechanical Division | 470.88 | 60.45 | 0.42 | 0 | 531.75 | 470.88 | 57.11 | 0.42 | 0 | 528.41 | 69.62 | 93
57 | PURULIA | SM/10544 | Providing FHTC under Arsha Water Supply Scheme | TSM/010923 | 40061270 | Augmentation | MVS | GO2223000334PH | 18/04/2022 | 317.07 | 0 | 317.07 | Purulia Division |  | 115.24 | 0 | 0 | 0 | 115.24 | 61.1 | 0 | 0 | 0 | 61.1 | 19.27 | 88
58 | PURULIA | SM/18641 | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | TSM/016015 | 40062847 | New | MVS | 2168/PHE-28011/80/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 48504.55 | 12482 | 60986.55 | Purulia Division | Purulia Mechanical Division | 173.76 | 0 | 2006.14 | 0 | 2179.9 | 0 | 0 | 1695.27 | 0 | 1695.27 | 2.78 | 1
59 | PURULIA | SM/18653 | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | TSM/018257 | 40061535 | New | MVS | 2193/PHE-28011/90/2023-ESTT CELL-Dept. of PHE | 01/08/2023 | 16409.28 | 0 | 16409.28 | Purulia Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
60 | PURULIA | SM/09577 | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | TSM/009010 | 40008884 | Augmentation | MVS | GO2122005678PH | 22/11/2021 | 649.89 | 141.82 | 791.71 | Purulia Division | Purulia Mechanical Division | 437.49 | 120.02 | 101.06 | 0 | 658.57 | 437.19 | 114.27 | 71.26 | 0 | 622.72 | 78.66 | 73
61 | PURULIA | SM/07563 | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006307 | 8178048 | Retrofitting | MVS | GO2021004028PH | 04/01/2021 | 185.57 | 0 | 185.57 | Purulia Division |  | 180.16 | 0 | 0 | 0 | 180.16 | 180.16 | 0 | 0 | 0 | 180.16 | 97.09 | 100
62 | PURULIA | SM/07564 | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006308 | 8178075 | Retrofitting | MVS | GO2021004029PH | 04/01/2021 | 128.34 | 0 | 128.34 | Purulia Division |  | 124.6 | 0 | 0 | 0 | 124.6 | 124.6 | 0 | 0 | 0 | 124.6 | 97.09 | 100
63 | PURULIA | SM/06942 | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006313 | 8136150 | Retrofitting | MVS | GO2021002276PH | 03/11/2020 | 86.91 | 0 | 86.91 | Purulia Division |  | 86.91 | 0 | 0 | 0 | 86.91 | 68.33 | 0 | 0 | 0 | 68.33 | 78.62 | 100
64 | PURULIA | SM/07836 | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006757 | 8178234 | Retrofitting | MVS | GO2021004549PH | 14/01/2021 | 91.65 | 0 | 91.65 | Purulia Division |  | 88.98 | 0 | 0 | 0 | 88.98 | 88.98 | 0 | 0 | 0 | 88.98 | 97.09 | 100
65 | PURULIA | SM/06940 | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006312 | 8136144 | Retrofitting | MVS | GO2021002275PH | 03/11/2020 | 96.09 | 0 | 96.09 | Purulia Division |  | 96.09 | 0 | 0 | 0 | 96.09 | 96.09 | 0 | 0 | 0 | 96.09 | 100 | 100
66 | PURULIA | SM/07837 | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006758 | 8178221 | Retrofitting | MVS | GO2021004548PH | 14/01/2021 | 224.29 | 0 | 224.29 | Purulia Division |  | 112.33 | 0 | 0 | 0 | 112.33 | 112.33 | 0 | 0 | 0 | 112.33 | 50.08 | 100
67 | PURULIA | SM/07566 | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006311 | 8178111 | Retrofitting | MVS | GO2021004032PH | 04/01/2021 | 244.44 | 0 | 244.44 | Purulia Division |  | 237.32 | 0 | 0 | 0 | 237.32 | 237.32 | 0 | 0 | 0 | 237.32 | 97.09 | 100
68 | PURULIA | SM/06941 | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006316 | 8136154 | Retrofitting | MVS | GO2021002277PH | 03/11/2020 | 68.58 | 0 | 68.58 | Purulia Division |  | 68.58 | 0 | 0 | 0 | 68.58 | 65.35 | 0 | 0 | 0 | 65.35 | 95.28 | 100
69 | PURULIA | SM/08584 | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006315 | 8224773 | Retrofitting | MVS | GO2021006092PH | 03/02/2021 | 474.74 | 0 | 474.74 | Purulia Division |  | 460.91 | 0 | 0 | 0 | 460.91 | 460.91 | 0 | 0 | 0 | 460.91 | 97.09 | 100
70 | PURULIA | SM/07839 | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006760 | 8178197 | Retrofitting | MVS | GO2021004546PH | 14/01/2021 | 175.07 | 0 | 175.07 | Purulia Division |  | 169.97 | 0 | 0 | 0 | 169.97 | 169.94 | 0 | 0 | 0 | 169.94 | 97.07 | 100
71 | PURULIA | SM/07840 | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006761 | 8178181 | Retrofitting | SVS | GO2021004545PH | 14/01/2021 | 10.75 | 0 | 10.75 | Purulia Division |  | 10.74 | 0 | 0 | 0 | 10.74 | 9.2 | 0 | 0 | 0 | 9.2 | 85.61 | 100
72 | PURULIA | SM/07841 | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006762 | 8178159 | Retrofitting | MVS | GO2021004544PH | 14/01/2021 | 120.54 | 0 | 120.54 | Purulia Division |  | 73.14 | 0 | 0 | 0 | 73.14 | 73.14 | 0 | 0 | 0 | 73.14 | 60.68 | 100
73 | PURULIA | SM/06939 | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006310 | 8136137 | Retrofitting | MVS | GO2021002274PH | 03/11/2020 | 81.16 | 0 | 81.16 | Purulia Division |  | 81.06 | 0 | 0 | 0 | 81.06 | 81.05 | 0 | 0 | 0 | 81.05 | 99.87 | 100
74 | PURULIA | SM/07567 | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006314 | 8178130 | Retrofitting | MVS | GO2021004033PH | 04/01/2021 | 168.98 | 0 | 168.98 | Purulia Division |  | 164.38 | 0 | 0 | 0 | 164.38 | 164.06 | 0 | 0 | 0 | 164.06 | 97.09 | 100
75 | PURULIA | SM/07838 | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006759 | 8178210 | Retrofitting | MVS | GO2021004547PH | 14/01/2021 | 73.08 | 0 | 73.08 | Purulia Division |  | 70.95 | 0 | 0 | 0 | 70.95 | 70.95 | 0 | 0 | 0 | 70.95 | 97.09 | 100
76 | PURULIA | SM/07565 | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006309 | 8178088 | Retrofitting | MVS | GO2021004030PH | 04/01/2021 | 159.92 | 0 | 159.92 | Purulia Division |  | 154.03 | 0 | 0 | 0 | 154.03 | 154.03 | 0 | 0 | 0 | 154.03 | 96.31 | 100
77 | PURULIA | SM/10720 | Sarbari Piped Water Supply Scheme to Accommodate FHTC | TSM/009012 | 40015235 | Augmentation | MVS | GO2223002002PH | 18/05/2022 | 1060.41 | 170.66 | 1231.07 | Purulia Division | Purulia Mechanical Division | 506.24 | 82.65 | 276.41 | 0 | 865.29 | 494.48 | 82.65 | 276.41 | 0 | 853.53 | 69.33 | 70
78 | PURULIA | SM/18915 | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | TSM/012987 | 0 | Augmentation | MVS | PHE/IV/3069/W-672/23 | 09/10/2023 | 148.7 | 518.03 | 666.74 | Purulia Division | Purulia Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
79 | PURULIA | SM/18528 | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | TSM/012586 | 40032566 | New | MVS | 2048/PHE-28011/65/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 26262.3 | 1328.97 | 27591.27 | Purulia Division | Purulia Mechanical Division | 604.14 | 0 | 0 | 0 | 604.14 | 5.38 | 0 | 0 | 0 | 5.38 | 0.02 | 1
80 | PURULIA | SM/18731 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | TSM/015985 | 40061528 | New | MVS | 2362/PHE-28011/213/2023-ESTT CELL-Dept. of PHE | 14/08/2023 | 133975.56 | 27782.75 | 161758.31 | Purulia Division | Purulia Mechanical Division | 1054.26 | 0 | 7955.82 | 0 | 9010.07 | 429.12 | 0 | 7229.04 | 0 | 7658.16 | 4.73 | 1
81 | PURULIA | SM/18654 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | TSM/017881 | 40061531 | New | MVS | 2193/PHE-28011/90/2023-ESTT CELL-Dept. of PHE | 01/08/2023 | 65922.47 | 0 | 65922.47 | Purulia Division | Purulia Mechanical Division | 255.18 | 0 | 0 | 0 | 255.18 | 17.87 | 0 | 0 | 0 | 17.87 | 0.03 | 1
82 | PURULIA | SM/15041 | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | TSM/019807 | 40061520 | Augmentation | MVS | GO2223013203PH | 04/02/2023 | 249.02 | 49.8 | 298.83 | Purulia Division | Purulia Mechanical Division | 122.9 | 8.12 | 0 | 0 | 131.02 | 18.13 | 7.2 | 0 | 0 | 25.33 | 8.48 | 9
83 | PURULIA | SM/15040 | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | TSM/019805 | 40061510 | Augmentation | MVS | GO2223013199PH | 04/02/2023 | 330.81 | 66.16 | 396.97 | Purulia Division | Purulia Mechanical Division | 78.27 | 0 | 0 | 0 | 78.27 | 13.05 | 0 | 0 | 0 | 13.05 | 3.29 | 6
84 | PURULIA | SM/15336 | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | TSM/019806 | 40061518 | Augmentation | MVS | GO2223013675PH | 09/02/2023 | 302.63 | 60.53 | 363.16 | Purulia Division | Purulia Mechanical Division | 80.74 | 0 | 0 | 0 | 80.74 | 18.7 | 0 | 0 | 0 | 18.7 | 5.15 | 7
85 | PURULIA | SM/15039 | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | TSM/019808 | 40061562 | Augmentation | MVS | GO2223013195PH | 04/02/2023 | 426.98 | 85.4 | 512.38 | Purulia Division | Purulia Mechanical Division | 229.11 | 0 | 0 | 0 | 229.11 | 69.1 | 0 | 0 | 0 | 69.1 | 13.49 | 8
Total | [9 empty] | 350526.73 | 52080.09 | 402606.82 |  |  | 22395.83 | 4089.33 | 17797.48 | 0 | 44282.64 | 18102.95 | 3969.83 | 16153.25 | 0 | 38226.02 | 9.49