## JJM Schemes Financial Status (H
JJM Schemes Financial Status (HOWRAH) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | HOWRAH | SM/18565 | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | TSM/017876 | 40034293 | Augmentation | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1051.92 | 124.01 | 1175.93 | Howrah Division | Electrical Division | 88.33 | 26.97 | 11.4 | 0 | 126.69 | 88.33 | 26.97 | 11.4 | 0 | 126.69 | 10.77 | 30
2 | HOWRAH | SM/19186 | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | TSM/019280 | 40042934 | Augmentation | MVS | 631/PHE-28011/220/2023-ESTT CELL-Dept. of PHE | 06/03/2024 | 45532.55 | 9787 | 55319.55 | Howrah Division | Electrical Division | 400.8 | 117.29 | 2725.8 | 0 | 3243.89 | 400.8 | 117.29 | 2725.8 | 0 | 3243.89 | 5.86 | 20
3 | HOWRAH | SM/13751 | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015610 | 40046910 | New | MVS | GO2223009823PH | 17/11/2022 | 644.06 | 56.53 | 700.58 | Howrah Division | Electrical Division | 217.55 | 21.81 | 62.07 | 0 | 301.43 | 217.55 | 23.49 | 62.07 | 0 | 303.12 | 43.27 | 73
4 | HOWRAH | SM/11159 | Makardaha PWSS with provision of FHTC in connection of Domjur Block | TSM/010688 | 40026097 | Augmentation | MVS | GO2223003772PH | 02/06/2022 | 1034.65 | 49.5 | 1084.15 | Howrah Division | Electrical Division | 476.9 | 44.07 | 74.08 | 0 | 595.05 | 476.9 | 44.07 | 74.08 | 0 | 595.05 | 54.89 | 75
5 | HOWRAH | SM/13770 | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | TSM/012056 | 40035464 | New | MVS | GO2223009883PH | 18/11/2022 | 735.59 | 56.53 | 792.12 | Howrah Division | Electrical Division | 321.52 | 37.06 | 15.21 | 0 | 373.79 | 325.68 | 37.94 | 15.21 | 0 | 378.84 | 47.83 | 76
6 | HOWRAH | SM/11790 | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | TSM/011795 | 40026680 | New | SVS | GO2223006084PH | 05/08/2022 | 162.21 | 53.07 | 215.28 | Howrah Division | Electrical Division | 123.01 | 29.83 | 4.58 | 0 | 157.42 | 127.17 | 31.6 | 4.58 | 0 | 163.35 | 75.88 | 98
7 | HOWRAH | SM/18848 | Source Augmentation of Chitnan Water Supply Scheme | TSM/021553 | 40067378 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 12.73 | 4.85 | 0 | 0 | 17.58 | 12.73 | 4.85 | 0 | 0 | 17.58 | 15.25 | 75
8 | HOWRAH | SM/12874 | Augmentation of Bamunhati Water Supply Scheme | TSM/012517 | 40046847 | Augmentation | MVS | GO2223008169PH | 23/09/2022 | 1185.08 | 118.82 | 1303.9 | Howrah Division | Electrical Division | 43.42 | 0 | 113.87 | 0 | 157.29 | 43.42 | 0 | 113.87 | 0 | 157.29 | 12.06 | 45
9 | HOWRAH | SM/10145 | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | TSM/008353 | 40009853 | Augmentation | MVS | GO2122009619PH | 10/02/2022 | 1074.46 | 18.15 | 1092.62 | Howrah Division | Electrical Division | 728.74 | 17.46 | 16.61 | 0 | 762.8 | 728.74 | 17.46 | 16.61 | 0 | 762.8 | 69.81 | 78
10 | HOWRAH | SM/10020 | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | TSM/008354 | 40009800 | Augmentation | MVS | GO2122007937PH | 05/01/2022 | 1486.8 | 37.42 | 1524.22 | Howrah Division | Electrical Division | 1148.38 | 35.88 | 118.74 | 0 | 1303 | 1148.38 | 36.76 | 118.74 | 0 | 1303.88 | 85.54 | 78
11 | HOWRAH | SM/09930 | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | TSM/008801 | 40009743 | Augmentation | MVS | GO2122006610PH | 09/12/2021 | 653.16 | 25.88 | 679.04 | Howrah Division | Electrical Division | 357.08 | 24.3 | 0 | 0 | 381.39 | 357.08 | 24.3 | 0 | 0 | 381.39 | 56.17 | 85
12 | HOWRAH | SM/15186 | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | TSM/011062 | 40041479 | Augmentation | MVS | GO2223013414PH | 07/02/2023 | 753.96 | 73 | 826.95 | Howrah Division | Electrical Division | 192.51 | 5.13 | 76.66 | 0 | 274.31 | 192.51 | 5.13 | 76.66 | 0 | 274.31 | 33.17 | 41
13 | HOWRAH | SM/09351 | Augmentation of Ground water based PWSS Bhurshit Bamunpara | TSM/008620 | 40011752 | Augmentation | MVS | GO2122005397PH | 12/11/2021 | 618.61 | 0 | 618.61 | Howrah Division | Electrical Division | 490.7 | 0 | 97.38 | 0 | 588.08 | 490.64 | 0 | 97.38 | 0 | 588.01 | 95.05 | 96
14 | HOWRAH | SM/09586 | Augmentation of Ground Water Based PWSS for Shekrahati | TSM/008595 | 40009699 | Augmentation | MVS | GO2122005672PH | 22/11/2021 | 576.22 | 23.98 | 600.2 | Howrah Division | Electrical Division | 347.15 | 13.45 | 43.11 | 0 | 403.71 | 347.15 | 13.45 | 43.11 | 0 | 403.71 | 67.26 | 98
15 | HOWRAH | SM/10146 | Augmentation of Ground water based PWSS Jujarsah | TSM/008639 | 40009676 | Augmentation | MVS | GO2122009618PH | 10/02/2022 | 1488.67 | 111.95 | 1600.62 | Howrah Division | Electrical Division | 628.93 | 6.57 | 276.33 | 0 | 911.83 | 628.93 | 6.57 | 276.33 | 0 | 911.83 | 56.97 | 66
16 | HOWRAH | SM/09350 | Augmentation of Ground water based PWSS Kanupat. | TSM/008622 | 40012002 | Augmentation | MVS | GO2122005391PH | 12/11/2021 | 390.73 | 23.98 | 414.71 | Howrah Division | Electrical Division | 231.46 | 8.07 | 11.87 | 9.37 | 260.76 | 231.46 | 8.07 | 11.87 | 9.37 | 260.76 | 62.88 | 98
17 | HOWRAH | SM/09349 | Augmentation of Ground water based PWSS Mankur Deulgram | TSM/008627 | 40009877 | Augmentation | MVS | GO2122005394PH | 12/11/2021 | 951.27 | 42.13 | 993.4 | Howrah Division | Electrical Division | 540.57 | 28.21 | 63.68 | 0 | 632.45 | 540.57 | 28.21 | 63.68 | 0 | 632.45 | 63.67 | 74
18 | HOWRAH | SM/09347 | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | TSM/008640 | 40009678 | Augmentation | MVS | GO2122005392PH | 12/11/2021 | 529.86 | 16.59 | 546.45 | Howrah Division | Electrical Division | 309.04 | 16.54 | 58.4 | 33.93 | 417.91 | 309.04 | 16.54 | 58.4 | 33.93 | 417.91 | 76.48 | 69
19 | HOWRAH | SM/09348 | Augmentation of Ground water based PWSS Pancharul | TSM/008635 | 40009873 | Augmentation | MVS | GO2122005395PH | 12/11/2021 | 738.12 | 23.98 | 762.1 | Howrah Division | Electrical Division | 490.99 | 9.99 | 33.66 | 0 | 534.65 | 490.99 | 9.99 | 33.66 | 0 | 534.65 | 70.15 | 95
20 | HOWRAH | SM/10143 | Augmentation of Ground water based PWSS Pulgustia | TSM/008637 | 40005287 | Augmentation | MVS | GO2122009587PH | 09/02/2022 | 652.4 | 56.32 | 708.72 | Howrah Division | Electrical Division | 570.45 | 54.68 | 62.95 | 0 | 688.08 | 570.45 | 55.56 | 62.95 | 0 | 688.96 | 97.21 | 98
21 | HOWRAH | SM/18567 | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | TSM/017891 | 40046852 | Augmentation | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1262.25 | 154.01 | 1416.25 | Howrah Division | Electrical Division | 382.65 | 30.7 | 0 | 0 | 413.35 | 382.65 | 30.7 | 0 | 0 | 413.35 | 29.19 | 60
22 | HOWRAH | SM/09428 | Augmentation of Ground water PWSS for Islampur | TSM/008589 | 40009796 | Augmentation | MVS | GO2122005477PH | 17/11/2021 | 730.26 | 23.99 | 754.25 | Howrah Division | Electrical Division | 387.16 | 20.38 | 27.6 | 0 | 435.14 | 387.16 | 20.38 | 27.6 | 0 | 435.14 | 57.69 | 81
23 | HOWRAH | SM/10021 | Augmentation of Kanpur Piped water supply scheme (Zone-II) | TSM/008513 | 40009622 | Augmentation | MVS | GO2122007939PH | 05/01/2022 | 1489.28 | 63.87 | 1553.14 | Howrah Division | Electrical Division | 565.14 | 40.86 | 48.78 | 39.93 | 694.72 | 565.14 | 40.86 | 48.78 | 39.93 | 694.72 | 44.73 | 95
24 | HOWRAH | SM/16947 | Augmentation of Keshabpur Water supply scheme | TSM/010465 | 40065699 | Augmentation | SVS | GO2223016574PH | 16/03/2023 | 857.9 | 0 | 857.9 | Howrah Division | Electrical Division | 160.37 | 8.98 | 60.32 | 0 | 229.68 | 160.37 | 8.98 | 60.32 | 0 | 229.68 | 26.77 | 85
25 | HOWRAH | SM/11271 | Augmentation of Khalatpur PWSS | TSM/008963 | 40021524 | Augmentation | MVS | GO2223004442PH | 24/06/2022 | 957.54 | 27.83 | 985.37 | Howrah Division | Electrical Division | 341.73 | 0 | 19.61 | 0 | 361.34 | 341.73 | 0 | 19.61 | 0 | 361.34 | 36.67 | 92
26 | HOWRAH | SM/10035 | Augmentation of Maju piped water supply scheme. | TSM/008091 | 40046828 | Augmentation | MVS | GO2122008405PH | 19/01/2022 | 1628.89 | 63.87 | 1692.75 | Howrah Division | Electrical Division | 1012.94 | 48.68 | 97.34 | 0 | 1158.96 | 1012.94 | 48.68 | 97.34 | 0 | 1158.96 | 68.47 | 5
27 | HOWRAH | SM/09720 | Augmentation of Nischintapur piped water supply scheme. | TSM/008092 | 40005599 | Augmentation | MVS | GO2122005968PH | 26/11/2021 | 589.85 | 0 | 589.85 | Howrah Division |  | 397.41 | 0 | 19.07 | 0 | 416.47 | 397.41 | 0 | 19.07 | 0 | 416.47 | 70.61 | 95
28 | HOWRAH | SM/19187 | Augmentation of surface water based Sankrail Piped water supply scheme | TSM/019257 | 40041744 | Augmentation | MVS | 631/PHE-28011/220/2023-ESTT CELL-Dept. of PHE | 06/03/2024 | 33316.69 | 663.61 | 33980.3 | Howrah Division | Electrical Division | 2005.14 | 0 | 1931.2 | 0 | 3936.34 | 2005.14 | 0 | 1931.2 | 0 | 3936.34 | 11.58 | 25
29 | HOWRAH | SM/18398 | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | TSM/010806 | 40048641 | Augmentation | MVS | 1847/PHE-28011/86/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 1809.87 | 77.28 | 1887.15 | Howrah Division |  | 787.64 | 17.22 | 229 | 0 | 1033.86 | 787.64 | 21.24 | 229 | 0 | 1037.88 | 55 | 67
30 | HOWRAH | SM/09429 | Aumentation of PWSS for Surikhali | TSM/008596 | 40009613 | Augmentation | SVS | GO2122005480PH | 17/11/2021 | 278.74 | 55.01 | 333.75 | Howrah Division | Electrical Division | 184.28 | 19.44 | 0 | 0 | 203.72 | 184.24 | 19.44 | 0 | 0 | 203.67 | 61.03 | 98
31 | HOWRAH | SM/16760 | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | TSM/011301 | 40046919 | New | MVS | GO2223015659PH | 13/03/2023 | 937.41 | 61.66 | 999.07 | Howrah Division | Electrical Division | 84.58 | 6.26 | 41.38 | 0 | 132.21 | 84.58 | 6.26 | 41.38 | 0 | 132.21 | 13.23 | 30
32 | HOWRAH | SM/11723 | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | TSM/011532 | 40046834 | Augmentation | MVS | GO2223005913PH | 02/08/2022 | 777.32 | 75.85 | 853.17 | Howrah Division | Electrical Division | 368.52 | 42.98 | 42.89 | 0 | 454.39 | 368.52 | 42.98 | 42.89 | 0 | 454.39 | 53.26 | 91
33 | HOWRAH | SM/11722 | Baniara PWSS with provision of FHTC connection | TSM/010919 | 40035122 | New | MVS | GO2223006005PH | 03/08/2022 | 707.69 | 95.75 | 803.44 | Howrah Division | Electrical Division | 378.21 | 69.75 | 41.18 | 0 | 489.14 | 378.21 | 69.75 | 41.18 | 0 | 489.14 | 60.88 | 95
34 | HOWRAH | SM/18747 | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | TSM/015233 | 40046942 | New | MVS | 2445/PHE-28011/50/2023-SCHM CELL-Dept. of PHE | 17/08/2023 | 1023.48 | 79.31 | 1102.79 | Howrah Division | Electrical Division | 84.58 | 16.12 | 0 | 0 | 100.69 | 84.58 | 16.12 | 0 | 0 | 100.69 | 9.13 | 25
35 | HOWRAH | SM/18566 | Baniban Zone-I Piped Water Supply Scheme | TSM/017947 | 40046957 | New | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1392.77 | 119.11 | 1511.88 | Howrah Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
36 | HOWRAH | SM/18564 | Baniban Zone-III Piped water Supply Scheme | TSM/018485 | 40059954 | New | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1490.28 | 116.68 | 1606.96 | Howrah Division | Electrical Division | 7.16 | 0 | 0 | 0 | 7.16 | 7.16 | 0 | 0 | 0 | 7.16 | 0.45 | 36
37 | HOWRAH | SM/13750 | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | TSM/015228 | 40059910 | New | SVS | GO2223009817PH | 17/11/2022 | 476.76 | 47.38 | 524.14 | Howrah Division | Electrical Division | 93.73 | 45.84 | 25.26 | 0 | 164.83 | 93.73 | 47.61 | 25.26 | 0 | 166.6 | 31.78 | 68
38 | HOWRAH | SM/18490 | Bedhi Chandrapur Piped Water Supply Scheme | TSM/012815 | 40047803 | New | SVS | PHE/IV/2003/W-613/23 | 24/07/2023 | 440.65 | 56.53 | 497.17 | Howrah Division | Electrical Division | 155.31 | 34.64 | 16.52 | 0 | 206.48 | 158.94 | 37.29 | 16.52 | 0 | 212.75 | 42.79 | 82
39 | HOWRAH | SM/14197 | Bhandardah PWSS with provision of FHTC connection | TSM/010904 | 40034422 | New | MVS | GO2223011800PH | 10/01/2023 | 1078.74 | 71.03 | 1149.77 | Howrah Division | Electrical Division | 521.91 | 31.74 | 104.23 | 0 | 657.88 | 521.91 | 32.65 | 104.23 | 0 | 658.79 | 57.3 | 80
40 | HOWRAH | SM/11711 | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | TSM/011760 | 40026100 | New | MVS | GO2223006004PH | 03/08/2022 | 1007.05 | 65.76 | 1072.81 | Howrah Division | Electrical Division | 303.16 | 28.89 | 70.74 | 0 | 402.8 | 303.16 | 28.89 | 70.74 | 0 | 402.8 | 37.55 | 74
41 | HOWRAH | SM/16557 | Chak Kadamtala Piped Water Supply scheme | TSM/016145 | 40046922 | New | SVS | GO2223015486PH | 10/03/2023 | 29.58 | 10.69 | 40.27 | Howrah Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
42 | HOWRAH | SM/08987 | Chakur water supply scheme. | TSM/008182 | 40011737 | New | SVS | GO2122004666PH | 29/10/2021 | 266.57 | 25.75 | 292.32 | Howrah Division | Electrical Division | 144.16 | 25.75 | 11.59 | 9.15 | 190.65 | 144.16 | 25.75 | 11.59 | 9.15 | 190.65 | 65.22 | 98
43 | HOWRAH | SM/11717 | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | TSM/011766 | 40035157 | New | SVS | GO2223006000PH | 03/08/2022 | 422.12 | 53.07 | 475.19 | Howrah Division | Electrical Division | 13.25 | 7.33 | 54.26 | 0 | 74.84 | 13.25 | 7.33 | 54.26 | 0 | 74.84 | 15.75 | 23
44 | HOWRAH | SM/15290 | Charkata Pukuria Piped Water Supply Scheme | TSM/016153 | 40047798 | New | SVS | GO2223013682PH | 09/02/2023 | 33.35 | 8.75 | 42.1 | Howrah Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | HOWRAH | SM/17196 | Dakshin Panchla Piped Water Supply Scheme | TSM/018488 | 40065177 | New | SVS | GO2223016248PH | 15/03/2023 | 205.14 | 31.45 | 236.59 | Howrah Division | Electrical Division | 2.6 | 0 | 4.98 | 0 | 7.58 | 2.6 | 0 | 4.98 | 0 | 7.58 | 3.2 | 23
46 | HOWRAH | SM/18562 | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | TSM/011637 | 40033952 | New | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1303.59 | 80.6 | 1384.19 | Howrah Division | Electrical Division | 380.74 | 21.01 | 57.85 | 0 | 459.6 | 380.74 | 24.12 | 57.85 | 0 | 462.72 | 33.43 | 90
47 | HOWRAH | SM/18560 | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | TSM/014806 | 40046851 | Augmentation | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1356.34 | 67.87 | 1424.21 | Howrah Division | Electrical Division | 481.42 | 6.52 | 94.66 | 0 | 582.61 | 481.42 | 6.52 | 94.66 | 0 | 582.61 | 40.91 | 64
48 | HOWRAH | SM/14154 | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | TSM/015277 | 40046826 | Augmentation | MVS | GO2223011612PH | 05/01/2023 | 1379.66 | 80.6 | 1460.26 | Howrah Division | Electrical Division | 386.74 | 0.32 | 316.82 | 0 | 703.89 | 386.74 | 0.32 | 316.82 | 0 | 703.89 | 48.2 | 90
49 | HOWRAH | SM/11894 | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | TSM/011932 | 40035837 | New | MVS | GO2223006444PH | 17/08/2022 | 664.96 | 95.75 | 760.71 | Howrah Division | Electrical Division | 216.77 | 30.75 | 51.77 | 0 | 299.29 | 216.77 | 30.75 | 51.77 | 0 | 299.29 | 39.34 | 70
50 | HOWRAH | SM/17175 | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | TSM/011909 | 40035817 | New | MVS | GO2223016573PH | 16/03/2023 | 860.95 | 125.74 | 986.69 | Howrah Division | Electrical Division | 233.33 | 26.11 | 174.43 | 0 | 433.87 | 233.33 | 26.11 | 174.43 | 0 | 433.87 | 43.97 | 61
51 | HOWRAH | SM/11893 | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | TSM/011933 | 40035848 | New | MVS | GO2223006408PH | 17/08/2022 | 922.8 | 95.75 | 1018.55 | Howrah Division | Electrical Division | 363.13 | 55.78 | 139.08 | 0 | 557.99 | 363.13 | 55.78 | 139.08 | 0 | 557.99 | 54.78 | 82
52 | HOWRAH | SM/14095 | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | TSM/010279 | 40046837 | Augmentation | MVS | GO2223010908PH | 14/12/2022 | 7698.57 | 513.14 | 8211.71 | Howrah Division | Electrical Division | 3005.98 | 373 | 483.01 | 0 | 3861.99 | 3005.98 | 373 | 483.01 | 0 | 3861.99 | 47.03 | 55
53 | HOWRAH | SM/13749 | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | TSM/015269 | 40046980 | New | MVS | GO2223009818PH | 17/11/2022 | 882.2 | 92.98 | 975.18 | Howrah Division | Electrical Division | 15.29 | 0 | 59.25 | 0 | 74.53 | 15.29 | 0 | 59.25 | 0 | 74.53 | 7.64 | 22
54 | HOWRAH | SM/11573 | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | TSM/011001 | 40034243 | New | MVS | GO2223005427PH | 22/07/2022 | 755.68 | 53.07 | 808.74 | Howrah Division | Electrical Division | 374.64 | 31.6 | 26.98 | 12.78 | 446 | 378.27 | 33.36 | 26.98 | 12.78 | 451.38 | 55.81 | 88
55 | HOWRAH | SM/17198 | Ghuteghari Piped Water Supply Scheme | TSM/018482 | 40060140 | New | SVS | GO2223016245PH | 15/03/2023 | 46.95 | 8.75 | 55.7 | Howrah Division | Electrical Division | 0.03 | 0.3 | 0 | 0 | 0.33 | 0.03 | 1.9 | 0 | 0 | 1.94 | 3.47 | 98
56 | HOWRAH | SM/13748 | Gopalpur Piped Water Supply Scheme | TSM/015625 | 40035279 | New | MVS | GO2223009822PH | 17/11/2022 | 483.25 | 55.91 | 539.15 | Howrah Division | Electrical Division | 27.22 | 25.6 | 40 | 0 | 92.81 | 27.22 | 26.01 | 40 | 0 | 93.22 | 17.29 | 30
57 | HOWRAH | SM/11221 | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | TSM/011679 | 40019537 | New | MVS | GO2223004145PH | 15/06/2022 | 561.36 | 51.34 | 612.7 | Howrah Division | Electrical Division | 286.68 | 35.44 | 20.78 | 0 | 342.91 | 290.3 | 37.2 | 20.78 | 0 | 348.29 | 56.85 | 90
58 | HOWRAH | SM/11641 | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | TSM/011056 | 40026716 | New | MVS | GO2223005650PH | 27/07/2022 | 924.11 | 73 | 997.11 | Howrah Division | Electrical Division | 257.45 | 7.79 | 194.3 | 0 | 459.54 | 257.45 | 7.79 | 194.3 | 0 | 459.54 | 46.09 | 60
59 | HOWRAH | SM/11222 | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | TSM/011678 | 40019543 | New | MVS | GO2223004148PH | 15/06/2022 | 421.36 | 47.87 | 469.24 | Howrah Division | Electrical Division | 213.86 | 30.65 | 20.98 | 0 | 265.5 | 213.86 | 31.53 | 20.98 | 0 | 266.37 | 56.77 | 70
60 | HOWRAH | SM/18719 | Ground Water Based Raspur PWSS | TSM/017956 | 40034499 | New | MVS | 2343/PHE-28011/241/2023-SCHM CELL-Dept. of PHE | 10/08/2023 | 1338.7 | 59.55 | 1398.26 | Howrah Division | Electrical Division | 236.47 | 26.15 | 65.35 | 0 | 327.97 | 236.47 | 26.15 | 65.35 | 0 | 327.97 | 23.46 | 32
61 | HOWRAH | SM/11458 | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | TSM/011688 | 40022472 | New | MVS | GO2223004707PH | 12/07/2022 | 1131 | 56.53 | 1187.53 | Howrah Division | Electrical Division | 787.58 | 50.8 | 68.99 | 0 | 907.37 | 787.58 | 52.56 | 68.99 | 0 | 909.13 | 76.56 | 98
62 | HOWRAH | SM/18561 | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | TSM/017917 | 40035292 | New | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1547.18 | 89.03 | 1636.21 | Howrah Division | Electrical Division | 342.23 | 28.09 | 54.97 | 0 | 425.29 | 342.23 | 28.09 | 54.97 | 0 | 425.29 | 25.99 | 50
63 | HOWRAH | SM/18748 | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. | TSM/015619 | 40035006 | New | MVS | 2445/PHE-28011/50/2023-SCHM CELL-Dept. of PHE | 17/08/2023 | 1274.99 | 125.74 | 1400.74 | Howrah Division | Electrical Division | 3.55 | 0 | 0 | 0 | 3.55 | 3.55 | 0 | 0 | 0 | 3.55 | 0.25 | 5
64 | HOWRAH | SM/13752 | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015621 | 40046906 | New | SVS | GO2223009830PH | 17/11/2022 | 869.31 | 58.26 | 927.57 | Howrah Division | Electrical Division | 343.58 | 34.97 | 114.81 | 0 | 493.36 | 343.58 | 34.92 | 114.81 | 0 | 493.31 | 53.18 | 99
65 | HOWRAH | SM/14155 | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | TSM/015622 | 40046937 | New | SVS | GO2223011545PH | 05/01/2023 | 1004.34 | 114.33 | 1118.67 | Howrah Division | Electrical Division | 368.29 | 34.3 | 116.56 | 0 | 519.15 | 368.29 | 34.3 | 116.56 | 0 | 519.15 | 46.41 | 86
66 | HOWRAH | SM/11720 | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | TSM/011550 | 40019542 | New | MVS | GO2223006002PH | 03/08/2022 | 587.01 | 53.07 | 640.07 | Howrah Division | Electrical Division | 150.29 | 32.23 | 8.15 | 0 | 190.67 | 150.29 | 32.82 | 8.15 | 0 | 191.26 | 29.88 | 60
67 | HOWRAH | SM/11719 | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | TSM/011570 | 40019540 | New | MVS | GO2223005998PH | 04/08/2022 | 874.69 | 58.26 | 932.95 | Howrah Division | Electrical Division | 339.35 | 38.48 | 29.4 | 0 | 407.23 | 339.35 | 39.37 | 29.4 | 0 | 408.11 | 43.74 | 55
68 | HOWRAH | SM/11793 | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | TSM/011548 | 40028638 | New | MVS | GO2223006088PH | 05/08/2022 | 838.12 | 58.26 | 896.37 | Howrah Division | Electrical Division | 217.59 | 44.37 | 30.29 | 0 | 292.26 | 217.59 | 44.37 | 30.29 | 0 | 292.26 | 32.6 | 75
69 | HOWRAH | SM/11000 | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | TSM/011600 | 40022103 | New | MVS | GO2223003720PH | 01/06/2022 | 884.08 | 81.91 | 965.98 | Howrah Division | Electrical Division | 477.6 | 52.27 | 99.1 | 12.42 | 641.39 | 477.6 | 53.46 | 99.1 | 12.42 | 642.58 | 66.52 | 70
70 | HOWRAH | SM/13747 | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | TSM/015623 | 40067485 | New | SVS | GO2223009819PH | 17/11/2022 | 396.67 | 55.91 | 452.58 | Howrah Division | Electrical Division | 113.91 | 5.55 | 0 | 0 | 119.46 | 113.91 | 5.55 | 0 | 0 | 119.46 | 26.4 | 40
71 | HOWRAH | SM/13629 | ICHAPUR PWSS | TSM/012520 | 40024405 | New | MVS | GO2223009619PH | 11/11/2022 | 533.41 | 53.07 | 586.48 | Howrah Division | Electrical Division | 152.02 | 34.65 | 71.06 | 0 | 257.73 | 152.02 | 34.65 | 71.06 | 0 | 257.73 | 43.95 | 53
72 | HOWRAH | SM/14865 | Jaynagar Piped Water Supply Scheme | TSM/018489 | 40036006 | New | MVS | GO2223012991PH | 03/02/2023 | 668.39 | 92.98 | 761.37 | Howrah Division | Electrical Division | 3.11 | 32.04 | 33.4 | 0 | 68.56 | 3.11 | 32.04 | 33.4 | 0 | 68.56 | 9 | 22
73 | HOWRAH | SM/16927 | Kamina Piped Water Supply Scheme with provision of FHTC | TSM/011290 | 40035081 | New | MVS | GO2223016575PH | 16/03/2023 | 680.83 | 41.11 | 721.94 | Howrah Division | Electrical Division | 354.85 | 32.89 | 93.25 | 0 | 480.99 | 354.85 | 34.67 | 93.25 | 0 | 482.77 | 66.87 | 90
74 | HOWRAH | SM/13847 | Khadinan Piped Water Supply Scheme | TSM/015626 | 40035291 | New | SVS | GO2223010076PH | 25/11/2022 | 729.97 | 61.38 | 791.35 | Howrah Division | Electrical Division | 107.84 | 10.79 | 7.95 | 0 | 126.58 | 107.84 | 10.79 | 7.95 | 0 | 126.58 | 16 | 72
75 | HOWRAH | SM/12270 | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | TSM/011009 | 40046926 | New | MVS | GO2223007393PH | 09/09/2022 | 1258.85 | 68 | 1326.85 | Howrah Division | Electrical Division | 342.67 | 18.7 | 77.01 | 0 | 438.38 | 346.29 | 18.7 | 77.01 | 0 | 442 | 33.31 | 75
76 | HOWRAH | SM/11892 | Khorda Etarai Piped Water Supply Scheme | TSM/012017 | 40046883 | New | MVS | GO2223006407PH | 17/08/2022 | 270.58 | 53.07 | 323.64 | Howrah Division | Electrical Division | 143.21 | 34.76 | 21.27 | 0 | 199.24 | 147.54 | 37.47 | 21.27 | 0 | 206.27 | 63.73 | 75
77 | HOWRAH | SM/15200 | Manirampur Piped Water Supply Scheme | TSM/016149 | 40065709 | New | SVS | GO2223013412PH | 07/02/2023 | 32.41 | 10.78 | 43.19 | Howrah Division | Electrical Division | 21.89 | 0.08 | 0 | 0 | 21.98 | 21.89 | 0.97 | 0 | 0 | 22.86 | 52.93 | 99
78 | HOWRAH | SM/15285 | Matinala Piped Water Supply Scheme | TSM/016162 | 40060055 | New | MVS | GO2223013681PH | 09/02/2023 | 735.04 | 62.01 | 797.05 | Howrah Division | Electrical Division | 459.68 | 4.07 | 35.21 | 0 | 498.96 | 459.68 | 4.07 | 35.21 | 0 | 498.96 | 62.6 | 97
79 | HOWRAH | SM/15288 | Mollar Chak Piped Water Supplu scheme | TSM/016154 | 40067394 | New | SVS | GO2223013679PH | 09/02/2023 | 35.61 | 8.75 | 44.36 | Howrah Division | Electrical Division | 21.47 | 0.09 | 0 | 0 | 21.57 | 21.47 | 0.09 | 0 | 0 | 21.57 | 48.62 | 99
80 | HOWRAH | SM/11007 | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | TSM/011420 | 40021882 | New | MVS | GO2223003721PH | 01/06/2022 | 644.61 | 53.07 | 697.67 | Howrah Division | Electrical Division | 324.89 | 20.65 | 40.48 | 0 | 386.02 | 324.89 | 22.41 | 40.48 | 0 | 387.79 | 55.58 | 66
81 | HOWRAH | SM/18563 | PANCHLA PIPED WATER SUPPLY SCHEME. | TSM/014879 | 40048944 | New | SVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1224.02 | 118.82 | 1342.84 | Howrah Division | Electrical Division | 350.04 | 25.38 | 92.17 | 0 | 467.59 | 350.04 | 26.89 | 92.17 | 0 | 469.1 | 34.93 | 72
82 | HOWRAH | SM/13768 | Paschim Panchla Piped Water Supply Scheme. | TSM/014766 | 40047300 | New | SVS | GO2223009879PH | 18/11/2022 | 627.09 | 89.13 | 716.22 | Howrah Division | Electrical Division | 244.71 | 70.45 | 34.36 | 0 | 349.52 | 244.71 | 72.21 | 34.36 | 0 | 351.29 | 49.05 | 92
83 | HOWRAH | SM/13848 | Patinan Piped Water Supply Scheme | TSM/015627 | 40047788 | New | SVS | GO2223010075PH | 25/11/2022 | 374.94 | 55.91 | 430.85 | Howrah Division | Electrical Division | 203.42 | 26.1 | 22.58 | 0 | 252.09 | 203.42 | 30.44 | 22.58 | 0 | 256.43 | 59.52 | 95
84 | HOWRAH | SM/11572 | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | TSM/010977 | 40034146 | New | MVS | GO2223005430PH | 22/07/2022 | 864.37 | 56.53 | 920.9 | Howrah Division | Electrical Division | 254.02 | 32.97 | 47.87 | 0 | 334.86 | 254.02 | 32.97 | 47.87 | 0 | 334.86 | 36.36 | 75
85 | HOWRAH | SM/15287 | Purbba Gazipur Piped Water Supply Scheme | TSM/016144 | 40048974 | New | SVS | GO2223013683PH | 09/02/2023 | 36.75 | 8.75 | 45.5 | Howrah Division | Electrical Division | 21.92 | 0.08 | 0 | 0 | 22 | 21.92 | 1.93 | 0 | 0 | 23.85 | 52.41 | 90
86 | HOWRAH | SM/11168 | Rampur PWSS | TSM/008769 | 40021516 | Augmentation | MVS | GO2223003775PH | 02/06/2022 | 586.44 | 27.83 | 614.27 | Howrah Division | Electrical Division | 343.3 | 0 | 0 | 0 | 343.3 | 343.3 | 1.76 | 0 | 0 | 345.06 | 56.17 | 92
87 | HOWRAH | SM/08966 | Rejuvenation of Amta Piped water supply scheme. | TSM/005366 | 40011765 | Augmentation | MVS | GO2122003932PH | 28/10/2021 | 2432.63 | 79.11 | 2511.74 | Howrah Division | Electrical Division | 2007.07 | 74.68 | 58.95 | 0 | 2140.7 | 2007.07 | 74.68 | 58.95 | 0 | 2140.7 | 85.23 | 98
88 | HOWRAH | SM/09105 | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS. | TSM/008212 | 40060370 | Retrofitting | MVS | GO2122004568PH | 28/10/2021 | 94.09 | 0 | 94.09 | Howrah Division |  | 4.48 | 0 | 0 | 0 | 4.48 | 4.48 | 0 | 0 | 0 | 4.48 | 4.76 | 95
89 | HOWRAH | SM/07880 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006749 | 40060321 | Retrofitting | MVS | GO2021004762PH | 19/01/2021 | 157.59 | 0 | 157.59 | Howrah Division |  | 143.94 | 0 | 0 | 0 | 143.94 | 143.94 | 0 | 0 | 0 | 143.94 | 91.34 | 99
90 | HOWRAH | SM/07882 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | TSM/006748 | 40060333 | Retrofitting | MVS | GO2021004752PH | 19/01/2021 | 174.48 | 0 | 174.48 | Howrah Division |  | 158.03 | 0 | 0 | 0 | 158.03 | 158.03 | 0 | 0 | 0 | 158.03 | 90.57 | 98
91 | HOWRAH | SM/07887 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006743 | 7940683 | Retrofitting | MVS | GO2021004738PH | 19/01/2021 | 147.18 | 0 | 147.18 | Howrah Division |  | 97.77 | 0 | 0 | 0 | 97.77 | 97.77 | 0 | 0 | 0 | 97.77 | 66.43 | 96
92 | HOWRAH | SM/07883 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | TSM/006746 | 7944255 | Retrofitting | MVS | GO2021004747PH | 19/01/2021 | 140.91 | 0 | 140.91 | Howrah Division |  | 104.21 | 0 | 14.47 | 0 | 118.68 | 104.21 | 0 | 14.47 | 0 | 118.68 | 84.22 | 98
93 | HOWRAH | SM/07881 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block | TSM/006747 | 7940691 | Retrofitting | MVS | GO2021004749PH | 19/01/2021 | 112.45 | 0 | 112.45 | Howrah Division |  | 90.64 | 0 | 0 | 0 | 90.64 | 90.64 | 0 | 0 | 0 | 90.64 | 80.6 | 98
94 | HOWRAH | SM/07886 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block | TSM/006742 | 7946393 | Retrofitting | MVS | GO2021004737PH | 19/01/2021 | 173.76 | 0 | 173.76 | Howrah Division |  | 130.19 | 0 | 3.08 | 0 | 133.27 | 130.19 | 0 | 3.08 | 0 | 133.27 | 76.7 | 98
95 | HOWRAH | SM/07885 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) | TSM/006744 | 7587002 | Retrofitting | MVS | GO2021004742PH | 19/01/2021 | 96.53 | 0 | 96.53 | Howrah Division |  | 60.65 | 0 | 0 | 0 | 60.65 | 60.65 | 0 | 0 | 0 | 60.65 | 62.83 | 91
96 | HOWRAH | SM/07884 | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | TSM/006745 | 7587002 | Retrofitting | SVS | GO2021004744PH | 19/01/2021 | 135.21 | 0 | 135.21 | Howrah Division |  | 91.45 | 0 | 0 | 0 | 91.45 | 91.45 | 0 | 0 | 0 | 91.45 | 67.63 | 91
97 | HOWRAH | SM/06784 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | TSM/005644 | 7395795 | Retrofitting | MVS | GO2021001377PH | 22/09/2020 | 78.15 | 0 | 78.15 | Howrah Division |  | 66.26 | 0 | 8.01 | 0 | 74.27 | 66.26 | 0 | 8.01 | 0 | 74.27 | 95.03 | 98
98 | HOWRAH | SM/06785 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bara Mahara and Kasra Mouza of Khosalpur piped water supply scheme (Phase-I) | TSM/005647 | 7741072 | Retrofitting | MVS | GO2021001382PH | 22/09/2020 | 83.99 | 0 | 83.99 | Howrah Division |  | 81.55 | 0 | 0 | 0 | 81.55 | 81.55 | 0 | 0 | 0 | 81.55 | 97.09 | 98
99 | HOWRAH | SM/06788 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | TSM/005652 | 6858751 | Retrofitting | MVS | GO2021001383PH | 22/09/2020 | 97.34 | 0 | 97.34 | Howrah Division |  | 62 | 0 | 0 | 0 | 62 | 62 | 0 | 0 | 0 | 62 | 63.69 | 96
100 | HOWRAH | SM/06713 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | TSM/005648 | 7741072 | Retrofitting | MVS | GO2021001234PH | 18/09/2020 | 63.09 | 0 | 63.09 | Howrah Division |  | 63.09 | 0 | 0 | 0 | 63.09 | 63.09 | 0 | 0 | 0 | 63.09 | 99.99 | 98
101 | HOWRAH | SM/07396 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | TSM/006292 | 7332672 | Retrofitting | MVS | GO2021003885PH | 30/12/2020 | 139.91 | 0 | 139.91 | Howrah Division |  | 135.83 | 0 | 0 | 0 | 135.83 | 135.83 | 0 | 0 | 0 | 135.83 | 97.09 | 98
102 | HOWRAH | SM/07395 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block | TSM/006293 | 7362165 | Retrofitting | MVS | GO2021003884PH | 30/12/2020 | 158.03 | 0 | 158.03 | Howrah Division |  | 140.97 | 0 | 0 | 0 | 140.97 | 140.97 | 0 | 0 | 0 | 140.97 | 89.2 | 97
103 | HOWRAH | SM/06717 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Darapur & Kurit Mouza Mouza of Khosalpur piped water supply scheme | TSM/005650 | 7741072 | Retrofitting | MVS | GO2021001238PH | 18/09/2020 | 80.45 | 0 | 80.45 | Howrah Division |  | 80.45 | 0 | 0 | 0 | 80.45 | 80.45 | 0 | 0 | 0 | 80.45 | 100 | 98
104 | HOWRAH | SM/07466 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | TSM/006299 | 6848085 | Retrofitting | MVS | GO2021003853PH | 30/12/2020 | 167.14 | 0 | 167.14 | Howrah Division |  | 151.27 | 0 | 0 | 0 | 151.27 | 151.27 | 0 | 0 | 0 | 151.27 | 90.5 | 95
105 | HOWRAH | SM/07465 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block | TSM/006300 | 0 | Retrofitting | MVS | GO2021003854PH | 30/12/2020 | 123.54 | 0 | 123.54 | Howrah Division |  | 117.7 | 0 | 0 | 0 | 117.7 | 117.7 | 0 | 0 | 0 | 117.7 | 95.27 | 100
106 | HOWRAH | SM/07464 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II | TSM/006294 | 7332604 | Retrofitting | MVS | GO2021003850PH | 30/12/2020 | 164.03 | 0 | 164.03 | Howrah Division |  | 107.56 | 0 | 0 | 0 | 107.56 | 107.56 | 0 | 0 | 0 | 107.56 | 65.57 | 95
107 | HOWRAH | SM/06786 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme (Phase-I) | TSM/005645 | 7404329 | Retrofitting | SVS | GO2021001381PH | 22/09/2020 | 94.88 | 0 | 94.88 | Howrah Division |  | 80 | 0 | 0 | 0 | 80 | 79.67 | 0 | 0 | 0 | 79.67 | 83.97 | 95
108 | HOWRAH | SM/06714 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme | TSM/005653 | 6821854 | Retrofitting | SVS | GO2021001235PH | 18/09/2020 | 79.55 | 0 | 79.55 | Howrah Division |  | 79.55 | 0 | 0 | 0 | 79.55 | 55.98 | 0 | 0 | 0 | 55.98 | 70.38 | 98
109 | HOWRAH | SM/06716 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur & Kotalpara Mouza of Khosalpur piped water supply scheme | TSM/005649 | 7741072 | Retrofitting | MVS | GO2021001237PH | 18/09/2020 | 93.35 | 0 | 93.35 | Howrah Division |  | 93.35 | 0 | 0 | 0 | 93.35 | 93.35 | 0 | 0 | 0 | 93.35 | 100 | 98
110 | HOWRAH | SM/06721 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | TSM/005656 | 7401894 | Retrofitting | SVS | GO2021001242PH | 18/09/2020 | 72.52 | 0 | 72.52 | Howrah Division |  | 31.58 | 0 | 0 | 13.48 | 45.07 | 31.58 | 0 | 0 | 13.48 | 45.07 | 62.15 | 98
111 | HOWRAH | SM/06787 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Manikara, Purash & Kanpur (part) of kanpur Rejuvenation piped water supply scheme (Phase-II) | TSM/005646 | 7404329 | Retrofitting | SVS | GO2021001378PH | 22/09/2020 | 90.51 | 0 | 90.51 | Howrah Division |  | 70 | 0 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 70 | 77.34 | 95
112 | HOWRAH | SM/07010 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | TSM/006295 | 7332631 | Retrofitting | MVS | GO2021002670PH | 18/11/2020 | 99.28 | 0 | 99.28 | Howrah Division |  | 96.39 | 0 | 0 | 0 | 96.39 | 96.08 | 0 | 0 | 0 | 96.08 | 96.77 | 99
113 | HOWRAH | SM/06715 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Nignan & Khari Geria Mouza of Kasmali piped water supply scheme | TSM/005654 | 6821854 | Retrofitting | MVS | GO2021001236PH | 18/09/2020 | 73.1 | 0 | 73.1 | Howrah Division |  | 60.45 | 0 | 0 | 0 | 60.45 | 21.96 | 0 | 0 | 0 | 21.96 | 30.04 | 98
114 | HOWRAH | SM/07467 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | TSM/006298 | 8266336 | Retrofitting | MVS | GO2021003851PH | 30/12/2020 | 232.33 | 0 | 232.33 | Howrah Division |  | 216.96 | 0 | 0 | 8.5 | 225.46 | 219.27 | 0 | 0 | 8.5 | 227.77 | 98.03 | 98
115 | HOWRAH | SM/06783 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | TSM/005643 | 7395795 | Retrofitting | MVS | GO2021001380PH | 22/09/2020 | 83.47 | 0 | 83.47 | Howrah Division |  | 83.47 | 0 | 0 | 0 | 83.47 | 83.47 | 0 | 0 | 0 | 83.47 | 100 | 98
116 | HOWRAH | SM/06789 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | TSM/005651 | 7741072 | Retrofitting | MVS | GO2021001379PH | 22/09/2020 | 59.15 | 0 | 59.15 | Howrah Division |  | 55.77 | 0 | 0 | 0 | 55.77 | 55.77 | 0 | 0 | 0 | 55.77 | 94.28 | 98
117 | HOWRAH | SM/06720 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme | TSM/005655 | 7401894 | Retrofitting | SVS | GO2021001241PH | 18/09/2020 | 92.54 | 0 | 92.54 | Howrah Division |  | 92.08 | 0 | 0 | 0 | 92.08 | 92.08 | 0 | 0 | 0 | 92.08 | 99.5 | 98
118 | HOWRAH | SM/06719 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sital Chak & Bankura Mouza of Sarda piped water supply scheme | TSM/005657 | 7401894 | Retrofitting | MVS | GO2021001240PH | 18/09/2020 | 67.6 | 0 | 67.6 | Howrah Division |  | 67.6 | 0 | 0 | 0 | 67.6 | 67.5 | 0 | 0 | 0 | 67.5 | 99.85 | 98
119 | HOWRAH | SM/07008 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | TSM/006296 | 0 | Retrofitting | SVS | GO2021002668PH | 18/11/2020 | 98.14 | 0 | 98.14 | Howrah Division |  | 98.14 | 0 | 0 | 0 | 98.14 | 90.55 | 0 | 0 | 0 | 90.55 | 92.26 | 90
120 | HOWRAH | SM/07009 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | TSM/006297 | 0 | Retrofitting | SVS | GO2021002669PH | 18/11/2020 | 50.47 | 0 | 50.47 | Howrah Division |  | 31.86 | 0 | 0 | 0 | 31.86 | 30.15 | 0 | 0 | 0 | 30.15 | 59.75 | 90
121 | HOWRAH | SM/06718 | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | TSM/005658 | 7573350 | Retrofitting | SVS | GO2021001239PH | 18/09/2020 | 94.59 | 0 | 94.59 | Howrah Division |  | 85 | 0 | 0 | 0 | 85 | 79.25 | 0 | 0 | 0 | 79.25 | 83.78 | 98
122 | HOWRAH | SM/06779 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | TSM/005665 | 8136072 | Retrofitting | SVS | GO2021001374PH | 22/09/2020 | 89.06 | 0 | 89.06 | Howrah Division |  | 89.06 | 0 | 0 | 0 | 89.06 | 89.06 | 0 | 0 | 0 | 89.06 | 100 | 100
123 | HOWRAH | SM/06780 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | TSM/005666 | 8136078 | Retrofitting | SVS | GO2021001373PH | 22/09/2020 | 77.58 | 0 | 77.58 | Howrah Division |  | 77.58 | 0 | 0 | 0 | 77.58 | 77.58 | 0 | 0 | 0 | 77.58 | 100 | 100
124 | HOWRAH | SM/06781 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | TSM/005667 | 8136084 | Retrofitting | SVS | GO2021001372PH | 22/09/2020 | 69.04 | 0 | 69.04 | Howrah Division |  | 69.04 | 0 | 0 | 0 | 69.04 | 69.04 | 0 | 0 | 0 | 69.04 | 99.99 | 100
125 | HOWRAH | SM/06782 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-IV) | TSM/005668 | 8136090 | Retrofitting | SVS | GO2021001371PH | 22/09/2020 | 68.15 | 0 | 68.15 | Howrah Division |  | 68.15 | 0 | 0 | 0 | 68.15 | 62.97 | 0 | 0 | 0 | 62.97 | 92.4 | 100
126 | HOWRAH | SM/06775 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | TSM/005661 | 8136056 | Retrofitting | SVS | GO2021001384PH | 22/09/2020 | 99.82 | 0 | 99.82 | Howrah Division |  | 98.35 | 0 | 0 | 0 | 98.35 | 98.35 | 0 | 0 | 0 | 98.35 | 98.53 | 98
127 | HOWRAH | SM/06776 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-II) | TSM/005662 | 8129225 | Retrofitting | SVS | GO2021001385PH | 22/09/2020 | 99.91 | 0 | 99.91 | Howrah Division |  | 99.91 | 0 | 0 | 0 | 99.91 | 99.91 | 0 | 0 | 0 | 99.91 | 100 | 100
128 | HOWRAH | SM/06777 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-III) | TSM/005663 | 8136064 | Retrofitting | SVS | GO2021001376PH | 22/09/2020 | 99.91 | 0 | 99.91 | Howrah Division |  | 99.91 | 0 | 0 | 0 | 99.91 | 100.74 | 0 | 0 | 0 | 100.74 | 100.82 | 100
129 | HOWRAH | SM/06778 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | TSM/005664 | 8136039 | Retrofitting | SVS | GO2021001375PH | 22/09/2020 | 99.91 | 0 | 99.91 | Howrah Division |  | 98 | 0 | 0 | 0 | 98 | 65.94 | 0 | 0 | 0 | 65.94 | 66 | 98
130 | HOWRAH | SM/06774 | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | TSM/005660 | 6858746 | Retrofitting | SVS | GO2021001386PH | 22/09/2020 | 69.51 | 0 | 69.51 | Howrah Division |  | 69.51 | 0 | 0 | 0 | 69.51 | 69.51 | 0 | 0 | 0 | 69.51 | 100 | 98
131 | HOWRAH | SM/07074 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) | TSM/006301 | 8136134 | Retrofitting | SVS | GO2021002852PH | 27/11/2020 | 99.1 | 0 | 99.1 | Howrah Division |  | 99.1 | 0 | 0 | 0 | 99.1 | 99.1 | 0 | 0 | 0 | 99.1 | 100 | 100
132 | HOWRAH | SM/07075 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | TSM/006302 | 8136140 | Retrofitting | SVS | GO2021002851PH | 27/11/2020 | 99.1 | 0 | 99.1 | Howrah Division |  | 99.1 | 0 | 0 | 0 | 99.1 | 99.1 | 0 | 0 | 0 | 99.1 | 100 | 98
133 | HOWRAH | SM/07076 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | TSM/006303 | 8136148 | Retrofitting | SVS | GO2021002850PH | 27/11/2020 | 99.1 | 0 | 99.1 | Howrah Division |  | 99.1 | 0 | 0 | 0 | 99.1 | 99.1 | 0 | 0 | 0 | 99.1 | 100 | 100
134 | HOWRAH | SM/07077 | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | TSM/006304 | 8136152 | Retrofitting | SVS | GO2021002849PH | 27/11/2020 | 99.1 | 0 | 99.1 | Howrah Division |  | 50.36 | 0 | 0 | 0 | 50.36 | 50.36 | 0 | 0 | 0 | 50.36 | 50.81 | 98
135 | HOWRAH | SM/11515 | Rudrapur PWSS with provision of FHTC connection. | TSM/010920 | 40046864 | New | MVS | GO2223005253PH | 19/07/2022 | 818.98 | 95.75 | 914.73 | Howrah Division | Electrical Division | 369.67 | 66.19 | 86.47 | 0 | 522.33 | 369.67 | 67.52 | 86.47 | 0 | 523.66 | 57.25 | 99
136 | HOWRAH | SM/12562 | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | TSM/011584 | 40046845 | New | MVS | GO2223007698PH | 14/09/2022 | 1746.56 | 95.75 | 1842.31 | Howrah Division | Electrical Division | 704.45 | 3.59 | 326.58 | 0 | 1034.62 | 704.45 | 3.59 | 326.58 | 0 | 1034.62 | 56.16 | 63
137 | HOWRAH | SM/15189 | Sankardari Mini Piped Water Supply Scheme | TSM/016140 | 40047795 | New | SVS | GO2223013413PH | 07/02/2023 | 34.86 | 10.86 | 45.72 | Howrah Division | Electrical Division | 21.85 | 0.08 | 0 | 0 | 21.93 | 21.85 | 0.97 | 0 | 0 | 22.81 | 49.89 | 99
138 | HOWRAH | SM/15289 | Sankhali Piped Water Supply Scheme | TSM/015853 | 40047784 | New | SVS | GO2223013680PH | 09/02/2023 | 310.66 | 61.99 | 372.64 | Howrah Division | Electrical Division | 187.62 | 26.36 | 10.53 | 0 | 224.5 | 187.62 | 27.31 | 10.53 | 0 | 225.45 | 60.5 | 91
139 | HOWRAH | SM/14866 | Sealdanga Piped Water Supply Scheme | TSM/018484 | 40065706 | New | MVS | GO2223012992PH | 03/02/2023 | 632.76 | 57 | 689.76 | Howrah Division | Electrical Division | 50.24 | 39.71 | 10.53 | 0 | 100.48 | 50.24 | 39.71 | 10.53 | 0 | 100.48 | 14.57 | 53
140 | HOWRAH | SM/15199 | Senpur Dwitiya Piped Water Supply Scheme | TSM/016151 | 40047280 | New | SVS | GO2223013411PH | 07/02/2023 | 32.22 | 10.87 | 43.09 | Howrah Division | Electrical Division | 21.02 | 0.71 | 0 | 0 | 21.73 | 21.02 | 0.71 | 0 | 0 | 21.73 | 50.42 | 99
141 | HOWRAH | SM/18426 | Sherpur Piped Water Supply Scheme | TSM/018486 | 40041402 | New | MVS | 1923/PHE-28011/146/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 1898.87 | 101.49 | 2000.35 | Howrah Division | Electrical Division | 352.73 | 40.42 | 51.56 | 0 | 444.71 | 352.73 | 40.42 | 51.56 | 0 | 444.71 | 22.23 | 45
142 | HOWRAH | SM/18193 | Shibgachhia Piped Water Supply Scheme | TSM/018487 | 40035984 | New | SVS | GO2223018120PH | 31/03/2023 | 468.77 | 38.97 | 507.75 | Howrah Division | Electrical Division | 140.57 | 23.47 | 2.4 | 0 | 166.44 | 140.57 | 23.47 | 2.4 | 0 | 166.44 | 32.78 | 80
143 | HOWRAH | SM/15284 | Shyamchak Mini Piped water Supply Scheme | TSM/016331 | 40047791 | New | SVS | GO2223013677PH | 09/02/2023 | 31.85 | 8.75 | 40.6 | Howrah Division | Electrical Division | 21.3 | 0.09 | 0 | 0 | 21.4 | 21.3 | 0.09 | 0 | 0 | 21.4 | 52.69 | 55
144 | HOWRAH | SM/13769 | Sibpur Piped Water Supply Scheme. | TSM/014685 | 40047719 | New | SVS | GO2223009882PH | 18/11/2022 | 544.81 | 53.07 | 597.87 | Howrah Division | Electrical Division | 201.68 | 43.02 | 14.63 | 0 | 259.33 | 206.01 | 44.78 | 14.63 | 0 | 265.41 | 44.39 | 81
145 | HOWRAH | SM/11853 | Sitapur Piper water Supply Scheme , Block- Udayanaryanpur, Dist- Howrah. | TSM/011491 | 40026705 | New | MVS | GO2223006294PH | 16/08/2022 | 998.07 | 58.26 | 1056.32 | Howrah Division | Electrical Division | 205.65 | 31.33 | 49.16 | 0 | 286.14 | 205.65 | 31.33 | 49.16 | 0 | 286.14 | 27.09 | 83
146 | HOWRAH | SM/14949 | Sonatala Piped Water Supply Scheme | TSM/015612 | 40046936 | New | MVS | GO2223012956PH | 03/02/2023 | 673.38 | 55.91 | 729.29 | Howrah Division | Electrical Division | 296.16 | 27.59 | 51.96 | 0 | 375.72 | 299.79 | 28.51 | 51.96 | 0 | 380.26 | 52.14 | 78
147 | HOWRAH | SM/18882 | Source Augmentaion of kulgacchi Water Supply Scheme | TSM/021380 | 40067372 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 162.52 | 89.03 | 251.54 | Howrah Division | Electrical Division | 79.8 | 54.65 | 0 | 0 | 134.45 | 79.8 | 54.65 | 0 | 0 | 134.45 | 53.45 | 95
148 | HOWRAH | SM/18883 | Source Augmentation of Amragari Water Supply Scheme | TSM/021379 | 40067401 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 430.61 | 61.38 | 491.99 | Howrah Division | Electrical Division | 29.12 | 48.83 | 0 | 0 | 77.95 | 29.12 | 48.83 | 0 | 0 | 77.95 | 15.84 | 50
149 | HOWRAH | SM/18885 | Source Augmentation of Balichak Water Supply Scheme | TSM/021377 | 40067396 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 115.78 | 61.38 | 177.16 | Howrah Division | Electrical Division | 28.06 | 31.24 | 0 | 0 | 59.29 | 28.06 | 31.24 | 0 | 0 | 59.29 | 33.47 | 50
150 | HOWRAH | SM/18850 | Source Augmentation of Bauria Water Supply Scheme | TSM/021551 | 40067375 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 79.14 | 10.4 | 0 | 0 | 89.54 | 79.14 | 10.4 | 0 | 0 | 89.54 | 77.7 | 92
151 | HOWRAH | SM/18845 | Source Augmentation of Beldubi Water Supply Scheme | TSM/021363 | 40067384 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 121.41 | 33.73 | 155.14 | Howrah Division | Electrical Division | 29.53 | 4.8 | 0 | 0 | 34.34 | 29.53 | 4.8 | 0 | 0 | 34.34 | 22.13 | 91
152 | HOWRAH | SM/18846 | Source Augmentation of Bikihakola Water Supply Scheme | TSM/021345 | 40067382 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 425.05 | 33.72 | 458.77 | Howrah Division | Electrical Division | 63.64 | 14.53 | 0 | 0 | 78.17 | 63.64 | 14.53 | 0 | 0 | 78.17 | 17.04 | 36
153 | HOWRAH | SM/18849 | Source Augmentation of Garbhabanipur Water Supply Scheme | TSM/021552 | 40067377 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 14.62 | 12.18 | 0 | 0 | 26.8 | 14.62 | 12.18 | 0 | 0 | 26.8 | 23.25 | 60
154 | HOWRAH | SM/18843 | Source Augmentation of Gobindapur Piped Water Supply Scheme | TSM/021367 | 40067388 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 111.55 | 33.73 | 145.28 | Howrah Division | Electrical Division | 56.45 | 19.93 | 0 | 0 | 76.38 | 56.45 | 19.93 | 0 | 0 | 76.38 | 52.58 | 80
155 | HOWRAH | SM/18842 | Source Augmentation of Laskarpur Piped Water Supply Scheme | TSM/021371 | 40067389 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 154.56 | 67.45 | 222.01 | Howrah Division | Electrical Division | 32.32 | 58.48 | 0 | 0 | 90.79 | 32.32 | 58.48 | 0 | 0 | 90.79 | 40.9 | 95
156 | HOWRAH | SM/18841 | Source Augmentation of Majhu Khetra Water Supply Scheme | TSM/021407 | 40067478 | Augmentation | SVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 16.09 | 0 | 0 | 0 | 16.09 | 16.09 | 0 | 0 | 0 | 16.09 | 13.96 | 98
157 | HOWRAH | SM/18847 | Source Augmentation of Nakubar Water Supply Scheme | TSM/021308 | 40067379 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 127.82 | 61.38 | 189.2 | Howrah Division | Electrical Division | 11.44 | 9.56 | 0 | 0 | 21 | 11.44 | 9.56 | 0 | 0 | 21 | 11.1 | 90
158 | HOWRAH | SM/18844 | Source Augmentation of Sahapur Piped Water Supply Scheme | TSM/021366 | 40067385 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 119.08 | 33.73 | 152.8 | Howrah Division | Electrical Division | 1.31 | 6.26 | 0 | 0 | 7.57 | 1.31 | 6.26 | 0 | 0 | 7.57 | 4.95 | 63
159 | HOWRAH | SM/18884 | Source Augmentation of Sarda Water Supply Scheme | TSM/021378 | 40067398 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 77.61 | 61.38 | 138.99 | Howrah Division | Electrical Division | 0.78 | 4.13 | 0 | 0 | 4.9 | 0.78 | 4.13 | 0 | 0 | 4.9 | 3.53 | 22
160 | HOWRAH | SM/08582 | Summary of Capital cost for Function house hold tap connection FHTC and remainng laying distribution system in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block (Phase-I) | TSM/005659 | 7607488 | Retrofitting | MVS | GO2021007647PH | 26/02/2021 | 3304.1 | 0 | 3304.1 | Howrah Division |  | 2630.43 | 0 | 56 | 0 | 2686.42 | 2630.17 | 0 | 56 | 0 | 2686.17 | 81.3 | 98
161 | HOWRAH | SM/11574 | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | TSM/011292 | 40035101 | New | MVS | GO2223005402PH | 22/07/2022 | 658.55 | 41.11 | 699.66 | Howrah Division | Electrical Division | 393.32 | 37.4 | 35.17 | 0 | 465.9 | 393.32 | 39.16 | 35.17 | 0 | 467.66 | 66.84 | 99
162 | HOWRAH | SM/11718 | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | TSM/011761 | 40047829 | New | SVS | GO2223006001PH | 03/08/2022 | 649.85 | 56.53 | 706.38 | Howrah Division | Electrical Division | 2.69 | 0 | 65.44 | 0 | 68.13 | 2.69 | 0 | 65.44 | 0 | 68.13 | 9.65 | 22
163 | HOWRAH | SM/18914 | Uttar Manasri Piped Water Supply Scheme. | TSM/004182 | 40046915 | New | MVS | PHE/IV/3070/W-669/23 | 09/10/2023 | 998.15 | 48.37 | 1046.52 | Howrah Division | Electrical Division | 354.83 | 17.8 | 149.85 | 0 | 522.47 | 354.83 | 17.8 | 149.85 | 0 | 522.47 | 49.92 | 56
Total | [9 empty] | 175127.46 | 17406.96 | 192534.42 |  |  | 41725.68 | 3040.9 | 10551.24 | 139.57 | 55457.38 | 41648.46 | 3096.21 | 10551.24 | 139.57 | 55435.47 | 28.79