## JJM Schemes Financial Status (S
JJM Schemes Financial Status (SOUTH 24 PARAGANAS) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | SOUTH 24 PARAGANAS | SM/18391 | AUGMENTATION OF CHAR BAIDYARABAD PIPED WATER SUPPLY SCHEME, BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/015090 | 40032978 | Augmentation | SVS | 1814/PHE-28011/191/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1065.81 | 70.13 | 1135.95 | Alipore Division | South 24 Pgs Mechanical Division | 432.14 | 13.14 | 74.75 | 0 | 520.04 | 301.06 | 13.14 | 68.96 | 0 | 383.17 | 33.73 | 13
2 | SOUTH 24 PARAGANAS | SM/13441 | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | TSM/014213 | 40049611 | Augmentation | MVS | GO2223009216PH | 02/11/2022 | 722.1 | 65.66 | 787.76 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 349.67 | 34.05 | 15.43 | 0 | 399.15 | 349.67 | 34.05 | 15.43 | 0 | 399.15 | 50.67 | 36
3 | SOUTH 24 PARAGANAS | SM/13766 | Augmentation of ground water based PADMAJALA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | TSM/014212 | 40033393 | Augmentation | MVS | GO2223009884PH | 18/11/2022 | 567.51 | 43.78 | 611.29 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 214.07 | 21.81 | 10.85 | 0 | 246.73 | 214.07 | 21.81 | 10.85 | 0 | 246.73 | 40.36 | 38
4 | SOUTH 24 PARAGANAS | SM/18575 | BHAGABANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/017739 | 40047327 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1258.05 | 81.54 | 1339.6 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 233.25 | 9.53 | 18.77 | 0 | 261.55 | 233.25 | 9.53 | 18.77 | 0 | 261.55 | 19.52 | 24
5 | SOUTH 24 PARAGANAS | SM/13771 | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016026 | 40033771 | Augmentation | MVS | GO2223009894PH | 18/11/2022 | 771.07 | 73.27 | 844.34 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 115.42 | 4.52 | 37.99 | 0 | 157.94 | 115.42 | 4.52 | 37.99 | 0 | 157.94 | 18.71 | 15
6 | SOUTH 24 PARAGANAS | SM/18266 | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | TSM/017506 | 40034006 | Augmentation | MVS | 1588/PHE-28011/165/2023-SCHM CELL-Dept. of PHE | 21/06/2023 | 1020.06 | 83.86 | 1103.92 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.82 | 0 | 106 | 0 | 108.82 | 2.82 | 0 | 106 | 0 | 108.82 | 9.86 | 2
7 | SOUTH 24 PARAGANAS | SM/13297 | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | TSM/015373 | 40060615 | Augmentation | SVS | GO2223008851PH | 17/10/2022 | 143.51 | 23.69 | 167.2 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 129.27 | 2.92 | 0 | 0 | 132.19 | 129.27 | 2.92 | 0 | 0 | 132.19 | 79.06 | 37
8 | SOUTH 24 PARAGANAS | SM/11988 | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | TSM/011226 | 40025993 | New | SVS | GO2223006885PH | 01/09/2022 | 280.13 | 71.66 | 351.79 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 165.32 | 15.52 | 3.34 | 0 | 184.19 | 165.32 | 15.52 | 3.34 | 0 | 184.19 | 52.36 | 68
9 | SOUTH 24 PARAGANAS | SM/13801 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011610 | 40034037 | New | SVS | GO2223009957PH | 22/11/2022 | 778.37 | 75.49 | 853.87 | Alipore Division | South 24 Pgs Mechanical Division | 183.62 | 0 | 0 | 0 | 183.62 | 136.94 | 0 | 0 | 0 | 136.94 | 16.04 | 5
10 | SOUTH 24 PARAGANAS | SM/15754 | JAGULGACHHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018474 | 40053199 | Augmentation | MVS | GO2223014332PH | 20/02/2023 | 912.31 | 79.24 | 991.55 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 144.38 | 0 | 39.26 | 0 | 183.64 | 144.38 | 0 | 38.29 | 0 | 182.67 | 18.42 | 5
11 | SOUTH 24 PARAGANAS | SM/13512 | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | TSM/014455 | 40034176 | Augmentation | MVS | GO2223009268PH | 02/11/2022 | 725.39 | 71.63 | 797.02 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 411.92 | 14.26 | 12.69 | 0 | 438.87 | 288.99 | 14.26 | 12.69 | 0 | 315.94 | 39.64 | 24
12 | SOUTH 24 PARAGANAS | SM/13772 | KHODAHATI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016076 | 40034339 | Augmentation | MVS | GO2223009896PH | 18/11/2022 | 843.55 | 72.54 | 916.1 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 166.2 | 38.53 | 23.15 | 0 | 227.88 | 166.2 | 38.53 | 23.15 | 0 | 227.88 | 24.88 | 21
13 | SOUTH 24 PARAGANAS | SM/18548 | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018471 | 40053171 | Augmentation | MVS | 2059/PHE-28011/199/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1401.47 | 79.83 | 1481.3 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 37.42 | 0 | 37.42 | 0 | 0 | 37.42 | 0 | 37.42 | 2.53 | 0
14 | SOUTH 24 PARAGANAS | SM/13773 | RAYPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016075 | 40033124 | Augmentation | MVS | GO2223009897PH | 18/11/2022 | 856.71 | 73.33 | 930.04 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 238.65 | 32.86 | 39.17 | 0 | 310.69 | 119.49 | 15.55 | 39.17 | 0 | 174.21 | 18.73 | 15
15 | SOUTH 24 PARAGANAS | SM/18501 | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018470 | 40053155 | Augmentation | SVS | 2036/PHE-28011/194/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1746.63 | 81.9 | 1828.53 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 176.63 | 0 | 38.29 | 0 | 214.92 | 176.63 | 0 | 20.28 | 0 | 196.92 | 10.77 | 19
16 | SOUTH 24 PARAGANAS | SM/13307 | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | TSM/015202 | 40034212 | Augmentation | MVS | GO2223008842PH | 17/10/2022 | 909.11 | 71.05 | 980.16 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 236.47 | 16.48 | 54.43 | 0 | 307.38 | 236.47 | 16.48 | 54.43 | 0 | 307.38 | 31.36 | 24
17 | SOUTH 24 PARAGANAS | SM/10560 | ADDITIONAL WORK FOR RETROFITTING OF DISTRIBUTION SYSTEM FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ADDITIONAL HOUSEHOLD (1219 NOS.) IN EXCESS OF IMIS IN CONNECTION FOR LOT NO. - 126 WATER SUPPLY SCHEME INCLUDING ONE YEAR OPERATION AND MAI | TSM/010677 | 7773669 | Augmentation | SVS | GO2223000339PH | 18/04/2022 | 73.48 | 0 | 73.48 | Alipore Division |  | 0 | 0 | 0 | 11.34 | 11.34 | 0 | 0 | 0 | 11.34 | 11.34 | 15.43 | 22
18 | SOUTH 24 PARAGANAS | SM/14857 | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018118 | 40047332 | Augmentation | MVS | GO2223012959PH | 03/02/2023 | 923.77 | 75.24 | 999.01 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 15.53 | 0 | 18.9 | 0 | 34.43 | 0 | 0 | 18.9 | 0 | 18.9 | 1.89 | 9
19 | SOUTH 24 PARAGANAS | SM/15477 | AUGMENTATION & RETROFITTING OF ADHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017798 | 40037078 | Augmentation | MVS | GO2223013247PH | 04/02/2023 | 210.05 | 35.83 | 245.88 | Alipore Division | South 24 Pgs Mechanical Division | 17.91 | 0 | 15.31 | 0 | 33.22 | 17.91 | 0 | 0 | 0 | 17.91 | 7.28 | 3
20 | SOUTH 24 PARAGANAS | SM/15959 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/018328 | 40060355 | Augmentation | MVS | GO2223014530PH | 22/02/2023 | 670.27 | 45 | 715.27 | Alipore Division | South 24 Pgs Mechanical Division | 192.85 | 5.3 | 22.62 | 0 | 220.77 | 116.78 | 5.3 | 22.62 | 0 | 144.69 | 20.23 | 3
21 | SOUTH 24 PARAGANAS | SM/15564 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/018260 | 40060406 | Augmentation | SVS | GO2223013881PH | 15/02/2023 | 340.52 | 71.66 | 412.18 | Alipore Division | South 24 Pgs Mechanical Division | 95.25 | 43.16 | 18.27 | 0 | 156.67 | 95.25 | 33.51 | 18.27 | 0 | 147.02 | 35.67 | 32
22 | SOUTH 24 PARAGANAS | SM/15052 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/018315 | 40037085 | Augmentation | MVS | GO2223013022PH | 03/02/2023 | 931.52 | 67.5 | 999.02 | Alipore Division | South 24 Pgs Mechanical Division | 141.87 | 0 | 37.06 | 0 | 178.94 | 101.27 | 0 | 37.06 | 0 | 138.34 | 13.85 | 2
23 | SOUTH 24 PARAGANAS | SM/15972 | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-VII) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/018307 | 40060413 | Augmentation | MVS | GO2223014510PH | 22/02/2023 | 592.96 | 45 | 637.96 | Alipore Division | South 24 Pgs Mechanical Division | 82.37 | 0 | 41.55 | 0 | 123.93 | 4.64 | 0 | 41.55 | 0 | 46.19 | 7.24 | 4
24 | SOUTH 24 PARAGANAS | SM/15963 | Augmentation & Retrofitting of Basanti Zone-IX PWSS for providing Functional Household tap Connection (FHTC) Block - Basanti under canning Sub - Division, PHE dte. | TSM/018392 | 40049248 | Augmentation | SVS | GO2223014514PH | 22/02/2023 | 687 | 67.5 | 754.5 | Alipore Division | South 24 Pgs Mechanical Division | 119.64 | 10.24 | 84.97 | 0 | 214.85 | 119.64 | 10.24 | 84.97 | 0 | 214.85 | 28.48 | 5
25 | SOUTH 24 PARAGANAS | SM/15503 | AUGMENTATION & RETROFITTING OF BHARATGARH PWSS FOR PROVIDING FHTC BLOCK-BASANTI | TSM/017793 | 40037005 | Augmentation | MVS | GO2223013842PH | 15/02/2023 | 252.51 | 71.66 | 324.17 | Alipore Division | South 24 Pgs Mechanical Division | 36.35 | 14.74 | 0 | 0 | 51.09 | 16.25 | 14.74 | 0 | 0 | 30.99 | 9.56 | 7
26 | SOUTH 24 PARAGANAS | SM/15088 | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017975 | 40037088 | Augmentation | MVS | GO2223013243PH | 04/02/2023 | 538.67 | 46.35 | 585.02 | Alipore Division | South 24 Pgs Mechanical Division | 66.04 | 0 | 109.08 | 0 | 175.12 | 66.04 | 0 | 109.08 | 0 | 175.12 | 29.93 | 4
27 | SOUTH 24 PARAGANAS | SM/15043 | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/018243 | 40037087 | Augmentation | SVS | GO2223013021PH | 03/02/2023 | 599.33 | 67.5 | 666.83 | Alipore Division | South 24 Pgs Mechanical Division | 78.41 | 48.85 | 1 | 0 | 128.26 | 71.55 | 48.85 | 1 | 0 | 121.4 | 18.21 | 14
28 | SOUTH 24 PARAGANAS | SM/15044 | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | TSM/017808 | 40060368 | Augmentation | SVS | GO2223013242PH | 04/02/2023 | 243.58 | 71.66 | 315.24 | Alipore Division | South 24 Pgs Mechanical Division | 16.52 | 0 | 85.25 | 0 | 101.78 | 16.52 | 0 | 85.25 | 0 | 101.78 | 32.29 | 3
29 | SOUTH 24 PARAGANAS | SM/15198 | AUGMENTATION & RETROFITTING OF HARBHANGI PWSS FOR PROVING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017821 | 40037017 | Augmentation | MVS | GO2223013319PH | 06/02/2023 | 305.47 | 71.66 | 377.13 | Alipore Division | South 24 Pgs Mechanical Division | 35.96 | 33.2 | 201.86 | 0 | 271.02 | 4.31 | 33.2 | 201.86 | 0 | 239.37 | 63.47 | 6
30 | SOUTH 24 PARAGANAS | SM/15471 | AUGMENTATION & RETROFITTING OF HOMRAPOLTA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017902 | 40037076 | Augmentation | MVS | GO2223013249PH | 04/02/2023 | 236.81 | 23.18 | 259.99 | Alipore Division | South 24 Pgs Mechanical Division | 3.5 | 0 | 27.37 | 0 | 30.87 | 3.5 | 0 | 27.37 | 0 | 30.87 | 11.87 | 5
31 | SOUTH 24 PARAGANAS | SM/15081 | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017965 | 40037070 | Augmentation | MVS | GO2223013241PH | 04/02/2023 | 505.19 | 92.7 | 597.89 | Alipore Division | South 24 Pgs Mechanical Division | 255.99 | 39.24 | 0 | 0 | 295.22 | 186.3 | 39.24 | 0 | 0 | 225.54 | 37.72 | 4
32 | SOUTH 24 PARAGANAS | SM/15045 | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017928 | 40037072 | Augmentation | SVS | GO2223013238PH | 04/02/2023 | 208.41 | 23.69 | 232.1 | Alipore Division | South 24 Pgs Mechanical Division | 18.77 | 0 | 49.71 | 0 | 68.48 | 18.77 | 0 | 49.71 | 0 | 68.48 | 29.5 | 2
33 | SOUTH 24 PARAGANAS | SM/15966 | Augmentation & Retrofitting of Purba Radhanagar (Zone- I) PWSS for Providing (FHTC) , Block - Gosaba | TSM/018318 | 40049244 | Augmentation | SVS | GO2223014511PH | 22/02/2023 | 478.23 | 35.83 | 514.06 | Alipore Division | South 24 Pgs Mechanical Division | 175.39 | 0 | 20.71 | 0 | 196.1 | 83.92 | 0 | 20.71 | 0 | 104.64 | 20.36 | 3
34 | SOUTH 24 PARAGANAS | SM/15974 | AUGMENTATION & RETROFITTING OF PURBA RADHANAGAR (ZONE-III) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/018287 | 40049281 | Augmentation | SVS | GO2223014518PH | 22/02/2023 | 566.51 | 71.66 | 638.17 | Alipore Division | South 24 Pgs Mechanical Division | 216.13 | 0 | 62.81 | 0 | 278.94 | 171.04 | 0 | 62.81 | 0 | 233.84 | 36.64 | 3
35 | SOUTH 24 PARAGANAS | SM/15501 | AUGMENTATION & RETROFITTING OF UTTAR ANGADBERIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017945 | 40060318 | Augmentation | MVS | GO2223013829PH | 15/02/2023 | 213.99 | 23.69 | 237.68 | Alipore Division | South 24 Pgs Mechanical Division | 1.52 | 0 | 59.66 | 0 | 61.18 | 0 | 0 | 59.66 | 0 | 59.66 | 25.1 | 3
36 | SOUTH 24 PARAGANAS | SM/15055 | AUGMENTATION AND RETROFITTING OF ADHIA (PART-B) (KAKRADAHA)PWSS FOR PROVIDING FHTC, BLOCK - CANNING-I | TSM/018331 | 40037080 | Augmentation | MVS | GO2223013027PH | 03/02/2023 | 548.4 | 67.5 | 615.9 | Alipore Division | South 24 Pgs Mechanical Division | 44.82 | 4.82 | 0 | 0 | 49.64 | 3.88 | 4.82 | 0 | 0 | 8.7 | 1.41 | 5
37 | SOUTH 24 PARAGANAS | SM/15097 | AUGMENTATION AND RETROFITTING OF ATHARABEKI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017665 | 40037086 | Augmentation | MVS | GO2223013240PH | 04/02/2023 | 304.6 | 31.12 | 335.72 | Alipore Division | South 24 Pgs Mechanical Division | 62.95 | 4.2 | 25.3 | 0 | 92.45 | 62.95 | 4.2 | 0 | 0 | 67.15 | 20 | 13
38 | SOUTH 24 PARAGANAS | SM/15500 | AUGMENTATION AND RETROFITTING OF BANIBADABELEKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017911 | 40060299 | Augmentation | MVS | GO2223013834PH | 15/02/2023 | 250.12 | 23.18 | 273.3 | Alipore Division | South 24 Pgs Mechanical Division | 91.4 | 0 | 46.38 | 0 | 137.78 | 89.65 | 0 | 43.43 | 0 | 133.08 | 48.69 | 4
39 | SOUTH 24 PARAGANAS | SM/15490 | AUGMENTATION AND RETROFITTING OF BANSRA (ZONE - I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017940 | 40060448 | Augmentation | SVS | GO2223013836PH | 15/02/2023 | 465.74 | 47.38 | 513.12 | Alipore Division | South 24 Pgs Mechanical Division | 139.79 | 0 | 210.48 | 0 | 350.26 | 86.2 | 0 | 210.48 | 0 | 296.68 | 57.82 | 2
40 | SOUTH 24 PARAGANAS | SM/15053 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | TSM/018323 | 40037084 | Augmentation | MVS | GO2223013030PH | 03/02/2023 | 929.92 | 67.5 | 997.42 | Alipore Division | South 24 Pgs Mechanical Division | 10.45 | 0 | 128.05 | 0 | 138.5 | 8.83 | 0 | 128.05 | 0 | 136.88 | 13.72 | 2
41 | SOUTH 24 PARAGANAS | SM/15975 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-IV) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | TSM/018297 | 40060380 | Augmentation | MVS | GO2223014527PH | 22/02/2023 | 802.59 | 67.5 | 870.09 | Alipore Division | South 24 Pgs Mechanical Division | 146.52 | 10.56 | 40.77 | 0 | 197.85 | 63.95 | 10.56 | 40.77 | 0 | 115.28 | 13.25 | 4
42 | SOUTH 24 PARAGANAS | SM/15976 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VI) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | TSM/018303 | 40060408 | Augmentation | MVS | GO2223014526PH | 22/02/2023 | 678.29 | 45 | 723.29 | Alipore Division | South 24 Pgs Mechanical Division | 90.23 | 0 | 70.77 | 0 | 161 | 6.83 | 0 | 70.77 | 0 | 77.59 | 10.73 | 1
43 | SOUTH 24 PARAGANAS | SM/15957 | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-VIII) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | TSM/018332 | 40060421 | Augmentation | MVS | GO2223014531PH | 22/02/2023 | 855.06 | 67.5 | 922.56 | Alipore Division | South 24 Pgs Mechanical Division | 216.04 | 23.44 | 83.45 | 0 | 322.93 | 177.42 | 23.44 | 81.79 | 0 | 282.66 | 30.64 | 4
44 | SOUTH 24 PARAGANAS | SM/15502 | AUGMENTATION AND RETROFITTING OF BHALEYA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017810 | 40037090 | Augmentation | MVS | GO2223013831PH | 15/02/2023 | 334.99 | 71.66 | 406.64 | Alipore Division | South 24 Pgs Mechanical Division | 77.73 | 0 | 81.05 | 0 | 158.79 | 37.08 | 0 | 50.52 | 0 | 87.6 | 21.54 | 3
45 | SOUTH 24 PARAGANAS | SM/15499 | AUGMENTATION AND RETROFITTING OF BIJOYNAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017893 | 40037075 | Augmentation | MVS | GO2223013843PH | 15/02/2023 | 567.26 | 62.57 | 629.83 | Alipore Division | South 24 Pgs Mechanical Division | 2.76 | 0 | 101.65 | 0 | 104.42 | 2.76 | 0 | 101.65 | 0 | 104.42 | 16.58 | 1
46 | SOUTH 24 PARAGANAS | SM/15107 | AUGMENTATION AND RETROFITTING OF BUDH KHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017653 | 40037076 | Augmentation | MVS | GO2223013237PH | 04/02/2023 | 289.88 | 31.12 | 321 | Alipore Division | South 24 Pgs Mechanical Division | 19.12 | 0 | 77.63 | 0 | 96.75 | 2.16 | 0 | 77.63 | 0 | 79.79 | 24.86 | 2
47 | SOUTH 24 PARAGANAS | SM/15104 | AUGMENTATION AND RETROFITTING OF CHUNAKHALI (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017635 | 40037043 | Augmentation | MVS | GO2223013244PH | 04/02/2023 | 428.03 | 62.23 | 490.26 | Alipore Division | South 24 Pgs Mechanical Division | 65 | 0 | 153.9 | 0 | 218.9 | 61.23 | 0 | 153.9 | 0 | 215.13 | 43.88 | 2
48 | SOUTH 24 PARAGANAS | SM/15475 | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017666 | 40037081 | Augmentation | MVS | GO2223013263PH | 04/02/2023 | 310.54 | 31.12 | 341.66 | Alipore Division | South 24 Pgs Mechanical Division | 25.6 | 5.41 | 85.9 | 0 | 116.91 | 25.6 | 5.41 | 83.53 | 0 | 114.54 | 33.52 | 4
49 | SOUTH 24 PARAGANAS | SM/15472 | AUGMENTATION AND RETROFITTING OF KALIKATALA (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017924 | 40037069 | Augmentation | MVS | GO2223013246PH | 04/02/2023 | 449.55 | 41.72 | 491.27 | Alipore Division | South 24 Pgs Mechanical Division | 17.9 | 4.18 | 104.35 | 0 | 126.43 | 17.9 | 4.18 | 104.35 | 0 | 126.43 | 25.74 | 4
50 | SOUTH 24 PARAGANAS | SM/15478 | AUGMENTATION AND RETROFITTING OF KALUGACHHI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017587 | 40037079 | Augmentation | MVS | GO2223013256PH | 04/02/2023 | 274.93 | 31.63 | 306.56 | Alipore Division | South 24 Pgs Mechanical Division | 7.41 | 0 | 0 | 0 | 7.41 | 0 | 0 | 0 | 0 | 0 | 0 | 2
51 | SOUTH 24 PARAGANAS | SM/15464 | AUGMENTATION AND RETROFITTING OF LOT NO. 126 (ZONE-I & II) PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017643 | 40037036 | Augmentation | SVS | GO2223013264PH | 04/02/2023 | 334.2 | 71.66 | 405.86 | Alipore Division | South 24 Pgs Mechanical Division | 111.17 | 37.09 | 86.67 | 0 | 234.94 | 97.91 | 37.09 | 86.67 | 0 | 221.67 | 54.62 | 27
52 | SOUTH 24 PARAGANAS | SM/15196 | AUGMENTATION AND RETROFITTING OF MALLIK KATI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017662 | 40037077 | Augmentation | MVS | GO2223013250PH | 06/02/2023 | 418.68 | 62.23 | 480.91 | Alipore Division | South 24 Pgs Mechanical Division | 53.15 | 0 | 65.04 | 0 | 118.19 | 44.37 | 0 | 65.04 | 0 | 109.41 | 22.75 | 2
53 | SOUTH 24 PARAGANAS | SM/15473 | AUGMENTATION AND RETROFITTING OF MAUKHALI PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017950 | 40037082 | Augmentation | MVS | GO2223013271PH | 04/02/2023 | 375.11 | 46.35 | 421.46 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
54 | SOUTH 24 PARAGANAS | SM/17225 | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017657 | 40037083 | Augmentation | MVS | GO2223016076PH | 15/03/2023 | 197.65 | 35.83 | 233.48 | Alipore Division | South 24 Pgs Mechanical Division | 33.18 | 11.2 | 0 | 0 | 44.39 | 33.18 | 11.2 | 0 | 0 | 44.39 | 19.01 | 11
55 | SOUTH 24 PARAGANAS | SM/15969 | AUGMENTATION AND RETROFITTING OF PURBA RADHANAGAR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | TSM/018313 | 40049280 | Augmentation | SVS | GO2223014528PH | 22/02/2023 | 535.48 | 71.66 | 607.14 | Alipore Division | South 24 Pgs Mechanical Division | 185.11 | 2.56 | 17.11 | 0 | 204.78 | 101.91 | 2.56 | 17.11 | 0 | 121.58 | 20.03 | 5
56 | SOUTH 24 PARAGANAS | SM/15965 | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | TSM/018319 | 40049279 | Augmentation | SVS | GO2223014517PH | 22/02/2023 | 823.73 | 71.66 | 895.39 | Alipore Division | South 24 Pgs Mechanical Division | 190.28 | 0 | 61.86 | 0 | 252.13 | 6.53 | 0 | 61.46 | 0 | 67.99 | 7.59 | 2
57 | SOUTH 24 PARAGANAS | SM/15563 | AUGMENTATION AND RETROFITTING OF SADHUPUR (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | TSM/018327 | 40049278 | Augmentation | SVS | GO2223013885PH | 15/02/2023 | 885.13 | 55.5 | 940.63 | Alipore Division | South 24 Pgs Mechanical Division | 117.41 | 10.08 | 62.53 | 0 | 190.02 | 0 | 10.08 | 62.53 | 0 | 72.61 | 7.72 | 3
58 | SOUTH 24 PARAGANAS | SM/16002 | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | TSM/018254 | 40060145 | Augmentation | SVS | GO2223014534PH | 22/02/2023 | 545.81 | 71.05 | 616.86 | Alipore Division | South 24 Pgs Mechanical Division | 191.94 | 8.94 | 49.19 | 0 | 250.07 | 3.82 | 8.94 | 49.19 | 0 | 61.95 | 10.04 | 3
59 | SOUTH 24 PARAGANAS | SM/15973 | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-II) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | TSM/018259 | 40060281 | Augmentation | SVS | GO2223014507PH | 22/02/2023 | 545.81 | 71.05 | 616.86 | Alipore Division | South 24 Pgs Mechanical Division | 224.66 | 11.79 | 6.62 | 0 | 243.07 | 38.16 | 11.79 | 6.62 | 0 | 56.57 | 9.17 | 3
60 | SOUTH 24 PARAGANAS | SM/15992 | AUGMENTATION AND RETROFITTING OF SATJELIA (ZONE-III) PWSS FOR PROVIDING FHTC, BLOCK - GOSABA | TSM/018279 | 40049277 | Augmentation | MVS | GO2223014506PH | 22/02/2023 | 595.5 | 70.51 | 666.01 | Alipore Division | South 24 Pgs Mechanical Division | 205.58 | 6.92 | 55.12 | 0 | 267.62 | 157.45 | 6.92 | 52.82 | 0 | 217.2 | 32.61 | 4
61 | SOUTH 24 PARAGANAS | SM/15476 | AUGMENTATION AND RETROFITTING OF SINGESHWAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017826 | 40037074 | Augmentation | MVS | GO2223013258PH | 04/02/2023 | 102.83 | 35.83 | 138.66 | Alipore Division | South 24 Pgs Mechanical Division | 25.34 | 16.54 | 24.45 | 0 | 66.34 | 18.28 | 16.54 | 24.45 | 0 | 59.28 | 42.75 | 21
62 | SOUTH 24 PARAGANAS | SM/15095 | AUGMENTATION AND RETROFITTING OF SRINAGAR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/017796 | 40049608 | Augmentation | MVS | GO2223013248PH | 04/02/2023 | 219.03 | 35.83 | 254.86 | Alipore Division | South 24 Pgs Mechanical Division | 70.21 | 0 | 0 | 0 | 70.21 | 70.21 | 0 | 0 | 0 | 70.21 | 27.55 | 23
63 | SOUTH 24 PARAGANAS | SM/13872 | AUGMENTATION FOR FOR GROUND WATER BASED MAHISMARI(ZONE- I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011572 | 40035510 | Augmentation | MVS | GO2223010056PH | 25/11/2022 | 872.73 | 71.66 | 944.38 | Alipore Division | South 24 Pgs Mechanical Division | 179.39 | 7.45 | 6.33 | 0 | 193.17 | 179.39 | 7.45 | 5.38 | 0 | 192.22 | 20.35 | 23
64 | SOUTH 24 PARAGANAS | SM/13876 | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011505 | 40033847 | Augmentation | SVS | GO2223010054PH | 25/11/2022 | 778.94 | 71.66 | 850.59 | Alipore Division | South 24 Pgs Mechanical Division | 55.5 | 4.71 | 3.97 | 0 | 64.18 | 55.5 | 4.71 | 0 | 0 | 60.21 | 7.08 | 90
65 | SOUTH 24 PARAGANAS | SM/18698 | AUGMENTATION FOR GROUND WATER BASED HARIPUR (ZONE- I & II), PIPED WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | TSM/011498 | 40033867 | Augmentation | MVS | 2250/PHE-28011/222/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1044.35 | 71.66 | 1116.01 | Alipore Division | South 24 Pgs Mechanical Division | 191.52 | 4 | 2.97 | 0 | 198.49 | 139.39 | 4 | 0 | 0 | 143.39 | 12.85 | 3
66 | SOUTH 24 PARAGANAS | SM/18871 | AUGMENTATION FOR GROUND WATER BASED KHAS RAMKARCHAR, PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/020444 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 728.15 | 35.83 | 763.97 | Alipore Division | South 24 Pgs Mechanical Division | 58.83 | 0 | 9.83 | 0 | 68.66 | 37.69 | 0 | 9.24 | 0 | 46.93 | 6.14 | 4
67 | SOUTH 24 PARAGANAS | SM/13972 | AUGMENTATION FOR GROUND WATER BASED RADHAKRISHNAPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011502 | 7573225 | Augmentation | SVS | GO2223010328PH | 01/12/2022 | 652.58 | 35.83 | 688.41 | Alipore Division | South 24 Pgs Mechanical Division | 196.86 | 0 | 1.78 | 0 | 198.65 | 151.42 | 0 | 0 | 0 | 151.42 | 22 | 16
68 | SOUTH 24 PARAGANAS | SM/13788 | AUGMENTATION FOR GROUND WATER BASED SHIBPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011454 | 40033025 | Augmentation | SVS | GO2223009885PH | 18/11/2022 | 828.39 | 71.66 | 900.05 | Alipore Division | South 24 Pgs Mechanical Division | 243.96 | 0 | 7.22 | 0 | 251.18 | 199.21 | 0 | 0 | 0 | 199.21 | 22.13 | 17
69 | SOUTH 24 PARAGANAS | SM/11875 | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | TSM/011461 | 40019294 | Augmentation | SVS | GO2223006371PH | 17/08/2022 | 607.47 | 35.83 | 643.29 | Alipore Division | South 24 Pgs Mechanical Division | 5.02 | 0 | 38.6 | 0 | 43.62 | 5.02 | 0 | 38.6 | 0 | 43.62 | 6.78 | 5
70 | SOUTH 24 PARAGANAS | SM/13569 | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011470 | 40031747 | Augmentation | MVS | GO2223009536PH | 09/11/2022 | 1042.97 | 71.66 | 1114.62 | Alipore Division | South 24 Pgs Mechanical Division | 676.02 | 15.06 | 10.31 | 0 | 701.38 | 671.71 | 15.06 | 10.31 | 0 | 697.08 | 62.54 | 70
71 | SOUTH 24 PARAGANAS | SM/11876 | AUGMENTATION FOR GROUND WATER BASED TAKTIPUR ABAD (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011501 | 40019368 | Augmentation | SVS | GO2223006438PH | 17/08/2022 | 761.83 | 71.66 | 833.48 | Alipore Division | South 24 Pgs Mechanical Division | 304.27 | 29.93 | 12.3 | 0 | 346.5 | 270.85 | 29.93 | 12.3 | 0 | 313.08 | 37.56 | 43
72 | SOUTH 24 PARAGANAS | SM/16962 | Augmentation for providing balance FHTC in Buita Chingripota Nischintipur Rajibpur & Uttar Roypur GP under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/020326 | 40063604 | Augmentation | MVS | GO2223016505PH | 16/03/2023 | 99.8 | 0 | 99.8 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 15.74 | 0 | 15.74 | 0 | 0 | 15.74 | 0 | 15.74 | 15.77 | 10
73 | SOUTH 24 PARAGANAS | SM/14823 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - III OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | TSM/016460 | 40034153 | Augmentation | MVS | GO2223013099PH | 04/02/2023 | 751.73 | 0 | 751.73 | Alipore Division |  | 227.34 | 0 | 59.11 | 0 | 286.45 | 37.68 | 0 | 59.11 | 0 | 96.79 | 12.88 | 25
74 | SOUTH 24 PARAGANAS | SM/14475 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | TSM/016455 | 40034193 | Augmentation | MVS | GO2223012379PH | 20/01/2023 | 347.31 | 0 | 347.31 | Alipore Division |  | 96.67 | 0 | 1.38 | 0 | 98.04 | 0 | 0 | 1.38 | 0 | 1.38 | 0.4 | 20
75 | SOUTH 24 PARAGANAS | SM/14476 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-I OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | TSM/016454 | 40034101 | Augmentation | MVS | GO2223012338PH | 20/01/2023 | 469.18 | 0 | 469.18 | Alipore Division |  | 9.87 | 0 | 19.34 | 0 | 29.21 | 9.87 | 0 | 19.34 | 0 | 29.21 | 6.23 | 6
76 | SOUTH 24 PARAGANAS | SM/14474 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | TSM/016459 | 40034220 | Augmentation | MVS | GO2223012330PH | 20/01/2023 | 953.38 | 0 | 953.38 | Alipore Division |  | 328.5 | 0 | 62.75 | 0 | 391.24 | 324.34 | 0 | 62.75 | 0 | 387.09 | 40.6 | 70
77 | SOUTH 24 PARAGANAS | SM/15322 | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-X OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - | TSM/016463 | 40034554 | Augmentation | MVS | GO2223013644PH | 09/02/2023 | 1390 | 0 | 1390 | Alipore Division |  | 207.75 | 0 | 34.15 | 0 | 241.9 | 111.18 | 0 | 30.68 | 0 | 141.86 | 10.21 | 20
78 | SOUTH 24 PARAGANAS | SM/14470 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-I OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | TSM/016657 | 40064464 | Augmentation | MVS | GO2223012316PH | 20/01/2023 | 155.77 | 0 | 155.77 | Alipore Division |  | 53.66 | 0 | 60.99 | 0 | 114.65 | 53.66 | 0 | 58.09 | 0 | 111.74 | 71.74 | 5
79 | SOUTH 24 PARAGANAS | SM/13914 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | TSM/016540 | 40064227 | Augmentation | MVS | GO2223010228PH | 29/11/2022 | 152.41 | 0 | 152.41 | Alipore Division |  | 76.3 | 0 | 14.52 | 0 | 90.82 | 76.3 | 0 | 14.52 | 0 | 90.82 | 59.59 | 0
80 | SOUTH 24 PARAGANAS | SM/14469 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IX OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SU | TSM/016594 | 40064473 | Augmentation | MVS | GO2223012325PH | 20/01/2023 | 120.72 | 0 | 120.72 | Alipore Division |  | 0 | 0 | 78.09 | 0 | 78.09 | 0 | 0 | 78.09 | 0 | 78.09 | 64.69 | 2
81 | SOUTH 24 PARAGANAS | SM/13915 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-V OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BA | TSM/016532 | 40065268 | Augmentation | MVS | GO2223010229PH | 29/11/2022 | 122.23 | 0 | 122.23 | Alipore Division |  | 14.31 | 0 | 0 | 0 | 14.31 | 14.31 | 0 | 0 | 0 | 14.31 | 11.71 | 4
82 | SOUTH 24 PARAGANAS | SM/13916 | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | TSM/016523 | 40064235 | Augmentation | MVS | GO2223010224PH | 29/11/2022 | 122.23 | 0 | 122.23 | Alipore Division |  | 103.13 | 0 | 0 | 0 | 103.13 | 103.13 | 0 | 0 | 0 | 103.13 | 84.37 | 12
83 | SOUTH 24 PARAGANAS | SM/14901 | AUGMENTATION IN DISTRIBUTION SYSTEM INCLUDING OHR WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALT | TSM/016519 | 40064219 | Augmentation | MVS | GO2223013100PH | 04/02/2023 | 407.52 | 0 | 407.52 | Alipore Division |  | 46.78 | 0 | 0 | 0 | 46.78 | 19.1 | 0 | 0 | 0 | 19.1 | 4.69 | 10
84 | SOUTH 24 PARAGANAS | SM/15532 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIST | TSM/016465 | 40034562 | Augmentation | MVS | GO2223013994PH | 16/02/2023 | 1410.79 | 0 | 1410.79 | Alipore Division |  | 789.49 | 0 | 143.07 | 0 | 932.57 | 512.74 | 0 | 142.44 | 0 | 655.18 | 46.44 | 25
85 | SOUTH 24 PARAGANAS | SM/15531 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR & ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | TSM/016467 | 40034553 | Augmentation | MVS | GO2223013992PH | 16/02/2023 | 3281.96 | 0 | 3281.96 | Alipore Division |  | 164.77 | 0 | 155.86 | 0 | 320.63 | 164.77 | 0 | 126.85 | 0 | 291.62 | 8.89 | 25
86 | SOUTH 24 PARAGANAS | SM/13891 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, | TSM/016568 | 40035352 | Augmentation | MVS | GO2223010086PH | 25/11/2022 | 543.76 | 0 | 543.76 | Alipore Division |  | 231.32 | 0 | 0 | 0 | 231.32 | 101 | 0 | 0 | 0 | 101 | 18.58 | 30
87 | SOUTH 24 PARAGANAS | SM/14468 | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | TSM/016583 | 40064468 | Augmentation | MVS | GO2223012318PH | 20/01/2023 | 518.03 | 0 | 518.03 | Alipore Division |  | 167.65 | 0 | 170.24 | 0 | 337.89 | 139.43 | 0 | 170.24 | 0 | 309.67 | 59.78 | 4
88 | SOUTH 24 PARAGANAS | SM/14985 | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | TSM/016348 | 40035985 | Augmentation | SVS | GO2223013111PH | 04/02/2023 | 397.02 | 58 | 455.02 | Alipore Division | South 24 Pgs Mechanical Division | 191.1 | 3.59 | 0 | 0 | 194.69 | 191.1 | 3.59 | 0 | 0 | 194.69 | 42.79 | 20
89 | SOUTH 24 PARAGANAS | SM/18286 | AUGMENTATION OF BHANGAN KHALI PIPED WATER SUPPLY SCHEME BLOCK-BASANTI UNDER CANNING SUB-DIVISION OF ALIPORE DIVISION,PHE DTE | TSM/015210 | 40032446 | Augmentation | SVS | 1621/PHE-28011/52/2023-SCHM CELL-Dept. of PHE | 23/06/2023 | 1098.69 | 70.13 | 1168.82 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 137.46 | 0 | 137.46 | 0 | 0 | 137.46 | 0 | 137.46 | 11.76 | 2
90 | SOUTH 24 PARAGANAS | SM/13116 | Augmentation of Canning Water Supply Scheme. | TSM/003712 | 40028726 | Augmentation | MVS | GO2223008575PH | 10/10/2022 | 2931.88 | 212.88 | 3144.76 | Alipore Division | South 24 Pgs Mechanical Division | 765.8 | 77.48 | 138.78 | 0 | 982.05 | 750.27 | 77.48 | 138.78 | 0 | 966.52 | 30.73 | 26
91 | SOUTH 24 PARAGANAS | SM/15469 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR UNDER ZONE-III, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAP | TSM/018067 | 40063814 | Augmentation | MVS | GO2223013267PH | 04/02/2023 | 734.1 | 0 | 734.1 | Alipore Division |  | 77.24 | 0 | 7.85 | 0 | 85.09 | 43.43 | 0 | 7.85 | 0 | 51.28 | 6.99 | 5
92 | SOUTH 24 PARAGANAS | SM/15468 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORK UNDER ZONE-VIII, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | TSM/018187 | 40065189 | Augmentation | MVS | GO2223013255PH | 04/02/2023 | 506.99 | 0 | 506.99 | Alipore Division |  | 43.89 | 0 | 13.4 | 0 | 57.29 | 2.81 | 0 | 13.4 | 0 | 16.21 | 3.2 | 5
93 | SOUTH 24 PARAGANAS | SM/18379 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-II, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018140 | 40065180 | Augmentation | SVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1121.79 | 0 | 1121.79 | Alipore Division |  | 269.13 | 0 | 46.72 | 0 | 315.85 | 106.18 | 0 | 46.72 | 0 | 152.9 | 13.63 | 5
94 | SOUTH 24 PARAGANAS | SM/18380 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-IV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER A | TSM/018167 | 40064786 | Augmentation | SVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1622.84 | 0 | 1622.84 | Alipore Division |  | 0 | 0 | 198.96 | 0 | 198.96 | 0 | 0 | 198.96 | 0 | 198.96 | 12.26 | 5
95 | SOUTH 24 PARAGANAS | SM/18376 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-VI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) | TSM/018163 | 40065170 | Augmentation | MVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1502.9 | 0 | 1502.9 | Alipore Division |  | 0 | 0 | 9.1 | 0 | 9.1 | 0 | 0 | 9.1 | 0 | 9.1 | 0.61 | 5
96 | SOUTH 24 PARAGANAS | SM/18377 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-VII, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER | TSM/018065 | 40064788 | Augmentation | MVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 3043.4 | 0 | 3043.4 | Alipore Division |  | 606.53 | 0 | 60.37 | 0 | 666.91 | 438.02 | 0 | 60.37 | 0 | 498.39 | 16.38 | 5
97 | SOUTH 24 PARAGANAS | SM/15058 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018184 | 40064486 | Augmentation | MVS | GO2223013245PH | 04/02/2023 | 349.37 | 0 | 349.37 | Alipore Division |  | 87.74 | 0 | 0 | 0 | 87.74 | 78.33 | 0 | 0 | 0 | 78.33 | 22.42 | 5
98 | SOUTH 24 PARAGANAS | SM/15506 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XIV, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER | TSM/018181 | 40064780 | Augmentation | SVS | GO2223013833PH | 15/02/2023 | 386.34 | 0 | 386.34 | Alipore Division |  | 30.98 | 0 | 14.56 | 0 | 45.54 | 0 | 0 | 14.56 | 0 | 14.56 | 3.77 | 5
99 | SOUTH 24 PARAGANAS | SM/18872 | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) | TSM/018194 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 312.1 | 0 | 312.1 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | SOUTH 24 PARAGANAS | SM/10218 | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | TSM/009231 | 5344170 | Augmentation | MVS | GO2122009961PH | 24/02/2022 | 459.16 | 29.87 | 489.03 | Alipore Division | South 24 Pgs Mechanical Division | 31.72 | 0 | 52.95 | 0 | 84.67 | 31.72 | 0 | 52.95 | 0 | 84.67 | 17.31 | 5
101 | SOUTH 24 PARAGANAS | SM/18716 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-IV, PURBA RANAGHAT PIPED WATER SUPPLY SCHEME, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY S | TSM/018099 | 40064625 | Augmentation | MVS | 2340/PHE/IV/W-268/23 | 10/08/2023 | 143.17 | 0 | 143.17 | Alipore Division |  | 46.22 | 0 | 4.88 | 0 | 51.1 | 30.4 | 0 | 0 | 0 | 30.4 | 21.24 | 5
102 | SOUTH 24 PARAGANAS | SM/15481 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-IX, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | TSM/018198 | 40065186 | Augmentation | SVS | GO2223013252PH | 04/02/2023 | 196.11 | 0 | 196.11 | Alipore Division |  | 19.27 | 0 | 0 | 0 | 19.27 | 0 | 0 | 0 | 0 | 0 | 0 | 5
103 | SOUTH 24 PARAGANAS | SM/15505 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI | TSM/018113 | 40064560 | Augmentation | SVS | GO2223013840PH | 15/02/2023 | 642.88 | 0 | 642.88 | Alipore Division |  | 163.16 | 0 | 8.36 | 0 | 171.52 | 163.16 | 0 | 8.36 | 0 | 171.52 | 26.68 | 5
104 | SOUTH 24 PARAGANAS | SM/15465 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-VI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | TSM/018168 | 40064629 | Augmentation | MVS | GO2223013265PH | 04/02/2023 | 230.56 | 0 | 230.56 | Alipore Division |  | 98.13 | 0 | 2.56 | 0 | 100.69 | 79.75 | 0 | 0 | 0 | 79.75 | 34.59 | 10
105 | SOUTH 24 PARAGANAS | SM/15507 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-VII, MATHURAPUR PIPED WATER SUPPLY SCHEME, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | TSM/018182 | 40064555 | Augmentation | SVS | GO2223013833PH | 15/02/2023 | 72.1 | 0 | 72.1 | Alipore Division |  | 70 | 0 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 70 | 97.09 | 50
106 | SOUTH 24 PARAGANAS | SM/15474 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | TSM/018044 | 40064792 | Augmentation | MVS | GO2223013261PH | 04/02/2023 | 129.48 | 0 | 129.48 | Alipore Division |  | 81.89 | 0 | 5.01 | 0 | 86.91 | 40.8 | 0 | 5.01 | 0 | 45.82 | 35.39 | 25
107 | SOUTH 24 PARAGANAS | SM/15466 | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-XI, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE D | TSM/018209 | 40065182 | Augmentation | MVS | GO2223013268PH | 04/02/2023 | 368.17 | 0 | 368.17 | Alipore Division |  | 50.79 | 0 | 0 | 0 | 50.79 | 4.23 | 0 | 0 | 0 | 4.23 | 1.15 | 5
108 | SOUTH 24 PARAGANAS | SM/18378 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE | TSM/018063 | 40064615 | Augmentation | MVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1225.12 | 0 | 1225.12 | Alipore Division |  | 73.64 | 0 | 43.47 | 0 | 117.11 | 12.95 | 0 | 43.47 | 0 | 56.42 | 4.61 | 5
109 | SOUTH 24 PARAGANAS | SM/15496 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-I, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | TSM/018135 | 40064485 | Augmentation | MVS | GO2223013847PH | 15/02/2023 | 220.17 | 0 | 220.17 | Alipore Division |  | 169.52 | 0 | 5.3 | 0 | 174.82 | 169.52 | 0 | 5.3 | 0 | 174.82 | 79.4 | 5
110 | SOUTH 24 PARAGANAS | SM/15470 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | TSM/018051 | 40063800 | Augmentation | MVS | GO2223013270PH | 04/02/2023 | 286.46 | 0 | 286.46 | Alipore Division |  | 137.37 | 0 | 6.71 | 0 | 144.08 | 91.42 | 0 | 6.71 | 0 | 98.14 | 34.26 | 5
111 | SOUTH 24 PARAGANAS | SM/15504 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-III, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | TSM/018147 | 40063793 | Augmentation | SVS | GO2223013832PH | 15/02/2023 | 200.81 | 0 | 200.81 | Alipore Division |  | 98.18 | 0 | 4.97 | 0 | 103.15 | 94.84 | 0 | 0 | 0 | 94.84 | 47.23 | 5
112 | SOUTH 24 PARAGANAS | SM/15492 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-IX, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018159 | 40064549 | Augmentation | MVS | GO2223013837PH | 15/02/2023 | 390.64 | 0 | 390.64 | Alipore Division |  | 326.45 | 0 | 8.13 | 0 | 334.58 | 290.34 | 0 | 8.13 | 0 | 298.47 | 76.4 | 5
113 | SOUTH 24 PARAGANAS | SM/15508 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-V, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | TSM/018190 | 40064483 | Augmentation | SVS | GO2223013828PH | 15/02/2023 | 341.02 | 0 | 341.02 | Alipore Division |  | 122.7 | 0 | 9.17 | 0 | 131.86 | 103.47 | 0 | 9.17 | 0 | 112.64 | 33.03 | 5
114 | SOUTH 24 PARAGANAS | SM/15497 | Augmentation of Distribution System under Zone-VIII, Mathurapur-II Block by Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta | TSM/018117 | 40064753 | Augmentation | MVS | GO2223013849PH | 15/02/2023 | 205.87 | 0 | 205.87 | Alipore Division |  | 23.62 | 0 | 5.21 | 0 | 28.83 | 23.62 | 0 | 5.21 | 0 | 28.83 | 14 | 5
115 | SOUTH 24 PARAGANAS | SM/15495 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-X, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | TSM/018211 | 40064482 | Augmentation | MVS | GO2223013846PH | 15/02/2023 | 177.9 | 0 | 177.9 | Alipore Division |  | 2.95 | 0 | 3.84 | 0 | 6.79 | 2.95 | 0 | 0 | 0 | 2.95 | 1.66 | 5
116 | SOUTH 24 PARAGANAS | SM/15491 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XI, MATHURAPUR-II BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018212 | 40064484 | Augmentation | MVS | GO2223013845PH | 15/02/2023 | 287.23 | 0 | 287.23 | Alipore Division |  | 92.48 | 0 | 5.13 | 0 | 97.61 | 19.65 | 0 | 5.13 | 0 | 24.78 | 8.63 | 5
117 | SOUTH 24 PARAGANAS | SM/15493 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018173 | 40064488 | Augmentation | MVS | GO2223013838PH | 15/02/2023 | 219.73 | 0 | 219.73 | Alipore Division |  | 166.89 | 0 | 4.07 | 0 | 170.96 | 163.72 | 0 | 0 | 0 | 163.72 | 74.51 | 5
118 | SOUTH 24 PARAGANAS | SM/15498 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XII, MATHURAPUR-II BLOCK PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018123 | 40064552 | Augmentation | MVS | GO2223013844PH | 15/02/2023 | 216.4 | 0 | 216.4 | Alipore Division |  | 8.95 | 0 | 5.33 | 0 | 14.28 | 8.95 | 0 | 5.33 | 0 | 14.28 | 6.6 | 5
119 | SOUTH 24 PARAGANAS | SM/15494 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018178 | 40064487 | Augmentation | MVS | GO2223013848PH | 15/02/2023 | 147.31 | 0 | 147.31 | Alipore Division |  | 101.69 | 0 | 0 | 0 | 101.69 | 101.69 | 0 | 0 | 0 | 101.69 | 69.03 | 5
120 | SOUTH 24 PARAGANAS | SM/15479 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XIII, MATHURAPUR-II BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALI | TSM/017982 | 40064611 | Augmentation | SVS | GO2223013259PH | 04/02/2023 | 89.53 | 0 | 89.53 | Alipore Division |  | 49.26 | 0 | 1.69 | 0 | 50.96 | 43.69 | 0 | 0 | 0 | 43.69 | 48.79 | 5
121 | SOUTH 24 PARAGANAS | SM/15480 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVI, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION PHE DTE. | TSM/018200 | 40064775 | Augmentation | SVS | GO2223013251PH | 04/02/2023 | 38.02 | 0 | 38.02 | Alipore Division |  | 8.83 | 0 | 0.63 | 0 | 9.46 | 8.83 | 0 | 0 | 0 | 8.83 | 23.22 | 5
122 | SOUTH 24 PARAGANAS | SM/15467 | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-XVII, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. | TSM/018202 | 40064794 | Augmentation | MVS | GO2223013269PH | 04/02/2023 | 566.92 | 0 | 566.92 | Alipore Division |  | 189.79 | 0 | 0 | 0 | 189.79 | 0 | 0 | 0 | 0 | 0 | 0 | 5
123 | SOUTH 24 PARAGANAS | SM/14726 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | TSM/014907 | 40054071 | Augmentation | MVS | GO2223012767PH | 31/01/2023 | 1485.87 | 0 | 1485.87 | South 24 Pgs. W/S Division - I |  | 20.08 | 0 | 1.32 | 0 | 21.4 | 20.08 | 0 | 0 | 0 | 20.08 | 1.35 | 2
124 | SOUTH 24 PARAGANAS | SM/18707 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II at RAJBALLABHPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | TSM/014908 | 40054072 | Augmentation | MVS | 2252/PHE-28011/187/2022-SCHM CELL-Dept. of PHE | 04/08/2023 | 1438.58 | 0 | 1438.58 | South 24 Pgs. W/S Division - I |  | 86.98 | 0 | 89.22 | 0 | 176.2 | 86.98 | 0 | 11.08 | 0 | 98.06 | 6.82 | 1
125 | SOUTH 24 PARAGANAS | SM/14725 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-IX at GHOLA NOAPARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | TSM/014913 | 40054080 | Augmentation | MVS | GO2223012769PH | 31/01/2023 | 1046.17 | 0 | 1046.17 | South 24 Pgs. W/S Division - I |  | 306.25 | 0 | 37.06 | 0 | 343.31 | 306.25 | 0 | 33.25 | 0 | 339.51 | 32.45 | 46
126 | SOUTH 24 PARAGANAS | SM/14727 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-V at BARIJPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- Sout | TSM/014909 | 40054076 | Augmentation | MVS | GO2223012752PH | 31/01/2023 | 1363.72 | 0 | 1363.72 | South 24 Pgs. W/S Division - I |  | 97.05 | 0 | 33.41 | 0 | 130.46 | 97.05 | 0 | 0 | 0 | 97.05 | 7.12 | 66
127 | SOUTH 24 PARAGANAS | SM/18708 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | TSM/014910 | 40054077 | Augmentation | MVS | 2252/PHE-28011/187/2022-SCHM CELL-Dept. of PHE | 04/08/2023 | 1824.04 | 0 | 1824.04 | South 24 Pgs. W/S Division - I |  | 76.87 | 0 | 0 | 0 | 76.87 | 76.87 | 0 | 0 | 0 | 76.87 | 4.21 | 5
128 | SOUTH 24 PARAGANAS | SM/14729 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | TSM/014912 | 40054079 | Augmentation | MVS | GO2223012770PH | 31/01/2023 | 2446.13 | 0 | 2446.13 | South 24 Pgs. W/S Division - I |  | 513.15 | 0 | 0 | 0 | 513.15 | 451.77 | 0 | 0 | 0 | 451.77 | 18.47 | 30
129 | SOUTH 24 PARAGANAS | SM/14724 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So | TSM/014914 | 40054081 | Augmentation | MVS | GO2223012771PH | 31/01/2023 | 1926.73 | 0 | 1926.73 | South 24 Pgs. W/S Division - I |  | 68.4 | 0 | 61.13 | 0 | 129.53 | 68.4 | 0 | 24.55 | 0 | 92.95 | 4.82 | 15
130 | SOUTH 24 PARAGANAS | SM/14728 | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/B at KALOKAPOTA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- | TSM/014916 | 40054083 | Augmentation | MVS | GO2223012753PH | 31/01/2023 | 1501.8 | 0 | 1501.8 | South 24 Pgs. W/S Division - I |  | 510.47 | 0 | 0 | 0 | 510.47 | 510.47 | 0 | 0 | 0 | 510.47 | 33.99 | 30
131 | SOUTH 24 PARAGANAS | SM/18706 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | TSM/014517 | 40055836 | Augmentation | MVS | 2252/PHE-28011/187/2022-SCHM CELL-Dept. of PHE | 04/08/2023 | 2440.32 | 0 | 2440.32 | South 24 Pgs. W/S Division - I |  | 194.32 | 0 | 215.9 | 0 | 410.23 | 194.32 | 0 | 215.9 | 0 | 410.23 | 16.81 | 4
132 | SOUTH 24 PARAGANAS | SM/15485 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-II AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | TSM/014522 | 40055845 | Augmentation | MVS | GO2223013705PH | 15/02/2023 | 2125.83 | 0 | 2125.83 | South 24 Pgs. W/S Division - I |  | 287.18 | 0 | 854.42 | 0 | 1141.6 | 287.18 | 0 | 851.09 | 0 | 1138.27 | 53.54 | 3
133 | SOUTH 24 PARAGANAS | SM/15484 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIV | TSM/014525 | 40055849 | Augmentation | MVS | GO2223013704PH | 15/02/2023 | 1932.84 | 0 | 1932.84 | South 24 Pgs. W/S Division - I |  | 255.59 | 0 | 413.04 | 0 | 668.63 | 157.17 | 0 | 398.44 | 0 | 555.6 | 28.75 | 10
134 | SOUTH 24 PARAGANAS | SM/12204 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | TSM/014530 | 40055853 | Augmentation | MVS | GO2223007094PH | 06/09/2022 | 482.42 | 0 | 482.42 | South 24 Pgs. W/S Division - I |  | 119.52 | 0 | 0 | 0 | 119.52 | 119.52 | 0 | 0 | 0 | 119.52 | 24.78 | 10
135 | SOUTH 24 PARAGANAS | SM/18715 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | TSM/014532 | 40055856 | Augmentation | MVS | 2339/PHE-28011/187/2022-SCHM CELL-Dept. of PHE | 10/08/2023 | 841.46 | 0 | 841.46 | South 24 Pgs. W/S Division - I |  | 261.59 | 0 | 0 | 0 | 261.59 | 261.59 | 0 | 0 | 0 | 261.59 | 31.09 | 7
136 | SOUTH 24 PARAGANAS | SM/12205 | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | TSM/014544 | 40055861 | Augmentation | MVS | GO2223007117PH | 07/09/2022 | 669.5 | 0 | 669.5 | South 24 Pgs. W/S Division - I |  | 227.88 | 0 | 0 | 0 | 227.88 | 227.88 | 0 | 0 | 0 | 227.88 | 34.04 | 4
137 | SOUTH 24 PARAGANAS | SM/09922 | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/008771 | 40002566 | Augmentation | SVS | GO2122006637PH | 10/12/2021 | 1145.92 | 67.98 | 1213.9 | Alipore Division | South 24 Pgs Mechanical Division | 76.13 | 0 | 181.72 | 0 | 257.85 | 55.33 | 0 | 181.72 | 0 | 237.05 | 19.53 | 38
138 | SOUTH 24 PARAGANAS | SM/10336 | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008772 | 40014843 | Augmentation | MVS | GO2122010685PH | 14/03/2022 | 1675.06 | 101.97 | 1777.03 | Alipore Division | South 24 Pgs Mechanical Division | 333.1 | 0 | 143.47 | 0 | 476.57 | 320.87 | 0 | 128.45 | 0 | 449.32 | 25.29 | 30
139 | SOUTH 24 PARAGANAS | SM/13442 | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | TSM/014211 | 40033448 | Augmentation | MVS | GO2223009217PH | 02/11/2022 | 492.65 | 43.78 | 536.43 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 113.1 | 9.29 | 8.64 | 0 | 131.03 | 113.1 | 9.29 | 8.64 | 0 | 131.03 | 24.43 | 11
140 | SOUTH 24 PARAGANAS | SM/14120 | AUGMENTATION OF GROUND WATER BASED AMTALI (ZONE-I & II), PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/015896 | 40035966 | Augmentation | SVS | GO2223011384PH | 02/01/2023 | 933.33 | 71.66 | 1004.99 | Alipore Division | South 24 Pgs Mechanical Division | 295.33 | 0 | 204.68 | 0 | 500.01 | 211.23 | 0 | 204.68 | 0 | 415.92 | 41.39 | 2
141 | SOUTH 24 PARAGANAS | SM/13117 | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011270 | 40028717 | Augmentation | MVS | GO2223008579PH | 10/10/2022 | 1535.01 | 71.66 | 1606.67 | Alipore Division | South 24 Pgs Mechanical Division | 757.86 | 29.36 | 17.06 | 0 | 804.28 | 757.86 | 29.36 | 17.06 | 0 | 804.28 | 50.06 | 49
142 | SOUTH 24 PARAGANAS | SM/14041 | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | TSM/011575 | 40033949 | Augmentation | MVS | GO2223010772PH | 12/12/2022 | 969.87 | 71.66 | 1041.53 | Alipore Division | South 24 Pgs Mechanical Division | 349.01 | 15.59 | 5.64 | 0 | 370.24 | 334.5 | 15.59 | 0 | 0 | 350.09 | 33.61 | 28
143 | SOUTH 24 PARAGANAS | SM/14123 | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- II (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | TSM/011577 | 40033958 | Augmentation | MVS | GO2223011497PH | 02/01/2023 | 963.26 | 71.66 | 1034.92 | Alipore Division | South 24 Pgs Mechanical Division | 325.92 | 0 | 9.29 | 0 | 335.21 | 307.65 | 0 | 0 | 0 | 307.65 | 29.73 | 23
144 | SOUTH 24 PARAGANAS | SM/13812 | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011453 | 40035502 | Augmentation | SVS | GO2223009960PH | 22/11/2022 | 549.77 | 35.83 | 585.6 | Alipore Division | South 24 Pgs Mechanical Division | 21.86 | 6.71 | 24.52 | 0 | 53.09 | 21.86 | 6.71 | 24.52 | 0 | 53.09 | 9.07 | 6
145 | SOUTH 24 PARAGANAS | SM/18381 | AUGMENTATION OF GROUND WATER BASED CHATRAKHALI (ZONE-I, II & III) PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : BASANTI, DISTRICT : SOUTH 24 PARGANAS | TSM/018333 | 40036955 | Augmentation | MVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1781.4 | 286.62 | 2068.02 | Alipore Division | South 24 Pgs Mechanical Division | 30.96 | 0 | 41.73 | 0 | 72.68 | 30.96 | 0 | 41.73 | 0 | 72.68 | 3.51 | 3
146 | SOUTH 24 PARAGANAS | SM/11748 | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011341 | 40019241 | Augmentation | MVS | GO2223005996PH | 03/08/2022 | 801.91 | 35.83 | 837.74 | Alipore Division | South 24 Pgs Mechanical Division | 387.94 | 12.45 | 12.3 | 0 | 412.69 | 315.51 | 12.45 | 12.3 | 0 | 340.26 | 40.62 | 48
147 | SOUTH 24 PARAGANAS | SM/18697 | AUGMENTATION OF GROUND WATER BASED DAKSHIN GANGADHARPUR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011579 | 40033912 | Augmentation | MVS | 2250/PHE-28011/222/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1175.03 | 35.83 | 1210.86 | Alipore Division | South 24 Pgs Mechanical Division | 123.11 | 0 | 5.35 | 0 | 128.45 | 8.84 | 0 | 0 | 0 | 8.84 | 0.73 | 2
148 | SOUTH 24 PARAGANAS | SM/11213 | AUGMENTATION OF GROUND WATER BASED DAKSHIN RAYPUR PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009274 | 40014916 | Augmentation | MVS | GO2223004063PH | 13/06/2022 | 1139.55 | 79.22 | 1218.77 | Alipore Division | South 24 Pgs Mechanical Division | 309.73 | 11.81 | 29.79 | 0 | 351.33 | 232.22 | 11.81 | 29.79 | 0 | 273.83 | 22.47 | 15
149 | SOUTH 24 PARAGANAS | SM/10482 | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009275 | 40014926 | Augmentation | SVS | GO2223000237PH | 13/04/2022 | 405.83 | 44.29 | 450.12 | Alipore Division | South 24 Pgs Mechanical Division | 3.36 | 0 | 44.22 | 0 | 47.57 | 3.36 | 0 | 44.22 | 0 | 47.57 | 10.57 | 2
150 | SOUTH 24 PARAGANAS | SM/10092 | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009237 | 40009481 | Augmentation | MVS | GO2122009009PH | 01/02/2022 | 1115.79 | 44.29 | 1160.08 | Alipore Division | South 24 Pgs Mechanical Division | 376.83 | 0 | 171.56 | 0 | 548.39 | 376.83 | 0 | 171.56 | 0 | 548.39 | 47.27 | 10
151 | SOUTH 24 PARAGANAS | SM/15221 | AUGMENTATION OF GROUND WATER BASED DHASPARA (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011344 | 40033021 | Augmentation | MVS | GO2223013357PH | 06/02/2023 | 1152.32 | 71.66 | 1223.98 | Alipore Division | South 24 Pgs Mechanical Division | 312.31 | 7.12 | 12.17 | 0 | 331.59 | 311.82 | 7.12 | 12.17 | 0 | 331.11 | 27.05 | 6
152 | SOUTH 24 PARAGANAS | SM/15834 | AUGMENTATION OF GROUND WATER BASED DHURI, PIPED WATER SUPPLY SCHEME BLOCK - BASANTI UNDER CANNING SUB - DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/015102 | 40035963 | Augmentation | SVS | GO2223014293PH | 20/02/2023 | 805.05 | 71.66 | 876.71 | Alipore Division | South 24 Pgs Mechanical Division | 313.49 | 14.21 | 0 | 0 | 327.7 | 306.65 | 14.21 | 0 | 0 | 320.85 | 36.6 | 37
153 | SOUTH 24 PARAGANAS | SM/11847 | AUGMENTATION OF GROUND WATER BASED DWARIKNAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS. | TSM/011573 | 40019764 | Augmentation | SVS | GO2223006274PH | 16/08/2022 | 618.74 | 35.83 | 654.57 | Alipore Division | South 24 Pgs Mechanical Division | 123.75 | 9.71 | 1.19 | 0 | 134.64 | 104.88 | 9.71 | 1.19 | 0 | 115.78 | 17.69 | 10
154 | SOUTH 24 PARAGANAS | SM/11805 | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011460 | 40019325 | Augmentation | SVS | GO2223006081PH | 05/08/2022 | 791.56 | 71.66 | 863.21 | Alipore Division | South 24 Pgs Mechanical Division | 233.55 | 22.89 | 30.17 | 0 | 286.62 | 199.67 | 22.89 | 30.17 | 0 | 252.73 | 29.28 | 42
155 | SOUTH 24 PARAGANAS | SM/18983 | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | TSM/009565 | 0 | Augmentation | SVS | 3152/PHE-28011/252/2023-ESTT CELL-Dept. of PHE | 12/10/2023 | 971.41 | 71.66 | 1043.06 | Alipore Division | South 24 Pgs Mechanical Division | 145.95 | 0 | 49.52 | 0 | 195.46 | 80.67 | 0 | 49.52 | 0 | 130.19 | 12.48 | 16
156 | SOUTH 24 PARAGANAS | SM/18674 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE - II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE.IN THE DISTRICT OF SOUTH 24 PARGANAS | TSM/018435 | 40049272 | Augmentation | MVS | 2241/PHE-28011/200/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 4392.92 | 465.76 | 4858.69 | Alipore Division | South 24 Pgs Mechanical Division | 36.38 | 0 | 765.21 | 0 | 801.59 | 35.42 | 0 | 685.58 | 0 | 721 | 14.84 | 3
157 | SOUTH 24 PARAGANAS | SM/15056 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-I), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | TSM/018433 | 40036992 | Augmentation | MVS | GO2223012962PH | 03/02/2023 | 915.6 | 35.83 | 951.43 | Alipore Division | South 24 Pgs Mechanical Division | 235.41 | 0 | 157.7 | 0 | 393.11 | 235.41 | 0 | 142.97 | 0 | 378.38 | 39.77 | 37
158 | SOUTH 24 PARAGANAS | SM/15954 | AUGMENTATION OF GROUND WATER BASED GOSABA (ZONE-III), PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS. | TSM/018434 | 40049270 | Augmentation | SVS | GO2223014520PH | 22/02/2023 | 399.71 | 35.83 | 435.54 | Alipore Division | South 24 Pgs Mechanical Division | 3.18 | 0 | 16.46 | 0 | 19.64 | 3.18 | 0 | 16.46 | 0 | 19.64 | 4.51 | 1
159 | SOUTH 24 PARAGANAS | SM/10486 | AUGMENTATION OF GROUND WATER BASED GURUDASPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009276 | 40014845 | Augmentation | MVS | GO2223000245PH | 13/04/2022 | 809.53 | 33.64 | 843.18 | Alipore Division | South 24 Pgs Mechanical Division | 208.48 | 0 | 58.5 | 0 | 266.99 | 208.48 | 0 | 53.29 | 0 | 261.77 | 31.05 | 58
160 | SOUTH 24 PARAGANAS | SM/14159 | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011327 | 40032987 | Augmentation | SVS | GO2223011614PH | 05/01/2023 | 944.46 | 71.66 | 1016.12 | Alipore Division | South 24 Pgs Mechanical Division | 541.18 | 15.56 | 13.92 | 0 | 570.66 | 486.77 | 5.05 | 8.22 | 0 | 500.04 | 49.21 | 51
161 | SOUTH 24 PARAGANAS | SM/10480 | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | TSM/009569 | 40014847 | Augmentation | MVS | GO2223000218PH | 13/04/2022 | 796.24 | 62.32 | 858.56 | Alipore Division | South 24 Pgs Mechanical Division | 525.87 | 0 | 21.58 | 0 | 547.45 | 424.49 | 0 | 0 | 0 | 424.49 | 49.44 | 30
162 | SOUTH 24 PARAGANAS | SM/16013 | AUGMENTATION OF GROUND WATER BASED KALARIA (ZONE-IIB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I, DISTRICT-SOUTH 24 PARGANAS | TSM/017459 | 40060044 | Augmentation | SVS | GO2223014523PH | 22/02/2023 | 729.62 | 63.25 | 792.87 | Alipore Division | South 24 Pgs Mechanical Division | 193.73 | 19.56 | 35.75 | 0 | 249.04 | 112.62 | 19.56 | 35.75 | 0 | 167.93 | 21.18 | 12
163 | SOUTH 24 PARAGANAS | SM/18873 | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | TSM/009574 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 762.21 | 35.83 | 798.04 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 25.84 | 0 | 25.84 | 0 | 0 | 25.84 | 0 | 25.84 | 3.24 | 0
164 | SOUTH 24 PARAGANAS | SM/18874 | AUGMENTATION OF GROUND WATER BASED KHAN SAHEBER ABAD PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | TSM/009568 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 476.56 | 35.83 | 512.39 | Alipore Division | South 24 Pgs Mechanical Division | 36.71 | 0 | 0 | 0 | 36.71 | 0 | 0 | 0 | 0 | 0 | 0 | 19
165 | SOUTH 24 PARAGANAS | SM/11747 | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011331 | 40019238 | Augmentation | SVS | GO2223005997PH | 03/08/2022 | 713.09 | 35.83 | 748.92 | Alipore Division | South 24 Pgs Mechanical Division | 540.71 | 11.97 | 12.3 | 0 | 564.99 | 540.71 | 11.97 | 12.3 | 0 | 564.99 | 75.44 | 82
166 | SOUTH 24 PARAGANAS | SM/12731 | AUGMENTATION OF GROUND WATER BASED KUSUMTALA, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | TSM/011499 | 40028487 | Augmentation | SVS | GO2223007933PH | 20/09/2022 | 702.55 | 35.83 | 738.38 | Alipore Division | South 24 Pgs Mechanical Division | 246.9 | 0 | 12.36 | 0 | 259.26 | 246.9 | 0 | 12.36 | 0 | 259.26 | 35.11 | 76
167 | SOUTH 24 PARAGANAS | SM/10484 | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | TSM/009566 | 40016994 | Augmentation | MVS | GO2223000236PH | 13/04/2022 | 637.93 | 15.45 | 653.38 | Alipore Division | South 24 Pgs Mechanical Division | 416.16 | 13.95 | 26.17 | 0 | 456.28 | 367.81 | 13.95 | 26.17 | 0 | 407.93 | 62.43 | 49
168 | SOUTH 24 PARAGANAS | SM/14518 | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011335 | 40032994 | Augmentation | MVS | GO2223012596PH | 30/01/2023 | 1273.63 | 71.66 | 1345.28 | Alipore Division | South 24 Pgs Mechanical Division | 225.88 | 8.76 | 12.64 | 0 | 247.29 | 196.29 | 8.76 | 10.56 | 0 | 215.62 | 16.03 | 24
169 | SOUTH 24 PARAGANAS | SM/18280 | AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II & III) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | TSM/016448 | 40049265 | Augmentation | SVS | 1626/PHE-28011/166/2023-SCHM CELL-Dept. of PHE | 23/06/2023 | 1449.55 | 214.97 | 1664.52 | Alipore Division | South 24 Pgs Mechanical Division | 270.02 | 0 | 0 | 0 | 270.02 | 175.9 | 0 | 0 | 0 | 175.9 | 10.57 | 8
170 | SOUTH 24 PARAGANAS | SM/13584 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-I), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/012785 | 40032949 | Augmentation | SVS | GO2223009492PH | 09/11/2022 | 43.77 | 7.53 | 51.31 | Alipore Division | South 24 Pgs Mechanical Division | 32.74 | 7.31 | 0.65 | 0 | 40.7 | 29.39 | 7.31 | 0.65 | 0 | 37.35 | 72.8 | 48
171 | SOUTH 24 PARAGANAS | SM/12746 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-II), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/012793 | 40028517 | Augmentation | SVS | GO2223007938PH | 20/09/2022 | 40.87 | 7.53 | 48.4 | Alipore Division | South 24 Pgs Mechanical Division | 35.05 | 7.31 | 0.43 | 0 | 42.79 | 28.32 | 7.31 | 0.43 | 0 | 36.06 | 74.51 | 32
172 | SOUTH 24 PARAGANAS | SM/12747 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-III), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/012795 | 40028519 | Augmentation | SVS | GO2223007935PH | 20/09/2022 | 35.65 | 7.53 | 43.19 | Alipore Division | South 24 Pgs Mechanical Division | 33.97 | 7.26 | 0.65 | 0 | 41.88 | 33.97 | 7.26 | 0.65 | 0 | 41.88 | 96.97 | 40
173 | SOUTH 24 PARAGANAS | SM/13585 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHUN KHALI (PART-IV), UNDER ALIPORE DIVISION, PHE DTE., BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/012796 | 40032952 | Augmentation | SVS | GO2223009493PH | 09/11/2022 | 36.92 | 7.53 | 44.46 | Alipore Division | South 24 Pgs Mechanical Division | 24.55 | 7.31 | 0.43 | 0 | 32.29 | 24.55 | 7.31 | 0.43 | 0 | 32.29 | 72.64 | 44
174 | SOUTH 24 PARAGANAS | SM/13576 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014669 | 40032497 | Augmentation | SVS | GO2223009495PH | 09/11/2022 | 47.56 | 7.53 | 55.09 | Alipore Division | South 24 Pgs Mechanical Division | 39.72 | 7.31 | 0.91 | 0 | 47.95 | 31.28 | 7.31 | 0.91 | 0 | 39.51 | 71.71 | 18
175 | SOUTH 24 PARAGANAS | SM/13575 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014670 | 40032541 | Augmentation | SVS | GO2223009507PH | 09/11/2022 | 45.55 | 7.53 | 53.09 | Alipore Division | South 24 Pgs Mechanical Division | 43.82 | 6.35 | 0.76 | 0 | 50.93 | 35.89 | 6.35 | 0.76 | 0 | 43 | 81 | 2
176 | SOUTH 24 PARAGANAS | SM/13577 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-III) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014537 | 40032569 | Augmentation | SVS | GO2223009501PH | 09/11/2022 | 42.99 | 7.53 | 50.52 | Alipore Division | South 24 Pgs Mechanical Division | 21.87 | 5.83 | 0.91 | 0 | 28.62 | 13.89 | 5.83 | 0.91 | 0 | 20.64 | 40.85 | 12
177 | SOUTH 24 PARAGANAS | SM/13574 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-IV) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014671 | 40032585 | Augmentation | SVS | GO2223009504PH | 09/11/2022 | 46.92 | 7.53 | 54.45 | Alipore Division | South 24 Pgs Mechanical Division | 35.16 | 4 | 0.76 | 0 | 39.92 | 28.36 | 4 | 0.76 | 0 | 33.12 | 60.82 | 36
178 | SOUTH 24 PARAGANAS | SM/13581 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-IX) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014541 | 40032908 | Augmentation | SVS | GO2223009500PH | 09/11/2022 | 52.06 | 7.53 | 59.59 | Alipore Division | South 24 Pgs Mechanical Division | 30.37 | 6.87 | 1.07 | 0 | 38.31 | 16.94 | 6.87 | 1.07 | 0 | 24.88 | 41.76 | 14
179 | SOUTH 24 PARAGANAS | SM/13578 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-V) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014538 | 40032592 | Augmentation | SVS | GO2223009505PH | 09/11/2022 | 68.74 | 7.53 | 76.27 | Alipore Division | South 24 Pgs Mechanical Division | 45.3 | 18.58 | 1.52 | 0 | 65.4 | 33.75 | 18.58 | 1.52 | 0 | 53.86 | 70.61 | 15
180 | SOUTH 24 PARAGANAS | SM/13573 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-VI) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014673 | 40032596 | Augmentation | SVS | GO2223009510PH | 09/11/2022 | 45.18 | 7.53 | 52.71 | Alipore Division | South 24 Pgs Mechanical Division | 23.86 | 5.37 | 0.91 | 0 | 30.14 | 23.86 | 5.37 | 0.91 | 0 | 30.14 | 57.18 | 15
181 | SOUTH 24 PARAGANAS | SM/13579 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-VII) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014539 | 40032892 | Augmentation | SVS | GO2223009494PH | 09/11/2022 | 76.02 | 7.53 | 83.55 | Alipore Division | South 24 Pgs Mechanical Division | 67.78 | 6.22 | 2.13 | 0 | 76.12 | 63.58 | 6.22 | 2.13 | 0 | 71.93 | 86.08 | 48
182 | SOUTH 24 PARAGANAS | SM/13580 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-VIII) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014540 | 40032905 | Augmentation | SVS | GO2223009499PH | 09/11/2022 | 65.99 | 7.53 | 73.53 | Alipore Division | South 24 Pgs Mechanical Division | 27.82 | 19.36 | 1.52 | 0 | 48.71 | 27.82 | 19.36 | 1.52 | 0 | 48.71 | 66.24 | 12
183 | SOUTH 24 PARAGANAS | SM/13572 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-X) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014674 | 40032914 | Augmentation | SVS | GO2223009498PH | 09/11/2022 | 68.21 | 7.53 | 75.74 | Alipore Division | South 24 Pgs Mechanical Division | 45.24 | 15.38 | 1.22 | 0 | 61.84 | 31.9 | 15.38 | 1.22 | 0 | 48.5 | 64.03 | 25
184 | SOUTH 24 PARAGANAS | SM/13582 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-XI) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014542 | 40032940 | Augmentation | SVS | GO2223009496PH | 09/11/2022 | 72.47 | 7.53 | 80 | Alipore Division | South 24 Pgs Mechanical Division | 52.04 | 12.33 | 1.68 | 0 | 66.04 | 37.48 | 12.33 | 1.68 | 0 | 51.49 | 64.36 | 33
185 | SOUTH 24 PARAGANAS | SM/13583 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-XII) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/014543 | 40032943 | Augmentation | SVS | GO2223009508PH | 09/11/2022 | 80.45 | 7.53 | 87.98 | Alipore Division | South 24 Pgs Mechanical Division | 58.59 | 11.26 | 1.83 | 0 | 71.67 | 58.59 | 11.26 | 1.83 | 0 | 71.67 | 81.46 | 32
186 | SOUTH 24 PARAGANAS | SM/12744 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR TAMBUL DAHA (PART - I) UNDER ALIPORE DIVISION, BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/012783 | 40028508 | Augmentation | SVS | GO2223007936PH | 20/09/2022 | 55.6 | 7.53 | 63.13 | Alipore Division | South 24 Pgs Mechanical Division | 42.53 | 7.31 | 0 | 0 | 49.85 | 40.46 | 7.31 | 0 | 0 | 47.78 | 75.67 | 48
187 | SOUTH 24 PARAGANAS | SM/12745 | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR TAMBUL DAHA (PART - II) UNDER ALIPORE DIVISION, BLOCK : CANNING-II, DISTRICT : SOUTH 24 PARGANAS | TSM/012789 | 40028511 | Augmentation | SVS | GO2223007937PH | 20/09/2022 | 46.84 | 7.53 | 54.38 | Alipore Division | South 24 Pgs Mechanical Division | 12.18 | 0 | 0 | 0 | 12.18 | 12.18 | 0 | 0 | 0 | 12.18 | 22.39 | 40
188 | SOUTH 24 PARAGANAS | SM/11698 | AUGMENTATION OF GROUND WATER BASED MRITYUNJAYNAGAR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011494 | 40019763 | Augmentation | SVS | GO2223005732PH | 29/07/2022 | 629.44 | 35.83 | 665.26 | Alipore Division | South 24 Pgs Mechanical Division | 290.73 | 11.3 | 55.19 | 0 | 357.22 | 250.9 | 11.3 | 55.19 | 0 | 317.38 | 47.71 | 82
189 | SOUTH 24 PARAGANAS | SM/12626 | AUGMENTATION OF GROUND WATER BASED NAGANDRAGANJ (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | TSM/011481 | 40028483 | Augmentation | MVS | GO2223007844PH | 19/09/2022 | 1112.71 | 71.66 | 1184.36 | Alipore Division | South 24 Pgs Mechanical Division | 413.78 | 15.26 | 29.85 | 0 | 458.9 | 413.78 | 15.26 | 11.93 | 0 | 440.98 | 37.23 | 16
190 | SOUTH 24 PARAGANAS | SM/10535 | AUGMENTATION OF GROUND WATER BASED NAMKHANA PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009238 | 40014899 | Augmentation | MVS | GO2223000251PH | 13/04/2022 | 784.33 | 54.08 | 838.4 | Alipore Division | South 24 Pgs Mechanical Division | 652.91 | 12.25 | 68.95 | 0 | 734.11 | 507.48 | 12.25 | 50.24 | 0 | 569.98 | 67.98 | 19
191 | SOUTH 24 PARAGANAS | SM/18876 | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | TSM/009560 | 0 | Augmentation | MVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 833.49 | 35.83 | 869.32 | Alipore Division | South 24 Pgs Mechanical Division | 144.08 | 0 | 0 | 0 | 144.08 | 0 | 0 | 0 | 0 | 0 | 0 | 10
192 | SOUTH 24 PARAGANAS | SM/18984 | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009239 | 0 | Augmentation | MVS | 3152/PHE-28011/252/2023-ESTT CELL-Dept. of PHE | 12/10/2023 | 2022.3 | 112.27 | 2134.57 | Alipore Division | South 24 Pgs Mechanical Division | 177.85 | 0 | 47.74 | 0 | 225.59 | 177.85 | 0 | 24.89 | 0 | 202.74 | 9.5 | 24
193 | SOUTH 24 PARAGANAS | SM/11750 | AUGMENTATION OF GROUND WATER BASED NEBUTALA, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011455 | 40019356 | Augmentation | SVS | GO2223005982PH | 03/08/2022 | 485.89 | 35.83 | 521.71 | Alipore Division | South 24 Pgs Mechanical Division | 83.35 | 0 | 22.37 | 0 | 105.71 | 83.35 | 0 | 22.37 | 0 | 105.71 | 20.26 | 20
194 | SOUTH 24 PARAGANAS | SM/14124 | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011500 | 40033777 | Augmentation | MVS | GO2223011487PH | 02/01/2023 | 1110.35 | 143.31 | 1253.66 | Alipore Division | South 24 Pgs Mechanical Division | 191.95 | 12.91 | 0 | 0 | 204.86 | 173.57 | 0 | 0 | 0 | 173.57 | 13.84 | 90
195 | SOUTH 24 PARAGANAS | SM/13873 | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-II) (PART I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011504 | 40033785 | Augmentation | MVS | GO2223010057PH | 25/11/2022 | 774.28 | 71.66 | 845.93 | Alipore Division | South 24 Pgs Mechanical Division | 365.08 | 11.7 | 0 | 0 | 376.78 | 347.2 | 11.7 | 0 | 0 | 358.9 | 42.43 | 46
196 | SOUTH 24 PARAGANAS | SM/13072 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | TSM/014717 | 40028599 | Augmentation | MVS | GO2223008465PH | 29/09/2022 | 353.84 | 59.74 | 413.58 | Alipore Division | South 24 Pgs Mechanical Division | 69.18 | 34.47 | 0 | 0 | 103.65 | 62.16 | 24.65 | 0 | 0 | 86.81 | 20.99 | 13
197 | SOUTH 24 PARAGANAS | SM/18864 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAORAKHALI AND ADJOINING MOUZAS (BAKULTALA). | TSM/021504 | 0 | Augmentation | MVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 203.96 | 19.83 | 223.79 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | SOUTH 24 PARAGANAS | SM/18866 | Augmentation of ground water based piped water supply scheme for Kaparpuri & adjoining mouzas | TSM/020722 | 0 | Augmentation | MVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 213.56 | 19.83 | 233.39 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | SOUTH 24 PARAGANAS | SM/18863 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SABEK MAHISAHARA AND ADJOINING MOUZA (CHUNPURI) | TSM/021510 | 0 | Augmentation | MVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 83.73 | 19.83 | 103.56 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | SOUTH 24 PARAGANAS | SM/18875 | AUGMENTATION OF GROUND WATER BASED PURUSOTTAMPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE IN SOUTH 24 PARGANAS DISTRICT | TSM/009567 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 718.41 | 35.83 | 754.23 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | SOUTH 24 PARAGANAS | SM/13875 | AUGMENTATION OF GROUND WATER BASED RAJNAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | TSM/011506 | 40033814 | Augmentation | SVS | GO2223010055PH | 25/11/2022 | 483.92 | 35.83 | 519.75 | Alipore Division | South 24 Pgs Mechanical Division | 95.21 | 0 | 10.14 | 0 | 105.36 | 76.07 | 0 | 10.14 | 0 | 86.21 | 16.59 | 19
202 | SOUTH 24 PARAGANAS | SM/14987 | AUGMENTATION OF GROUND WATER BASED RAKHALPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | TSM/016093 | 40035979 | Augmentation | SVS | GO2223013169PH | 04/02/2023 | 758.84 | 71.66 | 830.49 | Alipore Division | South 24 Pgs Mechanical Division | 7.04 | 0 | 0 | 0 | 7.04 | 7.04 | 0 | 0 | 0 | 7.04 | 0.85 | 14
203 | SOUTH 24 PARAGANAS | SM/11749 | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011473 | 40019291 | Augmentation | SVS | GO2223005962PH | 03/08/2022 | 699.39 | 35.83 | 735.22 | Alipore Division | South 24 Pgs Mechanical Division | 7.61 | 0 | 36.24 | 0 | 43.85 | 7.61 | 0 | 30.46 | 0 | 38.07 | 5.18 | 0
204 | SOUTH 24 PARAGANAS | SM/11281 | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | TSM/009573 | 40016300 | Augmentation | MVS | GO2223004517PH | 28/06/2022 | 949.51 | 54.08 | 1003.59 | Alipore Division | South 24 Pgs Mechanical Division | 269.6 | 4.55 | 21.43 | 0 | 295.57 | 269.6 | 4.55 | 21.43 | 0 | 295.57 | 29.45 | 25
205 | SOUTH 24 PARAGANAS | SM/11751 | AUGMENTATION OF GROUND WATER BASED RAMTANUNAGAR , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011503 | 40019350 | Augmentation | SVS | GO2223005961PH | 03/08/2022 | 421.96 | 35.83 | 457.78 | Alipore Division | South 24 Pgs Mechanical Division | 143.1 | 11.02 | 24.11 | 0 | 178.24 | 143.1 | 11.02 | 24.11 | 0 | 178.24 | 38.93 | 39
206 | SOUTH 24 PARAGANAS | SM/14986 | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | TSM/016127 | 40035972 | Augmentation | SVS | GO2223013170PH | 04/02/2023 | 838.13 | 71.66 | 909.79 | Alipore Division | South 24 Pgs Mechanical Division | 6.64 | 0 | 0 | 0 | 6.64 | 6.64 | 0 | 0 | 0 | 6.64 | 0.73 | 9
207 | SOUTH 24 PARAGANAS | SM/13811 | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011467 | 40034265 | Augmentation | SVS | GO2223009961PH | 22/11/2022 | 779.44 | 71.66 | 851.09 | Alipore Division | South 24 Pgs Mechanical Division | 279.65 | 0 | 0 | 0 | 279.65 | 269.23 | 0 | 0 | 0 | 269.23 | 31.63 | 5
208 | SOUTH 24 PARAGANAS | SM/13570 | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011495 | 40033922 | Augmentation | MVS | GO2223009472PH | 09/11/2022 | 1473.86 | 143.31 | 1617.17 | Alipore Division | South 24 Pgs Mechanical Division | 502.08 | 33.77 | 5.38 | 0 | 541.23 | 489.44 | 33.77 | 0 | 0 | 523.2 | 32.35 | 34
209 | SOUTH 24 PARAGANAS | SM/12572 | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011468 | 40028477 | Augmentation | MVS | GO2223007756PH | 15/09/2022 | 1261.61 | 71.66 | 1333.27 | Alipore Division | South 24 Pgs Mechanical Division | 355 | 21.82 | 47.92 | 0 | 424.74 | 339.89 | 21.82 | 47.92 | 0 | 409.62 | 30.72 | 25
210 | SOUTH 24 PARAGANAS | SM/17200 | AUGMENTATION OF HARISHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | TSM/018329 | 40049264 | Augmentation | MVS | GO2223016361PH | 15/03/2023 | 756.77 | 74.41 | 831.19 | Alipore Division | South 24 Pgs Mechanical Division | 155.82 | 0 | 97.14 | 0 | 252.97 | 5.24 | 0 | 97.14 | 0 | 102.38 | 12.32 | 1
211 | SOUTH 24 PARAGANAS | SM/16008 | AUGMENTATION OF HARISHPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/017457 | 40049262 | Augmentation | SVS | GO2223014522PH | 22/02/2023 | 543.97 | 40.43 | 584.4 | Alipore Division | South 24 Pgs Mechanical Division | 66.65 | 0 | 48.19 | 0 | 114.84 | 3.68 | 0 | 43.78 | 0 | 47.46 | 8.12 | 2
212 | SOUTH 24 PARAGANAS | SM/18868 | AUGMENTATION OF JAMALPUR W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE. (PHASE-II) | TSM/020615 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 113.58 | 0 | 113.58 | Alipore Division |  | 47.3 | 0 | 0 | 0 | 47.3 | 47.3 | 0 | 0 | 0 | 47.3 | 41.64 | 90
213 | SOUTH 24 PARAGANAS | SM/18267 | AUGMENTATION OF KACHU KHALI PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/016456 | 40035997 | Augmentation | SVS | 1588/PHE-28011/165/2023-SCHM CELL-Dept. of PHE | 21/06/2023 | 1028.8 | 75.95 | 1104.75 | Alipore Division | South 24 Pgs Mechanical Division | 120.27 | 0 | 0 | 0 | 120.27 | 120.27 | 0 | 0 | 0 | 120.27 | 10.89 | 2
214 | SOUTH 24 PARAGANAS | SM/09997 | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | TSM/008794 | 40009461 | Augmentation | MVS | GO2122007096PH | 22/12/2021 | 1181.94 | 67.98 | 1249.92 | Alipore Division | South 24 Pgs Mechanical Division | 627.93 | 10.41 | 123.11 | 0 | 761.46 | 500.81 | 10.41 | 97.88 | 0 | 609.11 | 48.73 | 20
215 | SOUTH 24 PARAGANAS | SM/09998 | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008787 | 40009444 | Augmentation | MVS | GO2122007095PH | 22/12/2021 | 1493.03 | 152.96 | 1645.98 | Alipore Division | South 24 Pgs Mechanical Division | 629.95 | 0 | 58.18 | 0 | 688.13 | 518.17 | 0 | 58.18 | 0 | 576.35 | 35.02 | 40
216 | SOUTH 24 PARAGANAS | SM/18676 | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | TSM/017465 | 40060194 | Augmentation | SVS | 2241/PHE-28011/200/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 997.17 | 35.83 | 1032.99 | Alipore Division | South 24 Pgs Mechanical Division | 405.04 | 29.3 | 41.56 | 0 | 475.89 | 277.63 | 29.3 | 41.56 | 0 | 348.49 | 33.74 | 11
217 | SOUTH 24 PARAGANAS | SM/15100 | AUGMENTATION OF KALARIA (ZONE-IIA) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | TSM/017473 | 40036939 | Augmentation | MVS | GO2223013025PH | 03/02/2023 | 863.38 | 63.25 | 926.63 | Alipore Division | South 24 Pgs Mechanical Division | 72.46 | 7.04 | 68.49 | 0 | 147.99 | 65.7 | 7.04 | 68.49 | 0 | 141.23 | 15.24 | 2
218 | SOUTH 24 PARAGANAS | SM/18332 | AUGMENTATION OF KALARIA PIPED WATER SUPPLY SCHEME IN CANNING-I BLOCK IN SOUTH 24 PARGANAS OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011086 | 40036912 | Augmentation | MVS | 1691/PHE-28011/192/2023-SCHM CELL-Dept. of PHE | 27/06/2023 | 1915.47 | 189 | 2104.47 | Alipore Division | South 24 Pgs Mechanical Division | 5.51 | 0 | 0 | 0 | 5.51 | 5.51 | 0 | 0 | 0 | 5.51 | 0.26 | 2
219 | SOUTH 24 PARAGANAS | SM/10151 | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | TSM/008774 | 40009487 | Augmentation | MVS | GO2122009596PH | 10/02/2022 | 1000.71 | 67.98 | 1068.69 | Alipore Division | South 24 Pgs Mechanical Division | 796.76 | 0 | 87.5 | 0 | 884.26 | 765.03 | 0 | 67.35 | 0 | 832.38 | 77.89 | 53
220 | SOUTH 24 PARAGANAS | SM/13757 | AUGMENTATION OF KANTHALBERIA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | TSM/015087 | 40032959 | Augmentation | SVS | GO2223009880PH | 18/11/2022 | 928.88 | 70.13 | 999.02 | Alipore Division | South 24 Pgs Mechanical Division | 65.54 | 0 | 0 | 0 | 65.54 | 3.72 | 0 | 0 | 0 | 3.72 | 0.37 | 3
221 | SOUTH 24 PARAGANAS | SM/16197 | AUGMENTATION OF KANTHALBERIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PART-B) | TSM/009230 | 40060433 | Augmentation | SVS | GO2223014834PH | 24/02/2023 | 771.18 | 63.86 | 835.04 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | SOUTH 24 PARAGANAS | SM/10478 | AUGMENTATION OF KUMARKHALI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) UNDER BASANTI BLOCK OF CANNING SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | TSM/009570 | 40014932 | Augmentation | SVS | GO2223000220PH | 13/04/2022 | 874.18 | 63.86 | 938.04 | Alipore Division | South 24 Pgs Mechanical Division | 423.54 | 14.55 | 120.71 | 0 | 558.8 | 388.58 | 14.55 | 120.71 | 0 | 523.84 | 55.84 | 37
223 | SOUTH 24 PARAGANAS | SM/18285 | AUGMENTATION OF KUMIRMARI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/016395 | 40033993 | Augmentation | SVS | 1622/PHE-28011/89/2023-ESTT CELL-Dept. of PHE | 23/06/2023 | 1209.03 | 75.95 | 1284.98 | Alipore Division | South 24 Pgs Mechanical Division | 153.06 | 0 | 18.25 | 0 | 171.31 | 8.1 | 0 | 18.25 | 0 | 26.35 | 2.05 | 2
224 | SOUTH 24 PARAGANAS | SM/15526 | AUGMENTATION OF KUMIRMARI (ZONE-II) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/016352 | 40035993 | Augmentation | SVS | GO2223013995PH | 16/02/2023 | 1124.16 | 75.95 | 1200.11 | Alipore Division | South 24 Pgs Mechanical Division | 7.44 | 0 | 37.33 | 0 | 44.77 | 7.44 | 0 | 37.33 | 0 | 44.77 | 3.73 | 2
225 | SOUTH 24 PARAGANAS | SM/14681 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DIS | TSM/016453 | 40064476 | Augmentation | MVS | GO2223012760PH | 14/06/2023 | 1020.93 | 0 | 1020.93 | Alipore Division |  | 272.03 | 0 | 15.4 | 0 | 287.43 | 272.03 | 0 | 15.4 | 0 | 287.43 | 28.15 | 45
226 | SOUTH 24 PARAGANAS | SM/18550 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-I OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016531 | 40035920 | Augmentation | MVS | 2060/PHE-28011/257/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 1014.94 | 0 | 1014.94 | Alipore Division |  | 0 | 0 | 46.53 | 0 | 46.53 | 0 | 0 | 46.53 | 0 | 46.53 | 4.58 | 0
227 | SOUTH 24 PARAGANAS | SM/14471 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-II OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016535 | 40035905 | Augmentation | MVS | GO2223012322PH | 20/01/2023 | 742.41 | 0 | 742.41 | Alipore Division |  | 107.92 | 0 | 23.75 | 0 | 131.68 | 52.36 | 0 | 23.75 | 0 | 76.12 | 10.25 | 20
228 | SOUTH 24 PARAGANAS | SM/15529 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-III OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 2 | TSM/016539 | 40035891 | Augmentation | MVS | GO2223013991PH | 16/02/2023 | 1593.85 | 0 | 1593.85 | Alipore Division |  | 515.78 | 0 | 24.6 | 0 | 540.38 | 496 | 0 | 24.6 | 0 | 520.6 | 32.66 | 40
229 | SOUTH 24 PARAGANAS | SM/14680 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016469 | 40064429 | Augmentation | MVS | GO2223012761PH | 31/01/2023 | 3361.02 | 0 | 3361.02 | Alipore Division |  | 637.4 | 0 | 353.07 | 0 | 990.47 | 281.77 | 0 | 353.07 | 0 | 634.85 | 18.89 | 1
230 | SOUTH 24 PARAGANAS | SM/18549 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016548 | 40035872 | Augmentation | MVS | 2060/PHE-28011/257/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 2067.43 | 0 | 2067.43 | Alipore Division |  | 41.7 | 0 | 123.47 | 0 | 165.17 | 3.26 | 0 | 108.97 | 0 | 112.22 | 5.43 | 5
231 | SOUTH 24 PARAGANAS | SM/18551 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016671 | 40035629 | Augmentation | MVS | 2060/PHE-28011/257/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 1245.82 | 0 | 1245.82 | Alipore Division |  | 270.75 | 0 | 17.52 | 0 | 288.27 | 125.79 | 0 | 11.14 | 0 | 136.94 | 10.99 | 2
232 | SOUTH 24 PARAGANAS | SM/18554 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016574 | 40035682 | Augmentation | MVS | 2060/PHE-28011/257/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 2100.55 | 0 | 2100.55 | Alipore Division |  | 309.64 | 0 | 35.58 | 0 | 345.22 | 244.09 | 0 | 35.58 | 0 | 279.67 | 13.31 | 30
233 | SOUTH 24 PARAGANAS | SM/18400 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VII OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 2 | TSM/016588 | 40035665 | Augmentation | MVS | 1848/PHE-28011/29/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 1869.02 | 0 | 1869.02 | Alipore Division |  | 219.58 | 0 | 61.06 | 0 | 280.63 | 219.58 | 0 | 46.8 | 0 | 266.38 | 14.25 | 5
234 | SOUTH 24 PARAGANAS | SM/18552 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(A) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | TSM/016619 | 40035655 | Augmentation | MVS | 2060/PHE-28011/257/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 2895.68 | 0 | 2895.68 | Alipore Division |  | 814.93 | 0 | 376.15 | 0 | 1191.08 | 548.21 | 0 | 75.66 | 0 | 623.88 | 21.55 | 15
235 | SOUTH 24 PARAGANAS | SM/15320 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII(B) OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOU | TSM/016633 | 40035640 | Augmentation | SVS | GO2223013642PH | 09/02/2023 | 2499.96 | 0 | 2499.96 | Alipore Division |  | 595.82 | 0 | 42.11 | 0 | 637.93 | 595.82 | 0 | 42.11 | 0 | 637.93 | 25.52 | 19
236 | SOUTH 24 PARAGANAS | SM/18553 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-X OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016692 | 40035616 | Augmentation | MVS | 2060/PHE-28011/257/2022-SCHM CELL-Dept. of PHE | 26/07/2023 | 1612.47 | 0 | 1612.47 | Alipore Division |  | 250.29 | 0 | 476.46 | 0 | 726.75 | 229.05 | 0 | 253.79 | 0 | 482.85 | 29.94 | 2
237 | SOUTH 24 PARAGANAS | SM/13909 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016697 | 40035595 | Augmentation | MVS | GO2223010223PH | 29/11/2022 | 746.69 | 0 | 746.69 | Alipore Division |  | 89.29 | 0 | 16.1 | 0 | 105.38 | 35.69 | 0 | 16.1 | 0 | 51.79 | 6.94 | 7
238 | SOUTH 24 PARAGANAS | SM/14140 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | TSM/015333 | 40054085 | Augmentation | MVS | GO2223011504PH | 02/01/2023 | 2417.25 | 0 | 2417.25 | South 24 Pgs. W/S Division - I |  | 163.1 | 0 | 156.5 | 0 | 319.61 | 163.1 | 0 | 156.5 | 0 | 319.61 | 13.22 | 2
239 | SOUTH 24 PARAGANAS | SM/18219 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dt | TSM/016360 | 40054095 | Augmentation | MVS | GO2324000351PH | 27/04/2023 | 3818.38 | 0 | 3818.38 | South 24 Pgs. W/S Division - I |  | 23.51 | 0 | 1269.76 | 0 | 1293.26 | 23.51 | 0 | 1115.37 | 0 | 1138.88 | 29.83 | 1
240 | SOUTH 24 PARAGANAS | SM/16184 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water su | TSM/015075 | 40054074 | Augmentation | MVS | GO2223014397PH | 20/02/2023 | 291.35 | 455.51 | 746.86 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 155.06 | 0 | 0 | 0 | 155.06 | 155.06 | 0 | 0 | 0 | 155.06 | 20.76 | 8
241 | SOUTH 24 PARAGANAS | SM/16185 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | TSM/015334 | 40054089 | Augmentation | MVS | GO2223014398PH | 20/02/2023 | 1555.02 | 0 | 1555.02 | South 24 Pgs. W/S Division - I |  | 242.04 | 0 | 298.55 | 0 | 540.6 | 242.04 | 0 | 298.55 | 0 | 540.6 | 34.76 | 19
242 | SOUTH 24 PARAGANAS | SM/16186 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | TSM/015332 | 40054097 | Augmentation | MVS | GO2223014395PH | 20/02/2023 | 2189.82 | 0 | 2189.82 | South 24 Pgs. W/S Division - I |  | 468.93 | 0 | 212.3 | 0 | 681.23 | 468.93 | 0 | 212.3 | 0 | 681.23 | 31.11 | 21
243 | SOUTH 24 PARAGANAS | SM/16187 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply | TSM/015076 | 40054075 | Augmentation | MVS | GO2223014393PH | 20/02/2023 | 1161.61 | 0 | 1161.61 | South 24 Pgs. W/S Division - I |  | 250.05 | 0 | 0 | 0 | 250.05 | 250.05 | 0 | 0 | 0 | 250.05 | 21.53 | 15
244 | SOUTH 24 PARAGANAS | SM/18220 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | TSM/016361 | 40054100 | Augmentation | MVS | GO2324000353PH | 27/04/2023 | 2893.58 | 0 | 2893.58 | South 24 Pgs. W/S Division - I |  | 375.08 | 0 | 1328.5 | 0 | 1703.57 | 375.08 | 0 | 1328.5 | 0 | 1703.57 | 58.87 | 5
245 | SOUTH 24 PARAGANAS | SM/13513 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | TSM/015078 | 40054078 | Augmentation | MVS | GO2223009262PH | 02/11/2022 | 717.38 | 0 | 717.38 | South 24 Pgs. W/S Division - I |  | 90.49 | 0 | 0 | 0 | 90.49 | 90.49 | 0 | 0 | 0 | 90.49 | 12.61 | 50
246 | SOUTH 24 PARAGANAS | SM/16183 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | TSM/015335 | 40054093 | Augmentation | MVS | GO2223014388PH | 20/02/2023 | 1817.52 | 0 | 1817.52 | South 24 Pgs. W/S Division - I |  | 197.23 | 0 | 291.14 | 0 | 488.38 | 197.23 | 0 | 291.14 | 0 | 488.38 | 26.87 | 10
247 | SOUTH 24 PARAGANAS | SM/18221 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | TSM/016362 | 40054101 | Augmentation | MVS | GO2324000354PH | 27/04/2023 | 2879.31 | 0 | 2879.31 | South 24 Pgs. W/S Division - I |  | 233.7 | 0 | 1421.74 | 0 | 1655.44 | 233.7 | 0 | 1421.74 | 0 | 1655.44 | 57.49 | 0
248 | SOUTH 24 PARAGANAS | SM/18656 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | TSM/015336 | 40054094 | Augmentation | MVS | 2235/PHE-28011/153/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1120.85 | 0 | 1120.85 | South 24 Pgs. W/S Division - I |  | 287.91 | 0 | 113.51 | 0 | 401.42 | 287.91 | 0 | 113.51 | 0 | 401.42 | 35.81 | 26
249 | SOUTH 24 PARAGANAS | SM/16188 | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-XI at MANDIRBAZAR block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, P | TSM/015099 | 40055867 | Augmentation | MVS | GO2223014389PH | 20/02/2023 | 905.6 | 0 | 905.6 | South 24 Pgs. W/S Division - I |  | 376.27 | 0 | 0 | 0 | 376.27 | 376.27 | 0 | 0 | 0 | 376.27 | 41.55 | 40
250 | SOUTH 24 PARAGANAS | SM/13970 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC IN THE LEFT OUT AREAS IN ZONE-I AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UND | TSM/016330 | 40035396 | Augmentation | MVS | GO2223010359PH | 01/12/2022 | 574.64 | 0 | 574.64 | Alipore Division |  | 283.35 | 0 | 48.81 | 0 | 332.16 | 283.35 | 0 | 48.81 | 0 | 332.16 | 57.8 | 20
251 | SOUTH 24 PARAGANAS | SM/14890 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC IN THE LEFT OUT AREAS IN ZONE-VI AT DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT - SOUTH | TSM/016771 | 40035273 | Augmentation | MVS | GO2223013106PH | 04/02/2023 | 117.28 | 0 | 117.28 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | SOUTH 24 PARAGANAS | SM/13833 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IX OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDER DIA | TSM/016462 | 40034557 | Augmentation | MVS | GO2223010088PH | 25/11/2022 | 672.9 | 0 | 672.9 | Alipore Division |  | 214.96 | 0 | 13.78 | 0 | 228.74 | 67.91 | 0 | 13.78 | 0 | 81.68 | 12.14 | 65
253 | SOUTH 24 PARAGANAS | SM/15321 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-VIII OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDER D | TSM/016461 | 40034555 | Augmentation | MVS | GO2223013646PH | 09/02/2023 | 1279.51 | 0 | 1279.51 | Alipore Division |  | 2.85 | 0 | 29.07 | 0 | 31.92 | 2.85 | 0 | 29.07 | 0 | 31.92 | 2.49 | 5
254 | SOUTH 24 PARAGANAS | SM/13832 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDER DIA | TSM/016464 | 40034560 | Augmentation | MVS | GO2223010087PH | 25/11/2022 | 668.65 | 0 | 668.65 | Alipore Division |  | 2.57 | 0 | 12.91 | 0 | 15.48 | 2.57 | 0 | 12.91 | 0 | 15.48 | 2.32 | 12
255 | SOUTH 24 PARAGANAS | SM/18222 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | TSM/016052 | 40054087 | Augmentation | MVS | GO2324000355PH | 27/04/2023 | 2324.6 | 0 | 2324.6 | South 24 Pgs. W/S Division - I |  | 503.62 | 0 | 437.75 | 0 | 941.37 | 503.62 | 0 | 437.75 | 0 | 941.37 | 40.5 | 25
256 | SOUTH 24 PARAGANAS | SM/18223 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | TSM/016053 | 40054096 | Augmentation | MVS | GO2324000356PH | 27/04/2023 | 2958.02 | 0 | 2958.02 | South 24 Pgs. W/S Division - I |  | 1237.38 | 0 | 513.21 | 0 | 1750.59 | 1237.38 | 0 | 513.21 | 0 | 1750.59 | 59.18 | 33
257 | SOUTH 24 PARAGANAS | SM/18655 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | TSM/014962 | 40054090 | Augmentation | MVS | 2235/PHE-28011/153/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1782.14 | 0 | 1782.14 | South 24 Pgs. W/S Division - I |  | 149.85 | 0 | 474.73 | 0 | 624.58 | 149.85 | 0 | 474.73 | 0 | 624.58 | 35.05 | 15
258 | SOUTH 24 PARAGANAS | SM/16189 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-p | TSM/014995 | 40054098 | Augmentation | MVS | GO2223014394PH | 20/02/2023 | 1691.01 | 0 | 1691.01 | South 24 Pgs. W/S Division - I |  | 489.01 | 0 | 0 | 0 | 489.01 | 489.01 | 0 | 0 | 0 | 489.01 | 28.92 | 38
259 | SOUTH 24 PARAGANAS | SM/16190 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 2 | TSM/014963 | 40054091 | Augmentation | MVS | GO2223014391PH | 20/02/2023 | 1547.3 | 0 | 1547.3 | South 24 Pgs. W/S Division - I |  | 296.34 | 0 | 220.62 | 0 | 516.96 | 296.34 | 0 | 220.62 | 0 | 516.96 | 33.41 | 22
260 | SOUTH 24 PARAGANAS | SM/18224 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | TSM/016054 | 40054099 | Augmentation | MVS | GO2324000357PH | 27/04/2023 | 2657.13 | 0 | 2657.13 | South 24 Pgs. W/S Division - I |  | 304.22 | 0 | 282.86 | 0 | 587.09 | 304.22 | 0 | 282.86 | 0 | 587.09 | 22.09 | 14
261 | SOUTH 24 PARAGANAS | SM/16191 | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | TSM/014964 | 40054092 | Augmentation | MVS | GO2223014390PH | 20/02/2023 | 1247.95 | 0 | 1247.95 | South 24 Pgs. W/S Division - I |  | 631.56 | 0 | 78.88 | 0 | 710.44 | 631.56 | 0 | 78.88 | 0 | 710.44 | 56.93 | 43
262 | SOUTH 24 PARAGANAS | SM/13952 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | TSM/016349 | 40064237 | Augmentation | MVS | GO2223010358PH | 01/12/2022 | 334.04 | 0 | 334.04 | Alipore Division |  | 232.15 | 0 | 12.32 | 0 | 244.47 | 180.91 | 0 | 12.32 | 0 | 193.23 | 57.85 | 3
263 | SOUTH 24 PARAGANAS | SM/14892 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | TSM/016702 | 40035005 | Augmentation | MVS | GO2223013098PH | 04/02/2023 | 544.13 | 0 | 544.13 | Alipore Division |  | 97.88 | 0 | 19.99 | 0 | 117.87 | 7.68 | 0 | 19.99 | 0 | 27.66 | 5.08 | 25
264 | SOUTH 24 PARAGANAS | SM/13969 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | TSM/016375 | 40064239 | Augmentation | MVS | GO2223010360PH | 01/12/2022 | 329.74 | 0 | 329.74 | Alipore Division |  | 47.39 | 0 | 0 | 0 | 47.39 | 15.77 | 0 | 0 | 0 | 15.77 | 4.78 | 10
265 | SOUTH 24 PARAGANAS | SM/13912 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- IV AT DIAMOND HARBOUR II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DIS | TSM/016707 | 40035043 | Augmentation | MVS | GO2223010225PH | 29/11/2022 | 631.92 | 0 | 631.92 | Alipore Division |  | 0 | 0 | 16.32 | 0 | 16.32 | 0 | 0 | 16.32 | 0 | 16.32 | 2.58 | 0
266 | SOUTH 24 PARAGANAS | SM/14464 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- IX AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | TSM/016698 | 40064461 | Augmentation | MVS | GO2223012321PH | 20/01/2023 | 395.19 | 0 | 395.19 | Alipore Division |  | 273.13 | 0 | 3.08 | 0 | 276.21 | 210.95 | 0 | 3.08 | 0 | 214.03 | 54.16 | 15
267 | SOUTH 24 PARAGANAS | SM/14463 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC | TSM/016768 | 40035267 | Augmentation | MVS | GO2223012326PH | 20/01/2023 | 406.93 | 0 | 406.93 | Alipore Division |  | 139.59 | 0 | 0 | 0 | 139.59 | 139.59 | 0 | 0 | 0 | 139.59 | 34.3 | 10
268 | SOUTH 24 PARAGANAS | SM/14477 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | TSM/016447 | 40064330 | Augmentation | MVS | GO2223012339PH | 20/01/2023 | 341.86 | 0 | 341.86 | Alipore Division |  | 40.25 | 0 | 13.43 | 0 | 53.68 | 40.25 | 0 | 13.43 | 0 | 53.68 | 15.7 | 1
269 | SOUTH 24 PARAGANAS | SM/14902 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | TSM/016484 | 40064433 | Augmentation | MVS | GO2223013103PH | 04/02/2023 | 375.18 | 0 | 375.18 | Alipore Division |  | 75.4 | 0 | 14.78 | 0 | 90.19 | 9.76 | 0 | 14.78 | 0 | 24.55 | 6.54 | 5
270 | SOUTH 24 PARAGANAS | SM/14891 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VII AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRI | TSM/016772 | 40064479 | Augmentation | MVS | GO2223013105PH | 04/02/2023 | 247.47 | 0 | 247.47 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | SOUTH 24 PARAGANAS | SM/17182 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | TSM/016541 | 40064457 | Augmentation | MVS | GO2223016352PH | 15/03/2023 | 371.8 | 0 | 371.8 | Alipore Division |  | 275.87 | 0 | 0 | 0 | 275.87 | 253.04 | 0 | 0 | 0 | 253.04 | 68.06 | 70
272 | SOUTH 24 PARAGANAS | SM/14473 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | TSM/016563 | 40064458 | Augmentation | MVS | GO2223012328PH | 20/01/2023 | 265.91 | 0 | 265.91 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
273 | SOUTH 24 PARAGANAS | SM/18399 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-II OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PAR | TSM/016609 | 40034127 | Augmentation | MVS | 1848/PHE-28011/29/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 2023.72 | 0 | 2023.72 | Alipore Division |  | 0 | 0 | 61.88 | 0 | 61.88 | 0 | 0 | 38.95 | 0 | 38.95 | 1.92 | 15
274 | SOUTH 24 PARAGANAS | SM/13913 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-V OF DIAMOND HARBOUR-I BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARG | TSM/016600 | 40034209 | Augmentation | MVS | GO2223010227PH | 29/11/2022 | 817.13 | 0 | 817.13 | Alipore Division |  | 2.69 | 0 | 2.34 | 0 | 5.03 | 2.69 | 0 | 2.34 | 0 | 5.03 | 0.62 | 8
275 | SOUTH 24 PARAGANAS | SM/15530 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS FOR PROVIDING FHTC TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS AT ZONE-VIII OF DIAMOND HARBOUR-II BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | TSM/016468 | 40035286 | Augmentation | MVS | GO2223013993PH | 16/02/2023 | 1376.48 | 0 | 1376.48 | Alipore Division |  | 158.58 | 0 | 37.23 | 0 | 195.81 | 3.14 | 0 | 37.23 | 0 | 40.37 | 2.93 | 25
276 | SOUTH 24 PARAGANAS | SM/13911 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | TSM/016700 | 40035581 | Augmentation | MVS | GO2223010226PH | 29/11/2022 | 740.12 | 0 | 740.12 | Alipore Division |  | 32.63 | 0 | 1.53 | 0 | 34.16 | 32.63 | 0 | 1.53 | 0 | 34.16 | 4.62 | 10
277 | SOUTH 24 PARAGANAS | SM/14472 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-V OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' UNDE | TSM/016567 | 40035687 | Augmentation | MVS | GO2223012319PH | 20/01/2023 | 461.17 | 0 | 461.17 | Alipore Division |  | 72.49 | 0 | 24.6 | 0 | 97.09 | 46.75 | 0 | 24.6 | 0 | 71.35 | 15.47 | 10
278 | SOUTH 24 PARAGANAS | SM/13910 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XIII OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 PARGANAS' U | TSM/016699 | 40035557 | Augmentation | MVS | GO2223010222PH | 29/11/2022 | 943.26 | 0 | 943.26 | Alipore Division |  | 155.55 | 0 | 62.81 | 0 | 218.36 | 3 | 0 | 62.81 | 0 | 65.81 | 6.98 | 20
279 | SOUTH 24 PARAGANAS | SM/14465 | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | TSM/016695 | 40064250 | Augmentation | MVS | GO2223012332PH | 20/01/2023 | 633.13 | 0 | 633.13 | Alipore Division |  | 200.05 | 0 | 14.35 | 0 | 214.4 | 146.37 | 0 | 14.35 | 0 | 160.72 | 25.38 | 1
280 | SOUTH 24 PARAGANAS | SM/10783 | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | TSM/008798 | 40014393 | Augmentation | MVS | GO2223003489PH | 25/05/2022 | 959.84 | 96.82 | 1056.66 | Alipore Division | South 24 Pgs Mechanical Division | 566.1 | 0 | 126.19 | 0 | 692.29 | 442.81 | 0 | 126.19 | 0 | 569 | 53.85 | 30
281 | SOUTH 24 PARAGANAS | SM/18867 | AUGMENTATION OF MOUKHALI W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE (PHASE-II) | TSM/020616 | 0 | Augmentation | MVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 262.32 | 0 | 262.32 | Alipore Division |  | 15.98 | 0 | 0 | 0 | 15.98 | 15.98 | 0 | 0 | 0 | 15.98 | 6.09 | 10
282 | SOUTH 24 PARAGANAS | SM/15961 | AUGMENTATION OF NARAYANGAR (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK : CANNING-I, DISTRICT : SOUTH 24 PARGANAS | TSM/018335 | 40060069 | Augmentation | SVS | GO2223014515PH | 22/02/2023 | 624.12 | 106.77 | 730.89 | Alipore Division | South 24 Pgs Mechanical Division | 226.51 | 59.11 | 1.17 | 0 | 286.8 | 213.66 | 59.11 | 1.17 | 0 | 273.95 | 37.48 | 49
283 | SOUTH 24 PARAGANAS | SM/13756 | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | TSM/015138 | 40032965 | Augmentation | SVS | GO2223009881PH | 18/11/2022 | 446.23 | 37.33 | 483.56 | Alipore Division | South 24 Pgs Mechanical Division | 43.11 | 0 | 0 | 0 | 43.11 | 43.11 | 0 | 0 | 0 | 43.11 | 8.92 | 5
284 | SOUTH 24 PARAGANAS | SM/18244 | AUGMENTATION OF PATHANKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/016411 | 40036009 | Augmentation | MVS | 1556/PHE-28011/159/2023-SCHM CELL-Dept. of PHE | 16/06/2023 | 1121 | 80.85 | 1201.85 | Alipore Division | South 24 Pgs Mechanical Division | 171.82 | 0 | 172.19 | 0 | 344.01 | 171.82 | 0 | 172.19 | 0 | 344.01 | 28.62 | 2
285 | SOUTH 24 PARAGANAS | SM/15968 | Augmentation of Pathankhali PWSS Zone-II for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | TSM/018317 | 40060106 | Augmentation | MVS | GO2223014513PH | 22/02/2023 | 731.36 | 55.5 | 786.86 | Alipore Division | South 24 Pgs Mechanical Division | 150.02 | 0 | 49.44 | 0 | 199.47 | 150.02 | 0 | 49.44 | 0 | 199.47 | 25.35 | 2
286 | SOUTH 24 PARAGANAS | SM/15561 | Augmentation of Pathankhali PWSS Zone-III for Providing Functional Household Tap Connection (FHTC) Block - Gosaba | TSM/018321 | 40049234 | Augmentation | SVS | GO2223013883PH | 15/02/2023 | 516.3 | 71.66 | 587.95 | Alipore Division | South 24 Pgs Mechanical Division | 231.44 | 0 | 16.04 | 0 | 247.48 | 157.37 | 0 | 16.04 | 0 | 173.41 | 29.49 | 3
287 | SOUTH 24 PARAGANAS | SM/15225 | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | TSM/015103 | 40032974 | Augmentation | SVS | GO2223013355PH | 06/02/2023 | 1053.92 | 70.13 | 1124.06 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 30.78 | 0 | 30.78 | 0 | 0 | 21.64 | 0 | 21.64 | 1.92 | 0
288 | SOUTH 24 PARAGANAS | SM/16195 | AUGMENTATION OF PHULMALANCHA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC)(PART-B) | TSM/009229 | 40060410 | Augmentation | SVS | GO2223014835PH | 24/02/2023 | 736.61 | 80.86 | 817.46 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 13.54 | 0 | 13.54 | 0 | 0 | 13.54 | 0 | 13.54 | 1.66 | 0
289 | SOUTH 24 PARAGANAS | SM/18865 | Augmentation of Sirakol Zone-I Water Supply Scheme of Magrahat-I Block under Alipore Division,PHE Dte. | TSM/020734 | 0 | Augmentation | MVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 69.96 | 0 | 69.96 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | SOUTH 24 PARAGANAS | SM/16005 | AUGMENTATION OF SONAKHALI (ZONE-I) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | TSM/017464 | 40060326 | Augmentation | MVS | GO2223014516PH | 22/02/2023 | 504.77 | 45.5 | 550.27 | Alipore Division | South 24 Pgs Mechanical Division | 142.08 | 14.59 | 5.55 | 0 | 162.22 | 79.42 | 14.59 | 5.55 | 0 | 99.57 | 18.09 | 4
291 | SOUTH 24 PARAGANAS | SM/16116 | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | TSM/017766 | 40049261 | Augmentation | MVS | GO2223014508PH | 22/02/2023 | 695.53 | 40.5 | 736.03 | Alipore Division | South 24 Pgs Mechanical Division | 124.22 | 0 | 84.85 | 0 | 209.07 | 21.42 | 0 | 84.85 | 0 | 106.27 | 14.44 | 2
292 | SOUTH 24 PARAGANAS | SM/18675 | AUGMENTATION OF SONAKHALI (ZONE-III) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | TSM/017952 | 40060430 | Augmentation | SVS | 2241/PHE-28011/200/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 952.14 | 62 | 1014.14 | Alipore Division | South 24 Pgs Mechanical Division | 102.3 | 0 | 50.73 | 0 | 153.03 | 102.3 | 0 | 40.8 | 0 | 143.1 | 14.11 | 8
293 | SOUTH 24 PARAGANAS | SM/15566 | AUGMENTATION OF SONAKHALI (ZONE-IV) PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI,DISTRICT-SOUTH 24 PARGANAS | TSM/017560 | 40060435 | Augmentation | MVS | GO2223013878PH | 15/02/2023 | 451.61 | 45.5 | 497.11 | Alipore Division | South 24 Pgs Mechanical Division | 88.92 | 0 | 40.48 | 0 | 129.4 | 88.92 | 0 | 40.48 | 0 | 129.4 | 26.03 | 3
294 | SOUTH 24 PARAGANAS | SM/09435 | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008786 | 40008777 | Augmentation | SVS | GO2122005555PH | 18/11/2021 | 162.6 | 67.98 | 230.58 | Alipore Division | South 24 Pgs Mechanical Division | 93.24 | 0 | 0 | 0 | 93.24 | 93.24 | 0 | 0 | 0 | 93.24 | 40.44 | 85
295 | SOUTH 24 PARAGANAS | SM/14466 | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/016706 | 40035436 | Augmentation | SVS | GO2223012336PH | 20/01/2023 | 696.95 | 40.43 | 737.38 | Alipore Division | South 24 Pgs Mechanical Division | 3.76 | 3.29 | 27.88 | 0 | 34.92 | 3.76 | 3.29 | 27.88 | 0 | 34.92 | 4.74 | 4
296 | SOUTH 24 PARAGANAS | SM/08869 | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | TSM/005541 | 40021909 | Augmentation | SVS | GO2122003261PH | 14/09/2021 | 56400 | 0 | 56400 | South 24 Pgs. W/S Division - I |  | 21474.84 | 0 | 8178.24 | 0 | 29653.08 | 21474.84 | 0 | 8138.32 | 0 | 29613.16 | 38.08 | 41
297 | SOUTH 24 PARAGANAS | SM/18281 | AUGMENTATION OF TILKUMAR PIPED WATER SUPPLY SCHEME, BLOCK-BASANTI UNDER ALIPORE DIVISION, PHE DTE | TSM/018398 | 40060310 | Augmentation | MVS | 1626/PHE-28011/166/2023-SCHM CELL-Dept. of PHE | 23/06/2023 | 3559.13 | 54.51 | 3613.64 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 20.4 | 0 | 0 | 20.4 | 0 | 20.4 | 0 | 0 | 20.4 | 0.56 | 2
298 | SOUTH 24 PARAGANAS | SM/10520 | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | TSM/009236 | 5344170 | Augmentation | MVS | GO2223000225PH | 13/04/2022 | 301.1 | 59.74 | 360.84 | Alipore Division | South 24 Pgs Mechanical Division | 26.04 | 0 | 251.32 | 0 | 277.36 | 26.04 | 0 | 251.32 | 0 | 277.36 | 76.86 | 4
299 | SOUTH 24 PARAGANAS | SM/10217 | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | TSM/009240 | 5344170 | Augmentation | MVS | GO2122010005PH | 24/02/2022 | 487.5 | 59.74 | 547.24 | Alipore Division | South 24 Pgs Mechanical Division | 12.58 | 0 | 47.12 | 0 | 59.7 | 12.58 | 0 | 47.12 | 0 | 59.7 | 10.91 | 4
300 | SOUTH 24 PARAGANAS | SM/10534 | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | TSM/009241 | 5344170 | Augmentation | SVS | GO2223000224PH | 13/04/2022 | 148.76 | 59.74 | 208.5 | Alipore Division | South 24 Pgs Mechanical Division | 2.39 | 0 | 10.9 | 0 | 13.28 | 2.39 | 0 | 10.9 | 0 | 13.28 | 6.37 | 4
301 | SOUTH 24 PARAGANAS | SM/10532 | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | TSM/009232 | 5344170 | Augmentation | MVS | GO2223000221PH | 13/04/2022 | 94.6 | 59.74 | 154.34 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 3.06 | 4.42 | 0 | 7.48 | 0 | 3.06 | 0 | 0 | 3.06 | 1.98 | 9
302 | SOUTH 24 PARAGANAS | SM/18279 | AUGMENTATION SCHEME FOR HAREKRISHNAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK - BASANTI | TSM/018402 | 40049254 | Augmentation | MVS | 1626/PHE-28011/166/2023-SCHM CELL-Dept. of PHE | 23/06/2023 | 1040.09 | 94.76 | 1134.85 | Alipore Division | South 24 Pgs Mechanical Division | 58.52 | 0 | 106.67 | 0 | 165.19 | 58.52 | 0 | 88.48 | 0 | 146.99 | 12.95 | 3
303 | SOUTH 24 PARAGANAS | SM/14487 | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/014173 | 40033879 | Augmentation | MVS | GO2223012257PH | 20/01/2023 | 1364.92 | 81.16 | 1446.08 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 129.46 | 0 | 37.98 | 0 | 167.44 | 129.46 | 0 | 37.98 | 0 | 167.44 | 11.58 | 9
304 | SOUTH 24 PARAGANAS | SM/18392 | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011013 | 40035973 | New | SVS | 1815/PHE-28011/211/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 961.3 | 53.47 | 1014.76 | Alipore Division | South 24 Pgs Mechanical Division | 103.42 | 0 | 16.9 | 0 | 120.32 | 61.01 | 0 | 16.9 | 0 | 77.91 | 7.68 | 9
305 | SOUTH 24 PARAGANAS | SM/13774 | BENIABOW piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016028 | 40033105 | Augmentation | MVS | GO2223009895PH | 18/11/2022 | 558.85 | 69.88 | 628.73 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 125.55 | 21.59 | 35.39 | 0 | 182.53 | 125.55 | 21.59 | 35.39 | 0 | 182.53 | 29.03 | 15
306 | SOUTH 24 PARAGANAS | SM/13308 | BHABANIPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015505 | 40034097 | Augmentation | SVS | GO2223008850PH | 17/10/2022 | 620.53 | 72.61 | 693.14 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 68.94 | 27.19 | 24.18 | 0 | 120.31 | 68.94 | 27.19 | 24.18 | 0 | 120.31 | 17.36 | 16
307 | SOUTH 24 PARAGANAS | SM/13341 | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | TSM/015204 | 40034226 | Augmentation | MVS | GO2223008844PH | 17/10/2022 | 927.29 | 71.05 | 998.34 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 338.71 | 14.57 | 29.97 | 0 | 383.25 | 338.71 | 3.77 | 29.19 | 0 | 371.68 | 37.23 | 25
308 | SOUTH 24 PARAGANAS | SM/18225 | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016321 | 40034128 | Augmentation | SVS | GO2324000359PH | 27/04/2023 | 1205.41 | 77.64 | 1283.05 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 18.7 | 0 | 18.7 | 0 | 0 | 18.7 | 0 | 18.7 | 1.46 | 0
309 | SOUTH 24 PARAGANAS | SM/12044 | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | TSM/010740 | 40026140 | New | MVS | GO2223006889PH | 01/09/2022 | 841.38 | 78.5 | 919.88 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 223.57 | 14.4 | 15.39 | 0 | 253.36 | 223.57 | 14.4 | 15.39 | 0 | 253.36 | 27.54 | 11
310 | SOUTH 24 PARAGANAS | SM/14419 | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | TSM/010665 | 40033918 | New | MVS | GO2223012151PH | 20/01/2023 | 1003.89 | 76.05 | 1079.94 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 285.64 | 0 | 51.93 | 0 | 337.57 | 285.64 | 0 | 51.93 | 0 | 337.57 | 31.26 | 19
311 | SOUTH 24 PARAGANAS | SM/18328 | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016315 | 40034266 | Augmentation | MVS | 1690/PHE-28011/218/2022-SCHM CELL-Dept. of PHE | 27/06/2023 | 1425.17 | 83.02 | 1508.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 81.59 | 16.3 | 20.3 | 0 | 118.19 | 81.59 | 16.3 | 20.3 | 0 | 118.19 | 7.84 | 6
312 | SOUTH 24 PARAGANAS | SM/13370 | Construction and installation of MANIFOLD and allied works at OHR site of Zone-9, Bishnupur-II Block, under of Surface Water Based Water Supply Scheme in the arsenic affected areas of south 24 parganas district. | TSM/014338 | 40055872 | Augmentation | MVS | GO2223008953PH | 19/10/2022 | 22.37 | 0 | 22.37 | South 24 Pgs. W/S Division - I |  | 16.26 | 0 | 0 | 0 | 16.26 | 16.26 | 0 | 0 | 0 | 16.26 | 72.71 | 60
313 | SOUTH 24 PARAGANAS | SM/18394 | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | TSM/017111 | 40035213 | New | MVS | 1817/PHE-28011/182/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1198.45 | 47.27 | 1245.72 | Alipore Division | South 24 Pgs Mechanical Division | 263.9 | 11.61 | 53.24 | 0 | 328.74 | 191.99 | 8.06 | 53.24 | 0 | 253.29 | 20.33 | 15
314 | SOUTH 24 PARAGANAS | SM/18684 | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | TSM/011020 | 40066198 | New | MVS | 2245/PHE-28011/229/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1251.64 | 49.24 | 1300.88 | Alipore Division | South 24 Pgs Mechanical Division | 355.4 | 8.67 | 18.6 | 0 | 382.67 | 347.1 | 0 | 18.6 | 0 | 365.69 | 28.11 | 19
315 | SOUTH 24 PARAGANAS | SM/16758 | Dakshin Durgapur Piped Water Supply Scheme. | TSM/003912 | 40060099 | New | SVS | GO2223015683PH | 13/03/2023 | 763.9 | 36.37 | 800.27 | Alipore Division | South 24 Pgs Mechanical Division | 342.72 | 0 | 14.52 | 0 | 357.24 | 140.62 | 0 | 14.52 | 0 | 155.14 | 19.39 | 29
316 | SOUTH 24 PARAGANAS | SM/15861 | DAKSHIN RAJAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/017116 | 40052556 | Augmentation | MVS | GO2223014351PH | 20/02/2023 | 924.67 | 75.23 | 999.91 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 88.1 | 0 | 40.06 | 0 | 128.16 | 88.1 | 0 | 30.63 | 0 | 118.73 | 11.87 | 9
317 | SOUTH 24 PARAGANAS | SM/13674 | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | TSM/014441 | 40034129 | Augmentation | MVS | GO2223009273PH | 02/11/2022 | 914.23 | 76.56 | 990.8 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 439.23 | 31.61 | 24.76 | 0 | 495.6 | 439.23 | 31.61 | 24.76 | 0 | 495.6 | 50.02 | 39
318 | SOUTH 24 PARAGANAS | SM/18329 | DEARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016320 | 40034147 | Augmentation | MVS | 1690/PHE-28011/218/2022-SCHM CELL-Dept. of PHE | 27/06/2023 | 1099.41 | 73.33 | 1172.73 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 261.27 | 10.24 | 49.71 | 0 | 321.21 | 261.27 | 10.24 | 41.89 | 0 | 313.4 | 26.72 | 10
319 | SOUTH 24 PARAGANAS | SM/18569 | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | TSM/018465 | 40047246 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1043.92 | 81.54 | 1125.46 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 36.58 | 0 | 36.58 | 0 | 0 | 36.58 | 0 | 36.58 | 3.25 | 0
320 | SOUTH 24 PARAGANAS | SM/15757 | Detailed project report for BODRA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under | TSM/017117 | 40052616 | Augmentation | MVS | GO2223014321PH | 20/02/2023 | 922.71 | 74.55 | 997.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 164.91 | 0 | 48.92 | 0 | 213.82 | 164.91 | 0 | 48.92 | 0 | 213.82 | 21.44 | 9
321 | SOUTH 24 PARAGANAS | SM/18499 | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | TSM/018469 | 40053120 | Augmentation | MVS | 2036/PHE-28011/194/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1435.45 | 80.73 | 1516.18 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 17.43 | 0 | 17.43 | 0 | 0 | 7.69 | 0 | 7.69 | 0.51 | 0
322 | SOUTH 24 PARAGANAS | SM/18572 | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | TSM/018472 | 40047259 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1062.08 | 83.02 | 1145.1 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 17.56 | 0 | 17.56 | 0 | 0 | 5.8 | 0 | 5.8 | 0.51 | 1
323 | SOUTH 24 PARAGANAS | SM/18497 | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | TSM/017715 | 40053087 | Augmentation | MVS | 2036/PHE-28011/194/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1370.38 | 72.21 | 1442.59 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 223.51 | 0 | 15.42 | 0 | 238.93 | 144.56 | 0 | 7.31 | 0 | 151.87 | 10.53 | 14
324 | SOUTH 24 PARAGANAS | SM/18546 | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | TSM/018121 | 40053590 | Augmentation | MVS | 2059/PHE-28011/199/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 981.01 | 74.03 | 1055.04 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 183.51 | 4.84 | 27.58 | 0 | 215.94 | 183.51 | 4.84 | 22.05 | 0 | 210.4 | 19.94 | 16
325 | SOUTH 24 PARAGANAS | SM/18545 | Detailed project report for KHARAMBA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Und | TSM/018344 | 40052642 | Augmentation | MVS | 2059/PHE-28011/199/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1610.17 | 81.16 | 1691.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 102.49 | 0 | 19.42 | 0 | 121.91 | 102.49 | 0 | 19.42 | 0 | 121.91 | 7.21 | 10
326 | SOUTH 24 PARAGANAS | SM/18547 | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | TSM/018316 | 40052634 | Augmentation | MVS | 2059/PHE-28011/199/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1167.89 | 75.18 | 1243.06 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 184.27 | 0 | 33.31 | 0 | 217.58 | 184.27 | 0 | 25.41 | 0 | 209.68 | 16.87 | 9
327 | SOUTH 24 PARAGANAS | SM/15633 | DETAILED PROJECT REPORT FORPROPOSED GROUND WATER BASED DONGAJORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KULTALI BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT | TSM/020398 | 40053038 | New | SVS | GO2223013879PH | 15/02/2023 | 91.69 | 28.23 | 119.91 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.39 | 0 | 0 | 0 | 2.39 | 2.39 | 0 | 0 | 0 | 2.39 | 2 | 2
328 | SOUTH 24 PARAGANAS | SM/18127 | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011063 | 40066195 | New | SVS | GO2223017946PH | 29/03/2023 | 195.22 | 22.34 | 217.56 | Alipore Division | South 24 Pgs Mechanical Division | 53.83 | 0 | 1.55 | 0 | 55.39 | 53.83 | 0 | 1.55 | 0 | 55.39 | 25.46 | 56
329 | SOUTH 24 PARAGANAS | SM/12043 | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | TSM/010678 | 40026128 | New | MVS | GO2223006888PH | 01/09/2022 | 904.48 | 76.7 | 981.18 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 19.64 | 0 | 19.64 | 0 | 0 | 19.64 | 0 | 19.64 | 2 | 0
330 | SOUTH 24 PARAGANAS | SM/15773 | GANGAJOARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/017714 | 40053052 | Augmentation | MVS | GO2223014316PH | 20/02/2023 | 913.83 | 74.69 | 988.51 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 276.29 | 19.74 | 73.78 | 0 | 369.81 | 276.29 | 19.74 | 73.78 | 0 | 369.81 | 37.41 | 14
331 | SOUTH 24 PARAGANAS | SM/12206 | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | TSM/014452 | 40026105 | Augmentation | MVS | GO2223007097PH | 06/09/2022 | 740.33 | 71.63 | 811.97 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 186.7 | 10.21 | 14.88 | 0 | 211.78 | 186.7 | 10.21 | 14.88 | 0 | 211.78 | 26.08 | 16
332 | SOUTH 24 PARAGANAS | SM/14988 | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | TSM/017110 | 40035211 | New | SVS | GO2223013173PH | 04/02/2023 | 453.74 | 69.8 | 523.55 | Alipore Division | South 24 Pgs Mechanical Division | 271.37 | 23.11 | 7.67 | 0 | 302.15 | 271.37 | 23.11 | 0 | 0 | 294.48 | 56.25 | 81
333 | SOUTH 24 PARAGANAS | SM/15862 | GOBINDAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/017732 | 40053531 | Augmentation | MVS | GO2223014345PH | 20/02/2023 | 800.34 | 73.91 | 874.24 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 41.22 | 0 | 43.13 | 0 | 84.35 | 41.22 | 0 | 43.13 | 0 | 84.35 | 9.65 | 9
334 | SOUTH 24 PARAGANAS | SM/15524 | GOPALNAGAR UTTAR ZONE-I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011055 | 40032818 | New | MVS | GO2223013999PH | 16/02/2023 | 1124.68 | 43.99 | 1168.66 | Alipore Division | South 24 Pgs Mechanical Division | 232.49 | 0 | 30.64 | 0 | 263.13 | 190.52 | 0 | 30.64 | 0 | 221.16 | 18.92 | 29
335 | SOUTH 24 PARAGANAS | SM/13974 | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | TSM/016105 | 40035320 | New | SVS | GO2223010327PH | 01/12/2022 | 722.86 | 75.49 | 798.36 | Alipore Division | South 24 Pgs Mechanical Division | 387.22 | 6.73 | 7.94 | 0 | 401.89 | 258.37 | 6.73 | 7.94 | 0 | 273.04 | 34.2 | 25
336 | SOUTH 24 PARAGANAS | SM/18573 | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | TSM/018363 | 40046804 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 925.64 | 140.36 | 1066 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 226.83 | 3.19 | 26.22 | 0 | 256.25 | 226.83 | 3.19 | 26.22 | 0 | 256.25 | 24.04 | 4
337 | SOUTH 24 PARAGANAS | SM/14156 | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | TSM/015403 | 40034582 | New | MVS | GO2223011626PH | 05/01/2023 | 1170.12 | 107.48 | 1277.6 | Alipore Division | South 24 Pgs Mechanical Division | 371.44 | 0 | 16.45 | 0 | 387.89 | 310.68 | 0 | 0 | 0 | 310.68 | 24.32 | 10
338 | SOUTH 24 PARAGANAS | SM/18680 | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | TSM/016562 | 40033700 | Augmentation | MVS | 2244/PHE-28011/163/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 962.22 | 55.66 | 1017.88 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 95.63 | 0 | 18.62 | 0 | 114.26 | 95.63 | 0 | 18.62 | 0 | 114.26 | 11.22 | 1
339 | SOUTH 24 PARAGANAS | SM/12208 | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014830 | 40033989 | Augmentation | MVS | GO2223007092PH | 06/09/2022 | 423.36 | 62.92 | 486.27 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 62.98 | 0 | 29.08 | 0 | 92.06 | 62.98 | 0 | 7.77 | 0 | 70.75 | 14.55 | 2
340 | SOUTH 24 PARAGANAS | SM/12209 | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014842 | 40026049 | Augmentation | SVS | GO2223007088PH | 06/09/2022 | 645.05 | 70.21 | 715.25 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 37.36 | 4.42 | 22.22 | 0 | 64.01 | 37.36 | 0 | 22.22 | 0 | 59.58 | 8.33 | 7
341 | SOUTH 24 PARAGANAS | SM/14547 | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | TSM/017322 | 40033975 | Augmentation | MVS | GO2223012589PH | 30/01/2023 | 1594.15 | 83.49 | 1677.64 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 3.14 | 0 | 69.01 | 0 | 72.14 | 3.14 | 0 | 69.01 | 0 | 72.14 | 4.3 | 2
342 | SOUTH 24 PARAGANAS | SM/15866 | Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sou | TSM/017761 | 40052586 | Augmentation | MVS | GO2223014346PH | 20/02/2023 | 907.68 | 81 | 988.68 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 17.95 | 3.92 | 19.75 | 0 | 41.63 | 17.95 | 3.92 | 12.8 | 0 | 34.68 | 3.51 | 5
343 | SOUTH 24 PARAGANAS | SM/12733 | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011946 | 40028498 | New | SVS | GO2223007931PH | 20/09/2022 | 642.04 | 71.66 | 713.69 | Alipore Division | South 24 Pgs Mechanical Division | 324.44 | 2.51 | 35.34 | 0 | 362.29 | 314.57 | 2.51 | 35.34 | 0 | 352.42 | 49.38 | 45
344 | SOUTH 24 PARAGANAS | SM/11848 | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | TSM/011952 | 40019085 | New | MVS | GO2223006310PH | 16/08/2022 | 814.61 | 71.66 | 886.26 | Alipore Division | South 24 Pgs Mechanical Division | 280.22 | 0 | 10.23 | 0 | 290.45 | 280.22 | 0 | 10.23 | 0 | 290.45 | 32.77 | 28
345 | SOUTH 24 PARAGANAS | SM/14858 | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | TSM/018364 | 40046827 | Augmentation | MVS | GO2223012988PH | 03/02/2023 | 794.1 | 108.9 | 903 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 159.19 | 0 | 18.17 | 0 | 177.35 | 159.19 | 0 | 18.17 | 0 | 177.35 | 19.64 | 1
346 | SOUTH 24 PARAGANAS | SM/12211 | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014835 | 40026024 | Augmentation | MVS | GO2223007105PH | 06/09/2022 | 921.39 | 71.32 | 992.71 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 64.28 | 15.18 | 33.44 | 0 | 112.9 | 63.88 | 4.52 | 33.44 | 0 | 101.84 | 10.26 | 10
347 | SOUTH 24 PARAGANAS | SM/12261 | Ground water based BARUIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012660 | 40025903 | Augmentation | MVS | GO2223007154PH | 07/09/2022 | 652.65 | 63.35 | 715.99 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 91.07 | 15.97 | 53.66 | 0 | 160.7 | 91.07 | 6.33 | 53.66 | 0 | 151.07 | 21.1 | 17
348 | SOUTH 24 PARAGANAS | SM/12212 | Ground water based BARULI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014838 | 40025974 | Augmentation | MVS | GO2223007128PH | 07/09/2022 | 804.2 | 71.63 | 875.83 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 224.45 | 37.72 | 13.27 | 0 | 275.44 | 224.05 | 37.72 | 13.27 | 0 | 275.04 | 31.4 | 15
349 | SOUTH 24 PARAGANAS | SM/13840 | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | TSM/015936 | 40034597 | New | SVS | GO2223010124PH | 25/11/2022 | 520.55 | 71.66 | 592.21 | Alipore Division | South 24 Pgs Mechanical Division | 98.72 | 0 | 46.68 | 0 | 145.4 | 4.32 | 0 | 39.82 | 0 | 44.14 | 7.45 | 4
350 | SOUTH 24 PARAGANAS | SM/13917 | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | TSM/017471 | 40034718 | Augmentation | MVS | GO2223010234PH | 29/11/2022 | 261.19 | 25.71 | 286.9 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 66.83 | 0 | 3.82 | 0 | 70.65 | 66.83 | 0 | 3.82 | 0 | 70.65 | 24.62 | 18
351 | SOUTH 24 PARAGANAS | SM/15864 | Ground water based BELADANGA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | TSM/020328 | 40053454 | Augmentation | SVS | GO2223014347PH | 20/02/2023 | 521.07 | 56.45 | 577.52 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.47 | 6.54 | 23.05 | 0 | 32.05 | 2.47 | 6.54 | 23.05 | 0 | 32.05 | 5.55 | 4
352 | SOUTH 24 PARAGANAS | SM/11771 | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | TSM/011099 | 40026585 | New | SVS | GO2223005918PH | 02/08/2022 | 801.64 | 71.66 | 873.29 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 248.22 | 8.73 | 9.88 | 0 | 266.83 | 248.22 | 8.73 | 9.88 | 0 | 266.83 | 30.55 | 20
353 | SOUTH 24 PARAGANAS | SM/16294 | GROUND WATER BASED BHUBANNAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015386 | 40049227 | New | SVS | GO2223014839PH | 24/02/2023 | 768.73 | 71.66 | 840.39 | Alipore Division | South 24 Pgs Mechanical Division | 6.05 | 0 | 13.1 | 0 | 19.15 | 6.05 | 0 | 13.1 | 0 | 19.15 | 2.28 | 2
354 | SOUTH 24 PARAGANAS | SM/13975 | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | TSM/016104 | 40035288 | New | MVS | GO2223010329PH | 01/12/2022 | 679.11 | 107.48 | 786.59 | Alipore Division | South 24 Pgs Mechanical Division | 236.13 | 12.07 | 100.82 | 0 | 349.02 | 189.48 | 12.07 | 100.82 | 0 | 302.36 | 38.44 | 27
355 | SOUTH 24 PARAGANAS | SM/18571 | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | TSM/019595 | 40047333 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1095.69 | 66.27 | 1161.95 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 151.73 | 4.76 | 0 | 0 | 156.48 | 151.73 | 4.76 | 0 | 0 | 156.48 | 13.47 | 21
356 | SOUTH 24 PARAGANAS | SM/13839 | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | TSM/015937 | 40034592 | New | SVS | GO2223010115PH | 25/11/2022 | 606.18 | 71.66 | 677.84 | Alipore Division | South 24 Pgs Mechanical Division | 155.72 | 0 | 53.94 | 0 | 209.66 | 155.72 | 0 | 46.24 | 0 | 201.96 | 29.79 | 10
357 | SOUTH 24 PARAGANAS | SM/12213 | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | TSM/014396 | 40025934 | Augmentation | MVS | GO2223007093PH | 06/09/2022 | 291.11 | 21.89 | 312.99 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 153.05 | 16.02 | 20.38 | 0 | 189.45 | 153.05 | 16.02 | 20.38 | 0 | 189.45 | 60.53 | 62
358 | SOUTH 24 PARAGANAS | SM/12214 | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | TSM/013487 | 40065924 | Augmentation | SVS | GO2223007100PH | 06/09/2022 | 577.08 | 71.66 | 648.73 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 217.71 | 32.14 | 0 | 0 | 249.85 | 198.19 | 32.14 | 0 | 0 | 230.34 | 35.51 | 33
359 | SOUTH 24 PARAGANAS | SM/13309 | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | TSM/015376 | 40034924 | Augmentation | SVS | GO2223008853PH | 17/10/2022 | 743.3 | 47.38 | 790.68 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 179.01 | 11.18 | 34.34 | 0 | 224.53 | 179.01 | 11.18 | 31.69 | 0 | 221.88 | 28.06 | 15
360 | SOUTH 24 PARAGANAS | SM/13310 | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | TSM/015225 | 40035149 | Augmentation | SVS | GO2223008847PH | 17/10/2022 | 581.39 | 27.81 | 609.2 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 174.69 | 4.53 | 7.28 | 0 | 186.5 | 174.69 | 4.53 | 7.28 | 0 | 186.5 | 30.61 | 12
361 | SOUTH 24 PARAGANAS | SM/18718 | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | TSM/015410 | 40049223 | New | SVS | 2342/PHE-28011/233/2023-ESTT CELL-Dept. of PHE | 10/08/2023 | 1137.08 | 143.31 | 1280.39 | Alipore Division | South 24 Pgs Mechanical Division | 346 | 0 | 0 | 0 | 346 | 151.46 | 0 | 0 | 0 | 151.46 | 11.83 | 2
362 | SOUTH 24 PARAGANAS | SM/12883 | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | TSM/014901 | 40035857 | Augmentation | MVS | GO2223008159PH | 23/09/2022 | 666.19 | 47.38 | 713.57 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.62 | 0 | 0 | 0 | 2.62 | 2.62 | 0 | 0 | 0 | 2.62 | 0.37 | 2
363 | SOUTH 24 PARAGANAS | SM/14657 | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | TSM/017334 | 40034002 | Augmentation | MVS | GO2223012716PH | 31/01/2023 | 784.09 | 55.66 | 839.75 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.7 | 0 | 13.9 | 0 | 16.6 | 2.7 | 0 | 13.9 | 0 | 16.6 | 1.98 | 2
364 | SOUTH 24 PARAGANAS | SM/11782 | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | TSM/011738 | 40025915 | Augmentation | MVS | GO2223005923PH | 02/08/2022 | 438.42 | 71.66 | 510.08 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 88.76 | 16.42 | 31.64 | 0 | 136.82 | 88.76 | 16.42 | 31.64 | 0 | 136.82 | 26.82 | 60
365 | SOUTH 24 PARAGANAS | SM/15867 | Ground water based CHAK ROSANMAMUD piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | TSM/018431 | 40061805 | Augmentation | MVS | GO2223014350PH | 20/02/2023 | 418.63 | 63.46 | 482.09 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.43 | 0 | 27.32 | 0 | 29.75 | 2.43 | 0 | 27.32 | 0 | 29.75 | 6.17 | 2
366 | SOUTH 24 PARAGANAS | SM/13011 | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011097 | 40033934 | New | MVS | GO2223008394PH | 29/09/2022 | 870.04 | 71.66 | 941.69 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 86.11 | 19.01 | 9.43 | 0 | 114.55 | 86.11 | 19.01 | 9.43 | 0 | 114.55 | 12.16 | 11
367 | SOUTH 24 PARAGANAS | SM/14877 | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | TSM/017980 | 40053518 | Augmentation | MVS | GO2223012958PH | 03/02/2023 | 123.82 | 21.89 | 145.71 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 69.2 | 11.94 | 0 | 0 | 81.14 | 69.2 | 11.94 | 0 | 0 | 81.14 | 55.68 | 38
368 | SOUTH 24 PARAGANAS | SM/12046 | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/012519 | 40026586 | Augmentation | SVS | GO2223006938PH | 01/09/2022 | 213.13 | 31.67 | 244.81 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 75.87 | 12.34 | 5.81 | 0 | 94.01 | 75.87 | 12.34 | 0 | 0 | 88.2 | 36.03 | 20
369 | SOUTH 24 PARAGANAS | SM/11787 | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/011441 | 40034360 | Augmentation | MVS | GO2223005924PH | 02/08/2022 | 792.79 | 71.66 | 864.45 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 383.28 | 4.96 | 112.41 | 0 | 500.65 | 383.28 | 4.96 | 112.41 | 0 | 500.65 | 57.92 | 63
370 | SOUTH 24 PARAGANAS | SM/12217 | Ground water based CHHAYANI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas Distric for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parga | TSM/014887 | 40035295 | Augmentation | SVS | GO2223007098PH | 06/09/2022 | 202.14 | 27.81 | 229.95 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 76.75 | 0 | 5.59 | 0 | 82.34 | 76.75 | 0 | 5.59 | 0 | 82.34 | 35.81 | 2
371 | SOUTH 24 PARAGANAS | SM/13835 | GROUND WATER BASED CHHOTO BANASHYAM NAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/016114 | 40037413 | New | SVS | GO2223010121PH | 25/11/2022 | 792.86 | 71.66 | 864.51 | Alipore Division | South 24 Pgs Mechanical Division | 87.16 | 0 | 9.36 | 0 | 96.51 | 86.67 | 0 | 9.36 | 0 | 96.03 | 11.11 | 5
372 | SOUTH 24 PARAGANAS | SM/15527 | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | TSM/016112 | 40035303 | New | SVS | GO2223014000PH | 16/02/2023 | 872.36 | 143.31 | 1015.67 | Alipore Division | South 24 Pgs Mechanical Division | 274.32 | 0 | 45.84 | 0 | 320.16 | 253.95 | 0 | 45.84 | 0 | 299.79 | 29.52 | 2
373 | SOUTH 24 PARAGANAS | SM/12053 | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | TSM/012523 | 40026809 | Augmentation | SVS | GO2223006937PH | 01/09/2022 | 351.33 | 31.67 | 383 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 133.76 | 16.73 | 5.61 | 0 | 156.1 | 133.76 | 16.73 | 5.61 | 0 | 156.1 | 40.76 | 38
374 | SOUTH 24 PARAGANAS | SM/14870 | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/017968 | 40047355 | Augmentation | MVS | GO2223013029PH | 03/02/2023 | 763.21 | 81 | 844.2 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.58 | 0 | 22.46 | 0 | 25.03 | 2.58 | 0 | 22.46 | 0 | 25.03 | 2.97 | 0
375 | SOUTH 24 PARAGANAS | SM/13797 | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011941 | 40034030 | New | SVS | GO2223009951PH | 22/11/2022 | 464.99 | 71.66 | 536.65 | Alipore Division | South 24 Pgs Mechanical Division | 154.75 | 0 | 9.3 | 0 | 164.06 | 67.71 | 0 | 0 | 0 | 67.71 | 12.62 | 9
376 | SOUTH 24 PARAGANAS | SM/12057 | Ground water based DAKSHIN SASAN (P) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012622 | 40026810 | Augmentation | SVS | GO2223006939PH | 01/09/2022 | 672.84 | 63.35 | 736.18 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 217.27 | 33.01 | 21.65 | 0 | 271.93 | 217.27 | 33.01 | 21.65 | 0 | 271.93 | 36.94 | 35
377 | SOUTH 24 PARAGANAS | SM/12230 | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014845 | 40026062 | Augmentation | SVS | GO2223007112PH | 06/09/2022 | 850.05 | 72.91 | 922.96 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 150.63 | 12.93 | 16.93 | 0 | 180.49 | 150.63 | 12.93 | 16.93 | 0 | 180.49 | 19.56 | 10
378 | SOUTH 24 PARAGANAS | SM/16027 | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | TSM/016701 | 40036936 | New | SVS | GO2223014532PH | 22/02/2023 | 730.52 | 71.66 | 802.18 | Alipore Division | South 24 Pgs Mechanical Division | 366.11 | 4.87 | 15.09 | 0 | 386.07 | 329.39 | 4.87 | 0 | 0 | 334.26 | 41.67 | 4
379 | SOUTH 24 PARAGANAS | SM/11499 | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011007 | 40034079 | New | MVS | GO2223005184PH | 19/07/2022 | 566.81 | 71.66 | 638.47 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 230.48 | 15.47 | 44.43 | 0 | 290.38 | 230.48 | 15.47 | 44.43 | 0 | 290.38 | 45.48 | 19
380 | SOUTH 24 PARAGANAS | SM/12054 | Ground water based DHANBERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/012518 | 40026811 | Augmentation | SVS | GO2223006929PH | 01/09/2022 | 281.2 | 31.67 | 312.87 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 40.94 | 12.41 | 1.29 | 0 | 54.64 | 40.94 | 11.87 | 1.29 | 0 | 54.1 | 17.29 | 16
381 | SOUTH 24 PARAGANAS | SM/13918 | Ground water based DHANPOTA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | TSM/016727 | 40034611 | Augmentation | MVS | GO2223010214PH | 29/11/2022 | 920.59 | 55.66 | 976.25 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.62 | 0 | 0 | 0 | 2.62 | 2.62 | 0 | 0 | 0 | 2.62 | 0.27 | 5
382 | SOUTH 24 PARAGANAS | SM/18568 | Ground water based DIHI KASLAS piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | TSM/018231 | 40047374 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1113.15 | 71.07 | 1184.22 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 15.08 | 0 | 0 | 0 | 15.08 | 15.08 | 0 | 0 | 0 | 15.08 | 1.27 | 9
383 | SOUTH 24 PARAGANAS | SM/14871 | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | TSM/018429 | 40047281 | Augmentation | MVS | GO2223012970PH | 03/02/2023 | 862.11 | 83.86 | 945.98 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 144.25 | 0 | 79.54 | 0 | 223.79 | 144.25 | 0 | 79.54 | 0 | 223.79 | 23.66 | 2
384 | SOUTH 24 PARAGANAS | SM/13842 | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | TSM/015904 | 40034588 | New | SVS | GO2223010111PH | 25/11/2022 | 357.29 | 71.66 | 428.95 | Alipore Division | South 24 Pgs Mechanical Division | 88.24 | 0 | 6.11 | 0 | 94.35 | 18.99 | 0 | 6.11 | 0 | 25.1 | 5.85 | 25
385 | SOUTH 24 PARAGANAS | SM/13973 | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | TSM/016109 | 40035297 | New | SVS | GO2223010325PH | 01/12/2022 | 451.82 | 71.66 | 523.48 | Alipore Division | South 24 Pgs Mechanical Division | 191.98 | 8.32 | 8.11 | 0 | 208.42 | 144.63 | 8.32 | 8.11 | 0 | 161.06 | 30.77 | 24
386 | SOUTH 24 PARAGANAS | SM/12061 | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012659 | 40025949 | Augmentation | MVS | GO2223006940PH | 01/09/2022 | 569.6 | 95.02 | 664.62 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 217.14 | 14.47 | 53.53 | 0 | 285.14 | 217.14 | 14.47 | 39.79 | 0 | 271.41 | 40.84 | 21
387 | SOUTH 24 PARAGANAS | SM/15177 | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | TSM/018365 | 40046950 | Augmentation | MVS | GO2223013419PH | 07/02/2023 | 407.29 | 68.97 | 476.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 163.59 | 4.82 | 25.05 | 0 | 193.46 | 133.72 | 4.82 | 8.78 | 0 | 147.32 | 30.93 | 27
388 | SOUTH 24 PARAGANAS | SM/13843 | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | TSM/015899 | 40034589 | New | SVS | GO2223010120PH | 25/11/2022 | 632.19 | 75.49 | 707.69 | Alipore Division | South 24 Pgs Mechanical Division | 79.74 | 0 | 6.89 | 0 | 86.62 | 79.25 | 0 | 6.89 | 0 | 86.14 | 12.17 | 5
389 | SOUTH 24 PARAGANAS | SM/11732 | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/011791 | 40026053 | Augmentation | MVS | GO2223006011PH | 03/08/2022 | 411.74 | 71.66 | 483.4 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 100.3 | 21.71 | 23.85 | 0 | 145.86 | 100.3 | 21.71 | 23.85 | 0 | 145.86 | 30.17 | 24
390 | SOUTH 24 PARAGANAS | SM/13443 | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/015205 | 40033745 | Augmentation | MVS | GO2223009215PH | 02/11/2022 | 564.17 | 55.62 | 619.79 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 128.54 | 0 | 33.45 | 0 | 161.99 | 128.54 | 0 | 12.14 | 0 | 140.68 | 22.7 | 9
391 | SOUTH 24 PARAGANAS | SM/15774 | Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | TSM/018461 | 40053441 | Augmentation | MVS | GO2223014334PH | 20/02/2023 | 448.27 | 52.16 | 500.43 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 88.54 | 0 | 5.41 | 0 | 93.95 | 35.27 | 0 | 5.41 | 0 | 40.67 | 8.13 | 13
392 | SOUTH 24 PARAGANAS | SM/12771 | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | TSM/014757 | 40033940 | Augmentation | MVS | GO2223008042PH | 21/09/2022 | 677.4 | 47.38 | 724.78 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 182.35 | 0 | 4.68 | 0 | 187.02 | 182.35 | 0 | 0 | 0 | 182.35 | 25.16 | 14
393 | SOUTH 24 PARAGANAS | SM/13834 | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | TSM/015945 | 40034595 | New | SVS | GO2223010117PH | 25/11/2022 | 377.97 | 71.66 | 449.63 | Alipore Division | South 24 Pgs Mechanical Division | 74.51 | 0 | 10.96 | 0 | 85.47 | 3.28 | 0 | 10.96 | 0 | 14.24 | 3.17 | 1
394 | SOUTH 24 PARAGANAS | SM/15775 | Ground water based GOPALPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of Sou | TSM/019594 | 40054107 | Augmentation | MVS | GO2223014338PH | 20/02/2023 | 589.1 | 66.27 | 655.37 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 153.86 | 0 | 23.37 | 0 | 177.23 | 153.86 | 0 | 23.37 | 0 | 177.23 | 27.04 | 13
395 | SOUTH 24 PARAGANAS | SM/14859 | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/018361 | 40046969 | Augmentation | MVS | GO2223012989PH | 03/02/2023 | 783.23 | 119.79 | 903.02 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 173.48 | 0 | 12.87 | 0 | 186.35 | 173.48 | 0 | 12.87 | 0 | 186.35 | 20.64 | 10
396 | SOUTH 24 PARAGANAS | SM/14157 | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015400 | 40034027 | New | SVS | GO2223011624PH | 05/01/2023 | 1089.39 | 107.48 | 1196.88 | Alipore Division | South 24 Pgs Mechanical Division | 102.1 | 0 | 18.32 | 0 | 120.42 | 101.61 | 0 | 18.32 | 0 | 119.93 | 10.02 | 5
397 | SOUTH 24 PARAGANAS | SM/11849 | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011951 | 40019081 | New | SVS | GO2223006314PH | 16/08/2022 | 582.13 | 71.66 | 653.78 | Alipore Division | South 24 Pgs Mechanical Division | 121.64 | 0 | 24.83 | 0 | 146.46 | 41.62 | 0 | 24.83 | 0 | 66.45 | 10.16 | 9
398 | SOUTH 24 PARAGANAS | SM/18869 | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | TSM/020495 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 585.29 | 112.9 | 698.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 2.61 | 0 | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 2.61 | 0.37 | 5
399 | SOUTH 24 PARAGANAS | SM/14860 | Ground water based HARIHARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/017835 | 40046990 | Augmentation | MVS | GO2223012957PH | 03/02/2023 | 816.96 | 56.45 | 873.42 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 72.01 | 6.06 | 46.56 | 0 | 124.63 | 72.01 | 6.06 | 46.56 | 0 | 124.63 | 14.27 | 10
400 | SOUTH 24 PARAGANAS | SM/12635 | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011095 | 40025976 | New | MVS | GO2223007811PH | 19/09/2022 | 694.4 | 71.66 | 766.05 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 122.25 | 5.39 | 8.83 | 0 | 136.47 | 122.25 | 5.39 | 8.83 | 0 | 136.47 | 17.81 | 20
401 | SOUTH 24 PARAGANAS | SM/14643 | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/016566 | 40034403 | Augmentation | SVS | GO2223012740PH | 31/01/2023 | 900.25 | 84.68 | 984.92 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 164.62 | 0 | 88.28 | 0 | 252.9 | 164.62 | 0 | 88.28 | 0 | 252.9 | 25.68 | 15
402 | SOUTH 24 PARAGANAS | SM/12772 | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | TSM/014760 | 40033978 | Augmentation | MVS | GO2223008044PH | 21/09/2022 | 608.56 | 47.38 | 655.94 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.64 | 0 | 23.62 | 0 | 26.27 | 2.64 | 0 | 23.62 | 0 | 26.27 | 4 | 2
403 | SOUTH 24 PARAGANAS | SM/12264 | Ground water based INDRAPALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012606 | 40026812 | Augmentation | SVS | GO2223007108PH | 06/09/2022 | 469.43 | 63.35 | 532.77 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 147.34 | 25.07 | 39.71 | 0 | 212.11 | 147.34 | 25.07 | 39.71 | 0 | 212.11 | 39.81 | 21
404 | SOUTH 24 PARAGANAS | SM/13075 | Ground water based JAGADISHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014216 | 40065251 | Augmentation | MVS | GO2223008456PH | 29/09/2022 | 231.61 | 21.89 | 253.5 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 132.95 | 18.8 | 24.24 | 0 | 175.99 | 132.95 | 18.8 | 24.24 | 0 | 175.99 | 69.43 | 35
405 | SOUTH 24 PARAGANAS | SM/11501 | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011012 | 40025987 | New | MVS | GO2223005181PH | 19/07/2022 | 696.42 | 71.66 | 768.07 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 81.08 | 27.18 | 8.73 | 0 | 116.98 | 81.08 | 6.04 | 8.73 | 0 | 95.84 | 12.48 | 15
406 | SOUTH 24 PARAGANAS | SM/13836 | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | TSM/015943 | 40034594 | New | SVS | GO2223010127PH | 25/11/2022 | 383.82 | 71.66 | 455.48 | Alipore Division | South 24 Pgs Mechanical Division | 77.89 | 7.55 | 44.87 | 0 | 130.3 | 3.32 | 7.55 | 41.43 | 0 | 52.29 | 11.48 | 5
407 | SOUTH 24 PARAGANAS | SM/12636 | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011011 | 40026144 | New | MVS | GO2223007813PH | 19/09/2022 | 682.04 | 71.66 | 753.69 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 126.07 | 0 | 10.3 | 0 | 136.37 | 126.07 | 0 | 10.3 | 0 | 136.37 | 18.09 | 18
408 | SOUTH 24 PARAGANAS | SM/11772 | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | TSM/011093 | 40026206 | New | MVS | GO2223005926PH | 02/08/2022 | 843.2 | 71.66 | 914.86 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 187.28 | 9.42 | 0 | 0 | 196.7 | 187.28 | 9.42 | 0 | 0 | 196.7 | 21.5 | 20
409 | SOUTH 24 PARAGANAS | SM/11730 | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/011788 | 40026031 | Augmentation | MVS | GO2223006010PH | 03/08/2022 | 414.82 | 71.66 | 486.48 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 60.88 | 0 | 26.38 | 0 | 87.26 | 60.88 | 0 | 26.38 | 0 | 87.26 | 17.94 | 13
410 | SOUTH 24 PARAGANAS | SM/18682 | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | TSM/015387 | 40066197 | New | SVS | 2245/PHE-28011/229/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1569.64 | 107.48 | 1677.13 | Alipore Division | South 24 Pgs Mechanical Division | 47.31 | 6.83 | 30.76 | 0 | 84.89 | 46.83 | 6.83 | 30.76 | 0 | 84.41 | 5.03 | 29
411 | SOUTH 24 PARAGANAS | SM/14872 | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/018436 | 40047052 | Augmentation | MVS | GO2223013026PH | 03/02/2023 | 841.53 | 84.68 | 926.21 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 163.88 | 0 | 17.89 | 0 | 181.77 | 163.88 | 0 | 17.89 | 0 | 181.77 | 19.62 | 9
412 | SOUTH 24 PARAGANAS | SM/15776 | Ground water based KALYANPUR (KHODAR BAZAR) PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 2 | TSM/018149 | 40053003 | Augmentation | SVS | GO2223014325PH | 20/02/2023 | 471.27 | 56.45 | 527.72 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.47 | 13.25 | 23.31 | 0 | 39.03 | 2.47 | 13.25 | 23.31 | 0 | 39.03 | 7.4 | 4
413 | SOUTH 24 PARAGANAS | SM/13837 | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | TSM/015942 | 40034596 | New | SVS | GO2223010123PH | 25/11/2022 | 667.43 | 71.66 | 739.08 | Alipore Division | South 24 Pgs Mechanical Division | 143.3 | 0 | 30.47 | 0 | 173.77 | 65.78 | 0 | 30.47 | 0 | 96.25 | 13.02 | 1
414 | SOUTH 24 PARAGANAS | SM/13775 | Ground water based KAMARIA ZONE - I piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/016158 | 40033970 | Augmentation | SVS | GO2223009904PH | 18/11/2022 | 617.53 | 71.66 | 689.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 33.45 | 16.14 | 79.31 | 0 | 128.89 | 33.45 | 16.14 | 79.31 | 0 | 128.89 | 18.7 | 15
415 | SOUTH 24 PARAGANAS | SM/13776 | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/016159 | 40034643 | Augmentation | SVS | GO2223009906PH | 18/11/2022 | 567.54 | 71.66 | 639.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 98.99 | 24.45 | 63.21 | 0 | 186.65 | 98.99 | 24.45 | 63.21 | 0 | 186.65 | 29.2 | 11
416 | SOUTH 24 PARAGANAS | SM/13838 | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/015940 | 40034593 | New | SVS | GO2223010118PH | 25/11/2022 | 544.09 | 71.66 | 615.74 | Alipore Division | South 24 Pgs Mechanical Division | 121.14 | 0 | 59.64 | 0 | 180.78 | 121.14 | 0 | 52.25 | 0 | 173.39 | 28.16 | 2
417 | SOUTH 24 PARAGANAS | SM/12051 | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/012516 | 40026220 | Augmentation | MVS | GO2223006935PH | 01/09/2022 | 418.2 | 31.67 | 449.87 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 218.21 | 16.27 | 5.8 | 0 | 240.28 | 218.21 | 16.27 | 5.8 | 0 | 240.28 | 53.41 | 56
418 | SOUTH 24 PARAGANAS | SM/11733 | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | TSM/011792 | 40026023 | Augmentation | SVS | GO2223005925PH | 02/08/2022 | 422.39 | 71.66 | 494.04 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 138.94 | 15.62 | 6.07 | 0 | 160.62 | 138.94 | 15.62 | 6.07 | 0 | 160.62 | 32.51 | 27
419 | SOUTH 24 PARAGANAS | SM/12059 | Ground water based KESHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012609 | 40026814 | Augmentation | SVS | GO2223006936PH | 01/09/2022 | 448.12 | 63.35 | 511.47 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 174.31 | 31.92 | 7.28 | 0 | 213.5 | 174.31 | 31.92 | 0 | 0 | 206.23 | 40.32 | 38
420 | SOUTH 24 PARAGANAS | SM/11789 | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | TSM/011787 | 40026003 | Augmentation | MVS | GO2223006007PH | 03/08/2022 | 467.76 | 71.66 | 539.41 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 111.26 | 15.41 | 30.73 | 0 | 157.4 | 111.26 | 15.41 | 30.73 | 0 | 157.4 | 29.18 | 21
421 | SOUTH 24 PARAGANAS | SM/18673 | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | TSM/016106 | 40049221 | New | SVS | 2241/PHE-28011/200/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1049.32 | 143.31 | 1192.64 | Alipore Division | South 24 Pgs Mechanical Division | 218.32 | 0 | 0 | 0 | 218.32 | 93.52 | 0 | 0 | 0 | 93.52 | 7.84 | 2
422 | SOUTH 24 PARAGANAS | SM/12266 | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012662 | 40026250 | Augmentation | MVS | GO2223007099PH | 06/09/2022 | 644.43 | 63.35 | 707.77 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 224.79 | 17.94 | 59.58 | 0 | 302.31 | 224.79 | 17.94 | 49.9 | 0 | 292.64 | 41.35 | 33
423 | SOUTH 24 PARAGANAS | SM/11500 | Ground water based KURULI piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011008 | 40026258 | New | MVS | GO2223005179PH | 19/07/2022 | 669.61 | 71.66 | 741.27 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 252.71 | 41.19 | 9.32 | 0 | 303.23 | 252.71 | 41.19 | 9.32 | 0 | 303.23 | 40.91 | 33
424 | SOUTH 24 PARAGANAS | SM/14873 | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/018292 | 40046978 | Augmentation | MVS | GO2223012973PH | 03/02/2023 | 860.13 | 84.68 | 944.81 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.66 | 0 | 72.06 | 0 | 74.72 | 2.66 | 0 | 69.92 | 0 | 72.58 | 7.68 | 2
425 | SOUTH 24 PARAGANAS | SM/11877 | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011619 | 40019090 | New | MVS | GO2223006372PH | 17/08/2022 | 731.98 | 71.66 | 803.64 | Alipore Division | South 24 Pgs Mechanical Division | 87.68 | 0 | 47.07 | 0 | 134.75 | 87.34 | 0 | 47.07 | 0 | 134.41 | 16.73 | 5
426 | SOUTH 24 PARAGANAS | SM/18126 | GROUND WATER BASED MADHUSUDANPUR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011944 | 40066196 | New | SVS | GO2223017940PH | 29/03/2023 | 541.5 | 35.83 | 577.33 | Alipore Division | South 24 Pgs Mechanical Division | 206.43 | 0 | 11.45 | 0 | 217.88 | 205.95 | 0 | 0 | 0 | 205.95 | 35.67 | 2
427 | SOUTH 24 PARAGANAS | SM/12237 | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012625 | 40026813 | Augmentation | SVS | GO2223007268PH | 07/09/2022 | 749.85 | 95.02 | 844.87 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 194.53 | 32.14 | 105.09 | 0 | 331.76 | 194.53 | 32.14 | 105.09 | 0 | 331.76 | 39.27 | 12
428 | SOUTH 24 PARAGANAS | SM/15180 | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | TSM/018360 | 40047070 | Augmentation | MVS | GO2223013420PH | 07/02/2023 | 190.91 | 70.18 | 261.09 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 32.43 | 0 | 5.18 | 0 | 37.61 | 32.43 | 0 | 5.18 | 0 | 37.61 | 14.4 | 7
429 | SOUTH 24 PARAGANAS | SM/13444 | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | TSM/012612 | 40033731 | Augmentation | SVS | GO2223009214PH | 02/11/2022 | 355.9 | 83.43 | 439.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 17.8 | 0.08 | 41.06 | 0 | 58.94 | 17.8 | 0.08 | 41.06 | 0 | 58.94 | 13.42 | 2
430 | SOUTH 24 PARAGANAS | SM/15777 | Ground water based MALLIKPUR PART-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | TSM/017349 | 40052544 | Augmentation | SVS | GO2223014333PH | 20/02/2023 | 812.29 | 132.52 | 944.81 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.56 | 0 | 70.62 | 0 | 73.18 | 2.56 | 0 | 70.62 | 0 | 73.18 | 7.75 | 4
431 | SOUTH 24 PARAGANAS | SM/16291 | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015397 | 40049220 | New | SVS | GO2223014836PH | 24/02/2023 | 888 | 71.66 | 959.66 | Alipore Division | South 24 Pgs Mechanical Division | 164.63 | 0 | 14.57 | 0 | 179.2 | 164.15 | 0 | 14.57 | 0 | 178.71 | 18.62 | 2
432 | SOUTH 24 PARAGANAS | SM/11779 | Ground water based MASTIKARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/011743 | 40034240 | Augmentation | MVS | GO2223005920PH | 02/08/2022 | 770.2 | 71.66 | 841.85 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.73 | 0 | 37.23 | 0 | 39.96 | 2.73 | 0 | 12.66 | 0 | 15.4 | 1.83 | 10
433 | SOUTH 24 PARAGANAS | SM/13964 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Anduldaha Gopalpur village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sys | TSM/014812 | 40035203 | New | SVS | GO2223010351PH | 01/12/2022 | 35.77 | 8.75 | 44.52 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | SOUTH 24 PARAGANAS | SM/12575 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of BAINTALA village of Tambuldaha-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution syste | TSM/013450 | 40034031 | New | SVS | GO2223007748PH | 15/09/2022 | 35.65 | 8.75 | 44.39 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 4.7 | 0 | 0 | 4.7 | 0 | 4.7 | 0 | 0 | 4.7 | 10.59 | 5
435 | SOUTH 24 PARAGANAS | SM/12759 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Bhairabitala village of Keoratala Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, | TSM/014816 | 40028665 | New | SVS | GO2223007941PH | 20/09/2022 | 35.82 | 8.75 | 44.57 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | SOUTH 24 PARAGANAS | SM/12756 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Bijoyrampur village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, B | TSM/014808 | 40028647 | New | SVS | GO2223007940PH | 20/09/2022 | 35.39 | 8.75 | 44.14 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | SOUTH 24 PARAGANAS | SM/13961 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Chak Ruplaskar village of Ramkishore Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system | TSM/014819 | 40035201 | New | SVS | GO2223010354PH | 01/12/2022 | 34.62 | 8.75 | 43.37 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | SOUTH 24 PARAGANAS | SM/12573 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of HAZRABAND village of Netra Gram Panchayet in Diamond Harbour-I Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution syst | TSM/013461 | 0 | New | SVS | GO2223007734PH | 15/09/2022 | 36.5 | 8.75 | 45.25 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | SOUTH 24 PARAGANAS | SM/12757 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kabasenre village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou | TSM/014809 | 40028651 | New | SVS | GO2223007944PH | 20/09/2022 | 34.53 | 8.75 | 43.28 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | SOUTH 24 PARAGANAS | SM/12758 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kamarchak village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou | TSM/014810 | 40028662 | New | SVS | GO2223007942PH | 22/09/2022 | 35.13 | 8.75 | 43.88 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | SOUTH 24 PARAGANAS | SM/12576 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of KULER KHOJ village of Tambuldaha-II Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | TSM/013459 | 40034580 | New | SVS | GO2223007735PH | 15/09/2022 | 36.46 | 8.75 | 45.21 | Alipore Division | South 24 Pgs Mechanical Division | 17.28 | 0 | 0 | 0 | 17.28 | 17.28 | 0 | 0 | 0 | 17.28 | 38.22 | 2
442 | SOUTH 24 PARAGANAS | SM/13073 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Mithakundu village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bo | TSM/014811 | 40028663 | New | SVS | GO2223008451PH | 29/09/2022 | 35.05 | 8.75 | 43.8 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | SOUTH 24 PARAGANAS | SM/13963 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Padmapukhuria village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, | TSM/014814 | 40035198 | New | SVS | GO2223010352PH | 01/12/2022 | 35.35 | 8.75 | 44.1 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | SOUTH 24 PARAGANAS | SM/12574 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of PAR KALUGACHHI village of Deuli-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.5 km distribution syst | TSM/013449 | 40034032 | New | SVS | GO2223007754PH | 15/09/2022 | 36.42 | 8.75 | 45.17 | Alipore Division | South 24 Pgs Mechanical Division | 25.66 | 11.27 | 0 | 0 | 36.93 | 25.66 | 11.27 | 0 | 0 | 36.93 | 81.76 | 67
445 | SOUTH 24 PARAGANAS | SM/12984 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of RADHABALLABHPUR village of Dearak Gram Panchayet in Diamond Harbour-I Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distributi | TSM/013460 | 40028584 | New | SVS | GO2223008381PH | 28/09/2022 | 34.92 | 8.75 | 43.67 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | SOUTH 24 PARAGANAS | SM/13962 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Ramanandapur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | TSM/014818 | 40035200 | New | SVS | GO2223010353PH | 01/12/2022 | 35.77 | 8.75 | 44.52 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | SOUTH 24 PARAGANAS | SM/12755 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Uttar Damodarpur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distributio | TSM/014820 | 40028670 | New | SVS | GO2223007943PH | 20/09/2022 | 36.12 | 8.75 | 44.87 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | SOUTH 24 PARAGANAS | SM/12577 | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | TSM/013463 | 40060027 | New | SVS | GO2223007738PH | 15/09/2022 | 29.92 | 8.75 | 38.67 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | SOUTH 24 PARAGANAS | SM/13978 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015392 | 40034029 | New | SVS | GO2223010320PH | 01/12/2022 | 76.48 | 7.32 | 83.79 | Alipore Division | South 24 Pgs Mechanical Division | 17.68 | 0 | 0 | 0 | 17.68 | 17.68 | 0 | 0 | 0 | 17.68 | 21.1 | 4
450 | SOUTH 24 PARAGANAS | SM/15577 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | TSM/017752 | 40036949 | New | SVS | GO2223013886PH | 15/02/2023 | 210.94 | 7.94 | 218.88 | Alipore Division | South 24 Pgs Mechanical Division | 177.1 | 0 | 0 | 0 | 177.1 | 177.1 | 0 | 0 | 0 | 177.1 | 80.91 | 39
451 | SOUTH 24 PARAGANAS | SM/15046 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR NARAYANGANJ, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS. | TSM/018314 | 40036984 | New | SVS | GO2223012961PH | 03/02/2023 | 86.75 | 7.71 | 94.46 | Alipore Division | South 24 Pgs Mechanical Division | 18.42 | 0 | 0 | 0 | 18.42 | 0.67 | 0 | 0 | 0 | 0.67 | 0.7 | 2
452 | SOUTH 24 PARAGANAS | SM/15050 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | TSM/018293 | 40036967 | New | SVS | GO2223012960PH | 03/02/2023 | 102.26 | 7.71 | 109.97 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 1.14 | 0 | 1.14 | 1.04 | 0
453 | SOUTH 24 PARAGANAS | SM/16292 | GROUND WATER BASED MRINALNAGAR PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | TSM/015396 | 40049219 | New | SVS | GO2223014837PH | 24/02/2023 | 893.93 | 71.66 | 965.59 | Alipore Division | South 24 Pgs Mechanical Division | 191.62 | 0 | 14.33 | 0 | 205.96 | 71.35 | 0 | 14.33 | 0 | 85.68 | 8.87 | 2
454 | SOUTH 24 PARAGANAS | SM/13311 | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/015206 | 40034776 | Augmentation | SVS | GO2223008846PH | 17/10/2022 | 636.35 | 83.43 | 719.78 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 308.2 | 3.49 | 43.05 | 0 | 354.74 | 308.2 | 3.49 | 43.05 | 0 | 354.74 | 49.28 | 35
455 | SOUTH 24 PARAGANAS | SM/14158 | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | TSM/015408 | 40035217 | New | MVS | GO2223011625PH | 05/01/2023 | 958.35 | 71.66 | 1030 | Alipore Division | South 24 Pgs Mechanical Division | 111.72 | 15.12 | 14.05 | 0 | 140.88 | 111.24 | 15.12 | 14.05 | 0 | 140.4 | 13.63 | 20
456 | SOUTH 24 PARAGANAS | SM/12803 | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | TSM/014759 | 40033968 | Augmentation | MVS | GO2223008046PH | 21/09/2022 | 643.42 | 47.38 | 690.8 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.57 | 0 | 24.79 | 0 | 27.36 | 2.57 | 0 | 24.79 | 0 | 27.36 | 3.96 | 2
457 | SOUTH 24 PARAGANAS | SM/11780 | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/011744 | 40034064 | Augmentation | MVS | GO2223005914PH | 02/08/2022 | 687.49 | 71.66 | 759.14 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 85.06 | 6.42 | 40.72 | 0 | 132.19 | 85.06 | 6.42 | 40.72 | 0 | 132.19 | 17.41 | 7
458 | SOUTH 24 PARAGANAS | SM/12240 | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | TSM/014833 | 40026269 | Augmentation | MVS | GO2223007111PH | 08/09/2022 | 336.3 | 53.6 | 389.9 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 44.75 | 13.25 | 7.04 | 0 | 65.04 | 44.75 | 13.25 | 7.04 | 0 | 65.04 | 16.68 | 12
459 | SOUTH 24 PARAGANAS | SM/13919 | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | TSM/017504 | 40035596 | Augmentation | MVS | GO2223010231PH | 29/11/2022 | 886.44 | 48.2 | 934.64 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 33.89 | 5.58 | 0 | 0 | 39.47 | 33.89 | 5.58 | 0 | 0 | 39.47 | 4.22 | 6
460 | SOUTH 24 PARAGANAS | SM/15778 | Ground water based PARULDAHA (ZONE-26) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | TSM/018358 | 40060628 | Augmentation | SVS | GO2223014336PH | 20/02/2023 | 257.02 | 68.97 | 325.99 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 77.31 | 0 | 6.34 | 0 | 83.65 | 77.31 | 0 | 6.34 | 0 | 83.65 | 25.66 | 1
461 | SOUTH 24 PARAGANAS | SM/16930 | Ground water based PASCHIM CHAKPANCHGHORA piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | TSM/012513 | 40033831 | Augmentation | MVS | GO2223016506PH | 16/03/2023 | 479.5 | 43.78 | 523.27 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 32.57 | 0 | 38.11 | 0 | 70.68 | 32.57 | 0 | 38.11 | 0 | 70.68 | 13.51 | 9
462 | SOUTH 24 PARAGANAS | SM/12047 | Ground water based PETUA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/012604 | 40026808 | Augmentation | SVS | GO2223006941PH | 01/09/2022 | 644.29 | 63.35 | 707.63 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 20.17 | 0 | 17.5 | 0 | 37.68 | 20.17 | 0 | 8.76 | 0 | 28.93 | 4.09 | 9
463 | SOUTH 24 PARAGANAS | SM/13827 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRANARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011628 | 40034041 | New | SVS | GO2223010073PH | 25/11/2022 | 458.11 | 75.49 | 533.61 | Alipore Division | South 24 Pgs Mechanical Division | 153.72 | 0 | 6.21 | 0 | 159.93 | 69.39 | 0 | 6.21 | 0 | 75.59 | 14.17 | 26
464 | SOUTH 24 PARAGANAS | SM/12732 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BHAJNA UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011581 | 40028492 | New | SVS | GO2223007932PH | 20/09/2022 | 587.08 | 75.49 | 662.57 | Alipore Division | South 24 Pgs Mechanical Division | 226.7 | 17.06 | 8.48 | 0 | 252.24 | 210.74 | 17.06 | 8.48 | 0 | 236.28 | 35.66 | 47
465 | SOUTH 24 PARAGANAS | SM/13763 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN KASHINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011582 | 40034033 | New | SVS | GO2223009891PH | 18/11/2022 | 503.01 | 71.66 | 574.67 | Alipore Division | South 24 Pgs Mechanical Division | 4.2 | 0 | 8.61 | 0 | 12.81 | 4.2 | 0 | 8.61 | 0 | 12.81 | 2.23 | 5
466 | SOUTH 24 PARAGANAS | SM/13869 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011585 | 40035271 | New | SVS | GO2223010128PH | 25/11/2022 | 509.04 | 71.66 | 580.69 | Alipore Division | South 24 Pgs Mechanical Division | 84.13 | 0 | 8 | 0 | 92.13 | 34.2 | 0 | 8 | 0 | 42.2 | 7.27 | 18
467 | SOUTH 24 PARAGANAS | SM/13764 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DIGAMBERPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011256 | 40035430 | New | SVS | GO2223009892PH | 18/11/2022 | 616.16 | 75.49 | 691.66 | Alipore Division | South 24 Pgs Mechanical Division | 168.71 | 0 | 10.5 | 0 | 179.21 | 114.35 | 0 | 10.5 | 0 | 124.85 | 18.05 | 22
468 | SOUTH 24 PARAGANAS | SM/13803 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DURGA GOBINDOPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011606 | 40034035 | New | SVS | GO2223009952PH | 22/11/2022 | 538.77 | 75.49 | 614.26 | Alipore Division | South 24 Pgs Mechanical Division | 133.91 | 0 | 7.9 | 0 | 141.81 | 133.91 | 0 | 7.9 | 0 | 141.81 | 23.09 | 31
469 | SOUTH 24 PARAGANAS | SM/11744 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GAYADHAM, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011259 | 40018954 | New | MVS | GO2223006014PH | 03/08/2022 | 444.71 | 71.66 | 516.37 | Alipore Division | South 24 Pgs Mechanical Division | 228.37 | 0 | 40.92 | 0 | 269.29 | 129.46 | 0 | 34.52 | 0 | 163.98 | 31.76 | 21
470 | SOUTH 24 PARAGANAS | SM/13870 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOPALNAGAR UTTAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 | TSM/011611 | 40034039 | New | SVS | GO2223010122PH | 25/11/2022 | 559.57 | 75.49 | 635.06 | Alipore Division | South 24 Pgs Mechanical Division | 256.76 | 5.63 | 8.29 | 0 | 270.67 | 239.08 | 5.63 | 8.29 | 0 | 252.99 | 39.84 | 21
471 | SOUTH 24 PARAGANAS | SM/13804 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPRASTHA PWSS , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011587 | 40034034 | New | MVS | GO2223009953PH | 22/11/2022 | 339.78 | 71.66 | 411.44 | Alipore Division | South 24 Pgs Mechanical Division | 48.42 | 0 | 4.35 | 0 | 52.77 | 48.42 | 0 | 4.35 | 0 | 52.77 | 12.83 | 10
472 | SOUTH 24 PARAGANAS | SM/13871 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KRISHNADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011605 | 40035262 | New | SVS | GO2223010113PH | 25/11/2022 | 573.95 | 75.49 | 649.44 | Alipore Division | South 24 Pgs Mechanical Division | 37.49 | 3.37 | 4.84 | 0 | 45.7 | 37.01 | 3.37 | 4.84 | 0 | 45.22 | 6.96 | 90
473 | SOUTH 24 PARAGANAS | SM/11746 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUMARPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011263 | 40019072 | New | MVS | GO2223006006PH | 03/08/2022 | 675.69 | 71.66 | 747.35 | Alipore Division | South 24 Pgs Mechanical Division | 222.75 | 0 | 17.7 | 0 | 240.44 | 207.99 | 0 | 17.7 | 0 | 225.68 | 30.2 | 27
474 | SOUTH 24 PARAGANAS | SM/11745 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011262 | 40018958 | New | SVS | GO2223006003PH | 03/08/2022 | 444.17 | 71.66 | 515.83 | Alipore Division | South 24 Pgs Mechanical Division | 155.16 | 5.72 | 8.15 | 0 | 169.02 | 155.16 | 5.72 | 1.74 | 0 | 162.61 | 31.52 | 26
475 | SOUTH 24 PARAGANAS | SM/13760 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PASCHIM SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011631 | 40034042 | New | SVS | GO2223009890PH | 18/11/2022 | 609.32 | 71.66 | 680.98 | Alipore Division | South 24 Pgs Mechanical Division | 350.82 | 16.77 | 10.13 | 0 | 377.73 | 350.82 | 16.77 | 10.13 | 0 | 377.73 | 55.47 | 20
476 | SOUTH 24 PARAGANAS | SM/11846 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PIPRAKHALI UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011580 | 40019096 | New | SVS | GO2223006284PH | 16/08/2022 | 387.8 | 75.49 | 463.3 | Alipore Division | South 24 Pgs Mechanical Division | 140.61 | 16.85 | 3.63 | 0 | 161.09 | 140.61 | 16.85 | 3.63 | 0 | 161.09 | 34.77 | 28
477 | SOUTH 24 PARAGANAS | SM/13800 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011626 | 40034040 | New | SVS | GO2223009956PH | 22/11/2022 | 535.08 | 71.66 | 606.73 | Alipore Division | South 24 Pgs Mechanical Division | 315 | 0 | 7.65 | 0 | 322.65 | 314.52 | 0 | 7.65 | 0 | 322.17 | 53.1 | 17
478 | SOUTH 24 PARAGANAS | SM/13799 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SURENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011633 | 40032982 | New | SVS | GO2223009955PH | 22/11/2022 | 548.88 | 71.66 | 620.54 | Alipore Division | South 24 Pgs Mechanical Division | 162.82 | 0 | 9.36 | 0 | 172.18 | 87.17 | 0 | 9.36 | 0 | 96.54 | 15.56 | 5
479 | SOUTH 24 PARAGANAS | SM/13802 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAKHASKHALI , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011607 | 40034036 | New | SVS | GO2223009954PH | 22/11/2022 | 905.59 | 75.49 | 981.09 | Alipore Division | South 24 Pgs Mechanical Division | 421.03 | 26.77 | 8.63 | 0 | 456.43 | 405.87 | 26.77 | 8.63 | 0 | 441.26 | 44.98 | 56
480 | SOUTH 24 PARAGANAS | SM/13965 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011629 | 40051497 | New | MVS | GO2223010350PH | 01/12/2022 | 649.88 | 75.49 | 725.37 | Alipore Division | South 24 Pgs Mechanical Division | 420.94 | 10.4 | 7.67 | 0 | 439.01 | 397.1 | 10.4 | 7.67 | 0 | 415.17 | 57.24 | 27
481 | SOUTH 24 PARAGANAS | SM/13828 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011267 | 40032850 | New | SVS | GO2223010045PH | 25/11/2022 | 783.68 | 71.66 | 855.33 | Alipore Division | South 24 Pgs Mechanical Division | 198.67 | 0 | 8.98 | 0 | 207.64 | 158.87 | 0 | 8.98 | 0 | 167.85 | 19.62 | 32
482 | SOUTH 24 PARAGANAS | SM/11296 | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | TSM/009670 | 40033599 | New | SVS | GO2223004567PH | 28/06/2022 | 272.39 | 29.87 | 302.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 123.17 | 3.79 | 6.78 | 0 | 133.73 | 123.17 | 3.79 | 6.78 | 0 | 133.73 | 44.24 | 42
483 | SOUTH 24 PARAGANAS | SM/11295 | Ground water based piped water supply scheme at Chitrasali (Chitrasali,J.L-112), Baruipur Block under South 24 Parganas dist | TSM/009669 | 40033904 | New | SVS | GO2223004566PH | 28/06/2022 | 119.25 | 29.87 | 149.12 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 52.1 | 9.43 | 6.4 | 0 | 67.93 | 52.1 | 9.43 | 0 | 0 | 61.53 | 41.26 | 28
484 | SOUTH 24 PARAGANAS | SM/11299 | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | TSM/009671 | 40033608 | New | SVS | GO2223004571PH | 28/06/2022 | 185.05 | 29.87 | 214.92 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 63.91 | 13.08 | 5.61 | 0 | 82.6 | 31.96 | 0 | 5.61 | 0 | 37.56 | 17.48 | 17
485 | SOUTH 24 PARAGANAS | SM/11294 | Ground water based piped water supply scheme at Kalyanpur, Khodarbazar (Khodarbazar CT, J.L-40), Baruipur Block under South 24 Parganas dist.(PART-I) | TSM/009672 | 40033937 | New | SVS | GO2223004568PH | 28/06/2022 | 139.15 | 29.87 | 169.02 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 64.59 | 3.58 | 5.01 | 0 | 73.18 | 64.59 | 3.58 | 5.01 | 0 | 73.18 | 43.29 | 58
486 | SOUTH 24 PARAGANAS | SM/11297 | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | TSM/009674 | 40035427 | New | SVS | GO2223004569PH | 28/06/2022 | 162.9 | 29.87 | 192.77 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.51 | 0 | 5.01 | 0 | 7.52 | 2.51 | 0 | 5.01 | 0 | 7.52 | 3.9 | 2
487 | SOUTH 24 PARAGANAS | SM/11298 | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | TSM/009673 | 40033604 | New | SVS | GO2223004570PH | 28/06/2022 | 206.22 | 29.87 | 236.09 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 175.45 | 5.31 | 8.48 | 0 | 189.24 | 175.45 | 0 | 6.36 | 0 | 181.81 | 77.01 | 28
488 | SOUTH 24 PARAGANAS | SM/11279 | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | TSM/010734 | 40049580 | New | SVS | GO2223004441PH | 24/06/2022 | 816.73 | 71.66 | 888.39 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 123.36 | 13.84 | 24.43 | 0 | 161.63 | 123.36 | 13.84 | 24.43 | 0 | 161.63 | 18.19 | 22
489 | SOUTH 24 PARAGANAS | SM/12873 | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | TSM/010745 | 40034309 | New | SVS | GO2223008158PH | 23/09/2022 | 720.64 | 71.66 | 792.29 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 82.03 | 8.41 | 36.85 | 0 | 127.29 | 82.03 | 7.37 | 36.85 | 0 | 126.25 | 15.93 | 6
490 | SOUTH 24 PARAGANAS | SM/11278 | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | TSM/010744 | 40034274 | New | SVS | GO2223004451PH | 24/06/2022 | 392.5 | 71.66 | 464.16 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 23.77 | 11.57 | 18.41 | 0 | 53.75 | 23.77 | 7.11 | 18.41 | 0 | 49.29 | 10.62 | 7
491 | SOUTH 24 PARAGANAS | SM/11280 | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | TSM/010741 | 40034619 | New | SVS | GO2223004453PH | 24/06/2022 | 649.61 | 71.66 | 721.27 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 39.48 | 15.69 | 45.14 | 0 | 100.31 | 39.48 | 15.69 | 45.14 | 0 | 100.31 | 13.91 | 11
492 | SOUTH 24 PARAGANAS | SM/11277 | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | TSM/010747 | 40034491 | New | MVS | GO2223004449PH | 24/06/2022 | 742.08 | 71.66 | 813.74 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 241.18 | 8.55 | 248.15 | 0 | 497.88 | 241.18 | 8.55 | 240.37 | 0 | 490.11 | 60.23 | 25
493 | SOUTH 24 PARAGANAS | SM/11276 | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | TSM/010754 | 40034475 | New | SVS | GO2223004448PH | 24/06/2022 | 732.31 | 71.66 | 803.97 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 253.97 | 10.24 | 53.77 | 0 | 317.97 | 253.97 | 10.24 | 51.46 | 0 | 315.66 | 39.26 | 25
494 | SOUTH 24 PARAGANAS | SM/13844 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBNAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/015898 | 40034590 | New | SVS | GO2223010112PH | 25/11/2022 | 954.77 | 75.49 | 1030.27 | Alipore Division | South 24 Pgs Mechanical Division | 56.72 | 0 | 10.34 | 0 | 67.06 | 56.23 | 0 | 10.34 | 0 | 66.58 | 6.46 | 5
495 | SOUTH 24 PARAGANAS | SM/13841 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR UTTAR SURENDRAGANJ, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/015908 | 40034587 | New | SVS | GO2223010114PH | 25/11/2022 | 562.03 | 75.49 | 637.52 | Alipore Division | South 24 Pgs Mechanical Division | 510.04 | 0 | 7.38 | 0 | 517.42 | 510.04 | 0 | 6.23 | 0 | 516.27 | 80.98 | 17
496 | SOUTH 24 PARAGANAS | SM/11731 | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/011789 | 40026046 | Augmentation | MVS | GO2223005934PH | 02/08/2022 | 459.19 | 71.66 | 530.84 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 70.77 | 17.11 | 34.58 | 0 | 122.46 | 70.77 | 17.11 | 34.58 | 0 | 122.46 | 23.07 | 16
497 | SOUTH 24 PARAGANAS | SM/14658 | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/012506 | 40033783 | Augmentation | MVS | GO2223012735PH | 31/01/2023 | 545.58 | 55.66 | 601.24 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 17.74 | 19.28 | 40.87 | 0 | 77.9 | 17.74 | 19.28 | 40.87 | 0 | 77.9 | 12.96 | 6
498 | SOUTH 24 PARAGANAS | SM/11784 | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | TSM/011438 | 40034120 | Augmentation | SVS | GO2223005990PH | 03/08/2022 | 673.24 | 71.66 | 744.9 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 359.78 | 28.45 | 12.12 | 0 | 400.34 | 359.78 | 28.45 | 12.12 | 0 | 400.34 | 53.74 | 47
499 | SOUTH 24 PARAGANAS | SM/13779 | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | TSM/011437 | 40034145 | Augmentation | SVS | GO2223009900PH | 18/11/2022 | 894.98 | 71.66 | 966.64 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.76 | 0 | 18.73 | 0 | 21.49 | 2.76 | 0 | 12.12 | 0 | 14.87 | 1.54 | 5
500 | SOUTH 24 PARAGANAS | SM/11778 | Ground water based RAJAK GOHALIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | TSM/011742 | 40025950 | Augmentation | MVS | GO2223005919PH | 02/08/2022 | 392.54 | 71.66 | 464.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 97.08 | 14.92 | 5.93 | 0 | 117.93 | 97.08 | 14.92 | 5.93 | 0 | 117.93 | 25.41 | 43
501 | SOUTH 24 PARAGANAS | SM/12804 | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | TSM/014752 | 40033786 | Augmentation | MVS | GO2223008053PH | 21/09/2022 | 646.28 | 47.38 | 693.66 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.67 | 0 | 0 | 0 | 2.67 | 2.67 | 0 | 0 | 0 | 2.67 | 0.39 | 2
502 | SOUTH 24 PARAGANAS | SM/12805 | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | TSM/014755 | 40033897 | Augmentation | SVS | GO2223008052PH | 21/09/2022 | 616.83 | 47.38 | 664.21 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.64 | 0 | 0 | 0 | 2.64 | 2.64 | 0 | 0 | 0 | 2.64 | 0.4 | 2
503 | SOUTH 24 PARAGANAS | SM/15337 | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | TSM/018366 | 40047094 | Augmentation | MVS | GO2223013418PH | 07/02/2023 | 781.05 | 137.94 | 918.99 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 203.24 | 0 | 23.24 | 0 | 226.49 | 203.24 | 0 | 18.3 | 0 | 221.54 | 24.11 | 9
504 | SOUTH 24 PARAGANAS | SM/13976 | GROUND WATER BASED RAMGOPALPUR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015405 | 40034583 | New | SVS | GO2223010321PH | 01/12/2022 | 528.83 | 71.66 | 600.48 | Alipore Division | South 24 Pgs Mechanical Division | 99.62 | 4.97 | 8.98 | 0 | 113.56 | 41.57 | 4.97 | 8.98 | 0 | 55.51 | 9.24 | 15
505 | SOUTH 24 PARAGANAS | SM/18570 | Ground Water Based RAMKRISHNAPUR Pipe Water Supply Scheme to Accommodate FHTC in Jaynagar - I Block under South 24 Parganas W/S Division - I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Ar | TSM/018530 | 40047379 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1166.4 | 84.68 | 1251.08 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.83 | 0 | 18.94 | 0 | 21.77 | 2.83 | 0 | 18.94 | 0 | 21.77 | 1.74 | 2
506 | SOUTH 24 PARAGANAS | SM/15755 | Ground water based RAMNAGAR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dist | TSM/018210 | 40053020 | Augmentation | SVS | GO2223014329PH | 20/02/2023 | 651.91 | 55.62 | 707.53 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 125.6 | 26.9 | 11.61 | 0 | 164.11 | 125.6 | 26.9 | 11.61 | 0 | 164.11 | 23.19 | 15
507 | SOUTH 24 PARAGANAS | SM/15634 | Ground water based RAMNAGAR (ZONE-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | TSM/018217 | 40053028 | Augmentation | SVS | GO2223013880PH | 15/02/2023 | 660.96 | 55.62 | 716.58 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 237.07 | 31.39 | 18.1 | 0 | 286.56 | 237.07 | 31.39 | 18.1 | 0 | 286.56 | 39.99 | 20
508 | SOUTH 24 PARAGANAS | SM/15756 | Ground water based RAMNAGAR (ZONE-III) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | TSM/018222 | 40053051 | Augmentation | SVS | GO2223014330PH | 20/02/2023 | 404.53 | 55.62 | 460.15 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 119.31 | 19.3 | 5.81 | 0 | 144.42 | 119.31 | 19.3 | 5.81 | 0 | 144.42 | 31.39 | 20
509 | SOUTH 24 PARAGANAS | SM/18576 | Ground water based RASAPUNJA piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESTALA block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | TSM/018477 | 40047321 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1477.22 | 49.35 | 1526.57 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 200.06 | 2.75 | 84.37 | 0 | 287.18 | 200.06 | 2.75 | 84.37 | 0 | 287.18 | 18.81 | 10
510 | SOUTH 24 PARAGANAS | SM/11783 | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | TSM/011734 | 40025898 | Augmentation | MVS | GO2223005930PH | 02/08/2022 | 476.47 | 71.66 | 548.13 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 108.56 | 3.44 | 5.61 | 0 | 117.6 | 108.56 | 3.44 | 5.61 | 0 | 117.6 | 21.46 | 46
511 | SOUTH 24 PARAGANAS | SM/18870 | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | TSM/020489 | 0 | Augmentation | SVS | PHE/IV/3037/W-665/23 | 05/10/2023 | 245.51 | 27.81 | 273.32 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 89.37 | 0 | 0 | 0 | 89.37 | 68.23 | 0 | 0 | 0 | 68.23 | 24.96 | 2
512 | SOUTH 24 PARAGANAS | SM/11781 | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | TSM/011741 | 40026001 | Augmentation | MVS | GO2223005921PH | 02/08/2022 | 395.23 | 71.66 | 466.89 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 75.81 | 26.08 | 27.94 | 0 | 129.83 | 75.81 | 26.08 | 27.94 | 0 | 129.83 | 27.81 | 12
513 | SOUTH 24 PARAGANAS | SM/14874 | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | TSM/017755 | 40034009 | Augmentation | MVS | GO2223013028PH | 03/02/2023 | 707.52 | 56.45 | 763.97 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 182.83 | 0 | 13.59 | 0 | 196.41 | 182.83 | 0 | 13.59 | 0 | 196.41 | 25.71 | 19
514 | SOUTH 24 PARAGANAS | SM/12806 | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | TSM/014761 | 40053434 | Augmentation | MVS | GO2223008054PH | 21/09/2022 | 591.79 | 47.38 | 639.17 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.54 | 0 | 2.54 | 0 | 5.08 | 2.54 | 0 | 0 | 0 | 2.54 | 0.4 | 2
515 | SOUTH 24 PARAGANAS | SM/14875 | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | TSM/018169 | 40047337 | Augmentation | MVS | GO2223012971PH | 03/02/2023 | 898.82 | 84.68 | 983.49 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 157.3 | 0.58 | 76.6 | 0 | 234.48 | 157.3 | 0.58 | 76.6 | 0 | 234.48 | 23.84 | 11
516 | SOUTH 24 PARAGANAS | SM/11645 | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/011439 | 40034379 | Augmentation | SVS | GO2223005659PH | 27/07/2022 | 588.55 | 71.66 | 660.2 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 146 | 15.15 | 10.8 | 0 | 171.95 | 146 | 15.15 | 10.8 | 0 | 171.95 | 26.04 | 22
517 | SOUTH 24 PARAGANAS | SM/11646 | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/011440 | 40034450 | Augmentation | SVS | GO2223005656PH | 27/07/2022 | 532.29 | 71.66 | 603.94 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 136.22 | 21.2 | 10.8 | 0 | 168.21 | 136.22 | 21.2 | 10.8 | 0 | 168.21 | 27.85 | 26
518 | SOUTH 24 PARAGANAS | SM/12770 | Ground water based SRI KRISHNANAGAR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | TSM/012514 | 40033898 | Augmentation | MVS | GO2223008051PH | 21/09/2022 | 597.92 | 63.35 | 661.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 17.82 | 0 | 46.96 | 0 | 64.78 | 17.82 | 0 | 46.96 | 0 | 64.78 | 9.8 | 5
519 | SOUTH 24 PARAGANAS | SM/14861 | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/018300 | 40047253 | Augmentation | MVS | GO2223012974PH | 03/02/2023 | 916.95 | 66.27 | 983.21 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 93.33 | 0 | 34.98 | 0 | 128.31 | 93.33 | 0 | 34.98 | 0 | 128.31 | 13.05 | 2
520 | SOUTH 24 PARAGANAS | SM/14862 | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | TSM/018362 | 40047164 | Augmentation | MVS | GO2223012987PH | 03/02/2023 | 784.23 | 140.36 | 924.59 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 353.36 | 0 | 21.5 | 0 | 374.86 | 353.36 | 0 | 16.56 | 0 | 369.91 | 40.01 | 21
521 | SOUTH 24 PARAGANAS | SM/11850 | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | TSM/011945 | 40019074 | New | SVS | GO2223006285PH | 16/08/2022 | 475.41 | 71.66 | 547.06 | Alipore Division | South 24 Pgs Mechanical Division | 221.79 | 28.12 | 5.33 | 0 | 255.25 | 205.24 | 28.12 | 5.33 | 0 | 238.69 | 43.63 | 19
522 | SOUTH 24 PARAGANAS | SM/15865 | Ground Water Based TILPI(Zone-II) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of | TSM/018041 | 40053357 | Augmentation | SVS | GO2223014349PH | 20/02/2023 | 802.33 | 56.45 | 858.78 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 250.16 | 7.92 | 39.17 | 0 | 297.25 | 250.16 | 7.92 | 39.17 | 0 | 297.25 | 34.61 | 10
523 | SOUTH 24 PARAGANAS | SM/12058 | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | TSM/012521 | 40035467 | Augmentation | SVS | GO2223006934PH | 01/09/2022 | 205.85 | 31.67 | 237.52 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 98.78 | 10.12 | 6.08 | 0 | 114.99 | 98.78 | 10.12 | 0 | 0 | 108.91 | 45.85 | 45
524 | SOUTH 24 PARAGANAS | SM/14863 | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/017336 | 40047368 | Augmentation | MVS | GO2223013024PH | 03/02/2023 | 732.13 | 55.91 | 788.04 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 240.38 | 0 | 51.53 | 0 | 291.9 | 240.38 | 0 | 51.53 | 0 | 291.9 | 37.04 | 19
525 | SOUTH 24 PARAGANAS | SM/12231 | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | TSM/014832 | 40034520 | Augmentation | SVS | GO2223007101PH | 06/09/2022 | 623.71 | 55.62 | 679.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 175.32 | 5.05 | 25.41 | 0 | 205.78 | 175.32 | 5.05 | 25.41 | 0 | 205.78 | 30.29 | 9
526 | SOUTH 24 PARAGANAS | SM/14876 | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/017757 | 40046943 | Augmentation | MVS | GO2223012972PH | 03/02/2023 | 840.22 | 99.4 | 939.62 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 47.98 | 0 | 43.99 | 0 | 91.97 | 47.98 | 0 | 43.99 | 0 | 91.97 | 9.79 | 2
527 | SOUTH 24 PARAGANAS | SM/13846 | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | TSM/015401 | 40034585 | New | MVS | GO2223010126PH | 25/11/2022 | 600.25 | 71.66 | 671.91 | Alipore Division | South 24 Pgs Mechanical Division | 131.74 | 6.17 | 8.45 | 0 | 146.36 | 104.07 | 6.17 | 8.45 | 0 | 118.69 | 17.66 | 25
528 | SOUTH 24 PARAGANAS | SM/18375 | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | TSM/018475 | 40047297 | Augmentation | MVS | 1808/PHE-28011/127/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1133.47 | 0 | 1133.47 | South 24 Pgs. W/S Division - I |  | 64.42 | 0 | 120.1 | 0 | 184.52 | 46.94 | 0 | 120.1 | 0 | 167.03 | 14.74 | 15
529 | SOUTH 24 PARAGANAS | SM/13977 | GROUND WATER BASED WATER SUPPLY SCHEME FOR DAKSHIN MADHUSUDANPUR UNDER ALIPORE DIVISION, BLOCK-PATAHRPRATIMA,DISTRICT - SOUTH 24 PARGANAS | TSM/015395 | 40034028 | New | MVS | GO2223010322PH | 01/12/2022 | 487.52 | 75.49 | 563.02 | Alipore Division | South 24 Pgs Mechanical Division | 137.84 | 6.64 | 8.61 | 0 | 153.09 | 105.94 | 6.64 | 8.61 | 0 | 121.19 | 21.53 | 22
530 | SOUTH 24 PARAGANAS | SM/13867 | GROUND WATER BASED WATER SUPPLY SCHEME FOR PURBA DWAROKAPUR UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA,DISTRICT-SOUTH 24 PARGANAS | TSM/015897 | 40034591 | New | SVS | GO2223010116PH | 25/11/2022 | 470.78 | 71.66 | 542.43 | Alipore Division | South 24 Pgs Mechanical Division | 4.45 | 12.15 | 6.31 | 0 | 22.91 | 4.45 | 12.15 | 6.31 | 0 | 22.91 | 4.22 | 7
531 | SOUTH 24 PARAGANAS | SM/13868 | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | TSM/015407 | 40034584 | New | MVS | GO2223010048PH | 25/11/2022 | 555.98 | 71.66 | 627.64 | Alipore Division | South 24 Pgs Mechanical Division | 141.17 | 0 | 4.34 | 0 | 145.51 | 141.17 | 0 | 4.34 | 0 | 145.51 | 23.18 | 5
532 | SOUTH 24 PARAGANAS | SM/14984 | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | TSM/016092 | 40035278 | New | MVS | GO2223013148PH | 04/02/2023 | 288.06 | 71.66 | 359.72 | Alipore Division | South 24 Pgs Mechanical Division | 37.64 | 10.32 | 3.96 | 0 | 51.92 | 37.64 | 10.32 | 3.96 | 0 | 51.92 | 14.43 | 11
533 | SOUTH 24 PARAGANAS | SM/13845 | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | TSM/015874 | 40034586 | New | SVS | GO2223010119PH | 25/11/2022 | 420.78 | 71.66 | 492.44 | Alipore Division | South 24 Pgs Mechanical Division | 102.87 | 2.47 | 5.03 | 0 | 110.36 | 102.87 | 2.47 | 5.03 | 0 | 110.36 | 22.41 | 6
534 | SOUTH 24 PARAGANAS | SM/15759 | HASANPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018119 | 40053555 | Augmentation | MVS | GO2223014328PH | 20/02/2023 | 781.98 | 76.15 | 858.13 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 207.66 | 17.75 | 19.45 | 0 | 244.86 | 207.66 | 5.89 | 19.45 | 0 | 233 | 27.15 | 11
535 | SOUTH 24 PARAGANAS | SM/15771 | HOGALKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/017730 | 40053105 | Augmentation | MVS | GO2223014331PH | 20/02/2023 | 750.4 | 74.63 | 825.04 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 36.29 | 0 | 28.88 | 0 | 65.17 | 36.29 | 0 | 28.88 | 0 | 65.17 | 7.9 | 9
536 | SOUTH 24 PARAGANAS | SM/09931 | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008768 | 40009384 | Augmentation | MVS | GO2122006631PH | 10/12/2021 | 812.88 | 55.11 | 867.99 | Alipore Division | South 24 Pgs Mechanical Division | 376.33 | 0 | 36.58 | 0 | 412.91 | 278.23 | 0 | 36.58 | 0 | 314.81 | 36.27 | 26
537 | SOUTH 24 PARAGANAS | SM/09932 | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008764 | 40009398 | Augmentation | MVS | GO2122006639PH | 10/12/2021 | 272.28 | 21.63 | 293.91 | Alipore Division | South 24 Pgs Mechanical Division | 199.39 | 0 | 0.8 | 0 | 200.2 | 199.39 | 0 | 0.8 | 0 | 200.2 | 68.12 | 59
538 | SOUTH 24 PARAGANAS | SM/10051 | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008765 | 40009466 | Augmentation | MVS | GO2122008592PH | 24/01/2022 | 1628.89 | 71.59 | 1700.47 | Alipore Division | South 24 Pgs Mechanical Division | 817.81 | 0 | 139.28 | 0 | 957.09 | 817.81 | 0 | 139.28 | 0 | 957.09 | 56.28 | 56
539 | SOUTH 24 PARAGANAS | SM/09935 | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | TSM/008685 | 40009437 | Augmentation | MVS | GO2122006708PH | 13/12/2021 | 804.15 | 71.59 | 875.73 | Alipore Division | South 24 Pgs Mechanical Division | 264.3 | 2.64 | 14.55 | 0 | 281.49 | 264.3 | 2.64 | 14.55 | 0 | 281.49 | 32.14 | 42
540 | SOUTH 24 PARAGANAS | SM/08182 | Improvement of W/S by interconnection from existing big dia TW and laying distribution system with CIDF, UPVC pipes including providing FHTC by retrofitting of scheme Improvement of WS [Phase-III] in Baruipur and Mograhat-II Block of Sankarpur-II GP withi | TSM/006926 | 40002624 | Retrofitting | MVS | GO2021006721PH | 09/02/2021 | 200.38 | 0 | 200.38 | South 24 Pgs. W/S Division - I |  | 184.05 | 0 | 0 | 0 | 184.05 | 184.05 | 0 | 0 | 0 | 184.05 | 91.85 | 95
541 | SOUTH 24 PARAGANAS | SM/08180 | Improvement of W/S including providing FHTC for Chandanpukur, Bagdaha, Dhanberia & Durgapur mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | TSM/006927 | 40002630 | Retrofitting | MVS | GO2021006719PH | 09/02/2021 | 225.68 | 0 | 225.68 | South 24 Pgs. W/S Division - I |  | 159.03 | 0 | 0 | 0 | 159.03 | 159.03 | 0 | 0 | 0 | 159.03 | 70.46 | 80
542 | SOUTH 24 PARAGANAS | SM/08181 | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | TSM/006928 | 40002655 | Retrofitting | MVS | GO2021006722PH | 09/02/2021 | 260.42 | 0 | 260.42 | South 24 Pgs. W/S Division - I |  | 211.85 | 0 | 0 | 0 | 211.85 | 211.85 | 0 | 0 | 0 | 211.85 | 81.35 | 80
543 | SOUTH 24 PARAGANAS | SM/18128 | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | TSM/011042 | 40066194 | New | SVS | GO2223017941PH | 29/03/2023 | 129.52 | 20.71 | 150.23 | Alipore Division | South 24 Pgs Mechanical Division | 44.62 | 3.87 | 1.29 | 0 | 49.78 | 44.62 | 3.87 | 1.29 | 0 | 49.78 | 33.13 | 9
544 | SOUTH 24 PARAGANAS | SM/13514 | JAYKRISHNAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015398 | 40034646 | Augmentation | SVS | GO2223009267PH | 02/11/2022 | 867.96 | 71.11 | 939.07 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 134.91 | 19.45 | 25.2 | 0 | 179.56 | 134.91 | 19.45 | 25.2 | 0 | 179.56 | 19.12 | 10
545 | SOUTH 24 PARAGANAS | SM/11273 | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | TSM/010767 | 40026132 | New | MVS | GO2223004440PH | 24/06/2022 | 918.73 | 75.02 | 993.75 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 513.12 | 40.83 | 16.4 | 0 | 570.34 | 513.12 | 40.83 | 16.4 | 0 | 570.34 | 57.39 | 37
546 | SOUTH 24 PARAGANAS | SM/12207 | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | TSM/014873 | 40026084 | Augmentation | SVS | GO2223007095PH | 06/09/2022 | 854.95 | 73.02 | 927.96 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 194.89 | 32.62 | 31.76 | 0 | 259.26 | 194.89 | 32.62 | 31.76 | 0 | 259.26 | 27.94 | 14
547 | SOUTH 24 PARAGANAS | SM/11647 | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/011003 | 40034467 | Augmentation | SVS | GO2223005657PH | 27/07/2022 | 614.96 | 71.66 | 686.61 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 4.42 | 0 | 22.23 | 0 | 26.65 | 4.42 | 0 | 22.23 | 0 | 26.65 | 3.88 | 4
548 | SOUTH 24 PARAGANAS | SM/11788 | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | TSM/011004 | 40034438 | Augmentation | SVS | GO2223005993PH | 03/08/2022 | 561.14 | 71.66 | 632.8 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 186.35 | 10.49 | 12.63 | 0 | 209.48 | 186.35 | 10.49 | 12.63 | 0 | 209.48 | 33.1 | 29
549 | SOUTH 24 PARAGANAS | SM/13777 | KANTIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016074 | 40034476 | Augmentation | MVS | GO2223009908PH | 18/11/2022 | 906.8 | 74.69 | 981.49 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 141 | 22.19 | 53.21 | 0 | 216.4 | 141 | 22.19 | 53.21 | 0 | 216.4 | 22.05 | 11
550 | SOUTH 24 PARAGANAS | SM/12016 | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | TSM/010748 | 40026117 | New | MVS | GO2223006890PH | 01/09/2022 | 846.12 | 79.02 | 925.13 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 141.11 | 4.18 | 50.47 | 0 | 195.76 | 141.11 | 4.18 | 50.47 | 0 | 195.76 | 21.16 | 10
551 | SOUTH 24 PARAGANAS | SM/15525 | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/010690 | 40035410 | New | MVS | GO2223013997PH | 16/02/2023 | 1394.62 | 46.32 | 1440.94 | Alipore Division | South 24 Pgs Mechanical Division | 16.47 | 5.92 | 16.49 | 0 | 38.88 | 0 | 5.92 | 16.49 | 0 | 22.41 | 1.56 | 3
552 | SOUTH 24 PARAGANAS | SM/14462 | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011018 | 40032540 | New | MVS | GO2223012264PH | 20/01/2023 | 1360.76 | 46.32 | 1407.08 | Alipore Division | South 24 Pgs Mechanical Division | 93.75 | 12.09 | 14.01 | 0 | 119.85 | 44.15 | 12.09 | 14.01 | 0 | 70.25 | 4.99 | 6
553 | SOUTH 24 PARAGANAS | SM/13778 | MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015478 | 40034164 | Augmentation | MVS | GO2223009901PH | 18/11/2022 | 924.25 | 71.92 | 996.17 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 324.49 | 27.7 | 25.9 | 0 | 378.09 | 324.49 | 27.7 | 25.9 | 0 | 378.09 | 37.95 | 20
554 | SOUTH 24 PARAGANAS | SM/13515 | MALIPUKURIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015504 | 40034616 | Augmentation | SVS | GO2223009258PH | 02/11/2022 | 848.95 | 71.11 | 920.07 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 40.55 | 0 | 40.55 | 0 | 0 | 40.55 | 0 | 40.55 | 4.41 | 0
555 | SOUTH 24 PARAGANAS | SM/13500 | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015390 | 40033835 | Augmentation | MVS | GO2223009259PH | 02/11/2022 | 868.4 | 71.11 | 939.52 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 252.71 | 13.55 | 41.59 | 0 | 307.86 | 252.71 | 13.55 | 41.59 | 0 | 307.86 | 32.77 | 24
556 | SOUTH 24 PARAGANAS | SM/12017 | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | TSM/010689 | 40026121 | New | MVS | GO2223006891PH | 01/09/2022 | 919.91 | 76.72 | 996.63 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 54.41 | 0 | 57.41 | 0 | 111.81 | 54.41 | 0 | 57.41 | 0 | 111.81 | 11.22 | 5
557 | SOUTH 24 PARAGANAS | SM/13499 | NATAGACHHI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015394 | 40034669 | Augmentation | MVS | GO2223009264PH | 02/11/2022 | 674.8 | 70 | 744.8 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 159.74 | 22.69 | 41.35 | 0 | 223.79 | 159.74 | 13.53 | 41.35 | 0 | 214.62 | 28.82 | 20
558 | SOUTH 24 PARAGANAS | SM/15772 | PADMAPUKURIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018416 | 40053091 | Augmentation | MVS | GO2223014318PH | 20/02/2023 | 914.33 | 75.32 | 989.64 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 135.15 | 0 | 17.24 | 0 | 152.39 | 135.15 | 0 | 17.24 | 0 | 152.39 | 15.4 | 9
559 | SOUTH 24 PARAGANAS | SM/18395 | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | TSM/017112 | 40035206 | New | MVS | 1817/PHE-28011/182/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1243.24 | 46.72 | 1289.96 | Alipore Division | South 24 Pgs Mechanical Division | 260.81 | 0 | 55.68 | 0 | 316.49 | 152.72 | 0 | 55.68 | 0 | 208.41 | 16.16 | 2
560 | SOUTH 24 PARAGANAS | SM/18744 | Pilot scale implementation of IOT based Measurement & Monitoring of water service delivery in Srinagar Water Supply Scheme, Canning-II Block, South 24 Parganas under South 24-Pgs Mechanical Division, PHE Dte. | TSM/010773 | 40063778 | Augmentation | MVS | 2441/PHE/IV/W-627/23 | 17/08/2023 | 0 | 5.18 | 5.18 |  | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
561 | SOUTH 24 PARAGANAS | SM/11160 | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | TSM/010373 | 40027056 | New | MVS | GO2223003746PH | 02/06/2022 | 2050.89 | 119.48 | 2170.37 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 1131.39 | 19.64 | 390.75 | 0 | 1541.78 | 1131.39 | 19.64 | 390.75 | 0 | 1541.78 | 71.04 | 72
562 | SOUTH 24 PARAGANAS | SM/11488 | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | TSM/010374 | 40018966 | New | MVS | GO2223005082PH | 15/07/2022 | 999.64 | 0 | 999.64 | South 24 Pgs. W/S Division - I |  | 335.09 | 0 | 0 | 0 | 335.09 | 335.09 | 0 | 0 | 0 | 335.09 | 33.52 | 70
563 | SOUTH 24 PARAGANAS | SM/11493 | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011230 | 40025878 | New | SVS | GO2223005189PH | 19/07/2022 | 409.23 | 71.66 | 480.88 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 134.79 | 0 | 27.39 | 0 | 162.19 | 134.79 | 0 | 27.39 | 0 | 162.19 | 33.73 | 55
564 | SOUTH 24 PARAGANAS | SM/15660 | Proposed ground water based ASUTI I/II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 parganas W/S division-I, South 24 parganas district | TSM/019643 | 40047324 | Augmentation | MVS | GO2223014317PH | 20/02/2023 | 2409.22 | 298.7 | 2707.92 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 899.84 | 84.76 | 3.73 | 0 | 988.33 | 899.84 | 84.76 | 3.73 | 0 | 988.33 | 36.5 | 24
565 | SOUTH 24 PARAGANAS | SM/15782 | Proposed Ground water based BAGDAHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/018476 | 40054149 | Augmentation | MVS | GO2223014323PH | 20/02/2023 | 440.17 | 54.7 | 494.87 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 73.42 | 8.7 | 27.69 | 0 | 109.81 | 73.42 | 8.7 | 27.69 | 0 | 109.81 | 22.19 | 15
566 | SOUTH 24 PARAGANAS | SM/18677 | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | TSM/017335 | 40034099 | Augmentation | MVS | 2242/PHE-28011/38/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1153.48 | 84.68 | 1238.15 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 303.13 | 0 | 33.39 | 0 | 336.51 | 303.13 | 0 | 33.39 | 0 | 336.51 | 27.18 | 9
567 | SOUTH 24 PARAGANAS | SM/13782 | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | TSM/016358 | 40033683 | Augmentation | MVS | GO2223009902PH | 18/11/2022 | 840.11 | 48.2 | 888.31 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.66 | 0 | 14.97 | 0 | 17.63 | 2.66 | 0 | 14.97 | 0 | 17.63 | 1.99 | 2
568 | SOUTH 24 PARAGANAS | SM/18498 | Proposed Ground water based BANTRA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | TSM/018420 | 40053427 | Augmentation | SVS | 2036/PHE-28011/194/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1089.1 | 69.28 | 1158.38 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 45.4 | 0 | 72.22 | 0 | 117.63 | 45.4 | 0 | 72.22 | 0 | 117.63 | 10.15 | 2
569 | SOUTH 24 PARAGANAS | SM/14548 | Proposed Ground water based BELARIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/016728 | 40034298 | Augmentation | MVS | GO2223012597PH | 30/01/2023 | 1022.46 | 102.51 | 1124.97 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.76 | 0 | 0 | 0 | 2.76 | 2.76 | 0 | 0 | 0 | 2.76 | 0.24 | 0
570 | SOUTH 24 PARAGANAS | SM/14659 | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/017337 | 40034219 | Augmentation | MVS | GO2223012698PH | 31/01/2023 | 910.85 | 84.68 | 995.53 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 207.68 | 10.82 | 89.29 | 0 | 307.79 | 207.68 | 0.47 | 89.29 | 0 | 297.43 | 29.88 | 16
571 | SOUTH 24 PARAGANAS | SM/15783 | Proposed Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/018427 | 40054162 | Augmentation | MVS | GO2223014324PH | 20/02/2023 | 502.6 | 56.45 | 559.05 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 120.09 | 3.88 | 6.1 | 0 | 130.07 | 120.09 | 3.88 | 6.1 | 0 | 130.07 | 23.27 | 9
572 | SOUTH 24 PARAGANAS | SM/18681 | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/017323 | 40033936 | Augmentation | MVS | 2244/PHE-28011/163/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1257 | 120.33 | 1377.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 39.87 | 0 | 22.92 | 0 | 62.79 | 39.87 | 0 | 22.92 | 0 | 62.79 | 4.56 | 9
573 | SOUTH 24 PARAGANAS | SM/11497 | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011211 | 40025998 | New | SVS | GO2223005176PH | 19/07/2022 | 493.02 | 71.66 | 564.67 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 45.82 | 10.2 | 52.62 | 0 | 108.63 | 45.82 | 10.2 | 52.62 | 0 | 108.63 | 19.24 | 36
574 | SOUTH 24 PARAGANAS | SM/11496 | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011224 | 40025988 | New | MVS | GO2223005182PH | 19/07/2022 | 408.24 | 71.66 | 479.9 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 129.7 | 19.17 | 21.67 | 0 | 170.54 | 129.7 | 19.17 | 21.67 | 0 | 170.54 | 35.54 | 21
575 | SOUTH 24 PARAGANAS | SM/18678 | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | TSM/017284 | 40034891 | Augmentation | MVS | 2242/PHE-28011/38/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1014.93 | 56.45 | 1071.38 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.75 | 0 | 15.58 | 0 | 18.34 | 2.75 | 0 | 15.58 | 0 | 18.34 | 1.71 | 2
576 | SOUTH 24 PARAGANAS | SM/13783 | Proposed ground water based CHAK BALAIBAG piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTE | TSM/016350 | 40033687 | Augmentation | MVS | GO2223009905PH | 18/11/2022 | 893.03 | 71.07 | 964.1 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.94 | 0 | 47.54 | 0 | 50.48 | 2.94 | 0 | 47.54 | 0 | 50.48 | 5.24 | 100
577 | SOUTH 24 PARAGANAS | SM/14864 | Proposed Ground water based CHAK HARANANDAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | TSM/018438 | 40047362 | Augmentation | MVS | GO2223013023PH | 03/02/2023 | 585.03 | 56.45 | 641.48 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 59.12 | 0 | 0 | 0 | 59.12 | 59.12 | 0 | 0 | 0 | 59.12 | 9.22 | 9
578 | SOUTH 24 PARAGANAS | SM/12801 | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | TSM/014899 | 40035976 | Augmentation | SVS | GO2223008043PH | 21/09/2022 | 668.26 | 47.38 | 715.64 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 82.99 | 0 | 21.29 | 0 | 104.28 | 82.99 | 0 | 21.29 | 0 | 104.28 | 14.57 | 9
579 | SOUTH 24 PARAGANAS | SM/15784 | Proposed Ground water based CHAKAR BAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/018426 | 40054187 | Augmentation | MVS | GO2223014327PH | 20/02/2023 | 384.69 | 55.22 | 439.92 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 16.95 | 3.75 | 22.32 | 0 | 43.03 | 16.95 | 3.75 | 22.32 | 0 | 43.03 | 9.78 | 7
580 | SOUTH 24 PARAGANAS | SM/15785 | Proposed Ground water based CHANDANPUKUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/018249 | 40053163 | Augmentation | MVS | GO2223014322PH | 20/02/2023 | 427.27 | 71.18 | 498.45 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 18.03 | 12.34 | 25.96 | 0 | 56.33 | 18.03 | 12.34 | 25.96 | 0 | 56.33 | 11.3 | 4
581 | SOUTH 24 PARAGANAS | SM/13920 | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | TSM/017296 | 40054119 | Augmentation | SVS | GO2223010235PH | 29/11/2022 | 264.56 | 27.81 | 292.37 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 143.62 | 12.27 | 2.37 | 0 | 158.25 | 143.62 | 12.27 | 2.37 | 0 | 158.25 | 54.13 | 36
582 | SOUTH 24 PARAGANAS | SM/18330 | Proposed Ground water based DAKSHIN GOURIPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic A | TSM/016359 | 40033695 | Augmentation | MVS | 1690/PHE-28011/218/2022-SCHM CELL-Dept. of PHE | 27/06/2023 | 1039.11 | 83.86 | 1122.98 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 219.53 | 0 | 67.45 | 0 | 286.98 | 219.53 | 0 | 67.45 | 0 | 286.98 | 25.56 | 21
583 | SOUTH 24 PARAGANAS | SM/15779 | PROPOSED GROUND WATER BASED DAKSHIN KALYANPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BARUIPUR BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT AUGMENTATION OF SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTE | TSM/018483 | 40054113 | Augmentation | MVS | GO2223014319PH | 20/02/2023 | 438.33 | 51.42 | 489.75 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 23.68 | 11.26 | 5.96 | 0 | 40.9 | 23.68 | 11.26 | 5.96 | 0 | 40.9 | 8.35 | 4
584 | SOUTH 24 PARAGANAS | SM/13780 | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/016355 | 40033673 | Augmentation | MVS | GO2223009909PH | 18/11/2022 | 879.12 | 55.91 | 935.03 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 90.43 | 3.33 | 15.26 | 0 | 109.03 | 90.43 | 3.33 | 15.26 | 0 | 109.03 | 11.66 | 11
585 | SOUTH 24 PARAGANAS | SM/14856 | Proposed Ground water based DEHIMEDAN MALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | TSM/018699 | 40047215 | Augmentation | MVS | GO2223012969PH | 03/02/2023 | 719.02 | 61.36 | 780.38 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 62.98 | 6.4 | 53.12 | 0 | 122.51 | 62.98 | 0 | 53.12 | 0 | 116.11 | 14.88 | 2
586 | SOUTH 24 PARAGANAS | SM/11498 | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011201 | 40025986 | New | MVS | GO2223005178PH | 19/07/2022 | 433.17 | 71.66 | 504.82 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 124.5 | 28.99 | 27.63 | 0 | 181.13 | 124.5 | 28.99 | 27.63 | 0 | 181.13 | 35.88 | 42
587 | SOUTH 24 PARAGANAS | SM/15786 | Proposed Ground water based DHOPA GACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/018424 | 40054158 | Augmentation | MVS | GO2223014320PH | 20/02/2023 | 431.86 | 55.22 | 487.09 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 106.17 | 2.31 | 28.1 | 0 | 136.59 | 106.17 | 2.31 | 28.1 | 0 | 136.59 | 28.04 | 11
588 | SOUTH 24 PARAGANAS | SM/16117 | Proposed Ground water based DHOSA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/018462 | 40053446 | Augmentation | SVS | GO2223014654PH | 22/02/2023 | 309.74 | 52.16 | 361.89 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 102.36 | 12.62 | 3.83 | 0 | 118.81 | 102.36 | 12.62 | 3.83 | 0 | 118.81 | 32.83 | 7
589 | SOUTH 24 PARAGANAS | SM/13921 | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | TSM/014903 | 40034730 | Augmentation | MVS | GO2223010213PH | 29/11/2022 | 804.52 | 56.45 | 860.97 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.64 | 0 | 27.91 | 0 | 30.55 | 2.64 | 0 | 27.91 | 0 | 30.55 | 3.55 | 0
590 | SOUTH 24 PARAGANAS | SM/11503 | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011196 | 40025982 | New | SVS | GO2223005188PH | 19/07/2022 | 395.6 | 71.66 | 467.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 129.63 | 17.3 | 20.58 | 0 | 167.51 | 129.63 | 17.3 | 20.58 | 0 | 167.51 | 35.85 | 15
591 | SOUTH 24 PARAGANAS | SM/16118 | Proposed Ground water based DUDHNAI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | TSM/017763 | 40052632 | Augmentation | SVS | GO2223014652PH | 22/02/2023 | 403.18 | 71.18 | 474.36 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 97.21 | 16.66 | 23.02 | 0 | 136.89 | 97.21 | 16.66 | 23.02 | 0 | 136.89 | 28.86 | 8
592 | SOUTH 24 PARAGANAS | SM/13985 | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/015218 | 40034642 | Augmentation | MVS | GO2223010330PH | 01/12/2022 | 865.11 | 81 | 946.1 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.63 | 0 | 23.62 | 0 | 26.26 | 2.63 | 0 | 23.62 | 0 | 26.26 | 2.78 | 1
593 | SOUTH 24 PARAGANAS | SM/18269 | Proposed Ground water based JALDHAPA piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/017282 | 40035112 | Augmentation | MVS | 1588/PHE-28011/165/2023-SCHM CELL-Dept. of PHE | 21/06/2023 | 1052.23 | 71.07 | 1123.3 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 27.13 | 0 | 0 | 0 | 27.13 | 27.13 | 0 | 0 | 0 | 27.13 | 2.42 | 2
594 | SOUTH 24 PARAGANAS | SM/15780 | PROPOSED GROUND WATER BASED JAMALHATI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BARUIPUR, SONARPUR BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT FOR AUGMENTATION GROUND WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFEC | TSM/019799 | 40061509 | Augmentation | MVS | GO2223014326PH | 20/02/2023 | 210.41 | 51.43 | 261.84 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.45 | 0 | 6.26 | 0 | 8.71 | 2.45 | 0 | 0 | 0 | 2.45 | 0.94 | 2
595 | SOUTH 24 PARAGANAS | SM/13986 | Proposed Ground water based JANGALIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/017293 | 40034158 | Augmentation | SVS | GO2223010331PH | 01/12/2022 | 723.17 | 56.45 | 779.62 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.54 | 0 | 36.37 | 0 | 38.91 | 2.54 | 0 | 36.37 | 0 | 38.91 | 4.99 | 5
596 | SOUTH 24 PARAGANAS | SM/14549 | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | TSM/016726 | 40034502 | Augmentation | SVS | GO2223012599PH | 30/01/2023 | 1132.35 | 84.68 | 1217.03 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 4.59 | 0 | 20.98 | 0 | 25.57 | 4.59 | 0 | 20.98 | 0 | 25.57 | 2.1 | 2
597 | SOUTH 24 PARAGANAS | SM/12234 | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | TSM/014900 | 40026040 | Augmentation | MVS | GO2223007175PH | 07/09/2022 | 483.52 | 71.66 | 555.18 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 98.3 | 5.28 | 36.03 | 0 | 139.6 | 98.3 | 0 | 36.03 | 0 | 134.33 | 24.2 | 15
598 | SOUTH 24 PARAGANAS | SM/15870 | Proposed Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | TSM/018250 | 40053345 | Augmentation | SVS | GO2223014296PH | 20/02/2023 | 367.4 | 51.42 | 418.82 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 87.28 | 7.18 | 9.88 | 0 | 104.33 | 87.28 | 7.18 | 9.88 | 0 | 104.33 | 24.91 | 9
599 | SOUTH 24 PARAGANAS | SM/18574 | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | TSM/018432 | 40047289 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1233.69 | 84.68 | 1318.37 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.92 | 0 | 28.1 | 0 | 31.02 | 2.92 | 0 | 28.1 | 0 | 31.02 | 2.35 | 2
600 | SOUTH 24 PARAGANAS | SM/13922 | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | TSM/016376 | 40033678 | Augmentation | MVS | GO2223010232PH | 29/11/2022 | 239.1 | 55.91 | 295.01 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 80.51 | 15.9 | 4.55 | 0 | 100.95 | 80.51 | 15.9 | 4.55 | 0 | 100.95 | 34.22 | 12
601 | SOUTH 24 PARAGANAS | SM/13923 | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/017164 | 40034175 | Augmentation | MVS | GO2223010233PH | 29/11/2022 | 750.61 | 56.45 | 807.06 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 161.02 | 0 | 44.53 | 0 | 205.55 | 161.02 | 0 | 44.53 | 0 | 205.55 | 25.47 | 5
602 | SOUTH 24 PARAGANAS | SM/15871 | Proposed Ground water based KHARUPATALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/018473 | 40054175 | Augmentation | MVS | GO2223014294PH | 20/02/2023 | 414.87 | 54.7 | 469.57 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.54 | 0 | 21.78 | 0 | 24.32 | 2.54 | 0 | 21.78 | 0 | 24.32 | 5.18 | 2
603 | SOUTH 24 PARAGANAS | SM/12802 | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | TSM/014902 | 40034088 | Augmentation | MVS | GO2223008049PH | 21/09/2022 | 601.74 | 47.38 | 649.12 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 6.87 | 0 | 0 | 0 | 6.87 | 6.87 | 0 | 0 | 0 | 6.87 | 1.06 | 2
604 | SOUTH 24 PARAGANAS | SM/11502 | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011195 | 40025945 | New | MVS | GO2223005186PH | 19/07/2022 | 378.4 | 71.66 | 450.06 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 136.61 | 18.04 | 19.81 | 0 | 174.46 | 135.84 | 18.04 | 19.81 | 0 | 173.69 | 38.59 | 47
605 | SOUTH 24 PARAGANAS | SM/18578 | Proposed Ground water based MAGRAHAT piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/018189 | 40047346 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1030.51 | 81.69 | 1112.2 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.6 | 0 | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 2.6 | 0.23 | 2
606 | SOUTH 24 PARAGANAS | SM/16125 | Proposed Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/018296 | 40053374 | Augmentation | MVS | GO2223014649PH | 22/02/2023 | 639.39 | 71.18 | 710.57 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 32.98 | 0 | 6.31 | 0 | 39.29 | 32.98 | 0 | 6.31 | 0 | 39.29 | 5.53 | 2
607 | SOUTH 24 PARAGANAS | SM/14661 | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | TSM/016725 | 40034456 | Augmentation | MVS | GO2223012719PH | 31/01/2023 | 635.41 | 56.45 | 691.87 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 177.03 | 0 | 12.09 | 0 | 189.11 | 177.03 | 0 | 12.09 | 0 | 189.11 | 27.33 | 14
608 | SOUTH 24 PARAGANAS | SM/14662 | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/015217 | 40034773 | Augmentation | MVS | GO2223012751PH | 31/01/2023 | 957.47 | 81 | 1038.47 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 97.02 | 0 | 25.96 | 0 | 122.98 | 97.02 | 0 | 25.96 | 0 | 122.98 | 11.84 | 9
609 | SOUTH 24 PARAGANAS | SM/12045 | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011202 | 40025996 | New | MVS | GO2223006887PH | 01/09/2022 | 394.67 | 71.66 | 466.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 62.46 | 0 | 25.82 | 0 | 88.29 | 62.46 | 0 | 25.82 | 0 | 88.29 | 18.93 | 17
610 | SOUTH 24 PARAGANAS | SM/18268 | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/016565 | 40035327 | Augmentation | MVS | 1588/PHE-28011/165/2023-SCHM CELL-Dept. of PHE | 21/06/2023 | 943.47 | 83.86 | 1027.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 193.17 | 0 | 37.32 | 0 | 230.49 | 193.17 | 0 | 37.32 | 0 | 230.49 | 22.44 | 14
611 | SOUTH 24 PARAGANAS | SM/14663 | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | TSM/017503 | 40035381 | Augmentation | MVS | GO2223012744PH | 31/01/2023 | 915.31 | 84.68 | 999.99 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 435.26 | 0 | 71.46 | 0 | 506.72 | 435.26 | 0 | 71.46 | 0 | 506.72 | 50.67 | 18
612 | SOUTH 24 PARAGANAS | SM/11495 | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011225 | 40033600 | New | MVS | GO2223005191PH | 19/07/2022 | 668.53 | 71.66 | 740.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 332.07 | 0 | 18.8 | 0 | 350.87 | 332.07 | 0 | 9.41 | 0 | 341.48 | 46.13 | 27
613 | SOUTH 24 PARAGANAS | SM/16126 | Proposed Ground water based NOR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | TSM/018252 | 40053421 | Augmentation | SVS | GO2223014656PH | 22/02/2023 | 380.81 | 46.36 | 427.17 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 34.16 | 15.85 | 4.11 | 0 | 54.12 | 34.16 | 15.85 | 4.11 | 0 | 54.12 | 12.67 | 7
614 | SOUTH 24 PARAGANAS | SM/11494 | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011229 | 40025887 | New | SVS | GO2223005190PH | 19/07/2022 | 419.58 | 71.66 | 491.24 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 129.48 | 17.01 | 22.6 | 0 | 169.08 | 129.48 | 17.01 | 22.6 | 0 | 169.08 | 34.42 | 47
615 | SOUTH 24 PARAGANAS | SM/16128 | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | TSM/018425 | 40054192 | Augmentation | SVS | GO2223014655PH | 22/02/2023 | 119.01 | 26.08 | 145.09 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.36 | 0 | 4.09 | 0 | 6.45 | 2.36 | 0 | 0 | 0 | 2.36 | 1.63 | 2
616 | SOUTH 24 PARAGANAS | SM/17299 | Proposed Ground water based PETUA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | TSM/018705 | 40054198 | Augmentation | MVS | GO2223016078PH | 15/03/2023 | 572 | 61.36 | 633.36 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 122.11 | 6.24 | 66.34 | 0 | 194.68 | 122.11 | 6.24 | 66.34 | 0 | 194.68 | 30.74 | 16
617 | SOUTH 24 PARAGANAS | SM/13798 | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011641 | 40032962 | New | SVS | GO2223009958PH | 22/11/2022 | 811.81 | 113.24 | 925.05 | Alipore Division | South 24 Pgs Mechanical Division | 440.72 | 13.84 | 32.13 | 0 | 486.7 | 245.22 | 13.84 | 32.13 | 0 | 291.2 | 31.48 | 9
618 | SOUTH 24 PARAGANAS | SM/16129 | Proposed Ground water based PURANDARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/018251 | 40053410 | Augmentation | MVS | GO2223014644PH | 22/02/2023 | 434.46 | 55.22 | 489.69 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 76.32 | 0 | 27.04 | 0 | 103.36 | 76.32 | 0 | 27.04 | 0 | 103.36 | 21.11 | 9
619 | SOUTH 24 PARAGANAS | SM/16131 | Proposed Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | TSM/018299 | 40053417 | Augmentation | SVS | GO2223014646PH | 22/02/2023 | 727.17 | 56.45 | 783.62 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.62 | 6.04 | 20.68 | 0 | 29.33 | 2.62 | 6.04 | 20.68 | 0 | 29.33 | 3.74 | 3
620 | SOUTH 24 PARAGANAS | SM/13784 | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | TSM/016316 | 40033680 | Augmentation | MVS | GO2223009907PH | 18/11/2022 | 780.05 | 55.91 | 835.96 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 57.48 | 3.64 | 34.14 | 0 | 95.25 | 57.48 | 3.64 | 34.14 | 0 | 95.25 | 11.39 | 11
621 | SOUTH 24 PARAGANAS | SM/16132 | Proposed Ground water based RANA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | TSM/018248 | 40053089 | Augmentation | MVS | GO2223014653PH | 22/02/2023 | 487.1 | 53.64 | 540.74 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 31.57 | 12.94 | 6.15 | 0 | 50.66 | 31.57 | 12.94 | 6.15 | 0 | 50.66 | 9.37 | 3
622 | SOUTH 24 PARAGANAS | SM/18331 | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | TSM/016353 | 40033690 | Augmentation | MVS | 1690/PHE-28011/218/2022-SCHM CELL-Dept. of PHE | 27/06/2023 | 1028.87 | 83.86 | 1112.74 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 101.27 | 0 | 86.97 | 0 | 188.24 | 101.27 | 0 | 86.97 | 0 | 188.24 | 16.92 | 2
623 | SOUTH 24 PARAGANAS | SM/16133 | Proposed Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | TSM/017962 | 40052638 | Augmentation | MVS | GO2223014651PH | 22/02/2023 | 451.34 | 71.18 | 522.52 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 49.03 | 0 | 6.18 | 0 | 55.21 | 49.03 | 0 | 6.18 | 0 | 55.21 | 10.57 | 4
624 | SOUTH 24 PARAGANAS | SM/18577 | Proposed Ground water based RAYNAGAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | TSM/018294 | 40047169 | Augmentation | MVS | 2143/PHE-28011/121/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1185.22 | 99.4 | 1284.63 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 102.7 | 0 | 20.23 | 0 | 122.93 | 102.7 | 0 | 20.23 | 0 | 122.93 | 9.57 | 2
625 | SOUTH 24 PARAGANAS | SM/16134 | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | TSM/017762 | 40052627 | Augmentation | MVS | GO2223014648PH | 22/02/2023 | 206.01 | 56.45 | 262.46 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 51.07 | 5 | 35.62 | 0 | 91.69 | 51.07 | 5 | 35.62 | 0 | 91.69 | 34.93 | 2
626 | SOUTH 24 PARAGANAS | SM/14550 | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | TSM/017546 | 40035784 | Augmentation | MVS | GO2223012598PH | 30/01/2023 | 1107.05 | 84.68 | 1191.73 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 21.36 | 0 | 35.82 | 0 | 57.18 | 21.36 | 0 | 35.82 | 0 | 57.18 | 4.8 | 9
627 | SOUTH 24 PARAGANAS | SM/16135 | Proposed Ground water based SURJAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | TSM/018700 | 40054200 | Augmentation | SVS | GO2223014647PH | 22/02/2023 | 137.81 | 61.36 | 199.17 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 45.04 | 10.52 | 4.28 | 0 | 59.84 | 45.04 | 10.52 | 0 | 0 | 55.55 | 27.89 | 17
628 | SOUTH 24 PARAGANAS | SM/16137 | Proposed Ground water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | TSM/017759 | 40052567 | Augmentation | MVS | GO2223014645PH | 22/02/2023 | 403.47 | 71.18 | 474.65 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 93.45 | 7.95 | 25.37 | 0 | 126.77 | 93.45 | 7.95 | 25.37 | 0 | 126.77 | 26.71 | 7
629 | SOUTH 24 PARAGANAS | SM/15781 | Proposed Ground Water Based TILPI(Zone-I) Piped Water Supply Scheme to Accommodate FHTC inJAYNAGAR-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected A | TSM/018024 | 40053320 | Augmentation | SVS | GO2223014337PH | 20/02/2023 | 589.63 | 56.45 | 646.08 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 161.67 | 0 | 28.86 | 0 | 190.53 | 161.67 | 0 | 28.86 | 0 | 190.53 | 29.49 | 5
630 | SOUTH 24 PARAGANAS | SM/14551 | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | TSM/017505 | 40035521 | Augmentation | MVS | GO2223012588PH | 30/01/2023 | 1032.9 | 84.68 | 1117.57 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 365.49 | 10.95 | 83.63 | 0 | 460.07 | 365.49 | 0.68 | 83.63 | 0 | 449.8 | 40.25 | 15
631 | SOUTH 24 PARAGANAS | SM/13781 | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | TSM/015329 | 40034150 | Augmentation | MVS | GO2223009899PH | 18/11/2022 | 875.34 | 55.66 | 931 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.7 | 0 | 0 | 0 | 2.7 | 2.7 | 0 | 0 | 0 | 2.7 | 0.29 | 0
632 | SOUTH 24 PARAGANAS | SM/14849 | Proposed Ground Water Based UTTARPARANIJ Piped Water Supply Scheme to accommodate FHTC in Jaynagar - I Block, under South 24 Parganas W/S Division - I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic A | TSM/018529 | 40047474 | Augmentation | MVS | GO2223013031PH | 03/02/2023 | 849.7 | 56.45 | 906.15 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.66 | 0 | 41.3 | 0 | 43.96 | 2.66 | 0 | 39.31 | 0 | 41.98 | 4.63 | 2
633 | SOUTH 24 PARAGANAS | SM/11972 | Providing 100% FHTC in Mograhat-1/IV at Hijalghat Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. | TSM/010897 | 40034879 | New | MVS | GO2223006796PH | 29/08/2022 | 511.19 | 0 | 511.19 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 38.87 | 0 | 38.87 | 0 | 0 | 38.87 | 0 | 38.87 | 7.6 | 0
634 | SOUTH 24 PARAGANAS | SM/11769 | PROVIDING 100% FHTC IN ZONE I -A & ZONE I-B AT NAPUKURIA MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | TSM/011546 | 40034682 | New | MVS | GO2223005917PH | 02/08/2022 | 760.33 | 0 | 760.33 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 60.86 | 0 | 60.86 | 0 | 0 | 60.86 | 0 | 60.86 | 8 | 0
635 | SOUTH 24 PARAGANAS | SM/11768 | PROVIDING 100% FHTC IN ZONE I -A & ZONE I-B AT PURBA TATULBERIA MOUZA OF KULTALI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | TSM/011555 | 40035308 | New | MVS | GO2223005928PH | 02/08/2022 | 992.71 | 0 | 992.71 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 34.13 | 0 | 34.13 | 0 | 0 | 34.13 | 0 | 34.13 | 3.44 | 0
636 | SOUTH 24 PARAGANAS | SM/11770 | PROVIDING 100% FHTC IN ZONE VII -A & ZONE VII-B AT NALGORA MOUZA OF JOYNAGAR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | TSM/011554 | 40035018 | New | MVS | GO2223005927PH | 02/08/2022 | 838.69 | 0 | 838.69 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 73.26 | 0 | 73.26 | 0 | 0 | 73.26 | 0 | 73.26 | 8.73 | 0
637 | SOUTH 24 PARAGANAS | SM/11252 | PROVIDING 100% FHTC IN ZONE- IV AT DASKHIN GARANKATHI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010551 | 40035849 | New | MVS | GO2223004337PH | 22/06/2022 | 468.16 | 0 | 468.16 | South 24 Pgs. W/S Division - I |  | 229.73 | 0 | 0 | 0 | 229.73 | 229.73 | 0 | 0 | 0 | 229.73 | 49.07 | 15
638 | SOUTH 24 PARAGANAS | SM/11248 | PROVIDING 100% FHTC IN ZONE- VI AT RADHA BALLAVPUR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010559 | 40034972 | New | MVS | GO2223004331PH | 22/06/2022 | 494.23 | 0 | 494.23 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 36.03 | 0 | 36.03 | 0 | 0 | 36.03 | 0 | 36.03 | 7.29 | 0
639 | SOUTH 24 PARAGANAS | SM/11246 | PROVIDING 100% FHTC IN ZONE- VIII AT NIMPITH MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | TSM/010560 | 40035056 | New | MVS | GO2223004329PH | 22/06/2022 | 616.99 | 0 | 616.99 | South 24 Pgs. W/S Division - I |  | 172.53 | 0 | 44.98 | 0 | 217.51 | 172.53 | 0 | 44.98 | 0 | 217.51 | 35.25 | 17
640 | SOUTH 24 PARAGANAS | SM/11265 | Providing 100% FHTC in Zone-I at Bainch Beria Srichanda mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010749 | 40034680 | New | MVS | GO2223004395PH | 23/06/2022 | 469.65 | 0 | 469.65 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 35.72 | 0 | 35.72 | 0 | 0 | 35.72 | 0 | 35.72 | 7.61 | 0
641 | SOUTH 24 PARAGANAS | SM/11251 | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT JALABERIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010549 | 40035442 | New | MVS | GO2223004335PH | 22/06/2022 | 794.73 | 0 | 794.73 | South 24 Pgs. W/S Division - I |  | 21.09 | 0 | 57.92 | 0 | 79.02 | 21.09 | 0 | 57.92 | 0 | 79.02 | 9.94 | 7
642 | SOUTH 24 PARAGANAS | SM/11255 | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010555 | 40034759 | New | MVS | GO2223004340PH | 22/06/2022 | 776.49 | 0 | 776.49 | South 24 Pgs. W/S Division - I |  | 13.81 | 0 | 0 | 0 | 13.81 | 13.81 | 0 | 0 | 0 | 13.81 | 1.78 | 10
643 | SOUTH 24 PARAGANAS | SM/11250 | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MONDOLER LAT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010546 | 40035543 | New | MVS | GO2223004334PH | 22/06/2022 | 794.81 | 0 | 794.81 | South 24 Pgs. W/S Division - I |  | 213.82 | 0 | 57.93 | 0 | 271.75 | 213.82 | 0 | 57.93 | 0 | 271.75 | 34.19 | 30
644 | SOUTH 24 PARAGANAS | SM/11973 | Providing 100% FHTC in Zone-II at Rajballabhpur Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. | TSM/010894 | 40034757 | New | MVS | GO2223006798PH | 29/08/2022 | 503.71 | 0 | 503.71 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 38.31 | 0 | 38.31 | 0 | 0 | 38.31 | 0 | 38.31 | 7.61 | 0
645 | SOUTH 24 PARAGANAS | SM/11256 | PROVIDING 100% FHTC IN ZONE-III A & ZONE-III B AT BELADURGANAGAR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010556 | 40034855 | New | MVS | GO2223004342PH | 22/06/2022 | 653.33 | 0 | 653.33 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 47.55 | 0 | 47.55 | 0 | 0 | 47.55 | 0 | 47.55 | 7.28 | 0
646 | SOUTH 24 PARAGANAS | SM/11266 | Providing 100% FHTC in Zone-III at Pratapberia (Baneswarpur) mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010756 | 40034862 | New | MVS | GO2223004396PH | 23/06/2022 | 332.14 | 0 | 332.14 | South 24 Pgs. W/S Division - I |  | 7.09 | 0 | 25.27 | 0 | 32.36 | 7.09 | 0 | 25.27 | 0 | 32.36 | 9.74 | 10
647 | SOUTH 24 PARAGANAS | SM/11249 | PROVIDING 100% FHTC IN ZONE-IV AT GARDOANI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010557 | 40034882 | New | MVS | GO2223004332PH | 22/06/2022 | 959.87 | 0 | 959.87 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 79.69 | 0 | 79.69 | 0 | 0 | 79.69 | 0 | 79.69 | 8.3 | 8
648 | SOUTH 24 PARAGANAS | SM/11259 | Providing 100% FHTC in Zone-IX at Ghola Noapara Usthi mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010782 | 40035477 | New | MVS | GO2223004392PH | 23/06/2022 | 430.01 | 0 | 430.01 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 32.7 | 0 | 32.7 | 0 | 0 | 32.7 | 0 | 32.7 | 7.61 | 0
649 | SOUTH 24 PARAGANAS | SM/11257 | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT KATAMARI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | TSM/010543 | 40035975 | New | MVS | GO2223004322PH | 22/06/2022 | 856.61 | 0 | 856.61 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 506.38 | 0 | 506.38 | 0 | 0 | 498.83 | 0 | 498.83 | 58.23 | 5
650 | SOUTH 24 PARAGANAS | SM/11247 | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT MONIRTAT MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010561 | 40034922 | New | MVS | GO2223004330PH | 22/06/2022 | 685.07 | 0 | 685.07 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 49.95 | 0 | 49.95 | 0 | 0 | 49.95 | 0 | 49.95 | 7.29 | 9
651 | SOUTH 24 PARAGANAS | SM/11267 | Providing 100% FHTC in Zone-V at Barijpur mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010758 | 40034909 | New | MVS | GO2223004397PH | 23/06/2022 | 753.66 | 0 | 753.66 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 57.32 | 0 | 57.32 | 0 | 0 | 57.32 | 0 | 57.32 | 7.61 | 0
652 | SOUTH 24 PARAGANAS | SM/11253 | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010552 | 40035931 | New | MVS | GO2223004338PH | 22/06/2022 | 585.88 | 0 | 585.88 | South 24 Pgs. W/S Division - I |  | 59.38 | 0 | 41.82 | 0 | 101.2 | 59.38 | 0 | 41.82 | 0 | 101.2 | 17.27 | 15
653 | SOUTH 24 PARAGANAS | SM/11264 | Providing 100% FHTC in Zone-VI at Sadhukhan Ardari Ektara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010761 | 40034923 | New | MVS | GO2223004394PH | 23/06/2022 | 747.46 | 0 | 747.46 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 56.86 | 0 | 56.86 | 0 | 0 | 56.86 | 0 | 56.86 | 7.61 | 0
654 | SOUTH 24 PARAGANAS | SM/11254 | PROVIDING 100% FHTC IN ZONE-VII A & ZONE-VII B AT MAIPIT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010553 | 40035903 | New | MVS | GO2223004339PH | 22/06/2022 | 803.21 | 0 | 803.21 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 58.56 | 0 | 58.56 | 0 | 0 | 58.56 | 0 | 58.56 | 7.29 | 8
655 | SOUTH 24 PARAGANAS | SM/11261 | Providing 100% FHTC in Zone-VII at Ajodhyanagar mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010774 | 40034997 | New | MVS | GO2223004390PH | 23/06/2022 | 277.69 | 0 | 277.69 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 42.22 | 0 | 42.22 | 0 | 0 | 42.22 | 0 | 42.22 | 15.2 | 0
656 | SOUTH 24 PARAGANAS | SM/11260 | Providing 100% FHTC in Zone-VIII at Khela Rampur Sirakol mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010780 | 40035019 | New | MVS | GO2223004388PH | 23/06/2022 | 913 | 0 | 913 | South 24 Pgs. W/S Division - I |  | 44.96 | 0 | 69.45 | 0 | 114.4 | 0 | 0 | 69.45 | 0 | 69.45 | 7.61 | 10
657 | SOUTH 24 PARAGANAS | SM/11263 | Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte | TSM/010766 | 40035488 | New | MVS | GO2223004393PH | 23/06/2022 | 749.74 | 0 | 749.74 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 57.02 | 0 | 57.02 | 0 | 0 | 57.02 | 0 | 57.02 | 7.6 | 0
658 | SOUTH 24 PARAGANAS | SM/11262 | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010770 | 40035512 | New | MVS | GO2223004391PH | 23/06/2022 | 387.24 | 0 | 387.24 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 195.28 | 0 | 195.28 | 0 | 0 | 29.44 | 0 | 29.44 | 7.6 | 5
659 | SOUTH 24 PARAGANAS | SM/11487 | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | TSM/010530 | 40026589 | New | MVS | GO2223005124PH | 15/07/2022 | 673.5 | 119.48 | 792.98 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 555.19 | 52.44 | 16.17 | 0 | 623.8 | 555.19 | 52.44 | 16.17 | 0 | 623.8 | 78.67 | 65
660 | SOUTH 24 PARAGANAS | SM/07051 | Providing Functional Household Tap Connection for Atmarampur W/S Scheme for Atmarampur,Chingripota and Santoshpur Mouza under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur. | TSM/006114 | 8136130 | Retrofitting | MVS | GO2021002753PH | 25/11/2020 | 99.79 | 0 | 99.79 | South 24 Pgs. W/S Division - I |  | 99.79 | 0 | 0 | 0 | 99.79 | 93.94 | 0 | 0 | 0 | 93.94 | 94.14 | 95
661 | SOUTH 24 PARAGANAS | SM/07052 | Providing Functional Household Tap Connection for Betuabati W/S Scheme under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur | TSM/006116 | 8136113 | Retrofitting | MVS | GO2021002757PH | 25/11/2020 | 68.39 | 0 | 68.39 | South 24 Pgs. W/S Division - I |  | 68.39 | 0 | 0 | 0 | 68.39 | 63.57 | 0 | 0 | 0 | 63.57 | 92.96 | 52
662 | SOUTH 24 PARAGANAS | SM/11245 | Providing Functional Household Tap Connection (FHTC) in Zone-I at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010772 | 40034692 | New | MVS | GO2223004319PH | 22/06/2022 | 744.81 | 0 | 744.81 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 57.77 | 0 | 57.77 | 0 | 0 | 57.77 | 0 | 57.77 | 7.76 | 1
663 | SOUTH 24 PARAGANAS | SM/11243 | Providing Functional Household Tap Connection (FHTC) in Zone-II at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010783 | 40034900 | New | MVS | GO2223004328PH | 22/06/2022 | 765.3 | 0 | 765.3 | South 24 Pgs. W/S Division - I |  | 53.08 | 0 | 59.25 | 0 | 112.34 | 53.08 | 0 | 59.25 | 0 | 112.34 | 14.68 | 5
664 | SOUTH 24 PARAGANAS | SM/11244 | Providing Functional Household Tap Connection (FHTC) in Zone-III at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte | TSM/010826 | 40034946 | New | MVS | GO2223004318PH | 22/06/2022 | 619.31 | 0 | 619.31 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 47.52 | 0 | 47.52 | 0 | 0 | 47.52 | 0 | 47.52 | 7.67 | 0
665 | SOUTH 24 PARAGANAS | SM/11242 | Providing Functional Household Tap Connection (FHTC) in Zone-IV at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010828 | 40035025 | New | MVS | GO2223004327PH | 22/06/2022 | 186.05 | 0 | 186.05 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 13.98 | 0 | 13.98 | 0 | 0 | 13.98 | 0 | 13.98 | 7.52 | 0
666 | SOUTH 24 PARAGANAS | SM/11238 | Providing Functional Household Tap Connection (FHTC) in Zone-IX at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010833 | 40035374 | New | MVS | GO2223004323PH | 22/06/2022 | 286.44 | 0 | 286.44 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 21.15 | 0 | 21.15 | 0 | 0 | 21.15 | 0 | 21.15 | 7.38 | 8
667 | SOUTH 24 PARAGANAS | SM/11241 | Providing Functional Household Tap Connection (FHTC) in Zone-V at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010829 | 40035089 | New | MVS | GO2223004326PH | 22/06/2022 | 316.26 | 0 | 316.26 | South 24 Pgs. W/S Division - I |  | 91.98 | 0 | 23.59 | 0 | 115.57 | 91.98 | 0 | 23.59 | 0 | 115.57 | 36.54 | 11
668 | SOUTH 24 PARAGANAS | SM/11240 | Providing Functional Household Tap Connection (FHTC) in Zone-VI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010830 | 40035257 | New | MVS | GO2223004325PH | 22/06/2022 | 265.35 | 0 | 265.35 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 19.44 | 0 | 19.44 | 0 | 0 | 19.44 | 0 | 19.44 | 7.33 | 0
669 | SOUTH 24 PARAGANAS | SM/11235 | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010841 | 40035294 | New | MVS | GO2223004320PH | 22/06/2022 | 733.04 | 0 | 733.04 | South 24 Pgs. W/S Division - I |  | 61.56 | 0 | 56.63 | 0 | 118.19 | 42.75 | 0 | 56.63 | 0 | 99.37 | 13.56 | 10
670 | SOUTH 24 PARAGANAS | SM/11239 | Providing Functional Household Tap Connection (FHTC) in Zone-VIII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010831 | 40035342 | New | MVS | GO2223004324PH | 22/06/2022 | 465.42 | 0 | 465.42 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 34.83 | 0 | 34.83 | 0 | 0 | 34.83 | 0 | 34.83 | 7.48 | 8
671 | SOUTH 24 PARAGANAS | SM/11237 | Providing Functional Household Tap Connection (FHTC) in Zone-X at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010836 | 40035397 | New | MVS | GO2223004316PH | 22/06/2022 | 468 | 0 | 468 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 35.04 | 0 | 35.04 | 0 | 0 | 35.04 | 0 | 35.04 | 7.49 | 8
672 | SOUTH 24 PARAGANAS | SM/11236 | Providing Functional Household Tap Connection (FHTC) in Zone-XI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010837 | 40035411 | New | MVS | GO2223004321PH | 22/06/2022 | 190.17 | 0 | 190.17 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 14.32 | 0 | 14.32 | 0 | 0 | 14.32 | 0 | 14.32 | 7.53 | 0
673 | SOUTH 24 PARAGANAS | SM/09505 | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | TSM/008279 | 5344170 | Retrofitting | MVS | GO2122005594PH | 19/11/2021 | 235.76 | 0 | 235.76 | Alipore Division |  | 210.48 | 0 | 0 | 0 | 210.48 | 210.48 | 0 | 0 | 0 | 210.48 | 89.28 | 90
674 | SOUTH 24 PARAGANAS | SM/09506 | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone VI including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | TSM/008280 | 5344170 | Retrofitting | MVS | GO2122005594PH | 19/11/2021 | 97.92 | 0 | 97.92 | Alipore Division |  | 74.19 | 0 | 16.82 | 0 | 91.01 | 74.19 | 0 | 16.82 | 0 | 91.01 | 92.94 | 99
675 | SOUTH 24 PARAGANAS | SM/13785 | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016318 | 40034242 | Augmentation | MVS | GO2223009910PH | 18/11/2022 | 922.36 | 73.27 | 995.63 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 18.2 | 4.62 | 75.1 | 0 | 97.91 | 17.8 | 4.62 | 75.1 | 0 | 97.51 | 9.79 | 6
676 | SOUTH 24 PARAGANAS | SM/13786 | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016148 | 40034495 | Augmentation | SVS | GO2223009903PH | 18/11/2022 | 922.99 | 76.24 | 999.23 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 117.11 | 16.01 | 41.83 | 0 | 174.94 | 115.54 | 4.13 | 41.83 | 0 | 161.5 | 16.16 | 14
677 | SOUTH 24 PARAGANAS | SM/16759 | Ramnagar Abad Piped Water Supply Scheme. | TSM/003913 | 40059615 | New | MVS | GO2223015682PH | 13/03/2023 | 910.64 | 37.82 | 948.46 | Alipore Division | South 24 Pgs Mechanical Division | 232.88 | 4.06 | 9.55 | 0 | 246.5 | 158.82 | 4.06 | 9.55 | 0 | 172.44 | 18.18 | 30
678 | SOUTH 24 PARAGANAS | SM/15863 | RANIGACHI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018478 | 40053311 | Augmentation | MVS | GO2223014348PH | 20/02/2023 | 673.4 | 74.93 | 748.34 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 63.22 | 0 | 11.91 | 0 | 75.13 | 63.22 | 0 | 11.91 | 0 | 75.13 | 10.04 | 9
679 | SOUTH 24 PARAGANAS | SM/19199 | Repair & Replacement of Tubewells in Uttar Roypur, Nischintipur and Buita Water Supply Schemes for Supporting FHTC Drive in Budge Budge I Block under South 24 Pargana W/S Division-I PHE Dte. | TSM/022034 | 0 | Augmentation | MVS | GO2324017985PH | 15/03/2024 | 161.67 | 125.66 | 287.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
680 | SOUTH 24 PARAGANAS | SM/12884 | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | TSM/013413 | 40053497 | Augmentation | MVS | GO2223008153PH | 23/09/2022 | 143.8 | 35.66 | 179.46 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 69.71 | 21.32 | 0 | 0 | 91.04 | 69.71 | 21.32 | 0 | 0 | 91.04 | 50.73 | 45
681 | SOUTH 24 PARAGANAS | SM/18253 | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | TSM/014925 | 40036363 | Augmentation | MVS | 1564/PHE-28011/209/2022-ESTT CELL-Dept. of PHE | 16/06/2023 | 2480.06 | 347.74 | 2827.8 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 666.73 | 0 | 146.16 | 0 | 812.9 | 622.28 | 0 | 146.16 | 0 | 768.45 | 27.17 | 13
682 | SOUTH 24 PARAGANAS | SM/08800 | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007698 | 40007384 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 100.52 | 0 | 100.52 | Alipore Division |  | 0 | 0 | 16.99 | 0 | 16.99 | 0 | 0 | 16.99 | 0 | 16.99 | 16.9 | 6
683 | SOUTH 24 PARAGANAS | SM/08802 | Retrofitting for Providing FHTC at Ground Water Based Companir Char & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007694 | 40008675 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 57.2 | 0 | 57.2 | Alipore Division |  | 0 | 0 | 5.39 | 0 | 5.39 | 0 | 0 | 5.39 | 0 | 5.39 | 9.42 | 6
684 | SOUTH 24 PARAGANAS | SM/08804 | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007692 | 40008579 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 76.86 | 0 | 76.86 | Alipore Division |  | 55.06 | 0 | 18.95 | 0 | 74.02 | 55.06 | 0 | 18.95 | 0 | 74.02 | 96.31 | 6
685 | SOUTH 24 PARAGANAS | SM/08793 | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007690 | 40007328 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 66.55 | 0 | 66.55 | Alipore Division |  | 5 | 0 | 10.78 | 0 | 15.78 | 4.9 | 0 | 10.78 | 0 | 15.68 | 23.57 | 6
686 | SOUTH 24 PARAGANAS | SM/08801 | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007695 | 40008684 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 136.66 | 0 | 136.66 | Alipore Division |  | 10.43 | 0 | 24.87 | 0 | 35.3 | 10.43 | 0 | 24.87 | 0 | 35.3 | 25.83 | 6
687 | SOUTH 24 PARAGANAS | SM/08794 | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | TSM/007688 | 40007442 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 208.29 | 0 | 208.29 | Alipore Division |  | 23.5 | 0 | 33.81 | 0 | 57.32 | 23.5 | 0 | 33.81 | 0 | 57.32 | 27.52 | 6
688 | SOUTH 24 PARAGANAS | SM/08795 | Retrofitting for Providing FHTC at Ground Water Based Kamalpur Rudranagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007686 | 40007425 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 100.31 | 0 | 100.31 | Alipore Division |  | 14.85 | 0 | 17.19 | 0 | 32.05 | 14.85 | 0 | 17.19 | 0 | 32.05 | 31.95 | 6
689 | SOUTH 24 PARAGANAS | SM/08808 | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007691 | 40008531 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 50.16 | 0 | 50.16 | Alipore Division |  | 12.35 | 0 | 11.16 | 0 | 23.51 | 12.35 | 0 | 11.16 | 0 | 23.51 | 46.87 | 6
690 | SOUTH 24 PARAGANAS | SM/08803 | Retrofitting for Providing FHTC at Ground Water Based Krishnanagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007693 | 40008672 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 61.78 | 0 | 61.78 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
691 | SOUTH 24 PARAGANAS | SM/08805 | Retrofitting for Providing FHTC at Ground Water Based Mandirtala & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007689 | 40008573 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 121.55 | 0 | 121.55 | Alipore Division |  | 11.08 | 0 | 21.22 | 0 | 32.3 | 11.08 | 0 | 21.22 | 0 | 32.3 | 26.57 | 41
692 | SOUTH 24 PARAGANAS | SM/08807 | Retrofitting for Providing FHTC at Ground Water Based Mansadwip & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007696 | 40008535 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 78.11 | 0 | 78.11 | Alipore Division |  | 0 | 0 | 12.34 | 0 | 12.34 | 0 | 0 | 12.34 | 0 | 12.34 | 15.8 | 0
693 | SOUTH 24 PARAGANAS | SM/08810 | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007699 | 40007464 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 69.52 | 0 | 69.52 | Alipore Division |  | 5.17 | 0 | 0 | 0 | 5.17 | 5.17 | 0 | 0 | 0 | 5.17 | 7.44 | 6
694 | SOUTH 24 PARAGANAS | SM/08809 | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007687 | 40008523 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 58.39 | 0 | 58.39 | Alipore Division |  | 6.56 | 0 | 12.38 | 0 | 18.95 | 6.56 | 0 | 12.38 | 0 | 18.95 | 32.45 | 6
695 | SOUTH 24 PARAGANAS | SM/08792 | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | TSM/007697 | 40008817 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 69 | 0 | 69 | Alipore Division |  | 31.47 | 0 | 11.27 | 0 | 42.74 | 31.47 | 0 | 11.27 | 0 | 42.74 | 61.95 | 6
696 | SOUTH 24 PARAGANAS | SM/09467 | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) | TSM/008284 | 40013826 | Retrofitting | SVS | GO2122005584PH | 19/11/2021 | 44.84 | 0 | 44.84 | Alipore Division |  | 35.97 | 0 | 4.4 | 0 | 40.37 | 35.97 | 0 | 4.4 | 0 | 40.37 | 90.03 | 40
697 | SOUTH 24 PARAGANAS | SM/09468 | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) | TSM/008285 | 40049284 | Retrofitting | MVS | GO2122005584PH | 19/11/2021 | 85.95 | 0 | 85.95 | Alipore Division |  | 10.57 | 0 | 18.1 | 0 | 28.67 | 10.57 | 0 | 18.1 | 0 | 28.67 | 33.36 | 6
698 | SOUTH 24 PARAGANAS | SM/09464 | Retrofitting for Providing FHTC of Ground Water Based Kasinagar Water Supply Scheme (Phase - A) | TSM/008281 | 40049283 | Retrofitting | SVS | GO2122005584PH | 19/11/2021 | 67.56 | 0 | 67.56 | Alipore Division |  | 8.76 | 0 | 28.25 | 0 | 37.01 | 8.76 | 0 | 28.25 | 0 | 37.01 | 54.78 | 6
699 | SOUTH 24 PARAGANAS | SM/09465 | Retrofitting for Providing FHTC of Ground Water Based Nebutala Water Supply Scheme (Phase - A) | TSM/008282 | 40001245 | Retrofitting | MVS | GO2122005584PH | 19/11/2021 | 30.88 | 0 | 30.88 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
700 | SOUTH 24 PARAGANAS | SM/09466 | Retrofitting for Providing FHTC of Ground Water Based Ramchandranagar Water Supply Scheme (Phase - A) | TSM/008283 | 4334811 | Retrofitting | SVS | GO2122005584PH | 19/11/2021 | 60.25 | 0 | 60.25 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
701 | SOUTH 24 PARAGANAS | SM/07016 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:137 to 140 and Adjoining Areas under Budge Budge-I Block | TSM/006121 | 8136156 | Retrofitting | MVS | GO2021002655PH | 18/11/2020 | 98.72 | 0 | 98.72 | South 24 Pgs. W/S Division - I |  | 98.72 | 0 | 0 | 0 | 98.72 | 90.33 | 0 | 0 | 0 | 90.33 | 91.5 | 85
702 | SOUTH 24 PARAGANAS | SM/07017 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:141 to 144 and Adjoining Areas under Budge Budge-I Block | TSM/006119 | 8136172 | Retrofitting | MVS | GO2021002654PH | 18/11/2020 | 96.57 | 0 | 96.57 | South 24 Pgs. W/S Division - I |  | 96.57 | 0 | 0 | 0 | 96.57 | 91.31 | 0 | 0 | 0 | 91.31 | 94.55 | 90
703 | SOUTH 24 PARAGANAS | SM/07015 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:186 to 190 and 192 and 196 and Adjoining Areas under Budge Budge-I Block | TSM/006122 | 8136160 | Retrofitting | MVS | GO2021002656PH | 18/11/2020 | 95.42 | 0 | 95.42 | South 24 Pgs. W/S Division - I |  | 95.42 | 0 | 0 | 0 | 95.42 | 92.26 | 0 | 0 | 0 | 92.26 | 96.68 | 80
704 | SOUTH 24 PARAGANAS | SM/07014 | Retrofitting of distribution System For Buita W/S Scheme for Booth No:197 to 198 and Adjoining Areas under Budge Budge-I Block | TSM/006124 | 8136165 | Retrofitting | MVS | GO2021002657PH | 18/11/2020 | 28.3 | 0 | 28.3 | South 24 Pgs. W/S Division - I |  | 28.3 | 0 | 0 | 0 | 28.3 | 27.08 | 0 | 0 | 0 | 27.08 | 95.7 | 97
705 | SOUTH 24 PARAGANAS | SM/07056 | Retrofitting of distribution System For Jamalpur W/S Scheme for habitations of Jamalpur Mouza and adjoining areas under Budge Budge-I Block with allied works | TSM/006138 | 8136136 | Retrofitting | SVS | GO2021002752PH | 25/11/2020 | 82.14 | 0 | 82.14 | South 24 Pgs. W/S Division - I |  | 82.14 | 0 | 0 | 0 | 82.14 | 80.03 | 0 | 0 | 0 | 80.03 | 97.44 | 98
706 | SOUTH 24 PARAGANAS | SM/07055 | Retrofitting of distribution System For Moukhali W/S Scheme for Durgapur Moukhali and Jagatballavpur under Budge Budge-I Block with allied works | TSM/006131 | 8136142 | Retrofitting | MVS | GO2021002755PH | 25/11/2020 | 99.25 | 0 | 99.25 | South 24 Pgs. W/S Division - I |  | 99.25 | 0 | 0 | 0 | 99.25 | 91.45 | 0 | 0 | 0 | 91.45 | 92.14 | 95
707 | SOUTH 24 PARAGANAS | SM/07019 | Retrofitting of distribution System For Nandarampur W/S Scheme for Chak Nabashan Mouza and adjoining areas under Budge Budge-I Block | TSM/006139 | 8136188 | Retrofitting | MVS | GO2021002653PH | 18/11/2020 | 26.02 | 0 | 26.02 | South 24 Pgs. W/S Division - I |  | 26.02 | 0 | 0 | 0 | 26.02 | 24.42 | 0 | 0 | 0 | 24.42 | 93.84 | 97
708 | SOUTH 24 PARAGANAS | SM/07020 | Retrofitting of distribution System For Nandarampur W/S Scheme for Booth No:170 and Adjoining Areas under Budge Budge-I Block | TSM/006127 | 8136177 | Retrofitting | MVS | GO2021002652PH | 18/11/2020 | 94.56 | 0 | 94.56 | South 24 Pgs. W/S Division - I |  | 94.56 | 0 | 0 | 0 | 94.56 | 94.56 | 0 | 0 | 0 | 94.56 | 100 | 100
709 | SOUTH 24 PARAGANAS | SM/07018 | Retrofitting of distribution System For Nischintipur W/S Scheme for Nischintipur Mouza near Head Work Site and Adjoining Areas under Budge Budge-I Block | TSM/006129 | 8136123 | Retrofitting | SVS | GO2021002658PH | 18/11/2020 | 94.23 | 0 | 94.23 | South 24 Pgs. W/S Division - I |  | 94.23 | 0 | 0 | 0 | 94.23 | 80.02 | 0 | 0 | 0 | 80.02 | 84.92 | 97
710 | SOUTH 24 PARAGANAS | SM/08634 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (one) no. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gangacheri Water Supply Scheme including one yea | TSM/007264 | 7940737 | Retrofitting | SVS | GO2122000854PH | 27/05/2021 | 38.38 | 0 | 38.38 | Alipore Division |  | 35.15 | 0 | 0 | 0 | 35.15 | 35.15 | 0 | 0 | 0 | 35.15 | 91.58 | 78
711 | SOUTH 24 PARAGANAS | SM/09359 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (One) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme including one year | TSM/008689 | 40001251 | Retrofitting | SVS | GO2122005380PH | 12/11/2021 | 87.59 | 0 | 87.59 | Alipore Division |  | 53.81 | 0 | 0 | 0 | 53.81 | 53.81 | 0 | 0 | 0 | 53.81 | 61.43 | 71
712 | SOUTH 24 PARAGANAS | SM/09361 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur Water Supply Scheme including one year | TSM/008687 | 8198217 | Retrofitting | SVS | GO2122005380PH | 12/11/2021 | 101.2 | 0 | 101.2 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
713 | SOUTH 24 PARAGANAS | SM/09016 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S | TSM/007274 | 7755686 | Retrofitting | MVS | GO2122000827PH | 26/05/2021 | 86.12 | 0 | 86.12 | Alipore Division |  | 79.5 | 0 | 0 | 0 | 79.5 | 79.5 | 0 | 0 | 0 | 79.5 | 92.31 | 100
714 | SOUTH 24 PARAGANAS | SM/07593 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ananda Abad Water Supply S | TSM/006865 | 7756977 | Retrofitting | MVS | GO2021003941PH | 31/12/2020 | 65.34 | 0 | 65.34 | Alipore Division |  | 61.04 | 0 | 0 | 0 | 61.04 | 61.04 | 0 | 0 | 0 | 61.04 | 93.42 | 100
715 | SOUTH 24 PARAGANAS | SM/09012 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 03 (three) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhuri Water Supply Scheme including one year | TSM/007262 | 7391291 | Retrofitting | SVS | GO2122000855PH | 27/05/2021 | 96.07 | 0 | 96.07 | Alipore Division |  | 0 | 0 | 17.89 | 0 | 17.89 | 0 | 0 | 17.89 | 0 | 17.89 | 18.63 | 7
716 | SOUTH 24 PARAGANAS | SM/07627 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 04 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lot-126 Water Supply Sche | TSM/006872 | 7773669 | Retrofitting | SVS | GO2021004178PH | 07/01/2021 | 204.47 | 0 | 204.47 | Alipore Division |  | 192.23 | 0 | 0 | 0 | 192.23 | 192.23 | 0 | 0 | 0 | 192.23 | 94.01 | 100
717 | SOUTH 24 PARAGANAS | SM/09395 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one | TSM/008691 | 40004891 | Retrofitting | SVS | GO2122005504PH | 17/11/2021 | 213.05 | 0 | 213.05 | Alipore Division |  | 0 | 0 | 36.92 | 0 | 36.92 | 0 | 0 | 36.92 | 0 | 36.92 | 17.33 | 0
718 | SOUTH 24 PARAGANAS | SM/09360 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including | TSM/008688 | 40004811 | Retrofitting | SVS | GO2122005380PH | 12/11/2021 | 123.14 | 0 | 123.14 | Alipore Division |  | 80.22 | 0 | 4.51 | 0 | 84.73 | 50.89 | 0 | 4.51 | 0 | 55.4 | 44.99 | 61
719 | SOUTH 24 PARAGANAS | SM/09097 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one y | TSM/008594 | 7750540 | Retrofitting | MVS | GO2122004657PH | 29/10/2021 | 119.6 | 0 | 119.6 | Alipore Division |  | 104.98 | 0 | 0 | 0 | 104.98 | 104.98 | 0 | 0 | 0 | 104.98 | 87.77 | 72
720 | SOUTH 24 PARAGANAS | SM/08637 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year | TSM/007256 | 7751587 | Retrofitting | MVS | GO2122000861PH | 27/05/2021 | 157.43 | 0 | 157.43 | Alipore Division |  | 109.55 | 0 | 0 | 0 | 109.55 | 145.52 | 0 | 0 | 0 | 145.52 | 92.43 | 53
721 | SOUTH 24 PARAGANAS | SM/07643 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jyotishpur Water Supply S | TSM/006899 | 7756906 | Retrofitting | MVS | GO2021004145PH | 07/01/2021 | 117.77 | 0 | 117.77 | Alipore Division |  | 86.25 | 0 | 0 | 0 | 86.25 | 86.25 | 0 | 0 | 0 | 86.25 | 73.24 | 88
722 | SOUTH 24 PARAGANAS | SM/08028 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bansra Water Supply Scheme | TSM/006867 | 7402374 | Retrofitting | SVS | GO2021005809PH | 29/01/2021 | 352.06 | 0 | 352.06 | Alipore Division |  | 208.81 | 0 | 0 | 0 | 208.81 | 208.81 | 0 | 0 | 0 | 208.81 | 59.31 | 63
723 | SOUTH 24 PARAGANAS | SM/07644 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Goran Bose Water Supply Sc | TSM/006896 | 7572737 | Retrofitting | SVS | GO2021004152PH | 07/01/2021 | 147.9 | 0 | 147.9 | Alipore Division |  | 48.67 | 0 | 0 | 0 | 48.67 | 48.17 | 0 | 0 | 0 | 48.17 | 32.57 | 62
724 | SOUTH 24 PARAGANAS | SM/07595 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Luxbagan Water Supply Sche | TSM/006906 | 7756914 | Retrofitting | SVS | GO2021003950PH | 31/12/2020 | 72.33 | 0 | 72.33 | Alipore Division |  | 70.23 | 0 | 0 | 0 | 70.23 | 70.23 | 0 | 0 | 0 | 70.23 | 97.09 | 73
725 | SOUTH 24 PARAGANAS | SM/07592 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar Water Supply Sche | TSM/006875 | 8200028 | Retrofitting | MVS | GO2021003948PH | 31/12/2020 | 95.32 | 0 | 95.32 | Alipore Division |  | 92.55 | 0 | 0 | 0 | 92.55 | 92.55 | 0 | 0 | 0 | 92.55 | 97.09 | 88
726 | SOUTH 24 PARAGANAS | SM/09393 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | TSM/008693 | 40004820 | Retrofitting | SVS | GO2122005504PH | 17/11/2021 | 270.16 | 0 | 270.16 | Alipore Division |  | 91.76 | 0 | 13.23 | 0 | 105 | 91.76 | 0 | 6.19 | 0 | 97.96 | 36.26 | 86
727 | SOUTH 24 PARAGANAS | SM/09013 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hiranmoypur Water Supply Scheme including one | TSM/007270 | 7940620 | Retrofitting | MVS | GO2122000806PH | 26/05/2021 | 193.76 | 0 | 193.76 | Alipore Division |  | 169.26 | 0 | 0 | 0 | 169.26 | 169.26 | 0 | 0 | 0 | 169.26 | 87.36 | 84
728 | SOUTH 24 PARAGANAS | SM/07638 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Makhaltala Water Supply | TSM/006907 | 7327705 | Retrofitting | SVS | GO2021004156PH | 07/01/2021 | 129.74 | 0 | 129.74 | Alipore Division |  | 121.22 | 0 | 0 | 0 | 121.22 | 121.22 | 0 | 0 | 0 | 121.22 | 93.44 | 80
729 | SOUTH 24 PARAGANAS | SM/09094 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y | TSM/008628 | 7402367 | Retrofitting | SVS | GO2122004657PH | 29/10/2021 | 95.53 | 0 | 95.53 | Alipore Division |  | 79.11 | 0 | 0 | 0 | 79.11 | 79.11 | 0 | 0 | 0 | 79.11 | 82.81 | 74
730 | SOUTH 24 PARAGANAS | SM/09015 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayangarh Water Supply Scheme including one | TSM/007273 | 7750440 | Retrofitting | MVS | GO2122000828PH | 26/05/2021 | 63.53 | 0 | 63.53 | Alipore Division |  | 60 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 94.45 | 100
731 | SOUTH 24 PARAGANAS | SM/09014 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year | TSM/007272 | 7402343 | Retrofitting | MVS | GO2122000829PH | 27/05/2021 | 82.73 | 0 | 82.73 | Alipore Division |  | 30.59 | 0 | 0 | 0 | 30.59 | 30.59 | 0 | 0 | 0 | 30.59 | 36.97 | 41
732 | SOUTH 24 PARAGANAS | SM/07598 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bhaleya Water Supply Sch | TSM/006877 | 7402340 | Retrofitting | MVS | GO2021003949PH | 31/12/2020 | 92.37 | 0 | 92.37 | Alipore Division |  | 74.66 | 0 | 0 | 0 | 74.66 | 74.66 | 0 | 0 | 0 | 74.66 | 80.83 | 82
733 | SOUTH 24 PARAGANAS | SM/08635 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | TSM/007266 | 7940833 | Retrofitting | MVS | GO2122000853PH | 27/05/2021 | 124.75 | 0 | 124.75 | Alipore Division |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 16 | 16 | 12.83 | 15
734 | SOUTH 24 PARAGANAS | SM/09010 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | TSM/007258 | 40006463 | Retrofitting | SVS | GO2122000860PH | 27/05/2021 | 102.43 | 0 | 102.43 | Alipore Division |  | 82.73 | 0 | 0 | 17.12 | 99.84 | 82.73 | 0 | 0 | 17.12 | 99.84 | 97.48 | 73
735 | SOUTH 24 PARAGANAS | SM/07763 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Lahiripur Water Supply Sc | TSM/006905 | 7750455 | Retrofitting | SVS | GO2021004318PH | 08/01/2021 | 119.81 | 0 | 119.81 | Alipore Division |  | 115.42 | 0 | 0 | 0 | 115.42 | 115.42 | 0 | 0 | 0 | 115.42 | 96.34 | 97
736 | SOUTH 24 PARAGANAS | SM/09358 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | TSM/008690 | 40004903 | Retrofitting | MVS | GO2122005380PH | 12/11/2021 | 383.9 | 0 | 383.9 | Alipore Division |  | 130.65 | 0 | 20.57 | 0 | 151.22 | 130.65 | 0 | 20.57 | 0 | 151.22 | 39.39 | 95
737 | SOUTH 24 PARAGANAS | SM/09096 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daharani Water Supply Scheme including one year | TSM/008644 | 7714398 | Retrofitting | MVS | GO2122004657PH | 29/10/2021 | 165.49 | 0 | 165.49 | Alipore Division |  | 64.46 | 0 | 9.23 | 0 | 73.69 | 64.46 | 0 | 9.23 | 0 | 73.69 | 44.53 | 73
738 | SOUTH 24 PARAGANAS | SM/09394 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sumatinagar Water Supply Scheme including one y | TSM/008692 | 40014909 | Retrofitting | MVS | GO2122005504PH | 17/11/2021 | 246.56 | 0 | 246.56 | Alipore Division |  | 0 | 0 | 8.93 | 0 | 8.93 | 0 | 0 | 8.93 | 0 | 8.93 | 3.62 | 0
739 | SOUTH 24 PARAGANAS | SM/09509 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | TSM/008289 | 40008795 | Retrofitting | MVS | GO2122005580PH | 19/11/2021 | 261.42 | 0 | 261.42 | Alipore Division |  | 51.28 | 0 | 0 | 0 | 51.28 | 32.69 | 0 | 0 | 0 | 32.69 | 12.51 | 57
740 | SOUTH 24 PARAGANAS | SM/07631 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalaria Water Supply Schem | TSM/006871 | 8200069 | Retrofitting | MVS | GO2021004176PH | 07/01/2021 | 214.03 | 0 | 214.03 | Alipore Division |  | 87.52 | 0 | 0 | 1.43 | 88.96 | 87.52 | 0 | 0 | 1.43 | 88.96 | 41.56 | 47
741 | SOUTH 24 PARAGANAS | SM/07632 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayanpur Water Supply Sc | TSM/006874 | 7327723 | Retrofitting | SVS | GO2021004185PH | 07/01/2021 | 126.68 | 0 | 126.68 | Alipore Division |  | 87.49 | 0 | 0 | 0 | 87.49 | 87.49 | 0 | 0 | 0 | 87.49 | 69.06 | 75
742 | SOUTH 24 PARAGANAS | SM/09098 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one | TSM/008646 | 7755634 | Retrofitting | MVS | GO2122004657PH | 29/10/2021 | 125.76 | 0 | 125.76 | Alipore Division |  | 84.56 | 0 | 0 | 0 | 84.56 | 84.56 | 0 | 0 | 0 | 84.56 | 67.24 | 72
743 | SOUTH 24 PARAGANAS | SM/09008 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Amlamethi Water Supply Scheme including one y | TSM/007253 | 7773610 | Retrofitting | MVS | GO2122000808PH | 26/05/2021 | 212.32 | 0 | 212.32 | Alipore Division |  | 175.39 | 0 | 30.75 | 0 | 206.14 | 175.39 | 0 | 30.75 | 0 | 206.14 | 97.09 | 81
744 | SOUTH 24 PARAGANAS | SM/07642 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bharatgarh Water Supply | TSM/006878 | 7402298 | Retrofitting | MVS | GO2021004148PH | 07/01/2021 | 117.22 | 0 | 117.22 | Alipore Division |  | 107.69 | 0 | 0 | 0 | 107.69 | 107.36 | 0 | 0 | 0 | 107.36 | 91.59 | 98
745 | SOUTH 24 PARAGANAS | SM/07637 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Uttar Angadberia Water | TSM/006913 | 7402363 | Retrofitting | MVS | GO2021004157PH | 07/01/2021 | 114.83 | 0 | 114.83 | Alipore Division |  | 78.13 | 0 | 0 | 0 | 78.13 | 78.13 | 0 | 0 | 0 | 78.13 | 68.04 | 85
746 | SOUTH 24 PARAGANAS | SM/09007 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | TSM/007275 | 7940609 | Retrofitting | MVS | GO2122000826PH | 26/05/2021 | 220.12 | 0 | 220.12 | Alipore Division |  | 10 | 0 | 59.04 | 17.28 | 86.32 | 5.54 | 0 | 59.04 | 17.28 | 81.86 | 37.19 | 13
747 | SOUTH 24 PARAGANAS | SM/07634 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Banibadabelekhali Wat | TSM/006866 | 6854898 | Retrofitting | MVS | GO2021004166PH | 07/01/2021 | 175.16 | 0 | 175.16 | Alipore Division |  | 158.68 | 0 | 0 | 0 | 158.68 | 158.68 | 0 | 0 | 0 | 158.68 | 90.59 | 85
748 | SOUTH 24 PARAGANAS | SM/07628 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Sch | TSM/006870 | 7327778 | Retrofitting | MVS | GO2021004173PH | 07/01/2021 | 169.04 | 0 | 169.04 | Alipore Division |  | 158.72 | 0 | 5.4 | 0 | 164.11 | 158.72 | 0 | 5.4 | 0 | 164.11 | 97.09 | 79
749 | SOUTH 24 PARAGANAS | SM/09095 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | TSM/008684 | 40008764 | Retrofitting | MVS | GO2122004657PH | 29/10/2021 | 261.46 | 0 | 261.46 | Alipore Division |  | 244.47 | 0 | 9.23 | 0 | 253.69 | 244.47 | 0 | 9.23 | 0 | 253.69 | 97.03 | 71
750 | SOUTH 24 PARAGANAS | SM/09009 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 17 (seventeen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandrakhali Water Supply Scheme inclu | TSM/007255 | 7940589 | Retrofitting | MVS | GO2122000807PH | 26/05/2021 | 232.94 | 0 | 232.94 | Alipore Division |  | 151.55 | 0 | 0 | 0 | 151.55 | 151.55 | 0 | 0 | 0 | 151.55 | 65.06 | 39
751 | SOUTH 24 PARAGANAS | SM/07639 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Moukhali Water Suppl | TSM/006908 | 8200064 | Retrofitting | MVS | GO2021004155PH | 07/01/2021 | 217.52 | 0 | 217.52 | Alipore Division |  | 117.75 | 0 | 0 | 0 | 117.75 | 89.5 | 0 | 0 | 0 | 89.5 | 41.14 | 70
752 | SOUTH 24 PARAGANAS | SM/07762 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bijoynagar Water Supp | TSM/006879 | 8200071 | Retrofitting | MVS | GO2021004316PH | 08/01/2021 | 280.36 | 0 | 280.36 | Alipore Division |  | 261.1 | 0 | 0 | 0 | 261.1 | 258.54 | 0 | 0 | 0 | 258.54 | 92.22 | 87
753 | SOUTH 24 PARAGANAS | SM/07641 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Suppl | TSM/006880 | 7571769 | Retrofitting | MVS | GO2021004150PH | 07/01/2021 | 207.07 | 0 | 207.07 | Alipore Division |  | 152.47 | 0 | 0 | 0 | 152.47 | 151.85 | 0 | 0 | 0 | 151.85 | 73.33 | 74
754 | SOUTH 24 PARAGANAS | SM/07630 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone-II) | TSM/006868 | 8200067 | Retrofitting | MVS | GO2021004169PH | 07/01/2021 | 170.64 | 0 | 170.64 | Alipore Division |  | 124.82 | 0 | 0 | 0 | 124.82 | 124.82 | 0 | 0 | 0 | 124.82 | 73.15 | 78
755 | SOUTH 24 PARAGANAS | SM/07633 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagartala Water Suppl | TSM/006873 | 8200070 | Retrofitting | MVS | GO2021004183PH | 07/01/2021 | 241.76 | 0 | 241.76 | Alipore Division |  | 163.67 | 0 | 0 | 0 | 163.67 | 163.67 | 0 | 0 | 0 | 163.67 | 67.7 | 63
756 | SOUTH 24 PARAGANAS | SM/09011 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including o | TSM/007260 | 7940550 | Retrofitting | MVS | GO2122000859PH | 27/05/2021 | 178.14 | 0 | 178.14 | Alipore Division |  | 80.9 | 0 | 0 | 0 | 80.9 | 0 | 0 | 0 | 0 | 0 | 0 | 21
757 | SOUTH 24 PARAGANAS | SM/08636 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one | TSM/007268 | 7755731 | Retrofitting | MVS | GO2122000921PH | 31/05/2021 | 134.28 | 0 | 134.28 | Alipore Division |  | 129.48 | 0 | 0 | 0 | 129.48 | 129.48 | 0 | 0 | 0 | 129.48 | 96.43 | 87
758 | SOUTH 24 PARAGANAS | SM/09017 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year | TSM/007276 | 7940582 | Retrofitting | MVS | GO2122000771PH | 26/05/2021 | 287.5 | 0 | 287.5 | Alipore Division |  | 247.41 | 0 | 29.69 | 0 | 277.1 | 247.41 | 0 | 29.69 | 0 | 277.1 | 96.38 | 58
759 | SOUTH 24 PARAGANAS | SM/07596 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Adhia Water Supply Sche | TSM/006876 | 8191825 | Retrofitting | MVS | GO2021003926PH | 31/12/2020 | 92.66 | 0 | 92.66 | Alipore Division |  | 50 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 50 | 53.96 | 76
760 | SOUTH 24 PARAGANAS | SM/07640 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dharmatala Water Supply | TSM/006895 | 8200059 | Retrofitting | MVS | GO2021004153PH | 07/01/2021 | 275.12 | 0 | 275.12 | Alipore Division |  | 206.43 | 0 | 0 | 14.89 | 221.32 | 206.43 | 0 | 0 | 14.89 | 221.32 | 80.45 | 76
761 | SOUTH 24 PARAGANAS | SM/07629 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 21 (twenty one) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Rendokhali | TSM/006869 | 8200068 | Retrofitting | MVS | GO2021004171PH | 07/01/2021 | 272.76 | 0 | 272.76 | Alipore Division |  | 172.32 | 0 | 0 | 0 | 172.32 | 167.61 | 0 | 0 | 0 | 167.61 | 61.45 | 56
762 | SOUTH 24 PARAGANAS | SM/07597 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Puinjali Water Supply Sche | TSM/006909 | 7751580 | Retrofitting | SVS | GO2021003951PH | 31/12/2020 | 87.3 | 0 | 87.3 | Alipore Division |  | 65 | 0 | 0 | 0 | 65 | 17.92 | 0 | 0 | 0 | 17.92 | 20.53 | 73
763 | SOUTH 24 PARAGANAS | SM/07594 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Singheswar Water Supply S | TSM/006910 | 7571786 | Retrofitting | MVS | GO2021003952PH | 31/12/2020 | 72.82 | 0 | 72.82 | Alipore Division |  | 64.86 | 0 | 0 | 0 | 64.86 | 64.86 | 0 | 0 | 0 | 64.86 | 89.06 | 87
764 | SOUTH 24 PARAGANAS | SM/09973 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-I including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divis | TSM/009195 | 5344170 | Retrofitting | MVS | GO2122006875PH | 15/12/2021 | 197.83 | 0 | 197.83 | Alipore Division |  | 0 | 0 | 20.59 | 0 | 20.59 | 0 | 0 | 20.59 | 0 | 20.59 | 10.41 | 35
765 | SOUTH 24 PARAGANAS | SM/09974 | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | TSM/009222 | 5344170 | Retrofitting | MVS | GO2122006875PH | 15/12/2021 | 164.33 | 0 | 164.33 | Alipore Division |  | 0 | 0 | 16.91 | 0 | 16.91 | 0 | 0 | 16.91 | 0 | 16.91 | 10.29 | 30
766 | SOUTH 24 PARAGANAS | SM/09076 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including | TSM/008428 | 40001945 | Retrofitting | SVS | GO2122004658PH | 29/10/2021 | 120.65 | 0 | 120.65 | Alipore Division |  | 71.55 | 0 | 0 | 0 | 71.55 | 71.55 | 0 | 0 | 0 | 71.55 | 59.31 | 81
767 | SOUTH 24 PARAGANAS | SM/09077 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | TSM/008429 | 40001969 | Retrofitting | MVS | GO2122004658PH | 29/10/2021 | 154.41 | 0 | 154.41 | Alipore Division |  | 80 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 80 | 51.81 | 95
768 | SOUTH 24 PARAGANAS | SM/09075 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | TSM/008340 | 40001951 | Retrofitting | MVS | GO2122004658PH | 29/10/2021 | 125.25 | 0 | 125.25 | Alipore Division |  | 36.93 | 0 | 17.96 | 0 | 54.89 | 26.93 | 0 | 17.96 | 0 | 44.89 | 35.84 | 66
769 | SOUTH 24 PARAGANAS | SM/09470 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | TSM/008287 | 8390881 | Retrofitting | MVS | GO2122005584PH | 19/11/2021 | 107.52 | 0 | 107.52 | Alipore Division |  | 51.18 | 0 | 0 | 0 | 51.18 | 51.18 | 0 | 0 | 0 | 51.18 | 47.6 | 80
770 | SOUTH 24 PARAGANAS | SM/07410 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 08 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme incl | TSM/006803 | 8198037 | Retrofitting | SVS | GO2021003704PH | 29/12/2020 | 49.5 | 0 | 49.5 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82
771 | SOUTH 24 PARAGANAS | SM/07635 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 09 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taktipur Abad W/S Scheme incl | TSM/006912 | 8200066 | Retrofitting | SVS | GO2021004160PH | 07/01/2021 | 124.87 | 0 | 124.87 | Alipore Division |  | 53.02 | 0 | 0 | 0 | 53.02 | 51.84 | 0 | 0 | 0 | 51.84 | 41.51 | 76
772 | SOUTH 24 PARAGANAS | SM/07402 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kusumtala W/S Scheme includ | TSM/006800 | 7773468 | Retrofitting | SVS | GO2021003703PH | 29/12/2020 | 92.72 | 0 | 92.72 | Alipore Division |  | 90.02 | 0 | 0 | 0 | 90.02 | 83.7 | 0 | 0 | 0 | 83.7 | 90.27 | 100
773 | SOUTH 24 PARAGANAS | SM/07754 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mrityunjoynagar W/S Scheme | TSM/006802 | 7394380 | Retrofitting | MVS | GO2021004326PH | 08/01/2021 | 150.06 | 0 | 150.06 | Alipore Division |  | 74.21 | 0 | 0 | 0 | 74.21 | 74.21 | 0 | 0 | 0 | 74.21 | 49.45 | 95
774 | SOUTH 24 PARAGANAS | SM/07409 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 11 (eleven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nagendraganj W/S Scheme inc | TSM/006849 | 8197974 | Retrofitting | MVS | GO2021003701PH | 29/12/2020 | 75.22 | 0 | 75.22 | Alipore Division |  | 40.98 | 0 | 0 | 0 | 40.98 | 33.9 | 0 | 0 | 0 | 33.9 | 45.07 | 89
775 | SOUTH 24 PARAGANAS | SM/09469 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | TSM/008286 | 8390879 | Retrofitting | MVS | GO2122005584PH | 19/11/2021 | 148.34 | 0 | 148.34 | Alipore Division |  | 55.2 | 0 | 14.15 | 0 | 69.35 | 54.2 | 0 | 14.15 | 0 | 68.35 | 46.08 | 80
776 | SOUTH 24 PARAGANAS | SM/07761 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 13 (thirteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Gangadharpur W/S | TSM/006893 | 8200072 | Retrofitting | MVS | GO2021004319PH | 08/01/2021 | 185.64 | 0 | 185.64 | Alipore Division |  | 181.03 | 0 | 0 | 0 | 181.03 | 159.14 | 0 | 0 | 0 | 159.14 | 85.72 | 85
777 | SOUTH 24 PARAGANAS | SM/07760 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl | TSM/006898 | 8200073 | Retrofitting | MVS | GO2021004323PH | 08/01/2021 | 264.49 | 0 | 264.49 | Alipore Division |  | 49.95 | 0 | 23.82 | 0 | 73.77 | 49.95 | 0 | 23.82 | 0 | 73.77 | 27.89 | 57
778 | SOUTH 24 PARAGANAS | SM/07412 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S | TSM/006806 | 8198396 | Retrofitting | MVS | GO2021003708PH | 29/12/2020 | 82.69 | 0 | 82.69 | Alipore Division |  | 68.8 | 0 | 0 | 0 | 68.8 | 68.8 | 0 | 0 | 0 | 68.8 | 83.2 | 95
779 | SOUTH 24 PARAGANAS | SM/07415 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-II) W/S | TSM/006808 | 8198481 | Retrofitting | MVS | GO2021003711PH | 29/12/2020 | 96.04 | 0 | 96.04 | Alipore Division |  | 89.28 | 0 | 0 | 0 | 89.28 | 59.28 | 0 | 0 | 0 | 59.28 | 61.72 | 71
780 | SOUTH 24 PARAGANAS | SM/09471 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | TSM/008288 | 40001915 | Retrofitting | MVS | GO2122005584PH | 19/11/2021 | 162.44 | 0 | 162.44 | Alipore Division |  | 18.06 | 0 | 0 | 0 | 18.06 | 18.06 | 0 | 0 | 0 | 18.06 | 11.12 | 20
781 | SOUTH 24 PARAGANAS | SM/07411 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-I) W/S S | TSM/006805 | 8198353 | Retrofitting | MVS | GO2021003707PH | 29/12/2020 | 92.29 | 0 | 92.29 | Alipore Division |  | 79.54 | 0 | 0 | 0 | 79.54 | 79.54 | 0 | 0 | 0 | 79.54 | 86.18 | 91
782 | SOUTH 24 PARAGANAS | SM/07414 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 19 (nineteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhakhali (Zone-II) W/S | TSM/006807 | 8198445 | Retrofitting | MVS | GO2021003710PH | 29/12/2020 | 99.77 | 0 | 99.77 | Alipore Division |  | 83.02 | 0 | 0 | 0 | 83.02 | 83.02 | 0 | 0 | 0 | 83.02 | 83.21 | 80
783 | SOUTH 24 PARAGANAS | SM/07403 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | TSM/006812 | 8199962 | Retrofitting | SVS | GO2021003713PH | 29/12/2020 | 75.56 | 0 | 75.56 | Alipore Division |  | 31.17 | 0 | 0 | 0 | 31.17 | 31.17 | 0 | 0 | 0 | 31.17 | 41.25 | 92
784 | SOUTH 24 PARAGANAS | SM/07405 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhablat W/S Scheme including on | TSM/006813 | 8199964 | Retrofitting | SVS | GO2021003714PH | 29/12/2020 | 71.63 | 0 | 71.63 | Alipore Division |  | 35.69 | 0 | 0 | 0 | 35.69 | 35.69 | 0 | 0 | 0 | 35.69 | 49.83 | 91
785 | SOUTH 24 PARAGANAS | SM/07407 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme including | TSM/006853 | 7940666 | Retrofitting | SVS | GO2021003697PH | 29/12/2020 | 56.09 | 0 | 56.09 | Alipore Division |  | 23.33 | 0 | 0 | 0 | 23.33 | 23.33 | 0 | 0 | 0 | 23.33 | 41.6 | 100
786 | SOUTH 24 PARAGANAS | SM/07416 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 2 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | TSM/006804 | 8198217 | Retrofitting | SVS | GO2021003705PH | 29/12/2020 | 69.83 | 0 | 69.83 | Alipore Division |  | 5.65 | 0 | 0 | 0 | 5.65 | 5.65 | 0 | 0 | 0 | 5.65 | 8.09 | 91
787 | SOUTH 24 PARAGANAS | SM/07626 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 20 (twenty) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinarayanpur W/S Scheme in | TSM/006864 | 7573196 | Retrofitting | SVS | GO2021004163PH | 07/01/2021 | 225.98 | 0 | 225.98 | Alipore Division |  | 150.09 | 0 | 18.94 | 0 | 169.03 | 150.09 | 0 | 18.94 | 0 | 169.03 | 74.8 | 86
788 | SOUTH 24 PARAGANAS | SM/07584 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | TSM/006838 | 7394385 | Retrofitting | MVS | GO2021003934PH | 31/12/2020 | 80.41 | 0 | 80.41 | Alipore Division |  | 80.41 | 0 | 0 | 0 | 80.41 | 80.41 | 0 | 0 | 0 | 80.41 | 100 | 97
789 | SOUTH 24 PARAGANAS | SM/07587 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mahishamari W/S Scheme includ | TSM/006839 | 7394385 | Retrofitting | SVS | GO2021003935PH | 31/12/2020 | 79.53 | 0 | 79.53 | Alipore Division |  | 31.88 | 0 | 6.61 | 0 | 38.49 | 31.88 | 0 | 0 | 0 | 31.88 | 40.09 | 96
790 | SOUTH 24 PARAGANAS | SM/07588 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Manasadwip W/S Scheme includi | TSM/006840 | 8199996 | Retrofitting | SVS | GO2021003936PH | 31/12/2020 | 91.66 | 0 | 91.66 | Alipore Division |  | 30.03 | 0 | 0 | 0 | 30.03 | 30.03 | 0 | 0 | 0 | 30.03 | 32.76 | 100
791 | SOUTH 24 PARAGANAS | SM/07406 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rakhalpur W/S Scheme includin | TSM/006852 | 7940666 | Retrofitting | SVS | GO2021003698PH | 29/12/2020 | 75.91 | 0 | 75.91 | Alipore Division |  | 74.33 | 0 | 0 | 0 | 74.33 | 74.33 | 0 | 0 | 0 | 74.33 | 97.91 | 100
792 | SOUTH 24 PARAGANAS | SM/07413 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 3 (three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including | TSM/006858 | 8197426 | Retrofitting | SVS | GO2021003691PH | 29/12/2020 | 82.02 | 0 | 82.02 | Alipore Division |  | 21.03 | 0 | 12.15 | 0 | 33.18 | 21.03 | 0 | 12.15 | 0 | 33.18 | 40.46 | 95
793 | SOUTH 24 PARAGANAS | SM/07757 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chemaguri W/S Scheme including | TSM/006810 | 7757017 | Retrofitting | SVS | GO2021004330PH | 08/01/2021 | 135.9 | 0 | 135.9 | Alipore Division |  | 40.77 | 0 | 0 | 0 | 40.77 | 40.77 | 0 | 0 | 0 | 40.77 | 30 | 99
794 | SOUTH 24 PARAGANAS | SM/07749 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dakshin Shibganj W/S Scheme in | TSM/006811 | 8217830 | Retrofitting | SVS | GO2021004331PH | 08/01/2021 | 108.22 | 0 | 108.22 | Alipore Division |  | 41.15 | 0 | 0 | 0 | 41.15 | 39.3 | 0 | 0 | 0 | 39.3 | 36.32 | 96
795 | SOUTH 24 PARAGANAS | SM/07756 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | TSM/006836 | 8342762 | Retrofitting | SVS | GO2021004332PH | 08/01/2021 | 136.4 | 0 | 136.4 | Alipore Division |  | 50.23 | 0 | 0 | 0 | 50.23 | 27.85 | 0 | 0 | 0 | 27.85 | 20.42 | 77
796 | SOUTH 24 PARAGANAS | SM/07758 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Manasadwip W/S Scheme includin | TSM/006801 | 8200074 | Retrofitting | SVS | GO2021004324PH | 08/01/2021 | 100.03 | 0 | 100.03 | Alipore Division |  | 100.03 | 0 | 0 | 0 | 100.03 | 100.03 | 0 | 0 | 0 | 100.03 | 100 | 100
797 | SOUTH 24 PARAGANAS | SM/07759 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | TSM/006850 | 7573225 | Retrofitting | SVS | GO2021004340PH | 08/01/2021 | 101.4 | 0 | 101.4 | Alipore Division |  | 74.43 | 0 | 0 | 0 | 74.43 | 74.22 | 0 | 0 | 0 | 74.22 | 73.2 | 100
798 | SOUTH 24 PARAGANAS | SM/07399 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme inclu | TSM/006857 | 7749781 | Retrofitting | SVS | GO2021003692PH | 29/12/2020 | 58.55 | 0 | 58.55 | Alipore Division |  | 30 | 0 | 0 | 0 | 30 | 18.63 | 0 | 0 | 0 | 18.63 | 31.82 | 91
799 | SOUTH 24 PARAGANAS | SM/07589 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | TSM/006861 | 8200012 | Retrofitting | SVS | GO2021003944PH | 31/12/2020 | 43.41 | 0 | 43.41 | Alipore Division |  | 18.63 | 0 | 0 | 0 | 18.63 | 18.63 | 0 | 0 | 0 | 18.63 | 42.92 | 96
800 | SOUTH 24 PARAGANAS | SM/07580 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | TSM/006379 | 8199999 | Retrofitting | SVS | GO2021003939PH | 31/12/2020 | 58.99 | 0 | 58.99 | Alipore Division |  | 35.88 | 0 | 0 | 0 | 35.88 | 35.88 | 0 | 0 | 0 | 35.88 | 60.83 | 76
801 | SOUTH 24 PARAGANAS | SM/07398 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | TSM/006809 | 8199958 | Retrofitting | SVS | GO2021003712PH | 29/12/2020 | 59.32 | 0 | 59.32 | Alipore Division |  | 34.73 | 0 | 0 | 0 | 34.73 | 34.73 | 0 | 0 | 0 | 34.73 | 58.54 | 80
802 | SOUTH 24 PARAGANAS | SM/07585 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ | TSM/006816 | 7749768 | Retrofitting | SVS | GO2021003930PH | 31/12/2020 | 61.06 | 0 | 61.06 | Alipore Division |  | 53.84 | 0 | 0 | 0 | 53.84 | 53.84 | 0 | 0 | 0 | 53.84 | 88.17 | 76
803 | SOUTH 24 PARAGANAS | SM/07586 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dwarikanagar W/S Scheme includ | TSM/006817 | 7749768 | Retrofitting | SVS | GO2021003931PH | 31/12/2020 | 61.02 | 0 | 61.02 | Alipore Division |  | 13.92 | 0 | 0 | 0 | 13.92 | 13.92 | 0 | 0 | 0 | 13.92 | 22.82 | 76
804 | SOUTH 24 PARAGANAS | SM/07625 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sridharnagar W/S Scheme includ | TSM/006860 | 7940746 | Retrofitting | SVS | GO2021004161PH | 07/01/2021 | 136.98 | 0 | 136.98 | Alipore Division |  | 77.27 | 0 | 0 | 0 | 77.27 | 77.27 | 0 | 0 | 0 | 77.27 | 56.41 | 100
805 | SOUTH 24 PARAGANAS | SM/07576 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | TSM/006799 | 7572753 | Retrofitting | MVS | GO2021003940PH | 31/12/2020 | 88.57 | 0 | 88.57 | Alipore Division |  | 54.66 | 0 | 0 | 0 | 54.66 | 53.73 | 0 | 0 | 0 | 53.73 | 60.66 | 91
806 | SOUTH 24 PARAGANAS | SM/07400 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibkalinagar W/S Scheme includ | TSM/006856 | 7749781 | Retrofitting | MVS | GO2021003693PH | 29/12/2020 | 72.43 | 0 | 72.43 | Alipore Division |  | 50.54 | 0 | 0 | 0 | 50.54 | 50.54 | 0 | 0 | 0 | 50.54 | 69.78 | 91
807 | SOUTH 24 PARAGANAS | SM/07582 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Shibpur W/S Scheme including on | TSM/006859 | 8200006 | Retrofitting | SVS | GO2021003942PH | 31/12/2020 | 98.18 | 0 | 98.18 | Alipore Division |  | 60.63 | 0 | 0 | 0 | 60.63 | 60.63 | 0 | 0 | 0 | 60.63 | 61.75 | 86
808 | SOUTH 24 PARAGANAS | SM/07591 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including o | TSM/006863 | 8200024 | Retrofitting | SVS | GO2021003947PH | 31/12/2020 | 66.06 | 0 | 66.06 | Alipore Division |  | 11.28 | 0 | 0 | 0 | 11.28 | 11.28 | 0 | 0 | 0 | 11.28 | 17.07 | 81
809 | SOUTH 24 PARAGANAS | SM/07636 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 65 (sixty five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Suryanagar W/S Scheme i | TSM/006911 | 8200065 | Retrofitting | MVS | GO2021004158PH | 07/01/2021 | 276.48 | 0 | 276.48 | Alipore Division |  | 143.2 | 0 | 24.01 | 0 | 167.22 | 143.2 | 0 | 24.01 | 0 | 167.22 | 60.48 | 81
810 | SOUTH 24 PARAGANAS | SM/07404 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Rajnagar W/S Scheme including | TSM/006851 | 8197926 | Retrofitting | SVS | GO2021003700PH | 29/12/2020 | 93.55 | 0 | 93.55 | Alipore Division |  | 15.19 | 0 | 0 | 0 | 15.19 | 7.18 | 0 | 0 | 0 | 7.18 | 7.68 | 82
811 | SOUTH 24 PARAGANAS | SM/07590 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including | TSM/006862 | 8200020 | Retrofitting | SVS | GO2021003945PH | 31/12/2020 | 74.27 | 0 | 74.27 | Alipore Division |  | 67.55 | 0 | 0 | 0 | 67.55 | 67.55 | 0 | 0 | 0 | 67.55 | 90.95 | 81
812 | SOUTH 24 PARAGANAS | SM/07581 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | TSM/006814 | 8199988 | Retrofitting | MVS | GO2021003928PH | 31/12/2020 | 77.62 | 0 | 77.62 | Alipore Division |  | 33.84 | 0 | 12.79 | 0 | 46.63 | 33.84 | 0 | 12.79 | 0 | 46.63 | 60.07 | 91
813 | SOUTH 24 PARAGANAS | SM/07583 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhaspara W/S Scheme including | TSM/006815 | 8199992 | Retrofitting | SVS | GO2021003929PH | 31/12/2020 | 76.19 | 0 | 76.19 | Alipore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91
814 | SOUTH 24 PARAGANAS | SM/07579 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Koaberia W/S Scheme including | TSM/006837 | 7402330 | Retrofitting | MVS | GO2021003932PH | 31/12/2020 | 82.67 | 0 | 82.67 | Alipore Division |  | 48 | 0 | 0 | 0 | 48 | 46.32 | 0 | 0 | 0 | 46.32 | 56.03 | 93
815 | SOUTH 24 PARAGANAS | SM/07397 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | TSM/006854 | 7755616 | Retrofitting | SVS | GO2021003696PH | 29/12/2020 | 93.47 | 0 | 93.47 | Alipore Division |  | 69.1 | 0 | 0 | 0 | 69.1 | 67.2 | 0 | 0 | 0 | 67.2 | 71.9 | 96
816 | SOUTH 24 PARAGANAS | SM/07408 | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 9 (nine) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramtanunagar W/S Scheme includ | TSM/006855 | 8197844 | Retrofitting | SVS | GO2021003694PH | 29/12/2020 | 76.56 | 0 | 76.56 | Alipore Division |  | 56.87 | 0 | 0 | 0 | 56.87 | 56.11 | 0 | 0 | 0 | 56.11 | 73.29 | 96
817 | SOUTH 24 PARAGANAS | SM/08632 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 07 seven nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | TSM/007249 | 7940679 | Retrofitting | MVS | GO2122000863PH | 27/05/2021 | 157.27 | 0 | 157.27 | Alipore Division |  | 0 | 0 | 36.43 | 0 | 36.43 | 0 | 0 | 36.43 | 0 | 36.43 | 23.17 | 71
818 | SOUTH 24 PARAGANAS | SM/08628 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 08 eight nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Achintyanagar WS Scheme including | TSM/007246 | 7940679 | Retrofitting | MVS | GO2122000641PH | 31/05/2021 | 204.05 | 0 | 204.05 | Alipore Division |  | 105.6 | 0 | 12.28 | 0 | 117.88 | 100.61 | 0 | 12.28 | 0 | 112.89 | 55.33 | 77
819 | SOUTH 24 PARAGANAS | SM/08631 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Bagdanga WS Scheme including one | TSM/007244 | 7940557 | Retrofitting | MVS | GO2122000920PH | 31/05/2021 | 116.34 | 0 | 116.34 | Alipore Division |  | 4.11 | 0 | 0 | 0 | 4.11 | 4.11 | 0 | 0 | 0 | 4.11 | 3.53 | 25
820 | SOUTH 24 PARAGANAS | SM/08630 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 12 twelve nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sitarampur WS Scheme including on | TSM/007243 | 8123471 | Retrofitting | MVS | GO2122000644PH | 31/05/2021 | 166.84 | 0 | 166.84 | Alipore Division |  | 114 | 0 | 12.81 | 0 | 126.81 | 91.45 | 0 | 12.81 | 0 | 104.26 | 62.49 | 84
821 | SOUTH 24 PARAGANAS | SM/08633 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sambhunagar WS Scheme includin | TSM/007250 | 7940559 | Retrofitting | MVS | GO2122000862PH | 27/05/2021 | 167.07 | 0 | 167.07 | Alipore Division |  | 160.3 | 0 | 0 | 0 | 160.3 | 160.3 | 0 | 0 | 0 | 160.3 | 95.95 | 81
822 | SOUTH 24 PARAGANAS | SM/09006 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | TSM/007245 | 7940643 | Retrofitting | SVS | GO2122000640PH | 31/05/2021 | 131.88 | 0 | 131.88 | Alipore Division |  | 104.88 | 0 | 12.3 | 0 | 117.18 | 104.88 | 0 | 12.3 | 0 | 117.18 | 88.85 | 93
823 | SOUTH 24 PARAGANAS | SM/08791 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 24 (twenty four) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Chhota Molla Khali WS Sche | TSM/007252 | 7940699 | Retrofitting | MVS | GO2122003238PH | 13/09/2021 | 461.43 | 0 | 461.43 | Alipore Division |  | 439.8 | 0 | 0 | 0 | 439.8 | 318.44 | 0 | 0 | 0 | 318.44 | 69.01 | 27
824 | SOUTH 24 PARAGANAS | SM/08629 | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 43 forty three nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sibnagar WS Scheme including | TSM/007241 | 7940756 | Retrofitting | MVS | GO2122000643PH | 31/05/2021 | 111.49 | 0 | 111.49 | Alipore Division |  | 77.37 | 0 | 0 | 0 | 77.37 | 77.37 | 0 | 0 | 0 | 77.37 | 69.4 | 83
825 | SOUTH 24 PARAGANAS | SM/07054 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:145 to 152 under Budge Budge-I Block with allied works | TSM/006133 | 8136109 | Retrofitting | SVS | GO2021002756PH | 25/11/2020 | 99.29 | 0 | 99.29 | South 24 Pgs. W/S Division - I |  | 99.29 | 0 | 0 | 0 | 99.29 | 94.96 | 0 | 0 | 0 | 94.96 | 95.64 | 95
826 | SOUTH 24 PARAGANAS | SM/07053 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:153 to 169 under Budge Budge-I Block with allied works | TSM/006134 | 8136100 | Retrofitting | SVS | GO2021002754PH | 25/11/2020 | 99.78 | 0 | 99.78 | South 24 Pgs. W/S Division - I |  | 99.78 | 0 | 0 | 0 | 99.78 | 82.22 | 0 | 0 | 0 | 82.22 | 82.4 | 90
827 | SOUTH 24 PARAGANAS | SM/07050 | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Uttar Roypur Balarampur (Part), Chak Nabashan (Part) Mouza under Budge Budge-I Block with allied works | TSM/006136 | 8136091 | Retrofitting | SVS | GO2021002751PH | 25/11/2020 | 88.77 | 0 | 88.77 | South 24 Pgs. W/S Division - I |  | 88.77 | 0 | 0 | 0 | 88.77 | 85.9 | 0 | 0 | 0 | 85.9 | 96.76 | 86
828 | SOUTH 24 PARAGANAS | SM/09511 | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | TSM/008303 | 5344170 | Retrofitting | MVS | GO2122005579PH | 19/11/2021 | 131.93 | 0 | 131.93 | Alipore Division |  | 61.85 | 0 | 48.79 | 0 | 110.64 | 61.84 | 0 | 48.79 | 0 | 110.63 | 83.86 | 76
829 | SOUTH 24 PARAGANAS | SM/09515 | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | TSM/008307 | 5344170 | Retrofitting | MVS | GO2122005579PH | 19/11/2021 | 125.82 | 0 | 125.82 | Alipore Division |  | 108.19 | 0 | 3.08 | 0 | 111.26 | 108.19 | 0 | 3.08 | 0 | 111.26 | 88.43 | 100
830 | SOUTH 24 PARAGANAS | SM/09514 | Retrofitting of Distribution System of Mathurapur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & | TSM/008306 | 5344170 | Retrofitting | MVS | GO2122005579PH | 19/11/2021 | 197.25 | 0 | 197.25 | Alipore Division |  | 72.52 | 0 | 106.77 | 0 | 179.29 | 72.52 | 0 | 106.77 | 0 | 179.29 | 90.9 | 100
831 | SOUTH 24 PARAGANAS | SM/09513 | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | TSM/008305 | 5344170 | Retrofitting | MVS | GO2122005579PH | 19/11/2021 | 106.53 | 0 | 106.53 | Alipore Division |  | 63.94 | 0 | 0 | 0 | 63.94 | 59.67 | 0 | 0 | 0 | 59.67 | 56.02 | 100
832 | SOUTH 24 PARAGANAS | SM/09512 | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | TSM/008304 | 5344170 | Retrofitting | MVS | GO2122005579PH | 19/11/2021 | 102.7 | 0 | 102.7 | Alipore Division |  | 87.34 | 0 | 0 | 0 | 87.34 | 87.34 | 0 | 0 | 0 | 87.34 | 85.04 | 100
833 | SOUTH 24 PARAGANAS | SM/08118 | Retrofitting of Distribution system of Zone I Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | TSM/005826 | 5344170 | Retrofitting | MVS | GO2021007274PH | 19/02/2021 | 491.98 | 0 | 491.98 | Alipore Division |  | 477.65 | 0 | 0 | 0 | 477.65 | 477.65 | 0 | 0 | 0 | 477.65 | 97.09 | 100
834 | SOUTH 24 PARAGANAS | SM/08119 | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | TSM/005827 | 5344170 | Retrofitting | MVS | GO2021007277PH | 19/02/2021 | 356.83 | 0 | 356.83 | Alipore Division |  | 312.19 | 0 | 0 | 0 | 312.19 | 312.03 | 0 | 0 | 0 | 312.03 | 87.44 | 100
835 | SOUTH 24 PARAGANAS | SM/08124 | Retrofitting of Distribution system of Zone III Diamond Harbour II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/005832 | 5344170 | Retrofitting | MVS | GO2021007283PH | 19/02/2021 | 454.88 | 0 | 454.88 | Alipore Division |  | 363.96 | 0 | 22.17 | 0 | 386.14 | 363.47 | 0 | 22.17 | 0 | 385.64 | 84.78 | 99
836 | SOUTH 24 PARAGANAS | SM/08120 | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | TSM/005828 | 5344170 | Retrofitting | MVS | GO2021007280PH | 19/02/2021 | 389.87 | 0 | 389.87 | Alipore Division |  | 333.83 | 0 | 0 | 0 | 333.83 | 280.83 | 0 | 0 | 0 | 280.83 | 72.03 | 95
837 | SOUTH 24 PARAGANAS | SM/08123 | Retrofitting of Distribution system of Zone IX Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | TSM/005831 | 5344170 | Retrofitting | MVS | GO2021007282PH | 19/02/2021 | 271.61 | 0 | 271.61 | Alipore Division |  | 242.7 | 0 | 0 | 0 | 242.7 | 233.08 | 0 | 0 | 0 | 233.08 | 85.81 | 100
838 | SOUTH 24 PARAGANAS | SM/08122 | Retrofitting of Distribution system of Zone V Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathur | TSM/005829 | 5344170 | Retrofitting | MVS | GO2021007279PH | 19/02/2021 | 357.03 | 0 | 357.03 | Alipore Division |  | 271.91 | 0 | 19.73 | 0 | 291.64 | 229.12 | 0 | 19.73 | 0 | 248.85 | 69.7 | 95
839 | SOUTH 24 PARAGANAS | SM/08121 | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | TSM/005830 | 5344170 | Retrofitting | MVS | GO2021007281PH | 19/02/2021 | 383.26 | 0 | 383.26 | Alipore Division |  | 190.4 | 0 | 47.23 | 0 | 237.63 | 190.4 | 0 | 47.23 | 0 | 237.63 | 62 | 100
840 | SOUTH 24 PARAGANAS | SM/09770 | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/008586 | 5344170 | Retrofitting | MVS | GO2122006242PH | 30/11/2021 | 142.98 | 0 | 142.98 | Alipore Division |  | 114.63 | 0 | 3.08 | 0 | 117.7 | 110.87 | 0 | 3.08 | 0 | 113.95 | 79.69 | 80
841 | SOUTH 24 PARAGANAS | SM/09400 | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/008667 | 5344170 | Retrofitting | SVS | GO2122005506PH | 17/11/2021 | 229.18 | 0 | 229.18 | Alipore Division |  | 8.72 | 0 | 24.6 | 0 | 33.32 | 6.82 | 0 | 24.6 | 0 | 31.42 | 13.71 | 5
842 | SOUTH 24 PARAGANAS | SM/13360 | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-II,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | TSM/013430 | 40065323 | Retrofitting | MVS | GO2223008961PH | 19/10/2022 | 272.66 | 0 | 272.66 | Alipore Division |  | 3.13 | 0 | 30.8 | 0 | 33.93 | 3.13 | 0 | 30.8 | 0 | 33.93 | 12.44 | 0
843 | SOUTH 24 PARAGANAS | SM/09397 | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/008675 | 5344170 | Retrofitting | MVS | GO2122005507PH | 17/11/2021 | 153.42 | 0 | 153.42 | Alipore Division |  | 101.66 | 0 | 43.76 | 0 | 145.42 | 101.66 | 0 | 43.76 | 0 | 145.42 | 94.78 | 51
844 | SOUTH 24 PARAGANAS | SM/09771 | Retrofitting of Distribution System of Zone-III, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/008585 | 5344170 | Retrofitting | SVS | GO2122006242PH | 30/11/2021 | 131.44 | 0 | 131.44 | Alipore Division |  | 20.3 | 0 | 39.73 | 0 | 60.03 | 20.3 | 0 | 39.73 | 0 | 60.03 | 45.67 | 5
845 | SOUTH 24 PARAGANAS | SM/09508 | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | TSM/008310 | 5344170 | Retrofitting | MVS | GO2122005594PH | 19/11/2021 | 425.04 | 0 | 425.04 | Alipore Division |  | 1.2 | 0 | 22.34 | 0 | 23.55 | 0.71 | 0 | 22.34 | 0 | 23.05 | 5.42 | 6
846 | SOUTH 24 PARAGANAS | SM/09401 | Retrofitting of Distribution System of Zone-IV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/008665 | 5344170 | Retrofitting | SVS | GO2122005506PH | 17/11/2021 | 274.75 | 0 | 274.75 | Alipore Division |  | 191.64 | 0 | 33.26 | 0 | 224.9 | 134.28 | 0 | 33.26 | 0 | 167.53 | 60.98 | 41
847 | SOUTH 24 PARAGANAS | SM/07755 | Retrofitting of Distribution System of Zone-IX, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/006845 | 5344170 | Retrofitting | SVS | GO2021004336PH | 08/01/2021 | 127.96 | 0 | 127.96 | Alipore Division |  | 77.44 | 0 | 12.88 | 0 | 90.32 | 77.43 | 0 | 12.88 | 0 | 90.31 | 70.58 | 91
848 | SOUTH 24 PARAGANAS | SM/09769 | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/008664 | 5344170 | Retrofitting | MVS | GO2122006242PH | 30/11/2021 | 183.73 | 0 | 183.73 | Alipore Division |  | 20.29 | 0 | 94.09 | 0 | 114.38 | 0 | 0 | 94.09 | 0 | 94.09 | 51.21 | 5
849 | SOUTH 24 PARAGANAS | SM/09558 | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo | TSM/009106 | 5344170 | Retrofitting | SVS | GO2122005601PH | 19/11/2021 | 253.22 | 0 | 253.22 | Alipore Division |  | 70.6 | 0 | 24.54 | 0 | 95.14 | 70.6 | 0 | 24.54 | 0 | 95.14 | 37.57 | 5
850 | SOUTH 24 PARAGANAS | SM/09399 | Retrofitting of Distribution System of Zone-V, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/008670 | 5344170 | Retrofitting | MVS | GO2122005506PH | 17/11/2021 | 209.29 | 0 | 209.29 | Alipore Division |  | 144.48 | 0 | 55.57 | 0 | 200.04 | 144.48 | 0 | 55.57 | 0 | 200.04 | 95.58 | 81
851 | SOUTH 24 PARAGANAS | SM/09398 | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/008666 | 5344170 | Retrofitting | MVS | GO2122005507PH | 17/11/2021 | 97.07 | 0 | 97.07 | Alipore Division |  | 84.94 | 0 | 9.31 | 0 | 94.25 | 84.94 | 0 | 9.31 | 0 | 94.25 | 97.09 | 81
852 | SOUTH 24 PARAGANAS | SM/13364 | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | TSM/013433 | 40065336 | Retrofitting | MVS | GO2223008951PH | 19/10/2022 | 189.79 | 0 | 189.79 | Alipore Division |  | 2.71 | 0 | 20.38 | 0 | 23.1 | 2.71 | 0 | 20.38 | 0 | 23.1 | 12.17 | 0
853 | SOUTH 24 PARAGANAS | SM/09507 | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S | TSM/008308 | 5344170 | Retrofitting | MVS | GO2122005594PH | 19/11/2021 | 158.51 | 0 | 158.51 | Alipore Division |  | 21.5 | 0 | 17.45 | 0 | 38.95 | 6.31 | 0 | 17.45 | 0 | 23.76 | 14.99 | 6
854 | SOUTH 24 PARAGANAS | SM/09510 | Retrofitting of Distribution System of Zone-VII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Fal | TSM/008309 | 5344170 | Retrofitting | MVS | GO2122005580PH | 19/11/2021 | 323.42 | 0 | 323.42 | Alipore Division |  | 242.75 | 0 | 68.56 | 0 | 311.31 | 242.75 | 0 | 68.56 | 0 | 311.31 | 96.26 | 60
855 | SOUTH 24 PARAGANAS | SM/09425 | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | TSM/008679 | 5344170 | Retrofitting | MVS | GO2122005505PH | 17/11/2021 | 286.94 | 0 | 286.94 | Alipore Division |  | 235.93 | 0 | 40.04 | 0 | 275.97 | 198.62 | 0 | 40.04 | 0 | 238.66 | 83.17 | 9
856 | SOUTH 24 PARAGANAS | SM/09555 | Retrofitting of Distribution System of Zone-VIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/009099 | 5344170 | Retrofitting | MVS | GO2122005601PH | 19/11/2021 | 175.13 | 0 | 175.13 | Alipore Division |  | 137.19 | 0 | 3.08 | 0 | 140.26 | 137.19 | 0 | 3.08 | 0 | 140.26 | 80.09 | 5
857 | SOUTH 24 PARAGANAS | SM/07753 | Retrofitting of Distribution System of Zone-VIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | TSM/006846 | 5344170 | Retrofitting | MVS | GO2021004338PH | 08/01/2021 | 145.53 | 0 | 145.53 | Alipore Division |  | 121.9 | 0 | 18.45 | 0 | 140.35 | 121.9 | 0 | 18.45 | 0 | 140.35 | 96.44 | 81
858 | SOUTH 24 PARAGANAS | SM/07401 | Retrofitting of Distribution System of Zone-X, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/006847 | 5344170 | Retrofitting | MVS | GO2021003702PH | 29/12/2020 | 91.79 | 0 | 91.79 | Alipore Division |  | 89.12 | 0 | 0 | 0 | 89.12 | 80.73 | 0 | 0 | 0 | 80.73 | 87.95 | 100
859 | SOUTH 24 PARAGANAS | SM/07751 | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | TSM/006841 | 5344170 | Retrofitting | MVS | GO2021004333PH | 08/01/2021 | 158.44 | 0 | 158.44 | Alipore Division |  | 109.16 | 0 | 11.25 | 0 | 120.41 | 109.16 | 0 | 0 | 0 | 109.16 | 68.89 | 51
860 | SOUTH 24 PARAGANAS | SM/07750 | Retrofitting of Distribution System of Zone-XI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/006848 | 5344170 | Retrofitting | MVS | GO2021004339PH | 08/01/2021 | 114.21 | 0 | 114.21 | Alipore Division |  | 76.59 | 0 | 11.25 | 0 | 87.85 | 76.59 | 0 | 11.25 | 0 | 87.85 | 76.92 | 100
861 | SOUTH 24 PARAGANAS | SM/09557 | Retrofitting of Distribution System of Zone-XII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/009102 | 5344170 | Retrofitting | MVS | GO2122005601PH | 19/11/2021 | 93.7 | 0 | 93.7 | Alipore Division |  | 86.03 | 0 | 4.94 | 0 | 90.97 | 86.03 | 0 | 4.94 | 0 | 90.97 | 97.09 | 75
862 | SOUTH 24 PARAGANAS | SM/07752 | Retrofitting of Distribution System of Zone-XII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/006843 | 5344170 | Retrofitting | MVS | GO2021004334PH | 08/01/2021 | 127.48 | 0 | 127.48 | Alipore Division |  | 109.01 | 0 | 3.08 | 0 | 112.08 | 91.64 | 0 | 3.08 | 0 | 94.71 | 74.3 | 100
863 | SOUTH 24 PARAGANAS | SM/07578 | Retrofitting of Distribution System of Zone-XIII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/006842 | 5344170 | Retrofitting | MVS | GO2021003937PH | 31/12/2020 | 86.88 | 0 | 86.88 | Alipore Division |  | 84.35 | 0 | 0 | 0 | 84.35 | 84.35 | 0 | 0 | 0 | 84.35 | 97.09 | 100
864 | SOUTH 24 PARAGANAS | SM/07577 | Retrofitting of Distribution System of Zone-XIII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Schem | TSM/006844 | 5344170 | Retrofitting | SVS | GO2021003938PH | 31/12/2020 | 62.28 | 0 | 62.28 | Alipore Division |  | 52.98 | 0 | 0 | 0 | 52.98 | 52.98 | 0 | 0 | 0 | 52.98 | 85.06 | 81
865 | SOUTH 24 PARAGANAS | SM/09556 | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/009100 | 5344170 | Retrofitting | SVS | GO2122005601PH | 19/11/2021 | 21.75 | 0 | 21.75 | Alipore Division |  | 16.08 | 0 | 1.39 | 0 | 17.47 | 15.99 | 0 | 1.39 | 0 | 17.37 | 79.86 | 100
866 | SOUTH 24 PARAGANAS | SM/09396 | Retrofitting of Distribution System of Zone-XVII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | TSM/008676 | 5344170 | Retrofitting | MVS | GO2122005507PH | 17/11/2021 | 116.46 | 0 | 116.46 | Alipore Division |  | 0 | 0 | 12.62 | 0 | 12.62 | 0 | 0 | 12.62 | 0 | 12.62 | 10.84 | 5
867 | SOUTH 24 PARAGANAS | SM/08796 | Retrofitting of ground water based Bhangan Khali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | TSM/007700 | 40049283 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 214.82 | 0 | 214.82 | Alipore Division |  | 5.98 | 0 | 13.96 | 0 | 19.93 | 5.98 | 0 | 13.96 | 0 | 19.93 | 9.28 | 3
868 | SOUTH 24 PARAGANAS | SM/08797 | Retrofitting of ground water based Char Baidyarabad Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | TSM/007701 | 40007403 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 252.25 | 0 | 252.25 | Alipore Division |  | 6.66 | 0 | 12.11 | 0 | 18.77 | 6.66 | 0 | 12.11 | 0 | 18.77 | 7.44 | 6
869 | SOUTH 24 PARAGANAS | SM/08806 | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | TSM/007702 | 40007472 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 172.36 | 0 | 172.36 | Alipore Division |  | 5.03 | 0 | 158.75 | 0 | 163.78 | 5.03 | 0 | 158.75 | 0 | 163.78 | 95.02 | 2
870 | SOUTH 24 PARAGANAS | SM/08798 | Retrofitting of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | TSM/007703 | 40007394 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 99.12 | 0 | 99.12 | Alipore Division |  | 5.63 | 0 | 0 | 0 | 5.63 | 5.63 | 0 | 0 | 0 | 5.63 | 5.68 | 3
871 | SOUTH 24 PARAGANAS | SM/08799 | Retrofitting of ground water based Phulmalancha Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | TSM/007704 | 40007391 | Retrofitting | SVS | GO2122003238PH | 13/09/2021 | 210.24 | 0 | 210.24 | Alipore Division |  | 68.44 | 0 | 0 | 0 | 68.44 | 6.36 | 0 | 0 | 0 | 6.36 | 3.02 | 2
872 | SOUTH 24 PARAGANAS | SM/12808 | Retrofitting of pipeline for FHTC drive including PWD road restoration on connection with pipe water supply scheme incluiding FHTC for CHOTTA GP in THAKURPUKUR MEHESTALA block under South 24 pgs. W/S division-I , PHE Dte | TSM/014924 | 40029152 | Augmentation | MVS | GO2223008040PH | 21/09/2022 | 382.59 | 0 | 382.59 | South 24 Pgs. W/S Division - I |  | 174.21 | 0 | 0 | 0 | 174.21 | 174.21 | 0 | 0 | 0 | 174.21 | 45.53 | 46
873 | SOUTH 24 PARAGANAS | SM/09948 | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008299 | 40009607 | Retrofitting | MVS | GO2122006827PH | 14/12/2021 | 64.96 | 0 | 64.96 | South 24 Pgs. W/S Division - I |  | 57.34 | 0 | 2.21 | 0 | 59.55 | 57.34 | 0 | 2.21 | 0 | 59.55 | 91.67 | 37
874 | SOUTH 24 PARAGANAS | SM/09956 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 141 to 144 ) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008293 | 40009344 | Retrofitting | MVS | GO2122006834PH | 14/12/2021 | 299.18 | 0 | 299.18 | South 24 Pgs. W/S Division - I |  | 286.45 | 0 | 0 | 0 | 286.45 | 286.45 | 0 | 0 | 0 | 286.45 | 95.74 | 90
875 | SOUTH 24 PARAGANAS | SM/09955 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008292 | 40009341 | Retrofitting | MVS | GO2122006834PH | 14/12/2021 | 290.16 | 0 | 290.16 | South 24 Pgs. W/S Division - I |  | 158.68 | 0 | 0 | 0 | 158.68 | 158.68 | 0 | 0 | 0 | 158.68 | 54.69 | 52
876 | SOUTH 24 PARAGANAS | SM/09953 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 197 to 198) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008290 | 40007188 | Retrofitting | MVS | GO2122006834PH | 14/12/2021 | 42.18 | 0 | 42.18 | South 24 Pgs. W/S Division - I |  | 33.73 | 0 | 0 | 0 | 33.73 | 33.73 | 0 | 0 | 0 | 33.73 | 79.96 | 80
877 | SOUTH 24 PARAGANAS | SM/09954 | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008291 | 40009332 | Retrofitting | MVS | GO2122006834PH | 14/12/2021 | 287.71 | 0 | 287.71 | South 24 Pgs. W/S Division - I |  | 250.68 | 0 | 0 | 0 | 250.68 | 250.68 | 0 | 0 | 0 | 250.68 | 87.13 | 91
878 | SOUTH 24 PARAGANAS | SM/09949 | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008294 | 40009570 | Retrofitting | SVS | GO2122006827PH | 14/12/2021 | 100.01 | 0 | 100.01 | South 24 Pgs. W/S Division - I |  | 78.26 | 0 | 0 | 0 | 78.26 | 78.26 | 0 | 0 | 0 | 78.26 | 78.25 | 69
879 | SOUTH 24 PARAGANAS | SM/09950 | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008295 | 40009559 | Retrofitting | MVS | GO2122006827PH | 14/12/2021 | 89.53 | 0 | 89.53 | South 24 Pgs. W/S Division - I |  | 84.08 | 0 | 0 | 0 | 84.08 | 84.08 | 0 | 0 | 0 | 84.08 | 93.91 | 85
880 | SOUTH 24 PARAGANAS | SM/09952 | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008296 | 40009574 | Retrofitting | SVS | GO2122006834PH | 14/12/2021 | 65.43 | 0 | 65.43 | South 24 Pgs. W/S Division - I |  | 62.08 | 0 | 0 | 0 | 62.08 | 62.08 | 0 | 0 | 0 | 62.08 | 94.88 | 75
881 | SOUTH 24 PARAGANAS | SM/09951 | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | TSM/008297 | 40009576 | Retrofitting | SVS | GO2122006827PH | 14/12/2021 | 91.19 | 0 | 91.19 | South 24 Pgs. W/S Division - I |  | 87.06 | 0 | 0 | 0 | 87.06 | 87.06 | 0 | 0 | 0 | 87.06 | 95.48 | 80
882 | SOUTH 24 PARAGANAS | SM/09947 | Retrofitting of pipeline for supporting FHTC drive for under Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza including Balarampur Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas | TSM/008298 | 40009609 | Retrofitting | MVS | GO2122006827PH | 14/12/2021 | 163.78 | 0 | 163.78 | South 24 Pgs. W/S Division - I |  | 159 | 0 | 0 | 0 | 159 | 159 | 0 | 0 | 0 | 159 | 97.08 | 90
883 | SOUTH 24 PARAGANAS | SM/09945 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008301 | 40009595 | Retrofitting | SVS | GO2122006827PH | 14/12/2021 | 163.9 | 0 | 163.9 | South 24 Pgs. W/S Division - I |  | 78.81 | 0 | 0 | 0 | 78.81 | 78.81 | 0 | 0 | 0 | 78.81 | 48.09 | 40
884 | SOUTH 24 PARAGANAS | SM/09944 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | TSM/008300 | 40009592 | Retrofitting | SVS | GO2122006827PH | 14/12/2021 | 135.17 | 0 | 135.17 | South 24 Pgs. W/S Division - I |  | 51.77 | 0 | 0 | 0 | 51.77 | 51.77 | 0 | 0 | 0 | 51.77 | 38.3 | 35
885 | SOUTH 24 PARAGANAS | SM/09946 | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Uttar Roypur, Balarampur (Part) and Chak Nabasan (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | TSM/008302 | 40009602 | Retrofitting | SVS | GO2122006827PH | 14/12/2021 | 157.01 | 0 | 157.01 | South 24 Pgs. W/S Division - I |  | 149.18 | 0 | 0 | 0 | 149.18 | 149.18 | 0 | 0 | 0 | 149.18 | 95.01 | 85
886 | SOUTH 24 PARAGANAS | SM/13675 | SAHEBPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | TSM/015503 | 40034625 | Augmentation | SVS | GO2223009272PH | 02/11/2022 | 812.5 | 71.11 | 883.61 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 193.92 | 29.37 | 37.52 | 0 | 260.81 | 193.92 | 14.07 | 37.52 | 0 | 245.51 | 27.79 | 13
887 | SOUTH 24 PARAGANAS | SM/13787 | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016319 | 40034181 | Augmentation | MVS | GO2223009898PH | 18/11/2022 | 915.7 | 73.95 | 989.64 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 134.97 | 13.04 | 63.95 | 0 | 211.96 | 134.97 | 0 | 63.95 | 0 | 198.92 | 20.1 | 19
888 | SOUTH 24 PARAGANAS | SM/14545 | SANGUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/017137 | 40034304 | Augmentation | MVS | GO2223012590PH | 30/01/2023 | 1170.94 | 79.74 | 1250.69 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 216.36 | 28.25 | 48.41 | 0 | 293.02 | 216.36 | 28.25 | 48.41 | 0 | 293.02 | 23.43 | 15
889 | SOUTH 24 PARAGANAS | SM/11274 | SATBERIA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | TSM/010762 | 40026146 | New | MVS | GO2223004444PH | 24/06/2022 | 836.74 | 76.69 | 913.42 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 594.28 | 32.16 | 5.03 | 0 | 631.47 | 594.28 | 32.16 | 5.03 | 0 | 631.47 | 69.13 | 66
890 | SOUTH 24 PARAGANAS | SM/18500 | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/018414 | 40053001 | Augmentation | MVS | 2036/PHE-28011/194/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1119.68 | 73.91 | 1193.59 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 108.36 | 0 | 15.7 | 0 | 124.06 | 108.36 | 0 | 6.05 | 0 | 114.41 | 9.59 | 9
891 | SOUTH 24 PARAGANAS | SM/11275 | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | TSM/010765 | 40026130 | New | MVS | GO2223004446PH | 24/06/2022 | 749.33 | 78.67 | 828 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 410.66 | 21.71 | 13.92 | 0 | 446.28 | 410.66 | 21.71 | 13.92 | 0 | 446.28 | 53.9 | 43
892 | SOUTH 24 PARAGANAS | SM/18129 | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/010989 | 40066193 | New | SVS | GO2223017944PH | 29/03/2023 | 644.01 | 47.25 | 691.26 | Alipore Division | South 24 Pgs Mechanical Division | 83.41 | 3.86 | 8.93 | 0 | 96.2 | 0 | 0 | 8.93 | 0 | 8.93 | 1.29 | 9
893 | SOUTH 24 PARAGANAS | SM/14488 | TARDAHA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | TSM/016779 | 40034278 | Augmentation | MVS | GO2223012351PH | 20/01/2023 | 1277.46 | 76.42 | 1353.88 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 455.75 | 13.33 | 21.01 | 0 | 490.1 | 455.75 | 13.33 | 21.01 | 0 | 490.1 | 36.2 | 22
894 | SOUTH 24 PARAGANAS | SM/18683 | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011038 | 40066199 | New | MVS | 2245/PHE-28011/229/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1056.86 | 46.32 | 1103.18 | Alipore Division | South 24 Pgs Mechanical Division | 113.89 | 0 | 49.73 | 0 | 163.62 | 113.89 | 0 | 40.79 | 0 | 154.68 | 14.02 | 29
Total | [9 empty] | 592131.34 | 34007.25 | 626138.6 |  |  | 137005.86 | 3839.07 | 40661.16 | 78.05 | 181584.15 | 123800.94 | 3588.17 | 38614.32 | 78.05 | 166081.48 | 26.52