## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PASCHIM MEDINIPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PASCHIM MEDINIPUR | SM/14689 | ABHAYA AND ADJOINING MOUJAS PWSS | TSM/016168 | 40035537 | New | MVS | GO2223012728PH | 31/01/2023 | 139.41 | 18.63 | 158.04 | Midnapore Division | Jhargram Mechanical Division | 16.55 | 0 | 0 | 0 | 16.55 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2 | PASCHIM MEDINIPUR | SM/13052 | AGRA & ADJOINING MOUJAS PWSS | TSM/013395 | 40028713 | New | MVS | GO2223008502PH | 29/09/2022 | 306.78 | 36.38 | 343.16 | Midnapore Division | Jhargram Mechanical Division | 45.5 | 5.26 | 13.92 | 0 | 64.69 | 0 | 5.26 | 13.92 | 0 | 19.18 | 5.59 | 1
3 | PASCHIM MEDINIPUR | SM/13176 | AKANDA AND ADJOINING MOUJAS PWSS | TSM/014328 | 40034264 | New | MVS | GO2223008656PH | 12/10/2022 | 510.73 | 38.73 | 549.46 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 12.62 | 0 | 12.62 | 0 | 0 | 12.62 | 0 | 12.62 | 2.3 | 1
4 | PASCHIM MEDINIPUR | SM/17003 | AKRA MARKANDAPUR PWSS | TSM/017988 | 40054168 | New | SVS | GO2223016500PH | 16/03/2023 | 35.97 | 9.17 | 45.14 | Midnapore Division | Midnapore Mechanical Division | 5.67 | 4.16 | 0 | 0 | 9.84 | 0 | 0 | 0 | 0 | 0 | 0 | 3
5 | PASCHIM MEDINIPUR | SM/13177 | AMDA AND ADJOINING MOUJAS PWSS | TSM/014572 | 40034930 | New | MVS | GO2223008660PH | 12/10/2022 | 464.76 | 37.66 | 502.42 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 8.65 | 0 | 8.65 | 0 | 0 | 8.65 | 0 | 8.65 | 1.72 | 1
6 | PASCHIM MEDINIPUR | SM/13707 | AMJOR AND ADJOINING MOUJAS PWSS | TSM/015062 | 40059417 | New | MVS | GO2223009724PH | 14/11/2022 | 314.6 | 35.59 | 350.18 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
7 | PASCHIM MEDINIPUR | SM/10318 | Amjor Piped Water Supply Scheme. | TSM/004490 | 40059417 | New | MVS | GO2122010475PH | 04/03/2022 | 474.37 | 36.29 | 510.66 | Midnapore Division | Jhargram Mechanical Division | 144.51 | 22.26 | 26.07 | 0 | 192.85 | 118.2 | 22.26 | 26.07 | 0 | 166.53 | 32.61 | 49
8 | PASCHIM MEDINIPUR | SM/18584 | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | TSM/017358 | 40034546 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1178.57 | 41.23 | 1219.81 | Midnapore Division | Midnapore Mechanical Division | 173.6 | 8.69 | 0 | 0 | 182.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2
9 | PASCHIM MEDINIPUR | SM/14989 | AMLASULI AND ADJOINING MOUJAS PWSS | TSM/015791 | 40035448 | New | MVS | GO2223013050PH | 04/02/2023 | 513.11 | 49.87 | 562.97 | Midnapore Division | Jhargram Mechanical Division | 71.9 | 8.09 | 9.97 | 0 | 89.96 | 4.78 | 8.09 | 9.97 | 0 | 22.84 | 4.06 | 5
10 | PASCHIM MEDINIPUR | SM/13178 | AMRA TARYA AND ADJOINING MOUJAS PWSS | TSM/014571 | 40034915 | New | MVS | GO2223008659PH | 12/10/2022 | 428.59 | 37.64 | 466.23 | Midnapore Division | Midnapore Mechanical Division | 37.69 | 0 | 0 | 0 | 37.69 | 0 | 0 | 0 | 0 | 0 | 0 | 1
11 | PASCHIM MEDINIPUR | SM/13179 | AMSOL AND ADJOINING MOUJAS PWSS | TSM/014456 | 40033114 | New | MVS | GO2223008658PH | 12/10/2022 | 368.87 | 36.58 | 405.45 | Midnapore Division | Jhargram Mechanical Division | 20.71 | 10.25 | 0 | 0 | 30.97 | 0 | 4.13 | 0 | 0 | 4.13 | 1.02 | 1
12 | PASCHIM MEDINIPUR | SM/13180 | ANAR AND ADJOINING MOUJAS PWSS | TSM/014649 | 40034969 | New | MVS | GO2223008657PH | 12/10/2022 | 575.5 | 39.45 | 614.95 | Midnapore Division | Midnapore Mechanical Division | 41.45 | 7.23 | 14.72 | 23.39 | 86.8 | 0 | 0 | 14.72 | 23.1 | 37.81 | 6.15 | 2
13 | PASCHIM MEDINIPUR | SM/13635 | ANDHAR NAYAN AND ADJOINING MOUJAS PWSS | TSM/014629 | 40030361 | New | MVS | GO2223009606PH | 11/11/2022 | 601.22 | 57.66 | 658.87 | Midnapore Division | Jhargram Mechanical Division | 0 | 13.18 | 36.8 | 0 | 49.97 | 0 | 13.18 | 22.89 | 0 | 36.07 | 5.47 | 1
14 | PASCHIM MEDINIPUR | SM/12989 | ANGUA AND ADJOINING MOUJAS PWSS | TSM/014240 | 40025991 | New | MVS | GO2223008344PH | 28/09/2022 | 367.43 | 36.45 | 403.88 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 7.7 | 0 | 7.7 | 0 | 0 | 7.7 | 0 | 7.7 | 1.91 | 1
15 | PASCHIM MEDINIPUR | SM/09991 | Antla Piped Water Supply Scheme. | TSM/008037 | 40008563 | New | MVS | GO2122006951PH | 16/12/2021 | 669.25 | 0 | 669.25 | Midnapore Division | Midnapore Mechanical Division | 370.75 | 0 | 68.09 | 0 | 438.84 | 370.55 | 0 | 68.09 | 0 | 438.64 | 65.54 | 95
16 | PASCHIM MEDINIPUR | SM/13636 | ANTRI AND ADJOINING MOUJAS PWSS | TSM/014683 | 40030188 | New | MVS | GO2223009607PH | 11/11/2022 | 840.52 | 39.49 | 880.01 | Midnapore Division | Midnapore Mechanical Division | 244.83 | 8.6 | 1.89 | 0 | 255.32 | 57.46 | 0 | 1.89 | 0 | 59.35 | 6.74 | 29
17 | PASCHIM MEDINIPUR | SM/12198 | ASHARI AND IT'S ADJOINING MOUJAS PWSS | TSM/013126 | 40021620 | New | MVS | GO2223007234PH | 07/09/2022 | 369.7 | 37.89 | 407.59 | Midnapore Division | Midnapore Mechanical Division | 138.74 | 0 | 1.04 | 0 | 139.78 | 0 | 0 | 1.04 | 0 | 1.04 | 0.25 | 1
18 | PASCHIM MEDINIPUR | SM/13655 | ASTI AND ADJOINING MOUJAS PWSS | TSM/014385 | 40034135 | New | MVS | GO2223009605PH | 11/11/2022 | 740.59 | 40.11 | 780.7 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 20.4 | 0 | 25.18 | 4.78 | 0 | 20.4 | 0 | 25.18 | 3.23 | 2
19 | PASCHIM MEDINIPUR | SM/19051 | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | TSM/018890 | 40049053 | Augmentation | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 2324.71 | 152.02 | 2476.73 | Midnapore Division | Midnapore Mechanical Division | 15.4 | 0 | 0 | 0 | 15.4 | 0 | 0 | 0 | 0 | 0 | 0 | 5
20 | PASCHIM MEDINIPUR | SM/14485 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT DEBHOG AND OTHER 26 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | TSM/017389 | 40062013 | Augmentation | MVS | GO2223012340PH | 20/01/2023 | 0 | 54.66 | 54.66 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
21 | PASCHIM MEDINIPUR | SM/17184 | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT PIRAKATA AND OTHER 35 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | TSM/017386 | 40060316 | Augmentation | MVS | GO2223016356PH | 15/03/2023 | 0 | 72.89 | 72.89 |  | Midnapore Mechanical Division | 0 | 30.32 | 0 | 0 | 30.32 | 0 | 0 | 0 | 0 | 0 | 0 | 30
22 | PASCHIM MEDINIPUR | SM/16296 | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | TSM/011588 | 40036864 | Augmentation | SVS | GO2223014877PH | 24/02/2023 | 246.76 | 26.57 | 273.33 | Midnapore Division | Midnapore Mechanical Division | 8.54 | 4.68 | 5.51 | 0 | 18.74 | 8.54 | 4.68 | 5.51 | 0 | 18.74 | 6.85 | 15
23 | PASCHIM MEDINIPUR | SM/19050 | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/018326 | 40046984 | Augmentation | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1133.21 | 83.98 | 1217.19 | Midnapore Division | Midnapore Mechanical Division | 56.12 | 21.36 | 0 | 0 | 77.48 | 0 | 0 | 0 | 0 | 0 | 0 | 7
24 | PASCHIM MEDINIPUR | SM/13709 | Augmentation of Ground Based Pipe Water Supply Scheme for Belun & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/015080 | 40060041 | Augmentation | MVS | GO2223009712PH | 14/11/2022 | 213.06 | 26.57 | 239.63 | Midnapore Division | Midnapore Mechanical Division | 42.98 | 10.42 | 4.96 | 0 | 58.36 | 42.98 | 10.42 | 4.96 | 0 | 58.36 | 24.35 | 17
25 | PASCHIM MEDINIPUR | SM/19037 | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | TSM/020218 | 0 | Augmentation | MVS | 3416/PHE-28011/253/2023-SCHM CELL-Dept. of PHE | 08/11/2023 | 1672.77 | 91.92 | 1764.69 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | PASCHIM MEDINIPUR | SM/17946 | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | TSM/016253 | 40049997 | Augmentation | MVS | GO2223016955PH | 17/03/2023 | 524.86 | 55.99 | 580.85 | Midnapore Division | Midnapore Mechanical Division | 5.83 | 10.57 | 1.37 | 0 | 17.77 | 5.83 | 0 | 1.37 | 0 | 7.2 | 1.24 | 11
27 | PASCHIM MEDINIPUR | SM/14478 | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/014762 | 40060052 | Augmentation | MVS | GO2223012310PH | 20/01/2023 | 660.95 | 26.57 | 687.52 | Midnapore Division | Midnapore Mechanical Division | 340.95 | 16.19 | 1.89 | 0 | 359.02 | 50 | 5.48 | 1.89 | 0 | 57.36 | 8.34 | 87
28 | PASCHIM MEDINIPUR | SM/14479 | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/014863 | 40050218 | Augmentation | MVS | GO2223012307PH | 20/01/2023 | 501.96 | 26.57 | 528.53 | Midnapore Division | Midnapore Mechanical Division | 291.04 | 7.12 | 0 | 0 | 298.16 | 291.04 | 7.12 | 0 | 0 | 298.16 | 56.41 | 13
29 | PASCHIM MEDINIPUR | SM/13123 | Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/014553 | 40050133 | Augmentation | MVS | GO2223008538PH | 10/10/2022 | 455.86 | 26.57 | 482.44 | Midnapore Division | Midnapore Mechanical Division | 144.65 | 14.74 | 27.96 | 0 | 187.35 | 109.14 | 4.08 | 27.96 | 0 | 141.18 | 29.26 | 23
30 | PASCHIM MEDINIPUR | SM/15092 | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | TSM/018413 | 40036927 | Augmentation | MVS | GO2223013188PH | 04/02/2023 | 403.83 | 55.99 | 459.82 | Midnapore Division | Midnapore Mechanical Division | 87.11 | 24.94 | 3.24 | 0 | 115.3 | 7.1 | 24.94 | 3.24 | 0 | 35.28 | 7.67 | 56
31 | PASCHIM MEDINIPUR | SM/14480 | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/015518 | 40050541 | Augmentation | MVS | GO2223012304PH | 20/01/2023 | 184.53 | 26.57 | 211.1 | Midnapore Division | Midnapore Mechanical Division | 78.57 | 12.51 | 5.62 | 0 | 96.7 | 78.57 | 12.51 | 5.62 | 0 | 96.7 | 45.81 | 14
32 | PASCHIM MEDINIPUR | SM/14481 | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | TSM/015211 | 40050225 | Augmentation | MVS | GO2223012305PH | 20/01/2023 | 457.95 | 26.57 | 484.52 | Midnapore Division | Midnapore Mechanical Division | 187.54 | 7.28 | 0 | 0 | 194.82 | 2.88 | 0 | 0 | 0 | 2.88 | 0.59 | 73
33 | PASCHIM MEDINIPUR | SM/17949 | Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | TSM/015745 | 40035897 | Augmentation | MVS | GO2223016948PH | 17/03/2023 | 454.37 | 27.99 | 482.36 | Midnapore Division | Midnapore Mechanical Division | 97.75 | 3.49 | 0 | 0 | 101.24 | 97.75 | 3.49 | 0 | 0 | 101.24 | 20.99 | 76
34 | PASCHIM MEDINIPUR | SM/18191 | Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/016116 | 40048821 | Augmentation | SVS | GO2223018090PH | 30/03/2023 | 232.29 | 55.99 | 288.28 | Midnapore Division | Midnapore Mechanical Division | 25.81 | 15.72 | 0 | 0 | 41.54 | 2.14 | 0 | 0 | 0 | 2.14 | 0.74 | 17
35 | PASCHIM MEDINIPUR | SM/09923 | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | TSM/008491 | 40006991 | Augmentation | MVS | GO2122006611PH | 10/12/2021 | 961.18 | 84.47 | 1045.66 | Midnapore Division | Jhargram Mechanical Division | 372.71 | 0 | 63.43 | 0 | 436.14 | 206.32 | 0 | 63.43 | 0 | 269.75 | 25.8 | 32
36 | PASCHIM MEDINIPUR | SM/15570 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018343 | 40063829 | Augmentation | MVS | GO2223013904PH | 15/02/2023 | 299.77 | 84.47 | 384.24 | Midnapore Division | Midnapore Mechanical Division | 15.19 | 17.68 | 0 | 0 | 32.87 | 0 | 0 | 0 | 0 | 0 | 0 | 100
37 | PASCHIM MEDINIPUR | SM/15572 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018349 | 6372746 | Augmentation | MVS | GO2223013890PH | 15/02/2023 | 264.37 | 84.47 | 348.84 | Midnapore Division | Midnapore Mechanical Division | 4.2 | 17.68 | 1.72 | 0 | 23.6 | 4.2 | 0 | 1.72 | 0 | 5.92 | 1.7 | 100
38 | PASCHIM MEDINIPUR | SM/15574 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018342 | 40046946 | Augmentation | MVS | GO2223013892PH | 15/02/2023 | 391.54 | 42.24 | 433.78 | Midnapore Division | Midnapore Mechanical Division | 1.11 | 9.58 | 1.01 | 0 | 11.7 | 1.11 | 9.58 | 1.01 | 0 | 11.7 | 2.7 | 73
39 | PASCHIM MEDINIPUR | SM/11898 | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008557 | 40020403 | Augmentation | MVS | GO2223006587PH | 22/08/2022 | 1518.36 | 84.47 | 1602.83 | Midnapore Division | Midnapore Mechanical Division | 208.08 | 21.52 | 38.43 | 0 | 268.03 | 139.64 | 0 | 38.43 | 0 | 178.07 | 11.11 | 12
40 | PASCHIM MEDINIPUR | SM/13823 | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008549 | 40036745 | Augmentation | SVS | GO2223010041PH | 25/11/2022 | 167.91 | 42.24 | 210.14 | Midnapore Division | Midnapore Mechanical Division | 80.19 | 10.39 | 4.43 | 0 | 95.01 | 80.19 | 10.39 | 4.43 | 0 | 95.01 | 45.21 | 72
41 | PASCHIM MEDINIPUR | SM/13826 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | TSM/008494 | 40036645 | Augmentation | SVS | GO2223010042PH | 25/11/2022 | 239.12 | 42.24 | 281.35 | Midnapore Division | Midnapore Mechanical Division | 140.64 | 13.76 | 0 | 0 | 154.4 | 84.05 | 5.42 | 0 | 0 | 89.46 | 31.8 | 20
42 | PASCHIM MEDINIPUR | SM/10091 | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | TSM/008500 | 40007184 | Augmentation | MVS | GO2122009010PH | 01/02/2022 | 1645.45 | 126.71 | 1772.16 | Midnapore Division | Jhargram Mechanical Division | 562.7 | 11.13 | 104.44 | 0 | 678.28 | 454.71 | 11.13 | 104.44 | 0 | 570.28 | 32.18 | 51
43 | PASCHIM MEDINIPUR | SM/11880 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012022 | 40018795 | Augmentation | MVS | GO2223006437PH | 17/08/2022 | 345.75 | 42.24 | 387.99 | Midnapore Division | Midnapore Mechanical Division | 90.1 | 28.14 | 0 | 0 | 118.24 | 90.1 | 27.56 | 0 | 0 | 117.66 | 30.32 | 74
44 | PASCHIM MEDINIPUR | SM/10000 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | TSM/008553 | 40003855 | Augmentation | MVS | GO2122007049PH | 20/12/2021 | 1671.1 | 168.95 | 1840.05 | Midnapore Division | Midnapore Mechanical Division | 745.49 | 16.74 | 206.44 | 0 | 968.67 | 584.62 | 3.33 | 206.44 | 0 | 794.39 | 43.17 | 10
45 | PASCHIM MEDINIPUR | SM/18506 | Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/009166 | 40050725 | Augmentation | MVS | 2040/PHE-28011/17/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1284.16 | 126.71 | 1410.87 | Midnapore Division | Midnapore Mechanical Division | 94.6 | 16.87 | 0 | 0 | 111.47 | 3.88 | 0 | 0 | 0 | 3.88 | 0.27 | 4
46 | PASCHIM MEDINIPUR | SM/09430 | Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra, District - Paschim Medinipur. | TSM/008554 | 40027210 | Augmentation | MVS | GO2122005501PH | 17/11/2021 | 997.1 | 0 | 997.1 | Midnapore Division | Midnapore Mechanical Division | 611.05 | 0 | 76.32 | 0 | 687.37 | 534.31 | 0 | 76.32 | 0 | 610.63 | 61.24 | 10
47 | PASCHIM MEDINIPUR | SM/17395 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018218 | 40059683 | Augmentation | MVS | GO2223016349PH | 15/03/2023 | 162.04 | 0 | 162.04 | Midnapore Division |  | 3.25 | 0 | 0.43 | 0 | 3.69 | 1.23 | 0 | 0.43 | 0 | 1.66 | 1.03 | 100
48 | PASCHIM MEDINIPUR | SM/15576 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018213 | 40047109 | Augmentation | MVS | GO2223013891PH | 15/02/2023 | 412.64 | 0 | 412.64 | Midnapore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
49 | PASCHIM MEDINIPUR | SM/09933 | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | TSM/008584 | 40006982 | Augmentation | MVS | GO2122006699PH | 13/12/2021 | 810.35 | 92.2 | 902.55 | Midnapore Division | Jhargram Mechanical Division | 386.74 | 0 | 93.53 | 0 | 480.27 | 382.05 | 0 | 93.53 | 0 | 475.58 | 52.69 | 23
50 | PASCHIM MEDINIPUR | SM/12825 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012018 | 40024553 | Augmentation | MVS | GO2223008117PH | 22/09/2022 | 329.84 | 84.47 | 414.31 | Midnapore Division | Midnapore Mechanical Division | 43.81 | 18.01 | 0 | 0 | 61.82 | 17.28 | 7.36 | 0 | 0 | 24.64 | 5.95 | 77
51 | PASCHIM MEDINIPUR | SM/13822 | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | TSM/008555 | 40036736 | Augmentation | SVS | GO2223010040PH | 25/11/2022 | 354.83 | 84.74 | 439.58 | Midnapore Division | Midnapore Mechanical Division | 68.8 | 20.37 | 0 | 0 | 89.17 | 68.8 | 20.37 | 0 | 0 | 89.17 | 20.29 | 5
52 | PASCHIM MEDINIPUR | SM/17396 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018341 | 40059482 | Augmentation | SVS | GO2223016348PH | 15/03/2023 | 169.98 | 84.47 | 254.45 | Midnapore Division | Midnapore Mechanical Division | 0.81 | 13.95 | 0.2 | 0 | 14.96 | 0.81 | 0 | 0.2 | 0 | 1.01 | 0.4 | 15
53 | PASCHIM MEDINIPUR | SM/10124 | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | TSM/008498 | 40010379 | Augmentation | MVS | GO2122009286PH | 08/02/2022 | 880.97 | 168.95 | 1049.92 | Midnapore Division | Midnapore Mechanical Division | 487.89 | 37.01 | 55.56 | 0 | 580.46 | 318.67 | 20.6 | 55.56 | 0 | 394.82 | 37.6 | 56
54 | PASCHIM MEDINIPUR | SM/09979 | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | TSM/008559 | 40007023 | Augmentation | MVS | GO2122006878PH | 16/12/2021 | 853.12 | 168.95 | 1022.06 | Midnapore Division | Midnapore Mechanical Division | 577.02 | 22.68 | 6.62 | 0 | 606.31 | 531.74 | 8.73 | 6.62 | 0 | 547.09 | 53.53 | 68
55 | PASCHIM MEDINIPUR | SM/09431 | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | TSM/008552 | 40018306 | Augmentation | MVS | GO2122005500PH | 17/11/2021 | 589.71 | 0 | 589.71 | Midnapore Division |  | 302.72 | 0 | 12.33 | 0 | 315.04 | 297.5 | 0 | 12.33 | 0 | 309.82 | 52.54 | 76
56 | PASCHIM MEDINIPUR | SM/09432 | Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur. | TSM/008485 | 40027245 | Augmentation | MVS | GO2122005500PH | 17/11/2021 | 323.02 | 0 | 323.02 | Midnapore Division | Midnapore Mechanical Division | 124.72 | 11.65 | 7.59 | 0 | 143.97 | 124.72 | 0 | 7.59 | 0 | 132.31 | 40.96 | 26
57 | PASCHIM MEDINIPUR | SM/15084 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018354 | 6848018 | Augmentation | MVS | GO2223013191PH | 04/02/2023 | 365.97 | 42.24 | 408.2 | Midnapore Division | Midnapore Mechanical Division | 31.63 | 0 | 3.22 | 0 | 34.85 | 22.21 | 0 | 3.22 | 0 | 25.42 | 6.23 | 4
58 | PASCHIM MEDINIPUR | SM/10839 | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009942 | 40014619 | Augmentation | MVS | GO2223003643PH | 30/05/2022 | 854.03 | 42.24 | 896.27 | Midnapore Division | Midnapore Mechanical Division | 724.88 | 10.96 | 25.82 | 0 | 761.65 | 550.83 | 2.3 | 25.82 | 0 | 578.95 | 64.6 | 23
59 | PASCHIM MEDINIPUR | SM/15578 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018368 | 6348257 | Augmentation | MVS | GO2223013898PH | 15/02/2023 | 221.26 | 42.24 | 263.49 | Midnapore Division | Midnapore Mechanical Division | 7.52 | 0 | 2.11 | 0 | 9.63 | 0 | 0 | 2.11 | 0 | 2.11 | 0.8 | 100
60 | PASCHIM MEDINIPUR | SM/09999 | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | TSM/008832 | 40003885 | Augmentation | MVS | GO2122007048PH | 20/12/2021 | 923.51 | 84.47 | 1007.98 | Midnapore Division | Midnapore Mechanical Division | 694.92 | 20.93 | 21.67 | 0 | 737.52 | 694.92 | 20.93 | 21.67 | 0 | 737.52 | 73.17 | 52
61 | PASCHIM MEDINIPUR | SM/15072 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018372 | 40047956 | Augmentation | MVS | GO2223013184PH | 04/02/2023 | 267.74 | 42.24 | 309.98 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
62 | PASCHIM MEDINIPUR | SM/09585 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | TSM/008556 | 40000106 | Augmentation | MVS | GO2122005673PH | 22/11/2021 | 693.96 | 84.47 | 778.43 | Midnapore Division | Midnapore Mechanical Division | 249.26 | 20.91 | 55.31 | 0 | 325.48 | 249.26 | 20.91 | 55.31 | 0 | 325.48 | 41.81 | 63
63 | PASCHIM MEDINIPUR | SM/09455 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | TSM/008496 | 40000104 | Augmentation | MVS | GO2122005600PH | 19/11/2021 | 195.44 | 42.24 | 237.68 | Midnapore Division | Midnapore Mechanical Division | 53.09 | 14.81 | 12.81 | 0 | 80.71 | 37.47 | 10.16 | 12.81 | 0 | 60.44 | 25.43 | 58
64 | PASCHIM MEDINIPUR | SM/12826 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012024 | 40024574 | Augmentation | MVS | GO2223008119PH | 22/09/2022 | 296 | 84.47 | 380.48 | Midnapore Division | Midnapore Mechanical Division | 26.4 | 11.15 | 0 | 0 | 37.56 | 6.99 | 11.15 | 0 | 0 | 18.15 | 4.77 | 22
65 | PASCHIM MEDINIPUR | SM/12827 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/012025 | 40024128 | Augmentation | MVS | GO2223008120PH | 22/09/2022 | 426.33 | 42.24 | 468.57 | Midnapore Division | Midnapore Mechanical Division | 28.56 | 0 | 0 | 0 | 28.56 | 28.56 | 0 | 0 | 0 | 28.56 | 6.09 | 5
66 | PASCHIM MEDINIPUR | SM/16999 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/018179 | 40059581 | Augmentation | SVS | GO2223016503PH | 16/03/2023 | 170.91 | 84.47 | 255.39 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83
67 | PASCHIM MEDINIPUR | SM/09980 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | TSM/008495 | 40007004 | Augmentation | MVS | GO2122006877PH | 16/12/2021 | 1095.63 | 126.71 | 1222.34 | Midnapore Division | Midnapore Mechanical Division | 606.02 | 44.23 | 155.05 | 0 | 805.29 | 606.02 | 41.59 | 155.05 | 0 | 802.66 | 65.67 | 15
68 | PASCHIM MEDINIPUR | SM/15905 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/018382 | 6348345 | Augmentation | MVS | GO2223013894PH | 15/02/2023 | 316.19 | 84.47 | 400.66 | Midnapore Division | Midnapore Mechanical Division | 44 | 15.68 | 6.15 | 0 | 65.83 | 4.2 | 0 | 6.15 | 0 | 10.34 | 2.58 | 3
69 | PASCHIM MEDINIPUR | SM/15567 | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | TSM/018377 | 40046811 | Augmentation | MVS | GO2223013901PH | 15/02/2023 | 286.45 | 84.47 | 370.93 | Midnapore Division | Midnapore Mechanical Division | 11.74 | 13.67 | 0 | 0 | 25.41 | 4.2 | 0 | 0 | 0 | 4.2 | 1.13 | 88
70 | PASCHIM MEDINIPUR | SM/15569 | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | TSM/018394 | 40046859 | Augmentation | MVS | GO2223013900PH | 15/02/2023 | 426.81 | 42.24 | 469.04 | Midnapore Division | Jhargram Mechanical Division | 29 | 3.22 | 18.28 | 0 | 50.51 | 29 | 3.22 | 18.28 | 0 | 50.51 | 10.77 | 55
71 | PASCHIM MEDINIPUR | SM/17000 | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. | TSM/020423 | 40059720 | Augmentation | MVS | GO2223016498PH | 16/03/2023 | 877.42 | 54.2 | 931.61 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
72 | PASCHIM MEDINIPUR | SM/13753 | BABAIBASA AND ADJOINING MOUJAS PWSS | TSM/014992 | 40033948 | New | MVS | GO2223009800PH | 17/11/2022 | 349.48 | 38.33 | 387.81 | Midnapore Division | Jhargram Mechanical Division | 25.24 | 0 | 0 | 0 | 25.24 | 0 | 0 | 0 | 0 | 0 | 0 | 1
73 | PASCHIM MEDINIPUR | SM/13754 | BABALPUR AND ADJOINING MOUJAS PWSS | TSM/014504 | 40034187 | New | MVS | GO2223009798PH | 17/11/2022 | 423.48 | 38.53 | 462.01 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 0 | 0 | 4.78 | 4.78 | 0 | 0 | 0 | 4.78 | 1.03 | 1
74 | PASCHIM MEDINIPUR | SM/13805 | BAGBASA AND ADJOINING MOUJAS PWSS | TSM/014986 | 40034070 | New | MVS | GO2223009964PH | 22/11/2022 | 495.18 | 37.78 | 532.96 | Midnapore Division | Jhargram Mechanical Division | 75.94 | 9.63 | 51.03 | 0 | 136.6 | 0 | 9.63 | 51.03 | 0 | 60.67 | 11.38 | 2
75 | PASCHIM MEDINIPUR | SM/14690 | BAGDOBA AND ADJOINING MOUJAS PWSS | TSM/016495 | 40033440 | New | MVS | GO2223012732PH | 31/01/2023 | 353.24 | 54.59 | 407.83 | Midnapore Division | Jhargram Mechanical Division | 23.66 | 0 | 4.92 | 0 | 28.58 | 4.78 | 0 | 4.92 | 0 | 9.7 | 2.38 | 1
76 | PASCHIM MEDINIPUR | SM/19052 | BAGRUI AND ITS ADJOINING MOUZAS PWSS | TSM/017511 | 40044556 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1194.95 | 42.8 | 1237.75 | Midnapore Division | Midnapore Mechanical Division | 0 | 20.82 | 0 | 0 | 20.82 | 0 | 0 | 0 | 0 | 0 | 0 | 1
77 | PASCHIM MEDINIPUR | SM/17623 | BAGUYAN AND IT'S ADJOINING MOUJAS PWSS | TSM/011859 | 40033382 | New | MVS | GO2223017415PH | 21/03/2023 | 476.96 | 38.28 | 515.24 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 9.58 | 0 | 9.58 | 0 | 0 | 9.58 | 0 | 9.58 | 1.86 | 1
78 | PASCHIM MEDINIPUR | SM/13755 | BAHURUPA AND ADJOINING MOUJAS PWSS | TSM/014436 | 40034012 | New | MVS | GO2223009797PH | 17/11/2022 | 552.23 | 38.53 | 590.76 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 1.71 | 0 | 6.49 | 4.78 | 0 | 1.71 | 0 | 6.49 | 1.1 | 1
79 | PASCHIM MEDINIPUR | SM/18658 | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | TSM/017510 | 40036357 | New | MVS | 2231/PHE-28011/21/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1175.02 | 41.23 | 1216.26 | Midnapore Division | Midnapore Mechanical Division | 0 | 15.55 | 14.31 | 0 | 29.86 | 0 | 0 | 14.31 | 0 | 14.31 | 1.18 | 2
80 | PASCHIM MEDINIPUR | SM/12199 | BAKALSABAKARAM PWSS | TSM/011656 | 40021327 | New | MVS | GO2223007212PH | 07/09/2022 | 565.6 | 38.2 | 603.79 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 12.37 | 0 | 12.37 | 0 | 0 | 12.37 | 0 | 12.37 | 2.05 | 1
81 | PASCHIM MEDINIPUR | SM/12990 | BALADAGHATA AND ADJOINING MOUJAS PWSS | TSM/014125 | 40025985 | New | MVS | GO2223008343PH | 28/09/2022 | 633.23 | 40.02 | 673.25 | Midnapore Division | Jhargram Mechanical Division | 35.82 | 0 | 14.39 | 0 | 50.21 | 0 | 0 | 0 | 0 | 0 | 0 | 1
82 | PASCHIM MEDINIPUR | SM/13063 | BALARAMPUR AND ADJOINING MOUJAS PWSS | TSM/014493 | 40029976 | New | MVS | GO2223008478PH | 29/09/2022 | 352.11 | 36.58 | 388.69 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
83 | PASCHIM MEDINIPUR | SM/14990 | BALIBANDH AND ADJOINING MOUJAS PWSS | TSM/015799 | 40035559 | New | MVS | GO2223013091PH | 04/02/2023 | 505.34 | 40.17 | 545.5 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
84 | PASCHIM MEDINIPUR | SM/12991 | BAMANBIRUA AND ADJOINING MOUJAS PWSS | TSM/014261 | 40026005 | New | MVS | GO2223008337PH | 28/09/2022 | 515.74 | 38.61 | 554.34 | Midnapore Division | Midnapore Mechanical Division | 237.59 | 19.58 | 0 | 0 | 257.17 | 69.25 | 0 | 0 | 0 | 69.25 | 12.49 | 29
85 | PASCHIM MEDINIPUR | SM/12993 | BAMANDA AND ADJOINING MOUJAS PWSS | TSM/014223 | 40026018 | New | MVS | GO2223008345PH | 28/09/2022 | 525.97 | 38.85 | 564.82 | Midnapore Division | Midnapore Mechanical Division | 234.53 | 4.5 | 2.4 | 0 | 241.44 | 15.67 | 0 | 2.4 | 0 | 18.07 | 3.2 | 29
86 | PASCHIM MEDINIPUR | SM/13047 | BAMANSAI AND IT'S ADJOINING MOUJAS PWSS | TSM/013156 | 40031751 | New | MVS | GO2223008497PH | 29/09/2022 | 338.78 | 37.83 | 376.6 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
87 | PASCHIM MEDINIPUR | SM/13064 | BANAMALIPUR AND ADJOINING MOUJAS PWSS | TSM/015010 | 40029901 | New | MVS | GO2223008475PH | 29/09/2022 | 433.49 | 37.8 | 471.29 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
88 | PASCHIM MEDINIPUR | SM/13065 | BANKIBANDH AND ADJOINING MOUJAS PWSS | TSM/014956 | 40031740 | New | MVS | GO2223008496PH | 29/09/2022 | 371.43 | 37.82 | 409.26 | Midnapore Division | Jhargram Mechanical Division | 13.09 | 0 | 0 | 0 | 13.09 | 0 | 0 | 0 | 0 | 0 | 0 | 2
89 | PASCHIM MEDINIPUR | SM/12200 | BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS | TSM/013141 | 40021345 | New | MVS | GO2223007233PH | 07/09/2022 | 238.3 | 37.8 | 276.09 | Midnapore Division | Midnapore Mechanical Division | 87.37 | 0 | 2.53 | 0 | 89.9 | 0 | 0 | 2.53 | 0 | 2.53 | 0.92 | 1
90 | PASCHIM MEDINIPUR | SM/14941 | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | TSM/014437 | 40034011 | New | MVS | GO2223012938PH | 03/02/2023 | 430.97 | 38.61 | 469.58 | Midnapore Division | Midnapore Mechanical Division | 50.74 | 5.26 | 9.55 | 0 | 65.56 | 0 | 0 | 9.55 | 0 | 9.55 | 2.03 | 2
91 | PASCHIM MEDINIPUR | SM/13066 | BARABOLABANDI AND ADJOINING MOUJAS PWSS | TSM/014850 | 40030023 | New | MVS | GO2223008485PH | 29/09/2022 | 327.32 | 37.66 | 364.98 | Midnapore Division | Jhargram Mechanical Division | 57.59 | 9.67 | 5.93 | 0 | 73.19 | 4.78 | 0 | 5.93 | 0 | 10.71 | 2.93 | 1
92 | PASCHIM MEDINIPUR | SM/12201 | BARAGARH PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | TSM/011732 | 40021312 | New | MVS | GO2223007204PH | 07/09/2022 | 414.76 | 37.89 | 452.65 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
93 | PASCHIM MEDINIPUR | SM/14991 | BARAKADRA AND ADJOINING MOUJAS PWSS | TSM/015848 | 40035386 | New | MVS | GO2223013052PH | 04/02/2023 | 443.76 | 39.18 | 482.93 | Midnapore Division | Jhargram Mechanical Division | 74.04 | 4.04 | 8.68 | 0 | 86.76 | 4.78 | 4.04 | 8.68 | 0 | 17.5 | 3.62 | 1
94 | PASCHIM MEDINIPUR | SM/13067 | BARAKALANKI AND ADJOINING MOUJAS PWSS | TSM/014283 | 40031763 | New | MVS | GO2223008498PH | 29/09/2022 | 541.45 | 38.61 | 580.05 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 0 | 0 | 4.78 | 4.78 | 0 | 0 | 0 | 4.78 | 0.82 | 1
95 | PASCHIM MEDINIPUR | SM/13002 | BARAKEUNDI AND ADJOINING MOUJAS PWSS | TSM/015011 | 40026203 | New | MVS | GO2223008405PH | 29/09/2022 | 482.75 | 37.9 | 520.65 | Midnapore Division | Jhargram Mechanical Division | 66.69 | 6.96 | 0 | 0 | 73.65 | 0 | 6.96 | 0 | 0 | 6.96 | 1.34 | 1
96 | PASCHIM MEDINIPUR | SM/13068 | BARAKURYA AND ADJOINING MOUJAS PWSS | TSM/014496 | 40029978 | New | MVS | GO2223008481PH | 29/09/2022 | 267.97 | 60.49 | 328.47 | Midnapore Division | Jhargram Mechanical Division | 0 | 12.13 | 0 | 0 | 12.13 | 0 | 0 | 0 | 0 | 0 | 0 | 1
97 | PASCHIM MEDINIPUR | SM/12994 | BARAMURA AND ADJOINING MOUJAS PWSS | TSM/014126 | 40025978 | New | MVS | GO2223008342PH | 28/09/2022 | 426.69 | 38.39 | 465.08 | Midnapore Division | Jhargram Mechanical Division | 37.13 | 0 | 0 | 0 | 37.13 | 0 | 0 | 0 | 0 | 0 | 0 | 1
98 | PASCHIM MEDINIPUR | SM/13003 | BARANAGARA AND ADJOINING MOUJAS PWSS | TSM/014740 | 40026236 | New | MVS | GO2223008413PH | 29/09/2022 | 378.61 | 37.78 | 416.39 | Midnapore Division | Jhargram Mechanical Division | 60.83 | 16.89 | 0 | 0 | 77.73 | 0 | 16.89 | 0 | 0 | 16.89 | 4.06 | 1
99 | PASCHIM MEDINIPUR | SM/12996 | BARANGI AND ADJOINING MOUJAS PWSS | TSM/014222 | 40025954 | New | MVS | GO2223008336PH | 28/09/2022 | 652.34 | 40.04 | 692.38 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 16.34 | 0 | 16.34 | 0 | 0 | 16.34 | 0 | 16.34 | 2.36 | 1
100 | PASCHIM MEDINIPUR | SM/18507 | BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | TSM/016340 | 40035807 | New | MVS | 2041/PHE-28011/43/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1112.5 | 44.17 | 1156.66 | Midnapore Division | Midnapore Mechanical Division | 502.08 | 0 | 81.98 | 0 | 584.06 | 0 | 0 | 21.13 | 0 | 21.13 | 1.83 | 1
101 | PASCHIM MEDINIPUR | SM/12841 | BARBHUNA BASAN STAND ALONE PWSS | TSM/014548 | 40024290 | New | SVS | GO2223008080PH | 22/09/2022 | 46.81 | 8.69 | 55.5 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
102 | PASCHIM MEDINIPUR | SM/14692 | BARDIHA AND ADJOINING MOUJAS PWSS | TSM/014467 | 40036359 | New | MVS | GO2223012725PH | 31/01/2023 | 211.99 | 19.84 | 231.83 | Midnapore Division | Jhargram Mechanical Division | 6.72 | 0 | 0 | 0 | 6.72 | 0 | 0 | 0 | 0 | 0 | 0 | 1
103 | PASCHIM MEDINIPUR | SM/13004 | BARGOPAL AND ADJOINING MOUJAS PWSS | TSM/014779 | 40026199 | New | MVS | GO2223008401PH | 29/09/2022 | 742.95 | 39.29 | 782.23 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 0 | 0 | 4.78 | 4.78 | 0 | 0 | 0 | 4.78 | 0.61 | 1
104 | PASCHIM MEDINIPUR | SM/13048 | BELDA AND IT'S ADJOINING MOUJAS | TSM/013155 | 40031461 | New | MVS | GO2223008494PH | 29/09/2022 | 487.9 | 38.28 | 526.18 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 11.38 | 0 | 16.16 | 4.78 | 0 | 11.38 | 0 | 16.16 | 3.07 | 2
105 | PASCHIM MEDINIPUR | SM/14992 | BENACHAPRA AND ADJOINING MOUJAS PWSS | TSM/015807 | 40035704 | New | MVS | GO2223013090PH | 04/02/2023 | 362.63 | 38.84 | 401.48 | Midnapore Division | Jhargram Mechanical Division | 23.25 | 9.09 | 0 | 0 | 32.34 | 0 | 9.09 | 0 | 0 | 9.09 | 2.27 | 1
106 | PASCHIM MEDINIPUR | SM/14993 | BENADIHA AND ADJOINING MOUJAS PWSS | TSM/016082 | 40034137 | New | MVS | GO2223013089PH | 04/02/2023 | 819.34 | 39.18 | 858.52 | Midnapore Division | Midnapore Mechanical Division | 327.84 | 7.72 | 0 | 0 | 335.56 | 12.64 | 0 | 0 | 0 | 12.64 | 1.47 | 20
107 | PASCHIM MEDINIPUR | SM/13069 | BENUCHA AND ADJOINING MOUJAS PWSS | TSM/014953 | 40029977 | New | MVS | GO2223008480PH | 29/09/2022 | 419.65 | 39.06 | 458.71 | Midnapore Division | Jhargram Mechanical Division | 20.34 | 3.22 | 0 | 0 | 23.56 | 0 | 3.22 | 0 | 0 | 3.22 | 0.7 | 1
108 | PASCHIM MEDINIPUR | SM/14721 | BENYA AND IT'S ADJOINING MOUJAS PWSS. | TSM/013182 | 40033298 | New | MVS | GO2223012696PH | 31/01/2023 | 581.22 | 38.28 | 619.5 | Midnapore Division | Midnapore Mechanical Division | 0 | 15.96 | 11.09 | 0 | 27.05 | 0 | 0 | 11.09 | 0 | 11.09 | 1.79 | 4
109 | PASCHIM MEDINIPUR | SM/12202 | BHAGABANPUR PIPED WATER SUPPLY SCHEME | TSM/011569 | 40021629 | New | MVS | GO2223007260PH | 07/09/2022 | 416.75 | 38.05 | 454.8 | Midnapore Division | Midnapore Mechanical Division | 0 | 10.73 | 8.75 | 0 | 19.49 | 0 | 0 | 8.75 | 0 | 8.75 | 1.92 | 4
110 | PASCHIM MEDINIPUR | SM/13005 | BHANSRA AND ADJOINING MOUJAS PWSS | TSM/014653 | 40026202 | New | MVS | GO2223008403PH | 29/09/2022 | 492.45 | 39.33 | 531.78 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 14.24 | 11.91 | 0 | 30.93 | 4.78 | 0 | 11.91 | 0 | 16.69 | 3.14 | 5
111 | PASCHIM MEDINIPUR | SM/14644 | BHATMARA AND ADJOINING MOUJAS PWSS | TSM/016781 | 40033437 | New | MVS | GO2223012736PH | 31/01/2023 | 169.98 | 18.7 | 188.68 | Midnapore Division | Jhargram Mechanical Division | 23.38 | 0 | 13.48 | 0 | 36.87 | 4.78 | 0 | 13.48 | 0 | 18.26 | 9.68 | 1
112 | PASCHIM MEDINIPUR | SM/15509 | BHATUIGERYA PIPED WATER SUPPLY SCHEME | TSM/012537 | 40036355 | New | MVS | GO2223014032PH | 16/02/2023 | 1028.03 | 36.83 | 1064.86 | Midnapore Division | Midnapore Mechanical Division | 167.46 | 8.09 | 15.73 | 0 | 191.28 | 0 | 0 | 15.73 | 0 | 15.73 | 1.48 | 1
113 | PASCHIM MEDINIPUR | SM/14825 | BHATURBANDI AND ADJOINING MOUJAS PWSS | TSM/014562 | 40036361 | New | MVS | GO2223012931PH | 03/02/2023 | 266.57 | 35.56 | 302.13 | Midnapore Division | Jhargram Mechanical Division | 11.85 | 4.02 | 0 | 0 | 15.88 | 0 | 4.02 | 0 | 0 | 4.02 | 1.33 | 1
114 | PASCHIM MEDINIPUR | SM/13070 | BHAUDI AND ADJOINING MOUJAS PWSS | TSM/015008 | 40029899 | New | MVS | GO2223008473PH | 29/09/2022 | 372.13 | 37.8 | 409.94 | Midnapore Division | Jhargram Mechanical Division | 23.52 | 0 | 0 | 0 | 23.52 | 0 | 0 | 0 | 0 | 0 | 0 | 1
115 | PASCHIM MEDINIPUR | SM/12998 | BHETIAMLA AND ADJOINING MOUJAS PWSS | TSM/014219 | 40026007 | New | MVS | GO2223008340PH | 28/09/2022 | 501.13 | 38.73 | 539.86 | Midnapore Division | Midnapore Mechanical Division | 0 | 15.98 | 11.99 | 0 | 27.97 | 0 | 0 | 11.99 | 0 | 11.99 | 2.22 | 5
116 | PASCHIM MEDINIPUR | SM/13071 | BHIKUBAR AND ADJOINING MOUJAS PWSS | TSM/014774 | 40029979 | New | MVS | GO2223008482PH | 29/09/2022 | 366.83 | 37.66 | 404.49 | Midnapore Division | Midnapore Mechanical Division | 0.96 | 22.1 | 0 | 0 | 23.07 | 0 | 0 | 0 | 0 | 0 | 0 | 5
117 | PASCHIM MEDINIPUR | SM/12203 | BIKRAMPUR PWSS | TSM/011638 | 40021624 | New | MVS | GO2223007259PH | 07/09/2022 | 423.71 | 38.05 | 461.76 | Midnapore Division | Midnapore Mechanical Division | 174.04 | 25.4 | 0 | 0 | 199.43 | 98.75 | 0 | 0 | 0 | 98.75 | 21.39 | 12
118 | PASCHIM MEDINIPUR | SM/14994 | BIRSINGPUR AND ADJOINING MOUJAS PWSS | TSM/015842 | 40033239 | New | MVS | GO2223013088PH | 04/02/2023 | 573.09 | 40.6 | 613.69 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 0 | 10.31 | 0 | 15.08 | 4.78 | 0 | 10.31 | 0 | 15.08 | 2.46 | 1
119 | PASCHIM MEDINIPUR | SM/13006 | BISHNUPUR AND ADJOINING MOUJAS PWSS | TSM/015042 | 40026204 | New | MVS | GO2223008407PH | 29/09/2022 | 288.29 | 36.08 | 324.37 | Midnapore Division | Jhargram Mechanical Division | 49.17 | 3.92 | 0 | 0 | 53.09 | 0 | 3.92 | 0 | 0 | 3.92 | 1.21 | 1
120 | PASCHIM MEDINIPUR | SM/17398 | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017562 | 40053739 | New | MVS | GO2223016350PH | 15/03/2023 | 883.57 | 79.89 | 963.46 | Midnapore Division | Midnapore Mechanical Division | 0.57 | 0 | 31.63 | 0 | 32.2 | 0.57 | 0 | 31.63 | 0 | 32.2 | 3.34 | 1
121 | PASCHIM MEDINIPUR | SM/13051 | BRAHMAN KHALISA & ADJOINING MOUZAS | TSM/013158 | 40031783 | New | MVS | GO2223008499PH | 29/09/2022 | 397.22 | 38.28 | 435.5 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 10.59 | 0 | 10.59 | 0 | 0 | 10.59 | 0 | 10.59 | 2.43 | 1
122 | PASCHIM MEDINIPUR | SM/12384 | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | TSM/013157 | 40024222 | New | MVS | GO2223007524PH | 13/09/2022 | 484.4 | 37.89 | 522.3 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
123 | PASCHIM MEDINIPUR | SM/14031 | BULANPUR AND ADJOINING MOUJAS PWSS | TSM/015902 | 40035534 | New | MVS | GO2223010520PH | 05/12/2022 | 413.21 | 48.03 | 461.25 | Midnapore Division | Jhargram Mechanical Division | 19.4 | 7.86 | 6.79 | 0 | 34.04 | 4.78 | 7.86 | 6.79 | 0 | 19.43 | 4.21 | 1
124 | PASCHIM MEDINIPUR | SM/12410 | CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS | TSM/013046 | 40024218 | New | MVS | GO2223007523PH | 13/09/2022 | 330.34 | 37.8 | 368.13 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 6.34 | 0 | 6.34 | 0 | 0 | 6.34 | 0 | 6.34 | 1.72 | 1
125 | PASCHIM MEDINIPUR | SM/12411 | CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS | TSM/013204 | 40024206 | New | MVS | GO2223007522PH | 13/09/2022 | 301.14 | 37.66 | 338.8 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
126 | PASCHIM MEDINIPUR | SM/17615 | CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSS | TSM/011854 | 40033288 | New | MVS | GO2223017408PH | 21/03/2023 | 377.84 | 38.05 | 415.89 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 8.48 | 0 | 8.48 | 0 | 0 | 8.48 | 0 | 8.48 | 2.04 | 1
127 | PASCHIM MEDINIPUR | SM/12412 | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | TSM/013111 | 40024200 | New | MVS | GO2223007521PH | 13/09/2022 | 405.61 | 37.83 | 443.43 | Midnapore Division | Midnapore Mechanical Division | 91.5 | 15.23 | 0 | 0 | 106.73 | 77.68 | 4.7 | 0 | 0 | 82.38 | 18.58 | 24
128 | PASCHIM MEDINIPUR | SM/14995 | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | TSM/016157 | 40035772 | New | MVS | GO2223013051PH | 04/02/2023 | 605.88 | 37.5 | 643.38 | Midnapore Division | Midnapore Mechanical Division | 152.83 | 2.79 | 0 | 0 | 155.62 | 0 | 0 | 0 | 0 | 0 | 0 | 2
129 | PASCHIM MEDINIPUR | SM/16259 | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | TSM/016102 | 40035763 | New | MVS | GO2223014869PH | 24/02/2023 | 573.02 | 41.42 | 614.44 | Midnapore Division | Midnapore Mechanical Division | 122.13 | 6.88 | 0 | 0 | 129.02 | 0 | 0 | 0 | 0 | 0 | 0 | 2
130 | PASCHIM MEDINIPUR | SM/14996 | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | TSM/016125 | 40035764 | New | MVS | GO2223013048PH | 04/02/2023 | 359.56 | 18.97 | 378.53 | Midnapore Division | Midnapore Mechanical Division | 14.27 | 5.77 | 1.15 | 0 | 21.19 | 0 | 0 | 1.15 | 0 | 1.15 | 0.3 | 2
131 | PASCHIM MEDINIPUR | SM/14997 | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015716 | 40034745 | New | MVS | GO2223013177PH | 04/02/2023 | 571.34 | 77.41 | 648.75 | Midnapore Division | Midnapore Mechanical Division | 3.95 | 0 | 0 | 0 | 3.95 | 3.95 | 0 | 0 | 0 | 3.95 | 0.61 | 4
132 | PASCHIM MEDINIPUR | SM/13054 | CHANDABILA & ADJOINING MOUJAS PWSS | TSM/013387 | 40031792 | New | MVS | GO2223008500PH | 29/09/2022 | 362.88 | 36.34 | 399.22 | Midnapore Division | Jhargram Mechanical Division | 87.83 | 6.83 | 0 | 0 | 94.66 | 0 | 6.83 | 0 | 0 | 6.83 | 1.71 | 1
133 | PASCHIM MEDINIPUR | SM/13074 | CHANDANA AND ADJOINING MOUJAS PWSS | TSM/014627 | 40029840 | New | MVS | GO2223008469PH | 29/09/2022 | 310.43 | 36.8 | 347.23 | Midnapore Division | Midnapore Mechanical Division | 0 | 7.4 | 0 | 20.34 | 27.73 | 0 | 0 | 0 | 20.34 | 20.34 | 5.86 | 3
134 | PASCHIM MEDINIPUR | SM/14998 | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017443 | 40034656 | New | MVS | GO2223013152PH | 04/02/2023 | 198.36 | 37.91 | 236.26 | Midnapore Division | Midnapore Mechanical Division | 0.6 | 0 | 0 | 0 | 0.6 | 0.6 | 0 | 0 | 0 | 0.6 | 0.25 | 4
135 | PASCHIM MEDINIPUR | SM/13007 | CHHATNI AND ADJOINING MOUJAS PWSS | TSM/015014 | 40026227 | New | MVS | GO2223008412PH | 29/09/2022 | 249.44 | 35.6 | 285.05 | Midnapore Division | Jhargram Mechanical Division | 10.6 | 0 | 0 | 0 | 10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1
136 | PASCHIM MEDINIPUR | SM/13078 | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | TSM/014681 | 40026286 | New | MVS | GO2223008457PH | 29/09/2022 | 515.29 | 39.33 | 554.62 | Midnapore Division | Jhargram Mechanical Division | 67.46 | 8.83 | 10.08 | 0 | 86.37 | 67.46 | 8.83 | 10.08 | 0 | 86.37 | 15.57 | 10
137 | PASCHIM MEDINIPUR | SM/18619 | CHOTA TARA AND ADJOINING MOUJAS PWSS | TSM/014555 | 40033370 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 948.37 | 74.76 | 1023.13 | Midnapore Division | Jhargram Mechanical Division | 41.95 | 0 | 53.28 | 0 | 95.23 | 0 | 0 | 53.28 | 0 | 53.28 | 5.21 | 1
138 | PASCHIM MEDINIPUR | SM/16202 | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | TSM/016000 | 40065396 | New | MVS | GO2223014804PH | 23/02/2023 | 502.93 | 0 | 502.93 | Midnapore Division | Midnapore Mechanical Division | 217.08 | 0 | 0 | 0 | 217.08 | 189.37 | 0 | 0 | 0 | 189.37 | 37.65 | 10
139 | PASCHIM MEDINIPUR | SM/12999 | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | TSM/014246 | 40026006 | New | MVS | GO2223008338PH | 28/09/2022 | 355.53 | 36.34 | 391.87 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
140 | PASCHIM MEDINIPUR | SM/17004 | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | TSM/017512 | 40053744 | New | MVS | GO2223016499PH | 16/03/2023 | 788.53 | 38.79 | 827.32 | Midnapore Division | Midnapore Mechanical Division | 13.15 | 6.4 | 0 | 0 | 19.56 | 0 | 0 | 0 | 0 | 0 | 0 | 2
141 | PASCHIM MEDINIPUR | SM/13079 | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | TSM/014628 | 40029898 | New | MVS | GO2223008472PH | 29/09/2022 | 444.44 | 37.78 | 482.22 | Midnapore Division | Midnapore Mechanical Division | 93.43 | 5.94 | 0 | 19 | 118.36 | 0 | 0 | 0 | 19 | 19 | 3.94 | 2
142 | PASCHIM MEDINIPUR | SM/13008 | DAMODARPUR AND ADJOINING MOUJAS PWSS | TSM/014491 | 40026246 | New | MVS | GO2223008416PH | 29/09/2022 | 615.66 | 60.49 | 676.15 | Midnapore Division | Jhargram Mechanical Division | 22.01 | 0 | 13.92 | 0 | 35.93 | 0 | 0 | 0 | 0 | 0 | 0 | 1
143 | PASCHIM MEDINIPUR | SM/18524 | DHARMMA PUR AND ITS ADJOINING MOUZAS PWSS | TSM/017371 | 40034448 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1071.57 | 42.81 | 1114.38 | Midnapore Division | Midnapore Mechanical Division | 89.58 | 11.19 | 0 | 0 | 100.77 | 0 | 0 | 0 | 0 | 0 | 0 | 1
144 | PASCHIM MEDINIPUR | SM/13000 | DHENGADAHA AND ADJOINING MOUJAS PWSS | TSM/014168 | 40025969 | New | MVS | GO2223008341PH | 28/09/2022 | 443.79 | 38.53 | 482.32 | Midnapore Division | Jhargram Mechanical Division | 35.5 | 0 | 13.9 | 0 | 49.41 | 0 | 0 | 0 | 0 | 0 | 0 | 1
145 | PASCHIM MEDINIPUR | SM/16374 | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | TSM/017287 | 40035788 | New | MVS | GO2223014980PH | 28/02/2023 | 745.2 | 41.07 | 786.27 | Midnapore Division | Midnapore Mechanical Division | 116.32 | 5.9 | 0 | 0 | 122.23 | 0 | 0 | 0 | 0 | 0 | 0 | 2
146 | PASCHIM MEDINIPUR | SM/13140 | DHOBABARIA AND ADJOINIONG MOUJAS PWSS | TSM/014165 | 40033887 | New | MVS | GO2223008651PH | 12/10/2022 | 655.04 | 40.25 | 695.29 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 38.02 | 0 | 38.02 | 0 | 0 | 19.01 | 0 | 19.01 | 2.73 | 1
147 | PASCHIM MEDINIPUR | SM/17005 | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | TSM/018441 | 40053727 | New | MVS | GO2223016504PH | 16/03/2023 | 694.35 | 79.57 | 773.92 | Midnapore Division | Midnapore Mechanical Division | 4.15 | 0 | 9.27 | 0 | 13.42 | 4.15 | 0 | 9.27 | 0 | 13.42 | 1.73 | 1
148 | PASCHIM MEDINIPUR | SM/12828 | DINGAL AND ITS ADJOINING MOUJAS PWSS | TSM/011799 | 40024541 | New | MVS | GO2223008116PH | 22/09/2022 | 439.41 | 38.14 | 477.55 | Midnapore Division | Midnapore Mechanical Division | 245.55 | 20.66 | 8.55 | 0 | 274.76 | 46.88 | 0 | 8.55 | 0 | 55.43 | 11.61 | 5
149 | PASCHIM MEDINIPUR | SM/14646 | Dontiara & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017444 | 40034780 | New | MVS | GO2223012712PH | 31/01/2023 | 441.94 | 76.3 | 518.24 | Midnapore Division | Midnapore Mechanical Division | 2.66 | 0 | 0 | 0 | 2.66 | 2.66 | 0 | 0 | 0 | 2.66 | 0.51 | 4
150 | PASCHIM MEDINIPUR | SM/15589 | DOSATINA AND ITS ADJOINING MOUZAS PWSS | TSM/017367 | 40044668 | New | MVS | GO2223013897PH | 15/02/2023 | 936.82 | 42.81 | 979.63 | Midnapore Division | Midnapore Mechanical Division | 14.71 | 24.94 | 19.76 | 0 | 59.42 | 0 | 0 | 19.76 | 0 | 19.76 | 2.02 | 2
151 | PASCHIM MEDINIPUR | SM/17616 | DUAN-II AND ITS ADJOINING MOUJAS PWSS | TSM/011845 | 40033286 | New | MVS | GO2223017409PH | 21/03/2023 | 499.79 | 38.14 | 537.93 | Midnapore Division | Midnapore Mechanical Division | 235.33 | 6.61 | 11.32 | 0 | 253.26 | 0 | 0 | 11.32 | 0 | 11.32 | 2.1 | 2
152 | PASCHIM MEDINIPUR | SM/18533 | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | TSM/016524 | 40035880 | New | MVS | 2052/PHE-28011/223/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1034.17 | 52.78 | 1086.95 | Midnapore Division | Midnapore Mechanical Division | 514.73 | 26.71 | 1.71 | 0 | 543.15 | 0 | 0 | 1.71 | 0 | 1.71 | 0.16 | 3
153 | PASCHIM MEDINIPUR | SM/13080 | DUDHE BUDE AND ADJOINING MOUJAS PWSS | TSM/014626 | 40026295 | New | MVS | GO2223008459PH | 29/09/2022 | 661.31 | 37.98 | 699.28 | Midnapore Division | Midnapore Mechanical Division | 52.6 | 6.98 | 15.24 | 21.31 | 96.12 | 0 | 0 | 15.24 | 21.31 | 36.54 | 5.23 | 2
154 | PASCHIM MEDINIPUR | SM/14645 | DUKI AND ADJOINING MOUJAS PWSS | TSM/017109 | 40033275 | New | MVS | GO2223012737PH | 31/01/2023 | 562.22 | 57.41 | 619.63 | Midnapore Division | Jhargram Mechanical Division | 19.37 | 10.01 | 35.07 | 0 | 64.45 | 0 | 10.01 | 0 | 0 | 10.01 | 1.61 | 1
155 | PASCHIM MEDINIPUR | SM/14032 | DUMURIA AND ADJOINING MOUJAS PWSS | TSM/015808 | 40035413 | New | MVS | GO2223010499PH | 05/12/2022 | 678.36 | 66.16 | 744.52 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 8.54 | 12.12 | 0 | 25.44 | 4.78 | 3.59 | 12.12 | 0 | 20.5 | 2.75 | 1
156 | PASCHIM MEDINIPUR | SM/13009 | DURIA AND ADJOINING MOUJAS PWSS | TSM/014268 | 40026208 | New | MVS | GO2223008411PH | 29/09/2022 | 698.67 | 40.25 | 738.92 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 3.45 | 0 | 0 | 8.23 | 4.78 | 0 | 0 | 0 | 4.78 | 0.65 | 1
157 | PASCHIM MEDINIPUR | SM/14999 | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015715 | 40034653 | New | MVS | GO2223013156PH | 04/02/2023 | 531.96 | 78.37 | 610.33 | Midnapore Division | Midnapore Mechanical Division | 211.16 | 25.17 | 14.75 | 0 | 251.08 | 152.7 | 0 | 14.75 | 0 | 167.45 | 27.44 | 12
158 | PASCHIM MEDINIPUR | SM/13081 | ELUNI PIPED WATER SUPPLY SCHEME | TSM/014921 | 40026280 | New | MVS | GO2223008449PH | 29/09/2022 | 588.63 | 37.58 | 626.21 | Midnapore Division | Midnapore Mechanical Division | 15.54 | 20.31 | 0 | 0 | 35.85 | 15.54 | 14.24 | 0 | 0 | 29.77 | 4.75 | 5
159 | PASCHIM MEDINIPUR | SM/13062 | FATEHSINGPUR AND ADJOINING MOUJAS PWSS | TSM/013503 | 40031723 | New | MVS | GO2223008495PH | 29/09/2022 | 338.63 | 36.34 | 374.97 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 13.92 | 0 | 13.92 | 0 | 0 | 0 | 0 | 0 | 0 | 1
160 | PASCHIM MEDINIPUR | SM/13082 | GAGANESHWAR AND ADJOINING MOUJAS PWSS | TSM/014662 | 40029791 | New | MVS | GO2223008461PH | 29/09/2022 | 848 | 55.39 | 903.4 | Midnapore Division | Midnapore Mechanical Division | 108.49 | 11.14 | 15.68 | 21.25 | 156.56 | 4.78 | 0 | 15.68 | 21.25 | 41.71 | 4.62 | 2
161 | PASCHIM MEDINIPUR | SM/13010 | GAHIRA AND ADJOINING MOUJAS PWSS | TSM/014271 | 40026243 | New | MVS | GO2223008415PH | 29/09/2022 | 458.93 | 38.61 | 497.53 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 0 | 0 | 4.78 | 4.78 | 0 | 0 | 0 | 4.78 | 0.96 | 1
162 | PASCHIM MEDINIPUR | SM/13083 | GAMA AND ADJOINING MOUJAS PWSS | TSM/014270 | 40026300 | New | MVS | GO2223008460PH | 29/09/2022 | 545.23 | 36.72 | 581.95 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 0 | 0 | 4.78 | 4.78 | 0 | 0 | 0 | 4.78 | 0.82 | 1
163 | PASCHIM MEDINIPUR | SM/13141 | GAMARIA PIPED WATER SUPPLY SCHEME | TSM/013580 | 40034356 | New | MVS | GO2223008648PH | 12/10/2022 | 766.27 | 38.18 | 804.45 | Midnapore Division | Midnapore Mechanical Division | 86.35 | 19.12 | 0 | 0 | 105.47 | 15.54 | 5.86 | 0 | 0 | 21.4 | 2.66 | 3
164 | PASCHIM MEDINIPUR | SM/19099 | GANGANI AND ADJOINING MOUJAS PWSS | TSM/015823 | 40033429 | New | MVS | 3714/PHE-28011/267/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1332.65 | 78.62 | 1411.27 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | PASCHIM MEDINIPUR | SM/15000 | GANUA AND ADJOINING MOUJAS PWSS | TSM/015980 | 40034061 | New | MVS | GO2223013049PH | 04/02/2023 | 831.9 | 39.84 | 871.74 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
166 | PASCHIM MEDINIPUR | SM/14090 | GARMAL AND ADJOINING MOUJAS PWSS | TSM/015815 | 40035625 | New | MVS | GO2223010860PH | 12/12/2022 | 419.88 | 62.37 | 482.26 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
167 | PASCHIM MEDINIPUR | SM/13084 | GAZIPUR PATNA AND ADJOINING MOUJAS PWSS | TSM/014325 | 40029837 | New | MVS | GO2223008463PH | 29/09/2022 | 602.36 | 40.04 | 642.4 | Midnapore Division | Midnapore Mechanical Division | 203.36 | 0.72 | 1.71 | 0 | 205.79 | 6.08 | 0 | 1.71 | 0 | 7.8 | 1.21 | 29
168 | PASCHIM MEDINIPUR | SM/14647 | GHAGRASOL AND ADJOINING MOUJAS PWSS | TSM/016783 | 40035614 | New | MVS | GO2223012729PH | 31/01/2023 | 54.36 | 8.77 | 63.13 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
169 | PASCHIM MEDINIPUR | SM/18535 | GHOSHPUR PIPED WATER SUPPLY SCHEME | TSM/013511 | 40034439 | New | MVS | 2054/PHE-28011/48/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1084.91 | 41.28 | 1126.19 | Midnapore Division | Midnapore Mechanical Division | 0 | 24.4 | 0 | 0 | 24.4 | 0 | 0 | 0 | 0 | 0 | 0 | 3
170 | PASCHIM MEDINIPUR | SM/14648 | GHRITAGRAM AND ADJOINING MOUJAS PWSS | TSM/016544 | 40034941 | New | MVS | GO2223012726PH | 31/01/2023 | 873.73 | 47.64 | 921.37 | Midnapore Division | Midnapore Mechanical Division | 34.36 | 6.58 | 1.71 | 20.3 | 62.96 | 0 | 0 | 1.71 | 20.3 | 22.02 | 2.39 | 3
171 | PASCHIM MEDINIPUR | SM/13142 | GILABANI AND ADJOINING MOUJAS PWSS | TSM/014180 | 40033758 | New | MVS | GO2223008650PH | 12/10/2022 | 647.9 | 40.25 | 688.15 | Midnapore Division | Jhargram Mechanical Division | 31.23 | 0 | 0 | 0 | 31.23 | 0 | 0 | 0 | 0 | 0 | 0 | 1
172 | PASCHIM MEDINIPUR | SM/10066 | Gobindanagar Piped Water Supply Scheme | TSM/005229 | 40006618 | New | MVS | GO2122008790PH | 27/01/2022 | 359.55 | 52.53 | 412.08 | Midnapore Division | Midnapore Mechanical Division | 317.52 | 19.14 | 8.38 | 6.19 | 351.24 | 244.28 | 16.01 | 8.38 | 6.19 | 274.86 | 66.7 | 70
173 | PASCHIM MEDINIPUR | SM/17620 | GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013168 | 40033324 | New | MVS | GO2223017414PH | 21/03/2023 | 546.33 | 38.28 | 584.61 | Midnapore Division | Midnapore Mechanical Division | 232.84 | 6.28 | 0 | 0 | 239.13 | 48.18 | 0 | 0 | 0 | 48.18 | 8.24 | 2
174 | PASCHIM MEDINIPUR | SM/13077 | GODAPIASOL AND ADJOINING MOUJAS PWSS | TSM/014977 | 40029851 | New | MVS | GO2223008471PH | 29/09/2022 | 316.81 | 36.02 | 352.83 | Midnapore Division | Jhargram Mechanical Division | 41.25 | 6.76 | 0 | 0 | 48.01 | 0 | 6.76 | 0 | 0 | 6.76 | 1.92 | 1
175 | PASCHIM MEDINIPUR | SM/15004 | GOHALDANGA AND ADJOINING MOUJAS PWSS | TSM/016065 | 40035498 | New | MVS | GO2223013047PH | 04/02/2023 | 559.61 | 48.23 | 607.84 | Midnapore Division | Jhargram Mechanical Division | 103.45 | 20.73 | 9.47 | 0 | 133.65 | 4.78 | 20.73 | 9.47 | 0 | 34.98 | 5.76 | 1
176 | PASCHIM MEDINIPUR | SM/14649 | GOKULPUR AND ADJOINING MOUJAS PWSS | TSM/016187 | 40034049 | New | MVS | GO2223012711PH | 31/01/2023 | 590.98 | 55.45 | 646.43 | Midnapore Division | Midnapore Mechanical Division | 15.13 | 0 | 9.52 | 0 | 24.65 | 4.78 | 0 | 9.52 | 0 | 14.3 | 2.21 | 1
177 | PASCHIM MEDINIPUR | SM/17617 | GOLEGRAM AND ITS ADJOINING MOUJAS PWSS | TSM/011835 | 40033317 | New | MVS | GO2223017411PH | 21/03/2023 | 642 | 38.24 | 680.25 | Midnapore Division | Midnapore Mechanical Division | 0 | 12.32 | 14.77 | 0 | 27.09 | 0 | 12.32 | 14.77 | 0 | 27.09 | 3.98 | 4
178 | PASCHIM MEDINIPUR | SM/18508 | GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEME | TSM/014933 | 40034354 | New | MVS | 2042/PHE-28011/139/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1269.48 | 127.81 | 1397.29 | Midnapore Division | Midnapore Mechanical Division | 14.14 | 9.86 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2
179 | PASCHIM MEDINIPUR | SM/19044 | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015587 | 40034917 | New | MVS | 3546/PHE-28011/198/2023-SCHM CELL-Dept. of PHE | 24/11/2023 | 1135.06 | 77.24 | 1212.3 | Midnapore Division | Midnapore Mechanical Division | 159.02 | 10.58 | 0 | 0 | 169.59 | 7.4 | 0 | 0 | 0 | 7.4 | 0.61 | 3
180 | PASCHIM MEDINIPUR | SM/12986 | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/011810 | 40025997 | New | MVS | GO2223008330PH | 28/09/2022 | 383.93 | 37.89 | 421.82 | Midnapore Division | Midnapore Mechanical Division | 94.13 | 8.09 | 0 | 0 | 102.21 | 4.78 | 0 | 0 | 0 | 4.78 | 1.13 | 2
181 | PASCHIM MEDINIPUR | SM/07964 | Gopinathpur Piped Water Supply Scheme. | TSM/005703 | 8290938 | New | MVS | GO2021004404PH | 11/01/2021 | 616.81 | 36.39 | 653.2 | Midnapore Division | Midnapore Mechanical Division | 240.63 | 22.13 | 0 | 0 | 262.76 | 135.99 | 8.08 | 0 | 0 | 144.07 | 22.06 | 5
182 | PASCHIM MEDINIPUR | SM/14651 | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017439 | 40034982 | New | SVS | GO2223012714PH | 31/01/2023 | 439.03 | 77.41 | 516.44 | Midnapore Division | Midnapore Mechanical Division | 19.05 | 20.58 | 8.33 | 0 | 47.96 | 19.05 | 0 | 8.33 | 0 | 27.38 | 5.3 | 6
183 | PASCHIM MEDINIPUR | SM/15010 | GOTSHINGLA AND ADJOINING MOUJAS PWSS | TSM/016085 | 40035429 | New | MVS | GO2223013053PH | 04/02/2023 | 294.27 | 36.76 | 331.03 | Midnapore Division | Jhargram Mechanical Division | 19.91 | 3.68 | 0 | 0 | 23.59 | 0 | 3.68 | 0 | 0 | 3.68 | 1.11 | 1
184 | PASCHIM MEDINIPUR | SM/13076 | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | TSM/014580 | 40030026 | New | MVS | GO2223008489PH | 29/09/2022 | 892.61 | 39.41 | 932.03 | Midnapore Division | Midnapore Mechanical Division | 57.95 | 0 | 20.99 | 0 | 78.95 | 4.78 | 0 | 20.99 | 0 | 25.77 | 2.77 | 1
185 | PASCHIM MEDINIPUR | SM/11858 | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009250 | 40018793 | New | SVS | GO2223006396PH | 17/08/2022 | 104.18 | 15.07 | 119.24 | Midnapore Division | Midnapore Mechanical Division | 78.5 | 11.16 | 0 | 0 | 89.66 | 40.49 | 5.71 | 0 | 0 | 46.2 | 38.75 | 51
186 | PASCHIM MEDINIPUR | SM/10648 | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009245 | 40033734 | New | SVS | GO2223000499PH | 22/04/2022 | 95.7 | 15.07 | 110.76 | Midnapore Division | Midnapore Mechanical Division | 73.75 | 11.16 | 0 | 0 | 84.9 | 73.75 | 11.16 | 0 | 0 | 84.9 | 76.65 | 85
187 | PASCHIM MEDINIPUR | SM/09681 | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | TSM/008458 | 40002530 | New | SVS | GO2122005818PH | 24/11/2021 | 208.84 | 30.13 | 238.97 | Midnapore Division | Midnapore Mechanical Division | 187.66 | 26.45 | 5.54 | 0 | 219.65 | 187.02 | 26.45 | 5.54 | 0 | 219.02 | 91.65 | 76
188 | PASCHIM MEDINIPUR | SM/09441 | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | TSM/008114 | 40002283 | New | SVS | GO2122004669PH | 29/10/2021 | 32.59 | 7.53 | 40.12 | Midnapore Division | Midnapore Mechanical Division | 30.83 | 4.38 | 0 | 0 | 35.22 | 30.83 | 4.38 | 0 | 0 | 35.22 | 87.78 | 100
189 | PASCHIM MEDINIPUR | SM/10649 | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | TSM/010638 | 40014397 | New | MVS | GO2223000500PH | 22/04/2022 | 796.7 | 53.14 | 849.85 | Midnapore Division | Midnapore Mechanical Division | 294.06 | 27.43 | 43.87 | 17.71 | 383.08 | 294.06 | 27.43 | 43.87 | 17.71 | 383.08 | 45.08 | 56
190 | PASCHIM MEDINIPUR | SM/10658 | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | TSM/009246 | 40014735 | New | SVS | GO2223000514PH | 22/04/2022 | 88.51 | 15.07 | 103.58 | Midnapore Division | Midnapore Mechanical Division | 65.92 | 13.29 | 0 | 0 | 79.21 | 4.21 | 9.06 | 0 | 0 | 13.27 | 12.81 | 13
191 | PASCHIM MEDINIPUR | SM/17008 | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR | TSM/017509 | 40054163 | New | SVS | GO2223016502PH | 16/03/2023 | 34.57 | 7.94 | 42.51 | Midnapore Division | Jhargram Mechanical Division | 27.57 | 0 | 0 | 0 | 27.57 | 5.31 | 0 | 0 | 0 | 5.31 | 12.5 | 2
192 | PASCHIM MEDINIPUR | SM/10003 | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | TSM/009189 | 40008706 | New | SVS | GO2122007167PH | 22/12/2021 | 180.95 | 30.13 | 211.08 | Midnapore Division | Midnapore Mechanical Division | 123.7 | 21.29 | 4.04 | 0 | 149.02 | 121.38 | 16.59 | 4.04 | 0 | 142.01 | 67.28 | 77
193 | PASCHIM MEDINIPUR | SM/09439 | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | TSM/008113 | 40004888 | New | SVS | GO2122004669PH | 29/10/2021 | 38.41 | 7.53 | 45.94 | Midnapore Division | Midnapore Mechanical Division | 36.16 | 4.13 | 0 | 0 | 40.29 | 36.16 | 4 | 0 | 0 | 40.16 | 87.42 | 100
194 | PASCHIM MEDINIPUR | SM/09682 | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | TSM/008457 | 40004872 | New | SVS | GO2122005818PH | 24/11/2021 | 27.42 | 7.53 | 34.95 | Midnapore Division | Midnapore Mechanical Division | 23.72 | 6.8 | 0.67 | 0 | 31.19 | 23.72 | 6.67 | 0.67 | 0 | 31.06 | 88.87 | 25
195 | PASCHIM MEDINIPUR | SM/15220 | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009243 | 40032889 | New | SVS | GO2223013466PH | 07/02/2023 | 97.27 | 15.07 | 112.33 | Midnapore Division | Midnapore Mechanical Division | 73.36 | 10.72 | 0 | 0 | 84.07 | 13.23 | 0 | 0 | 0 | 13.23 | 11.77 | 19
196 | PASCHIM MEDINIPUR | SM/09680 | Ground Based Mini Piped Water Supply Scheme for Haripura mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008463 | 40004710 | New | SVS | GO2122005818PH | 24/11/2021 | 41.27 | 7.53 | 48.8 | Midnapore Division | Midnapore Mechanical Division | 39.03 | 6.66 | 1.04 | 0 | 46.73 | 36.49 | 6.66 | 1.04 | 0 | 44.19 | 90.54 | 29
197 | PASCHIM MEDINIPUR | SM/10655 | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009249 | 40014743 | New | SVS | GO2223000510PH | 22/04/2022 | 95.03 | 15.07 | 110.1 | Midnapore Division | Midnapore Mechanical Division | 73.72 | 11.79 | 0 | 0 | 85.51 | 73.72 | 11.24 | 0 | 0 | 84.96 | 77.16 | 78
198 | PASCHIM MEDINIPUR | SM/09684 | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008448 | 40002463 | New | MVS | GO2122005818PH | 24/11/2021 | 49.75 | 7.53 | 57.28 | Midnapore Division | Midnapore Mechanical Division | 45.59 | 6.92 | 1.27 | 0 | 53.78 | 45.59 | 6.92 | 1.27 | 0 | 53.78 | 93.88 | 80
199 | PASCHIM MEDINIPUR | SM/10717 | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009248 | 40014749 | New | SVS | GO2223002123PH | 18/05/2022 | 48.56 | 7.53 | 56.09 | Midnapore Division | Midnapore Mechanical Division | 0 | 5.55 | 0 | 0 | 5.55 | 0 | 0.13 | 0 | 0 | 0.13 | 0.22 | 12
200 | PASCHIM MEDINIPUR | SM/09675 | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | TSM/008487 | 40005314 | New | MVS | GO2122005818PH | 24/11/2021 | 56.64 | 15.07 | 71.71 | Midnapore Division | Midnapore Mechanical Division | 41.9 | 14.42 | 1.3 | 0 | 57.63 | 40.81 | 14.42 | 1.3 | 0 | 56.54 | 78.85 | 100
201 | PASCHIM MEDINIPUR | SM/09677 | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | TSM/008478 | 40005295 | New | SVS | GO2122005818PH | 24/11/2021 | 29.96 | 7.53 | 37.49 | Midnapore Division | Midnapore Mechanical Division | 21.88 | 6.52 | 0.58 | 0 | 28.98 | 21.88 | 6.52 | 0.58 | 0 | 28.98 | 77.3 | 76
202 | PASCHIM MEDINIPUR | SM/18785 | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur | TSM/009247 | 40048958 | New | SVS | PHE/IV/2608/W-641/23 | 29/08/2023 | 37.34 | 7.53 | 44.88 | Midnapore Division | Midnapore Mechanical Division | 17.7 | 0.1 | 0 | 0 | 17.8 | 17.7 | 0.1 | 0 | 0 | 17.8 | 39.67 | 2
203 | PASCHIM MEDINIPUR | SM/10002 | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | TSM/009187 | 40008696 | New | SVS | GO2122007167PH | 22/12/2021 | 85.48 | 15.07 | 100.55 | Midnapore Division | Midnapore Mechanical Division | 60.04 | 11.13 | 1.64 | 0 | 72.81 | 34.28 | 10.61 | 1.64 | 0 | 46.53 | 46.28 | 57
204 | PASCHIM MEDINIPUR | SM/09679 | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008475 | 40005301 | New | SVS | GO2122005818PH | 24/11/2021 | 23.47 | 7.53 | 31 | Midnapore Division | Midnapore Mechanical Division | 20.73 | 4.1 | 0.31 | 0 | 25.14 | 20.45 | 4.1 | 0.31 | 0 | 24.87 | 80.21 | 57
205 | PASCHIM MEDINIPUR | SM/09442 | Ground Based Mini Piped Water Supply Scheme For Nankarnila Mouzas | TSM/008115 | 40002331 | New | SVS | GO2122004669PH | 29/10/2021 | 36.2 | 7.53 | 43.73 | Midnapore Division | Midnapore Mechanical Division | 34.89 | 6.64 | 0 | 0 | 41.53 | 34.89 | 6.51 | 0 | 0 | 41.4 | 94.68 | 100
206 | PASCHIM MEDINIPUR | SM/09683 | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008454 | 40002349 | New | SVS | GO2122005818PH | 24/11/2021 | 101.39 | 15.07 | 116.45 | Midnapore Division | Midnapore Mechanical Division | 94.52 | 12.94 | 2.92 | 0 | 110.37 | 93.31 | 12.94 | 2.92 | 0 | 109.16 | 93.74 | 76
207 | PASCHIM MEDINIPUR | SM/09676 | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008479 | 40002347 | New | SVS | GO2122005818PH | 24/11/2021 | 43.95 | 7.53 | 51.48 | Midnapore Division | Midnapore Mechanical Division | 41.28 | 4 | 1.39 | 0 | 46.67 | 41.28 | 4 | 1.39 | 0 | 46.67 | 90.65 | 100
208 | PASCHIM MEDINIPUR | SM/10657 | Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | TSM/009244 | 40014394 | New | SVS | GO2223000516PH | 22/04/2022 | 142.86 | 22.6 | 165.46 | Midnapore Division | Midnapore Mechanical Division | 80.89 | 11.68 | 0 | 0 | 92.57 | 80.89 | 11.13 | 0 | 0 | 92.02 | 55.62 | 76
209 | PASCHIM MEDINIPUR | SM/09440 | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | TSM/008112 | 40004859 | New | SVS | GO2122004669PH | 29/10/2021 | 39.79 | 7.53 | 47.32 | Midnapore Division | Midnapore Mechanical Division | 22.67 | 6.67 | 0 | 0 | 29.35 | 22.67 | 7.82 | 0 | 0 | 30.49 | 64.44 | 100
210 | PASCHIM MEDINIPUR | SM/09678 | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | TSM/008476 | 40002471 | New | SVS | GO2122005818PH | 24/11/2021 | 76.56 | 15.07 | 91.62 | Midnapore Division | Midnapore Mechanical Division | 70.75 | 13.17 | 1.93 | 0 | 85.85 | 68.62 | 12.92 | 1.93 | 0 | 83.46 | 91.09 | 76
211 | PASCHIM MEDINIPUR | SM/09795 | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | TSM/008489 | 40003746 | New | SVS | GO2122006297PH | 01/12/2021 | 116.29 | 0 | 116.29 | Midnapore Division | Midnapore Mechanical Division | 96.35 | 0 | 2.28 | 0 | 98.63 | 96.35 | 0 | 2.28 | 0 | 98.63 | 84.82 | 90
212 | PASCHIM MEDINIPUR | SM/19049 | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017678 | 40043840 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1255.39 | 167.97 | 1423.36 | Midnapore Division | Midnapore Mechanical Division | 0.29 | 10.96 | 0 | 0 | 11.26 | 0 | 0 | 0 | 0 | 0 | 0 | 12
213 | PASCHIM MEDINIPUR | SM/15533 | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015517 | 40034848 | New | MVS | GO2223013987PH | 16/02/2023 | 1528.77 | 151.48 | 1680.25 | Midnapore Division | Midnapore Mechanical Division | 70.88 | 29.57 | 7.03 | 0 | 107.48 | 0 | 0 | 7.03 | 0 | 7.03 | 0.42 | 2
214 | PASCHIM MEDINIPUR | SM/18622 | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | TSM/012901 | 40034716 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1264.55 | 106.28 | 1370.84 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
215 | PASCHIM MEDINIPUR | SM/19053 | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017559 | 40044206 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1376.89 | 127.85 | 1504.74 | Midnapore Division | Midnapore Mechanical Division | 0 | 27.1 | 0 | 0 | 27.1 | 0 | 0 | 0 | 0 | 0 | 0 | 3
216 | PASCHIM MEDINIPUR | SM/18539 | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | TSM/020284 | 40053751 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1200.51 | 111.98 | 1312.49 | Midnapore Division | Midnapore Mechanical Division | 6.81 | 0 | 31.98 | 0 | 38.79 | 0 | 0 | 31.98 | 0 | 31.98 | 2.44 | 1
217 | PASCHIM MEDINIPUR | SM/12875 | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | TSM/011782 | 40024617 | New | MVS | GO2223008168PH | 23/09/2022 | 1343.8 | 106.28 | 1450.08 | Midnapore Division | Midnapore Mechanical Division | 130.72 | 56.13 | 0 | 0 | 186.85 | 23.86 | 4.7 | 0 | 0 | 28.56 | 1.97 | 8
218 | PASCHIM MEDINIPUR | SM/17558 | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | TSM/020257 | 40054155 | New | MVS | GO2223017029PH | 18/03/2023 | 529.05 | 55.99 | 585.04 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 9.07 | 0 | 9.07 | 0 | 0 | 9.07 | 0 | 9.07 | 1.55 | 1
219 | PASCHIM MEDINIPUR | SM/19102 | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | TSM/013481 | 40034767 | New | MVS | 3715/PHE-28011/265/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1335.41 | 113.82 | 1449.22 | Midnapore Division | Midnapore Mechanical Division | 0 | 10.96 | 0 | 0 | 10.96 | 0 | 0 | 0 | 0 | 0 | 0 | 2
220 | PASCHIM MEDINIPUR | SM/19048 | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017300 | 40044543 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 1051.16 | 111.98 | 1163.14 | Midnapore Division | Midnapore Mechanical Division | 30.86 | 0 | 0 | 0 | 30.86 | 0 | 0 | 0 | 0 | 0 | 0 | 9
221 | PASCHIM MEDINIPUR | SM/18621 | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | TSM/012657 | 40034735 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1659.55 | 121.35 | 1780.9 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
222 | PASCHIM MEDINIPUR | SM/14483 | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015079 | 40035690 | New | MVS | GO2223012272PH | 20/01/2023 | 991.62 | 121.35 | 1112.97 | Midnapore Division | Midnapore Mechanical Division | 216.2 | 43 | 21.96 | 0 | 281.16 | 24.95 | 36.45 | 21.96 | 0 | 83.36 | 7.49 | 13
223 | PASCHIM MEDINIPUR | SM/11622 | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | TSM/011566 | 40017903 | New | MVS | GO2223005555PH | 26/07/2022 | 848.95 | 53.14 | 902.09 | Midnapore Division | Midnapore Mechanical Division | 234.7 | 35.01 | 0.01 | 0 | 269.72 | 213.62 | 35.01 | 0.01 | 0 | 248.63 | 27.56 | 59
224 | PASCHIM MEDINIPUR | SM/14492 | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/016252 | 40035316 | New | MVS | GO2223012354PH | 20/01/2023 | 741.75 | 79.8 | 821.55 | Midnapore Division | Midnapore Mechanical Division | 331.92 | 30.38 | 2.7 | 0 | 365 | 164.62 | 0 | 2.7 | 0 | 167.31 | 20.37 | 47
225 | PASCHIM MEDINIPUR | SM/18758 | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. | TSM/012658 | 40036188 | New | MVS | 2525/PHE/IV/W-638/23 | 23/08/2023 | 759.63 | 53.14 | 812.77 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
226 | PASCHIM MEDINIPUR | SM/11879 | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | TSM/011673 | 40018787 | New | MVS | GO2223006377PH | 17/08/2022 | 589.43 | 53.14 | 642.57 | Midnapore Division | Midnapore Mechanical Division | 120.91 | 21.17 | 0 | 0 | 142.08 | 111.71 | 21.17 | 0 | 0 | 132.88 | 20.68 | 6
227 | PASCHIM MEDINIPUR | SM/18192 | Ground Based Pipe Water Supply Scheme for Keshuria (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017301 | 40053813 | New | MVS | GO2223018115PH | 31/03/2023 | 494.2 | 71.86 | 566.06 | Midnapore Division | Midnapore Mechanical Division | 14.67 | 4.55 | 4.46 | 0 | 23.67 | 9.59 | 4.55 | 4.46 | 0 | 18.6 | 3.29 | 3
228 | PASCHIM MEDINIPUR | SM/15590 | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/018412 | 40043813 | New | MVS | GO2223013903PH | 15/02/2023 | 174.37 | 23.81 | 198.18 | Midnapore Division | Midnapore Mechanical Division | 17.71 | 8.6 | 0 | 0 | 26.31 | 0 | 0.54 | 0 | 0 | 0.54 | 0.27 | 14
229 | PASCHIM MEDINIPUR | SM/19101 | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | TSM/012817 | 40034740 | New | MVS | 3715/PHE-28011/265/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1001.18 | 53.14 | 1054.32 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | PASCHIM MEDINIPUR | SM/18620 | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | TSM/013268 | 40034577 | New | MVS | 2162/PHE-28011/39/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 1465.1 | 106.28 | 1571.38 | Midnapore Division | Midnapore Mechanical Division | 12.99 | 0 | 7.21 | 0 | 20.2 | 0 | 0 | 7.21 | 0 | 7.21 | 0.46 | 1
231 | PASCHIM MEDINIPUR | SM/18538 | Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | TSM/020283 | 40053752 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1351.07 | 111.98 | 1463.05 | Midnapore Division | Midnapore Mechanical Division | 10.78 | 0 | 37.8 | 0 | 48.58 | 0 | 0 | 37.8 | 0 | 37.8 | 2.58 | 1
232 | PASCHIM MEDINIPUR | SM/15257 | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015744 | 40035307 | New | MVS | GO2223013432PH | 07/02/2023 | 703.47 | 55.99 | 759.46 | Midnapore Division | Midnapore Mechanical Division | 534.72 | 21.47 | 1.2 | 0 | 557.39 | 184.37 | 7.37 | 1.2 | 0 | 192.94 | 25.41 | 5
233 | PASCHIM MEDINIPUR | SM/11623 | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | TSM/011567 | 40017916 | New | MVS | GO2223005584PH | 26/07/2022 | 578.78 | 53.14 | 631.92 | Midnapore Division | Midnapore Mechanical Division | 279.46 | 35.36 | 16.84 | 0 | 331.66 | 214.38 | 34.02 | 16.84 | 0 | 265.25 | 41.97 | 23
234 | PASCHIM MEDINIPUR | SM/11624 | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | TSM/011561 | 40017910 | New | MVS | GO2223005582PH | 26/07/2022 | 848.82 | 53.14 | 901.96 | Midnapore Division | Midnapore Mechanical Division | 340.74 | 30.27 | 0 | 0 | 371.01 | 271.93 | 29.04 | 0 | 0 | 300.98 | 33.37 | 22
235 | PASCHIM MEDINIPUR | SM/15591 | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/017561 | 40044112 | New | MVS | GO2223013896PH | 15/02/2023 | 790.54 | 55.99 | 846.53 | Midnapore Division | Midnapore Mechanical Division | 323.91 | 11.55 | 2.57 | 0 | 338.03 | 183.93 | 0 | 2.57 | 0 | 186.5 | 22.03 | 20
236 | PASCHIM MEDINIPUR | SM/16262 | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/016251 | 40035711 | New | MVS | GO2223014805PH | 23/02/2023 | 777.46 | 95.67 | 873.13 | Midnapore Division | Midnapore Mechanical Division | 23.22 | 10.32 | 12.53 | 0 | 46.07 | 5.98 | 0 | 2.42 | 0 | 8.4 | 0.96 | 4
237 | PASCHIM MEDINIPUR | SM/18696 | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | TSM/015743 | 40035003 | New | MVS | 2249/PHE-28011/172/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 956.86 | 71.86 | 1028.72 | Midnapore Division | Midnapore Mechanical Division | 28.77 | 18 | 14.63 | 0 | 61.4 | 0 | 0 | 14.63 | 0 | 14.63 | 1.42 | 2
238 | PASCHIM MEDINIPUR | SM/12876 | Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. | TSM/011871 | 40024584 | New | MVS | GO2223008167PH | 23/09/2022 | 1417.93 | 106.28 | 1524.21 | Midnapore Division | Midnapore Mechanical Division | 25.11 | 21.89 | 0 | 0 | 47 | 15.91 | 0 | 0 | 0 | 15.91 | 1.04 | 2
239 | PASCHIM MEDINIPUR | SM/18171 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGCHHARI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013342 | 40066260 | New | MVS | GO2223017902PH | 29/03/2023 | 914.61 | 84.47 | 999.09 | Midnapore Division | Jhargram Mechanical Division | 259.07 | 14.94 | 14.97 | 0 | 288.98 | 0 | 14.94 | 14.97 | 0 | 29.91 | 2.99 | 1
240 | PASCHIM MEDINIPUR | SM/18172 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASANCHHARA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013349 | 40066261 | New | MVS | GO2223017899PH | 29/03/2023 | 864.31 | 84.47 | 948.79 | Midnapore Division | Jhargram Mechanical Division | 177.04 | 13.53 | 15 | 0 | 205.57 | 0 | 13.53 | 15 | 0 | 28.53 | 3.01 | 1
241 | PASCHIM MEDINIPUR | SM/18173 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LAKSHIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013346 | 40066262 | New | MVS | GO2223017900PH | 29/03/2023 | 730.56 | 84.47 | 815.03 | Midnapore Division | Jhargram Mechanical Division | 278.99 | 30.94 | 12.43 | 0 | 322.36 | 4.94 | 30.94 | 12.43 | 0 | 48.31 | 5.93 | 5
242 | PASCHIM MEDINIPUR | SM/18615 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | TSM/013347 | 40066263 | New | MVS | 2159/PHE-28011/232/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 964.27 | 84.47 | 1048.75 | Midnapore Division | Jhargram Mechanical Division | 282.49 | 6.48 | 17.09 | 0 | 306.06 | 0 | 6.48 | 17.09 | 0 | 23.57 | 2.25 | 1
243 | PASCHIM MEDINIPUR | SM/18184 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013443 | 40032934 | New | MVS | GO2223018114PH | 31/03/2023 | 773.1 | 84.47 | 857.57 | Midnapore Division | Jhargram Mechanical Division | 0 | 11.01 | 18.85 | 0 | 29.86 | 0 | 11.01 | 18.85 | 0 | 29.86 | 3.48 | 1
244 | PASCHIM MEDINIPUR | SM/13053 | HARI PURA AND ADJOINING MOUJAS PWSS | TSM/014660 | 40029983 | New | MVS | GO2223008483PH | 29/09/2022 | 418.14 | 37.78 | 455.91 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 14.69 | 10.6 | 0 | 30.07 | 4.78 | 0 | 10.6 | 0 | 15.38 | 3.37 | 4
245 | PASCHIM MEDINIPUR | SM/13085 | HARINASULI & ADJOINING MOUJAS PWSS | TSM/013388 | 40026272 | New | MVS | GO2223008448PH | 29/09/2022 | 578.97 | 40.37 | 619.34 | Midnapore Division | Jhargram Mechanical Division | 22.87 | 0 | 31.32 | 0 | 54.18 | 0 | 0 | 31.32 | 0 | 31.32 | 5.06 | 1
246 | PASCHIM MEDINIPUR | SM/15592 | HATKATA AND ITS ADJOINING MOUZAS PWSS | TSM/017354 | 40044770 | New | MVS | GO2223013888PH | 15/02/2023 | 865.21 | 42.81 | 908.02 | Midnapore Division | Midnapore Mechanical Division | 95.91 | 6.36 | 17.75 | 0 | 120.02 | 0 | 0 | 17.75 | 0 | 17.75 | 1.96 | 1
247 | PASCHIM MEDINIPUR | SM/15011 | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017445 | 40034696 | New | MVS | GO2223013154PH | 04/02/2023 | 198.87 | 37.91 | 236.77 | Midnapore Division | Midnapore Mechanical Division | 7.27 | 3.35 | 0 | 0 | 10.62 | 0.72 | 0 | 0 | 0 | 0.72 | 0.31 | 6
248 | PASCHIM MEDINIPUR | SM/07386 | IRPALA Piped Water Supply Scheme. | TSM/004506 | 8290871 | New | MVS | GO2021002983PH | 03/12/2020 | 689.48 | 39.41 | 728.89 | Midnapore Division | Midnapore Mechanical Division | 281.53 | 21.08 | 45.87 | 0 | 348.49 | 281.53 | 20.48 | 45.87 | 0 | 347.88 | 47.73 | 76
249 | PASCHIM MEDINIPUR | SM/18782 | Islampur Piped Water Supply Scheme. | TSM/004474 | 40026000 | New | MVS | PHE/IV/2605/W-642/23 | 29/08/2023 | 763.99 | 37.49 | 801.48 | Midnapore Division |  | 0 | 0 | 12.88 | 0 | 12.88 | 0 | 0 | 0.92 | 0 | 0.92 | 0.11 | 1
250 | PASCHIM MEDINIPUR | SM/13143 | JADABBATI AND ADJOINING MOUJAS PWSS | TSM/014184 | 40033466 | New | MVS | GO2223008643PH | 12/10/2022 | 530.64 | 40.04 | 570.68 | Midnapore Division | Jhargram Mechanical Division | 29.99 | 0 | 25.44 | 0 | 55.42 | 0 | 0 | 25.44 | 0 | 25.44 | 4.46 | 1
251 | PASCHIM MEDINIPUR | SM/18583 | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | TSM/016526 | 40036024 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1231.08 | 42.92 | 1274.01 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 127.15 | 0 | 127.15 | 0 | 0 | 127.15 | 0 | 127.15 | 9.98 | 1
252 | PASCHIM MEDINIPUR | SM/13055 | JAGARDANGA AND ADJOINING MOUJAS PWSS | TSM/014773 | 40031436 | New | MVS | GO2223008493PH | 29/09/2022 | 494.96 | 55.1 | 550.06 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 0 | 3.3 | 0 | 8.08 | 4.78 | 0 | 3.3 | 0 | 8.08 | 1.47 | 1
253 | PASCHIM MEDINIPUR | SM/13086 | JAHALDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013106 | 40026284 | New | MVS | GO2223008450PH | 29/09/2022 | 390.22 | 37.94 | 428.16 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 9.25 | 0 | 14.03 | 4.78 | 0 | 9.25 | 0 | 14.03 | 3.28 | 2
254 | PASCHIM MEDINIPUR | SM/13087 | JALIMANDA AND IT'S ADJOINING MOUJAS PWSS | TSM/013120 | 40026256 | New | MVS | GO2223008444PH | 29/09/2022 | 709.66 | 38.16 | 747.82 | Midnapore Division | Midnapore Mechanical Division | 148.31 | 0 | 14.71 | 0 | 163.02 | 0 | 0 | 14.71 | 0 | 14.71 | 1.97 | 5
255 | PASCHIM MEDINIPUR | SM/13056 | JAMUNA AND ADJOINING MOUJAS PWSS | TSM/014383 | 40029905 | New | MVS | GO2223008477PH | 29/09/2022 | 474.4 | 38.53 | 512.93 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 11.01 | 0 | 15.79 | 4.78 | 0 | 11.01 | 0 | 15.79 | 3.08 | 1
256 | PASCHIM MEDINIPUR | SM/18786 | Jankapur Piped Water Supply Scheme. | TSM/006520 | 40032925 | New | MVS | PHE/IV/2609/W-640/23 | 29/08/2023 | 767.9 | 38.8 | 806.7 | Midnapore Division | Midnapore Mechanical Division | 21.09 | 6.51 | 11.72 | 0 | 39.32 | 0 | 0 | 0 | 0 | 0 | 0 | 1
257 | PASCHIM MEDINIPUR | SM/17559 | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017568 | 40053733 | New | MVS | GO2223017050PH | 18/03/2023 | 564.75 | 76.24 | 641 | Midnapore Division | Midnapore Mechanical Division | 1.61 | 0 | 8.65 | 0 | 10.26 | 1.61 | 0 | 8.65 | 0 | 10.26 | 1.6 | 1
258 | PASCHIM MEDINIPUR | SM/17560 | Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017569 | 40053732 | New | MVS | GO2223017031PH | 18/03/2023 | 649.05 | 74.87 | 723.92 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 9.94 | 0 | 9.94 | 0 | 0 | 9.94 | 0 | 9.94 | 1.37 | 1
259 | PASCHIM MEDINIPUR | SM/14652 | JHARBHANGA AND ADJOINING MOUJAS PWSS | TSM/015951 | 40035495 | New | MVS | GO2223012720PH | 31/01/2023 | 638.75 | 57.35 | 696.1 | Midnapore Division | Jhargram Mechanical Division | 177.34 | 6.79 | 0 | 0 | 184.12 | 0 | 6.79 | 0 | 0 | 6.79 | 0.97 | 1
260 | PASCHIM MEDINIPUR | SM/13806 | JHETA JAMBONI PIPED WATER SUPPLY SCHEME | TSM/015054 | 40034527 | New | MVS | GO2223009969PH | 22/11/2022 | 871.52 | 41.52 | 913.04 | Midnapore Division | Midnapore Mechanical Division | 7.47 | 2.9 | 0 | 0 | 10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 1
261 | PASCHIM MEDINIPUR | SM/18188 | KADABANI AND ADJOINING MOUJAS PWSS | TSM/013999 | 40047060 | New | MVS | GO2223018189PH | 31/03/2023 | 262.78 | 36.17 | 298.95 | Midnapore Division | Jhargram Mechanical Division | 24.41 | 0 | 0 | 0 | 24.41 | 0 | 0 | 0 | 0 | 0 | 0 | 1
262 | PASCHIM MEDINIPUR | SM/13058 | KADAM BANDHI AND ADJOINING MOUJAS PWSS | TSM/014559 | 40031875 | New | MVS | GO2223008506PH | 29/09/2022 | 376.54 | 35.93 | 412.47 | Midnapore Division | Jhargram Mechanical Division | 53.92 | 15.85 | 5.5 | 0 | 75.27 | 4.78 | 15.85 | 5.5 | 0 | 26.13 | 6.33 | 1
263 | PASCHIM MEDINIPUR | SM/15012 | KADAM DIHA AND ADJOINING MOUJAS PWSS | TSM/015816 | 40033241 | New | MVS | GO2223013054PH | 04/02/2023 | 265.57 | 36.65 | 302.22 | Midnapore Division | Jhargram Mechanical Division | 15.95 | 0 | 0 | 0 | 15.95 | 0 | 0 | 0 | 0 | 0 | 0 | 1
264 | PASCHIM MEDINIPUR | SM/16620 | KADAMDIHA AND IT'S ADJOINING MOUJAS PWSS | TSM/017360 | 40036360 | New | MVS | GO2223015893PH | 14/03/2023 | 801.03 | 82.68 | 883.71 | Midnapore Division | Jhargram Mechanical Division | 16.03 | 0 | 0 | 0 | 16.03 | 0 | 0 | 0 | 0 | 0 | 0 | 1
265 | PASCHIM MEDINIPUR | SM/13144 | KADRA AND ADJOINING MOUJAS PWSS | TSM/014124 | 40033423 | New | MVS | GO2223008653PH | 12/10/2022 | 362.26 | 36.3 | 398.56 | Midnapore Division | Jhargram Mechanical Division | 67.65 | 6.27 | 43.71 | 0 | 117.62 | 4.78 | 6.27 | 25.5 | 0 | 36.55 | 9.17 | 1
266 | PASCHIM MEDINIPUR | SM/15013 | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | TSM/017352 | 40034388 | New | MVS | GO2223013176PH | 04/02/2023 | 787.66 | 42.67 | 830.33 | Midnapore Division | Midnapore Mechanical Division | 162.4 | 24.93 | 0 | 0 | 187.33 | 0 | 0 | 0 | 0 | 0 | 0 | 4
267 | PASCHIM MEDINIPUR | SM/18502 | Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015588 | 40028858 | New | MVS | 2037/PHE-28011/20/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1547.92 | 116.02 | 1663.94 | Midnapore Division | Midnapore Mechanical Division | 3.73 | 0 | 0 | 0 | 3.73 | 3.73 | 0 | 0 | 0 | 3.73 | 0.22 | 1
268 | PASCHIM MEDINIPUR | SM/12988 | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/011809 | 40025936 | New | MVS | GO2223008331PH | 28/09/2022 | 483.44 | 38.2 | 521.64 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 12.84 | 0 | 12.84 | 0 | 0 | 12.84 | 0 | 12.84 | 2.46 | 1
269 | PASCHIM MEDINIPUR | SM/13089 | KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS | TSM/013055 | 40065575 | New | MVS | GO2223008447PH | 29/09/2022 | 283.84 | 37.66 | 321.5 | Midnapore Division | Midnapore Mechanical Division | 100 | 0 | 6.54 | 0 | 106.54 | 0 | 0 | 6.54 | 0 | 6.54 | 2.03 | 1
270 | PASCHIM MEDINIPUR | SM/14033 | KANKRISOL AND ADJOINING MOUJAS PWSS | TSM/015827 | 40035384 | New | MVS | GO2223010498PH | 05/12/2022 | 265.76 | 36.65 | 302.42 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 5.11 | 2.92 | 0 | 12.81 | 4.78 | 5.11 | 2.92 | 0 | 12.81 | 4.24 | 2
271 | PASCHIM MEDINIPUR | SM/13059 | KANPUR AND ADJOINING MOUJAS PWSS | TSM/014655 | 40031419 | New | MVS | GO2223008492PH | 29/09/2022 | 523.34 | 39.33 | 562.67 | Midnapore Division | Midnapore Mechanical Division | 0 | 6.94 | 11.35 | 21.37 | 39.66 | 0 | 0 | 11.35 | 21.37 | 32.72 | 5.81 | 2
272 | PASCHIM MEDINIPUR | SM/13060 | KANTAL AND ADJOINING MOUJAS PWSS | TSM/014650 | 40031814 | New | MVS | GO2223008504PH | 29/09/2022 | 458.93 | 38.4 | 497.33 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 12.47 | 8.85 | 0 | 26.1 | 4.78 | 12.47 | 8.85 | 0 | 26.1 | 5.25 | 1
273 | PASCHIM MEDINIPUR | SM/13061 | KARANJIMURA AND ADJOINING MOUJAS PWSS | TSM/014756 | 40031799 | New | MVS | GO2223008501PH | 29/09/2022 | 392.81 | 37.76 | 430.57 | Midnapore Division | Midnapore Mechanical Division | 0 | 14.66 | 9.09 | 0 | 23.76 | 0 | 0 | 9.09 | 0 | 9.09 | 2.11 | 4
274 | PASCHIM MEDINIPUR | SM/13001 | KARNAGAR AND ADJOINING MAOUJAS PWSS | TSM/015012 | 40026205 | New | MVS | GO2223008409PH | 29/09/2022 | 522.52 | 39.33 | 561.85 | Midnapore Division | Jhargram Mechanical Division | 37.9 | 6.22 | 10.69 | 0 | 54.81 | 0 | 6.22 | 10.69 | 0 | 16.91 | 3.01 | 2
275 | PASCHIM MEDINIPUR | SM/13090 | KARSA AND ADJOINING MOUJAS PWSS | TSM/014471 | 40031911 | New | MVS | GO2223008533PH | 10/10/2022 | 361.95 | 60.49 | 422.45 | Midnapore Division | Jhargram Mechanical Division | 62.92 | 3.15 | 0 | 0 | 66.07 | 0 | 3.15 | 0 | 0 | 3.15 | 0.75 | 1
276 | PASCHIM MEDINIPUR | SM/19100 | KASBA NARAYANGARH AND ADJOINING MOUJAS PWSS | TSM/016189 | 40034225 | New | MVS | 3714/PHE-28011/267/2022-SCHM CELL-Dept. of PHE | 14/12/2023 | 1065.92 | 49.81 | 1115.72 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | PASCHIM MEDINIPUR | SM/14653 | KASHBA AND ITS ADJOINING MOUZAS PWSS | TSM/017291 | 40035835 | New | MVS | GO2223012731PH | 31/01/2023 | 271.44 | 19.75 | 291.2 | Midnapore Division | Midnapore Mechanical Division | 49.6 | 5.11 | 0.46 | 0 | 55.17 | 0 | 0 | 0.46 | 0 | 0.46 | 0.16 | 3
278 | PASCHIM MEDINIPUR | SM/12331 | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. | TSM/014276 | 40023590 | New | MVS | GO2223007342PH | 09/09/2022 | 612.01 | 38.73 | 650.74 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 16.38 | 0 | 16.38 | 0 | 0 | 16.38 | 0 | 16.38 | 2.52 | 1
279 | PASCHIM MEDINIPUR | SM/17561 | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017566 | 40053734 | New | MVS | GO2223017045PH | 18/03/2023 | 584.52 | 76.24 | 660.76 | Midnapore Division | Midnapore Mechanical Division | 1.69 | 0 | 8.49 | 0 | 10.18 | 1.69 | 0 | 8.49 | 0 | 10.18 | 1.54 | 1
280 | PASCHIM MEDINIPUR | SM/17562 | Kashida (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017567 | 40053735 | New | MVS | GO2223017074PH | 18/03/2023 | 841.92 | 77.87 | 919.79 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 13.6 | 0 | 13.6 | 0 | 0 | 13.6 | 0 | 13.6 | 1.48 | 1
281 | PASCHIM MEDINIPUR | SM/15014 | KASHIPUR AND ADJOINING MOUJAS PWSS | TSM/015979 | 40034081 | New | MVS | GO2223013055PH | 04/02/2023 | 858.33 | 41.57 | 899.9 | Midnapore Division | Midnapore Mechanical Division | 459.47 | 12.47 | 0 | 0 | 471.94 | 155.75 | 0 | 0 | 0 | 155.75 | 17.31 | 20
282 | PASCHIM MEDINIPUR | SM/13088 | KATAI AND IT'S ADJOINING MOUJAS PWSS | TSM/013121 | 40026264 | New | MVS | GO2223008446PH | 29/09/2022 | 421.54 | 37.83 | 459.37 | Midnapore Division | Midnapore Mechanical Division | 195.86 | 17.09 | 0 | 0 | 212.94 | 119.18 | 0 | 0 | 0 | 119.18 | 25.94 | 27
283 | PASCHIM MEDINIPUR | SM/17621 | KEDAR AND ITS ADJOINING MOUJAS PWSS | TSM/013136 | 40033089 | New | MVS | GO2223017413PH | 21/03/2023 | 321.75 | 37.89 | 359.64 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
284 | PASCHIM MEDINIPUR | SM/13023 | KESHARAMBHA AND IT'S ADJOINING MOUJAS PWSS | TSM/013163 | 40026032 | New | MVS | GO2223008353PH | 28/09/2022 | 697.07 | 38.51 | 735.57 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 17.95 | 0 | 22.72 | 4.78 | 0 | 17.95 | 0 | 22.72 | 3.09 | 2
285 | PASCHIM MEDINIPUR | SM/13124 | KESHIA AND ADJOINING MOUJAS PWSS | TSM/014747 | 40031906 | New | MVS | GO2223008532PH | 10/10/2022 | 467.2 | 37.78 | 504.98 | Midnapore Division | Jhargram Mechanical Division | 88.96 | 3.45 | 9.57 | 0 | 101.97 | 4.78 | 3.45 | 9.57 | 0 | 17.8 | 3.52 | 1
286 | PASCHIM MEDINIPUR | SM/13026 | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | TSM/010246 | 40026106 | New | MVS | GO2223008361PH | 28/09/2022 | 477.89 | 38.2 | 516.09 | Midnapore Division | Midnapore Mechanical Division | 307.9 | 17.46 | 0 | 0 | 325.36 | 152.54 | 0 | 0 | 0 | 152.54 | 29.56 | 25
287 | PASCHIM MEDINIPUR | SM/13024 | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | TSM/013105 | 40026141 | New | MVS | GO2223008366PH | 28/09/2022 | 350.31 | 37.83 | 388.14 | Midnapore Division | Midnapore Mechanical Division | 206.15 | 26.74 | 0 | 0 | 232.88 | 100.2 | 6.67 | 0 | 0 | 106.87 | 27.54 | 25
288 | PASCHIM MEDINIPUR | SM/13025 | KHANDRUI AND IT'S ADJOINING MOUJAS PWSS. | TSM/013179 | 40026116 | New | MVS | GO2223008362PH | 28/09/2022 | 471.71 | 38.28 | 509.99 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 12.01 | 0 | 12.01 | 0 | 0 | 12.01 | 0 | 12.01 | 2.36 | 1
289 | PASCHIM MEDINIPUR | SM/18532 | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | TSM/017513 | 40044943 | New | MVS | 2051/PHE-28011/177/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1011.28 | 42.82 | 1054.1 | Midnapore Division | Midnapore Mechanical Division | 144.24 | 8.74 | 17.2 | 0 | 170.18 | 0 | 0 | 17.2 | 0 | 17.2 | 1.63 | 2
290 | PASCHIM MEDINIPUR | SM/15015 | KHARIKA AND ITS ADJOINING MOUZAS PWSS | TSM/016020 | 40034390 | New | MVS | GO2223013087PH | 04/02/2023 | 942.1 | 39.86 | 981.96 | Midnapore Division | Midnapore Mechanical Division | 119.07 | 8 | 0 | 0 | 127.06 | 0 | 0 | 0 | 0 | 0 | 0 | 2
291 | PASCHIM MEDINIPUR | SM/13125 | KHARIPARA AND IT'S ADJOINING MOUJAS | TSM/014733 | 40031924 | New | MVS | GO2223008536PH | 10/10/2022 | 406.09 | 37.78 | 443.87 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
292 | PASCHIM MEDINIPUR | SM/14506 | KHAS JANGAL PIPED WATER SUPPLY SCHEME | TSM/015765 | 40034445 | New | MVS | GO2223012311PH | 20/01/2023 | 883.33 | 37.53 | 920.87 | Midnapore Division | Midnapore Mechanical Division | 321.31 | 22.36 | 0 | 0 | 343.66 | 164.53 | 6.41 | 0 | 0 | 170.94 | 18.56 | 2
293 | PASCHIM MEDINIPUR | SM/17618 | KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS | TSM/011838 | 40033914 | New | MVS | GO2223017410PH | 21/03/2023 | 578.14 | 38.2 | 616.34 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 13.37 | 0 | 13.37 | 0 | 0 | 13.37 | 0 | 13.37 | 2.17 | 1
294 | PASCHIM MEDINIPUR | SM/07393 | Khirinda Piped Water Supply Scheme. | TSM/004519 | 8290951 | New | MVS | GO2021003568PH | 21/12/2020 | 859.9 | 40.82 | 900.72 | Midnapore Division | Midnapore Mechanical Division | 4.52 | 5.32 | 0 | 27.2 | 37.03 | 4.52 | 5.32 | 0 | 27.2 | 37.03 | 4.11 | 14
295 | PASCHIM MEDINIPUR | SM/18525 | KHIRISH MUL AND ITS ADJOINING MOUZAS PWSS | TSM/017514 | 40034349 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1138.94 | 40.76 | 1179.7 | Midnapore Division | Midnapore Mechanical Division | 0 | 9.96 | 0 | 0 | 9.96 | 0 | 0 | 0 | 0 | 0 | 0 | 1
296 | PASCHIM MEDINIPUR | SM/13126 | KHURSI AND ADJOINING MOUJAS PWSS | TSM/014267 | 40034078 | New | MVS | GO2223008570PH | 10/10/2022 | 603.88 | 38.48 | 642.36 | Midnapore Division | Midnapore Mechanical Division | 119.49 | 3.44 | 15.74 | 0 | 138.68 | 4.78 | 0 | 15.74 | 0 | 20.52 | 3.2 | 2
297 | PASCHIM MEDINIPUR | SM/13113 | KONTORE AND ADJOINING MOUJAS PWSS | TSM/014749 | 40031882 | New | MVS | GO2223008531PH | 10/10/2022 | 333.76 | 37.66 | 371.42 | Midnapore Division | Jhargram Mechanical Division | 55.58 | 12.7 | 6.34 | 0 | 74.63 | 4.78 | 12.7 | 6.34 | 0 | 23.82 | 6.41 | 1
298 | PASCHIM MEDINIPUR | SM/14034 | KOREDAN AND ADJOINING MOUJAS PWSS | TSM/015817 | 40035656 | New | MVS | GO2223010497PH | 05/12/2022 | 445.27 | 39.38 | 484.66 | Midnapore Division | Jhargram Mechanical Division | 17.05 | 0 | 0 | 0 | 17.05 | 0 | 0 | 0 | 0 | 0 | 0 | 1
299 | PASCHIM MEDINIPUR | SM/14484 | KUBIR CHAK PIPED WATER SUPPLY SCHEME | TSM/015084 | 40034440 | New | MVS | GO2223012312PH | 20/01/2023 | 773.09 | 37.62 | 810.71 | Midnapore Division | Midnapore Mechanical Division | 27.68 | 25.9 | 0 | 0 | 53.58 | 7.77 | 0 | 0 | 0 | 7.77 | 0.96 | 1
300 | PASCHIM MEDINIPUR | SM/12335 | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. | TSM/013977 | 40023633 | New | MVS | GO2223007344PH | 09/09/2022 | 686.38 | 40.37 | 726.75 | Midnapore Division | Jhargram Mechanical Division | 66.43 | 0 | 16.98 | 0 | 83.41 | 0 | 0 | 16.98 | 0 | 16.98 | 2.34 | 1
301 | PASCHIM MEDINIPUR | SM/14654 | KUKRADA AND ITS ADJOINING MOUZAS PWSS | TSM/017288 | 40035810 | New | MVS | GO2223012733PH | 31/01/2023 | 627.67 | 41.21 | 668.88 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 1.71 | 0.26 | 1
302 | PASCHIM MEDINIPUR | SM/13121 | KULBANI AND ADJOINING MOUJAS PWSS | TSM/014763 | 40032102 | New | MVS | GO2223008559PH | 10/10/2022 | 673.26 | 57.61 | 730.87 | Midnapore Division | Midnapore Mechanical Division | 0 | 35.22 | 18.71 | 19.43 | 73.35 | 0 | 0 | 18.71 | 19.43 | 38.14 | 5.22 | 2
303 | PASCHIM MEDINIPUR | SM/14655 | KULDIHA AND ITS ADJOINING MOUZAS PWSS | TSM/017167 | 40035858 | New | MVS | GO2223012713PH | 31/01/2023 | 659.98 | 41.06 | 701.03 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 13.78 | 0 | 13.78 | 0 | 0 | 13.78 | 0 | 13.78 | 1.97 | 1
304 | PASCHIM MEDINIPUR | SM/14939 | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | TSM/011807 | 40033801 | New | MVS | GO2223012937PH | 03/02/2023 | 338.67 | 38.05 | 376.72 | Midnapore Division | Midnapore Mechanical Division | 196.04 | 30.04 | 0 | 0 | 226.07 | 75.64 | 0 | 0 | 0 | 75.64 | 20.08 | 25
305 | PASCHIM MEDINIPUR | SM/13122 | KUNARPUR AND ADJOINING MOUJAS PWSS | TSM/014399 | 40032106 | New | MVS | GO2223008560PH | 10/10/2022 | 515.04 | 36.72 | 551.76 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 20.27 | 0 | 20.27 | 0 | 0 | 20.27 | 0 | 20.27 | 3.67 | 1
306 | PASCHIM MEDINIPUR | SM/15017 | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017440 | 40034895 | New | MVS | GO2223013179PH | 04/02/2023 | 480.5 | 76.3 | 556.8 | Midnapore Division | Midnapore Mechanical Division | 216.63 | 16.54 | 14.79 | 0 | 247.96 | 123.85 | 1.02 | 14.79 | 0 | 139.66 | 25.08 | 34
307 | PASCHIM MEDINIPUR | SM/14656 | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017441 | 40034791 | New | MVS | GO2223012715PH | 31/01/2023 | 527.27 | 77.41 | 604.67 | Midnapore Division | Midnapore Mechanical Division | 16.72 | 0 | 0 | 0 | 16.72 | 3.46 | 0 | 0 | 0 | 3.46 | 0.57 | 1
308 | PASCHIM MEDINIPUR | SM/18531 | KUSUMDAHARI PIPED WATER SUPPLY SCHEME | TSM/014870 | 40034431 | New | MVS | 2050/PHE-28011/24/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1204.79 | 49.05 | 1253.84 | Midnapore Division | Midnapore Mechanical Division | 14.26 | 8.68 | 0 | 0 | 22.95 | 0 | 0 | 0 | 0 | 0 | 0 | 1
309 | PASCHIM MEDINIPUR | SM/13093 | KUSUMPUR AND ADJOINING MOUJAS | TSM/014746 | 40034914 | New | MVS | GO2223008574PH | 10/10/2022 | 544.81 | 39.33 | 584.14 | Midnapore Division | Midnapore Mechanical Division | 44.93 | 5.5 | 12.05 | 20.55 | 83.02 | 0 | 0 | 12.05 | 20.55 | 32.59 | 5.58 | 2
310 | PASCHIM MEDINIPUR | SM/15016 | KUTKI AND ADJOINING MOUJAS PWSS | TSM/014438 | 40034063 | New | MVS | GO2223013150PH | 04/02/2023 | 564.93 | 51.42 | 616.35 | Midnapore Division | Midnapore Mechanical Division | 0 | 3.97 | 0 | 0 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 2
311 | PASCHIM MEDINIPUR | SM/09988 | Kutulpur Piped Water Supply Scheme. | TSM/004504 | 40006881 | New | MVS | GO2122006952PH | 16/12/2021 | 490.72 | 42.59 | 533.31 | Midnapore Division | Midnapore Mechanical Division | 13.33 | 6.82 | 0 | 0 | 20.14 | 13.33 | 0 | 0 | 0 | 13.33 | 2.5 | 5
312 | PASCHIM MEDINIPUR | SM/13094 | LENGA MARA AND IT'S ADJOINING MOUJAS | TSM/014731 | 40032142 | New | MVS | GO2223008564PH | 10/10/2022 | 664.32 | 55.35 | 719.67 | Midnapore Division | Midnapore Mechanical Division | 32.29 | 28.26 | 15.57 | 20.14 | 96.26 | 0 | 0 | 15.57 | 20.14 | 35.71 | 4.96 | 2
313 | PASCHIM MEDINIPUR | SM/12992 | LOYADA AND ITS ADJOINING MOUJAS PWSS | TSM/011794 | 40025941 | New | MVS | GO2223008332PH | 28/09/2022 | 316.22 | 37.83 | 354.05 | Midnapore Division | Midnapore Mechanical Division | 137.04 | 15.46 | 7.71 | 0 | 160.2 | 0 | 0 | 7.71 | 0 | 7.71 | 2.18 | 4
314 | PASCHIM MEDINIPUR | SM/17622 | MADHABPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013137 | 40033285 | New | MVS | GO2223017405PH | 21/03/2023 | 349.21 | 37.83 | 387.04 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 6.89 | 0 | 6.89 | 0 | 0 | 6.89 | 0 | 6.89 | 1.78 | 1
315 | PASCHIM MEDINIPUR | SM/14035 | MADHUPUR AND ADJOINING MOUJAS PWSS | TSM/015831 | 40035518 | New | MVS | GO2223010488PH | 05/12/2022 | 476.77 | 40.32 | 517.09 | Midnapore Division | Jhargram Mechanical Division | 23.45 | 0 | 0 | 0 | 23.45 | 0 | 0 | 0 | 0 | 0 | 0 | 1
316 | PASCHIM MEDINIPUR | SM/15325 | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015712 | 40034649 | New | MVS | GO2223013664PH | 09/02/2023 | 812.03 | 80.51 | 892.54 | Midnapore Division | Midnapore Mechanical Division | 4.95 | 0 | 0 | 0 | 4.95 | 4.95 | 0 | 0 | 0 | 4.95 | 0.56 | 5
317 | PASCHIM MEDINIPUR | SM/14036 | MAHASOL AND ADJOINING MOUJAS PWSS | TSM/014959 | 40035554 | New | MVS | GO2223010500PH | 05/12/2022 | 522.4 | 56.8 | 579.21 | Midnapore Division | Jhargram Mechanical Division | 138.87 | 7.41 | 0 | 0 | 146.28 | 0 | 7.41 | 0 | 0 | 7.41 | 1.28 | 1
318 | PASCHIM MEDINIPUR | SM/13095 | MAHISAMURA PWSS | TSM/014787 | 40035030 | New | SVS | GO2223008567PH | 10/10/2022 | 417.82 | 37.82 | 455.65 | Midnapore Division | Midnapore Mechanical Division | 0 | 7.27 | 0 | 21.8 | 29.07 | 0 | 0 | 0 | 21.8 | 21.8 | 4.78 | 3
319 | PASCHIM MEDINIPUR | SM/18586 | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015925 | 40034970 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1002.76 | 77.78 | 1080.54 | Midnapore Division | Midnapore Mechanical Division | 79.34 | 9.39 | 0 | 0 | 88.72 | 0 | 0 | 0 | 0 | 0 | 0 | 2
320 | PASCHIM MEDINIPUR | SM/13096 | MAKLI AND ADJOINING MOUJAS PWSS | TSM/014874 | 40032111 | New | MVS | GO2223008562PH | 10/10/2022 | 342.72 | 35.62 | 378.34 | Midnapore Division | Jhargram Mechanical Division | 4.78 | 0 | 4.37 | 0 | 9.15 | 4.78 | 0 | 4.37 | 0 | 9.15 | 2.42 | 1
321 | PASCHIM MEDINIPUR | SM/13027 | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | TSM/011784 | 40026078 | New | MVS | GO2223008356PH | 28/09/2022 | 478.49 | 38.26 | 516.76 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 10.86 | 0 | 10.86 | 0 | 0 | 10.86 | 0 | 10.86 | 2.1 | 1
322 | PASCHIM MEDINIPUR | SM/16615 | MALIHATI AND IT'S ADJOINING MOUJAS PWSS | TSM/011812 | 40033283 | New | MVS | GO2223015963PH | 14/03/2023 | 343.62 | 37.83 | 381.45 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
323 | PASCHIM MEDINIPUR | SM/15020 | MANGAL BANDI AND ADJOINING MOUJAS PWSS | TSM/017105 | 40033256 | New | MVS | GO2223013174PH | 04/02/2023 | 557.44 | 39.15 | 596.58 | Midnapore Division | Jhargram Mechanical Division | 25.65 | 0 | 0 | 0 | 25.65 | 0 | 0 | 0 | 0 | 0 | 0 | 1
324 | PASCHIM MEDINIPUR | SM/14493 | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | TSM/016286 | 40035774 | New | MVS | GO2223012314PH | 20/01/2023 | 542.1 | 40.85 | 582.95 | Midnapore Division | Midnapore Mechanical Division | 94.72 | 8.44 | 0 | 0 | 103.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2
325 | PASCHIM MEDINIPUR | SM/13097 | MANIKDIPABARA AND AJOINING MOUJAS PWSS | TSM/014748 | 40032120 | New | MVS | GO2223008563PH | 10/10/2022 | 431.12 | 39.33 | 470.46 | Midnapore Division | Jhargram Mechanical Division | 0 | 3.39 | 0 | 0 | 3.39 | 0 | 3.39 | 0 | 0 | 3.39 | 0.72 | 1
326 | PASCHIM MEDINIPUR | SM/14002 | MANSINGHA AND IT'S ADJOINING MOUJAS PWSS | TSM/015944 | 40033482 | New | MVS | GO2223010486PH | 05/12/2022 | 141.27 | 9.83 | 151.1 | Midnapore Division | Jhargram Mechanical Division | 33.94 | 0 | 0 | 0 | 33.94 | 0 | 0 | 0 | 0 | 0 | 0 | 1
327 | PASCHIM MEDINIPUR | SM/15593 | MARKHA AND ITS ADJOINING MOUZAS PWSS | TSM/017515 | 40044482 | New | MVS | GO2223013887PH | 15/02/2023 | 945.67 | 44.91 | 990.58 | Midnapore Division | Midnapore Mechanical Division | 0 | 3.18 | 99.48 | 0 | 102.65 | 0 | 0 | 86.39 | 0 | 86.39 | 8.72 | 1
328 | PASCHIM MEDINIPUR | SM/13098 | MARKUNDA AND ADJOINING MOUJAS PWSS | TSM/014435 | 40034261 | New | MVS | GO2223008573PH | 10/10/2022 | 414.11 | 36.34 | 450.45 | Midnapore Division | Midnapore Mechanical Division | 250.05 | 7.61 | 21.69 | 0 | 279.35 | 63.15 | 0 | 21.69 | 0 | 84.84 | 18.83 | 20
329 | PASCHIM MEDINIPUR | SM/18587 | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | TSM/016525 | 40035943 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1071.76 | 42.81 | 1114.57 | Midnapore Division | Midnapore Mechanical Division | 546.58 | 26.62 | 0 | 0 | 573.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
330 | PASCHIM MEDINIPUR | SM/14624 | METELDEBIGHATA AND ADJOINING MOUJAS PWSS | TSM/016797 | 40035603 | New | MVS | GO2223012703PH | 31/01/2023 | 62.8 | 18.2 | 81 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
331 | PASCHIM MEDINIPUR | SM/13099 | MIRGA AND ADJOINING MOUJAS PWSS | TSM/015059 | 40032217 | New | MVS | GO2223008569PH | 10/10/2022 | 474.93 | 38.04 | 512.97 | Midnapore Division | Jhargram Mechanical Division | 26.49 | 10.95 | 0 | 0 | 37.44 | 0 | 10.95 | 0 | 0 | 10.95 | 2.14 | 1
332 | PASCHIM MEDINIPUR | SM/13028 | MOHANPUR & ADJOINING MOUJAS PWSS | TSM/013390 | 40026098 | New | MVS | GO2223008358PH | 28/09/2022 | 515.92 | 40.16 | 556.08 | Midnapore Division | Jhargram Mechanical Division | 78.87 | 9.42 | 11.82 | 0 | 100.11 | 0 | 9.42 | 11.82 | 0 | 21.24 | 3.82 | 1
333 | PASCHIM MEDINIPUR | SM/10017 | Monoharpur Piped Water Supply Scheme. | TSM/004465 | 40027372 | New | MVS | GO2122007553PH | 30/12/2021 | 928.81 | 0 | 928.81 | Midnapore Division | Midnapore Mechanical Division | 185.44 | 21.21 | 26.74 | 0 | 233.39 | 164.71 | 0 | 26.74 | 0 | 191.44 | 20.61 | 25
334 | PASCHIM MEDINIPUR | SM/16542 | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | TSM/017130 | 40035058 | New | MVS | GO2223015487PH | 10/03/2023 | 636.31 | 48.41 | 684.72 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 12.72 | 9.72 | 22.45 | 0 | 0 | 12.72 | 9.43 | 22.16 | 3.24 | 1
335 | PASCHIM MEDINIPUR | SM/13100 | MURAKATA AND ADJOINING MOUJAS PWSS | TSM/014445 | 40032184 | New | MVS | GO2223008565PH | 10/10/2022 | 604.59 | 38.61 | 643.19 | Midnapore Division | Midnapore Mechanical Division | 100.75 | 7.76 | 1.71 | 0 | 110.22 | 0 | 0 | 1.71 | 0 | 1.71 | 0.27 | 2
336 | PASCHIM MEDINIPUR | SM/14004 | MURAKATI AND ADJOINING MOUJAS PWSS | TSM/016132 | 40035405 | New | MVS | GO2223010487PH | 05/12/2022 | 429.87 | 38.84 | 468.71 | Midnapore Division | Jhargram Mechanical Division | 59.02 | 8.25 | 0 | 0 | 67.27 | 0 | 8.25 | 0 | 0 | 8.25 | 1.76 | 1
337 | PASCHIM MEDINIPUR | SM/15021 | MURARI AND ADJOINING MOUJAS PWSS | TSM/015110 | 40035591 | New | MVS | GO2223013147PH | 04/02/2023 | 586.63 | 57.29 | 643.92 | Midnapore Division | Jhargram Mechanical Division | 18.98 | 0 | 25.35 | 0 | 44.33 | 0 | 0 | 25.35 | 0 | 25.35 | 3.94 | 1
338 | PASCHIM MEDINIPUR | SM/13029 | NAHANJARA AND IT'S ADJOINING MOUJAS PWSS | TSM/013117 | 40026126 | New | MVS | GO2223008365PH | 28/09/2022 | 420.2 | 38.05 | 458.25 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 8.9 | 0 | 13.68 | 4.78 | 0 | 8.9 | 0 | 13.68 | 2.99 | 2
339 | PASCHIM MEDINIPUR | SM/15024 | NAHARPUR AND ADJOINING MOUJAS PWSS | TSM/015836 | 40034192 | New | MVS | GO2223013081PH | 04/02/2023 | 832.48 | 50.68 | 883.16 | Midnapore Division | Midnapore Mechanical Division | 22.71 | 2.96 | 17.75 | 0 | 43.42 | 4.78 | 0 | 17.75 | 0 | 22.53 | 2.55 | 2
340 | PASCHIM MEDINIPUR | SM/13101 | NALBONA AND ADJOINING MOUJAS PWSS | TSM/014450 | 40033372 | New | MVS | GO2223008571PH | 10/10/2022 | 458.22 | 38.61 | 496.83 | Midnapore Division | Jhargram Mechanical Division | 14.12 | 6.48 | 0 | 0 | 20.6 | 0 | 6.48 | 0 | 0 | 6.48 | 1.3 | 1
341 | PASCHIM MEDINIPUR | SM/14723 | NAMJABA AND ADJOINING MOUJAS PWSS | TSM/014172 | 40033472 | New | MVS | GO2223012710PH | 31/01/2023 | 759.99 | 58.49 | 818.48 | Midnapore Division | Jhargram Mechanical Division | 34.73 | 6.77 | 78.5 | 0 | 120 | 4.78 | 6.77 | 78.5 | 0 | 90.05 | 11 | 1
342 | PASCHIM MEDINIPUR | SM/13808 | NANASOL AND ADJOINING MOUJAS PWSS | TSM/015783 | 40035490 | New | MVS | GO2223009963PH | 22/11/2022 | 257.45 | 36.65 | 294.11 | Midnapore Division | Jhargram Mechanical Division | 16.22 | 7.91 | 3.26 | 0 | 27.38 | 0 | 7.91 | 3.26 | 0 | 11.17 | 3.8 | 1
343 | PASCHIM MEDINIPUR | SM/15025 | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | TSM/016101 | 40035730 | New | MVS | GO2223013137PH | 04/02/2023 | 518.95 | 37.42 | 556.37 | Midnapore Division | Midnapore Mechanical Division | 69.61 | 3.63 | 0 | 0 | 73.24 | 0 | 0 | 0 | 0 | 0 | 0 | 12
344 | PASCHIM MEDINIPUR | SM/18229 | NARMA AND ADJOINING MOUJAS PWSS | TSM/015801 | 40034051 | New | MVS | GO2324000612PH | 15/05/2023 | 1072.09 | 39.97 | 1112.06 | Midnapore Division | Midnapore Mechanical Division | 79.7 | 3.45 | 20.62 | 0 | 103.77 | 0 | 0 | 20.62 | 0 | 20.62 | 1.85 | 1
345 | PASCHIM MEDINIPUR | SM/14130 | NAYA BASAT AND ADJOINING MOUJAS PWSS | TSM/015824 | 40033143 | New | MVS | GO2223011524PH | 02/01/2023 | 861.6 | 59.99 | 921.59 | Midnapore Division | Jhargram Mechanical Division | 34.8 | 0 | 81.6 | 0 | 116.4 | 4.78 | 0 | 57.72 | 0 | 62.5 | 6.78 | 1
346 | PASCHIM MEDINIPUR | SM/13102 | NAYAPUKUR AND ADJOINING MOUJAS PWSS | TSM/014448 | 40034161 | New | MVS | GO2223008572PH | 10/10/2022 | 589.49 | 38.61 | 628.1 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 1.71 | 0 | 1.71 | 0.27 | 1
347 | PASCHIM MEDINIPUR | SM/13103 | NERASOL AND ADJOINING MOUJAS PWSS | TSM/014269 | 40032207 | New | MVS | GO2223008568PH | 10/10/2022 | 860.24 | 65.15 | 925.39 | Midnapore Division | Jhargram Mechanical Division | 37.68 | 0 | 64.84 | 0 | 102.51 | 4.78 | 0 | 64.84 | 0 | 69.61 | 7.52 | 1
348 | PASCHIM MEDINIPUR | SM/17619 | NIJPAPAN AND ITS ADJOINING MOUJAS PWSS | TSM/011785 | 40033305 | New | MVS | GO2223017412PH | 21/03/2023 | 318.96 | 37.83 | 356.79 | Midnapore Division | Midnapore Mechanical Division | 0 | 15.64 | 7.37 | 0 | 23.01 | 0 | 0 | 7.37 | 0 | 7.37 | 2.06 | 5
349 | PASCHIM MEDINIPUR | SM/17565 | NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MIDNAPUR DIVISION | TSM/018466 | 40053710 | New | MVS | GO2223017064PH | 18/03/2023 | 454.02 | 79.57 | 533.58 | Midnapore Division | Midnapore Mechanical Division | 7.66 | 0 | 1.5 | 0 | 9.16 | 7.66 | 0 | 1.5 | 0 | 9.16 | 1.72 | 3
350 | PASCHIM MEDINIPUR | SM/17566 | NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | TSM/018444 | 40053712 | New | MVS | GO2223017055PH | 18/03/2023 | 585.83 | 76.27 | 662.1 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
351 | PASCHIM MEDINIPUR | SM/14732 | PACHADAHARA & ADJOINING MOUJAS PWSS | TSM/013391 | 40033524 | New | MVS | GO2223012648PH | 31/01/2023 | 476.9 | 38.41 | 515.32 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
352 | PASCHIM MEDINIPUR | SM/13104 | PAKURSENI AND ADJOINING MOUJAS PWSS | TSM/014331 | 40032191 | New | MVS | GO2223008566PH | 10/10/2022 | 767.5 | 40.25 | 807.74 | Midnapore Division | Midnapore Mechanical Division | 139.08 | 3.38 | 16.16 | 0 | 158.62 | 4.78 | 0 | 16.16 | 0 | 20.94 | 2.59 | 1
353 | PASCHIM MEDINIPUR | SM/15026 | PALAIBANI AND ADJOINING MOUJAS PWSS | TSM/015949 | 40035351 | New | MVS | GO2223013065PH | 04/02/2023 | 305.26 | 36.67 | 341.93 | Midnapore Division | Jhargram Mechanical Division | 12.81 | 0 | 36.14 | 0 | 48.95 | 0 | 0 | 0 | 0 | 0 | 0 | 1
354 | PASCHIM MEDINIPUR | SM/13168 | PALASIA AND ADJOINING MOUJAS PWSS | TSM/014242 | 40036193 | New | MVS | GO2223008647PH | 12/10/2022 | 435.2 | 38.61 | 473.81 | Midnapore Division | Midnapore Mechanical Division | 147.87 | 0.64 | 0 | 0 | 148.51 | 81.65 | 0 | 0 | 0 | 81.65 | 17.23 | 29
355 | PASCHIM MEDINIPUR | SM/13216 | PANCHYAR AND ADJOINING MOUJAS PWSS | TSM/014654 | 40034894 | New | MVS | GO2223008642PH | 12/10/2022 | 464.57 | 37.78 | 502.34 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 6.2 | 9.2 | 22.24 | 42.43 | 4.78 | 0 | 9.2 | 0 | 13.98 | 2.78 | 2
356 | PASCHIM MEDINIPUR | SM/10065 | Panna Piped Water Supply Scheme. | TSM/005101 | 40006626 | New | MVS | GO2122008790PH | 27/01/2022 | 407.47 | 0 | 407.47 | Midnapore Division | Midnapore Mechanical Division | 85.59 | 9.34 | 4.73 | 0 | 99.66 | 54.43 | 0 | 4.73 | 0 | 59.16 | 14.52 | 71
357 | PASCHIM MEDINIPUR | SM/13105 | PARBATIPUR AND ADJOINING MOUJAS PWSS | TSM/014190 | 40032088 | New | MVS | GO2223008545PH | 10/10/2022 | 885.01 | 73.6 | 958.61 | Midnapore Division | Jhargram Mechanical Division | 24.08 | 0 | 48.46 | 0 | 72.54 | 0 | 0 | 48.46 | 0 | 48.46 | 5.06 | 1
358 | PASCHIM MEDINIPUR | SM/15027 | PATAJHARIA AND ADJOINING MOUJAS PWSS | TSM/015109 | 40035571 | New | MVS | GO2223013042PH | 04/02/2023 | 279.4 | 36.65 | 316.05 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
359 | PASCHIM MEDINIPUR | SM/13030 | PATHARISOL AND ADJOINING MOUJAS PWSS | TSM/013517 | 40026155 | New | MVS | GO2223008367PH | 28/09/2022 | 412.69 | 36.3 | 448.99 | Midnapore Division | Jhargram Mechanical Division | 28.08 | 0 | 27.84 | 0 | 55.93 | 0 | 0 | 13.92 | 0 | 13.92 | 3.1 | 1
360 | PASCHIM MEDINIPUR | SM/13106 | PATHARTERIA AND ADJOINING MOUJAS PWSS | TSM/014596 | 40032073 | New | MVS | GO2223008544PH | 10/10/2022 | 433.79 | 37.66 | 471.45 | Midnapore Division | Jhargram Mechanical Division | 91.06 | 0 | 15.4 | 0 | 106.46 | 0 | 0 | 15.4 | 0 | 15.4 | 3.27 | 1
361 | PASCHIM MEDINIPUR | SM/15535 | PATHRAJURI AND ADJOINING MOUJAS PWSS | TSM/016493 | 40035633 | New | MVS | GO2223013876PH | 15/02/2023 | 156.25 | 18.81 | 175.06 | Midnapore Division | Jhargram Mechanical Division | 13.6 | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1
362 | PASCHIM MEDINIPUR | SM/13807 | PATHRI AND AJOINING MOUJAS | TSM/015016 | 40033973 | New | MVS | GO2223009967PH | 22/11/2022 | 416.96 | 38.23 | 455.19 | Midnapore Division | Jhargram Mechanical Division | 15.55 | 11.82 | 0 | 0 | 27.36 | 0 | 11.82 | 0 | 0 | 11.82 | 2.6 | 1
363 | PASCHIM MEDINIPUR | SM/13031 | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | TSM/011739 | 40026171 | New | MVS | GO2223008369PH | 28/09/2022 | 483 | 38.14 | 521.14 | Midnapore Division | Midnapore Mechanical Division | 190.5 | 23.12 | 9.73 | 0 | 223.35 | 0 | 0 | 9.73 | 0 | 9.73 | 1.87 | 3
364 | PASCHIM MEDINIPUR | SM/16378 | PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | TSM/016334 | 40035782 | New | MVS | GO2223014979PH | 28/02/2023 | 717.42 | 40.66 | 758.08 | Midnapore Division | Midnapore Mechanical Division | 163.66 | 8.6 | 0 | 0 | 172.26 | 0 | 0 | 0 | 0 | 0 | 0 | 1
365 | PASCHIM MEDINIPUR | SM/13107 | PERUABAD AND ADJOINING MOUJAS PWSS | TSM/014804 | 40031954 | New | MVS | GO2223008540PH | 10/10/2022 | 377.56 | 39.06 | 416.62 | Midnapore Division | Jhargram Mechanical Division | 33.06 | 11.11 | 0 | 0 | 44.16 | 0 | 11.11 | 0 | 0 | 11.11 | 2.67 | 1
366 | PASCHIM MEDINIPUR | SM/14628 | PIASALA AND ADJOINING MOUJAS PWSS | TSM/016270 | 40036354 | New | MVS | GO2223012722PH | 31/01/2023 | 943.53 | 42.58 | 986.11 | Midnapore Division | Jhargram Mechanical Division | 163.01 | 14.99 | 15.17 | 0 | 193.17 | 100.18 | 14.99 | 15.17 | 0 | 130.34 | 13.22 | 10
367 | PASCHIM MEDINIPUR | SM/13032 | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | TSM/013446 | 40026181 | New | MVS | GO2223008370PH | 28/09/2022 | 924.17 | 41.32 | 965.49 | Midnapore Division | Midnapore Mechanical Division | 343.34 | 8.99 | 0 | 0 | 352.33 | 229.54 | 0 | 0 | 0 | 229.54 | 23.77 | 2
368 | PASCHIM MEDINIPUR | SM/15028 | PIRRAKULI AND ADJOINING MOUJAS PWSS | TSM/015097 | 40035575 | New | MVS | GO2223013043PH | 04/02/2023 | 519.69 | 38.96 | 558.66 | Midnapore Division | Jhargram Mechanical Division | 96.84 | 17.08 | 8.77 | 0 | 122.69 | 0 | 17.08 | 8.77 | 0 | 25.85 | 4.63 | 1
369 | PASCHIM MEDINIPUR | SM/15029 | PUKHARIA SOL AND ADJOINING MOUJAS PWSS | TSM/015809 | 40035497 | New | MVS | GO2223013080PH | 04/02/2023 | 426.37 | 38.84 | 465.21 | Midnapore Division | Jhargram Mechanical Division | 62.81 | 8.33 | 6.3 | 0 | 77.43 | 0 | 8.33 | 6.3 | 0 | 14.62 | 3.14 | 1
370 | PASCHIM MEDINIPUR | SM/13169 | PUNDRA AND ADJOINING MOUJAS PWSS | TSM/014255 | 40036086 | New | MVS | GO2223008644PH | 12/10/2022 | 461.42 | 38.61 | 500.02 | Midnapore Division | Midnapore Mechanical Division | 238.4 | 10.15 | 1.71 | 0 | 250.27 | 136.59 | 0 | 1.71 | 0 | 138.3 | 27.66 | 29
371 | PASCHIM MEDINIPUR | SM/13033 | PUNYA AND IT'S ADJOINING MOUJAS PWSS | TSM/013160 | 40026187 | New | MVS | GO2223008372PH | 28/09/2022 | 449.8 | 38.28 | 488.08 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 10.65 | 0 | 10.65 | 0 | 0 | 10.65 | 0 | 10.65 | 2.18 | 1
372 | PASCHIM MEDINIPUR | SM/17567 | Rabidaspur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015927 | 40053746 | New | MVS | GO2223017026PH | 18/03/2023 | 438.14 | 74.94 | 513.09 | Midnapore Division | Midnapore Mechanical Division | 4.37 | 0 | 5.32 | 0 | 9.68 | 4.37 | 0 | 5.32 | 0 | 9.68 | 1.89 | 1
373 | PASCHIM MEDINIPUR | SM/13034 | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS | TSM/013191 | 40026101 | New | MVS | GO2223008360PH | 28/09/2022 | 349.55 | 37.66 | 387.21 | Midnapore Division | Midnapore Mechanical Division | 6.43 | 0 | 0 | 0 | 6.43 | 6.43 | 0 | 0 | 0 | 6.43 | 1.66 | 3
374 | PASCHIM MEDINIPUR | SM/12997 | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | TSM/012538 | 40026004 | New | MVS | GO2223008335PH | 28/09/2022 | 783.32 | 36.38 | 819.71 | Midnapore Division | Midnapore Mechanical Division | 387.52 | 26.74 | 0 | 0 | 414.26 | 257.69 | 4.61 | 0 | 0 | 262.3 | 32 | 11
375 | PASCHIM MEDINIPUR | SM/18526 | RADHAKISHOR AND ITS ADJOINING MOUZAS PWSS | TSM/016507 | 40035798 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1221.36 | 42.96 | 1264.33 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 93.23 | 0 | 93.23 | 0 | 0 | 0 | 0 | 0 | 0 | 1
376 | PASCHIM MEDINIPUR | SM/14940 | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | TSM/011853 | 40033927 | New | MVS | GO2223012879PH | 03/02/2023 | 356.77 | 37.89 | 394.66 | Midnapore Division | Midnapore Mechanical Division | 127.29 | 5.95 | 6.86 | 0 | 140.09 | 0 | 0 | 6.86 | 0 | 6.86 | 1.74 | 2
377 | PASCHIM MEDINIPUR | SM/14131 | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017438 | 40034847 | New | MVS | GO2223011528PH | 02/01/2023 | 865.82 | 80.51 | 946.33 | Midnapore Division | Midnapore Mechanical Division | 18.34 | 0 | 0 | 0 | 18.34 | 5.8 | 0 | 0 | 0 | 5.8 | 0.61 | 2
378 | PASCHIM MEDINIPUR | SM/13217 | RADHANAGAR AND ADJOINING MOUJAS PWSS | TSM/014337 | 40034140 | New | MVS | GO2223008641PH | 12/10/2022 | 630.4 | 38.61 | 669 | Midnapore Division | Midnapore Mechanical Division | 0 | 4.23 | 0 | 0 | 4.23 | 0 | 0 | 0 | 0 | 0 | 0 | 2
379 | PASCHIM MEDINIPUR | SM/13170 | RAIPUR AND ITS ADJOINING MOUJAS PWSS | TSM/014287 | 40034284 | New | MVS | GO2223008646PH | 12/10/2022 | 502.31 | 36.34 | 538.65 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 13.67 | 0 | 18.45 | 4.78 | 0 | 13.67 | 0 | 18.45 | 3.42 | 1
380 | PASCHIM MEDINIPUR | SM/13035 | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | TSM/013128 | 40026087 | New | MVS | GO2223008357PH | 28/09/2022 | 544.84 | 38.28 | 583.12 | Midnapore Division | Midnapore Mechanical Division | 0 | 16.78 | 11.29 | 0 | 28.07 | 0 | 0 | 11.29 | 0 | 11.29 | 1.94 | 3
381 | PASCHIM MEDINIPUR | SM/16632 | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015585 | 40026087 | New | MVS | GO2223015892PH | 14/03/2023 | 476.01 | 74.96 | 550.96 | Midnapore Division | Midnapore Mechanical Division | 15.79 | 6.37 | 0 | 0 | 22.15 | 0 | 0 | 0 | 0 | 0 | 0 | 2
382 | PASCHIM MEDINIPUR | SM/15118 | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015714 | 40034676 | New | MVS | GO2223013224PH | 04/02/2023 | 678.25 | 78.37 | 756.61 | Midnapore Division | Midnapore Mechanical Division | 4.61 | 0 | 0 | 0 | 4.61 | 4.61 | 0 | 0 | 0 | 4.61 | 0.61 | 9
383 | PASCHIM MEDINIPUR | SM/13218 | RAUTARA AND ADJOINING MOUJAS PWSS | TSM/015013 | 40033974 | New | MVS | GO2223008639PH | 12/10/2022 | 413.98 | 39.06 | 453.04 | Midnapore Division | Jhargram Mechanical Division | 23.86 | 0 | 0 | 0 | 23.86 | 0 | 0 | 0 | 0 | 0 | 0 | 1
384 | PASCHIM MEDINIPUR | SM/18523 | RAUTMANI AND ITS ADJOINING MOUZAS PWSS | TSM/017289 | 40035852 | New | MVS | 2046/PHE-28011/118/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1035.31 | 41.24 | 1076.55 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 15.28 | 0 | 15.28 | 0 | 0 | 15.28 | 0 | 15.28 | 1.42 | 1
385 | PASCHIM MEDINIPUR | SM/17812 | Rejuvenation of Electro-Mechanical components of Chakismilepur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019360 | 0 | Augmentation | SVS | GO2223016671PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | PASCHIM MEDINIPUR | SM/17818 | Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019365 | 40061642 | Augmentation | MVS | GO2223016683PH | 17/03/2023 | 0 | 24.79 | 24.79 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
387 | PASCHIM MEDINIPUR | SM/17758 | Rejuvenation of Electro-Mechanical components of Chatra PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019370 | 40061040 | Augmentation | SVS | GO2223016694PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 5.07 | 0 | 0 | 5.07 | 0 | 5.07 | 0 | 0 | 5.07 | 40.9 | 60
388 | PASCHIM MEDINIPUR | SM/17779 | Rejuvenation of Electro-Mechanical components of Chaupenia PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019366 | 40061492 | Augmentation | MVS | GO2223016685PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 11.28 | 0 | 0 | 11.28 | 0 | 0 | 0 | 0 | 0 | 0 | 60
389 | PASCHIM MEDINIPUR | SM/17796 | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019374 | 40061886 | Augmentation | SVS | GO2223016702PH | 17/03/2023 | 0 | 5.55 | 5.55 |  | Jhargram Mechanical Division | 0 | 5.07 | 0 | 0 | 5.07 | 0 | 5.07 | 0 | 0 | 5.07 | 91.37 | 60
390 | PASCHIM MEDINIPUR | SM/17754 | Rejuvenation of Electro-Mechanical components of Dhamsai PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019363 | 40060888 | Augmentation | MVS | GO2223016678PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 8.01 | 0 | 0 | 8.01 | 0 | 0 | 0 | 0 | 0 | 0 | 100
391 | PASCHIM MEDINIPUR | SM/17728 | Rejuvenation of Electro-Mechanical components of Dhaneswarpur (Block Dantan-II) PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019361 | 40060490 | Augmentation | MVS | GO2223016673PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | PASCHIM MEDINIPUR | SM/17822 | Rejuvenation of Electro-Mechanical components of Gobardhanpur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019372 | 40061275 | Augmentation | MVS | GO2223016697PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | PASCHIM MEDINIPUR | SM/17750 | Rejuvenation of Electro-Mechanical components of Hatimasan PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019373 | 40060747 | Augmentation | SVS | GO2223016700PH | 17/03/2023 | 0 | 5.55 | 5.55 |  | Jhargram Mechanical Division | 0 | 5.07 | 0 | 0 | 5.07 | 0 | 5.07 | 0 | 0 | 5.07 | 91.37 | 60
394 | PASCHIM MEDINIPUR | SM/17776 | Rejuvenation of Electro-Mechanical components of Keshpur PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019362 | 40061287 | Augmentation | MVS | GO2223016675PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
395 | PASCHIM MEDINIPUR | SM/17792 | Rejuvenation of Electro-Mechanical components of Lutunia PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019391 | 40061841 | Augmentation | MVS | GO2223016681PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 0.46 | 0 | 0 | 0.46 | 0 | 0.46 | 0 | 0 | 0.46 | 3.75 | 60
396 | PASCHIM MEDINIPUR | SM/17785 | Rejuvenation of Electro-Mechanical components of Satkui PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019359 | 40061512 | Augmentation | MVS | GO2223016669PH | 17/03/2023 | 0 | 12.39 | 12.39 |  | Midnapore Mechanical Division | 0 | 4.95 | 0 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0 | 0 | 30
397 | PASCHIM MEDINIPUR | SM/17820 | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019369 | 40062747 | Augmentation | SVS | GO2223016692PH | 17/03/2023 | 0 | 24.79 | 24.79 |  | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | PASCHIM MEDINIPUR | SM/17755 | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. | TSM/019368 | 40062693 | Augmentation | SVS | GO2223016689PH | 17/03/2023 | 0 | 24.79 | 24.79 |  | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
399 | PASCHIM MEDINIPUR | SM/13046 | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | TSM/011552 | 6372771 | Augmentation | MVS | GO2223008462PH | 29/09/2022 | 291.75 | 4.22 | 295.97 | Midnapore Division |  | 241.75 | 15.84 | 0 | 0 | 257.6 | 183.71 | 0 | 0 | 0 | 183.71 | 62.07 | 15
400 | PASCHIM MEDINIPUR | SM/15217 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009612 | 40063834 | Augmentation | MVS | GO2223013462PH | 07/02/2023 | 67.56 | 7.53 | 75.1 | Midnapore Division | Midnapore Mechanical Division | 65.48 | 7.25 | 0 | 0 | 72.73 | 64.31 | 0 | 0 | 0 | 64.31 | 85.64 | 17
401 | PASCHIM MEDINIPUR | SM/10842 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009954 | 40015135 | Augmentation | MVS | GO2223003647PH | 30/05/2022 | 60.23 | 27.66 | 87.89 | Midnapore Division | Midnapore Mechanical Division | 2.13 | 26.85 | 0 | 0 | 28.97 | 2.13 | 17.85 | 0 | 0 | 19.98 | 22.73 | 60
402 | PASCHIM MEDINIPUR | SM/15218 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009948 | 40063745 | Augmentation | MVS | GO2223013465PH | 07/02/2023 | 76.97 | 55.33 | 132.3 | Midnapore Division | Midnapore Mechanical Division | 65.5 | 25.68 | 0 | 0 | 91.18 | 62.08 | 25.06 | 0 | 0 | 87.14 | 65.87 | 27
403 | PASCHIM MEDINIPUR | SM/15219 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhemwa (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009955 | 40037019 | Augmentation | MVS | GO2223013464PH | 07/02/2023 | 117.66 | 27.66 | 145.33 | Midnapore Division | Midnapore Mechanical Division | 52.63 | 12.5 | 0 | 0 | 65.13 | 2.29 | 0.09 | 0 | 0 | 2.38 | 1.64 | 51
404 | PASCHIM MEDINIPUR | SM/10686 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009947 | 40014395 | Augmentation | MVS | GO2223000917PH | 06/05/2022 | 60.21 | 27.66 | 87.88 | Midnapore Division | Midnapore Mechanical Division | 50.02 | 17.23 | 0 | 0 | 67.25 | 46.51 | 16.99 | 0 | 0 | 63.49 | 72.25 | 65
405 | PASCHIM MEDINIPUR | SM/10840 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009615 | 40015136 | Augmentation | SVS | GO2223003648PH | 30/05/2022 | 57.35 | 7.53 | 64.89 | Midnapore Division | Midnapore Mechanical Division | 42.8 | 6.01 | 0 | 0 | 48.81 | 2.14 | 6.01 | 0 | 0 | 8.15 | 12.56 | 100
406 | PASCHIM MEDINIPUR | SM/10821 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009956 | 40014829 | Augmentation | MVS | GO2223003603PH | 27/05/2022 | 141.22 | 55.33 | 196.55 | Midnapore Division | Midnapore Mechanical Division | 45.82 | 27.62 | 0 | 8.94 | 82.38 | 45.82 | 15.82 | 0 | 8.94 | 70.57 | 35.9 | 58
407 | PASCHIM MEDINIPUR | SM/11811 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009949 | 40018782 | Augmentation | MVS | GO2223006318PH | 16/08/2022 | 56.65 | 27.66 | 84.32 | Midnapore Division | Midnapore Mechanical Division | 44.42 | 20.71 | 0 | 0 | 65.13 | 44.42 | 10 | 0 | 0 | 54.42 | 64.54 | 78
408 | PASCHIM MEDINIPUR | SM/11895 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009944 | 40018866 | Augmentation | MVS | GO2223006513PH | 18/08/2022 | 28.97 | 27.66 | 56.64 | Midnapore Division | Midnapore Mechanical Division | 26.83 | 26.86 | 0 | 0 | 53.69 | 26.83 | 19.5 | 0 | 0 | 46.32 | 81.79 | 70
409 | PASCHIM MEDINIPUR | SM/10778 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009952 | 40014750 | Augmentation | MVS | GO2223003518PH | 25/05/2022 | 112.92 | 27.66 | 140.59 | Midnapore Division | Midnapore Mechanical Division | 36.42 | 27.08 | 0 | 0 | 63.51 | 36.42 | 26.86 | 0 | 0 | 63.28 | 45.01 | 64
410 | PASCHIM MEDINIPUR | SM/10731 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009614 | 5265789 | Augmentation | MVS | GO2223002161PH | 19/05/2022 | 112.63 | 7.53 | 120.16 | Midnapore Division | Midnapore Mechanical Division | 50.54 | 4.63 | 0 | 0 | 55.17 | 50.54 | 4.63 | 0 | 0 | 55.17 | 45.91 | 13
411 | PASCHIM MEDINIPUR | SM/14720 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009951 | 40063744 | Augmentation | MVS | GO2223012743PH | 31/01/2023 | 62.64 | 27.66 | 90.31 | Midnapore Division | Midnapore Mechanical Division | 57.09 | 11.38 | 0 | 0 | 68.47 | 57.09 | 1.91 | 0 | 0 | 59 | 65.33 | 25
412 | PASCHIM MEDINIPUR | SM/10779 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009950 | 40014827 | Augmentation | MVS | GO2223003519PH | 25/05/2022 | 51.83 | 27.66 | 79.49 | Midnapore Division | Midnapore Mechanical Division | 8.73 | 14.62 | 0 | 9.35 | 32.7 | 2.08 | 7.71 | 0 | 9.35 | 19.14 | 24.08 | 18
413 | PASCHIM MEDINIPUR | SM/10841 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009945 | 40015132 | Augmentation | MVS | GO2223003646PH | 30/05/2022 | 66.01 | 27.66 | 93.67 | Midnapore Division | Midnapore Mechanical Division | 12.59 | 13.39 | 0 | 0 | 25.98 | 2.13 | 3.34 | 0 | 0 | 5.46 | 5.83 | 10
414 | PASCHIM MEDINIPUR | SM/10685 | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/009946 | 40014396 | Augmentation | MVS | GO2223000916PH | 06/05/2022 | 95.88 | 27.66 | 123.54 | Midnapore Division | Midnapore Mechanical Division | 74.22 | 15.46 | 0 | 0 | 89.68 | 74.22 | 4.59 | 0 | 0 | 78.8 | 63.79 | 79
415 | PASCHIM MEDINIPUR | SM/13036 | RELA AND IT'S ADJOINING MOUJAS PWSS | TSM/013214 | 40026120 | New | MVS | GO2223008364PH | 28/09/2022 | 361.03 | 37.83 | 398.86 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 7.26 | 0 | 12.04 | 4.78 | 0 | 7.26 | 0 | 12.04 | 3.02 | 2
416 | PASCHIM MEDINIPUR | SM/18530 | RERIPUR AND ADJ0INING MOUJAS PWSS | TSM/014535 | 40034188 | New | MVS | 2050/PHE-28011/24/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1128.05 | 57.85 | 1185.9 | Midnapore Division | Midnapore Mechanical Division | 147.36 | 6.42 | 23.61 | 0 | 177.39 | 0 | 0 | 23.61 | 0 | 23.61 | 1.99 | 1
417 | PASCHIM MEDINIPUR | SM/08677 | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/007661 | 8349398 | Retrofitting | SVS | GO2122001799PH | 20/07/2021 | 22.07 | 1.15 | 23.22 | Midnapore Division | Midnapore Mechanical Division | 12.41 | 0 | 0 | 0 | 12.41 | 12.41 | 0 | 0 | 0 | 12.41 | 53.43 | 100
418 | PASCHIM MEDINIPUR | SM/09107 | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/007662 | 40010488 | Retrofitting | MVS | GO2122004571PH | 28/10/2021 | 69.43 | 0 | 69.43 | Midnapore Division | Midnapore Mechanical Division | 34.99 | 0 | 0 | 0 | 34.99 | 28.78 | 0 | 0 | 0 | 28.78 | 41.46 | 76
419 | PASCHIM MEDINIPUR | SM/09724 | Retrofitting of ground water based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. | TSM/008252 | 40010378 | Retrofitting | MVS | GO2122005983PH | 26/11/2021 | 119.15 | 0 | 119.15 | Midnapore Division |  | 93.85 | 0 | 0 | 0 | 93.85 | 76.82 | 0 | 0 | 0 | 76.82 | 64.47 | 90
420 | PASCHIM MEDINIPUR | SM/09420 | Retrofitting of Ground Water Based Balichak Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008481 | 8389177 | Retrofitting | SVS | GO2122005516PH | 17/11/2021 | 181.41 | 0 | 181.41 | Midnapore Division |  | 3.08 | 0 | 0 | 0 | 3.08 | 3.08 | 0 | 0 | 0 | 3.08 | 1.7 | 0
421 | PASCHIM MEDINIPUR | SM/08675 | Retrofitting of Ground Water Based Bhimpur Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/007666 | 8349402 | Retrofitting | MVS | GO2122001797PH | 20/07/2021 | 37.88 | 1.1 | 38.98 | Midnapore Division | Midnapore Mechanical Division | 36.56 | 0 | 0 | 0 | 36.56 | 36.56 | 0 | 0 | 0 | 36.56 | 93.78 | 100
422 | PASCHIM MEDINIPUR | SM/16949 | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. | TSM/018430 | 40047126 | Retrofitting | MVS | GO2223016550PH | 16/03/2023 | 16.47 | 0 | 16.47 | Midnapore Division |  | 13.72 | 0 | 0 | 0 | 13.72 | 13.72 | 0 | 0 | 0 | 13.72 | 83.3 | 100
423 | PASCHIM MEDINIPUR | SM/09106 | Retrofitting of Ground Water Based Chatra Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/007665 | 8385286 | Retrofitting | SVS | GO2122004570PH | 28/10/2021 | 16.51 | 0 | 16.51 | Midnapore Division | Midnapore Mechanical Division | 1.46 | 0 | 0 | 0 | 1.46 | 1.46 | 0 | 0 | 0 | 1.46 | 8.86 | 1
424 | PASCHIM MEDINIPUR | SM/09418 | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008483 | 40004548 | Retrofitting | MVS | GO2122005516PH | 17/11/2021 | 37.56 | 0 | 37.56 | Midnapore Division |  | 26.8 | 0 | 0 | 0 | 26.8 | 26.8 | 0 | 0 | 0 | 26.8 | 71.35 | 100
425 | PASCHIM MEDINIPUR | SM/09722 | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. | TSM/008255 | 40027379 | Retrofitting | MVS | GO2122005983PH | 26/11/2021 | 100.27 | 0 | 100.27 | Midnapore Division |  | 63.83 | 0 | 0 | 0 | 63.83 | 63.83 | 0 | 0 | 0 | 63.83 | 63.66 | 80
426 | PASCHIM MEDINIPUR | SM/09721 | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | TSM/008256 | 40010374 | Retrofitting | MVS | GO2122005983PH | 26/11/2021 | 110.6 | 0 | 110.6 | Midnapore Division |  | 86.07 | 0 | 0 | 0 | 86.07 | 84.58 | 0 | 0 | 0 | 84.58 | 76.48 | 100
427 | PASCHIM MEDINIPUR | SM/09421 | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008482 | 40011075 | Retrofitting | MVS | GO2122005516PH | 17/11/2021 | 226.03 | 0 | 226.03 | Midnapore Division |  | 77.98 | 0 | 0 | 0 | 77.98 | 67.1 | 0 | 0 | 0 | 67.1 | 29.69 | 100
428 | PASCHIM MEDINIPUR | SM/08678 | Retrofitting of Ground Water Based Hatimasan Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/007664 | 8349406 | Retrofitting | SVS | GO2122001800PH | 20/07/2021 | 18.85 | 1.5 | 20.35 | Midnapore Division | Midnapore Mechanical Division | 18.17 | 0 | 0 | 0 | 18.17 | 18.17 | 0 | 0 | 0 | 18.17 | 89.29 | 100
429 | PASCHIM MEDINIPUR | SM/09419 | Retrofitting of Ground Water Based Kalshibhanga Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008546 | 40061441 | Retrofitting | SVS | GO2122005516PH | 17/11/2021 | 13.42 | 0 | 13.42 | Midnapore Division |  | 10.33 | 0 | 0 | 0 | 10.33 | 10.33 | 0 | 0 | 0 | 10.33 | 77 | 100
430 | PASCHIM MEDINIPUR | SM/09723 | Retrofitting of ground water based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. | TSM/008257 | 40010377 | Retrofitting | SVS | GO2122005983PH | 26/11/2021 | 61.9 | 0 | 61.9 | Midnapore Division |  | 42.13 | 0 | 0 | 0 | 42.13 | 42.13 | 0 | 0 | 0 | 42.13 | 68.06 | 100
431 | PASCHIM MEDINIPUR | SM/09417 | Retrofitting of Ground Water Based Keudi Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/008542 | 8388616 | Retrofitting | SVS | GO2122005516PH | 17/11/2021 | 11.59 | 0 | 11.59 | Midnapore Division |  | 7.62 | 0 | 0 | 0 | 7.62 | 7.62 | 0 | 0 | 0 | 7.62 | 65.74 | 100
432 | PASCHIM MEDINIPUR | SM/08676 | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | TSM/007663 | 8349385 | Retrofitting | SVS | GO2122001798PH | 20/07/2021 | 52.64 | 1.25 | 53.89 | Midnapore Division | Midnapore Mechanical Division | 49.9 | 0 | 0 | 0 | 49.9 | 49.9 | 0 | 0 | 0 | 49.9 | 92.59 | 78
433 | PASCHIM MEDINIPUR | SM/09726 | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | TSM/008253 | 40001065 | Retrofitting | SVS | GO2122005983PH | 26/11/2021 | 424.38 | 0 | 424.38 | Midnapore Division | Midnapore Mechanical Division | 372.93 | 0 | 0 | 0 | 372.93 | 340.93 | 0 | 0 | 0 | 340.93 | 80.34 | 96
434 | PASCHIM MEDINIPUR | SM/09725 | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | TSM/008254 | 40027399 | Retrofitting | SVS | GO2122005983PH | 26/11/2021 | 41.57 | 0 | 41.57 | Midnapore Division |  | 33.59 | 0 | 0 | 0 | 33.59 | 33.59 | 0 | 0 | 0 | 33.59 | 80.81 | 85
435 | PASCHIM MEDINIPUR | SM/08213 | Retrofitting of Jamdoba & Godamauli Piped Water Supply Scheme to accommodate all FHTC. | TSM/007153 | 8226428 | Retrofitting | MVS | GO2021006653PH | 09/02/2021 | 36.08 | 0 | 36.08 | Midnapore Division |  | 1.94 | 0 | 0 | 0 | 1.94 | 1.94 | 0 | 0 | 0 | 1.94 | 5.38 | 100
436 | PASCHIM MEDINIPUR | SM/08206 | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. | TSM/007155 | 8226473 | Retrofitting | MVS | GO2021006652PH | 09/02/2021 | 65.82 | 0 | 65.82 | Midnapore Division |  | 37.36 | 0 | 0 | 0 | 37.36 | 37.36 | 0 | 0 | 0 | 37.36 | 56.76 | 100
437 | PASCHIM MEDINIPUR | SM/08215 | Retrofitting of Kalaimuri Piped Water Supply Scheme to accommodate all FHTC. | TSM/007152 | 8226422 | Retrofitting | SVS | GO2021006655PH | 09/02/2021 | 36.97 | 0 | 36.97 | Midnapore Division |  | 17.95 | 0 | 0 | 0 | 17.95 | 17.95 | 0 | 0 | 0 | 17.95 | 48.56 | 100
438 | PASCHIM MEDINIPUR | SM/08208 | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. | TSM/007157 | 40008426 | Retrofitting | SVS | GO2021006650PH | 09/02/2021 | 38.64 | 0 | 38.64 | Midnapore Division |  | 15.82 | 0 | 0 | 0 | 15.82 | 15.77 | 0 | 0 | 0 | 15.77 | 40.82 | 100
439 | PASCHIM MEDINIPUR | SM/08205 | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. | TSM/007156 | 8226475 | Retrofitting | SVS | GO2021006649PH | 09/02/2021 | 41.47 | 0 | 41.47 | Midnapore Division |  | 18.58 | 0 | 0 | 0 | 18.58 | 18.58 | 0 | 0 | 0 | 18.58 | 44.81 | 100
440 | PASCHIM MEDINIPUR | SM/08211 | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. | TSM/007154 | 40008463 | Retrofitting | SVS | GO2021006648PH | 09/02/2021 | 115.14 | 0 | 115.14 | Midnapore Division |  | 52.24 | 0 | 0 | 0 | 52.24 | 50.8 | 0 | 0 | 0 | 50.8 | 44.13 | 81
441 | PASCHIM MEDINIPUR | SM/08204 | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | TSM/007166 | 8217604 | Retrofitting | MVS | GO2021006675PH | 09/02/2021 | 259.13 | 0 | 259.13 | Midnapore Division |  | 164.02 | 0 | 0 | 0 | 164.02 | 164 | 0 | 0 | 0 | 164 | 63.29 | 81
442 | PASCHIM MEDINIPUR | SM/08079 | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | TSM/006755 | 40010188 | Retrofitting | MVS | GO2021006268PH | 04/02/2021 | 652.85 | 0 | 652.85 | Midnapore Division |  | 184.28 | 0 | 0 | 0 | 184.28 | 174.88 | 0 | 0 | 0 | 174.88 | 26.79 | 71
443 | PASCHIM MEDINIPUR | SM/08203 | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | TSM/007167 | 8244044 | Retrofitting | MVS | GO2021006673PH | 09/02/2021 | 112.39 | 0 | 112.39 | Midnapore Division |  | 108.05 | 0 | 0 | 0 | 108.05 | 105.71 | 0 | 0 | 0 | 105.71 | 94.05 | 90
444 | PASCHIM MEDINIPUR | SM/08696 | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | TSM/007431 | 8374213 | Retrofitting | MVS | GO2122002843PH | 01/09/2021 | 250.75 | 0 | 250.75 | Midnapore Division |  | 242.69 | 0 | 0 | 0 | 242.69 | 237.89 | 0 | 0 | 0 | 237.89 | 94.87 | 100
445 | PASCHIM MEDINIPUR | SM/09101 | Retrofitting to accommodate FHTC in Bamanda PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | TSM/007396 | 8385100 | Retrofitting | SVS | GO2122004575PH | 28/10/2021 | 28.75 | 0 | 28.75 | Midnapore Division |  | 26.38 | 0 | 0 | 0 | 26.38 | 25.77 | 0 | 0 | 0 | 25.77 | 89.64 | 95
446 | PASCHIM MEDINIPUR | SM/06897 | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme. | TSM/005564 | 8126237 | Retrofitting | MVS | GO2021001855PH | 09/10/2020 | 97.58 | 0 | 97.58 | Midnapore Division |  | 93.31 | 0 | 0 | 0 | 93.31 | 90.35 | 0 | 0 | 0 | 90.35 | 92.59 | 76
447 | PASCHIM MEDINIPUR | SM/09704 | Retrofitting to accommodate FHTC under JJM in Bajpara PWSS under Midnapore Sadar Block in Paschim Medinipur District | TSM/008267 | 7756987 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 78.3 | 0 | 78.3 | Midnapore Division |  | 50 | 0 | 0 | 0 | 50 | 45.24 | 0 | 0 | 0 | 45.24 | 57.78 | 76
448 | PASCHIM MEDINIPUR | SM/09706 | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District | TSM/008262 | 7394358 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 79.89 | 0 | 79.89 | Midnapore Division |  | 72.8 | 0 | 0 | 0 | 72.8 | 68.8 | 0 | 0 | 0 | 68.8 | 86.11 | 12
449 | PASCHIM MEDINIPUR | SM/06908 | Retrofitting to accommodate FHTC under JJM in Beluria Piped Water Supply Scheme. | TSM/005565 | 8126431 | Retrofitting | MVS | GO2021001856PH | 09/10/2020 | 95.43 | 0 | 95.43 | Midnapore Division |  | 90.94 | 0 | 0 | 0 | 90.94 | 69.1 | 0 | 0 | 0 | 69.1 | 72.4 | 80
450 | PASCHIM MEDINIPUR | SM/09701 | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS under Midnapore Sadar Block in Paschim Medinipur District | TSM/008263 | 7757002 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 132.83 | 0 | 132.83 | Midnapore Division |  | 109.69 | 0 | 0 | 0 | 109.69 | 89.81 | 0 | 0 | 0 | 89.81 | 67.61 | 95
451 | PASCHIM MEDINIPUR | SM/06911 | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur Piped Water Supply Scheme. | TSM/005566 | 8126521 | Retrofitting | MVS | GO2021001857PH | 09/10/2020 | 94.57 | 0 | 94.57 | Midnapore Division |  | 89.65 | 0 | 0 | 0 | 89.65 | 89.4 | 0 | 0 | 0 | 89.4 | 94.53 | 98
452 | PASCHIM MEDINIPUR | SM/06912 | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. | TSM/005567 | 8126204 | Retrofitting | MVS | GO2021001858PH | 09/10/2020 | 97.5 | 0 | 97.5 | Midnapore Division |  | 84.95 | 0 | 0 | 0 | 84.95 | 84.95 | 0 | 0 | 0 | 84.95 | 87.13 | 90
453 | PASCHIM MEDINIPUR | SM/09702 | Retrofitting to accommodate FHTC under JJM in Chandipur PWSS under Daspur-I Block in Paschim Medinipur District | TSM/008260 | 7756922 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 97.46 | 0 | 97.46 | Midnapore Division |  | 18.26 | 0 | 0 | 0 | 18.26 | 15.8 | 0 | 0 | 0 | 15.8 | 16.21 | 60
454 | PASCHIM MEDINIPUR | SM/06894 | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | TSM/005559 | 6323280 | Retrofitting | MVS | GO2021001485PH | 09/10/2020 | 78.36 | 0 | 78.36 | Midnapore Division |  | 72.53 | 0 | 0 | 0 | 72.53 | 71.23 | 0 | 0 | 0 | 71.23 | 90.9 | 95
455 | PASCHIM MEDINIPUR | SM/06913 | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. | TSM/005568 | 8126842 | Retrofitting | MVS | GO2021001859PH | 09/10/2020 | 97.02 | 0 | 97.02 | Midnapore Division |  | 65.94 | 0 | 0 | 0 | 65.94 | 28.6 | 0 | 0 | 0 | 28.6 | 29.48 | 40
456 | PASCHIM MEDINIPUR | SM/06914 | Retrofitting to accommodate FHTC under JJM in Chhotokhelna Piped Water Supply Scheme. | TSM/005569 | 4724106 | Retrofitting | MVS | GO2021001860PH | 09/10/2020 | 96.46 | 0 | 96.46 | Midnapore Division |  | 80.57 | 0 | 0 | 11 | 91.57 | 80.57 | 0 | 0 | 11 | 91.57 | 94.92 | 90
457 | PASCHIM MEDINIPUR | SM/06915 | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | TSM/005570 | 8126213 | Retrofitting | MVS | GO2021001862PH | 09/10/2020 | 69.14 | 0 | 69.14 | Midnapore Division |  | 67.13 | 0 | 0 | 0 | 67.13 | 67.01 | 0 | 0 | 0 | 67.01 | 96.92 | 90
458 | PASCHIM MEDINIPUR | SM/06916 | Retrofitting to accommodate FHTC under JJM in Gobardhanpur Piped Water Supply Scheme. | TSM/005571 | 8126846 | Retrofitting | MVS | GO2021001863PH | 09/10/2020 | 90.78 | 0 | 90.78 | Midnapore Division |  | 87.65 | 0 | 0 | 0 | 87.65 | 81.86 | 0 | 0 | 0 | 81.86 | 90.17 | 90
459 | PASCHIM MEDINIPUR | SM/09088 | Retrofitting to accommodate FHTC under JJM in Gurguripal PWSS, Block - Midnapore Sadar, District - Paschim Medinipur. | TSM/008471 | 0 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 72.62 | 0 | 72.62 | Midnapore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | PASCHIM MEDINIPUR | SM/06899 | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. | TSM/005560 | 6919901 | Retrofitting | MVS | GO2021001486PH | 09/10/2020 | 98.16 | 0 | 98.16 | Midnapore Division |  | 98.16 | 0 | 0 | 0 | 98.16 | 94.3 | 0 | 0 | 0 | 94.3 | 96.06 | 0
461 | PASCHIM MEDINIPUR | SM/09085 | Retrofitting to accommodate FHTC under JJM in Kanchangeria PWSS, Block - Debra, District - Paschim Medinipur. | TSM/008470 | 7756990 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 89.46 | 0 | 89.46 | Midnapore Division |  | 35.47 | 0 | 0 | 0 | 35.47 | 35.47 | 0 | 0 | 0 | 35.47 | 39.65 | 80
462 | PASCHIM MEDINIPUR | SM/06923 | Retrofitting to accommodate FHTC under JJM in Kapasda Piped Water Supply Scheme. | TSM/005572 | 8126815 | Retrofitting | MVS | GO2021001864PH | 09/10/2020 | 96.2 | 0 | 96.2 | Midnapore Division |  | 70.21 | 0 | 0 | 0 | 70.21 | 66 | 0 | 0 | 0 | 66 | 68.61 | 100
463 | PASCHIM MEDINIPUR | SM/06901 | Retrofitting to accommodate FHTC under JJM in Karkai Piped Water Supply Scheme. | TSM/005573 | 5502115 | Retrofitting | MVS | GO2021001865PH | 09/10/2020 | 98.04 | 0 | 98.04 | Midnapore Division |  | 95.18 | 0 | 0 | 0 | 95.18 | 89.53 | 0 | 0 | 0 | 89.53 | 91.32 | 100
464 | PASCHIM MEDINIPUR | SM/09082 | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | TSM/008464 | 6854754 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 33.9 | 0 | 33.9 | Midnapore Division |  | 28.76 | 0 | 0 | 0 | 28.76 | 28.38 | 0 | 0 | 0 | 28.38 | 83.72 | 95
465 | PASCHIM MEDINIPUR | SM/09705 | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District | TSM/008265 | 7401910 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 47.69 | 0 | 47.69 | Midnapore Division |  | 46.3 | 0 | 0 | 0 | 46.3 | 46.3 | 0 | 0 | 0 | 46.3 | 97.09 | 90
466 | PASCHIM MEDINIPUR | SM/06900 | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | TSM/005561 | 6919887 | Retrofitting | MVS | GO2021001852PH | 09/10/2020 | 50.84 | 0 | 50.84 | Midnapore Division |  | 44.84 | 0 | 0 | 0 | 44.84 | 44.84 | 0 | 0 | 0 | 44.84 | 88.2 | 100
467 | PASCHIM MEDINIPUR | SM/09709 | Retrofitting to accommodate FHTC under JJM in Khagragerya PWSS under Sbang Block in Paschim Medinipur District | TSM/008266 | 7940642 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 125.44 | 0 | 125.44 | Midnapore Division |  | 43.38 | 0 | 0 | 0 | 43.38 | 43.38 | 0 | 0 | 0 | 43.38 | 34.58 | 55
468 | PASCHIM MEDINIPUR | SM/06902 | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. | TSM/005562 | 8127574 | Retrofitting | MVS | GO2021001853PH | 09/10/2020 | 50.48 | 0 | 50.48 | Midnapore Division |  | 49.01 | 0 | 0 | 0 | 49.01 | 49.01 | 0 | 0 | 0 | 49.01 | 97.09 | 95
469 | PASCHIM MEDINIPUR | SM/09086 | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. | TSM/008472 | 7394354 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 140.08 | 0 | 140.08 | Midnapore Division |  | 87.79 | 0 | 0 | 0 | 87.79 | 79.78 | 0 | 0 | 0 | 79.78 | 56.95 | 76
470 | PASCHIM MEDINIPUR | SM/06925 | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. | TSM/005574 | 5265789 | Retrofitting | MVS | GO2021001866PH | 09/10/2020 | 95.44 | 0 | 95.44 | Midnapore Division |  | 83.77 | 0 | 0 | 0 | 83.77 | 83.64 | 0 | 0 | 0 | 83.64 | 87.64 | 93
471 | PASCHIM MEDINIPUR | SM/06928 | Retrofitting to accommodate FHTC under JJM in Kolanda Piped Water Supply Scheme. | TSM/005575 | 8126850 | Retrofitting | MVS | GO2021001867PH | 09/10/2020 | 89.26 | 0 | 89.26 | Midnapore Division |  | 68.01 | 0 | 0 | 0 | 68.01 | 60.67 | 0 | 0 | 0 | 60.67 | 67.97 | 80
472 | PASCHIM MEDINIPUR | SM/09707 | Retrofitting to accommodate FHTC under JJM in Krishnapriya PWSS under Pingla Block in Paschim Medinipur District | TSM/008261 | 7757014 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 46.32 | 0 | 46.32 | Midnapore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
473 | PASCHIM MEDINIPUR | SM/09710 | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District | TSM/008259 | 7756996 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 72.27 | 0 | 72.27 | Midnapore Division |  | 58.45 | 0 | 0 | 0 | 58.45 | 58.4 | 0 | 0 | 0 | 58.4 | 80.81 | 90
474 | PASCHIM MEDINIPUR | SM/08694 | Retrofitting to accommodate FHTC under JJM in Madpur PWSS | TSM/007395 | 5627001 | Retrofitting | MVS | GO2122002587PH | 01/09/2021 | 99.66 | 0 | 99.66 | Midnapore Division |  | 89.95 | 0 | 0 | 0 | 89.95 | 75.6 | 0 | 0 | 0 | 75.6 | 75.85 | 95
475 | PASCHIM MEDINIPUR | SM/06895 | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. | TSM/005576 | 8136498 | Retrofitting | MVS | GO2021001868PH | 09/10/2020 | 98.9 | 0 | 98.9 | Midnapore Division |  | 96.02 | 0 | 0 | 0 | 96.02 | 96.02 | 0 | 0 | 0 | 96.02 | 97.09 | 100
476 | PASCHIM MEDINIPUR | SM/09084 | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | TSM/008469 | 40064150 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 50.05 | 0 | 50.05 | Midnapore Division |  | 0 | 0 | 0 | 19.63 | 19.63 | 0 | 0 | 0 | 19.63 | 19.63 | 39.23 | 5
477 | PASCHIM MEDINIPUR | SM/09703 | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District | TSM/008268 | 7327100 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 64.66 | 0 | 64.66 | Midnapore Division |  | 35.54 | 0 | 0 | 0 | 35.54 | 0 | 0 | 0 | 0 | 0 | 0 | 85
478 | PASCHIM MEDINIPUR | SM/06905 | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | TSM/005563 | 6935904 | Retrofitting | MVS | GO2021001854PH | 09/10/2020 | 73.67 | 0 | 73.67 | Midnapore Division |  | 73.51 | 0 | 0 | 0 | 73.51 | 69.47 | 0 | 0 | 0 | 69.47 | 94.29 | 100
479 | PASCHIM MEDINIPUR | SM/09081 | Retrofitting to accommodate FHTC under JJM in Nabin Mahespur PWSS, Block - Daspur-I, District - Paschim Medinipur. | TSM/008467 | 7401902 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 62.19 | 0 | 62.19 | Midnapore Division |  | 54.76 | 0 | 0 | 0 | 54.76 | 50 | 0 | 0 | 0 | 50 | 80.4 | 100
480 | PASCHIM MEDINIPUR | SM/06896 | Retrofitting to accommodate FHTC under JJM in Narayanbar Piped Water Supply Scheme. | TSM/005577 | 8127342 | Retrofitting | MVS | GO2021001869PH | 09/10/2020 | 95.91 | 0 | 95.91 | Midnapore Division |  | 80.2 | 0 | 0 | 0 | 80.2 | 57.97 | 0 | 0 | 0 | 57.97 | 60.44 | 85
481 | PASCHIM MEDINIPUR | SM/09708 | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS under Sabang Block in Paschim Medinipur District | TSM/008258 | 7462262 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 118.7 | 0 | 118.7 | Midnapore Division |  | 97.59 | 0 | 0 | 0 | 97.59 | 96.48 | 0 | 0 | 0 | 96.48 | 81.28 | 95
482 | PASCHIM MEDINIPUR | SM/06930 | Retrofitting to accommodate FHTC under JJM in Palashi Piped Water Supply Scheme. | TSM/005578 | 8126819 | Retrofitting | MVS | GO2021001870PH | 09/10/2020 | 89.32 | 0 | 89.32 | Midnapore Division |  | 86.72 | 0 | 0 | 0 | 86.72 | 86.19 | 0 | 0 | 0 | 86.19 | 96.5 | 96
483 | PASCHIM MEDINIPUR | SM/09711 | Retrofitting to accommodate FHTC under JJM in Paschim Beguni PWSS under Debra Block in Paschim Medinipur District | TSM/008264 | 7402016 | Retrofitting | MVS | GO2122005982PH | 26/11/2021 | 38.75 | 0 | 38.75 | Midnapore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
484 | PASCHIM MEDINIPUR | SM/08697 | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block - Dantan-II in the district of Paschim Medinipur. | TSM/007393 | 7327572 | Retrofitting | MVS | GO2122002589PH | 01/09/2021 | 92.77 | 0 | 92.77 | Midnapore Division |  | 50 | 0 | 0 | 0 | 50 | 43.4 | 0 | 0 | 0 | 43.4 | 46.79 | 80
485 | PASCHIM MEDINIPUR | SM/09087 | Retrofitting to accommodate FHTC under JJM in Sabang PWSS, Block - Sabang, District - Paschim Medinipur. | TSM/008473 | 40016203 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 221.59 | 0 | 221.59 | Midnapore Division |  | 43.73 | 0 | 0 | 0 | 43.73 | 43.73 | 0 | 0 | 0 | 43.73 | 19.74 | 81
486 | PASCHIM MEDINIPUR | SM/06933 | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | TSM/005579 | 8126847 | Retrofitting | MVS | GO2021001871PH | 09/10/2020 | 93.43 | 0 | 93.43 | Midnapore Division |  | 87.09 | 0 | 0 | 0 | 87.09 | 84.03 | 0 | 0 | 0 | 84.03 | 89.94 | 100
487 | PASCHIM MEDINIPUR | SM/09080 | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur | TSM/008465 | 40063746 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 35.97 | 0 | 35.97 | Midnapore Division |  | 21.63 | 0 | 0 | 0 | 21.63 | 19.93 | 0 | 0 | 0 | 19.93 | 55.4 | 5
488 | PASCHIM MEDINIPUR | SM/08695 | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS | TSM/007394 | 8376753 | Retrofitting | MVS | GO2122002588PH | 01/09/2021 | 125.78 | 0 | 125.78 | Midnapore Division |  | 95.6 | 0 | 0 | 0 | 95.6 | 91.25 | 0 | 0 | 0 | 91.25 | 72.55 | 90
489 | PASCHIM MEDINIPUR | SM/12117 | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | TSM/009927 | 40047128 | Retrofitting | MVS | GO2223007091PH | 06/09/2022 | 72.98 | 0 | 72.98 | Midnapore Division |  | 59.86 | 0 | 0 | 0 | 59.86 | 59.86 | 0 | 0 | 0 | 59.86 | 82.02 | 90
490 | PASCHIM MEDINIPUR | SM/09083 | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. | TSM/008468 | 7940687 | Retrofitting | MVS | GO2122004574PH | 28/10/2021 | 89.12 | 0 | 89.12 | Midnapore Division |  | 59.82 | 0 | 0 | 0 | 59.82 | 59.82 | 0 | 0 | 0 | 59.82 | 67.12 | 98
491 | PASCHIM MEDINIPUR | SM/07876 | Retrofitting to accomodate balance FHTC in 5 Nos. PWSS within Ghatal Sub-Division | TSM/006754 | 40016299 | Retrofitting | MVS | GO2021004736PH | 19/01/2021 | 99.92 | 0 | 99.92 | Midnapore Division |  | 15.04 | 0 | 0 | 0 | 15.04 | 15.04 | 0 | 0 | 0 | 15.04 | 15.05 | 71
492 | PASCHIM MEDINIPUR | SM/08210 | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur | TSM/007140 | 7757011 | Retrofitting | MVS | GO2021006665PH | 09/02/2021 | 73.21 | 0 | 73.21 | Midnapore Division |  | 70.09 | 0 | 0 | 0 | 70.09 | 70.09 | 0 | 0 | 0 | 70.09 | 95.74 | 100
493 | PASCHIM MEDINIPUR | SM/06932 | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Sabang & 1 No. PWSS within Pingla Block | TSM/005724 | 8127602 | Retrofitting | MVS | GO2021001900PH | 09/10/2020 | 51.23 | 0 | 51.23 | Midnapore Division |  | 51.23 | 0 | 0 | 0 | 51.23 | 39.55 | 0 | 0 | 0 | 39.55 | 77.2 | 96
494 | PASCHIM MEDINIPUR | SM/06935 | Retrofitting to accomodate FHTC under JJM in 1 No. PWSS within Salboni & 1 No. PWSS within Garhbeta-III Block | TSM/005723 | 40046262 | Retrofitting | MVS | GO2021001897PH | 09/10/2020 | 77.64 | 0 | 77.64 | Midnapore Division |  | 75.35 | 0 | 0 | 0 | 75.35 | 54.23 | 0 | 0 | 0 | 54.23 | 69.84 | 96
495 | PASCHIM MEDINIPUR | SM/18486 | RETROFITTING TO ACCOMODATE FHTC UNDER JJM IN 32 PWSS FOR DRAUGHT LIKE SITUATION PRONE BLOCKS OF PASCHIM MEDINIPUR DISTRICT (MID-TERM PLAN UNDER MASTER PLAN) UNDER MIDNAPORE DIVISION, P.H.E Dte. | TSM/018463 | 8136856 | Retrofitting | MVS | 1999/PHE-28011/236/2023-ESTT CELL-Dept. of PHE | 24/07/2023 | 3340.14 | 0 | 3340.14 | Midnapore Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
496 | PASCHIM MEDINIPUR | SM/06903 | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | TSM/005704 | 8126439 | Retrofitting | MVS | GO2021001872PH | 09/10/2020 | 99.71 | 0 | 99.71 | Midnapore Division |  | 78.49 | 0 | 0 | 0 | 78.49 | 77.76 | 0 | 0 | 0 | 77.76 | 77.99 | 76
497 | PASCHIM MEDINIPUR | SM/06906 | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS | TSM/005705 | 8126441 | Retrofitting | MVS | GO2021001873PH | 09/10/2020 | 99.91 | 0 | 99.91 | Midnapore Division |  | 79.25 | 0 | 0 | 0 | 79.25 | 76.09 | 0 | 0 | 0 | 76.09 | 76.16 | 80
498 | PASCHIM MEDINIPUR | SM/06926 | Retrofitting to accomodate FHTC under JJM in Barsahara PWSS | TSM/005721 | 8126358 | Retrofitting | MVS | GO2021001894PH | 09/10/2020 | 97.54 | 0 | 97.54 | Midnapore Division |  | 66.3 | 0 | 0 | 0 | 66.3 | 66.25 | 0 | 0 | 0 | 66.25 | 67.92 | 80
499 | PASCHIM MEDINIPUR | SM/08207 | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur | TSM/007143 | 7757006 | Retrofitting | MVS | GO2021006671PH | 09/02/2021 | 97.87 | 0 | 97.87 | Midnapore Division |  | 94.14 | 0 | 0 | 0 | 94.14 | 94.14 | 0 | 0 | 0 | 94.14 | 96.19 | 100
500 | PASCHIM MEDINIPUR | SM/06907 | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | TSM/005706 | 8126424 | Retrofitting | MVS | GO2021001874PH | 09/10/2020 | 88.73 | 0 | 88.73 | Midnapore Division |  | 61.44 | 0 | 0 | 15 | 76.44 | 61.44 | 0 | 0 | 15 | 76.44 | 86.15 | 73
501 | PASCHIM MEDINIPUR | SM/06909 | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | TSM/005707 | 8126427 | Retrofitting | MVS | GO2021001875PH | 09/10/2020 | 86.43 | 0 | 86.43 | Midnapore Division | Midnapore Mechanical Division | 78.75 | 0 | 0 | 0 | 78.75 | 64.49 | 0 | 0 | 0 | 64.49 | 74.62 | 90
502 | PASCHIM MEDINIPUR | SM/08209 | Retrofitting to accomodate FHTC under JJM in Bishnupur PWSS Block Sabang District Paschim Medinipur | TSM/007144 | 8339355 | Retrofitting | SVS | GO2021006667PH | 09/02/2021 | 92.74 | 0 | 92.74 | Midnapore Division |  | 73.87 | 0 | 0 | 0 | 73.87 | 51.28 | 0 | 0 | 0 | 51.28 | 55.3 | 76
503 | PASCHIM MEDINIPUR | SM/06917 | Retrofitting to accomodate FHTC under JJM in Bural (Zone-I) PWSS | TSM/005708 | 5616281 | Retrofitting | MVS | GO2021001876PH | 09/10/2020 | 99.8 | 0 | 99.8 | Midnapore Division |  | 93.72 | 0 | 0 | 0 | 93.72 | 93.72 | 0 | 0 | 0 | 93.72 | 93.9 | 98
504 | PASCHIM MEDINIPUR | SM/06919 | Retrofitting to accomodate FHTC under JJM in Bural (Zone-II) PWSS | TSM/005709 | 5616281 | Retrofitting | MVS | GO2021001877PH | 09/10/2020 | 99.9 | 0 | 99.9 | Midnapore Division |  | 94.89 | 0 | 0 | 0 | 94.89 | 81.71 | 0 | 0 | 0 | 81.71 | 81.79 | 89
505 | PASCHIM MEDINIPUR | SM/06920 | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-I) PWSS | TSM/005710 | 8126246 | Retrofitting | MVS | GO2021001878PH | 09/10/2020 | 90.08 | 0 | 90.08 | Midnapore Division |  | 87.46 | 0 | 0 | 0 | 87.46 | 63.02 | 0 | 0 | 0 | 63.02 | 69.96 | 80
506 | PASCHIM MEDINIPUR | SM/06922 | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-II) PWSS | TSM/005711 | 8126252 | Retrofitting | MVS | GO2021001883PH | 09/10/2020 | 83.25 | 0 | 83.25 | Midnapore Division |  | 74.59 | 0 | 0 | 0 | 74.59 | 63.89 | 0 | 0 | 0 | 63.89 | 76.74 | 85
507 | PASCHIM MEDINIPUR | SM/06904 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | TSM/005712 | 40043145 | Retrofitting | MVS | GO2021001884PH | 09/10/2020 | 99.98 | 0 | 99.98 | Midnapore Division |  | 97.4 | 0 | 0 | 0 | 97.4 | 77.92 | 0 | 0 | 0 | 77.92 | 77.93 | 100
508 | PASCHIM MEDINIPUR | SM/06910 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-II) PWSS | TSM/005713 | 40049956 | Retrofitting | MVS | GO2021001885PH | 09/10/2020 | 99.8 | 0 | 99.8 | Midnapore Division |  | 96.88 | 0 | 0 | 0 | 96.88 | 90.19 | 0 | 0 | 0 | 90.19 | 90.36 | 100
509 | PASCHIM MEDINIPUR | SM/06918 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | TSM/005714 | 5269591 | Retrofitting | MVS | GO2021001886PH | 09/10/2020 | 76.98 | 0 | 76.98 | Midnapore Division |  | 74.72 | 0 | 0 | 0 | 74.72 | 29.73 | 0 | 0 | 0 | 29.73 | 38.62 | 100
510 | PASCHIM MEDINIPUR | SM/06921 | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS | TSM/005715 | 5269591 | Retrofitting | MVS | GO2021001887PH | 09/10/2020 | 57.62 | 0 | 57.62 | Midnapore Division |  | 17.86 | 0 | 0 | 0 | 17.86 | 3.4 | 0 | 0 | 0 | 3.4 | 5.9 | 100
511 | PASCHIM MEDINIPUR | SM/08212 | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur | TSM/007145 | 6859097 | Retrofitting | MVS | GO2021006666PH | 09/02/2021 | 42.65 | 0 | 42.65 | Midnapore Division |  | 33.58 | 0 | 0 | 0 | 33.58 | 25.06 | 0 | 0 | 0 | 25.06 | 58.74 | 95
512 | PASCHIM MEDINIPUR | SM/06929 | Retrofitting to accomodate FHTC under JJM in Julkapur PWSS | TSM/005716 | 8137673 | Retrofitting | MVS | GO2021001888PH | 09/10/2020 | 50.26 | 0 | 50.26 | Midnapore Division |  | 48.8 | 0 | 0 | 0 | 48.8 | 47.25 | 0 | 0 | 0 | 47.25 | 94.02 | 100
513 | PASCHIM MEDINIPUR | SM/08214 | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur | TSM/007146 | 6904549 | Retrofitting | MVS | GO2021006664PH | 09/02/2021 | 102.3 | 0 | 102.3 | Midnapore Division |  | 69.49 | 0 | 0 | 0 | 69.49 | 69.49 | 0 | 0 | 0 | 69.49 | 67.92 | 83
514 | PASCHIM MEDINIPUR | SM/08221 | Retrofitting to accomodate FHTC under JJM in Malara PWSS | TSM/007149 | 7940618 | Retrofitting | MVS | GO2021006661PH | 09/02/2021 | 23.54 | 0 | 23.54 | Midnapore Division |  | 20 | 0 | 0 | 0 | 20 | 18.78 | 0 | 0 | 0 | 18.78 | 79.76 | 100
515 | PASCHIM MEDINIPUR | SM/06898 | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | TSM/005717 | 8125952 | Retrofitting | SVS | GO2021001890PH | 09/10/2020 | 44.54 | 0 | 44.54 | Midnapore Division | Midnapore Mechanical Division | 43.24 | 0 | 0 | 0 | 43.24 | 40.37 | 0 | 0 | 0 | 40.37 | 90.63 | 100
516 | PASCHIM MEDINIPUR | SM/08218 | Retrofitting to accomodate FHTC under JJM in Mugbasan PWSS | TSM/007150 | 7757008 | Retrofitting | MVS | GO2021006660PH | 09/02/2021 | 71.14 | 0 | 71.14 | Midnapore Division |  | 68.18 | 0 | 0 | 0 | 68.18 | 68.18 | 0 | 0 | 0 | 68.18 | 95.85 | 100
517 | PASCHIM MEDINIPUR | SM/06924 | Retrofitting to accomodate FHTC under JJM in Panpara PWSS | TSM/005719 | 8136320 | Retrofitting | MVS | GO2021001892PH | 09/10/2020 | 97.15 | 0 | 97.15 | Midnapore Division |  | 89.44 | 0 | 0 | 0 | 89.44 | 57.08 | 0 | 0 | 0 | 57.08 | 58.75 | 93
518 | PASCHIM MEDINIPUR | SM/06927 | Retrofitting to accomodate FHTC under JJM in Ragpur PWSS | TSM/005722 | 8136307 | Retrofitting | MVS | GO2021001896PH | 09/10/2020 | 97.83 | 0 | 97.83 | Midnapore Division |  | 66.49 | 0 | 0 | 0 | 66.49 | 55.13 | 0 | 0 | 0 | 55.13 | 56.35 | 80
519 | PASCHIM MEDINIPUR | SM/06931 | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | TSM/005718 | 8136479 | Retrofitting | MVS | GO2021001891PH | 09/10/2020 | 98.97 | 0 | 98.97 | Midnapore Division |  | 39.39 | 0 | 0 | 0 | 39.39 | 39.39 | 0 | 0 | 0 | 39.39 | 39.8 | 75
520 | PASCHIM MEDINIPUR | SM/06934 | Retrofitting to accomodate FHTC under JJM in Ranapur PWSS | TSM/005720 | 8136486 | Retrofitting | MVS | GO2021001893PH | 09/10/2020 | 95.64 | 0 | 95.64 | Midnapore Division |  | 92.08 | 0 | 0 | 0 | 92.08 | 91.92 | 0 | 0 | 0 | 91.92 | 96.12 | 100
521 | PASCHIM MEDINIPUR | SM/08219 | Retrofitting to accomodate FHTC under JJM in Satkui PWSS | TSM/007148 | 40010373 | Retrofitting | MVS | GO2021006657PH | 09/02/2021 | 63.45 | 0 | 63.45 | Midnapore Division |  | 61.61 | 0 | 0 | 0 | 61.61 | 61.12 | 0 | 0 | 0 | 61.12 | 96.33 | 96
522 | PASCHIM MEDINIPUR | SM/08216 | Retrofitting to accomodate FHTC under JJM in Sauri Kotbar PWSS Block - Dantan-II District Paschim Medinipur | TSM/007141 | 7401905 | Retrofitting | MVS | GO2021006662PH | 09/02/2021 | 91.33 | 0 | 91.33 | Midnapore Division |  | 88.67 | 0 | 0 | 0 | 88.67 | 88.67 | 0 | 0 | 0 | 88.67 | 97.09 | 10
523 | PASCHIM MEDINIPUR | SM/08217 | Retrofitting to accomodate FHTC under JJM in Shanrpur PWSS Block - Debra District Paschim Medinipur | TSM/007142 | 8288794 | Retrofitting | MVS | GO2021006669PH | 09/02/2021 | 89.04 | 0 | 89.04 | Midnapore Division |  | 78.77 | 0 | 0 | 0 | 78.77 | 78.77 | 0 | 0 | 0 | 78.77 | 88.47 | 100
524 | PASCHIM MEDINIPUR | SM/08220 | Retrofitting to accomodate FHTC under JJM in Tararui PWSS | TSM/007147 | 7394352 | Retrofitting | MVS | GO2021006659PH | 09/02/2021 | 76.79 | 0 | 76.79 | Midnapore Division |  | 73.75 | 0 | 0 | 0 | 73.75 | 68.32 | 0 | 0 | 0 | 68.32 | 88.97 | 95
525 | PASCHIM MEDINIPUR | SM/13108 | RUPARGHAGRA AND ADJOINING MOUJAS PWSS | TSM/014661 | 40031944 | New | MVS | GO2223008539PH | 10/10/2022 | 272.06 | 35.88 | 307.94 | Midnapore Division | Jhargram Mechanical Division | 46.62 | 15.72 | 0 | 0 | 62.35 | 0 | 15.72 | 0 | 0 | 15.72 | 5.11 | 1
526 | PASCHIM MEDINIPUR | SM/11460 | Sabra Piped Water Supply Scheme. | TSM/006521 | 40017888 | New | SVS | GO2223004996PH | 12/07/2022 | 953.45 | 58.5 | 1011.95 | Midnapore Division | Midnapore Mechanical Division | 542.96 | 50.39 | 107.15 | 0 | 700.5 | 434.17 | 49.31 | 107.15 | 0 | 590.62 | 58.37 | 71
527 | PASCHIM MEDINIPUR | SM/15119 | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015586 | 40036184 | New | MVS | GO2223013239PH | 04/02/2023 | 713.74 | 77.24 | 790.98 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
528 | PASCHIM MEDINIPUR | SM/17996 | SAIYADPUR AND ADJOINING MOUJAS PWSS | TSM/015810 | 40035558 | New | MVS | GO2223016935PH | 17/03/2023 | 373.06 | 36.66 | 409.72 | Midnapore Division | Jhargram Mechanical Division | 52.48 | 15.68 | 0 | 0 | 68.17 | 0 | 15.68 | 0 | 0 | 15.68 | 3.83 | 1
529 | PASCHIM MEDINIPUR | SM/13171 | SALIKOTHA AND ADJOINING MOUJAS PWSS | TSM/014259 | 40036074 | New | MVS | GO2223008649PH | 12/10/2022 | 936.24 | 40.04 | 976.28 | Midnapore Division | Midnapore Mechanical Division | 283.73 | 27.05 | 0 | 0 | 310.78 | 1.3 | 0 | 0 | 0 | 1.3 | 0.13 | 29
530 | PASCHIM MEDINIPUR | SM/17568 | SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | TSM/018445 | 40053721 | New | MVS | GO2223017035PH | 18/03/2023 | 496.34 | 76.27 | 572.61 | Midnapore Division | Midnapore Mechanical Division | 7.8 | 0 | 7.1 | 0 | 14.9 | 7.8 | 0 | 7.1 | 0 | 14.9 | 2.6 | 4
531 | PASCHIM MEDINIPUR | SM/17569 | SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION | TSM/018464 | 40053723 | New | MVS | GO2223017072PH | 18/03/2023 | 649.48 | 76.45 | 725.94 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 8.42 | 0 | 8.42 | 0 | 0 | 8.42 | 0 | 8.42 | 1.16 | 1
532 | PASCHIM MEDINIPUR | SM/13219 | SANTRAPUR AND ADJOINING MOUJAS PWSS | TSM/014737 | 40035104 | New | MVS | GO2223008640PH | 12/10/2022 | 504.44 | 37.98 | 542.41 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 0 | 0 | 4.78 | 4.78 | 0 | 0 | 0 | 4.78 | 0.88 | 1
533 | PASCHIM MEDINIPUR | SM/13172 | SAORAPIR AND ADJOINING MOUJAS PWSS | TSM/014253 | 40036163 | New | MVS | GO2223008654PH | 12/10/2022 | 309.68 | 36.31 | 345.99 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 1.15 | 0 | 1.15 | 0 | 0 | 1.15 | 0 | 1.15 | 0.33 | 1
534 | PASCHIM MEDINIPUR | SM/13809 | SARANG AND ADJOINING MOUJAS PWSS | TSM/015093 | 40033142 | New | MVS | GO2223009968PH | 22/11/2022 | 672.14 | 39.23 | 711.37 | Midnapore Division | Midnapore Mechanical Division | 278.16 | 10.48 | 10.56 | 0 | 299.2 | 83.06 | 0 | 10.56 | 0 | 93.62 | 13.16 | 29
535 | PASCHIM MEDINIPUR | SM/18001 | SASHA BEDIA AND ADJOINING MOUJAS PWSS | TSM/015797 | 40036348 | New | MVS | GO2223016938PH | 17/03/2023 | 917.77 | 77.79 | 995.57 | Midnapore Division | Jhargram Mechanical Division | 167.15 | 17.92 | 0 | 0 | 185.07 | 122.53 | 17.92 | 0 | 0 | 140.45 | 14.11 | 19
536 | PASCHIM MEDINIPUR | SM/18009 | SATPATI AND ADJOINING MOUJAS PWSS | TSM/015805 | 40035356 | New | MVS | GO2223016945PH | 17/03/2023 | 536.9 | 39.18 | 576.07 | Midnapore Division | Jhargram Mechanical Division | 26.12 | 0 | 10.72 | 0 | 36.84 | 0 | 0 | 10.72 | 0 | 10.72 | 1.86 | 1
537 | PASCHIM MEDINIPUR | SM/13038 | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013118 | 40026057 | New | MVS | GO2223008354PH | 28/09/2022 | 512.89 | 38.28 | 551.17 | Midnapore Division | Midnapore Mechanical Division | 130.7 | 16.47 | 12.47 | 0 | 159.63 | 0 | 0 | 12.47 | 0 | 12.47 | 2.26 | 4
538 | PASCHIM MEDINIPUR | SM/17572 | Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017563 | 40053736 | New | MVS | GO2223017059PH | 18/03/2023 | 665.28 | 75.01 | 740.3 | Midnapore Division | Midnapore Mechanical Division | 1.49 | 0 | 10.52 | 0 | 12 | 1.49 | 0 | 10.52 | 0 | 12 | 1.62 | 1
539 | PASCHIM MEDINIPUR | SM/17573 | Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | TSM/017564 | 40053737 | New | MVS | GO2223017034PH | 18/03/2023 | 508.78 | 75.01 | 583.8 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 7.86 | 0 | 7.86 | 0 | 0 | 7.86 | 0 | 7.86 | 1.35 | 1
540 | PASCHIM MEDINIPUR | SM/13220 | SHAKHA BAI AND ADJOINING MOUJAS PWSS | TSM/014590 | 40033129 | New | MVS | GO2223008637PH | 12/10/2022 | 355.04 | 36.02 | 391.07 | Midnapore Division | Jhargram Mechanical Division | 44.76 | 4.18 | 0 | 0 | 48.94 | 0 | 4.18 | 0 | 0 | 4.18 | 1.07 | 1
541 | PASCHIM MEDINIPUR | SM/18013 | SHAL DAHARA AND ADJOINING MOUJAS PWWSS | TSM/016553 | 40065561 | New | MVS | GO2223016957PH | 17/03/2023 | 323.91 | 29.87 | 353.79 | Midnapore Division | Jhargram Mechanical Division | 31.44 | 10.91 | 0 | 0 | 42.35 | 0 | 10.91 | 0 | 0 | 10.91 | 3.08 | 1
542 | PASCHIM MEDINIPUR | SM/18017 | SHASHINDA SVS PWSS | TSM/016249 | 40034157 | New | SVS | GO2223016959PH | 17/03/2023 | 402.55 | 55.45 | 458 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
543 | PASCHIM MEDINIPUR | SM/18585 | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/015713 | 40034737 | New | MVS | 2146/PHE-28011/134/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 999.84 | 78.9 | 1078.74 | Midnapore Division | Midnapore Mechanical Division | 121.08 | 7.75 | 0 | 0 | 128.83 | 6.59 | 0 | 0 | 0 | 6.59 | 0.61 | 8
544 | PASCHIM MEDINIPUR | SM/15120 | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | TSM/017442 | 40034703 | New | SVS | GO2223013229PH | 04/02/2023 | 194.95 | 38.15 | 233.1 | Midnapore Division | Midnapore Mechanical Division | 10.08 | 0 | 0 | 0 | 10.08 | 2.75 | 0 | 0 | 0 | 2.75 | 1.18 | 4
545 | PASCHIM MEDINIPUR | SM/13109 | SHUJA AND ADJOINING MOUJAS PWSS | TSM/014451 | 40031959 | New | MVS | GO2223008541PH | 10/10/2022 | 407.08 | 36.34 | 443.41 | Midnapore Division | Midnapore Mechanical Division | 14.63 | 0 | 6.27 | 0 | 20.9 | 4.78 | 0 | 6.27 | 0 | 11.05 | 2.49 | 1
546 | PASCHIM MEDINIPUR | SM/18020 | SHUKHNATOR AND ADJOINING MOUJAS PWSS | TSM/015814 | 40033206 | New | MVS | GO2223016940PH | 17/03/2023 | 760.95 | 59.63 | 820.59 | Midnapore Division | Jhargram Mechanical Division | 50.3 | 14.15 | 0 | 0 | 64.46 | 0 | 14.15 | 0 | 0 | 14.15 | 1.72 | 1
547 | PASCHIM MEDINIPUR | SM/13173 | SHYAMNAGAR AND ADJOINING MOUJAS PWSS | TSM/014133 | 40034038 | New | MVS | GO2223008652PH | 12/10/2022 | 766.22 | 38.85 | 805.07 | Midnapore Division | Jhargram Mechanical Division | 47.15 | 7.09 | 48.65 | 0 | 102.89 | 4.78 | 7.09 | 48.65 | 0 | 60.51 | 7.52 | 2
548 | PASCHIM MEDINIPUR | SM/17624 | SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013197 | 40033799 | New | MVS | GO2223017406PH | 21/03/2023 | 304.79 | 37.8 | 342.58 | Midnapore Division | Midnapore Mechanical Division | 90.45 | 0 | 6.25 | 0 | 96.69 | 0 | 0 | 6.25 | 0 | 6.25 | 1.82 | 1
549 | PASCHIM MEDINIPUR | SM/13110 | SINGLA AND IT'S ADJOINING MOUJAS | TSM/014730 | 40031880 | New | MVS | GO2223008530PH | 10/10/2022 | 279.43 | 38.41 | 317.84 | Midnapore Division | Jhargram Mechanical Division | 57.92 | 6.62 | 0 | 0 | 64.54 | 0 | 6.62 | 0 | 0 | 6.62 | 2.08 | 1
550 | PASCHIM MEDINIPUR | SM/18527 | SINNIBAR PIPED WATER SUPPLY SCHEME | TSM/013550 | 40034484 | New | MVS | 2047/PHE-28011/62/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1102.53 | 41.24 | 1143.77 | Midnapore Division | Midnapore Mechanical Division | 0 | 22.77 | 0 | 0 | 22.77 | 0 | 0 | 0 | 0 | 0 | 0 | 2
551 | PASCHIM MEDINIPUR | SM/13057 | SOHAGPUR AND IT'S ADJOINING MOUJAS PWSS | TSM/013200 | 40031808 | New | MVS | GO2223008503PH | 29/09/2022 | 429.67 | 38.14 | 467.81 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 9.64 | 0 | 14.42 | 4.78 | 0 | 9.64 | 0 | 14.42 | 3.08 | 2
552 | PASCHIM MEDINIPUR | SM/13139 | SOLEMANPUR AND IT'S ADJOINING MOJAS PWSS | TSM/013167 | 40033875 | New | MVS | GO2223008617PH | 12/10/2022 | 480.66 | 38.28 | 518.94 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 11.46 | 0 | 16.24 | 4.78 | 0 | 11.46 | 0 | 16.24 | 3.13 | 3
553 | PASCHIM MEDINIPUR | SM/13174 | SOLPOTA AND ADJOINING MOUJAS PWSS | TSM/014241 | 40036186 | New | MVS | GO2223008655PH | 12/10/2022 | 424.17 | 38.39 | 462.56 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
554 | PASCHIM MEDINIPUR | SM/13221 | SONIAKON AND ADJOINING MOUJAS PWSS | TSM/014868 | 40035404 | New | MVS | GO2223008635PH | 12/10/2022 | 413.64 | 39.33 | 452.97 | Midnapore Division | Jhargram Mechanical Division | 80.98 | 0 | 9.28 | 0 | 90.27 | 4.78 | 0 | 9.28 | 0 | 14.06 | 3.1 | 1
555 | PASCHIM MEDINIPUR | SM/19043 | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015926 | 40036221 | New | MVS | 3546/PHE-28011/198/2023-SCHM CELL-Dept. of PHE | 24/11/2023 | 961.39 | 77.24 | 1038.63 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 175.99 | 0 | 175.99 | 0 | 0 | 175.99 | 0 | 175.99 | 16.94 | 0
556 | PASCHIM MEDINIPUR | SM/19188 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | TSM/015039 | 40032798 | New | MVS | 650/PHE-28011/138/2021-SCHM CELL-Dept. of PHE | 07/03/2024 | 66852.52 | 7303.12 | 74155.64 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
557 | PASCHIM MEDINIPUR | SM/19188 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | TSM/015039 | 40032798 | New | MVS | 650/PHE-28011/138/2021-SCHM CELL-Dept. of PHE | 07/03/2024 | 66852.52 | 7303.12 | 74155.64 | Tamluk Division | Midnapore Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
558 | PASCHIM MEDINIPUR | SM/17614 | TALBANDI AND ITS ADJOINING MOUJAS PWSS | TSM/011840 | 40033188 | New | MVS | GO2223017407PH | 21/03/2023 | 262.12 | 37.76 | 299.88 | Midnapore Division | Midnapore Mechanical Division | 15.63 | 0 | 4.39 | 0 | 20.01 | 0 | 0 | 4.39 | 0 | 4.39 | 1.46 | 1
559 | PASCHIM MEDINIPUR | SM/09992 | Tanuya Piped Water Supply Scheme. | TSM/005513 | 40008567 | New | MVS | GO2122006950PH | 16/12/2021 | 883.09 | 0 | 883.09 | Midnapore Division | Midnapore Mechanical Division | 356.74 | 21.61 | 70.33 | 0 | 448.68 | 356.74 | 0 | 70.33 | 0 | 427.07 | 48.36 | 80
560 | PASCHIM MEDINIPUR | SM/13166 | TARUA AND ADJOINING MOUJAS PWSS | TSM/014582 | 40034311 | New | MVS | GO2223008636PH | 12/10/2022 | 808.83 | 39.41 | 848.24 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 31.36 | 0 | 31.36 | 0 | 0 | 31.36 | 0 | 31.36 | 3.7 | 1
561 | PASCHIM MEDINIPUR | SM/18540 | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015924 | 40053812 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1455.41 | 116.34 | 1571.76 | Midnapore Division | Midnapore Mechanical Division | 27.36 | 15.19 | 21.74 | 0 | 64.29 | 2.39 | 0 | 21.74 | 0 | 24.13 | 1.54 | 2
562 | PASCHIM MEDINIPUR | SM/15594 | TEGHARI AND ITS ADJOINING MOUZAS PWSS | TSM/017363 | 40044756 | New | MVS | GO2223013899PH | 15/02/2023 | 866.33 | 41.28 | 907.61 | Midnapore Division | Midnapore Mechanical Division | 0 | 10.99 | 0 | 0 | 10.99 | 0 | 0 | 0 | 0 | 0 | 0 | 2
563 | PASCHIM MEDINIPUR | SM/13175 | TELIJANT AND IT'S ADJOINING MOUJAS PWSS | TSM/014123 | 40033764 | New | MVS | GO2223008645PH | 12/10/2022 | 714.55 | 36.72 | 751.27 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
564 | PASCHIM MEDINIPUR | SM/15906 | THAUR AND ITS ADJOINING MOUZAS PWSS | TSM/017350 | 40044850 | New | MVS | GO2223013895PH | 15/02/2023 | 801.39 | 42.81 | 844.2 | Midnapore Division | Midnapore Mechanical Division | 0 | 21.58 | 14.99 | 0 | 36.57 | 0 | 0 | 14.99 | 0 | 14.99 | 1.78 | 3
565 | PASCHIM MEDINIPUR | SM/18236 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017054 | 40036238 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 941.53 | 84.47 | 1026.01 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
566 | PASCHIM MEDINIPUR | SM/18027 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017058 | 40036324 | New | MVS | GO2223016943PH | 17/03/2023 | 653.31 | 84.47 | 737.78 | Midnapore Division | Jhargram Mechanical Division | 150.62 | 42.78 | 34.55 | 0 | 227.95 | 90.28 | 42.78 | 34.55 | 0 | 167.61 | 22.72 | 5
567 | PASCHIM MEDINIPUR | SM/18028 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017061 | 40036216 | New | MVS | GO2223016956PH | 17/03/2023 | 766 | 84.47 | 850.47 | Midnapore Division | Jhargram Mechanical Division | 112.6 | 9.53 | 10.16 | 0 | 132.29 | 0 | 9.53 | 10.16 | 0 | 19.69 | 2.32 | 3
568 | PASCHIM MEDINIPUR | SM/17574 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DWARKHOLA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | TSM/017316 | 40053756 | New | SVS | GO2223017020PH | 18/03/2023 | 60.38 | 6.47 | 66.85 | Midnapore Division | Jhargram Mechanical Division | 25.89 | 4.69 | 0 | 0 | 30.59 | 0 | 4.69 | 0 | 0 | 4.69 | 7.02 | 9
569 | PASCHIM MEDINIPUR | SM/13111 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013441 | 40036225 | New | MVS | GO2223008542PH | 10/10/2022 | 412.79 | 42.24 | 455.02 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
570 | PASCHIM MEDINIPUR | SM/18249 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | TSM/016011 | 40032738 | New | MVS | 1560/PHE-28011/235/2023-ESTT CELL-Dept. of PHE | 16/06/2023 | 1073.7 | 84.47 | 1158.17 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
571 | PASCHIM MEDINIPUR | SM/15121 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | TSM/017060 | 40036309 | New | MVS | GO2223013232PH | 04/02/2023 | 700.22 | 84.47 | 784.7 | Midnapore Division | Jhargram Mechanical Division | 182.63 | 35.57 | 44.91 | 0 | 263.11 | 182.63 | 35.57 | 44.91 | 0 | 263.11 | 33.53 | 7
572 | PASCHIM MEDINIPUR | SM/18234 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017049 | 40036239 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1317.39 | 126.71 | 1444.1 | Midnapore Division | Jhargram Mechanical Division | 155.27 | 3.67 | 0 | 0 | 158.94 | 0 | 3.67 | 0 | 0 | 3.67 | 0.25 | 1
573 | PASCHIM MEDINIPUR | SM/19046 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017585 | 40043995 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 955.56 | 84.47 | 1040.03 | Midnapore Division | Jhargram Mechanical Division | 0 | 7.03 | 0 | 0 | 7.03 | 0 | 7.03 | 0 | 0 | 7.03 | 0.68 | 0
574 | PASCHIM MEDINIPUR | SM/18541 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KALLA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017582 | 40053730 | New | MVS | 2057/PHE-28011/205/2023-SCHM CELL-Dept. of PHE | 26/07/2023 | 1212.83 | 126.71 | 1339.54 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 17.96 | 0 | 17.96 | 0 | 0 | 17.96 | 0 | 17.96 | 1.34 | 1
575 | PASCHIM MEDINIPUR | SM/15595 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017583 | 40044064 | New | MVS | GO2223013889PH | 15/02/2023 | 893.82 | 84.47 | 978.29 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 16.63 | 0 | 16.63 | 0 | 0 | 16.63 | 0 | 16.63 | 1.7 | 1
576 | PASCHIM MEDINIPUR | SM/13167 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013440 | 40032983 | New | MVS | GO2223008638PH | 12/10/2022 | 899.66 | 84.47 | 984.13 | Midnapore Division | Jhargram Mechanical Division | 306.52 | 0 | 0 | 0 | 306.52 | 0 | 0 | 0 | 0 | 0 | 0 | 3
577 | PASCHIM MEDINIPUR | SM/18233 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDERMEDINIPUR DIVISION, PHE DTE. | TSM/016008 | 40036224 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1042.56 | 84.47 | 1127.03 | Midnapore Division | Jhargram Mechanical Division | 9.91 | 6.76 | 0 | 0 | 16.67 | 0 | 6.76 | 0 | 0 | 6.76 | 0.6 | 1
578 | PASCHIM MEDINIPUR | SM/19047 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017584 | 40044032 | New | MVS | 3549/PHE-28011/138/2023-ESTT CELL-Dept. of PHE | 24/11/2023 | 915.55 | 84.47 | 1000.02 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
579 | PASCHIM MEDINIPUR | SM/18032 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | TSM/016027 | 40036214 | New | MVS | GO2223016933PH | 17/03/2023 | 782.81 | 84.47 | 867.28 | Midnapore Division | Jhargram Mechanical Division | 224.29 | 4.07 | 12.26 | 0 | 240.62 | 0 | 4.07 | 12.26 | 0 | 16.33 | 1.88 | 1
580 | PASCHIM MEDINIPUR | SM/18237 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/017039 | 40034524 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1285.92 | 84.47 | 1370.39 | Midnapore Division | Jhargram Mechanical Division | 0 | 6.8 | 15.91 | 0 | 22.71 | 0 | 6.8 | 15.91 | 0 | 22.71 | 1.66 | 1
581 | PASCHIM MEDINIPUR | SM/15122 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATEFHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | TSM/017053 | 40034548 | New | MVS | GO2223013234PH | 04/02/2023 | 668.96 | 84.47 | 753.44 | Midnapore Division | Jhargram Mechanical Division | 0 | 9.56 | 11.14 | 0 | 20.71 | 0 | 9.56 | 11.14 | 0 | 20.71 | 2.75 | 1
582 | PASCHIM MEDINIPUR | SM/16252 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | TSM/013442 | 40036206 | New | MVS | GO2223014868PH | 24/02/2023 | 914.69 | 84.47 | 999.16 | Midnapore Division | Jhargram Mechanical Division | 226.6 | 12.52 | 17.04 | 0 | 256.17 | 93.77 | 12.52 | 17.04 | 0 | 123.33 | 12.34 | 4
583 | PASCHIM MEDINIPUR | SM/18235 | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE. | TSM/016022 | 40036292 | New | MVS | 1483/PHE-28011/208/2023-ESTT CELL-Dept. of PHE | 12/06/2023 | 1000.08 | 84.47 | 1084.55 | Midnapore Division | Jhargram Mechanical Division | 308.48 | 20.54 | 0 | 0 | 329.02 | 240.79 | 17.37 | 0 | 0 | 258.16 | 23.8 | 2
584 | PASCHIM MEDINIPUR | SM/17575 | Tiorberya Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | TSM/015589 | 40053749 | New | MVS | GO2223017023PH | 18/03/2023 | 352.38 | 72.16 | 424.54 | Midnapore Division | Midnapore Mechanical Division | 14.43 | 5.68 | 0 | 0 | 20.11 | 0 | 0 | 0 | 0 | 0 | 0 | 3
585 | PASCHIM MEDINIPUR | SM/18494 | TORIA PIPED WATER SUPPLY SCHEME | TSM/013444 | 40034393 | New | MVS | 2033/PHE-28011/25/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1060.88 | 39.84 | 1100.72 | Midnapore Division | Midnapore Mechanical Division | 101.28 | 7.19 | 0 | 0 | 108.47 | 0 | 0 | 0 | 0 | 0 | 0 | 1
586 | PASCHIM MEDINIPUR | SM/13112 | TRIKALPUR AND ADJOINING MOUJAS PWSS | TSM/014449 | 40031965 | New | MVS | GO2223008543PH | 10/10/2022 | 474.01 | 38.53 | 512.54 | Midnapore Division | Midnapore Mechanical Division | 107.22 | 6.29 | 0 | 0 | 113.51 | 0 | 0 | 0 | 0 | 0 | 0 | 2
587 | PASCHIM MEDINIPUR | SM/13049 | TRILOCHANPUR PWSS | TSM/011604 | 40031822 | New | MVS | GO2223008505PH | 29/09/2022 | 569.36 | 38.28 | 607.64 | Midnapore Division | Midnapore Mechanical Division | 4.78 | 0 | 11.96 | 0 | 16.74 | 4.78 | 0 | 11.96 | 0 | 16.74 | 2.75 | 2
588 | PASCHIM MEDINIPUR | SM/13050 | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS | TSM/013129 | 40031878 | New | MVS | GO2223008507PH | 29/09/2022 | 426.58 | 38.28 | 464.86 | Midnapore Division | Midnapore Mechanical Division | 0 | 0 | 10.85 | 0 | 10.85 | 0 | 0 | 10.85 | 0 | 10.85 | 2.34 | 1
589 | PASCHIM MEDINIPUR | SM/13131 | TUTRANGA AND ADJOINING MOUJAS PWSS | TSM/014384 | 40031916 | New | MVS | GO2223008535PH | 10/10/2022 | 439.25 | 38.53 | 477.78 | Midnapore Division | Midnapore Mechanical Division | 33.94 | 6.38 | 9.16 | 0 | 49.48 | 4.78 | 0 | 9.16 | 0 | 13.94 | 2.92 | 2
590 | PASCHIM MEDINIPUR | SM/15123 | UMRAPATA AND ADJOINING MOUJAS PWSS | TSM/016216 | 40035422 | New | MVS | GO2223013221PH | 04/02/2023 | 115.73 | 26.67 | 142.4 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
591 | PASCHIM MEDINIPUR | SM/13130 | URIYASHAI AND ADJOINING MOUJAS PWSS | TSM/014646 | 40031913 | New | MVS | GO2223008534PH | 10/10/2022 | 475.49 | 39.33 | 514.82 | Midnapore Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
592 | PASCHIM MEDINIPUR | SM/13129 | UTATR KARKARA AND ADJOINING MOUJAS PWSS | TSM/014277 | 40031936 | New | MVS | GO2223008537PH | 10/10/2022 | 495.4 | 38.53 | 533.93 | Midnapore Division | Midnapore Mechanical Division | 1.31 | 7.19 | 9.18 | 0 | 17.67 | 0 | 0 | 0 | 0 | 0 | 0 | 2
593 | PASCHIM MEDINIPUR | SM/13810 | UTTAR PIASHALA PIPED WATER SUPPLY SCHEME | TSM/014972 | 40034510 | New | MVS | GO2223009965PH | 22/11/2022 | 781.28 | 38.26 | 819.54 | Midnapore Division | Midnapore Mechanical Division | 85.54 | 19.68 | 0 | 0 | 105.21 | 7.77 | 0 | 0 | 0 | 7.77 | 0.95 | 1
Total | [9 empty] | 413870.36 | 37519.99 | 451390.34 |  |  | 43600.11 | 3874.1 | 4725.47 | 375.86 | 52575.54 | 22894.97 | 1743.28 | 4299.05 | 353.03 | 29290.32 | 6.49