## JJM Schemes Financial Status (A
JJM Schemes Financial Status (ALIPURDUAR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | ALIPURDUAR | SM/16506 | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | TSM/017682 | 0 | New | SVS | GO2223015231PH | 03/03/2023 | 923.43 | 66.97 | 990.41 | Alipurduar Division | Northern Mechanical Division II | 24.08 | 0 | 10.77 | 0 | 34.85 | 24.08 | 0 | 10.77 | 0 | 34.85 | 3.52 | 7
2 | ALIPURDUAR | SM/14092 | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017486 | 40037696 | New | MVS | GO2223010870PH | 12/12/2022 | 831.32 | 64.1 | 895.42 | Alipurduar Division | Northern Mechanical Division II | 260.87 | 10.51 | 196.25 | 0 | 467.63 | 260.87 | 4.7 | 196.25 | 0 | 461.82 | 51.58 | 75
3 | ALIPURDUAR | SM/12561 | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | TSM/009641 | 40006346 | Augmentation | MVS | GO2223007697PH | 14/09/2022 | 1743.38 | 109.28 | 1852.66 | Alipurduar Division | Northern Mechanical Division II | 1009.27 | 65.65 | 0 | 0 | 1074.92 | 1009.27 | 58.6 | 0 | 0 | 1067.87 | 57.64 | 86
4 | ALIPURDUAR | SM/10667 | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | TSM/010085 | 40019860 | Augmentation | MVS | GO2223000778PH | 29/04/2022 | 186.88 | 0 | 186.88 | Alipurduar Division | Northern Mechanical Division II | 51.71 | 0 | 0 | 0 | 51.71 | 51.71 | 0 | 0 | 0 | 51.71 | 27.67 | 95
5 | ALIPURDUAR | SM/10674 | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | TSM/010070 | 40012757 | Augmentation | MVS | GO2223000779PH | 29/04/2022 | 236.97 | 0 | 236.97 | Alipurduar Division | Northern Mechanical Division II | 8.25 | 0 | 61.6 | 0 | 69.85 | 8.25 | 0 | 61.6 | 0 | 69.85 | 29.48 | 80
6 | ALIPURDUAR | SM/14096 | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | TSM/009625 | 40005064 | Augmentation | MVS | GO2223010910PH | 15/12/2022 | 1885.69 | 145.71 | 2031.4 | Alipurduar Division | Northern Mechanical Division II | 799.99 | 82.8 | 0 | 0 | 882.79 | 799.99 | 0 | 0 | 0 | 799.99 | 39.38 | 38
7 | ALIPURDUAR | SM/09883 | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | TSM/009070 | 40005644 | Augmentation | SVS | GO2122006588PH | 08/12/2021 | 433.02 | 18.21 | 451.23 | Alipurduar Division | Northern Mechanical Division II | 277.83 | 11.61 | 0 | 0 | 289.43 | 273.52 | 11.61 | 0 | 0 | 285.13 | 63.19 | 98
8 | ALIPURDUAR | SM/09885 | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | TSM/009072 | 40005643 | Augmentation | MVS | GO2122006589PH | 08/12/2021 | 431.7 | 18.21 | 449.91 | Alipurduar Division | Northern Mechanical Division II | 431.7 | 11.36 | 0 | 0 | 443.06 | 431.7 | 1.43 | 0 | 0 | 433.13 | 96.27 | 95
9 | ALIPURDUAR | SM/10671 | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | TSM/010080 | 40019041 | Augmentation | SVS | GO2223000778PH | 29/04/2022 | 152.39 | 0 | 152.39 | Alipurduar Division | Northern Mechanical Division II | 22.83 | 0 | 0 | 0 | 22.83 | 22.83 | 0 | 0 | 0 | 22.83 | 14.98 | 96
10 | ALIPURDUAR | SM/14233 | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | TSM/010090 | 40012919 | Augmentation | SVS | GO2223011826PH | 11/01/2023 | 2064.2 | 224.73 | 2288.93 | Alipurduar Division | Northern Mechanical Division II | 348.21 | 56.71 | 163.68 | 0 | 568.6 | 336.17 | 10.33 | 163.68 | 0 | 510.18 | 22.29 | 46
11 | ALIPURDUAR | SM/10677 | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | TSM/010067 | 40012861 | Augmentation | MVS | GO2223000781PH | 29/04/2022 | 192.09 | 0 | 192.09 | Alipurduar Division | Northern Mechanical Division II | 8.65 | 0 | 0 | 0 | 8.65 | 8.65 | 0 | 0 | 0 | 8.65 | 4.5 | 98
12 | ALIPURDUAR | SM/11970 | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | TSM/010087 | 40012912 | Augmentation | MVS | GO2223006754PH | 29/08/2022 | 1239 | 36.43 | 1275.43 | Alipurduar Division | Northern Mechanical Division II | 352.29 | 22.68 | 0 | 0 | 374.96 | 352.29 | 8.4 | 0 | 0 | 360.69 | 28.28 | 58
13 | ALIPURDUAR | SM/18254 | AUGMENTATION OF DALIMPUR PWSS | TSM/009613 | 40006517 | Augmentation | MVS | 1583/PHE-28011/20/2022-ESTT CELL-Dept. of PHE | 21/06/2023 | 910.96 | 109.28 | 1020.25 | Alipurduar Division | Northern Mechanical Division II | 134.61 | 0 | 0 | 0 | 134.61 | 134.61 | 0 | 0 | 0 | 134.61 | 13.19 | 18
14 | ALIPURDUAR | SM/11960 | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/010082 | 40012814 | Augmentation | MVS | GO2223006716PH | 25/08/2022 | 448.33 | 64.58 | 512.91 | Alipurduar Division | Northern Mechanical Division II | 75.52 | 25.84 | 0 | 0 | 101.36 | 75.52 | 0 | 0 | 0 | 75.52 | 14.72 | 36
15 | ALIPURDUAR | SM/15210 | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | TSM/018074 | 40065422 | Augmentation | SVS | GO2223013433PH | 07/02/2023 | 93.1 | 18.21 | 111.32 | Alipurduar Division | Northern Mechanical Division II | 11.28 | 17.56 | 0 | 0 | 28.84 | 8.44 | 0 | 0 | 0 | 8.44 | 7.58 | 43
16 | ALIPURDUAR | SM/16824 | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | TSM/018091 | 40062650 | Augmentation | SVS | GO2223015819PH | 13/03/2023 | 200.8 | 72.86 | 273.66 | Alipurduar Division | Northern Mechanical Division II | 0 | 43.19 | 0 | 0 | 43.19 | 0 | 0 | 0 | 0 | 0 | 0 | 22
17 | ALIPURDUAR | SM/15209 | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | TSM/018090 | 40065426 | Augmentation | SVS | GO2223013433PH | 07/02/2023 | 93.97 | 18.21 | 112.19 | Alipurduar Division | Northern Mechanical Division II | 20.28 | 15.8 | 0 | 0 | 36.07 | 20.28 | 0 | 0 | 0 | 20.28 | 18.08 | 52
18 | ALIPURDUAR | SM/12361 | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | TSM/010086 | 40012816 | Augmentation | MVS | GO2223007581PH | 13/09/2022 | 1233.36 | 36.43 | 1269.79 | Alipurduar Division | Northern Mechanical Division II | 86.6 | 0 | 52.39 | 0 | 138.99 | 86.6 | 0 | 52.39 | 0 | 138.99 | 10.95 | 34
19 | ALIPURDUAR | SM/10169 | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | TSM/009622 | 40004531 | Augmentation | SVS | GO2122009752PH | 16/02/2022 | 360.63 | 18.21 | 378.84 | Alipurduar Division | Northern Mechanical Division II | 93.74 | 11.16 | 0 | 0 | 104.9 | 87.72 | 1.46 | 0 | 0 | 89.18 | 23.54 | 90
20 | ALIPURDUAR | SM/10668 | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | TSM/010084 | 40019779 | Augmentation | SVS | GO2223000778PH | 29/04/2022 | 69.44 | 0 | 69.44 | Alipurduar Division | Northern Mechanical Division II | 0.36 | 0 | 0 | 0 | 0.36 | 0.36 | 0 | 0 | 0 | 0.36 | 0.52 | 96
21 | ALIPURDUAR | SM/10156 | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | TSM/009623 | 40004526 | Augmentation | MVS | GO2122009654PH | 11/02/2022 | 669.74 | 36.43 | 706.17 | Alipurduar Division | Northern Mechanical Division II | 426.58 | 20.72 | 10.14 | 0 | 457.44 | 417.13 | 1.34 | 10.14 | 0 | 428.62 | 60.7 | 84
22 | ALIPURDUAR | SM/11402 | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | TSM/010849 | 40016307 | Augmentation | SVS | GO2223004639PH | 04/07/2022 | 68.09 | 18.21 | 86.31 | Alipurduar Division | Northern Mechanical Division II | 51.67 | 3.39 | 0 | 0 | 55.06 | 51.67 | 3.39 | 0 | 0 | 55.06 | 63.8 | 74
23 | ALIPURDUAR | SM/10678 | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | TSM/010066 | 40012879 | Augmentation | MVS | GO2223000781PH | 29/04/2022 | 256.24 | 18.21 | 274.45 | Alipurduar Division | Northern Mechanical Division II | 67.65 | 5.36 | 0 | 0 | 73.02 | 67.65 | 0 | 0 | 0 | 67.65 | 24.65 | 47
24 | ALIPURDUAR | SM/11958 | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | TSM/010089 | 40012860 | Augmentation | MVS | GO2223006713PH | 25/08/2022 | 525.74 | 36.43 | 562.16 | Alipurduar Division | Northern Mechanical Division II | 107.33 | 16.32 | 30.75 | 0 | 154.41 | 107.33 | 0 | 30.75 | 0 | 138.08 | 24.56 | 57
25 | ALIPURDUAR | SM/11985 | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | TSM/009618 | 40020242 | Augmentation | MVS | GO2223006916PH | 01/09/2022 | 2010.67 | 145.71 | 2156.38 | Alipurduar Division | Northern Mechanical Division II | 638.4 | 18.39 | 141.31 | 0 | 798.1 | 638.4 | 0 | 141.31 | 0 | 779.71 | 36.16 | 59
26 | ALIPURDUAR | SM/11767 | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | TSM/011251 | 40036753 | Augmentation | MVS | GO2223005966PH | 03/08/2022 | 167.73 | 36.43 | 204.15 | Alipurduar Division | Northern Mechanical Division II | 41.84 | 6.6 | 0 | 0 | 48.44 | 41.84 | 6.6 | 0 | 0 | 48.44 | 23.73 | 39
27 | ALIPURDUAR | SM/10673 | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | TSM/010071 | 40012695 | Augmentation | MVS | GO2223000779PH | 29/04/2022 | 252.98 | 0 | 252.98 | Alipurduar Division | Northern Mechanical Division II | 16.34 | 0 | 0 | 0 | 16.34 | 16.34 | 0 | 0 | 0 | 16.34 | 6.46 | 92
28 | ALIPURDUAR | SM/10675 | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME | TSM/010069 | 40012880 | Augmentation | MVS | GO2223000779PH | 29/04/2022 | 178.64 | 0 | 178.64 | Alipurduar Division | Northern Mechanical Division II | 51.29 | 0 | 0 | 0 | 51.29 | 51.29 | 0 | 0 | 0 | 51.29 | 28.71 | 90
29 | ALIPURDUAR | SM/10154 | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | TSM/009621 | 40004517 | Augmentation | MVS | GO2122009655PH | 11/02/2022 | 596.42 | 36.43 | 632.84 | Alipurduar Division | Northern Mechanical Division II | 530.51 | 21.7 | 47.32 | 0 | 599.53 | 509.95 | 21.7 | 47.32 | 0 | 578.97 | 91.49 | 97
30 | ALIPURDUAR | SM/11766 | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | TSM/011781 | 40036754 | Augmentation | SVS | GO2223005966PH | 03/08/2022 | 69.93 | 18.21 | 88.14 | Alipurduar Division | Northern Mechanical Division II | 30.66 | 0 | 0 | 0 | 30.66 | 30.66 | 0 | 0 | 0 | 30.66 | 34.78 | 64
31 | ALIPURDUAR | SM/10672 | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | TSM/010073 | 40019296 | Augmentation | MVS | GO2223000778PH | 29/04/2022 | 162.74 | 0 | 162.74 | Alipurduar Division | Northern Mechanical Division II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
32 | ALIPURDUAR | SM/11401 | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | TSM/010852 | 40016308 | Augmentation | MVS | GO2223004639PH | 04/07/2022 | 122.68 | 18.21 | 140.89 | Alipurduar Division | Northern Mechanical Division II | 112.03 | 14.58 | 0 | 0 | 126.61 | 112.03 | 14.03 | 0 | 0 | 126.06 | 89.48 | 60
33 | ALIPURDUAR | SM/10669 | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | TSM/010083 | 40012692 | Augmentation | MVS | GO2223000778PH | 29/04/2022 | 161.24 | 0 | 161.24 | Alipurduar Division | Northern Mechanical Division II | 13.42 | 0 | 0 | 0 | 13.42 | 13.42 | 0 | 0 | 0 | 13.42 | 8.32 | 33
34 | ALIPURDUAR | SM/11459 | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | TSM/009983 | 40006502 | Augmentation | MVS | GO2223004983PH | 12/07/2022 | 1727.9 | 145.71 | 1873.61 | Alipurduar Division | Northern Mechanical Division II | 813.81 | 88.21 | 76.69 | 0 | 978.7 | 813.81 | 17.16 | 76.69 | 0 | 907.65 | 48.44 | 60
35 | ALIPURDUAR | SM/09884 | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | TSM/009073 | 40005637 | Augmentation | MVS | GO2122006588PH | 08/12/2021 | 466.72 | 18.21 | 484.93 | Alipurduar Division | Northern Mechanical Division II | 453.12 | 10.95 | 0 | 0 | 464.08 | 452.29 | 6.82 | 0 | 0 | 459.11 | 94.68 | 97
36 | ALIPURDUAR | SM/10316 | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | TSM/009616 | 40006294 | Augmentation | SVS | GO2122010476PH | 04/03/2022 | 244.63 | 36.43 | 281.05 | Alipurduar Division | Northern Mechanical Division II | 39.95 | 22.42 | 0 | 0 | 62.36 | 39.95 | 2.91 | 0 | 0 | 42.86 | 15.25 | 80
37 | ALIPURDUAR | SM/10670 | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | TSM/010081 | 40019855 | Augmentation | MVS | GO2223000778PH | 29/04/2022 | 108.13 | 0 | 108.13 | Alipurduar Division | Northern Mechanical Division II | 29.6 | 0 | 0 | 0 | 29.6 | 29.6 | 0 | 0 | 0 | 29.6 | 27.37 | 56
38 | ALIPURDUAR | SM/10676 | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | TSM/010068 | 40012858 | Augmentation | MVS | GO2223000779PH | 29/04/2022 | 252.39 | 0 | 252.39 | Alipurduar Division | Northern Mechanical Division II | 5.02 | 0 | 0 | 0 | 5.02 | 5.02 | 0 | 0 | 0 | 5.02 | 1.99 | 90
39 | ALIPURDUAR | SM/11765 | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | TSM/011786 | 40036031 | Augmentation | SVS | GO2223005966PH | 03/08/2022 | 135.86 | 18.21 | 154.07 | Alipurduar Division | Northern Mechanical Division II | 39.61 | 12.1 | 0 | 0 | 51.71 | 39.61 | 12.1 | 0 | 0 | 51.71 | 33.56 | 32
40 | ALIPURDUAR | SM/10171 | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | TSM/009624 | 40004522 | Augmentation | MVS | GO2122009747PH | 16/02/2022 | 713.99 | 36.43 | 750.42 | Alipurduar Division | Northern Mechanical Division II | 543.1 | 15.76 | 30.65 | 0 | 589.51 | 534.15 | 15.76 | 30.65 | 0 | 580.56 | 77.36 | 97
41 | ALIPURDUAR | SM/11959 | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | TSM/010088 | 0 | Augmentation | MVS | GO2223006714PH | 25/08/2022 | 612.2 | 36.43 | 648.63 | Alipurduar Division | Northern Mechanical Division II | 25.17 | 0 | 0 | 0 | 25.17 | 25.17 | 0 | 0 | 0 | 25.17 | 3.88 | 50
42 | ALIPURDUAR | SM/14221 | BALLALGURI PIPED WATER SUPPLY SCHEME | TSM/015962 | 40037634 | New | MVS | GO2223011821PH | 10/01/2023 | 351.14 | 62.4 | 413.54 | Alipurduar Division | Northern Mechanical Division II | 120.85 | 18.63 | 3.49 | 0 | 142.98 | 120.85 | 3.19 | 0 | 0 | 124.05 | 30 | 61
43 | ALIPURDUAR | SM/11483 | Bandpani Tea Garden Areas Piped Water Supply Scheme. | TSM/005495 | 40023478 | New | SVS | GO2223005056PH | 14/07/2022 | 453.14 | 75.23 | 528.37 | Alipurduar Division | Northern Mechanical Division II | 200.76 | 28.82 | 0 | 0 | 229.58 | 200.73 | 3.3 | 0 | 0 | 204.03 | 38.61 | 60
44 | ALIPURDUAR | SM/13246 | BARIGURI PIPED WATER SUPPLY SCHEME | TSM/014599 | 40036814 | New | MVS | GO2223008740PH | 14/10/2022 | 813.95 | 81.82 | 895.77 | Alipurduar Division | Northern Mechanical Division II | 15.83 | 17.54 | 0 | 0 | 33.38 | 15.83 | 17.54 | 0 | 0 | 33.38 | 3.73 | 28
45 | ALIPURDUAR | SM/13241 | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | TSM/015362 | 40037161 | New | MVS | GO2223008736PH | 14/10/2022 | 717 | 63.16 | 780.16 | Alipurduar Division | Northern Mechanical Division II | 215.85 | 0 | 11.71 | 0 | 227.56 | 215.85 | 0 | 11.71 | 0 | 227.56 | 29.17 | 29
46 | ALIPURDUAR | SM/14214 | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015965 | 40036662 | New | SVS | GO2223011817PH | 10/01/2023 | 463.57 | 63.69 | 527.26 | Alipurduar Division | Northern Mechanical Division II | 202.99 | 31.18 | 44.26 | 0 | 278.43 | 202.99 | 11.07 | 44.26 | 0 | 258.33 | 48.99 | 85
47 | ALIPURDUAR | SM/16820 | BENGKANDI PIPED WATER SUPPLY SCHEME | TSM/017878 | 40049481 | New | MVS | GO2223015806PH | 13/03/2023 | 894.22 | 69.88 | 964.09 | Alipurduar Division | Northern Mechanical Division II | 286.8 | 10.66 | 29.35 | 0 | 326.82 | 149.58 | 0 | 29.35 | 0 | 178.94 | 18.56 | 33
48 | ALIPURDUAR | SM/14211 | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015968 | 40037095 | New | SVS | GO2223011820PH | 10/01/2023 | 466.53 | 63.69 | 530.22 | Alipurduar Division | Northern Mechanical Division II | 109.18 | 20.27 | 9.88 | 0 | 139.33 | 109.18 | 20.27 | 9.88 | 0 | 139.33 | 26.28 | 61
49 | ALIPURDUAR | SM/14212 | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015967 | 40037067 | New | SVS | GO2223011815PH | 10/01/2023 | 505.89 | 64.34 | 570.23 | Alipurduar Division | Northern Mechanical Division II | 251.6 | 26.52 | 43.2 | 0 | 321.32 | 251.6 | 0 | 43.2 | 0 | 294.79 | 51.7 | 72
50 | ALIPURDUAR | SM/18156 | Bhutri Forest Piped Water Supply Scheme | TSM/020702 | 40066311 | New | SVS | GO2223017907PH | 29/03/2023 | 38.49 | 21.05 | 59.54 | Alipurduar Division | Northern Mechanical Division II | 0 | 4.1 | 0 | 0 | 4.1 | 0 | 4.1 | 0 | 0 | 4.1 | 6.88 | 68
51 | ALIPURDUAR | SM/13300 | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | TSM/015364 | 40037133 | New | MVS | GO2223008829PH | 17/10/2022 | 880.65 | 63.55 | 944.2 | Alipurduar Division | Northern Mechanical Division II | 474.38 | 11.61 | 47.78 | 0 | 533.78 | 474.38 | 1.41 | 36.42 | 0 | 512.22 | 54.25 | 85
52 | ALIPURDUAR | SM/13249 | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | TSM/014604 | 40036855 | New | MVS | GO2223008733PH | 14/10/2022 | 707.33 | 152.89 | 860.22 | Alipurduar Division | Northern Mechanical Division II | 0 | 0 | 114.33 | 0 | 114.33 | 0 | 0 | 114.33 | 0 | 114.33 | 13.29 | 16
53 | ALIPURDUAR | SM/16507 | BUXA PIPE WATER SUPPLY SCHEME | TSM/017681 | 40065457 | New | SVS | GO2223015230PH | 03/03/2023 | 154.03 | 65.58 | 219.61 | Alipurduar Division | Northern Mechanical Division II | 0 | 0 | 16.34 | 0 | 16.34 | 0 | 0 | 16.34 | 0 | 16.34 | 7.44 | 3
54 | ALIPURDUAR | SM/15534 | CHALNIPAK PIPED WATER SUPPLY SCHEME. | TSM/015993 | 40037530 | New | MVS | GO2223014001PH | 16/02/2023 | 943.68 | 80.72 | 1024.4 | Alipurduar Division | Northern Mechanical Division II | 360.73 | 15.35 | 18.83 | 0 | 394.91 | 360.73 | 14.97 | 18.83 | 0 | 394.53 | 38.51 | 39
55 | ALIPURDUAR | SM/18152 | Chengmari Piped Water Supply Scheme | TSM/020700 | 40066306 | New | MVS | GO2223017951PH | 29/03/2023 | 731.44 | 40.71 | 772.15 | Alipurduar Division | Northern Mechanical Division II | 349.72 | 0 | 10.45 | 0 | 360.17 | 349.72 | 0 | 0 | 0 | 349.72 | 45.29 | 47
56 | ALIPURDUAR | SM/10179 | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009546 | 40005070 | New | SVS | GO2122009745PH | 16/02/2022 | 329.32 | 34.83 | 364.15 | Alipurduar Division | Northern Mechanical Division II | 316.91 | 22.04 | 2.82 | 0 | 341.77 | 316.39 | 22.04 | 2.82 | 0 | 341.25 | 93.71 | 99
57 | ALIPURDUAR | SM/13242 | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | TSM/015656 | 40037015 | New | SVS | GO2223008742PH | 14/10/2022 | 552.45 | 63.16 | 615.61 | Alipurduar Division | Northern Mechanical Division II | 126.18 | 2.41 | 6.16 | 0 | 134.76 | 126.18 | 2.41 | 0 | 0 | 128.6 | 20.89 | 22
58 | ALIPURDUAR | SM/13302 | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | TSM/014600 | 40036728 | New | SVS | GO2223008819PH | 17/10/2022 | 127.64 | 44.12 | 171.75 | Alipurduar Division | Northern Mechanical Division II | 74.21 | 14.49 | 0 | 0 | 88.7 | 74.21 | 5.32 | 0 | 0 | 79.53 | 46.31 | 53
59 | ALIPURDUAR | SM/13305 | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | TSM/015650 | 40037496 | New | MVS | GO2223008826PH | 17/10/2022 | 696.89 | 63.32 | 760.21 | Alipurduar Division | Northern Mechanical Division II | 376.3 | 7.4 | 18.39 | 0 | 402.09 | 376.3 | 7.4 | 18.39 | 0 | 402.09 | 52.89 | 83
60 | ALIPURDUAR | SM/10174 | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | TSM/009548 | 40005090 | New | MVS | GO2122009748PH | 16/02/2022 | 694.95 | 37.61 | 732.56 | Alipurduar Division | Northern Mechanical Division II | 631.12 | 11.94 | 11.75 | 0 | 654.8 | 617.26 | 11.25 | 11.75 | 0 | 640.26 | 87.4 | 95
61 | ALIPURDUAR | SM/14217 | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | TSM/015960 | 40037108 | New | SVS | GO2223011824PH | 10/01/2023 | 347.28 | 62.1 | 409.38 | Alipurduar Division | Northern Mechanical Division II | 77.23 | 23.34 | 9.77 | 0 | 110.34 | 77.23 | 23.34 | 9.77 | 0 | 110.34 | 26.95 | 38
62 | ALIPURDUAR | SM/16823 | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017770 | 40049276 | New | SVS | GO2223015811PH | 13/03/2023 | 672.54 | 67.13 | 739.67 | Alipurduar Division | Northern Mechanical Division II | 150.81 | 26.11 | 38.98 | 0 | 215.9 | 150.81 | 0 | 38.98 | 0 | 189.79 | 25.66 | 42
63 | ALIPURDUAR | SM/16821 | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/018324 | 40049258 | New | MVS | GO2223015815PH | 13/03/2023 | 304.59 | 100.69 | 405.28 | Alipurduar Division | Northern Mechanical Division II | 0 | 6.67 | 15.52 | 0 | 22.19 | 0 | 0 | 15.52 | 0 | 15.52 | 3.83 | 14
64 | ALIPURDUAR | SM/15208 | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | TSM/017875 | 40046803 | New | MVS | GO2223013436PH | 07/02/2023 | 602.67 | 67.65 | 670.33 | Alipurduar Division | Northern Mechanical Division II | 371.89 | 9.92 | 9.54 | 0 | 391.35 | 362.11 | 0 | 9.54 | 0 | 371.65 | 55.44 | 46
65 | ALIPURDUAR | SM/18153 | Dhantali Piped Water Supply Scheme | TSM/020699 | 40066307 | New | SVS | GO2223017910PH | 29/03/2023 | 245.66 | 39.91 | 285.56 | Alipurduar Division | Northern Mechanical Division II | 107.87 | 0 | 1.27 | 0 | 109.13 | 107.87 | 0 | 0 | 0 | 107.87 | 37.77 | 43
66 | ALIPURDUAR | SM/10038 | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | TSM/006527 | 40046709 | New | SVS | GO2122008403PH | 19/01/2022 | 247.03 | 0 | 247.03 | Alipurduar Division | Northern Mechanical Division II | 70.85 | 0 | 0 | 0 | 70.85 | 70.85 | 0 | 0 | 0 | 70.85 | 28.68 | 98
67 | ALIPURDUAR | SM/13449 | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/015106 | 40036937 | New | MVS | GO2223009245PH | 02/11/2022 | 587.78 | 107.67 | 695.45 | Alipurduar Division | Northern Mechanical Division II | 281.27 | 4.79 | 34.84 | 0 | 320.91 | 281.27 | 4.79 | 34.84 | 0 | 320.91 | 46.14 | 69
68 | ALIPURDUAR | SM/07174 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | TSM/005853 | 8174337 | Retrofitting | MVS | GO2021003037PH | 04/12/2020 | 76.33 | 0 | 76.33 | Alipurduar Division |  | 76.33 | 0 | 0 | 0 | 76.33 | 76.07 | 0 | 0 | 0 | 76.07 | 99.67 | 99
69 | ALIPURDUAR | SM/07058 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | TSM/005854 | 8130026 | Retrofitting | MVS | GO2021002769PH | 25/11/2020 | 82.69 | 0 | 82.69 | Alipurduar Division |  | 77 | 0 | 0 | 0 | 77 | 76.99 | 0 | 0 | 0 | 76.99 | 93.11 | 72
70 | ALIPURDUAR | SM/07187 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | TSM/005833 | 8174182 | Retrofitting | MVS | GO2021003051PH | 04/12/2020 | 73.94 | 0 | 73.94 | Alipurduar Division |  | 73.94 | 0 | 0 | 0 | 73.94 | 73.94 | 0 | 0 | 0 | 73.94 | 100 | 75
71 | ALIPURDUAR | SM/07188 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | TSM/005834 | 8174189 | Retrofitting | MVS | GO2021003025PH | 04/12/2020 | 73.94 | 0 | 73.94 | Alipurduar Division |  | 73.94 | 0 | 0 | 0 | 73.94 | 54.01 | 0 | 0 | 0 | 54.01 | 73.05 | 75
72 | ALIPURDUAR | SM/07185 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | TSM/005877 | 8173954 | Retrofitting | MVS | GO2021003049PH | 04/12/2020 | 82.87 | 0 | 82.87 | Alipurduar Division |  | 82.87 | 0 | 0 | 0 | 82.87 | 82.87 | 0 | 0 | 0 | 82.87 | 100 | 96
73 | ALIPURDUAR | SM/07127 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) | TSM/005878 | 8129729 | Retrofitting | MVS | GO2021002827PH | 26/11/2020 | 66.37 | 0 | 66.37 | Alipurduar Division |  | 66.37 | 0 | 0 | 0 | 66.37 | 66.37 | 0 | 0 | 0 | 66.37 | 100 | 99
74 | ALIPURDUAR | SM/07126 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | TSM/005879 | 8129734 | Retrofitting | SVS | GO2021002828PH | 26/11/2020 | 93 | 0 | 93 | Alipurduar Division |  | 93 | 0 | 0 | 0 | 93 | 93 | 0 | 0 | 0 | 93 | 100 | 91
75 | ALIPURDUAR | SM/07125 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | TSM/005880 | 8129732 | Retrofitting | SVS | GO2021002820PH | 26/11/2020 | 90.17 | 0 | 90.17 | Alipurduar Division |  | 90.17 | 0 | 0 | 0 | 90.17 | 90.17 | 0 | 0 | 0 | 90.17 | 100 | 91
76 | ALIPURDUAR | SM/07123 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | TSM/005881 | 8129704 | Retrofitting | MVS | GO2021002810PH | 26/11/2020 | 98.96 | 0 | 98.96 | Alipurduar Division |  | 98.96 | 0 | 0 | 0 | 98.96 | 98.96 | 0 | 0 | 0 | 98.96 | 100 | 91
77 | ALIPURDUAR | SM/07122 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) | TSM/005882 | 8129709 | Retrofitting | MVS | GO2021002812PH | 26/11/2020 | 98.68 | 0 | 98.68 | Alipurduar Division |  | 98.68 | 0 | 0 | 0 | 98.68 | 98.68 | 0 | 0 | 0 | 98.68 | 100 | 91
78 | ALIPURDUAR | SM/07175 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | TSM/005855 | 8173346 | Retrofitting | SVS | GO2021003038PH | 04/12/2020 | 91.69 | 0 | 91.69 | Alipurduar Division |  | 91.69 | 0 | 0 | 0 | 91.69 | 91.69 | 0 | 0 | 0 | 91.69 | 100 | 91
79 | ALIPURDUAR | SM/07121 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | TSM/005856 | 8174041 | Retrofitting | SVS | GO2021002814PH | 26/11/2020 | 82.27 | 0 | 82.27 | Alipurduar Division |  | 82.27 | 0 | 0 | 0 | 82.27 | 79.34 | 0 | 0 | 0 | 79.34 | 96.43 | 99
80 | ALIPURDUAR | SM/07059 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) | TSM/005857 | 6821967 | Retrofitting | MVS | GO2021002758PH | 25/11/2020 | 97.58 | 0 | 97.58 | Alipurduar Division |  | 97.58 | 0 | 0 | 0 | 97.58 | 97.58 | 0 | 0 | 0 | 97.58 | 100 | 43
81 | ALIPURDUAR | SM/07176 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | TSM/005858 | 6821967 | Retrofitting | SVS | GO2021003039PH | 04/12/2020 | 70.54 | 0 | 70.54 | Alipurduar Division |  | 68.86 | 0 | 0 | 0 | 68.86 | 68.86 | 0 | 0 | 0 | 68.86 | 97.62 | 80
82 | ALIPURDUAR | SM/07137 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | TSM/005883 | 8129765 | Retrofitting | MVS | GO2021002808PH | 26/11/2020 | 97.16 | 0 | 97.16 | Alipurduar Division |  | 87.69 | 0 | 0 | 0 | 87.69 | 86.26 | 0 | 0 | 0 | 86.26 | 88.79 | 99
83 | ALIPURDUAR | SM/07191 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme | TSM/005838 | 7399520 | Retrofitting | SVS | GO2021003028PH | 04/12/2020 | 62.8 | 0 | 62.8 | Alipurduar Division |  | 30.7 | 0 | 0 | 0 | 30.7 | 30.7 | 0 | 0 | 0 | 30.7 | 48.88 | 97
84 | ALIPURDUAR | SM/07194 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | TSM/005840 | 7399580 | Retrofitting | SVS | GO2021003031PH | 04/12/2020 | 98.15 | 0 | 98.15 | Alipurduar Division |  | 98.15 | 0 | 0 | 0 | 98.15 | 98.15 | 0 | 0 | 0 | 98.15 | 100 | 98
85 | ALIPURDUAR | SM/07068 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | TSM/005888 | 40011013 | Retrofitting | SVS | GO2021002764PH | 25/11/2020 | 85.62 | 0 | 85.62 | Alipurduar Division |  | 78.07 | 0 | 0 | 0 | 78.07 | 76.23 | 0 | 0 | 0 | 76.23 | 89.03 | 81
86 | ALIPURDUAR | SM/07069 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) | TSM/005889 | 40011015 | Retrofitting | SVS | GO2021002765PH | 25/11/2020 | 61.34 | 0 | 61.34 | Alipurduar Division |  | 61.34 | 0 | 0 | 0 | 61.34 | 61.33 | 0 | 0 | 0 | 61.33 | 99.98 | 99
87 | ALIPURDUAR | SM/07197 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | TSM/005847 | 8174306 | Retrofitting | SVS | GO2021003034PH | 04/12/2020 | 84.07 | 0 | 84.07 | Alipurduar Division |  | 63.14 | 0 | 0 | 0 | 63.14 | 59.32 | 0 | 0 | 0 | 59.32 | 70.56 | 81
88 | ALIPURDUAR | SM/07064 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | TSM/005866 | 7943136 | Retrofitting | SVS | GO2021002768PH | 25/11/2020 | 99.04 | 0 | 99.04 | Alipurduar Division |  | 95.51 | 0 | 0 | 0 | 95.51 | 95.26 | 0 | 0 | 0 | 95.26 | 96.18 | 99
89 | ALIPURDUAR | SM/07129 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | TSM/005844 | 8129525 | Retrofitting | SVS | GO2021002815PH | 26/11/2020 | 72.16 | 0 | 72.16 | Alipurduar Division |  | 72.16 | 0 | 0 | 0 | 72.16 | 72.16 | 0 | 0 | 0 | 72.16 | 100 | 56
90 | ALIPURDUAR | SM/07184 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | TSM/005872 | 8176916 | Retrofitting | SVS | GO2021003048PH | 04/12/2020 | 82.41 | 0 | 82.41 | Alipurduar Division |  | 82.41 | 0 | 0 | 0 | 82.41 | 82.27 | 0 | 0 | 0 | 82.27 | 99.83 | 98
91 | ALIPURDUAR | SM/07057 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | TSM/005852 | 8130049 | Retrofitting | SVS | GO2021002770PH | 25/11/2020 | 99.09 | 0 | 99.09 | Alipurduar Division |  | 99.09 | 0 | 0 | 0 | 99.09 | 99.09 | 0 | 0 | 0 | 99.09 | 100 | 99
92 | ALIPURDUAR | SM/07193 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | TSM/005841 | 8174256 | Retrofitting | SVS | GO2021003030PH | 04/12/2020 | 60.86 | 0 | 60.86 | Alipurduar Division |  | 60.86 | 0 | 0 | 0 | 60.86 | 60.86 | 0 | 0 | 0 | 60.86 | 100 | 98
93 | ALIPURDUAR | SM/07195 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | TSM/005843 | 8174344 | Retrofitting | SVS | GO2021003032PH | 04/12/2020 | 98.84 | 0 | 98.84 | Alipurduar Division |  | 98.84 | 0 | 0 | 0 | 98.84 | 98.84 | 0 | 0 | 0 | 98.84 | 100 | 99
94 | ALIPURDUAR | SM/07181 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | TSM/005868 | 8175962 | Retrofitting | MVS | GO2021003045PH | 04/12/2020 | 89.66 | 0 | 89.66 | Alipurduar Division |  | 89.63 | 0 | 0 | 0 | 89.63 | 89.61 | 0 | 0 | 0 | 89.61 | 99.95 | 98
95 | ALIPURDUAR | SM/07065 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | TSM/005869 | 8130060 | Retrofitting | SVS | GO2021002767PH | 25/11/2020 | 73.85 | 0 | 73.85 | Alipurduar Division |  | 24.29 | 0 | 9.83 | 0 | 34.11 | 24.29 | 0 | 9.83 | 0 | 34.11 | 46.19 | 68
96 | ALIPURDUAR | SM/07138 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | TSM/005884 | 8129741 | Retrofitting | SVS | GO2021002805PH | 26/11/2020 | 96.46 | 0 | 96.46 | Alipurduar Division |  | 96.46 | 0 | 0 | 0 | 96.46 | 96.46 | 0 | 0 | 0 | 96.46 | 100 | 99
97 | ALIPURDUAR | SM/07066 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | TSM/005885 | 8130057 | Retrofitting | MVS | GO2021002771PH | 25/11/2020 | 80.75 | 0 | 80.75 | Alipurduar Division |  | 78.4 | 0 | 0 | 0 | 78.4 | 78.08 | 0 | 0 | 0 | 78.08 | 96.69 | 99
98 | ALIPURDUAR | SM/07182 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | TSM/005870 | 8175877 | Retrofitting | MVS | GO2021003046PH | 04/12/2020 | 98.81 | 0 | 98.81 | Alipurduar Division |  | 98.81 | 0 | 0 | 0 | 98.81 | 98.81 | 0 | 0 | 0 | 98.81 | 100 | 99
99 | ALIPURDUAR | SM/07183 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) | TSM/005871 | 8175883 | Retrofitting | MVS | GO2021003047PH | 04/12/2020 | 56.02 | 0 | 56.02 | Alipurduar Division |  | 56.02 | 0 | 0 | 0 | 56.02 | 53.47 | 0 | 0 | 0 | 53.47 | 95.44 | 87
100 | ALIPURDUAR | SM/07192 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | TSM/005839 | 7723883 | Retrofitting | SVS | GO2021003029PH | 04/12/2020 | 83.76 | 0 | 83.76 | Alipurduar Division |  | 83.76 | 0 | 0 | 0 | 83.76 | 83.76 | 0 | 0 | 0 | 83.76 | 100 | 99
101 | ALIPURDUAR | SM/07199 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | TSM/005845 | 8174361 | Retrofitting | SVS | GO2021003036PH | 04/12/2020 | 61.63 | 0 | 61.63 | Alipurduar Division |  | 53.58 | 0 | 0 | 0 | 53.58 | 48.89 | 0 | 0 | 0 | 48.89 | 79.32 | 99
102 | ALIPURDUAR | SM/07198 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | TSM/005846 | 6856215 | Retrofitting | SVS | GO2021003035PH | 04/12/2020 | 69.04 | 0 | 69.04 | Alipurduar Division |  | 64.04 | 0 | 0 | 0 | 64.04 | 62.48 | 0 | 0 | 0 | 62.48 | 90.51 | 98
103 | ALIPURDUAR | SM/07178 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) | TSM/005864 | 8175850 | Retrofitting | SVS | GO2021003042PH | 04/12/2020 | 98.08 | 0 | 98.08 | Alipurduar Division |  | 98.08 | 0 | 0 | 0 | 98.08 | 98.03 | 0 | 0 | 0 | 98.03 | 99.95 | 72
104 | ALIPURDUAR | SM/07179 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | TSM/005865 | 8175853 | Retrofitting | SVS | GO2021003043PH | 04/12/2020 | 69.14 | 0 | 69.14 | Alipurduar Division |  | 42.87 | 0 | 0 | 0 | 42.87 | 42.69 | 0 | 0 | 0 | 42.69 | 61.74 | 72
105 | ALIPURDUAR | SM/07190 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | TSM/005835 | 6765701 | Retrofitting | SVS | GO2021003027PH | 04/12/2020 | 83.82 | 0 | 83.82 | Alipurduar Division |  | 83.82 | 0 | 0 | 0 | 83.82 | 83.8 | 0 | 0 | 0 | 83.8 | 99.97 | 98
106 | ALIPURDUAR | SM/07135 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) | TSM/005873 | 8174391 | Retrofitting | SVS | GO2021002802PH | 26/11/2020 | 87.03 | 0 | 87.03 | Alipurduar Division |  | 87.03 | 0 | 0 | 0 | 87.03 | 87.03 | 0 | 0 | 0 | 87.03 | 100 | 98
107 | ALIPURDUAR | SM/07136 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | TSM/005874 | 8174390 | Retrofitting | MVS | GO2021002803PH | 26/11/2020 | 80.05 | 0 | 80.05 | Alipurduar Division |  | 67.16 | 0 | 0 | 0 | 67.16 | 67.16 | 0 | 0 | 0 | 67.16 | 83.89 | 87
108 | ALIPURDUAR | SM/07060 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | TSM/005859 | 8130054 | Retrofitting | MVS | GO2021002762PH | 25/11/2020 | 86.77 | 0 | 86.77 | Alipurduar Division |  | 86.77 | 0 | 0 | 0 | 86.77 | 86.77 | 0 | 0 | 0 | 86.77 | 100 | 98
109 | ALIPURDUAR | SM/07061 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) | TSM/005860 | 8130056 | Retrofitting | MVS | GO2021002759PH | 25/11/2020 | 93.85 | 0 | 93.85 | Alipurduar Division |  | 93.85 | 0 | 0 | 0 | 93.85 | 93.85 | 0 | 0 | 0 | 93.85 | 100 | 64
110 | ALIPURDUAR | SM/07134 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) | TSM/005875 | 8174378 | Retrofitting | SVS | GO2021002801PH | 26/11/2020 | 89.44 | 0 | 89.44 | Alipurduar Division |  | 89.44 | 0 | 0 | 0 | 89.44 | 84.64 | 0 | 0 | 0 | 84.64 | 94.63 | 98
111 | ALIPURDUAR | SM/07124 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) | TSM/005876 | 8174381 | Retrofitting | SVS | GO2021002800PH | 26/11/2020 | 55.28 | 0 | 55.28 | Alipurduar Division |  | 55.28 | 0 | 0 | 0 | 55.28 | 47.81 | 0 | 0 | 0 | 47.81 | 86.49 | 96
112 | ALIPURDUAR | SM/07186 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | TSM/005887 | 40011021 | Retrofitting | SVS | GO2021003050PH | 04/12/2020 | 99.29 | 0 | 99.29 | Alipurduar Division |  | 85 | 0 | 0 | 0 | 85 | 81.62 | 0 | 0 | 0 | 81.62 | 82.2 | 99
113 | ALIPURDUAR | SM/07067 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) | TSM/005886 | 40011018 | Retrofitting | MVS | GO2021002766PH | 25/11/2020 | 98.86 | 0 | 98.86 | Alipurduar Division |  | 98.86 | 0 | 0 | 0 | 98.86 | 98.86 | 0 | 0 | 0 | 98.86 | 100 | 99
114 | ALIPURDUAR | SM/07196 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | TSM/005842 | 7943081 | Retrofitting | SVS | GO2021003033PH | 04/12/2020 | 67.24 | 0 | 67.24 | Alipurduar Division |  | 51.07 | 0 | 0 | 0 | 51.07 | 51.06 | 0 | 0 | 0 | 51.06 | 75.94 | 98
115 | ALIPURDUAR | SM/07177 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | TSM/005862 | 8175831 | Retrofitting | SVS | GO2021003041PH | 04/12/2020 | 68.96 | 0 | 68.96 | Alipurduar Division |  | 68.96 | 0 | 0 | 0 | 68.96 | 68.96 | 0 | 0 | 0 | 68.96 | 100 | 99
116 | ALIPURDUAR | SM/07063 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | TSM/005863 | 8130062 | Retrofitting | SVS | GO2021002761PH | 25/11/2020 | 91.9 | 0 | 91.9 | Alipurduar Division |  | 89.1 | 0 | 0 | 0 | 89.1 | 88.58 | 0 | 0 | 0 | 88.58 | 96.38 | 99
117 | ALIPURDUAR | SM/07128 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | TSM/005837 | 8174233 | Retrofitting | SVS | GO2021002817PH | 26/11/2020 | 62.07 | 0 | 62.07 | Alipurduar Division |  | 62.07 | 0 | 0 | 0 | 62.07 | 62.07 | 0 | 0 | 0 | 62.07 | 100 | 65
118 | ALIPURDUAR | SM/07189 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) | TSM/005836 | 8174226 | Retrofitting | MVS | GO2021003026PH | 04/12/2020 | 97.67 | 0 | 97.67 | Alipurduar Division |  | 97.67 | 0 | 0 | 0 | 97.67 | 97.67 | 0 | 0 | 0 | 97.67 | 100 | 81
119 | ALIPURDUAR | SM/07180 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | TSM/005867 | 8175892 | Retrofitting | SVS | GO2021003044PH | 04/12/2020 | 64.83 | 0 | 64.83 | Alipurduar Division |  | 35.82 | 0 | 0 | 0 | 35.82 | 11.34 | 0 | 0 | 0 | 11.34 | 17.49 | 42
120 | ALIPURDUAR | SM/07062 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | TSM/005861 | 8175965 | Retrofitting | SVS | GO2021002760PH | 25/11/2020 | 87.86 | 0 | 87.86 | Alipurduar Division |  | 87.86 | 0 | 0 | 0 | 87.86 | 87.86 | 0 | 0 | 0 | 87.86 | 100 | 99
121 | ALIPURDUAR | SM/07133 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | TSM/005850 | 8129737 | Retrofitting | SVS | PH202130005S000 | 26/11/2020 | 95.65 | 0 | 95.65 | Alipurduar Division |  | 95.65 | 0 | 0 | 0 | 95.65 | 95.65 | 0 | 0 | 0 | 95.65 | 100 | 99
122 | ALIPURDUAR | SM/07132 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | TSM/005851 | 8129739 | Retrofitting | SVS | GO2021002826PH | 26/11/2020 | 88.7 | 0 | 88.7 | Alipurduar Division |  | 13.95 | 0 | 0 | 0 | 13.95 | 13.76 | 0 | 0 | 0 | 13.76 | 15.52 | 22
123 | ALIPURDUAR | SM/07131 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | TSM/005849 | 7943047 | Retrofitting | SVS | GO2021002819PH | 26/11/2020 | 73.16 | 0 | 73.16 | Alipurduar Division |  | 67.15 | 0 | 0 | 0 | 67.15 | 67.15 | 0 | 0 | 0 | 67.15 | 91.79 | 50
124 | ALIPURDUAR | SM/07130 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | TSM/005848 | 8129510 | Retrofitting | SVS | GO2021002816PH | 26/11/2020 | 94.15 | 0 | 94.15 | Alipurduar Division |  | 86.11 | 0 | 0 | 0 | 86.11 | 86.11 | 0 | 0 | 0 | 86.11 | 91.46 | 47
125 | ALIPURDUAR | SM/08882 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | TSM/008184 | 8382128 | Retrofitting | MVS | GO2122003590PH | 27/09/2021 | 129.45 | 0 | 129.45 | Alipurduar Division |  | 129.45 | 0 | 0 | 0 | 129.45 | 128.72 | 0 | 0 | 0 | 128.72 | 99.44 | 98
126 | ALIPURDUAR | SM/08884 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | TSM/008186 | 8382141 | Retrofitting | MVS | GO2122003590PH | 27/09/2021 | 398.83 | 0 | 398.83 | Alipurduar Division |  | 387.21 | 0 | 0 | 0 | 387.21 | 387.18 | 0 | 0 | 0 | 387.18 | 97.08 | 77
127 | ALIPURDUAR | SM/08883 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | TSM/008185 | 8382132 | Retrofitting | SVS | GO2122003590PH | 27/09/2021 | 87.85 | 0 | 87.85 | Alipurduar Division |  | 87.85 | 0 | 0 | 0 | 87.85 | 82.8 | 0 | 0 | 0 | 82.8 | 94.26 | 61
128 | ALIPURDUAR | SM/08880 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | TSM/008218 | 8382115 | Retrofitting | SVS | GO2122003590PH | 27/09/2021 | 140.24 | 0 | 140.24 | Alipurduar Division |  | 140.24 | 0 | 0 | 0 | 140.24 | 140.24 | 0 | 0 | 0 | 140.24 | 100 | 81
129 | ALIPURDUAR | SM/08881 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | TSM/008216 | 8382122 | Retrofitting | MVS | GO2122003590PH | 27/09/2021 | 184.32 | 0 | 184.32 | Alipurduar Division |  | 97.55 | 0 | 35.82 | 0 | 133.37 | 95.13 | 0 | 35.82 | 0 | 130.95 | 71.04 | 99
130 | ALIPURDUAR | SM/08080 | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | TSM/006690 | 7497825 | Retrofitting | MVS | GO2021006295PH | 04/02/2021 | 1224.31 | 0 | 1224.31 | Alipurduar Division |  | 841.38 | 0 | 33.83 | 0 | 875.21 | 839.31 | 0 | 33.83 | 0 | 873.14 | 71.32 | 72
131 | ALIPURDUAR | SM/14210 | FOSKADANGA PIPED WATER SUPPLY SCHEME | TSM/015969 | 40037104 | New | SVS | GO2223011818PH | 10/01/2023 | 448.75 | 62.25 | 510.99 | Alipurduar Division | Northern Mechanical Division II | 158.54 | 40.41 | 4.21 | 0 | 203.15 | 158.54 | 27.49 | 0 | 0 | 186.02 | 36.4 | 17
132 | ALIPURDUAR | SM/10180 | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | TSM/009551 | 40005065 | New | SVS | GO2122009745PH | 16/02/2022 | 338.86 | 38.05 | 376.91 | Alipurduar Division | Northern Mechanical Division II | 253.9 | 25.26 | 75.09 | 0 | 354.25 | 253.82 | 19.24 | 75.09 | 0 | 348.14 | 92.37 | 85
133 | ALIPURDUAR | SM/14216 | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | TSM/015963 | 40037096 | New | SVS | GO2223011825PH | 10/01/2023 | 85.21 | 44.2 | 129.41 | Alipurduar Division | Northern Mechanical Division II | 35.62 | 8.27 | 23.4 | 0 | 67.29 | 35.62 | 1.46 | 23.4 | 0 | 60.48 | 46.74 | 69
134 | ALIPURDUAR | SM/10178 | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009543 | 40005165 | New | MVS | GO2122009749PH | 16/02/2022 | 516.27 | 61.06 | 577.33 | Alipurduar Division | Northern Mechanical Division II | 446.91 | 22.15 | 59.81 | 0 | 528.86 | 433.37 | 21.46 | 50.66 | 0 | 505.49 | 87.56 | 82
135 | ALIPURDUAR | SM/11696 | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011589 | 40024037 | New | MVS | GO2223005729PH | 29/07/2022 | 366.4 | 44.95 | 411.35 | Alipurduar Division | Northern Mechanical Division II | 182 | 30.79 | 0 | 0 | 212.79 | 182 | 3.2 | 0 | 0 | 185.19 | 45.02 | 79
136 | ALIPURDUAR | SM/10776 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME | TSM/009986 | 40022763 | New | MVS | GO2223003222PH | 23/05/2022 | 132.98 | 35 | 167.97 | Alipurduar Division | Northern Mechanical Division II | 97.37 | 0 | 0 | 0 | 97.37 | 97.37 | 0 | 0 | 0 | 97.37 | 57.96 | 72
137 | ALIPURDUAR | SM/13448 | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | TSM/015538 | 40036970 | New | MVS | GO2223009243PH | 02/11/2022 | 243.07 | 62.09 | 305.16 | Alipurduar Division | Northern Mechanical Division II | 40 | 19.24 | 3.46 | 0 | 62.7 | 40 | 0 | 0 | 0 | 40 | 13.11 | 34
138 | ALIPURDUAR | SM/10177 | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009547 | 40005154 | New | MVS | GO2122009749PH | 16/02/2022 | 300.98 | 37.61 | 338.59 | Alipurduar Division | Northern Mechanical Division II | 211.93 | 2.93 | 17.68 | 0 | 232.54 | 211.26 | 2.93 | 17.68 | 0 | 231.87 | 68.48 | 56
139 | ALIPURDUAR | SM/13239 | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/015105 | 40036914 | New | MVS | GO2223008732PH | 14/10/2022 | 593.09 | 123.89 | 716.98 | Alipurduar Division | Northern Mechanical Division II | 352.5 | 39.72 | 32.85 | 0 | 425.07 | 352.5 | 5.49 | 32.85 | 0 | 390.84 | 54.51 | 71
140 | ALIPURDUAR | SM/13306 | KALABERIA PIPED WATER SUPPLY SCHEME | TSM/014585 | 40036825 | New | MVS | GO2223008823PH | 17/10/2022 | 398.97 | 62.31 | 461.28 | Alipurduar Division | Northern Mechanical Division II | 142.38 | 8.48 | 6.56 | 0 | 157.42 | 142.38 | 8.48 | 6.56 | 0 | 157.42 | 34.13 | 40
141 | ALIPURDUAR | SM/15482 | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009552 | 40007035 | New | SVS | GO2223013769PH | 13/02/2023 | 1250.5 | 130.17 | 1380.67 | Alipurduar Division | Northern Mechanical Division II | 70 | 90.13 | 99.04 | 0 | 259.16 | 70 | 20.59 | 99.04 | 0 | 189.63 | 13.73 | 33
142 | ALIPURDUAR | SM/11991 | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | TSM/012047 | 40036699 | New | SVS | GO2223006897PH | 01/09/2022 | 394.43 | 37.61 | 432.05 | Alipurduar Division | Northern Mechanical Division II | 277.57 | 19.67 | 17.72 | 0 | 314.96 | 264.23 | 2.62 | 17.72 | 0 | 284.57 | 65.86 | 88
143 | ALIPURDUAR | SM/13299 | KAYAKHATA PIPED WATER SUPPLY SCHEME | TSM/015411 | 40036926 | New | MVS | GO2223008833PH | 17/10/2022 | 619.24 | 63.17 | 682.41 | Alipurduar Division | Northern Mechanical Division II | 142.96 | 3.2 | 37.46 | 0 | 183.63 | 142.96 | 0 | 27.72 | 0 | 170.67 | 25.01 | 42
144 | ALIPURDUAR | SM/18151 | Khagenhat Piped Water Supply Scheme | TSM/020701 | 40066308 | New | MVS | GO2223017955PH | 29/03/2023 | 782.27 | 40.71 | 822.98 | Alipurduar Division | Northern Mechanical Division II | 0 | 0 | 12.67 | 0 | 12.67 | 0 | 0 | 12.67 | 0 | 12.67 | 1.54 | 19
145 | ALIPURDUAR | SM/12113 | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/013061 | 40036804 | New | MVS | GO2223006993PH | 02/09/2022 | 761.82 | 59.54 | 821.35 | Alipurduar Division | Northern Mechanical Division II | 289.32 | 32.6 | 28.93 | 0 | 350.85 | 282.05 | 3.93 | 28.93 | 0 | 314.91 | 38.34 | 78
146 | ALIPURDUAR | SM/11482 | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | TSM/010924 | 40019043 | New | SVS | GO2223005056PH | 14/07/2022 | 357.61 | 37.61 | 395.23 | Alipurduar Division | Northern Mechanical Division II | 178.25 | 13.25 | 10.52 | 0 | 202.02 | 178.24 | 3.17 | 1.34 | 0 | 182.75 | 46.24 | 86
147 | ALIPURDUAR | SM/16819 | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | TSM/017918 | 40049480 | New | MVS | GO2223015808PH | 13/03/2023 | 590.47 | 67.82 | 658.29 | Alipurduar Division | Northern Mechanical Division II | 98.52 | 0 | 24.61 | 0 | 123.13 | 98.52 | 0 | 24.61 | 0 | 123.13 | 18.7 | 18
148 | ALIPURDUAR | SM/10173 | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009550 | 40005076 | New | MVS | GO2122009746PH | 16/02/2022 | 828.87 | 57.38 | 886.25 | Alipurduar Division | Northern Mechanical Division II | 705.11 | 35.65 | 104.21 | 0 | 844.96 | 704.34 | 35.65 | 104.21 | 0 | 844.2 | 95.26 | 91
149 | ALIPURDUAR | SM/15517 | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | TSM/014896 | 40037186 | New | MVS | GO2223014010PH | 16/02/2023 | 1002.88 | 64.14 | 1067.02 | Alipurduar Division | Northern Mechanical Division II | 437.46 | 2.41 | 60.18 | 0 | 500.06 | 437.46 | 2.41 | 60.18 | 0 | 500.06 | 46.86 | 66
150 | ALIPURDUAR | SM/13248 | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | TSM/014606 | 40036889 | New | MVS | GO2223008737PH | 14/10/2022 | 795.28 | 81.89 | 877.17 | Alipurduar Division | Northern Mechanical Division II | 352.3 | 29.61 | 15.14 | 0 | 397.05 | 352.3 | 29.61 | 15.14 | 0 | 397.05 | 45.27 | 37
151 | ALIPURDUAR | SM/15206 | MAIRADANGA PIPED WATER SUPPLY SCHEME | TSM/018061 | 40046877 | New | MVS | GO2223013434PH | 07/02/2023 | 895.18 | 68.54 | 963.71 | Alipurduar Division | Northern Mechanical Division II | 180.27 | 0 | 37.74 | 0 | 218.01 | 180.27 | 0 | 21.85 | 0 | 202.12 | 20.97 | 35
152 | ALIPURDUAR | SM/18150 | Malangi Tea Garden Area Piped Water Supply Scheme | TSM/020703 | 40066312 | New | SVS | GO2223017952PH | 29/03/2023 | 520.74 | 40.71 | 561.45 | Alipurduar Division | Northern Mechanical Division II | 9.01 | 1.36 | 13.03 | 0 | 23.39 | 9.01 | 0 | 13.03 | 0 | 22.03 | 3.92 | 33
153 | ALIPURDUAR | SM/16818 | MALSAGAON PIPED WATER SUPPLY SCHEME | TSM/017938 | 40049482 | New | MVS | GO2223015813PH | 13/03/2023 | 710.61 | 66.85 | 777.46 | Alipurduar Division | Northern Mechanical Division II | 491.73 | 0 | 9.12 | 0 | 500.85 | 491.73 | 0 | 9.12 | 0 | 500.85 | 64.42 | 38
154 | ALIPURDUAR | SM/13304 | MARAKHATA PIPED WATER SUPPLY SCHEME. | TSM/015657 | 40037495 | New | MVS | GO2223008805PH | 17/10/2022 | 776.66 | 62.43 | 839.09 | Alipurduar Division | Northern Mechanical Division II | 271.73 | 6.71 | 28.02 | 0 | 306.47 | 271.73 | 2.41 | 28.02 | 0 | 302.17 | 36.01 | 80
155 | ALIPURDUAR | SM/10172 | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009549 | 40005155 | New | MVS | GO2122009751PH | 16/02/2022 | 772.35 | 37.93 | 810.28 | Alipurduar Division | Northern Mechanical Division II | 554.88 | 23.03 | 7.4 | 0 | 585.31 | 545.8 | 23.03 | 7.4 | 0 | 576.24 | 71.12 | 98
156 | ALIPURDUAR | SM/10176 | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/009545 | 40005067 | New | SVS | GO2122009750PH | 16/02/2022 | 388.31 | 38.05 | 426.36 | Alipurduar Division | Northern Mechanical Division II | 158.93 | 30.9 | 1.72 | 0 | 191.55 | 158.62 | 0 | 1.72 | 0 | 160.34 | 37.61 | 56
157 | ALIPURDUAR | SM/12754 | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | TSM/014598 | 40036833 | New | MVS | GO2223007992PH | 20/09/2022 | 353.78 | 61.94 | 415.72 | Alipurduar Division | Northern Mechanical Division II | 164.49 | 11.37 | 0 | 0 | 175.86 | 164.49 | 11.37 | 0 | 0 | 175.86 | 42.3 | 31
158 | ALIPURDUAR | SM/15758 | NARASINGPUR PIPED WATER SUPPLY SCHEME | TSM/017984 | 40046823 | New | MVS | GO2223014254PH | 20/02/2023 | 772.25 | 70.21 | 842.46 | Alipurduar Division | Northern Mechanical Division II | 397.6 | 15.04 | 30.32 | 0 | 442.96 | 397.6 | 0 | 30.32 | 0 | 427.92 | 50.79 | 33
159 | ALIPURDUAR | SM/11484 | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | TSM/010927 | 40016485 | New | SVS | GO2223005062PH | 14/07/2022 | 417.62 | 37.61 | 455.23 | Alipurduar Division | Northern Mechanical Division II | 226.33 | 21.64 | 28.55 | 0 | 276.51 | 225.71 | 11.86 | 28.55 | 0 | 266.12 | 58.46 | 86
160 | ALIPURDUAR | SM/13244 | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | TSM/014603 | 40036856 | New | MVS | GO2223008738PH | 14/10/2022 | 646.44 | 63.83 | 710.27 | Alipurduar Division | Northern Mechanical Division II | 207.77 | 12.15 | 9.02 | 0 | 228.94 | 207.77 | 0 | 9.02 | 0 | 216.79 | 30.52 | 78
161 | ALIPURDUAR | SM/14215 | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015964 | 40037107 | New | SVS | GO2223011806PH | 10/01/2023 | 273.61 | 62.87 | 336.47 | Alipurduar Division | Northern Mechanical Division II | 120.37 | 2.72 | 6.17 | 0 | 129.26 | 120.37 | 2.72 | 6.17 | 0 | 129.26 | 38.42 | 61
162 | ALIPURDUAR | SM/14218 | NURPUR PIPED WATER SUPPLY SCHEME. | TSM/016017 | 40065468 | New | MVS | GO2223011803PH | 10/01/2023 | 370.75 | 80.61 | 451.36 | Alipurduar Division | Northern Mechanical Division II | 141.29 | 24.24 | 9.54 | 0 | 175.07 | 141.29 | 2.62 | 9.54 | 0 | 153.44 | 34 | 92
163 | ALIPURDUAR | SM/14223 | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | TSM/015992 | 40037029 | New | SVS | GO2223011804PH | 10/01/2023 | 428.44 | 81.31 | 509.75 | Alipurduar Division | Northern Mechanical Division II | 19.51 | 3.62 | 8.79 | 0 | 31.92 | 19.51 | 3.62 | 5.08 | 0 | 28.21 | 5.53 | 18
164 | ALIPURDUAR | SM/14209 | PARARPAR PIPED WATER SUPPLY SCHEME | TSM/015970 | 40037098 | New | SVS | GO2223011823PH | 10/01/2023 | 499.36 | 62.47 | 561.82 | Alipurduar Division | Northern Mechanical Division II | 183.62 | 25.71 | 0 | 0 | 209.33 | 183.62 | 13.96 | 0 | 0 | 197.58 | 35.17 | 28
165 | ALIPURDUAR | SM/18158 | Parpatla Khawa Piped Water Supply Scheme | TSM/020696 | 40066309 | New | SVS | GO2223017907PH | 29/03/2023 | 147.97 | 39.91 | 187.87 | Alipurduar Division | Northern Mechanical Division II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
166 | ALIPURDUAR | SM/13240 | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | TSM/015365 | 40037125 | New | MVS | GO2223008735PH | 14/10/2022 | 677.63 | 63.63 | 741.26 | Alipurduar Division | Northern Mechanical Division II | 201.82 | 2.41 | 5.71 | 0 | 209.95 | 201.82 | 2.41 | 5.71 | 0 | 209.95 | 28.32 | 73
167 | ALIPURDUAR | SM/15207 | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | TSM/017889 | 40046813 | New | MVS | GO2223013435PH | 07/02/2023 | 734.24 | 68.71 | 802.95 | Alipurduar Division | Northern Mechanical Division II | 239.02 | 0 | 15.57 | 0 | 254.59 | 239.02 | 0 | 2.67 | 0 | 241.69 | 30.1 | 50
168 | ALIPURDUAR | SM/13245 | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | TSM/014601 | 40036863 | New | MVS | GO2223008739PH | 14/10/2022 | 886.94 | 82.71 | 969.65 | Alipurduar Division | Northern Mechanical Division II | 610.46 | 4.08 | 0 | 0 | 614.54 | 592.95 | 4.08 | 0 | 0 | 597.02 | 61.57 | 80
169 | ALIPURDUAR | SM/11992 | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/013062 | 40036737 | New | MVS | GO2223006897PH | 01/09/2022 | 235.67 | 34.12 | 269.79 | Alipurduar Division | Northern Mechanical Division II | 96.88 | 11.07 | 1.34 | 0 | 109.28 | 82.11 | 2.62 | 1.34 | 0 | 86.07 | 31.9 | 71
170 | ALIPURDUAR | SM/13247 | PRODHANPARA PIPED WATER SUPPLY SCHEME | TSM/014597 | 40036842 | New | MVS | GO2223008741PH | 14/10/2022 | 575.75 | 62.39 | 638.14 | Alipurduar Division | Northern Mechanical Division II | 169.6 | 25.34 | 8.33 | 0 | 203.28 | 169.6 | 3.96 | 8.33 | 0 | 181.9 | 28.5 | 28
171 | ALIPURDUAR | SM/10637 | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | TSM/010851 | 40012889 | Augmentation | SVS | GO2223000476PH | 21/04/2022 | 252.1 | 0 | 252.1 | Alipurduar Division | Northern Mechanical Division II | 124.4 | 0 | 0 | 0 | 124.4 | 124.4 | 0 | 0 | 0 | 124.4 | 49.35 | 93
172 | ALIPURDUAR | SM/13301 | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | TSM/015363 | 40037145 | New | MVS | GO2223008814PH | 17/10/2022 | 812.11 | 63.55 | 875.66 | Alipurduar Division | Northern Mechanical Division II | 307.85 | 14.84 | 46.27 | 0 | 368.96 | 264.47 | 2.82 | 46.27 | 0 | 313.55 | 35.81 | 56
173 | ALIPURDUAR | SM/13243 | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | TSM/015658 | 40037447 | New | MVS | GO2223008734PH | 14/10/2022 | 900.24 | 63.36 | 963.61 | Alipurduar Division | Northern Mechanical Division II | 330.56 | 23.2 | 23.33 | 0 | 377.08 | 330.56 | 2.82 | 23.33 | 0 | 356.7 | 37.02 | 61
174 | ALIPURDUAR | SM/18157 | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | TSM/020697 | 40066320 | New | SVS | GO2223017907PH | 29/03/2023 | 319.44 | 40.71 | 360.16 | Alipurduar Division | Northern Mechanical Division II | 75.23 | 9.93 | 0 | 0 | 85.16 | 75.23 | 0 | 0 | 0 | 75.23 | 20.89 | 38
175 | ALIPURDUAR | SM/16537 | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | TSM/015628 | 40037398 | New | MVS | GO2223015521PH | 10/03/2023 | 1198.09 | 63.29 | 1261.38 | Alipurduar Division | Northern Mechanical Division II | 266.57 | 17.42 | 25.28 | 0 | 309.28 | 266.57 | 2.41 | 25.28 | 0 | 294.27 | 23.33 | 53
176 | ALIPURDUAR | SM/14093 | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017485 | 40037671 | New | MVS | GO2223010869PH | 12/12/2022 | 464.03 | 64.69 | 528.73 | Alipurduar Division | Northern Mechanical Division II | 164.47 | 7.85 | 12.83 | 0 | 185.15 | 164.47 | 4.08 | 12.83 | 0 | 181.38 | 34.31 | 76
177 | ALIPURDUAR | SM/14213 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/015966 | 40037066 | New | SVS | GO2223011819PH | 10/01/2023 | 611.81 | 129.17 | 740.97 | Alipurduar Division | Northern Mechanical Division II | 2.36 | 24.16 | 9.73 | 0 | 36.25 | 2.36 | 0 | 9.73 | 0 | 12.09 | 1.63 | 16
178 | ALIPURDUAR | SM/12114 | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/012048 | 40037056 | New | MVS | GO2223006991PH | 02/09/2022 | 531.84 | 56.42 | 588.27 | Alipurduar Division | Northern Mechanical Division II | 207.61 | 33.73 | 53.7 | 0 | 295.04 | 207.61 | 3.93 | 41.4 | 0 | 252.94 | 43 | 66
179 | ALIPURDUAR | SM/09890 | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' | TSM/009017 | 40008916 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 27 | 18.21 | 45.21 | Alipurduar Division | Northern Mechanical Division II | 10.18 | 10.73 | 0 | 0 | 20.92 | 10.18 | 10.73 | 0 | 0 | 20.92 | 46.26 | 95
180 | ALIPURDUAR | SM/09891 | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | TSM/008995 | 40009061 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 29.28 | 18.21 | 47.49 | Alipurduar Division | Northern Mechanical Division II | 25.28 | 10.36 | 0 | 0 | 35.64 | 10.74 | 6.92 | 0 | 0 | 17.67 | 37.2 | 90
181 | ALIPURDUAR | SM/09903 | REJUVENATION OF 'CHOTO SALKUMAR WATER SUPPLY SCHEME' | TSM/009007 | 40020252 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 27.01 | 18.21 | 45.22 | Alipurduar Division | Northern Mechanical Division II | 24 | 14.24 | 0 | 0 | 38.24 | 18.34 | 7.93 | 0 | 0 | 26.27 | 58.1 | 63
182 | ALIPURDUAR | SM/09905 | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | TSM/009029 | 40010749 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 27.3 | 18.21 | 45.51 | Alipurduar Division | Northern Mechanical Division II | 0 | 11 | 0 | 0 | 11 | 0 | 9.21 | 0 | 0 | 9.21 | 20.24 | 99
183 | ALIPURDUAR | SM/09900 | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' | TSM/009028 | 40020190 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 27.02 | 18.21 | 45.23 | Alipurduar Division | Northern Mechanical Division II | 0 | 2.97 | 0 | 0 | 2.97 | 0 | 2.87 | 0 | 0 | 2.87 | 6.36 | 5
184 | ALIPURDUAR | SM/09893 | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | TSM/008982 | 40010856 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 27.01 | 18.21 | 45.22 | Alipurduar Division | Northern Mechanical Division II | 20.16 | 10.1 | 0 | 0 | 30.26 | 20.16 | 10.1 | 0 | 0 | 30.26 | 66.91 | 52
185 | ALIPURDUAR | SM/09908 | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | TSM/008999 | 40010112 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 28.09 | 18.21 | 46.31 | Alipurduar Division | Northern Mechanical Division II | 23.4 | 6.04 | 0 | 0 | 29.45 | 23.4 | 6.04 | 0 | 0 | 29.45 | 63.59 | 59
186 | ALIPURDUAR | SM/09897 | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | TSM/009034 | 40010108 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 27.26 | 18.21 | 45.48 | Alipurduar Division | Northern Mechanical Division II | 26.72 | 11.64 | 0 | 0 | 38.35 | 26.18 | 11.64 | 0 | 0 | 37.82 | 83.15 | 59
187 | ALIPURDUAR | SM/09896 | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | TSM/008979 | 40008919 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 27.01 | 18.21 | 45.23 | Alipurduar Division | Northern Mechanical Division II | 0 | 15.77 | 0 | 0 | 15.77 | 0 | 15.77 | 0 | 0 | 15.77 | 34.87 | 89
188 | ALIPURDUAR | SM/09904 | Rejuvenation Of Dima T.G. W.S.S | TSM/008975 | 40020100 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 26.3 | 18.21 | 44.51 | Alipurduar Division | Northern Mechanical Division II | 14.26 | 2.67 | 0 | 0 | 16.93 | 11.32 | 2.19 | 0 | 0 | 13.51 | 30.36 | 39
189 | ALIPURDUAR | SM/09906 | Rejuvenation of Gargenda Tea Garden Water Supply Scheme | TSM/008964 | 40008918 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 27.01 | 18.21 | 45.22 | Alipurduar Division | Northern Mechanical Division II | 0 | 14.94 | 0 | 0 | 14.94 | 0 | 14.4 | 0 | 0 | 14.4 | 31.84 | 87
190 | ALIPURDUAR | SM/09901 | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | TSM/009031 | 40020254 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 26.03 | 18.21 | 44.25 | Alipurduar Division | Northern Mechanical Division II | 15.7 | 15.77 | 0 | 0 | 31.47 | 15.7 | 15.77 | 0 | 0 | 31.47 | 71.12 | 89
191 | ALIPURDUAR | SM/09887 | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | TSM/009039 | 40020272 | Augmentation | MVS | GO2122006589PH | 08/12/2021 | 56.07 | 36.43 | 92.5 | Alipurduar Division | Northern Mechanical Division II | 5.1 | 28.88 | 13.8 | 0 | 47.79 | 5.1 | 26.03 | 13.8 | 0 | 44.93 | 48.57 | 92
192 | ALIPURDUAR | SM/09898 | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME' | TSM/009030 | 40020253 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 29.26 | 18.21 | 47.48 | Alipurduar Division | Northern Mechanical Division II | 27.47 | 15 | 0 | 0 | 42.47 | 23.71 | 15 | 0 | 0 | 38.71 | 81.54 | 67
193 | ALIPURDUAR | SM/09909 | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | TSM/009041 | 40020101 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 27.25 | 18.21 | 45.46 | Alipurduar Division | Northern Mechanical Division II | 21.06 | 17.31 | 0 | 0 | 38.37 | 21.06 | 13.84 | 0 | 0 | 34.91 | 76.78 | 61
194 | ALIPURDUAR | SM/09886 | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | TSM/009071 | 40006132 | Augmentation | MVS | GO2122006589PH | 08/12/2021 | 239.6 | 18.21 | 257.81 | Alipurduar Division | Northern Mechanical Division II | 235.89 | 10.96 | 0 | 0 | 246.85 | 233.43 | 10.96 | 0 | 0 | 244.39 | 94.79 | 98
195 | ALIPURDUAR | SM/09895 | Rejuvenation of Makrapara TG WSS. | TSM/008906 | 40010681 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 27.01 | 18.21 | 45.22 | Alipurduar Division | Northern Mechanical Division II | 26.22 | 16.59 | 0 | 0 | 42.81 | 26.22 | 16.05 | 0 | 0 | 42.27 | 93.47 | 73
196 | ALIPURDUAR | SM/09894 | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | TSM/009036 | 40010700 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 25.79 | 18.21 | 44.01 | Alipurduar Division | Northern Mechanical Division II | 13.85 | 13.41 | 0 | 0 | 27.25 | 4 | 4.86 | 0 | 0 | 8.86 | 20.13 | 57
197 | ALIPURDUAR | SM/09910 | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | TSM/009033 | 40020186 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 29.24 | 18.21 | 47.45 | Alipurduar Division | Northern Mechanical Division II | 20.67 | 2.39 | 0 | 0 | 23.06 | 20.67 | 2.39 | 0 | 0 | 23.06 | 48.6 | 95
198 | ALIPURDUAR | SM/09907 | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME | TSM/008978 | 40008913 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 26.53 | 18.21 | 44.74 | Alipurduar Division | Northern Mechanical Division II | 0 | 2.12 | 0 | 0 | 2.12 | 0 | 2.39 | 0 | 0 | 2.39 | 5.35 | 99
199 | ALIPURDUAR | SM/16115 | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME | TSM/018098 | 0 | Augmentation | MVS | GO2223014614PH | 22/02/2023 | 240.25 | 0 | 240.25 | Alipurduar Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58
200 | ALIPURDUAR | SM/10155 | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | TSM/009619 | 40004533 | Augmentation | SVS | GO2122009655PH | 11/02/2022 | 140.66 | 0 | 140.66 | Alipurduar Division | Northern Mechanical Division II | 136.56 | 0 | 0 | 0 | 136.56 | 136.56 | 0 | 0 | 0 | 136.56 | 97.09 | 94
201 | ALIPURDUAR | SM/10170 | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | TSM/009620 | 40004527 | Augmentation | SVS | GO2122009752PH | 16/02/2022 | 491.51 | 18.21 | 509.72 | Alipurduar Division | Northern Mechanical Division II | 292.98 | 0.87 | 28.27 | 0 | 322.12 | 278.45 | 0.87 | 28.27 | 0 | 307.59 | 60.35 | 93
202 | ALIPURDUAR | SM/09902 | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | TSM/009040 | 40010674 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 29.28 | 18.21 | 47.49 | Alipurduar Division | Northern Mechanical Division II | 19.74 | 8.05 | 0 | 0 | 27.8 | 19.74 | 0 | 0 | 0 | 19.74 | 41.57 | 53
203 | ALIPURDUAR | SM/09892 | REJUVINATION OF 'CHANDIRJHAR WATER SUPPLY SCHEME' | TSM/009038 | 40009072 | Augmentation | MVS | GO2122006590PH | 08/12/2021 | 29.27 | 18.21 | 47.49 | Alipurduar Division | Northern Mechanical Division II | 21.55 | 12.88 | 0 | 0 | 34.43 | 19.95 | 11.08 | 0 | 0 | 31.03 | 65.34 | 99
204 | ALIPURDUAR | SM/09888 | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | TSM/009035 | 40020258 | Augmentation | SVS | GO2122006589PH | 08/12/2021 | 25.65 | 18.21 | 43.87 | Alipurduar Division | Northern Mechanical Division II | 17.04 | 11.5 | 0 | 0 | 28.53 | 17.04 | 1.31 | 0 | 0 | 18.35 | 41.82 | 62
205 | ALIPURDUAR | SM/09899 | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | TSM/009037 | 40019782 | Augmentation | SVS | GO2122006590PH | 08/12/2021 | 27.06 | 18.21 | 45.28 | Alipurduar Division | Northern Mechanical Division II | 19.24 | 16.77 | 0 | 0 | 36.01 | 17.8 | 16.77 | 0 | 0 | 34.57 | 76.35 | 98
206 | ALIPURDUAR | SM/11485 | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | TSM/010925 | 40021363 | New | SVS | GO2223005062PH | 14/07/2022 | 352.3 | 37.61 | 389.92 | Alipurduar Division | Northern Mechanical Division II | 191.25 | 23.91 | 20.16 | 0 | 235.31 | 191.25 | 13.25 | 20.16 | 0 | 224.65 | 57.61 | 78
207 | ALIPURDUAR | SM/11709 | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/011590 | 40023432 | New | MVS | GO2223005730PH | 29/07/2022 | 777.75 | 39.69 | 817.44 | Alipurduar Division | Northern Mechanical Division II | 574.4 | 21.58 | 10.47 | 0 | 606.44 | 574.38 | 1.62 | 10.47 | 0 | 586.47 | 71.74 | 90
208 | ALIPURDUAR | SM/10175 | SIDHABARI PIED WATER SUPPLY SCHEME | TSM/009544 | 40005092 | New | MVS | GO2122009750PH | 16/02/2022 | 322.71 | 37.61 | 360.32 | Alipurduar Division | Northern Mechanical Division II | 272.46 | 11.03 | 17.96 | 0 | 301.46 | 272.46 | 11.03 | 17.96 | 0 | 301.46 | 83.66 | 60
209 | ALIPURDUAR | SM/12753 | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | TSM/014605 | 40037789 | New | MVS | GO2223007993PH | 20/09/2022 | 715.78 | 82.01 | 797.79 | Alipurduar Division | Northern Mechanical Division II | 251.2 | 22.88 | 64.72 | 0 | 338.79 | 251.2 | 22.88 | 64.72 | 0 | 338.79 | 42.47 | 62
210 | ALIPURDUAR | SM/10054 | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | TSM/006526 | 40062567 | New | SVS | GO2122008728PH | 25/01/2022 | 332.16 | 0 | 332.16 | Alipurduar Division | Northern Mechanical Division II | 15.33 | 46.95 | 0 | 0 | 62.28 | 15.33 | 0 | 0 | 0 | 15.33 | 4.62 | 5
211 | ALIPURDUAR | SM/08580 | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | TSM/006524 | 40017906 | New | SVS | GO2021006847PH | 10/02/2021 | 226.52 | 69.45 | 295.97 | Alipurduar Division | Northern Mechanical Division II | 111.78 | 40.11 | 0 | 0 | 151.9 | 104.94 | 38.78 | 0 | 0 | 143.72 | 48.56 | 100
212 | ALIPURDUAR | SM/16822 | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/017771 | 40049275 | New | SVS | GO2223015804PH | 13/03/2023 | 502.52 | 67.13 | 569.65 | Alipurduar Division | Northern Mechanical Division II | 4.67 | 0 | 44.98 | 0 | 49.65 | 4.67 | 0 | 44.98 | 0 | 49.65 | 8.72 | 18
213 | ALIPURDUAR | SM/13303 | TELIPARA PIPED WATER SUPPLY SCHEME. | TSM/015706 | 40037504 | New | MVS | GO2223008810PH | 17/10/2022 | 424.98 | 63.16 | 488.14 | Alipurduar Division | Northern Mechanical Division II | 108.36 | 2.41 | 12.62 | 0 | 123.39 | 108.36 | 2.41 | 12.62 | 0 | 123.39 | 25.28 | 52
214 | ALIPURDUAR | SM/14220 | TORSHA FOREST PIPED WATER SUPPLY SCHEME | TSM/015971 | 40037619 | New | MVS | GO2223011822PH | 10/01/2023 | 97.94 | 44.2 | 142.14 | Alipurduar Division | Northern Mechanical Division II | 79.83 | 13.31 | 0 | 0 | 93.14 | 79.83 | 11.48 | 0 | 0 | 91.31 | 64.24 | 80
215 | ALIPURDUAR | SM/10039 | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | TSM/006525 | 40017092 | New | SVS | GO2122008403PH | 19/01/2022 | 284.23 | 0 | 284.23 | Alipurduar Division |  | 255.6 | 0 | 0 | 0 | 255.6 | 255.6 | 0 | 0 | 0 | 255.6 | 89.93 | 98
216 | ALIPURDUAR | SM/14219 | TURTURI PIPED WATER SUPPLY SCHEME. | TSM/016016 | 40037564 | New | MVS | GO2223011805PH | 10/01/2023 | 884.64 | 63.44 | 948.08 | Alipurduar Division | Northern Mechanical Division II | 272.01 | 25.17 | 26.38 | 0 | 323.55 | 272.01 | 2.97 | 26.38 | 0 | 301.35 | 31.79 | 57
217 | ALIPURDUAR | SM/16114 | UMACHARANPUR PIPED WATER SUPPLY SCHEME | TSM/017944 | 40046820 | New | MVS | GO2223014616PH | 22/02/2023 | 878.82 | 71.25 | 950.07 | Alipurduar Division | Northern Mechanical Division II | 89.91 | 12.04 | 18.81 | 0 | 120.76 | 89.91 | 0 | 18.81 | 0 | 108.72 | 11.44 | 15
218 | ALIPURDUAR | SM/15914 | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | TSM/017679 | 40065481 | New | SVS | GO2223014589PH | 22/02/2023 | 291.27 | 66.97 | 358.24 | Alipurduar Division | Northern Mechanical Division II | 15 | 0 | 11.78 | 0 | 26.78 | 15 | 0 | 11.78 | 0 | 26.78 | 7.48 | 9
219 | ALIPURDUAR | SM/16817 | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | TSM/018017 | 40049274 | New | MVS | GO2223015817PH | 13/03/2023 | 736.95 | 71.54 | 808.5 | Alipurduar Division | Northern Mechanical Division II | 279.25 | 14.43 | 0 | 0 | 293.68 | 279.25 | 0 | 0 | 0 | 279.25 | 34.54 | 28
220 | ALIPURDUAR | SM/18154 | Uttar Dhalkar Piped Water Supply Scheme | TSM/020698 | 40066310 | New | SVS | GO2223017910PH | 29/03/2023 | 363.42 | 40.71 | 404.14 | Alipurduar Division | Northern Mechanical Division II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
221 | ALIPURDUAR | SM/16538 | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | TSM/014886 | 40037510 | New | MVS | GO2223015520PH | 10/03/2023 | 1011.51 | 63.17 | 1074.69 | Alipurduar Division | Northern Mechanical Division II | 384.2 | 12.78 | 18.86 | 0 | 415.84 | 384.2 | 6.58 | 18.86 | 0 | 409.64 | 38.12 | 66
222 | ALIPURDUAR | SM/16539 | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | TSM/014602 | 40036877 | New | MVS | GO2223015522PH | 10/03/2023 | 1013.2 | 108.44 | 1121.63 | Alipurduar Division | Northern Mechanical Division II | 301.17 | 17.34 | 25.95 | 0 | 344.46 | 301.17 | 0 | 25.95 | 0 | 327.12 | 29.16 | 64
223 | ALIPURDUAR | SM/14222 | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | TSM/015961 | 40037655 | New | MVS | GO2223011816PH | 10/01/2023 | 367.31 | 62.4 | 429.71 | Alipurduar Division | Northern Mechanical Division II | 97.76 | 13.44 | 4.48 | 0 | 115.69 | 97.76 | 13.44 | 0 | 0 | 111.21 | 25.88 | 37
Total | [9 empty] | 81991.16 | 7675.91 | 89667.07 |  |  | 34018.59 | 2281.81 | 2744 | 0 | 39044.41 | 33515.53 | 998.74 | 2626.27 | 0 | 37140.53 | 41.42