## JJM Schemes Financial Status (K
JJM Schemes Financial Status (KALIMPONG) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | KALIMPONG | SM/15463 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | TSM/015692 | 40034830 | New | SVS | GO2223013212PH | 04/02/2023 | 226.88 | 0 | 226.88 | Neorakhola W/S Mnt. Division |  | 174.65 | 0 | 2.03 | 0 | 176.68 | 174.65 | 0 | 2.03 | 0 | 176.68 | 77.87 | 85
2 | KALIMPONG | SM/18322 | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | TSM/012509 | 40035873 | New | SVS | 1684/PHE-28011/197/2022-ESTT CELL-Dept. of PHE | 27/06/2023 | 1040.03 | 0 | 1040.03 | Neorakhola W/S Mnt. Division |  | 0.79 | 0 | 6.36 | 0 | 7.15 | 0.79 | 0 | 6.36 | 0 | 7.15 | 0.69 | 10
3 | KALIMPONG | SM/14170 | PANKHASARI KHASMAHAL PWSS | TSM/014359 | 40035830 | New | SVS | GO2223011644PH | 09/01/2023 | 1201.07 | 0 | 1201.07 | Neorakhola W/S Mnt. Division |  | 980.9 | 0 | 4.1 | 0 | 985 | 980.9 | 0 | 4.1 | 0 | 985 | 82.01 | 50
4 | KALIMPONG | SM/11376 | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/010973 | 40018670 | New | MVS | GO2223004632PH | 04/07/2022 | 191.02 | 0 | 191.02 | Neorakhola W/S Mnt. Division |  | 110.75 | 0 | 0 | 0 | 110.75 | 110.75 | 0 | 0 | 0 | 110.75 | 57.98
5 | KALIMPONG | SM/11377 | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/010972 | 40035329 | New | SVS | GO2223004633PH | 04/07/2022 | 89.16 | 0 | 89.16 | Neorakhola W/S Mnt. Division |  | 51.77 | 0 | 0 | 0 | 51.77 | 51.77 | 0 | 0 | 0 | 51.77 | 58.06 | 56
6 | KALIMPONG | SM/14171 | TODAY TANGTA KHASMAHAL PWSS | TSM/014294 | 40035839 | New | SVS | GO2223011645PH | 09/01/2023 | 1635.15 | 0 | 1635.15 | Neorakhola W/S Mnt. Division |  | 678.55 | 0 | 5.98 | 0 | 684.52 | 678.55 | 0 | 5.98 | 0 | 684.52 | 41.86 | 50
7 | KALIMPONG | SM/13610 | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/012753 | 40035418 | New | SVS | GO2223009611PH | 11/11/2022 | 260.67 | 0 | 260.67 | Kalimpong Division |  | 197.85 | 0 | 1.9 | 0 | 199.75 | 197.85 | 0 | 1.9 | 0 | 199.75 | 76.63 | 85
8 | KALIMPONG | SM/10705 | Augmentation of Lolaygoan Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission (JJM) under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009871 | 40014671 | Augmentation | MVS | GO2223001542PH | 12/05/2022 | 99.21 | 0 | 99.21 | Neorakhola W/S Mnt. Division |  | 67.31 | 0 | 0 | 0 | 67.31 | 67.31 | 0 | 0 | 0 | 67.31 | 67.84
9 | KALIMPONG | SM/10052 | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | TSM/008351 | 40008250 | Augmentation | SVS | GO2122008721PH | 25/01/2022 | 4402.74 | 0 | 4402.74 | Neorakhola W/S Mnt. Division |  | 787.17 | 0 | 0 | 0 | 787.17 | 787.17 | 0 | 0 | 0 | 787.17 | 17.88
10 | KALIMPONG | SM/18442 | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | TSM/020254 | 40065668 | Augmentation | MVS | 1931/PHE-28011/178/2023-SCHM CELL-Dept. of PHE | 18/07/2023 | 3858.84 | 0 | 3858.84 | Neorakhola W/S Mnt. Division |  | 472.55 | 0 | 0 | 0 | 472.55 | 472.55 | 0 | 0 | 0 | 472.55 | 12.25 | 15
11 | KALIMPONG | SM/13622 | BINDU PIPED WATER SUPPLY SCHEME | TSM/013475 | 40035865 | New | SVS | GO2223009628PH | 11/11/2022 | 130.17 | 0 | 130.17 | Kalimpong Division |  | 64.59 | 0 | 1.07 | 0 | 65.67 | 64.59 | 0 | 1.07 | 0 | 65.67 | 50.45 | 75
12 | KALIMPONG | SM/10729 | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | TSM/010520 | 40026806 | New | MVS | GO2223002061PH | 18/05/2022 | 136.35 | 0 | 136.35 | Neorakhola W/S Mnt. Division |  | 89.42 | 0 | 0 | 0 | 89.42 | 89.42 | 0 | 0 | 0 | 89.42 | 65.58 | 98
13 | KALIMPONG | SM/19112 | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | TSM/013403 | 40035669 | New | MVS | 3802/PHE-28011/219/2023-ESTT CELL-Dept. of PHE | 21/12/2023 | 1414.95 | 0 | 1414.95 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 4.82 | 0 | 4.82 | 0 | 0 | 4.82 | 0 | 4.82 | 0.34 | 100
14 | KALIMPONG | SM/11955 | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/012503 | 40033626 | New | SVS | GO2223006665PH | 24/08/2022 | 242.62 | 0 | 242.62 | Kalimpong Division |  | 156.13 | 0 | 0 | 0 | 156.13 | 156.13 | 0 | 0 | 0 | 156.13 | 64.35
15 | KALIMPONG | SM/11579 | DETAIL PROJECT REPORT OF LOWER DARA GAON AND UPPER & LOWER GAIRI GAON PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/011284 | 40033624 | New | SVS | GO2223005404PH | 22/07/2022 | 312.68 | 0 | 312.68 | Kalimpong Division |  | 248.74 | 0 | 0 | 0 | 248.74 | 248.74 | 0 | 0 | 0 | 248.74 | 79.55
16 | KALIMPONG | SM/15646 | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/011490 | 40034760 | New | SVS | GO2223014234PH | 20/02/2023 | 226.84 | 0 | 226.84 | Kalimpong Division |  | 98.59 | 0 | 1.05 | 0 | 99.64 | 98.59 | 0 | 1.05 | 0 | 99.64 | 43.93 | 96
17 | KALIMPONG | SM/11577 | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/011293 | 40046737 | New | SVS | GO2223005404PH | 22/07/2022 | 47.54 | 0 | 47.54 | Kalimpong Division |  | 18.08 | 0 | 0 | 0 | 18.08 | 18.08 | 0 | 0 | 0 | 18.08 | 38.04 | 60
18 | KALIMPONG | SM/11578 | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/011291 | 40033625 | New | SVS | GO2223005404PH | 22/07/2022 | 393.32 | 0 | 393.32 | Kalimpong Division |  | 297.56 | 0 | 0 | 0 | 297.56 | 297.56 | 0 | 0 | 0 | 297.56 | 75.65
19 | KALIMPONG | SM/10512 | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong | TSM/010474 | 40013796 | Retrofitting | MVS | GO2223000244PH | 13/04/2022 | 504.2 | 0 | 504.2 | Neorakhola W/S Mnt. Division |  | 409.33 | 0 | 0 | 0 | 409.33 | 409.03 | 0 | 0 | 0 | 409.03 | 81.12
20 | KALIMPONG | SM/14192 | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | TSM/011803 | 40035053 | New | SVS | GO2223011798PH | 10/01/2023 | 839.64 | 0 | 839.64 | Kalimpong Division |  | 442.44 | 0 | 4.25 | 0 | 446.69 | 442.44 | 0 | 4.25 | 0 | 446.69 | 53.2 | 100
21 | KALIMPONG | SM/14193 | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | TSM/011800 | 40035075 | New | SVS | GO2223011797PH | 10/01/2023 | 701.2 | 0 | 701.2 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 4.46 | 0 | 4.46 | 0 | 0 | 4.46 | 0 | 4.46 | 0.64
22 | KALIMPONG | SM/14194 | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | TSM/011692 | 40034622 | New | SVS | GO2223011795PH | 10/01/2023 | 747.62 | 0 | 747.62 | Neorakhola W/S Mnt. Division |  | 398.27 | 0 | 7.79 | 0 | 406.06 | 385.98 | 0 | 7.79 | 0 | 393.76 | 52.67
23 | KALIMPONG | SM/13606 | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG | TSM/011686 | 40033627 | New | SVS | GO2223009646PH | 11/11/2022 | 427.72 | 0 | 427.72 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
24 | KALIMPONG | SM/13604 | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | TSM/011801 | 40035113 | New | SVS | GO2223009648PH | 11/11/2022 | 564.2 | 0 | 564.2 | Neorakhola W/S Mnt. Division |  | 494.08 | 0 | 12.5 | 0 | 506.59 | 494.08 | 0 | 12.5 | 0 | 506.59 | 89.79 | 60
25 | KALIMPONG | SM/10266 | Functional household tap connection under Jal Swapno Programme, 10 Nos. existing schemes to be provided with FHTC under GTA. | TSM/006999 | 40009346 | Retrofitting | MVS | GO2021006716PH | 09/02/2021 | 187.99 | 0 | 187.99 | Kalimpong Division |  | 154.24 | 0 | 10.9 | 0 | 165.14 | 152.87 | 0 | 10.9 | 0 | 163.77 | 87.11
26 | KALIMPONG | SM/10265 | Functional household tap connection under Jal Swapno Programme, 14 Nos. existing schemes to be provided with FHTC under GTA. | TSM/006998 | 40009349 | Retrofitting | MVS | GO2021006715PH | 09/02/2021 | 228.22 | 0 | 228.22 | Kalimpong Division |  | 190.04 | 0 | 9.09 | 0 | 199.13 | 190.04 | 0 | 9.09 | 0 | 199.13 | 87.25
27 | KALIMPONG | SM/10267 | Functional household tap connection under Jal Swapno Programme, 8 Nos. existing schemes to be provided with FHTC under GTA. | TSM/007000 | 6260772 | Retrofitting | MVS | GO2021006717PH | 09/02/2021 | 127.68 | 0 | 127.68 | Kalimpong Division |  | 109.97 | 0 | 6.87 | 0 | 116.84 | 109.97 | 0 | 6.87 | 0 | 116.84 | 91.51 | 72
28 | KALIMPONG | SM/13608 | GODAK BUSTY PIPED WATER SUPPLY SCHEME. | TSM/011867 | 40035371 | New | SVS | GO2223009615PH | 11/11/2022 | 356.95 | 0 | 356.95 | Neorakhola W/S Mnt. Division |  | 165.11 | 0 | 0 | 0 | 165.11 | 165.11 | 0 | 0 | 0 | 165.11 | 46.26 | 50
29 | KALIMPONG | SM/14172 | GORUBATHAN-I PWSS | TSM/014336 | 40035766 | New | MVS | GO2223011643PH | 09/01/2023 | 1146.86 | 0 | 1146.86 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 11.19 | 0 | 11.19 | 0 | 0 | 11.19 | 0 | 11.19 | 0.98 | 20
30 | KALIMPONG | SM/13605 | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | TSM/012583 | 40035345 | New | SVS | GO2223009643PH | 11/11/2022 | 419.43 | 0 | 419.43 | Neorakhola W/S Mnt. Division |  | 56.82 | 0 | 6.1 | 0 | 62.92 | 56.82 | 0 | 6.1 | 0 | 62.92 | 15 | 80
31 | KALIMPONG | SM/16233 | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017375 | 40055759 | New | SVS | GO2223014854PH | 24/02/2023 | 963.91 | 0 | 963.91 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 3.98 | 0 | 3.98 | 0 | 0 | 3.98 | 0 | 3.98 | 0.41
32 | KALIMPONG | SM/16649 | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017321 | 40055839 | New | SVS | GO2223015965PH | 14/03/2023 | 437.66 | 0 | 437.66 | Neorakhola W/S Mnt. Division |  | 1.46 | 0 | 1.95 | 0 | 3.41 | 1.46 | 0 | 1.95 | 0 | 3.41 | 0.78 | 50
33 | KALIMPONG | SM/10575 | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009884 | 40015046 | New | SVS | GO2223000349PH | 18/04/2022 | 49.33 | 0 | 49.33 | Neorakhola W/S Mnt. Division |  | 28.68 | 0 | 0 | 0 | 28.68 | 28.68 | 0 | 0 | 0 | 28.68 | 58.14 | 90
34 | KALIMPONG | SM/10562 | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009883 | 40034016 | New | MVS | GO2223000379PH | 18/04/2022 | 132.05 | 0 | 132.05 | Neorakhola W/S Mnt. Division |  | 106.04 | 0 | 0 | 0 | 106.04 | 106.04 | 0 | 0 | 0 | 106.04 | 80.31 | 95
35 | KALIMPONG | SM/10599 | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009885 | 40033287 | New | SVS | GO2223000363PH | 18/04/2022 | 67.06 | 0 | 67.06 | Neorakhola W/S Mnt. Division |  | 52.65 | 0 | 0 | 0 | 52.65 | 52.65 | 0 | 0 | 0 | 52.65 | 78.51 | 95
36 | KALIMPONG | SM/10601 | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009877 | 40015044 | New | SVS | GO2223000386PH | 18/04/2022 | 9.66 | 0 | 9.66 | Neorakhola W/S Mnt. Division |  | 8.69 | 0 | 0 | 0 | 8.69 | 8.69 | 0 | 0 | 0 | 8.69 | 89.99 | 95
37 | KALIMPONG | SM/10624 | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009876 | 40014685 | New | SVS | GO2223000441PH | 20/04/2022 | 40.13 | 0 | 40.13 | Neorakhola W/S Mnt. Division |  | 38.03 | 0 | 0 | 0 | 38.03 | 38.03 | 0 | 0 | 0 | 38.03 | 94.78 | 95
38 | KALIMPONG | SM/16235 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | TSM/017340 | 40055830 | New | SVS | GO2223014852PH | 24/02/2023 | 233.82 | 0 | 233.82 | Neorakhola W/S Mnt. Division |  | 69.36 | 0 | 1.22 | 0 | 70.57 | 69.36 | 0 | 1.22 | 0 | 70.57 | 30.18 | 50
39 | KALIMPONG | SM/10623 | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009886 | 40015040 | New | SVS | GO2223000439PH | 20/04/2022 | 41.4 | 0 | 41.4 | Neorakhola W/S Mnt. Division |  | 33.46 | 0 | 0 | 0 | 33.46 | 33.46 | 0 | 0 | 0 | 33.46 | 80.83 | 95
40 | KALIMPONG | SM/15042 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017393 | 40034817 | New | SVS | GO2223013207PH | 04/02/2023 | 213.24 | 0 | 213.24 | Neorakhola W/S Mnt. Division |  | 94.23 | 0 | 1.98 | 0 | 96.21 | 94.23 | 0 | 1.98 | 0 | 96.21 | 45.12 | 50
41 | KALIMPONG | SM/10739 | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009879 | 40019298 | New | SVS | GO2223002402PH | 20/05/2022 | 5.37 | 0 | 5.37 | Neorakhola W/S Mnt. Division |  | 4.77 | 0 | 0 | 0 | 4.77 | 4.77 | 0 | 0 | 0 | 4.77 | 88.7 | 95
42 | KALIMPONG | SM/16234 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017366 | 40055769 | New | SVS | GO2223014850PH | 24/02/2023 | 55.28 | 0 | 55.28 | Neorakhola W/S Mnt. Division |  | 2.71 | 0 | 0 | 0 | 2.71 | 2.71 | 0 | 0 | 0 | 2.71 | 4.91 | 10
43 | KALIMPONG | SM/10603 | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009878 | 40026804 | New | SVS | GO2223000366PH | 18/04/2022 | 41.32 | 0 | 41.32 | Neorakhola W/S Mnt. Division |  | 37.19 | 0 | 0 | 0 | 37.19 | 37.19 | 0 | 0 | 0 | 37.19 | 90 | 95
44 | KALIMPONG | SM/10625 | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009880 | 40015247 | New | SVS | GO2223000446PH | 20/04/2022 | 49.5 | 0 | 49.5 | Neorakhola W/S Mnt. Division |  | 42.76 | 0 | 0 | 0 | 42.76 | 42.76 | 0 | 0 | 0 | 42.76 | 86.38 | 90
45 | KALIMPONG | SM/10576 | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009881 | 40034014 | New | SVS | GO2223000373PH | 18/04/2022 | 49.14 | 0 | 49.14 | Neorakhola W/S Mnt. Division |  | 30.78 | 0 | 0 | 0 | 30.78 | 30.78 | 0 | 0 | 0 | 30.78 | 62.63 | 50
46 | KALIMPONG | SM/10563 | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009887 | 40015047 | New | SVS | GO2223000342PH | 18/04/2022 | 62.89 | 0 | 62.89 | Neorakhola W/S Mnt. Division |  | 44.12 | 0 | 0 | 0 | 44.12 | 44.12 | 0 | 0 | 0 | 44.12 | 70.15 | 98
47 | KALIMPONG | SM/16513 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | TSM/017496 | 40055654 | New | SVS | GO2223015208PH | 03/03/2023 | 304 | 0 | 304 | Kalimpong Division |  | 87.62 | 0 | 2.27 | 0 | 89.89 | 87.62 | 0 | 2.27 | 0 | 89.89 | 29.57
48 | KALIMPONG | SM/10602 | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009875 | 40033289 | New | SVS | GO2223000367PH | 18/04/2022 | 25.25 | 0 | 25.25 | Neorakhola W/S Mnt. Division |  | 10.13 | 0 | 0 | 0 | 10.13 | 10.13 | 0 | 0 | 0 | 10.13 | 40.12 | 95
49 | KALIMPONG | SM/10600 | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | TSM/009882 | 40026805 | New | SVS | GO2223000368PH | 18/04/2022 | 10.62 | 0 | 10.62 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95
50 | KALIMPONG | SM/16512 | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017497 | 40055641 | New | SVS | GO2223015206PH | 03/03/2023 | 160.61 | 0 | 160.61 | Neorakhola W/S Mnt. Division |  | 1.54 | 0 | 0.84 | 0 | 2.38 | 1.54 | 0 | 0.84 | 0 | 2.38 | 1.48
51 | KALIMPONG | SM/12180 | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT | TSM/012581 | 40033603 | New | SVS | GO2223007208PH | 07/09/2022 | 520.75 | 0 | 520.75 | Kalimpong Division |  | 372.38 | 0 | 0 | 0 | 372.38 | 372.38 | 0 | 0 | 0 | 372.38 | 71.51
52 | KALIMPONG | SM/12181 | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK | TSM/012042 | 40033602 | New | SVS | GO2223007219PH | 07/09/2022 | 695.67 | 0 | 695.67 | Kalimpong Division |  | 367.45 | 0 | 0 | 0 | 367.45 | 367.45 | 0 | 0 | 0 | 367.45 | 52.82
53 | KALIMPONG | SM/16231 | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG | TSM/017437 | 40055709 | New | SVS | GO2223014849PH | 24/02/2023 | 944.04 | 0 | 944.04 | Kalimpong Division |  | 474.49 | 0 | 7.2 | 0 | 481.69 | 474.49 | 0 | 7.2 | 0 | 481.69 | 51.02
54 | KALIMPONG | SM/16230 | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG | TSM/017451 | 40065183 | New | SVS | GO2223014851PH | 24/02/2023 | 921.36 | 0 | 921.36 | Neorakhola W/S Mnt. Division |  | 664.52 | 0 | 6.58 | 0 | 671.1 | 664.52 | 0 | 6.58 | 0 | 671.1 | 72.84 | 70
55 | KALIMPONG | SM/15554 | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | TSM/016058 | 40059507 | New | MVS | GO2223013872PH | 15/02/2023 | 229.73 | 18.83 | 248.56 | Kalimpong Division |  | 108.88 | 0 | 0.86 | 0 | 109.74 | 108.88 | 0 | 0.86 | 0 | 109.74 | 44.15
56 | KALIMPONG | SM/13612 | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | TSM/011843 | 40035815 | New | SVS | GO2223009613PH | 11/11/2022 | 290.97 | 0 | 290.97 | Neorakhola W/S Mnt. Division |  | 115.41 | 0 | 1.5 | 0 | 116.92 | 115.41 | 0 | 1.5 | 0 | 116.92 | 40.18 | 10
57 | KALIMPONG | SM/15937 | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS | TSM/015530 | 40034782 | New | MVS | GO2223014617PH | 22/02/2023 | 657.46 | 0 | 657.46 | Kalimpong Division |  | 480.99 | 0 | 4.82 | 0 | 485.81 | 480.99 | 0 | 4.82 | 0 | 485.81 | 73.89 | 75
58 | KALIMPONG | SM/16511 | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG | TSM/017521 | 40055626 | New | SVS | GO2223015207PH | 03/03/2023 | 964.71 | 0 | 964.71 | Neorakhola W/S Mnt. Division |  | 272.24 | 0 | 6.24 | 0 | 278.48 | 272.24 | 0 | 6.24 | 0 | 278.48 | 28.87 | 70
59 | KALIMPONG | SM/13603 | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | TSM/012584 | 40035339 | New | SVS | GO2223009644PH | 11/11/2022 | 315.49 | 26.17 | 341.66 | Kalimpong Division |  | 202.04 | 0 | 4.09 | 0 | 206.13 | 202.04 | 0 | 4.09 | 0 | 206.13 | 60.33
60 | KALIMPONG | SM/13602 | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | TSM/012582 | 40035361 | New | SVS | GO2223009624PH | 11/11/2022 | 309.32 | 26.17 | 335.49 | Kalimpong Division |  | 187.52 | 0 | 5.48 | 0 | 193 | 187.52 | 0 | 5.48 | 0 | 193 | 57.53 | 75
61 | KALIMPONG | SM/11806 | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. | TSM/010916 | 40034020 | New | MVS | GO2223006194PH | 10/08/2022 | 204.57 | 0 | 204.57 | Neorakhola W/S Mnt. Division |  | 138.48 | 0 | 0 | 0 | 138.48 | 138.48 | 0 | 0 | 0 | 138.48 | 67.69 | 65
62 | KALIMPONG | SM/10820 | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | TSM/010201 | 40033292 | New | SVS | GO2223003535PH | 25/05/2022 | 47.33 | 0 | 47.33 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 2.13 | 0 | 2.13 | 0 | 0 | 2.13 | 0 | 2.13 | 4.5
63 | KALIMPONG | SM/18415 | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | TSM/011586 | 40035661 | New | MVS | 1870/PHE-28011/13/2023-ESTT CELL-Dept. of PHE | 13/07/2023 | 1069.7 | 0 | 1069.7 | Neorakhola W/S Mnt. Division |  | 306.22 | 0 | 2.91 | 0 | 309.14 | 306.22 | 0 | 2.91 | 0 | 309.14 | 28.9 | 80
64 | KALIMPONG | SM/16854 | PAGRAN BONG KHASMAHAL PWSS | TSM/015516 | 40058705 | New | SVS | GO2223015666PH | 13/03/2023 | 473.77 | 0 | 473.77 | Neorakhola W/S Mnt. Division |  | 317.92 | 0 | 1.15 | 0 | 319.07 | 317.92 | 0 | 1.15 | 0 | 319.07 | 67.35
65 | KALIMPONG | SM/13609 | PAREN FOREST PIPED WATER SUPPLY SCHEME | TSM/011674 | 40035379 | New | SVS | GO2223009617PH | 11/11/2022 | 133.18 | 0 | 133.18 | Neorakhola W/S Mnt. Division |  | 74.13 | 0 | 0 | 0 | 74.13 | 74.13 | 0 | 0 | 0 | 74.13 | 55.67 | 95
66 | KALIMPONG | SM/18255 | PATEN GODAK KHASMAHAL PWSS | TSM/013333 | 40035775 | New | SVS | 1584/PHE-28011/14/2023-ESTT CELL-Dept. of PHE | 21/06/2023 | 1128.06 | 0 | 1128.06 | Neorakhola W/S Mnt. Division |  | 340.4 | 0 | 5.38 | 0 | 345.78 | 340.4 | 0 | 5.38 | 0 | 345.78 | 30.65 | 35
67 | KALIMPONG | SM/10703 | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009652 | 40024849 | New | SVS | GO2223001539PH | 12/05/2022 | 286.37 | 0 | 286.37 | Kalimpong Division |  | 252.26 | 0 | 0 | 0 | 252.26 | 252.26 | 0 | 0 | 0 | 252.26 | 88.09
68 | KALIMPONG | SM/10704 | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009661 | 40036776 | New | SVS | GO2223001540PH | 12/05/2022 | 338.99 | 0 | 338.99 | Kalimpong Division |  | 301.93 | 0 | 0 | 0 | 301.93 | 301.93 | 0 | 0 | 0 | 301.93 | 89.07
69 | KALIMPONG | SM/10699 | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009654 | 40036385 | New | SVS | GO2223001535PH | 12/05/2022 | 152.76 | 0 | 152.76 | Kalimpong Division |  | 64.76 | 0 | 0 | 0 | 64.76 | 64.76 | 0 | 0 | 0 | 64.76 | 42.4
70 | KALIMPONG | SM/10698 | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009664 | 40026779 | New | SVS | GO2223001534PH | 12/05/2022 | 206.41 | 0 | 206.41 | Kalimpong Division |  | 186.41 | 0 | 0 | 0 | 186.41 | 186.41 | 0 | 0 | 0 | 186.41 | 90.31
71 | KALIMPONG | SM/10702 | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009650 | 40026733 | New | SVS | GO2223001538PH | 12/05/2022 | 113.56 | 0 | 113.56 | Kalimpong Division |  | 79.21 | 0 | 0 | 0 | 79.21 | 79.21 | 0 | 0 | 0 | 79.21 | 69.75
72 | KALIMPONG | SM/10697 | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009665 | 40036181 | New | SVS | GO2223001533PH | 12/05/2022 | 126.09 | 0 | 126.09 | Kalimpong Division |  | 73.25 | 0 | 0 | 0 | 73.25 | 73.25 | 0 | 0 | 0 | 73.25 | 58.09
73 | KALIMPONG | SM/10700 | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009635 | 40036409 | New | SVS | GO2223001536PH | 12/05/2022 | 173.31 | 0 | 173.31 | Kalimpong Division |  | 136.83 | 0 | 0 | 0 | 136.83 | 136.83 | 0 | 0 | 0 | 136.83 | 78.95
74 | KALIMPONG | SM/10696 | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009667 | 40046501 | New | SVS | GO2223001532PH | 12/05/2022 | 115.09 | 0 | 115.09 | Kalimpong Division |  | 80.87 | 0 | 0 | 0 | 80.87 | 80.87 | 0 | 0 | 0 | 80.87 | 70.27
75 | KALIMPONG | SM/09544 | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. | TSM/008815 | 40013259 | New | SVS | GO2122005571PH | 19/11/2021 | 198.74 | 0 | 198.74 | Kalimpong Division |  | 185.74 | 0 | 0.8 | 0 | 186.54 | 185.65 | 0 | 0.8 | 0 | 186.45 | 93.82 | 95
76 | KALIMPONG | SM/09599 | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. | TSM/008820 | 40012942 | New | SVS | GO2122005748PH | 23/11/2021 | 312 | 0 | 312 | Neorakhola W/S Mnt. Division |  | 225.03 | 0 | 2.76 | 0 | 227.79 | 225.03 | 0 | 2.76 | 0 | 227.79 | 73.01 | 90
77 | KALIMPONG | SM/10695 | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009662 | 40034432 | New | SVS | GO2223001531PH | 12/05/2022 | 138.07 | 0 | 138.07 | Kalimpong Division |  | 111.81 | 0 | 0 | 0 | 111.81 | 111.81 | 0 | 0 | 0 | 111.81 | 80.98
78 | KALIMPONG | SM/10694 | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009630 | 40036437 | New | SVS | GO2223001529PH | 12/05/2022 | 94.15 | 0 | 94.15 | Kalimpong Division |  | 55.95 | 0 | 0 | 0 | 55.95 | 55.95 | 0 | 0 | 0 | 55.95 | 59.43
79 | KALIMPONG | SM/10701 | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009626 | 40036484 | New | SVS | GO2223001537PH | 12/05/2022 | 114.57 | 0 | 114.57 | Kalimpong Division |  | 81.26 | 0 | 0 | 0 | 81.26 | 81.26 | 0 | 0 | 0 | 81.26 | 70.92
80 | KALIMPONG | SM/09665 | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG | TSM/008822 | 40013080 | New | SVS | GO2122005833PH | 24/11/2021 | 142.76 | 0 | 142.76 | Kalimpong Division |  | 45.78 | 0 | 1.21 | 0 | 46.99 | 45.78 | 0 | 1.21 | 0 | 46.99 | 32.92
81 | KALIMPONG | SM/19176 | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | TSM/013034 | 40035853 | New | SVS | PHE-421/28011/111/2023-SCHM CELL-Dept. of PHE | 15/02/2024 | 2560.38 | 0 | 2560.38 | Neorakhola W/S Mnt. Division |  | 123.67 | 0 | 0 | 0 | 123.67 | 123.67 | 0 | 0 | 0 | 123.67 | 4.83 | 10
82 | KALIMPONG | SM/15641 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015694 | 40034664 | New | SVS | GO2223014246PH | 20/02/2023 | 214.02 | 0 | 214.02 | Kalimpong Division |  | 142.7 | 0 | 1.69 | 0 | 144.39 | 142.7 | 0 | 1.69 | 0 | 144.39 | 67.47 | 100
83 | KALIMPONG | SM/13615 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014817 | 40035392 | New | SVS | GO2223009632PH | 11/11/2022 | 101.26 | 0 | 101.26 | Neorakhola W/S Mnt. Division |  | 54.28 | 0 | 0.22 | 0 | 54.49 | 54.28 | 0 | 0.22 | 0 | 54.49 | 53.81 | 50
84 | KALIMPONG | SM/16514 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017347 | 40055779 | New | SVS | GO2223015209PH | 03/03/2023 | 896.34 | 0 | 896.34 | Neorakhola W/S Mnt. Division |  | 239.02 | 0 | 3.33 | 0 | 242.34 | 222.83 | 0 | 3.33 | 0 | 226.15 | 25.23
85 | KALIMPONG | SM/16232 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017434 | 40055719 | New | SVS | GO2223014853PH | 24/02/2023 | 380.82 | 0 | 380.82 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 1.23 | 0 | 1.23 | 0 | 0 | 1.23 | 0 | 1.23 | 0.32
86 | KALIMPONG | SM/13617 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014807 | 40035408 | New | SVS | GO2223009638PH | 11/11/2022 | 442.25 | 0 | 442.25 | Kalimpong Division |  | 303.81 | 0 | 1.48 | 0 | 305.29 | 303.81 | 0 | 1.48 | 0 | 305.29 | 69.03
87 | KALIMPONG | SM/13616 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014813 | 40035402 | New | SVS | GO2223009630PH | 11/11/2022 | 268.04 | 0 | 268.04 | Neorakhola W/S Mnt. Division |  | 121.62 | 0 | 0.76 | 0 | 122.38 | 120.47 | 0 | 0.76 | 0 | 121.23 | 45.23 | 15
88 | KALIMPONG | SM/15642 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015687 | 40034673 | New | SVS | GO2223014236PH | 20/02/2023 | 211.63 | 0 | 211.63 | Kalimpong Division |  | 109.11 | 0 | 96.35 | 0 | 205.46 | 109.11 | 0 | 96.35 | 0 | 205.46 | 97.09
89 | KALIMPONG | SM/13621 | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/014805 | 40035823 | New | SVS | GO2223009639PH | 11/11/2022 | 236.28 | 0 | 236.28 | Kalimpong Division |  | 108.73 | 0 | 0.76 | 0 | 109.49 | 108.73 | 0 | 0.76 | 0 | 109.49 | 46.34
90 | KALIMPONG | SM/18247 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015695 | 0 | New | SVS | 1558/PHE-28011/193/2023-SCHM CELL-Dept. of PHE | 16/06/2023 | 1350.54 | 0 | 1350.54 | Neorakhola W/S Mnt. Division |  | 0 | 0 | 4.38 | 0 | 4.38 | 0 | 0 | 4.38 | 0 | 4.38 | 0.32 | 40
91 | KALIMPONG | SM/15645 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | TSM/012818 | 40034746 | New | SVS | GO2223014242PH | 20/02/2023 | 882.78 | 90.63 | 973.41 | Kalimpong Division |  | 703.56 | 0 | 2.99 | 0 | 706.56 | 703.56 | 0 | 2.99 | 0 | 706.56 | 72.59 | 75
92 | KALIMPONG | SM/15644 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | TSM/012819 | 40034723 | New | SVS | GO2223014240PH | 20/02/2023 | 620.51 | 30.21 | 650.72 | Kalimpong Division |  | 1.71 | 0 | 3.31 | 0 | 5.03 | 1.71 | 0 | 3.31 | 0 | 5.03 | 0.77 | 60
93 | KALIMPONG | SM/12630 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/012505 | 40046743 | New | SVS | GO2223007848PH | 19/09/2022 | 939.41 | 0 | 939.41 | Kalimpong Division |  | 685.16 | 0 | 0 | 0 | 685.16 | 685.16 | 0 | 0 | 0 | 685.16 | 72.93 | 90
94 | KALIMPONG | SM/12629 | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/012504 | 40026332 | New | SVS | GO2223007849PH | 19/09/2022 | 752.8 | 0 | 752.8 | Kalimpong Division |  | 425.76 | 0 | 0 | 0 | 425.76 | 425.76 | 0 | 0 | 0 | 425.76 | 56.56 | 40
95 | KALIMPONG | SM/15643 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | TSM/013305 | 40034709 | New | SVS | GO2223014245PH | 20/02/2023 | 300.21 | 0 | 300.21 | Kalimpong Division |  | 48.06 | 0 | 1.04 | 0 | 49.11 | 48.06 | 0 | 1.04 | 0 | 49.11 | 16.36
96 | KALIMPONG | SM/15640 | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015717 | 40034644 | New | SVS | GO2223014238PH | 20/02/2023 | 497.43 | 0 | 497.43 | Kalimpong Division |  | 252.77 | 0 | 8.44 | 0 | 261.21 | 252.77 | 0 | 8.44 | 0 | 261.21 | 52.51
97 | KALIMPONG | SM/10791 | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010480 | 40033351 | New | SVS | GO2223003522PH | 25/05/2022 | 470.31 | 0 | 470.31 | Neorakhola W/S Mnt. Division |  | 351.96 | 0 | 0 | 0 | 351.96 | 351.96 | 0 | 0 | 0 | 351.96 | 74.84 | 85
98 | KALIMPONG | SM/10787 | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | TSM/010521 | 40029110 | New | SVS | GO2223003524PH | 25/05/2022 | 975.33 | 0 | 975.33 | Neorakhola W/S Mnt. Division |  | 876.02 | 0 | 0 | 0 | 876.02 | 876.02 | 0 | 0 | 0 | 876.02 | 89.82 | 95
99 | KALIMPONG | SM/10793 | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010482 | 40033376 | New | SVS | GO2223003520PH | 25/05/2022 | 731.44 | 0 | 731.44 | Neorakhola W/S Mnt. Division |  | 586.1 | 0 | 0 | 0 | 586.1 | 586.1 | 0 | 0 | 0 | 586.1 | 80.13 | 90
100 | KALIMPONG | SM/10792 | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010478 | 40033387 | New | SVS | GO2223003521PH | 25/05/2022 | 606.74 | 0 | 606.74 | Neorakhola W/S Mnt. Division |  | 380.26 | 0 | 0 | 0 | 380.26 | 380.26 | 0 | 0 | 0 | 380.26 | 62.67 | 70
101 | KALIMPONG | SM/10635 | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010479 | 40033395 | New | SVS | GO2223000455PH | 20/04/2022 | 143.53 | 0 | 143.53 | Neorakhola W/S Mnt. Division |  | 119.03 | 0 | 0 | 0 | 119.03 | 119.03 | 0 | 0 | 0 | 119.03 | 82.93 | 85
102 | KALIMPONG | SM/18443 | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | TSM/020226 | 40058718 | New | MVS | 1955/PHE-28011/106/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 3488.92 | 0 | 3488.92 | Neorakhola W/S Mnt. Division |  | 392.16 | 0 | 3.47 | 0 | 395.64 | 392.16 | 0 | 3.47 | 0 | 395.64 | 11.34 | 40
103 | KALIMPONG | SM/11312 | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME | TSM/009677 | 40017340 | New | SVS | GO2223003649PH | 13/06/2022 | 100.81 | 0 | 100.81 | Neorakhola W/S Mnt. Division |  | 66.22 | 0 | 0 | 0 | 66.22 | 66.22 | 0 | 0 | 0 | 66.22 | 65.68 | 90
104 | KALIMPONG | SM/09548 | PWS from Samphong Khola to Kagey Busty District Kalimpong | TSM/008805 | 40013371 | New | MVS | GO2122005569PH | 19/11/2021 | 679.86 | 0 | 679.86 | Kalimpong Division |  | 595.44 | 0 | 3.54 | 0 | 598.98 | 595.44 | 0 | 3.54 | 0 | 598.98 | 88.1
105 | KALIMPONG | SM/09547 | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | TSM/008851 | 40013120 | New | SVS | GO2122005569PH | 19/11/2021 | 237.68 | 0 | 237.68 | Kalimpong Division |  | 127.05 | 0 | 1.65 | 0 | 128.7 | 127.05 | 0 | 1.65 | 0 | 128.7 | 54.15
106 | KALIMPONG | SM/09606 | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE | TSM/008867 | 40013126 | New | SVS | GO2122005754PH | 23/11/2021 | 198.35 | 0 | 198.35 | Kalimpong Division |  | 174.94 | 0 | 1.26 | 0 | 176.2 | 174.94 | 0 | 1.26 | 0 | 176.2 | 88.83
107 | KALIMPONG | SM/09602 | Pws scheme from 7th Mile Jhora to Algarah | TSM/008835 | 40010927 | New | SVS | GO2122005746PH | 23/11/2021 | 321.38 | 0 | 321.38 | Neorakhola W/S Mnt. Division |  | 235.28 | 0 | 2.48 | 0 | 237.76 | 235.28 | 0 | 2.48 | 0 | 237.76 | 73.98 | 93
108 | KALIMPONG | SM/09603 | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE | TSM/008847 | 40009753 | New | SVS | GO2122005746PH | 23/11/2021 | 258.69 | 0 | 258.69 | Neorakhola W/S Mnt. Division |  | 217.78 | 0 | 0.66 | 0 | 218.44 | 214.23 | 0 | 0.66 | 0 | 214.89 | 83.07 | 95
109 | KALIMPONG | SM/09608 | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | TSM/008862 | 40013244 | New | SVS | GO2122005754PH | 23/11/2021 | 367.78 | 0 | 367.78 | Kalimpong Division |  | 269.2 | 0 | 2.46 | 0 | 271.67 | 269.2 | 0 | 2.46 | 0 | 271.67 | 73.87 | 90
110 | KALIMPONG | SM/09668 | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON | TSM/008870 | 40013159 | New | SVS | GO2122005751PH | 23/11/2021 | 182.37 | 0 | 182.37 | Kalimpong Division |  | 145.9 | 0 | 0.77 | 0 | 146.67 | 145.9 | 0 | 0.77 | 0 | 146.67 | 80.42 | 80
111 | KALIMPONG | SM/10750 | PWS SCHEME FROM BANGLA JHORA TO JOGITAR | TSM/009634 | 40036423 | New | SVS | GO2223002371PH | 19/05/2022 | 65.73 | 0 | 65.73 | Kalimpong Division |  | 12.32 | 0 | 0 | 0 | 12.32 | 12.32 | 0 | 0 | 0 | 12.32 | 18.74
112 | KALIMPONG | SM/09540 | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING | TSM/008861 | 40014556 | New | MVS | GO2122005572PH | 19/11/2021 | 91.94 | 0 | 91.94 | Kalimpong Division |  | 71.94 | 0 | 0.33 | 0 | 72.27 | 71.94 | 0 | 0.33 | 0 | 72.27 | 78.61 | 90
113 | KALIMPONG | SM/10747 | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK | TSM/009642 | 40028488 | New | SVS | GO2223002367PH | 19/05/2022 | 72.57 | 0 | 72.57 | Kalimpong Division |  | 62.34 | 0 | 0 | 0 | 62.34 | 62.34 | 0 | 0 | 0 | 62.34 | 85.9
114 | KALIMPONG | SM/09607 | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN | TSM/008871 | 40013131 | New | SVS | GO2122005754PH | 23/11/2021 | 108.86 | 0 | 108.86 | Kalimpong Division |  | 74.3 | 0 | 1.14 | 0 | 75.45 | 74.3 | 0 | 1.14 | 0 | 75.45 | 69.31 | 80
115 | KALIMPONG | SM/09611 | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG | TSM/008842 | 40013257 | New | SVS | GO2122005832PH | 24/11/2021 | 80.8 | 0 | 80.8 | Kalimpong Division |  | 70.48 | 0 | 0.38 | 0 | 70.87 | 70.48 | 0 | 0.38 | 0 | 70.87 | 87.7
116 | KALIMPONG | SM/09615 | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON | TSM/008856 | 40013352 | New | SVS | GO2122005832PH | 24/11/2021 | 118.44 | 0 | 118.44 | Kalimpong Division |  | 118.14 | 0 | 0.3 | 0 | 118.44 | 118.14 | 0 | 0.3 | 0 | 118.44 | 100
117 | KALIMPONG | SM/09664 | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI | TSM/008865 | 40009704 | New | SVS | GO2122005833PH | 24/11/2021 | 137.62 | 0 | 137.62 | Neorakhola W/S Mnt. Division |  | 123.86 | 0 | 0.33 | 0 | 124.19 | 123.84 | 0 | 0.33 | 0 | 124.17 | 90.22 | 95
118 | KALIMPONG | SM/09601 | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | TSM/008836 | 40013094 | New | SVS | GO2122005746PH | 23/11/2021 | 206.39 | 0 | 206.39 | Kalimpong Division |  | 170.07 | 0 | 1.35 | 0 | 171.41 | 170.07 | 0 | 1.35 | 0 | 171.41 | 83.05
119 | KALIMPONG | SM/09543 | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY | TSM/008860 | 40013248 | New | SVS | GO2122005571PH | 19/11/2021 | 365.16 | 0 | 365.16 | Kalimpong Division |  | 283.07 | 0 | 2.34 | 0 | 285.41 | 283.07 | 0 | 2.34 | 0 | 285.41 | 78.16 | 65
120 | KALIMPONG | SM/09610 | PWS SCHEME FROM CHAWA KHOLA TO RELLI | TSM/008843 | 40013042 | New | SVS | GO2122005832PH | 24/11/2021 | 122.01 | 0 | 122.01 | Kalimpong Division |  | 117.19 | 0 | 0.69 | 0 | 117.87 | 117.19 | 0 | 0.69 | 0 | 117.87 | 96.61
121 | KALIMPONG | SM/09542 | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON | TSM/008869 | 40013857 | New | SVS | GO2122005572PH | 19/11/2021 | 108.18 | 0 | 108.18 | Neorakhola W/S Mnt. Division |  | 89.57 | 0 | 0 | 0 | 89.57 | 89.57 | 0 | 0 | 0 | 89.57 | 82.8 | 80
122 | KALIMPONG | SM/10741 | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | TSM/009663 | 40026840 | New | SVS | GO2223002362PH | 19/05/2022 | 92.28 | 0 | 92.28 | Kalimpong Division |  | 64.7 | 0 | 0 | 0 | 64.7 | 64.7 | 0 | 0 | 0 | 64.7 | 70.12
123 | KALIMPONG | SM/11342 | PWS SCHEME FROM DALDALEY JHORA TO PASSABONG | TSM/009638 | 40036793 | New | SVS | GO2223004081PH | 13/06/2022 | 100.52 | 0 | 100.52 | Kalimpong Division |  | 84.53 | 0 | 0 | 0 | 84.53 | 84.53 | 0 | 0 | 0 | 84.53 | 84.1
124 | KALIMPONG | SM/11341 | PWS SCHEME FROM DEORALI KHOLA TO PAKANG | TSM/009653 | 40036386 | New | SVS | GO2223004071PH | 13/06/2022 | 117.19 | 0 | 117.19 | Kalimpong Division |  | 89.7 | 0 | 0 | 0 | 89.7 | 89.7 | 0 | 0 | 0 | 89.7 | 76.54
125 | KALIMPONG | SM/09596 | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | TSM/008854 | 40009752 | New | SVS | GO2122005748PH | 23/11/2021 | 314.39 | 0 | 314.39 | Neorakhola W/S Mnt. Division |  | 311.25 | 0 | 1.76 | 0 | 313.01 | 311.23 | 0 | 1.76 | 0 | 312.99 | 99.55
126 | KALIMPONG | SM/10755 | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP | TSM/009627 | 40036453 | New | SVS | GO2223002374PH | 19/05/2022 | 201.1 | 0 | 201.1 | Kalimpong Division |  | 114.88 | 0 | 0 | 0 | 114.88 | 114.88 | 0 | 0 | 0 | 114.88 | 57.12
127 | KALIMPONG | SM/09541 | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | TSM/008864 | 40036895 | New | MVS | GO2122005572PH | 19/11/2021 | 568.83 | 0 | 568.83 | Neorakhola W/S Mnt. Division |  | 405.35 | 0 | 0 | 0 | 405.35 | 405.35 | 0 | 0 | 0 | 405.35 | 71.26 | 86
128 | KALIMPONG | SM/11354 | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR | TSM/009639 | 40036505 | New | SVS | GO2223004576PH | 28/06/2022 | 143.23 | 0 | 143.23 | Kalimpong Division |  | 126.58 | 0 | 0 | 0 | 126.58 | 126.58 | 0 | 0 | 0 | 126.58 | 88.37
129 | KALIMPONG | SM/09539 | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI | TSM/008868 | 40013136 | New | SVS | GO2122005572PH | 19/11/2021 | 151.5 | 0 | 151.5 | Kalimpong Division |  | 120.7 | 0 | 0.66 | 0 | 121.37 | 120.7 | 0 | 0.66 | 0 | 121.37 | 80.11
130 | KALIMPONG | SM/09597 | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA | TSM/008849 | 40013118 | New | SVS | GO2122005748PH | 23/11/2021 | 199.67 | 0 | 199.67 | Kalimpong Division |  | 171.97 | 0 | 0.41 | 0 | 172.38 | 171.97 | 0 | 0.41 | 0 | 172.38 | 86.33 | 100
131 | KALIMPONG | SM/09584 | PWS SCHEME FROM JHOLUNG KHOLA TO 45 DHURA | TSM/008859 | 40012993 | New | SVS | GO2122005674PH | 22/11/2021 | 138.09 | 0 | 138.09 | Kalimpong Division |  | 118.77 | 0 | 0.88 | 0 | 119.64 | 118.77 | 0 | 0.88 | 0 | 119.64 | 86.65 | 90
132 | KALIMPONG | SM/09667 | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP | TSM/008863 | 40009746 | New | SVS | GO2122005751PH | 23/11/2021 | 476.5 | 0 | 476.5 | Neorakhola W/S Mnt. Division |  | 460.69 | 0 | 1.93 | 0 | 462.62 | 460.69 | 0 | 1.93 | 0 | 462.62 | 97.09
133 | KALIMPONG | SM/09605 | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA | TSM/008866 | 40013155 | New | SVS | GO2122005754PH | 23/11/2021 | 164.46 | 0 | 164.46 | Kalimpong Division |  | 130.66 | 0 | 1.21 | 0 | 131.87 | 130.66 | 0 | 1.21 | 0 | 131.87 | 80.18
134 | KALIMPONG | SM/09614 | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY | TSM/008838 | 40013033 | New | MVS | GO2122005832PH | 24/11/2021 | 88.27 | 0 | 88.27 | Kalimpong Division |  | 68.54 | 0 | 0.33 | 0 | 68.87 | 68.54 | 0 | 0.33 | 0 | 68.87 | 78.02
135 | KALIMPONG | SM/09616 | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA | TSM/008846 | 40013054 | New | SVS | GO2122005832PH | 24/11/2021 | 143.99 | 0 | 143.99 | Kalimpong Division |  | 123.24 | 0 | 0.27 | 0 | 123.51 | 123.24 | 0 | 0.27 | 0 | 123.51 | 85.78
136 | KALIMPONG | SM/10754 | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY | TSM/009628 | 40026751 | New | SVS | GO2223002365PH | 19/05/2022 | 176.39 | 0 | 176.39 | Kalimpong Division |  | 157.47 | 0 | 0 | 0 | 157.47 | 157.47 | 0 | 0 | 0 | 157.47 | 89.28
137 | KALIMPONG | SM/10753 | PWS SCHEME FROM KHANI KHOLA TO CHUKIM | TSM/009629 | 40028596 | New | SVS | GO2223002375PH | 19/05/2022 | 138.36 | 0 | 138.36 | Kalimpong Division |  | 117.83 | 0 | 0 | 0 | 117.83 | 117.83 | 0 | 0 | 0 | 117.83 | 85.16
138 | KALIMPONG | SM/10756 | PWS SCHEME FROM KHARKHOLA TO LOWER REON | TSM/009617 | 40026759 | New | MVS | GO2223002370PH | 19/05/2022 | 105.07 | 0 | 105.07 | Kalimpong Division |  | 74.29 | 0 | 0 | 0 | 74.29 | 74.29 | 0 | 0 | 0 | 74.29 | 70.71
139 | KALIMPONG | SM/10749 | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE | TSM/009636 | 40024850 | New | MVS | GO2223002364PH | 19/05/2022 | 105.72 | 0 | 105.72 | Kalimpong Division |  | 97.81 | 0 | 0 | 0 | 97.81 | 97.81 | 0 | 0 | 0 | 97.81 | 92.52
140 | KALIMPONG | SM/10751 | PWS SCHEME FROM MANDIR KHOLA TO TANYANG | TSM/009633 | 40028592 | New | SVS | GO2223002366PH | 19/05/2022 | 214.24 | 0 | 214.24 | Kalimpong Division |  | 175.66 | 0 | 0 | 0 | 175.66 | 175.66 | 0 | 0 | 0 | 175.66 | 81.99
141 | KALIMPONG | SM/09546 | PWS SCHEME FROM MAWATAR TO UPPER DABLING | TSM/008852 | 40013086 | New | SVS | GO2122005571PH | 19/11/2021 | 192.44 | 0 | 192.44 | Kalimpong Division |  | 186.07 | 0 | 0.27 | 0 | 186.34 | 186.07 | 0 | 0.27 | 0 | 186.34 | 96.83
142 | KALIMPONG | SM/09670 | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA | TSM/008858 | 40013031 | New | SVS | GO2122005751PH | 23/11/2021 | 122.05 | 0 | 122.05 | Kalimpong Division |  | 106.55 | 0 | 0.36 | 0 | 106.91 | 106.55 | 0 | 0.36 | 0 | 106.91 | 87.59
143 | KALIMPONG | SM/09598 | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON | TSM/008853 | 40013059 | New | SVS | GO2122005748PH | 23/11/2021 | 96.33 | 0 | 96.33 | Kalimpong Division |  | 93.21 | 0 | 0.31 | 0 | 93.52 | 93.21 | 0 | 0.31 | 0 | 93.52 | 97.09
144 | KALIMPONG | SM/10745 | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN | TSM/009647 | 40036393 | New | SVS | GO2223002363PH | 19/05/2022 | 91.35 | 0 | 91.35 | Kalimpong Division |  | 74.93 | 0 | 0 | 0 | 74.93 | 74.93 | 0 | 0 | 0 | 74.93 | 82.02
145 | KALIMPONG | SM/10744 | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION | TSM/009651 | 40016076 | New | SVS | GO2223002361PH | 19/05/2022 | 225.47 | 0 | 225.47 | Kalimpong Division |  | 218.46 | 0 | 0 | 0 | 218.46 | 218.46 | 0 | 0 | 0 | 218.46 | 96.89 | 100
146 | KALIMPONG | SM/10746 | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON | TSM/009645 | 40014688 | New | SVS | GO2223002369PH | 19/05/2022 | 194.83 | 0 | 194.83 | Neorakhola W/S Mnt. Division |  | 189.16 | 0 | 0 | 0 | 189.16 | 189.16 | 0 | 0 | 0 | 189.16 | 97.09 | 100
147 | KALIMPONG | SM/10748 | PWS SCHEME FROM PHENTO SOURCE TO DUKA | TSM/009637 | 40036796 | New | SVS | GO2223002373PH | 19/05/2022 | 165.77 | 0 | 165.77 | Kalimpong Division |  | 137.75 | 0 | 0 | 0 | 137.75 | 137.75 | 0 | 0 | 0 | 137.75 | 83.1
148 | KALIMPONG | SM/09609 | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING | TSM/008857 | 40013261 | New | SVS | GO2122005754PH | 23/11/2021 | 98.66 | 0 | 98.66 | Kalimpong Division |  | 80.38 | 0 | 0.41 | 0 | 80.79 | 80.38 | 0 | 0.41 | 0 | 80.79 | 81.89
149 | KALIMPONG | SM/09612 | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON | TSM/008855 | 40046729 | New | SVS | GO2122005832PH | 24/11/2021 | 180.96 | 0 | 180.96 | Neorakhola W/S Mnt. Division |  | 90.46 | 0 | 0 | 0 | 90.46 | 90.46 | 0 | 0 | 0 | 90.46 | 49.99 | 80
150 | KALIMPONG | SM/11340 | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY | TSM/009666 | 40028613 | New | SVS | GO2223004072PH | 13/06/2022 | 220.09 | 0 | 220.09 | Kalimpong Division |  | 111.36 | 0 | 0 | 0 | 111.36 | 111.36 | 0 | 0 | 0 | 111.36 | 50.6 | 85
151 | KALIMPONG | SM/09600 | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | TSM/008848 | 40013082 | New | SVS | GO2122005746PH | 23/11/2021 | 169.19 | 0 | 169.19 | Kalimpong Division |  | 136.01 | 0 | 1.29 | 0 | 137.3 | 136.01 | 0 | 1.29 | 0 | 137.3 | 81.15
152 | KALIMPONG | SM/10742 | PWS SCHEME FROM SISNEY JHORA TO SAMTHAR BAZAR | TSM/009660 | 40027276 | New | SVS | GO2223002376PH | 19/05/2022 | 197.78 | 0 | 197.78 | Kalimpong Division |  | 178 | 0 | 0 | 0 | 178 | 178 | 0 | 0 | 0 | 178 | 90
153 | KALIMPONG | SM/10752 | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY | TSM/009632 | 40028499 | New | SVS | GO2223002368PH | 19/05/2022 | 75.91 | 0 | 75.91 | Kalimpong Division |  | 62.73 | 0 | 0 | 0 | 62.73 | 62.73 | 0 | 0 | 0 | 62.73 | 82.64
154 | KALIMPONG | SM/09666 | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE | TSM/008845 | 40013039 | New | SVS | GO2122005833PH | 24/11/2021 | 138.81 | 0 | 138.81 | Kalimpong Division |  | 102.3 | 0 | 0.77 | 0 | 103.07 | 102.3 | 0 | 0.77 | 0 | 103.07 | 74.25
155 | KALIMPONG | SM/09594 | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE | TSM/008850 | 40013835 | New | SVS | GO2122005741PH | 23/11/2021 | 776.35 | 0 | 776.35 | Neorakhola W/S Mnt. Division |  | 582.85 | 0 | 0 | 0 | 582.85 | 582.85 | 0 | 0 | 0 | 582.85 | 75.08 | 70
156 | KALIMPONG | SM/09595 | PWS SCHEME FROM UNEAK KHOLA TO DABLING | TSM/008844 | 40012237 | New | SVS | GO2122005741PH | 23/11/2021 | 126.98 | 0 | 126.98 | Kalimpong Division |  | 122.76 | 0 | 0.52 | 0 | 123.28 | 122.66 | 0 | 0.52 | 0 | 123.18 | 97.01 | 100
157 | KALIMPONG | SM/10743 | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA | TSM/009657 | 40028725 | New | SVS | GO2223002377PH | 19/05/2022 | 79.81 | 0 | 79.81 | Kalimpong Division |  | 69.1 | 0 | 0 | 0 | 69.1 | 69.1 | 0 | 0 | 0 | 69.1 | 86.58
158 | KALIMPONG | SM/11343 | PWSS FROM BHARKHOP JHORA TO LOWER KAFFER | TSM/009553 | 40036494 | New | SVS | GO2223004070PH | 13/06/2022 | 99.53 | 0 | 99.53 | Kalimpong Division |  | 69.95 | 0 | 0 | 0 | 69.95 | 69.95 | 0 | 0 | 0 | 69.95 | 70.29
159 | KALIMPONG | SM/09617 | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | TSM/008837 | 40013395 | New | SVS | GO2122005832PH | 24/11/2021 | 100.06 | 0 | 100.06 | Kalimpong Division |  | 73.75 | 0 | 0 | 0 | 73.75 | 73.75 | 0 | 0 | 0 | 73.75 | 73.71
160 | KALIMPONG | SM/09669 | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG | TSM/008839 | 40012989 | New | SVS | GO2122005751PH | 23/11/2021 | 125.27 | 0 | 125.27 | Kalimpong Division |  | 110.39 | 0 | 0.31 | 0 | 110.7 | 110.39 | 0 | 0.31 | 0 | 110.7 | 88.37
161 | KALIMPONG | SM/09545 | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON | TSM/008841 | 40012954 | New | SVS | GO2122005571PH | 19/11/2021 | 160.48 | 0 | 160.48 | Kalimpong Division |  | 98.01 | 0 | 0.69 | 0 | 98.7 | 98.01 | 0 | 0.69 | 0 | 98.7 | 61.5
162 | KALIMPONG | SM/09613 | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON | TSM/008840 | 40013778 | New | SVS | GO2122005832PH | 24/11/2021 | 110.68 | 0 | 110.68 | Neorakhola W/S Mnt. Division |  | 81.5 | 0 | 0 | 0 | 81.5 | 81.5 | 0 | 0 | 0 | 81.5 | 73.64 | 95
163 | KALIMPONG | SM/18823 | RANGO FOREST PWSS | TSM/013119 | 40035674 | New | MVS | 2742/PHE-28011/183/2023-SCHM CELL-Dept. of PHE | 11/09/2023 | 1664.29 | 0 | 1664.29 | Neorakhola W/S Mnt. Division |  | 381.23 | 0 | 11.65 | 0 | 392.88 | 381.23 | 0 | 11.65 | 0 | 392.88 | 23.61 | 50
164 | KALIMPONG | SM/07872 | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | TSM/006925 | 8174190 | Retrofitting | MVS | GO2021004741PH | 19/01/2021 | 72.63 | 0 | 72.63 | Neorakhola W/S Mnt. Division |  | 64.69 | 0 | 0 | 0 | 64.69 | 64.22 | 0 | 0 | 0 | 64.22 | 88.42 | 11
165 | KALIMPONG | SM/08693 | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | TSM/007291 | 8364260 | Retrofitting | MVS | GO2122002586PH | 01/09/2021 | 99.42 | 0 | 99.42 | Neorakhola W/S Mnt. Division |  | 98.58 | 0 | 0 | 0 | 98.58 | 98.58 | 0 | 0 | 0 | 98.58 | 99.16
166 | KALIMPONG | SM/13953 | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | TSM/014292 | 40035771 | New | MVS | GO2223010344PH | 01/12/2022 | 882.37 | 0 | 882.37 | Kalimpong Division |  | 476.33 | 0 | 8.17 | 0 | 484.49 | 476.33 | 0 | 8.17 | 0 | 484.49 | 54.91 | 60
167 | KALIMPONG | SM/13611 | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/011907 | 40035802 | New | SVS | GO2223009614PH | 11/11/2022 | 648.24 | 0 | 648.24 | Kalimpong Division |  | 440.8 | 0 | 4.25 | 0 | 445.05 | 440.8 | 0 | 4.25 | 0 | 445.05 | 68.66 | 90
168 | KALIMPONG | SM/13613 | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | TSM/013023 | 40036536 | New | SVS | GO2223009612PH | 11/11/2022 | 351.35 | 0 | 351.35 | Neorakhola W/S Mnt. Division |  | 50.86 | 0 | 1.87 | 0 | 52.73 | 50.86 | 0 | 1.87 | 0 | 52.73 | 15.01 | 40
169 | KALIMPONG | SM/14191 | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | TSM/012585 | 40035097 | New | SVS | GO2223011799PH | 10/01/2023 | 693.21 | 0 | 693.21 | Kalimpong Division |  | 445.04 | 0 | 0 | 0 | 445.04 | 445.04 | 0 | 0 | 0 | 445.04 | 64.2
170 | KALIMPONG | SM/11313 | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010477 | 40033322 | New | SVS | GO2223004146PH | 15/06/2022 | 829.3 | 0 | 829.3 | Neorakhola W/S Mnt. Division |  | 632.69 | 0 | 0 | 0 | 632.69 | 632.69 | 0 | 0 | 0 | 632.69 | 76.29 | 70
171 | KALIMPONG | SM/13607 | SURUK PIPED WATER SUPPLY SCHEME | TSM/012709 | 40036801 | New | SVS | GO2223009616PH | 11/11/2022 | 643.2 | 0 | 643.2 | Kalimpong Division |  | 223.97 | 0 | 4.16 | 0 | 228.14 | 223.97 | 0 | 4.16 | 0 | 228.14 | 35.47
172 | KALIMPONG | SM/13954 | UPPER FAGU PIPED WATER SUPPLY SCHEME. | TSM/012803 | 40035680 | New | MVS | GO2223010332PH | 01/12/2022 | 819.76 | 0 | 819.76 | Neorakhola W/S Mnt. Division |  | 0.64 | 0 | 5.69 | 0 | 6.33 | 0.64 | 0 | 5.69 | 0 | 6.33 | 0.77 | 10
173 | KALIMPONG | SM/18589 | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | TSM/012889 | 40055841 | New | SVS | 2147/PHE-28011/142/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1104.14 | 0 | 1104.14 | Neorakhola W/S Mnt. Division |  | 768.28 | 0 | 0 | 0 | 768.28 | 759.43 | 0 | 0 | 0 | 759.43 | 68.78 | 75
Total | [9 empty] | 72624.29 | 192.01 | 72816.3 |  |  | 32538.12 | 0 | 363.15 | 0 | 32901.26 | 32493.69 | 0 | 363.15 | 0 | 32856.84 | 45.12