## JJM Schemes Financial Status (J
JJM Schemes Financial Status (JHARGRAM) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | JHARGRAM | SM/09434 | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | TSM/007452 | 40009037 | Augmentation | MVS | GO2122005537PH | 18/11/2021 | 10.67 | 15.29 | 25.96 | Jhargram Division | Midnapore Mechanical Division | 8.17 | 0 | 0 | 0 | 8.17 | 8.17 | 0 | 0 | 0 | 8.17 | 31.47 | 100
2 | JHARGRAM | SM/17586 | AMARDA AND ADJOINING MOUJAS PWSS | TSM/012757 | 40033041 | New | MVS | GO2223017047PH | 18/03/2023 | 480.32 | 38.73 | 519.04 | Jhargram Division | Jhargram Mechanical Division | 0 | 4.41 | 0 | 16.04 | 20.46 | 0 | 4.41 | 0 | 16.04 | 20.46 | 3.94 | 20
3 | JHARGRAM | SM/12336 | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/013201 | 40028494 | New | MVS | GO2223007397PH | 09/09/2022 | 409.93 | 36.34 | 446.27 | Jhargram Division | Jhargram Mechanical Division | 274.9 | 25.97 | 8.71 | 0 | 309.58 | 274.9 | 25.97 | 8.71 | 0 | 309.58 | 69.37 | 85
4 | JHARGRAM | SM/17583 | ANANDAPUR AND ADJOINING MOUJAS PWSS | TSM/013053 | 40033040 | New | MVS | GO2223017053PH | 18/03/2023 | 337.43 | 36.3 | 373.73 | Jhargram Division | Jhargram Mechanical Division | 238.5 | 25.45 | 7.69 | 0 | 271.64 | 238.5 | 25.45 | 7.69 | 0 | 271.64 | 72.68 | 65
5 | JHARGRAM | SM/16991 | ANDHARI AND ADJOINING MOUJAS PWSS | TSM/013042 | 40032827 | New | MVS | GO2223016556PH | 16/03/2023 | 287.62 | 46.75 | 334.36 | Jhargram Division | Jhargram Mechanical Division | 158.67 | 11.86 | 23.96 | 15.2 | 209.69 | 158.67 | 11.86 | 23.96 | 15.2 | 209.69 | 62.71 | 60
6 | JHARGRAM | SM/12447 | ANKRO AND ADJOINING MOUJAS PWSS | TSM/014135 | 40029306 | New | MVS | GO2223007559PH | 13/09/2022 | 560.36 | 38.82 | 599.18 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 23.53 | 0 | 23.53 | 0 | 0 | 23.53 | 0 | 23.53 | 3.93
7 | JHARGRAM | SM/18435 | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | TSM/020327 | 40064074 | Augmentation | MVS | 1930/PHE-28011/206/2023-SCHM CELL-Dept. of PHE | 18/07/2023 | 2052.61 | 0 | 2052.61 | Jhargram Division |  | 218.11 | 0 | 0 | 0 | 218.11 | 218.11 | 0 | 0 | 0 | 218.11 | 10.63 | 80
8 | JHARGRAM | SM/09882 | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | TSM/007709 | 40006087 | Augmentation | SVS | GO2122006587PH | 08/12/2021 | 28.11 | 12.85 | 40.96 | Jhargram Division | Jhargram Mechanical Division | 6.16 | 9.71 | 0 | 0 | 15.87 | 6.16 | 10.59 | 0 | 0 | 16.75 | 40.9 | 100
9 | JHARGRAM | SM/13678 | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/009315 | 40002418 | Augmentation | MVS | GO2223009741PH | 14/11/2022 | 33.18 | 13.1 | 46.29 | Jhargram Division | Jhargram Mechanical Division | 25.97 | 10.39 | 0 | 0 | 36.35 | 25.97 | 10.39 | 0 | 0 | 36.35 | 78.54 | 100
10 | JHARGRAM | SM/10490 | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008539 | 40016370 | Augmentation | MVS | GO2223000283PH | 13/04/2022 | 337.13 | 16.21 | 353.34 | Jhargram Division | Jhargram Mechanical Division | 306.61 | 23.23 | 10.81 | 0 | 340.65 | 310.15 | 26.33 | 10.81 | 0 | 347.3 | 98.29 | 100
11 | JHARGRAM | SM/09379 | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008600 | 40002022 | Augmentation | MVS | GO2122005387PH | 12/11/2021 | 271.58 | 32.6 | 304.18 | Jhargram Division | Jhargram Mechanical Division | 166.87 | 12.78 | 77.58 | 0 | 257.22 | 167.63 | 12.78 | 77.58 | 0 | 257.99 | 84.81 | 93
12 | JHARGRAM | SM/10491 | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008550 | 40016328 | Augmentation | MVS | GO2223000284PH | 13/04/2022 | 324.19 | 20.67 | 344.86 | Jhargram Division | Jhargram Mechanical Division | 200.11 | 0 | 0 | 0 | 200.11 | 200.11 | 0 | 0 | 0 | 200.11 | 58.03 | 98
13 | JHARGRAM | SM/09373 | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008609 | 40002345 | Augmentation | MVS | GO2122005386PH | 12/11/2021 | 455.93 | 29.28 | 485.2 | Jhargram Division | Jhargram Mechanical Division | 383.64 | 29.97 | 1.86 | 0 | 415.48 | 383.63 | 29.97 | 1.86 | 0 | 415.46 | 85.63 | 98
14 | JHARGRAM | SM/09372 | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008611 | 7394368 | Augmentation | MVS | GO2122005386PH | 12/11/2021 | 98.03 | 20.67 | 118.7 | Jhargram Division | Jhargram Mechanical Division | 46.47 | 3.17 | 1.52 | 0 | 51.16 | 46.47 | 3.17 | 1.52 | 0 | 51.16 | 43.1 | 100
15 | JHARGRAM | SM/10492 | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | TSM/008543 | 40016290 | Augmentation | MVS | GO2223000285PH | 13/04/2022 | 182.33 | 32.6 | 214.93 | Jhargram Division | Jhargram Mechanical Division | 119.16 | 15.73 | 0 | 0 | 134.89 | 119.16 | 23.56 | 0 | 0 | 142.72 | 66.4 | 95
16 | JHARGRAM | SM/09374 | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | TSM/008608 | 40002214 | Augmentation | MVS | GO2122005389PH | 12/11/2021 | 371.32 | 29.77 | 401.09 | Jhargram Division | Jhargram Mechanical Division | 270.31 | 12.15 | 67.18 | 0 | 349.63 | 270.31 | 16.46 | 67.18 | 0 | 353.95 | 88.25 | 90
17 | JHARGRAM | SM/09375 | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | TSM/008606 | 40002301 | Augmentation | MVS | GO2122005389PH | 12/11/2021 | 113.25 | 20.71 | 133.96 | Jhargram Division | Jhargram Mechanical Division | 57.84 | 16.19 | 0.96 | 0 | 74.99 | 57.84 | 17.96 | 0.96 | 0 | 76.77 | 57.31 | 100
18 | JHARGRAM | SM/09378 | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | TSM/008602 | 40002473 | Augmentation | MVS | GO2122005389PH | 12/11/2021 | 115.7 | 19.2 | 134.9 | Jhargram Division | Jhargram Mechanical Division | 10.45 | 1.32 | 1.05 | 0 | 12.81 | 6.95 | 2.21 | 1.05 | 0 | 10.2 | 7.56 | 70
19 | JHARGRAM | SM/10064 | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | TSM/009129 | 40006060 | Augmentation | MVS | GO2122008816PH | 28/01/2022 | 993.23 | 67.43 | 1060.66 | Jhargram Division | Jhargram Mechanical Division | 786.07 | 41.31 | 159.21 | 0 | 986.59 | 786.01 | 45.23 | 159.21 | 0 | 990.45 | 93.38 | 95
20 | JHARGRAM | SM/09881 | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | TSM/007710 | 40002706 | Augmentation | SVS | GO2122006587PH | 08/12/2021 | 20.56 | 11.48 | 32.05 | Jhargram Division | Jhargram Mechanical Division | 6.75 | 4.18 | 0 | 0 | 10.92 | 6.55 | 5.96 | 0 | 0 | 12.51 | 39.04 | 100
21 | JHARGRAM | SM/09377 | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | TSM/008603 | 40002475 | Augmentation | MVS | GO2122005389PH | 12/11/2021 | 166.77 | 20.69 | 187.46 | Jhargram Division | Jhargram Mechanical Division | 118.34 | 19.77 | 5.8 | 0 | 143.9 | 118.34 | 19.77 | 5.8 | 0 | 143.9 | 76.77 | 100
22 | JHARGRAM | SM/18428 | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | TSM/018706 | 40053204 | Augmentation | MVS | 1924/PHE-28011/209/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 4078.41 | 141.24 | 4219.65 | Jhargram Division | Jhargram Mechanical Division | 395.19 | 0 | 184.29 | 0 | 579.48 | 395.19 | 1.48 | 184.29 | 0 | 580.96 | 13.77 | 70
23 | JHARGRAM | SM/17953 | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram | TSM/018036 | 40064069 | Augmentation | MVS | GO2223016786PH | 17/03/2023 | 476.22 | 99.91 | 576.13 | Jhargram Division | Jhargram Mechanical Division | 85.85 | 10.56 | 0 | 0 | 96.41 | 85.85 | 10.56 | 0 | 0 | 96.41 | 16.73
24 | JHARGRAM | SM/12523 | BAGMURI AND ADJOINING MOUJAS PWSS | TSM/013131 | 40028697 | New | MVS | GO2223007539PH | 13/09/2022 | 353.32 | 36.31 | 389.63 | Jhargram Division | Jhargram Mechanical Division | 1.34 | 7.7 | 0 | 20.18 | 29.22 | 1.34 | 7.7 | 0 | 20.18 | 29.22 | 7.5 | 5
25 | JHARGRAM | SM/12441 | BAHIR GRAM AND ADJOINING MOUJAS PWSS | TSM/014154 | 40029124 | New | MVS | GO2223007509PH | 13/09/2022 | 515.89 | 48.07 | 563.95 | Jhargram Division | Jhargram Mechanical Division | 56.61 | 14.9 | 0 | 31.04 | 102.55 | 56.61 | 15.79 | 0 | 31.04 | 103.43 | 18.34 | 55
26 | JHARGRAM | SM/12390 | BAKRA AND ITS ADJOINING MOUJAS PWSS | TSM/013058 | 40029237 | New | MVS | GO2223007540PH | 13/09/2022 | 598.96 | 38.85 | 637.82 | Jhargram Division | Jhargram Mechanical Division | 353.69 | 27.02 | 32.21 | 15.44 | 428.36 | 353.69 | 27.91 | 32.21 | 15.44 | 429.25 | 67.3 | 90
27 | JHARGRAM | SM/12388 | BALISHIRA AND ADJOINING MOUJAS PWSS | TSM/013504 | 40027549 | New | MVS | GO2223007513PH | 13/09/2022 | 494.46 | 40.21 | 534.67 | Jhargram Division | Jhargram Mechanical Division | 113.93 | 19.08 | 10.69 | 34.44 | 178.14 | 113.93 | 19.08 | 10.69 | 34.44 | 178.14 | 33.32 | 60
28 | JHARGRAM | SM/12442 | BANDARBANI AND ADJONING MOUJAS PWSS | TSM/014153 | 40029151 | New | MVS | GO2223007498PH | 13/09/2022 | 608.88 | 39.14 | 648.02 | Jhargram Division | Jhargram Mechanical Division | 298.42 | 5.59 | 69.18 | 27.55 | 400.75 | 298.42 | 5.59 | 69.18 | 27.55 | 400.75 | 61.84 | 80
29 | JHARGRAM | SM/12351 | BANKATI AND IT'S ADJOINING MOUJAS | TSM/013495 | 40027561 | New | MVS | GO2223007454PH | 12/09/2022 | 564.13 | 40.65 | 604.79 | Jhargram Division | Jhargram Mechanical Division | 492.05 | 16.64 | 61.17 | 14.53 | 584.39 | 492.05 | 16.64 | 61.17 | 14.53 | 584.39 | 96.63 | 60
30 | JHARGRAM | SM/17931 | BANKSOL AND ADJOINING MOUJAS PWSS | TSM/015563 | 40033016 | New | MVS | GO2223016672PH | 17/03/2023 | 0 | 480.2 | 480.2 | Jhargram Division | Jhargram Mechanical Division | 23.85 | 0.84 | 0 | 0 | 24.68 | 23.85 | 0.84 | 0 | 0 | 24.68 | 5.14
31 | JHARGRAM | SM/12722 | BARABARI AND ADJOINING MOUJAS PWSS | TSM/013236 | 40029366 | New | MVS | GO2223007918PH | 20/09/2022 | 492.28 | 45.16 | 537.44 | Jhargram Division | Jhargram Mechanical Division | 303.57 | 30.24 | 5.44 | 0 | 339.25 | 303.57 | 31.44 | 5.44 | 0 | 340.45 | 63.35 | 90
32 | JHARGRAM | SM/12324 | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | TSM/013108 | 40029220 | New | MVS | GO2223007408PH | 09/09/2022 | 427.88 | 36.45 | 464.32 | Jhargram Division | Jhargram Mechanical Division | 204.45 | 8.43 | 0 | 18.15 | 231.03 | 204.45 | 8.43 | 0 | 18.15 | 231.03 | 49.76 | 60
33 | JHARGRAM | SM/12451 | BELDA AND ADJOINING MOUJAS PWSS | TSM/014115 | 40029327 | New | MVS | GO2223007493PH | 13/09/2022 | 387.16 | 36.69 | 423.84 | Jhargram Division | Jhargram Mechanical Division | 211.4 | 21.79 | 4.92 | 0 | 238.1 | 211.4 | 21.79 | 4.92 | 0 | 238.1 | 56.18 | 90
34 | JHARGRAM | SM/12444 | BELIA AND ADJOINING MOUJAS PWSS | TSM/014152 | 40029258 | New | MVS | GO2223007508PH | 13/09/2022 | 475.03 | 48.14 | 523.17 | Jhargram Division | Jhargram Mechanical Division | 198.14 | 26.64 | 8.39 | 0 | 233.17 | 198.14 | 30.64 | 8.39 | 0 | 237.17 | 45.33 | 75
35 | JHARGRAM | SM/12391 | BHALUKASOL AND ADJOINING MOUJAS PWSS | TSM/012773 | 40029314 | New | MVS | GO2223007546PH | 13/09/2022 | 565.75 | 47.53 | 613.27 | Jhargram Division | Jhargram Mechanical Division | 320.09 | 7.19 | 0 | 37.51 | 364.78 | 320.09 | 7.19 | 0 | 37.51 | 364.78 | 59.48 | 65
36 | JHARGRAM | SM/17417 | BHAMAL AND ADOINING MOUJAS PWSS | TSM/011783 | 40026823 | New | MVS | GO2223017061PH | 18/03/2023 | 276.1 | 36.97 | 313.06 | Jhargram Division | Jhargram Mechanical Division | 0 | 6.28 | 6.22 | 0 | 12.49 | 0 | 6.28 | 6.22 | 0 | 12.49 | 3.99
37 | JHARGRAM | SM/12352 | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS | TSM/012711 | 40029325 | New | MVS | GO2223007463PH | 12/09/2022 | 629.69 | 38.71 | 668.4 | Jhargram Division | Jhargram Mechanical Division | 283.9 | 0 | 12.37 | 15.55 | 311.82 | 283.9 | 0 | 12.37 | 15.55 | 311.82 | 46.65 | 80
38 | JHARGRAM | SM/17582 | BHATAN DIA AND ADJOINING MOUJAS PWSS | TSM/013097 | 40033045 | New | MVS | GO2223017058PH | 18/03/2023 | 338.3 | 36.31 | 374.62 | Jhargram Division | Jhargram Mechanical Division | 5.73 | 0 | 0 | 6.52 | 12.25 | 5.73 | 0 | 0 | 6.52 | 12.25 | 3.27 | 5
39 | JHARGRAM | SM/12353 | BHAUDI AND ADJOINING MOUJAS PWSS | TSM/013161 | 40028675 | New | MVS | GO2223007456PH | 12/09/2022 | 448.04 | 36.34 | 484.38 | Jhargram Division | Jhargram Mechanical Division | 85.28 | 17.14 | 0 | 33.06 | 135.49 | 85.28 | 17.14 | 0 | 33.06 | 135.49 | 27.97 | 30
40 | JHARGRAM | SM/12452 | BHILA AND ADJOINING MOUJAS PWSS | TSM/013116 | 40029337 | New | MVS | GO2223007556PH | 13/09/2022 | 452.29 | 36.34 | 488.63 | Jhargram Division | Jhargram Mechanical Division | 219.72 | 6.82 | 0 | 34.44 | 260.98 | 219.72 | 8.3 | 0 | 34.44 | 262.46 | 53.71 | 80
41 | JHARGRAM | SM/17593 | BIRMADAL AND ADJOINING MOUJAS PWSS | TSM/014477 | 40032868 | New | MVS | GO2223017076PH | 18/03/2023 | 377.44 | 74.9 | 452.34 | Jhargram Division | Jhargram Mechanical Division | 25.59 | 0 | 0 | 0 | 25.59 | 25.59 | 0 | 0 | 0 | 25.59 | 5.66
42 | JHARGRAM | SM/12392 | BRAHMANDANA AND ADJOINING MOUJAS PWSS | TSM/013085 | 40029445 | New | MVS | GO2223007512PH | 13/09/2022 | 453.69 | 38.73 | 492.42 | Jhargram Division | Jhargram Mechanical Division | 77.12 | 10.17 | 0 | 33.93 | 121.22 | 77.12 | 12.54 | 0 | 33.93 | 123.59 | 25.1 | 40
43 | JHARGRAM | SM/17928 | BURIJHOR AND ADJOINING MOUJAS PWSS | TSM/015888 | 40033074 | New | MVS | GO2223016696PH | 17/03/2023 | 412.29 | 59.92 | 472.21 | Jhargram Division | Jhargram Mechanical Division | 87.45 | 0 | 0 | 0 | 87.45 | 87.45 | 0 | 0 | 0 | 87.45 | 18.52
44 | JHARGRAM | SM/12328 | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/013150 | 40028741 | New | MVS | GO2223007404PH | 09/09/2022 | 523.82 | 38.85 | 562.67 | Jhargram Division | Jhargram Mechanical Division | 70.38 | 9.1 | 0 | 34.38 | 113.86 | 70.38 | 9.1 | 0 | 34.38 | 113.86 | 20.24 | 30
45 | JHARGRAM | SM/18746 | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | TSM/015566 | 40033094 | New | MVS | 2443/PHE/IV/W-629/23 | 17/08/2023 | 0 | 789.66 | 789.66 | Jhargram Division | Jhargram Mechanical Division | 15.07 | 129.4 | 0 | 0 | 144.46 | 15.07 | 138.18 | 0 | 0 | 153.25 | 19.41
46 | JHARGRAM | SM/17925 | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | TSM/015919 | 40032947 | New | MVS | GO2223016684PH | 17/03/2023 | 0 | 639.18 | 639.18 | Jhargram Division | Jhargram Mechanical Division | 32.82 | 147.35 | 0 | 0 | 180.18 | 32.82 | 149.28 | 0 | 0 | 182.11 | 28.49
47 | JHARGRAM | SM/17596 | CHAKADOBA AND ADJOINING MOUJAS PWSS | TSM/014382 | 40033018 | New | MVS | GO2223017084PH | 18/03/2023 | 492.59 | 97.37 | 589.96 | Jhargram Division | Jhargram Mechanical Division | 49.14 | 0 | 0 | 0 | 49.14 | 49.14 | 0 | 0 | 0 | 49.14 | 8.33
48 | JHARGRAM | SM/12356 | CHAKKUA AND ADJOINING MOUJAS PWSS | TSM/013175 | 40028500 | New | MVS | GO2223007453PH | 12/09/2022 | 413.22 | 38.5 | 451.72 | Jhargram Division | Jhargram Mechanical Division | 214.24 | 29.4 | 28.09 | 0 | 271.73 | 214.24 | 31.18 | 28.09 | 0 | 273.5 | 60.55 | 75
49 | JHARGRAM | SM/12387 | CHAMPASOL AND ADJOINING MOUJAS PWSS | TSM/013507 | 40027529 | New | MVS | GO2223007517PH | 13/09/2022 | 465.65 | 38.52 | 504.16 | Jhargram Division | Jhargram Mechanical Division | 132.66 | 11.57 | 0 | 26.41 | 170.64 | 132.66 | 11.57 | 0 | 26.41 | 170.64 | 33.85 | 60
50 | JHARGRAM | SM/12435 | CHANDABILA AND ADJOINING MOPUJAS PWSS | TSM/014185 | 40029032 | New | MVS | GO2223007557PH | 13/09/2022 | 338 | 36.55 | 374.55 | Jhargram Division | Jhargram Mechanical Division | 223.6 | 6.49 | 0 | 19.02 | 249.11 | 223.6 | 7.38 | 0 | 19.02 | 250 | 66.75 | 90
51 | JHARGRAM | SM/12715 | CHANDRI AND ADJOINING MOUJAS PWSS | TSM/014162 | 40029106 | New | MVS | GO2223007922PH | 20/09/2022 | 506.78 | 39.14 | 545.91 | Jhargram Division | Jhargram Mechanical Division | 228.26 | 27.31 | 31.22 | 0 | 286.79 | 228.26 | 27.31 | 31.22 | 0 | 286.79 | 52.53 | 80
52 | JHARGRAM | SM/12445 | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | TSM/014139 | 40029262 | New | MVS | GO2223007499PH | 13/09/2022 | 494.3 | 38.93 | 533.24 | Jhargram Division | Jhargram Mechanical Division | 250.01 | 31.03 | 0 | 0 | 281.04 | 250.01 | 31.03 | 0 | 0 | 281.04 | 52.7 | 70
53 | JHARGRAM | SM/12448 | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | TSM/014131 | 40029313 | New | MVS | GO2223007558PH | 13/09/2022 | 382.54 | 38.52 | 421.06 | Jhargram Division | Jhargram Mechanical Division | 4.15 | 9.29 | 0 | 20.89 | 34.34 | 4.15 | 9.29 | 0 | 20.89 | 34.34 | 8.15
54 | JHARGRAM | SM/18604 | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS | TSM/018025 | 40053530 | New | MVS | 2155/PHE-28011/195/2023-SCHM CELL-Dept. of PHE | 31/07/2023 | 944.65 | 80.49 | 1025.14 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | JHARGRAM | SM/17930 | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | TSM/015763 | 40035126 | New | MVS | GO2223016703PH | 17/03/2023 | 0 | 730.76 | 730.76 | Jhargram Division | Jhargram Mechanical Division | 0 | 102.23 | 0 | 0 | 102.23 | 0 | 102.23 | 0 | 0 | 102.23 | 13.99
56 | JHARGRAM | SM/12385 | Chingra And Adjoining Moujas PWSS | TSM/013079 | 40029232 | New | MVS | GO2223007535PH | 13/09/2022 | 473.85 | 45.37 | 519.22 | Jhargram Division | Jhargram Mechanical Division | 0 | 6.17 | 0 | 32.76 | 38.92 | 0 | 6.17 | 0 | 32.76 | 38.92 | 7.5 | 20
57 | JHARGRAM | SM/12350 | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram | TSM/010230 | 40029384 | New | MVS | GO2223007458PH | 12/09/2022 | 313.49 | 50.23 | 363.72 | Jhargram Division | Jhargram Mechanical Division | 0 | 18.89 | 0 | 32.28 | 51.17 | 0 | 18.89 | 0 | 32.28 | 51.17 | 14.07
58 | JHARGRAM | SM/08081 | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | TSM/006371 | 40009137 | New | SVS | GO2021006205PH | 04/02/2021 | 3498 | 0 | 3498 | Jhargram Division |  | 131.22 | 0 | 0 | 0 | 131.22 | 131.22 | 0 | 0 | 0 | 131.22 | 3.75 | 100
59 | JHARGRAM | SM/12532 | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | TSM/014248 | 40028824 | New | MVS | GO2223007563PH | 13/09/2022 | 302.3 | 36.58 | 338.87 | Jhargram Division | Jhargram Mechanical Division | 53.11 | 12.37 | 0 | 0 | 65.48 | 53.11 | 12.37 | 0 | 0 | 65.48 | 19.32 | 40
60 | JHARGRAM | SM/17927 | DAKAI AND ADJOINING MOUJAS PWSS | TSM/015911 | 40032927 | New | MVS | GO2223016679PH | 17/03/2023 | 388.74 | 67.41 | 456.15 | Jhargram Division | Jhargram Mechanical Division | 43.69 | 0 | 0 | 0 | 43.69 | 43.69 | 0 | 0 | 0 | 43.69 | 9.58
61 | JHARGRAM | SM/12357 | DALKATI AND ADJOINING MOUJAS PWSS | TSM/013203 | 40028490 | New | MVS | GO2223007461PH | 12/09/2022 | 380.1 | 36.45 | 416.55 | Jhargram Division | Jhargram Mechanical Division | 126.34 | 19.54 | 6.26 | 0 | 152.15 | 126.97 | 19.54 | 6.26 | 0 | 152.77 | 36.68 | 50
62 | JHARGRAM | SM/12358 | DARUKULI AND ADJOINING MOUJAS PWSS | TSM/013081 | 40029435 | New | MVS | GO2223007455PH | 12/09/2022 | 379.39 | 38.46 | 417.84 | Jhargram Division | Jhargram Mechanical Division | 0 | 10.68 | 0 | 18.54 | 29.22 | 0 | 10.68 | 0 | 18.54 | 29.22 | 6.99 | 10
63 | JHARGRAM | SM/16992 | DHADANGIRI AND ADJOINING MOUJAS | TSM/011764 | 40032841 | New | MVS | GO2223016558PH | 16/03/2023 | 575.12 | 36.82 | 611.94 | Jhargram Division | Jhargram Mechanical Division | 0 | 3.86 | 12.3 | 9.3 | 25.47 | 0 | 3.86 | 12.3 | 9.3 | 25.47 | 4.16 | 5
64 | JHARGRAM | SM/17581 | DHANSOL AND ADJOINING MOUJAS PWSS | TSM/013095 | 40033034 | New | MVS | GO2223017056PH | 18/03/2023 | 414.8 | 38.52 | 453.32 | Jhargram Division | Jhargram Mechanical Division | 280.79 | 24.65 | 25.79 | 0 | 331.23 | 280.79 | 28.08 | 25.79 | 0 | 334.65 | 73.82 | 65
65 | JHARGRAM | SM/17924 | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | TSM/015892 | 40032980 | New | MVS | GO2223016617PH | 17/03/2023 | 0 | 522.61 | 522.61 | Jhargram Division | Jhargram Mechanical Division | 2.2 | 157.51 | 0 | 0 | 159.71 | 2.2 | 158.06 | 0 | 0 | 160.26 | 30.67
66 | JHARGRAM | SM/16675 | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS | TSM/017880 | 40053536 | New | MVS | GO2223015964PH | 14/03/2023 | 569.36 | 83.11 | 652.47 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | JHARGRAM | SM/16934 | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | TSM/015441 | 40033061 | New | MVS | GO2223016555PH | 16/03/2023 | 622.7 | 39.25 | 661.95 | Jhargram Division | Jhargram Mechanical Division | 334.1 | 24.49 | 30.82 | 0 | 389.4 | 334.1 | 24.49 | 30.82 | 0 | 389.4 | 58.83 | 40
68 | JHARGRAM | SM/17929 | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | TSM/015873 | 40033023 | New | MVS | GO2223016654PH | 17/03/2023 | 0 | 522.47 | 522.47 | Jhargram Division | Jhargram Mechanical Division | 33.25 | 243.44 | 0 | 0 | 276.69 | 33.25 | 243.44 | 0 | 0 | 276.69 | 52.96
69 | JHARGRAM | SM/16993 | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | TSM/015922 | 40032958 | New | MVS | GO2223016557PH | 16/03/2023 | 812.29 | 73.49 | 885.79 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 9.26 | 0 | 9.26 | 0 | 0 | 9.26 | 0 | 9.26 | 1.05 | 20
70 | JHARGRAM | SM/16994 | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS | TSM/015452 | 40032829 | New | MVS | GO2223016560PH | 16/03/2023 | 487.34 | 53.55 | 540.88 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 48.42 | 0 | 48.42 | 0 | 0 | 48.42 | 0 | 48.42 | 8.95 | 20
71 | JHARGRAM | SM/16982 | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | TSM/015762 | 40035141 | New | MVS | GO2223016559PH | 16/03/2023 | 326 | 36.72 | 362.71 | Jhargram Division | Jhargram Mechanical Division | 50.82 | 9.02 | 22.71 | 0 | 82.55 | 50.82 | 9.02 | 22.71 | 0 | 82.55 | 22.76 | 20
72 | JHARGRAM | SM/12438 | DOMAHANI AND ADJOINING MOUJAS PWSS | TSM/014171 | 40029087 | New | MVS | GO2223007505PH | 13/09/2022 | 430.58 | 38.98 | 469.57 | Jhargram Division | Jhargram Mechanical Division | 2.8 | 0 | 7.15 | 10.51 | 20.46 | 2.8 | 0 | 7.15 | 10.51 | 20.46 | 4.36
73 | JHARGRAM | SM/12723 | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | TSM/014335 | 40032389 | New | MVS | GO2223007946PH | 20/09/2022 | 553.09 | 48.6 | 601.69 | Jhargram Division | Jhargram Mechanical Division | 50.23 | 11.73 | 0 | 0 | 61.96 | 50.23 | 11.73 | 0 | 0 | 61.96 | 10.3 | 15
74 | JHARGRAM | SM/12359 | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | TSM/012784 | 40029307 | New | MVS | GO2223007462PH | 12/09/2022 | 548.63 | 38.85 | 587.48 | Jhargram Division | Jhargram Mechanical Division | 336.46 | 12.28 | 21.42 | 0 | 370.16 | 336.46 | 12.28 | 21.42 | 0 | 370.16 | 63.01 | 65
75 | JHARGRAM | SM/17590 | GAJPATHAR AND ADJOINING MOUJAS PWSS | TSM/014453 | 40033013 | New | MVS | GO2223017067PH | 18/03/2023 | 375.75 | 74.9 | 450.65 | Jhargram Division | Jhargram Mechanical Division | 65.24 | 0 | 0 | 0 | 65.24 | 65.24 | 0 | 0 | 0 | 65.24 | 14.48
76 | JHARGRAM | SM/12408 | GHORA PINCHA AND ADJOINING MOJAS PWSS | TSM/013094 | 40029404 | New | MVS | GO2223007538PH | 13/09/2022 | 369.08 | 36.31 | 405.39 | Jhargram Division | Jhargram Mechanical Division | 147.12 | 10.12 | 5.73 | 17.44 | 180.41 | 147.12 | 10.12 | 5.73 | 17.44 | 180.41 | 44.5 | 55
77 | JHARGRAM | SM/17926 | GIDIGHATI AND ADJOINING MOUJAS PWSS | TSM/015912 | 40032942 | New | MVS | GO2223016644PH | 17/03/2023 | 361.52 | 74.9 | 436.42 | Jhargram Division | Jhargram Mechanical Division | 73.78 | 0 | 0 | 0 | 73.78 | 73.78 | 0 | 0 | 0 | 73.78 | 16.91
78 | JHARGRAM | SM/17571 | GOBINDAPUR AND ADJOINING MOUJAS PWSS | TSM/013205 | 40032843 | New | MVS | GO2223017049PH | 18/03/2023 | 426.88 | 36.41 | 463.29 | Jhargram Division | Jhargram Mechanical Division | 239.02 | 14.7 | 0 | 19.52 | 273.24 | 239.02 | 14.7 | 0 | 19.52 | 273.24 | 58.98 | 70
79 | JHARGRAM | SM/12724 | GOBINDAPUR AND ADJOINING MOUJAS PWSS | TSM/014314 | 40032418 | New | MVS | GO2223007834PH | 20/09/2022 | 421.6 | 38.93 | 460.54 | Jhargram Division | Jhargram Mechanical Division | 192.66 | 13.64 | 7.94 | 30.42 | 244.65 | 192.66 | 13.64 | 7.94 | 30.42 | 244.65 | 53.12 | 70
80 | JHARGRAM | SM/12347 | GOBINDAPUR AND ADJOINING MOUJAS PWSS | TSM/011740 | 40027275 | New | MVS | GO2223007466PH | 12/09/2022 | 365.79 | 37.66 | 403.45 | Jhargram Division | Jhargram Mechanical Division | 0 | 6.03 | 7.06 | 19.32 | 32.41 | 0 | 6.03 | 7.06 | 19.32 | 32.41 | 8.03 | 5
81 | JHARGRAM | SM/12329 | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | TSM/013103 | 40029391 | New | MVS | GO2223007402PH | 09/09/2022 | 449.67 | 37.62 | 487.29 | Jhargram Division | Jhargram Mechanical Division | 263.9 | 21.4 | 32.87 | 9.98 | 328.14 | 263.9 | 23.18 | 32.87 | 9.98 | 329.92 | 67.71 | 95
82 | JHARGRAM | SM/17585 | GOHAL BURA AND ADJOINING MOUJAS PWSS | TSM/012735 | 40033028 | New | MVS | GO2223017051PH | 18/03/2023 | 503.92 | 38.52 | 542.43 | Jhargram Division | Jhargram Mechanical Division | 225.27 | 12.82 | 35.28 | 32.42 | 305.79 | 225.27 | 12.82 | 35.28 | 32.42 | 305.79 | 56.37 | 65
83 | JHARGRAM | SM/12340 | GOHALMARA AND ADJOINING MOUJAS PWSS | TSM/011775 | 40027149 | New | MVS | GO2223007472PH | 12/09/2022 | 403.75 | 38.32 | 442.07 | Jhargram Division | Jhargram Mechanical Division | 135.75 | 7.41 | 10.05 | 38.03 | 191.24 | 135.75 | 10.34 | 10.05 | 38.03 | 194.17 | 43.92 | 90
84 | JHARGRAM | SM/12725 | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS | TSM/014556 | 40032411 | New | MVS | GO2223007973PH | 20/09/2022 | 514.06 | 48.61 | 562.67 | Jhargram Division | Jhargram Mechanical Division | 267.85 | 31.53 | 7.2 | 0 | 306.59 | 267.85 | 33.31 | 7.2 | 0 | 308.36 | 54.8 | 60
85 | JHARGRAM | SM/11476 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. | TSM/010652 | 40026724 | New | MVS | GO2223005064PH | 14/07/2022 | 748 | 245 | 993 | Jhargram Division | Jhargram Mechanical Division | 493.41 | 3.56 | 7.32 | 0 | 504.29 | 493.41 | 3.56 | 7.32 | 0 | 504.29 | 50.78 | 40
86 | JHARGRAM | SM/11475 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | TSM/010656 | 40026995 | New | MVS | GO2223005065PH | 14/07/2022 | 741 | 254 | 995 | Jhargram Division | Jhargram Mechanical Division | 517.84 | 3.57 | 6.71 | 0 | 528.12 | 517.84 | 3.57 | 6.71 | 0 | 528.12 | 53.08 | 8
87 | JHARGRAM | SM/11477 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | TSM/010659 | 40026802 | New | MVS | GO2223005066PH | 14/07/2022 | 748 | 237 | 985 | Jhargram Division | Jhargram Mechanical Division | 301.27 | 1.59 | 8.21 | 0 | 311.06 | 301.27 | 1.59 | 8.21 | 0 | 311.06 | 31.58
88 | JHARGRAM | SM/11478 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | TSM/010660 | 40026687 | New | MVS | GO2223005067PH | 14/07/2022 | 745 | 237 | 982 | Jhargram Division | Jhargram Mechanical Division | 159.18 | 3.25 | 7.87 | 0 | 170.3 | 158.7 | 3.25 | 7.87 | 0 | 169.83 | 17.29 | 40
89 | JHARGRAM | SM/11480 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | TSM/010662 | 40026846 | New | MVS | GO2223005068PH | 14/07/2022 | 737 | 237 | 974 | Jhargram Division | Jhargram Mechanical Division | 623.8 | 4.61 | 7.5 | 0 | 635.92 | 623.8 | 4.61 | 7.5 | 0 | 635.92 | 65.29 | 70
90 | JHARGRAM | SM/11479 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | TSM/010661 | 40026878 | New | MVS | GO2223005069PH | 14/07/2022 | 722 | 245 | 967 | Jhargram Division | Jhargram Mechanical Division | 231.92 | 9.94 | 6.73 | 0 | 248.59 | 231.92 | 9.94 | 6.73 | 0 | 248.59 | 25.71
91 | JHARGRAM | SM/11481 | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | TSM/010663 | 40026937 | New | MVS | GO2223005070PH | 14/07/2022 | 371 | 114 | 485 | Jhargram Division | Jhargram Mechanical Division | 0 | 2.1 | 4.05 | 0 | 6.15 | 0 | 2.1 | 4.05 | 0 | 6.15 | 1.27 | 90
92 | JHARGRAM | SM/17039 | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | TSM/020266 | 40053154 | New | MVS | GO2223016491PH | 16/03/2023 | 539.48 | 0 | 539.48 | Jhargram Division | Jhargram Mechanical Division | 85.22 | 0 | 0 | 0 | 85.22 | 85.22 | 0 | 0 | 0 | 85.22 | 15.8
93 | JHARGRAM | SM/12436 | HARDA AND ADJOINING MOUJAS PWSS | TSM/014182 | 40029036 | New | MVS | GO2223007501PH | 13/09/2022 | 775.96 | 41.74 | 817.7 | Jhargram Division | Jhargram Mechanical Division | 614.71 | 15.16 | 55.59 | 37.51 | 722.97 | 614.71 | 15.16 | 55.59 | 37.51 | 722.97 | 88.41 | 50
94 | JHARGRAM | SM/12409 | HARIPURBIRUA AND AJOINING MOUJAS PWSS | TSM/013110 | 40028706 | New | MVS | GO2223007544PH | 13/09/2022 | 797.4 | 38.85 | 836.25 | Jhargram Division | Jhargram Mechanical Division | 485.97 | 6.08 | 93.01 | 17.44 | 602.5 | 485.97 | 6.08 | 93.01 | 17.44 | 602.5 | 72.05 | 65
95 | JHARGRAM | SM/17594 | HIJLA AND ADJOINING MOUJAS PWSS | TSM/014334 | 40033015 | New | MVS | GO2223017078PH | 18/03/2023 | 0 | 463.44 | 463.44 | Jhargram Division | Jhargram Mechanical Division | 22.91 | 92.01 | 0 | 0 | 114.92 | 22.91 | 96.81 | 0 | 0 | 119.71 | 25.83
96 | JHARGRAM | SM/17948 | Installation of Iron Elemination Plant(IEP) and related works in different schemes(Barajharia PWSS, Lalgarh PWSS, Baratilaboni PWSS) within Nayagram and Binpur-I Blocks in Jhargram District under Jhargram Division, PHE Dte. | TSM/017862 | 40065343 | Augmentation | MVS | GO2223016794PH | 17/03/2023 | 84.38 | 1.58 | 85.96 | Jhargram Division | Jhargram Mechanical Division | 38.13 | 0 | 0 | 0 | 38.13 | 38.13 | 0 | 0 | 0 | 38.13 | 44.36 | 30
97 | JHARGRAM | SM/12344 | JAKUA AND ADJOINING MOUJAS PWSS | TSM/011756 | 40027271 | New | MVS | GO2223007468PH | 12/09/2022 | 308.06 | 37.67 | 345.73 | Jhargram Division | Jhargram Mechanical Division | 187.53 | 5.49 | 24.12 | 19.05 | 236.19 | 187.53 | 5.49 | 24.12 | 19.05 | 236.19 | 68.32 | 80
98 | JHARGRAM | SM/12775 | JANGALKHAS AND ADJOINING MOUJAS PWSS | TSM/014319 | 40032433 | New | MVS | GO2223007970PH | 20/09/2022 | 616.7 | 48.68 | 665.38 | Jhargram Division | Jhargram Mechanical Division | 263 | 14.31 | 28.75 | 17.68 | 323.74 | 263 | 14.31 | 28.75 | 17.68 | 323.74 | 48.66 | 85
99 | JHARGRAM | SM/12533 | JIRAPARA AND ADJOINING MOUJAS PWSS | TSM/014214 | 40029012 | New | MVS | GO2223007494PH | 13/09/2022 | 626.69 | 50.79 | 677.48 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 37.1 | 0 | 37.1 | 0 | 0 | 37.1 | 0 | 37.1 | 5.48
100 | JHARGRAM | SM/12342 | JUNSOLA AND ADJOINING MOUJAS PWSS | TSM/011772 | 40027167 | New | MVS | GO2223007464PH | 12/09/2022 | 273.94 | 37.67 | 311.62 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 18.77 | 0 | 18.77 | 0.61 | 0 | 18.77 | 0 | 19.38 | 6.22
101 | JHARGRAM | SM/17597 | KALADABAR AND ADJOINING MOUJAS PWSS | TSM/014482 | 40033083 | New | MVS | GO2223017090PH | 18/03/2023 | 328.22 | 52.43 | 380.65 | Jhargram Division | Jhargram Mechanical Division | 50.09 | 0 | 0 | 0 | 50.09 | 50.09 | 0 | 0 | 0 | 50.09 | 13.16
102 | JHARGRAM | SM/12885 | KAMTA AND ADJOINING MOUZAS PWSS | TSM/013498 | 40027553 | New | MVS | GO2223008165PH | 23/09/2022 | 394.76 | 38.89 | 433.66 | Jhargram Division | Jhargram Mechanical Division | 0 | 4.37 | 0 | 25.35 | 29.73 | 0 | 4.37 | 0 | 25.35 | 29.73 | 6.85 | 30
103 | JHARGRAM | SM/12330 | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | TSM/013100 | 40029427 | New | MVS | GO2223007400PH | 09/09/2022 | 439.92 | 38.46 | 478.38 | Jhargram Division | Jhargram Mechanical Division | 203.53 | 5.87 | 75.49 | 8.72 | 293.61 | 203.53 | 5.87 | 75.49 | 8.72 | 293.61 | 61.38 | 55
104 | JHARGRAM | SM/12454 | KAPGARI AND IT'S ADJOINING MOUJAS PWSS | TSM/014249 | 40029364 | New | MVS | GO2223007495PH | 13/09/2022 | 348.75 | 38.93 | 387.68 | Jhargram Division | Jhargram Mechanical Division | 0 | 8.6 | 0 | 16.21 | 24.81 | 0.61 | 10.36 | 0 | 16.21 | 27.18 | 7.01 | 40
105 | JHARGRAM | SM/12524 | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS | TSM/013054 | 40029270 | New | MVS | GO2223007516PH | 13/09/2022 | 430.95 | 43.86 | 474.81 | Jhargram Division | Jhargram Mechanical Division | 274.39 | 39.91 | 56.9 | 0 | 371.19 | 274.39 | 45.85 | 56.9 | 0 | 377.14 | 79.43 | 80
106 | JHARGRAM | SM/12346 | KENDANA AND ADJOINING MOUJAS PWSS | TSM/011745 | 40027274 | New | MVS | GO2223007471PH | 12/09/2022 | 458.58 | 38.16 | 496.74 | Jhargram Division | Jhargram Mechanical Division | 10.85 | 8.12 | 0 | 38.27 | 57.24 | 10.85 | 8.12 | 0 | 38.27 | 57.24 | 11.52 | 40
107 | JHARGRAM | SM/12446 | KHAMARPARA AND ADJOINING MOUJAS PWSS | TSM/014136 | 40029301 | New | MVS | GO2223007561PH | 13/09/2022 | 381.76 | 38.92 | 420.68 | Jhargram Division | Jhargram Mechanical Division | 166.81 | 10.5 | 33.23 | 17.44 | 227.98 | 166.81 | 10.5 | 33.23 | 17.44 | 227.98 | 54.19 | 90
108 | JHARGRAM | SM/14133 | KHARBANDI AND ADJOINING MOUZAS PWSS | TSM/013520 | 40032913 | New | MVS | GO2223011499PH | 02/01/2023 | 1010.83 | 56.23 | 1067.06 | Jhargram Division | Jhargram Mechanical Division | 157.8 | 0 | 204.22 | 0 | 362.02 | 157.8 | 0 | 204.22 | 0 | 362.02 | 33.93 | 10
109 | JHARGRAM | SM/17592 | KHARIYARATA AND ADJOINING MOUJAS PWSS | TSM/014387 | 40033010 | New | MVS | GO2223017071PH | 18/03/2023 | 391.03 | 52.43 | 443.46 | Jhargram Division | Jhargram Mechanical Division | 83.13 | 0 | 0 | 0 | 83.13 | 83.13 | 0 | 0 | 0 | 83.13 | 18.75
110 | JHARGRAM | SM/12439 | KHAS JANGAL AND ADJOINING MOUJAS PWSS | TSM/014166 | 40029094 | New | MVS | GO2223007504PH | 13/09/2022 | 371.37 | 36.96 | 408.33 | Jhargram Division | Jhargram Mechanical Division | 81.87 | 5.9 | 0 | 19.77 | 107.55 | 81.87 | 5.9 | 0 | 19.77 | 107.55 | 26.34 | 30
111 | JHARGRAM | SM/17587 | KULIANA AND ADJOINING MOUJAS PWSS | TSM/011774 | 40033068 | New | MVS | GO2223017063PH | 18/03/2023 | 272.92 | 37.78 | 310.7 | Jhargram Division | Jhargram Mechanical Division | 56.06 | 17.25 | 0 | 31.69 | 105.01 | 56.06 | 17.25 | 0 | 31.69 | 105.01 | 33.8 | 65
112 | JHARGRAM | SM/12386 | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | TSM/010231 | 40029347 | New | MVS | GO2223007519PH | 13/09/2022 | 261.67 | 49.81 | 311.48 | Jhargram Division | Jhargram Mechanical Division | 0 | 7.02 | 5.48 | 19.23 | 31.73 | 0 | 7.02 | 5.48 | 19.23 | 31.73 | 10.19 | 5
113 | JHARGRAM | SM/12521 | MAHISAMURA & ADJOINING MOUJAS PWSS | TSM/013478 | 40028444 | New | MVS | GO2223007514PH | 13/09/2022 | 359.82 | 36.69 | 396.51 | Jhargram Division | Jhargram Mechanical Division | 0 | 9.66 | 0 | 29.51 | 39.17 | 0 | 9.66 | 0 | 29.51 | 39.17 | 9.88 | 55
114 | JHARGRAM | SM/12534 | MAHULBANI AND ADJOINING MOUJAS PWSS | TSM/014193 | 40029018 | New | MVS | GO2223007502PH | 13/09/2022 | 566.06 | 47.71 | 613.77 | Jhargram Division | Jhargram Mechanical Division | 269.2 | 15.05 | 0 | 6.5 | 290.76 | 269.2 | 15.05 | 0 | 6.5 | 290.76 | 47.37 | 55
115 | JHARGRAM | SM/12525 | MANTIPA & IT'S ADJOINING MOJAS PWSS | TSM/013189 | 40028496 | New | MVS | GO2223007536PH | 13/09/2022 | 364.93 | 36.31 | 401.24 | Jhargram Division | Jhargram Mechanical Division | 0 | 10.59 | 0 | 30.56 | 41.15 | 0 | 10.59 | 0 | 30.56 | 41.15 | 10.26 | 5
116 | JHARGRAM | SM/12437 | METIAL AND ADJOINING MOUJAS PWSS | TSM/014181 | 40029048 | New | MVS | GO2223007560PH | 13/09/2022 | 452.77 | 38.58 | 491.35 | Jhargram Division | Jhargram Mechanical Division | 74.61 | 11.73 | 0 | 33.97 | 120.31 | 74.61 | 11.73 | 0 | 33.97 | 120.31 | 24.49 | 40
117 | JHARGRAM | SM/12440 | MURABANI AND ADJOINING MOUJAS PWSS | TSM/014158 | 40029116 | New | MVS | GO2223007503PH | 13/09/2022 | 372.32 | 38.8 | 411.12 | Jhargram Division | Jhargram Mechanical Division | 129.93 | 10.61 | 7.66 | 0 | 148.2 | 129.93 | 10.61 | 7.66 | 0 | 148.2 | 36.05 | 60
118 | JHARGRAM | SM/12339 | MURAKATI AND ADJOINING MOUJAS PWSS | TSM/013502 | 40027551 | New | MVS | GO2223007460PH | 12/09/2022 | 373.05 | 38.7 | 411.75 | Jhargram Division | Jhargram Mechanical Division | 111.42 | 7.68 | 0 | 12.11 | 131.21 | 111.42 | 7.68 | 0 | 12.11 | 131.21 | 31.87 | 70
119 | JHARGRAM | SM/12776 | NEPURA AND ADJOINING MOUJAS PWSS | TSM/014401 | 40032438 | New | MVS | GO2223007972PH | 20/09/2022 | 738.6 | 85.52 | 824.12 | Jhargram Division | Jhargram Mechanical Division | 190.64 | 9.91 | 13.85 | 7.5 | 221.91 | 190.64 | 11.69 | 13.85 | 7.5 | 223.68 | 27.14 | 40
120 | JHARGRAM | SM/12526 | NOAGOAN AND ADJOINING MOUJAS PWSS | TSM/013102 | 40029410 | New | MVS | GO2223007541PH | 13/09/2022 | 552.71 | 38.6 | 591.31 | Jhargram Division | Jhargram Mechanical Division | 353.56 | 26.15 | 12.23 | 0 | 391.93 | 353.56 | 26.15 | 12.23 | 0 | 391.93 | 66.28 | 65
121 | JHARGRAM | SM/12711 | PALASHBANI AND ADJOINING MOUJAS PWSS | TSM/014218 | 40028834 | New | MVS | GO2223007919PH | 20/09/2022 | 402.88 | 38.87 | 441.75 | Jhargram Division | Jhargram Mechanical Division | 237.82 | 31.14 | 12.18 | 0 | 281.14 | 237.82 | 33.65 | 12.18 | 0 | 283.65 | 64.21 | 90
122 | JHARGRAM | SM/12325 | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | TSM/013140 | 40028722 | New | MVS | GO2223007401PH | 09/09/2022 | 302.89 | 40.13 | 343.02 | Jhargram Division | Jhargram Mechanical Division | 142.5 | 35.42 | 5.77 | 0 | 183.69 | 142.5 | 36.31 | 5.77 | 0 | 184.57 | 53.81 | 65
123 | JHARGRAM | SM/12455 | PARIHATI AND ADJOINING MOUJAS PWSS | TSM/014138 | 40029365 | New | MVS | GO2223007496PH | 13/09/2022 | 439.59 | 47.68 | 487.27 | Jhargram Division | Jhargram Mechanical Division | 0 | 3.25 | 8.41 | 0 | 11.66 | 0 | 4.13 | 8.41 | 0 | 12.54 | 2.57 | 5
124 | JHARGRAM | SM/12531 | PARSHULI AND ADJOINING MOUJAS PWSS | TSM/014282 | 40028813 | New | MVS | GO2223007506PH | 13/09/2022 | 415.48 | 48.14 | 463.62 | Jhargram Division | Jhargram Mechanical Division | 253.65 | 26.61 | 23.45 | 0 | 303.71 | 253.65 | 28.81 | 23.45 | 0 | 305.91 | 65.98 | 95
125 | JHARGRAM | SM/12527 | PATHARNALA AND ADJOINING MOUJAS PWSS | TSM/013218 | 40028459 | New | MVS | GO2223007520PH | 13/09/2022 | 529.6 | 38.65 | 568.25 | Jhargram Division | Jhargram Mechanical Division | 298.06 | 19.98 | 29.22 | 0 | 347.25 | 298.06 | 20.52 | 29.22 | 0 | 347.79 | 61.2 | 85
126 | JHARGRAM | SM/12354 | PETBINDHI AND ADJOINING MOUJAS PWSS | TSM/011771 | 40027186 | New | MVS | GO2223007474PH | 12/09/2022 | 484.29 | 38.08 | 522.37 | Jhargram Division | Jhargram Mechanical Division | 0 | 8.26 | 36.24 | 19.91 | 64.41 | 0 | 8.26 | 36.24 | 19.91 | 64.41 | 12.33 | 5
127 | JHARGRAM | SM/12450 | PINDRAKULI AND ADJOINING MOUJAS PWSS | TSM/014117 | 40029323 | New | MVS | GO2223007507PH | 13/09/2022 | 339.61 | 36.62 | 376.23 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | JHARGRAM | SM/12355 | PITHAPURA AND ADJOINING MOUJAS PWSS | TSM/011776 | 40027074 | New | MVS | GO2223007473PH | 12/09/2022 | 285.41 | 37.71 | 323.12 | Jhargram Division | Jhargram Mechanical Division | 82.97 | 13.71 | 5.71 | 36.84 | 139.24 | 82.97 | 13.71 | 5.71 | 36.84 | 139.24 | 43.09 | 60
129 | JHARGRAM | SM/12777 | RADHANAGAR AND ADJOINING MOUJAS PWSS | TSM/013239 | 40032765 | New | MVS | GO2223007945PH | 20/09/2022 | 527.13 | 38.93 | 566.07 | Jhargram Division | Jhargram Mechanical Division | 249.44 | 31.84 | 42.47 | 0 | 323.75 | 249.44 | 32.14 | 42.47 | 0 | 324.05 | 57.25 | 75
130 | JHARGRAM | SM/12713 | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | TSM/014215 | 40028844 | New | MVS | GO2223007921PH | 20/09/2022 | 685.73 | 56.48 | 742.21 | Jhargram Division | Jhargram Mechanical Division | 264.92 | 7.01 | 51.63 | 6.98 | 330.55 | 264.92 | 7.01 | 51.63 | 6.98 | 330.55 | 44.54 | 60
131 | JHARGRAM | SM/17595 | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | TSM/013231 | 40035127 | New | MVS | GO2223017081PH | 18/03/2023 | 370.17 | 67.41 | 437.57 | Jhargram Division | Jhargram Mechanical Division | 94.11 | 0 | 0 | 0 | 94.11 | 94.11 | 0 | 0 | 0 | 94.11 | 21.51
132 | JHARGRAM | SM/17174 | RAGRA AND ADJOINING MOUJAS PWSS | TSM/013093 | 40033027 | New | MVS | GO2223016582PH | 16/03/2023 | 390.86 | 37.64 | 428.5 | Jhargram Division | Jhargram Mechanical Division | 247.81 | 16.62 | 31.2 | 18.07 | 313.7 | 247.81 | 16.62 | 31.2 | 18.07 | 313.7 | 73.21 | 65
133 | JHARGRAM | SM/14184 | RAJABASA AND ADJOINING MOUJAS PWSS | TSM/014217 | 40033060 | New | MVS | GO2223011498PH | 02/01/2023 | 1214.92 | 77.15 | 1292.08 | Jhargram Division | Jhargram Mechanical Division | 1.34 | 7.41 | 0 | 19.59 | 28.34 | 1.34 | 7.41 | 0 | 19.59 | 28.34 | 2.19
134 | JHARGRAM | SM/12842 | RAJBAND AND ADJOINING MOUJAS PWSS | TSM/013139 | 40028694 | New | MVS | GO2223008077PH | 22/09/2022 | 308.13 | 36.36 | 344.49 | Jhargram Division | Midnapore Mechanical Division | 40.74 | 0 | 0 | 0 | 40.74 | 0 | 0 | 0 | 0 | 0 | 0
135 | JHARGRAM | SM/12332 | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/013153 | 40028728 | New | MVS | GO2223007405PH | 09/09/2022 | 361.35 | 36.31 | 397.66 | Jhargram Division | Jhargram Mechanical Division | 39.79 | 9.75 | 0 | 30.71 | 80.25 | 39.79 | 9.75 | 0 | 30.71 | 80.25 | 20.18 | 30
136 | JHARGRAM | SM/12880 | RAMPURA AND ADJOINING MOUJAS | TSM/011770 | 40027202 | New | MVS | GO2223008160PH | 23/09/2022 | 369.36 | 36.97 | 406.33 | Jhargram Division | Jhargram Mechanical Division | 135.03 | 13.3 | 7.69 | 24.86 | 180.88 | 135.03 | 13.3 | 7.69 | 24.86 | 180.88 | 44.52 | 50
137 | JHARGRAM | SM/12333 | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/012786 | 40029289 | New | MVS | GO2223007399PH | 09/09/2022 | 475.19 | 38.65 | 513.84 | Jhargram Division | Jhargram Mechanical Division | 181.19 | 32.36 | 51.33 | 0 | 264.88 | 181.19 | 32.36 | 51.33 | 0 | 264.88 | 51.55 | 70
138 | JHARGRAM | SM/18012 | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017847 | 40065700 | Augmentation | MVS | GO2223016800PH | 17/03/2023 | 49.97 | 0.53 | 50.5 | Jhargram Division | Jhargram Mechanical Division | 32.93 | 0 | 0 | 0 | 32.93 | 32.93 | 1.81 | 0 | 0 | 34.74 | 68.8 | 100
139 | JHARGRAM | SM/18008 | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017844 | 40045239 | Augmentation | MVS | GO2223016798PH | 17/03/2023 | 43.67 | 13.35 | 57.02 | Jhargram Division | Jhargram Mechanical Division | 28.32 | 0 | 0 | 0 | 28.32 | 28.32 | 0 | 0 | 0 | 28.32 | 49.67 | 95
140 | JHARGRAM | SM/18007 | Rejuvenation (Phase-II) of Ground Water Based Netai PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017845 | 40045274 | Augmentation | MVS | GO2223016816PH | 17/03/2023 | 96.77 | 19 | 115.77 | Jhargram Division | Jhargram Mechanical Division | 44.97 | 7.3 | 0 | 0 | 52.28 | 44.97 | 7.88 | 0 | 0 | 52.86 | 45.66 | 90
141 | JHARGRAM | SM/17959 | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017849 | 40045329 | Augmentation | MVS | GO2223016827PH | 17/03/2023 | 41.56 | 0 | 41.56 | Jhargram Division |  | 17.13 | 0 | 0 | 0 | 17.13 | 17.13 | 0 | 0 | 0 | 17.13 | 41.21 | 99
142 | JHARGRAM | SM/10483 | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008540 | 40016357 | Augmentation | MVS | GO2223000281PH | 13/04/2022 | 13.33 | 15.98 | 29.32 | Jhargram Division | Jhargram Mechanical Division | 10.94 | 15.92 | 0 | 0 | 26.87 | 10.94 | 17.7 | 0 | 0 | 28.64 | 97.71 | 100
143 | JHARGRAM | SM/18002 | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017846 | 40045166 | Augmentation | MVS | GO2223016823PH | 17/03/2023 | 54.3 | 13.35 | 67.65 | Jhargram Division | Jhargram Mechanical Division | 39.42 | 0 | 0 | 0 | 39.42 | 39.42 | 0 | 0 | 0 | 39.42 | 58.28 | 90
144 | JHARGRAM | SM/09376 | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | TSM/008605 | 40002346 | Augmentation | MVS | GO2122005389PH | 12/11/2021 | 106.35 | 24.96 | 131.31 | Jhargram Division | Jhargram Mechanical Division | 59.87 | 8.83 | 1.52 | 0 | 70.22 | 59.87 | 10.61 | 1.52 | 0 | 72 | 54.83 | 100
145 | JHARGRAM | SM/10488 | Rejuvenation of Ground Water Based Netai PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008544 | 0 | Augmentation | MVS | GO2223000282PH | 13/04/2022 | 34.89 | 0 | 34.89 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
146 | JHARGRAM | SM/10489 | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008545 | 40016367 | Augmentation | SVS | GO2223000280PH | 13/04/2022 | 81.98 | 0 | 81.98 | Jhargram Division | Jhargram Mechanical Division | 11.53 | 0 | 0 | 0 | 11.53 | 11.53 | 0 | 0 | 0 | 11.53 | 14.06 | 2
147 | JHARGRAM | SM/10485 | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008541 | 2482073 | Augmentation | MVS | GO2223000279PH | 13/04/2022 | 0 | 0 | 0 | Jhargram Division | Jhargram Mechanical Division | 4.37 | 0 | 0 | 0 | 4.37 | 4.37 | 6.92 | 0 | 0 | 11.3 | INF | 100
148 | JHARGRAM | SM/17956 | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017855 | 40045269 | Augmentation | MVS | GO2223016796PH | 17/03/2023 | 37.19 | 35.89 | 73.08 | Jhargram Division | Jhargram Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0 | 0 | 0.89 | 1.22 | 80
149 | JHARGRAM | SM/17966 | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017853 | 40045344 | Augmentation | MVS | GO2223016830PH | 17/03/2023 | 41.5 | 18.47 | 59.97 | Jhargram Division | Jhargram Mechanical Division | 11.44 | 0 | 0 | 0 | 11.44 | 11.44 | 0.89 | 0 | 0 | 12.33 | 20.55 | 90
150 | JHARGRAM | SM/18010 | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017851 | 40065348 | Augmentation | MVS | GO2223016785PH | 17/03/2023 | 52.57 | 0.53 | 53.1 | Jhargram Division | Jhargram Mechanical Division | 47.4 | 0 | 0 | 0 | 47.4 | 47.4 | 0 | 0 | 0 | 47.4 | 89.27 | 100
151 | JHARGRAM | SM/18014 | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017843 | 40045300 | Augmentation | MVS | GO2223016806PH | 17/03/2023 | 132.16 | 31.82 | 163.98 | Jhargram Division | Jhargram Mechanical Division | 67.34 | 0 | 0 | 0 | 67.34 | 67.34 | 0 | 0 | 0 | 67.34 | 41.06 | 95
152 | JHARGRAM | SM/17965 | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017848 | 40045387 | Augmentation | MVS | GO2223016818PH | 17/03/2023 | 33.36 | 13.35 | 46.72 | Jhargram Division | Jhargram Mechanical Division | 13.83 | 9.56 | 0 | 0 | 23.39 | 13.83 | 9.56 | 0 | 0 | 23.39 | 50.07 | 40
153 | JHARGRAM | SM/17964 | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | TSM/017850 | 40045431 | Augmentation | MVS | GO2223016811PH | 17/03/2023 | 150.57 | 37.47 | 188.03 | Jhargram Division | Jhargram Mechanical Division | 20.17 | 12.35 | 0 | 0 | 32.52 | 20.17 | 12.35 | 0 | 0 | 32.52 | 17.3 | 25
154 | JHARGRAM | SM/08733 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | TSM/007486 | 8383480 | Retrofitting | MVS | GO2122003142PH | 09/09/2021 | 52.37 | 0 | 52.37 | Jhargram Division |  | 51.11 | 0 | 0 | 0 | 51.11 | 51.11 | 0 | 0 | 0 | 51.11 | 97.6 | 100
155 | JHARGRAM | SM/08734 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | TSM/007487 | 8375936 | Retrofitting | SVS | GO2122003142PH | 09/09/2021 | 39.38 | 11.48 | 50.87 | Jhargram Division | Jhargram Mechanical Division | 30.58 | 11.39 | 0 | 0 | 41.97 | 30.58 | 11.39 | 0 | 0 | 41.97 | 82.51 | 100
156 | JHARGRAM | SM/08735 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | TSM/007488 | 8383478 | Retrofitting | MVS | GO2122003142PH | 09/09/2021 | 187.73 | 0 | 187.73 | Jhargram Division |  | 98.16 | 16.79 | 0 | 0 | 114.95 | 98.16 | 16.79 | 0 | 0 | 114.95 | 61.23 | 100
157 | JHARGRAM | SM/08736 | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | TSM/007489 | 8383474 | Retrofitting | SVS | GO2122003142PH | 09/09/2021 | 54.97 | 12.85 | 67.82 | Jhargram Division | Jhargram Mechanical Division | 46.19 | 12.13 | 0 | 0 | 58.31 | 46.19 | 12.13 | 0 | 0 | 58.31 | 85.99 | 100
158 | JHARGRAM | SM/09381 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008548 | 40006512 | Augmentation | SVS | GO2122005387PH | 12/11/2021 | 30.04 | 11.48 | 41.53 | Jhargram Division | Jhargram Mechanical Division | 27.01 | 8.26 | 0 | 0 | 35.27 | 27.01 | 8.26 | 0 | 0 | 35.27 | 84.94 | 100
159 | JHARGRAM | SM/09380 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008551 | 40006093 | Augmentation | SVS | GO2122005387PH | 12/11/2021 | 13.63 | 11.48 | 25.11 | Jhargram Division | Jhargram Mechanical Division | 6.19 | 4.36 | 0 | 0 | 10.54 | 6.19 | 4.36 | 0 | 0 | 10.54 | 41.99 | 100
160 | JHARGRAM | SM/09382 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008547 | 40002476 | Augmentation | SVS | GO2122005387PH | 12/11/2021 | 22.56 | 15.29 | 37.85 | Jhargram Division | Jhargram Mechanical Division | 16.08 | 11.23 | 0 | 0 | 27.31 | 16.08 | 13.31 | 0 | 0 | 29.39 | 77.66 | 100
161 | JHARGRAM | SM/09383 | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008527 | 40002348 | Augmentation | MVS | GO2122005387PH | 12/11/2021 | 128.77 | 12.85 | 141.62 | Jhargram Division | Jhargram Mechanical Division | 118.68 | 9.95 | 5.68 | 0 | 134.3 | 118.68 | 11.72 | 5.68 | 0 | 136.08 | 96.08 | 100
162 | JHARGRAM | SM/06831 | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II | TSM/005672 | 8136221 | Retrofitting | MVS | GO2021001723PH | 06/10/2020 | 97.11 | 0 | 97.11 | Jhargram Division |  | 97.1 | 0 | 0 | 0 | 97.1 | 87.69 | 0 | 0 | 0 | 87.69 | 90.3 | 100
163 | JHARGRAM | SM/06830 | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | TSM/005671 | 8136224 | Retrofitting | MVS | GO2021001722PH | 06/10/2020 | 91.19 | 0 | 91.19 | Jhargram Division |  | 91.17 | 0 | 0 | 0 | 91.17 | 82.61 | 0 | 0 | 0 | 82.61 | 90.59 | 100
164 | JHARGRAM | SM/06832 | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram | TSM/005673 | 8136295 | Retrofitting | MVS | GO2021001724PH | 06/10/2020 | 84.05 | 0 | 84.05 | Jhargram Division |  | 84.05 | 0 | 0 | 0 | 84.05 | 66.23 | 0 | 0 | 0 | 66.23 | 78.8 | 100
165 | JHARGRAM | SM/06833 | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Sankrail | TSM/005674 | 8136194 | Retrofitting | MVS | GO2021001725PH | 06/10/2020 | 67.61 | 0 | 67.61 | Jhargram Division |  | 67.6 | 0 | 0 | 0 | 67.6 | 52.14 | 0 | 0 | 0 | 52.14 | 77.12 | 100
166 | JHARGRAM | SM/06829 | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | TSM/005670 | 8136313 | Retrofitting | MVS | GO2021001721PH | 06/10/2020 | 98.99 | 0 | 98.99 | Jhargram Division |  | 98.99 | 0 | 0 | 0 | 98.99 | 81.65 | 0 | 0 | 0 | 81.65 | 82.48 | 100
167 | JHARGRAM | SM/07875 | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | TSM/006753 | 8175932 | Retrofitting | MVS | GO2021004745PH | 19/01/2021 | 39.75 | 0 | 39.75 | Jhargram Division |  | 38.59 | 0 | 0 | 0 | 38.59 | 38.59 | 0 | 0 | 0 | 38.59 | 97.08 | 100
168 | JHARGRAM | SM/08029 | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | TSM/006531 | 8240251 | Retrofitting | MVS | GO2021005807PH | 29/01/2021 | 337.45 | 0 | 337.45 | Jhargram Division |  | 286.06 | 0 | 0 | 0 | 286.06 | 285.72 | 0 | 0 | 0 | 285.72 | 84.67 | 100
169 | JHARGRAM | SM/06828 | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | TSM/005669 | 8136166 | Retrofitting | MVS | GO2021001719PH | 06/10/2020 | 98.98 | 0 | 98.98 | Jhargram Division |  | 98.97 | 0 | 0 | 0 | 98.97 | 71.01 | 0 | 0 | 0 | 71.01 | 71.74 | 100
170 | JHARGRAM | SM/08173 | Retrofitting to accommodate FHTC under JJM in Bahadurpur P.W.S.S. (Phase-II) within Binpur-I Block | TSM/007031 | 8210648 | Retrofitting | SVS | GO2021006576PH | 08/02/2021 | 4.66 | 0 | 4.66 | Jhargram Division |  | 3.73 | 0 | 0 | 0 | 3.73 | 3.73 | 0 | 0 | 0 | 3.73 | 80.09 | 100
171 | JHARGRAM | SM/09385 | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. | TSM/008669 | 40004258 | Retrofitting | MVS | GO2122005388PH | 12/11/2021 | 8.38 | 0 | 8.38 | Jhargram Division | Jhargram Mechanical Division | 7 | 0 | 0 | 0 | 7 | 6.11 | 0.89 | 0 | 0 | 7 | 83.44 | 100
172 | JHARGRAM | SM/06834 | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. | TSM/005583 | 40035387 | Retrofitting | MVS | GO2021001727PH | 06/10/2020 | 85.93 | 0 | 85.93 | Jhargram Division |  | 85.93 | 0 | 0 | 0 | 85.93 | 84.12 | 0 | 0 | 0 | 84.12 | 97.9 | 100
173 | JHARGRAM | SM/06835 | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. | TSM/005584 | 40035388 | Retrofitting | MVS | GO2021001728PH | 06/10/2020 | 81.41 | 0 | 81.41 | Jhargram Division |  | 81.4 | 0 | 0 | 0 | 81.4 | 78.88 | 0 | 0 | 0 | 78.88 | 96.89 | 100
174 | JHARGRAM | SM/09102 | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) | TSM/008213 | 40065698 | Retrofitting | SVS | GO2122004576PH | 28/10/2021 | 2.68 | 0 | 2.68 | Jhargram Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
175 | JHARGRAM | SM/08174 | Retrofitting to accommodate FHTC under JJM in Junsola P.W.S.S. (Phase-II) within Gopiballavpur-II Block | TSM/007032 | 8231853 | Retrofitting | SVS | GO2021006575PH | 08/02/2021 | 5.13 | 0 | 5.13 | Jhargram Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
176 | JHARGRAM | SM/09386 | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. | TSM/008668 | 40035552 | Retrofitting | MVS | GO2122005388PH | 12/11/2021 | 32.56 | 0 | 32.56 | Jhargram Division |  | 14.63 | 0 | 0 | 0 | 14.63 | 14.63 | 0 | 0 | 0 | 14.63 | 44.92 | 100
177 | JHARGRAM | SM/08175 | Retrofitting to accommodate FHTC under JJM in Lohamelya P.W.S.S. (Phase-II) within Jhargram Block | TSM/007033 | 8231866 | Retrofitting | SVS | PH202134893S000 | 08/02/2021 | 7.8 | 0 | 7.8 | Jhargram Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
178 | JHARGRAM | SM/09384 | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | TSM/008672 | 7481027 | Retrofitting | MVS | GO2122005388PH | 12/11/2021 | 919.72 | 0 | 919.72 | Jhargram Division |  | 569.15 | 0 | 135.64 | 0 | 704.8 | 563.77 | 0 | 135.64 | 0 | 699.41 | 76.05 | 97
179 | JHARGRAM | SM/10439 | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. | TSM/010186 | 40010926 | Retrofitting | MVS | GO2223000188PH | 12/04/2022 | 6.76 | 0 | 6.76 | Jhargram Division |  | 3.8 | 0 | 0 | 0 | 3.8 | 3.8 | 0 | 0 | 0 | 3.8 | 56.24 | 100
180 | JHARGRAM | SM/06827 | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | TSM/005582 | 2482073 | Retrofitting | MVS | GO2021001726PH | 06/10/2020 | 79.24 | 0 | 79.24 | Jhargram Division |  | 79.23 | 0 | 0 | 0 | 79.23 | 66.18 | 0 | 0 | 0 | 66.18 | 83.52 | 100
181 | JHARGRAM | SM/17950 | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | TSM/017859 | 40045302 | Augmentation | MVS | GO2223016832PH | 17/03/2023 | 61.74 | 8.79 | 70.53 | Jhargram Division | Jhargram Mechanical Division | 15.31 | 0 | 0 | 0 | 15.31 | 15.31 | 24.88 | 0 | 0 | 40.19 | 56.98 | 100
182 | JHARGRAM | SM/17945 | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. | TSM/017857 | 40045400 | Augmentation | MVS | GO2223016790PH | 17/03/2023 | 19.03 | 17.94 | 36.98 | Jhargram Division | Jhargram Mechanical Division | 5.23 | 10.33 | 0 | 0 | 15.56 | 5.23 | 10.33 | 0 | 0 | 15.56 | 42.07 | 100
183 | JHARGRAM | SM/18190 | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | TSM/017852 | 40065681 | Augmentation | SVS | GO2223018110PH | 31/03/2023 | 28.73 | 17.94 | 46.68 | Jhargram Division | Jhargram Mechanical Division | 16.04 | 0 | 0 | 0 | 16.04 | 16.04 | 0 | 0 | 0 | 16.04 | 34.36 | 99
184 | JHARGRAM | SM/17580 | SAFTALDIHA AND ADJOINING MOUJAS PWSS | TSM/013222 | 40033026 | New | MVS | GO2223017043PH | 18/03/2023 | 480.44 | 36.34 | 516.78 | Jhargram Division | Jhargram Mechanical Division | 320.72 | 23.83 | 9.24 | 0 | 353.79 | 321.18 | 25.6 | 9.24 | 0 | 356.02 | 68.89 | 80
185 | JHARGRAM | SM/17584 | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | TSM/012754 | 40033050 | New | MVS | GO2223017038PH | 18/03/2023 | 474.83 | 38.85 | 513.68 | Jhargram Division | Jhargram Mechanical Division | 5.88 | 7.7 | 0 | 6.5 | 20.08 | 5.88 | 7.7 | 0 | 6.5 | 20.08 | 3.91 | 5
186 | JHARGRAM | SM/12334 | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | TSM/013071 | 40029224 | New | MVS | GO2223007407PH | 09/09/2022 | 677.08 | 40.14 | 717.22 | Jhargram Division | Jhargram Mechanical Division | 432.17 | 12.55 | 13.91 | 29.03 | 487.66 | 432.17 | 13.16 | 13.91 | 29.03 | 488.27 | 68.08 | 55
187 | JHARGRAM | SM/12520 | SHALUKA AND ADJOINING MOUJAS PWSS | TSM/013489 | 40027565 | New | MVS | GO2223007515PH | 13/09/2022 | 279.43 | 36.72 | 316.15 | Jhargram Division | Jhargram Mechanical Division | 73.85 | 5.94 | 27.53 | 17.69 | 125.01 | 73.85 | 5.94 | 27.53 | 17.69 | 125.01 | 39.54 | 90
188 | JHARGRAM | SM/17591 | SHIYARBINDA AND ADJOINING MOUJAS PWSS | TSM/014447 | 40033667 | New | MVS | GO2223017069PH | 18/03/2023 | 380.25 | 52.43 | 432.68 | Jhargram Division | Jhargram Mechanical Division | 72.76 | 0 | 0 | 0 | 72.76 | 72.76 | 0 | 0 | 0 | 72.76 | 16.82
189 | JHARGRAM | SM/12345 | SHONA KONIA AND ADJOINING MOUJAS PWSS | TSM/011748 | 40027273 | New | MVS | GO2223007465PH | 12/09/2022 | 256.02 | 36.82 | 292.84 | Jhargram Division | Jhargram Mechanical Division | 47.3 | 12.14 | 0 | 27.66 | 87.1 | 47.3 | 13.92 | 0 | 27.66 | 88.88 | 30.35 | 40
190 | JHARGRAM | SM/12519 | SIJUA AND ADJOINING MOUJAS PWSS | TSM/013233 | 40028447 | New | MVS | GO2223007511PH | 13/09/2022 | 472.2 | 36.72 | 508.92 | Jhargram Division | Jhargram Mechanical Division | 106.74 | 10.27 | 7.33 | 13.04 | 137.38 | 106.74 | 11.14 | 7.33 | 13.04 | 138.25 | 27.17 | 60
191 | JHARGRAM | SM/12343 | SIMLADANGA AND ADJOINING MOUJAS PWSS | TSM/011762 | 40027258 | New | MVS | GO2223007467PH | 12/09/2022 | 792.51 | 38.11 | 830.61 | Jhargram Division | Jhargram Mechanical Division | 47.35 | 5.94 | 12.58 | 28.3 | 94.17 | 47.35 | 5.94 | 12.58 | 28.3 | 94.17 | 11.34
192 | JHARGRAM | SM/12326 | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. | TSM/013125 | 40028703 | New | MVS | GO2223007396PH | 09/09/2022 | 433.43 | 36.34 | 469.77 | Jhargram Division | Jhargram Mechanical Division | 24.16 | 0 | 0 | 9.68 | 33.84 | 0 | 0 | 0 | 9.68 | 9.68 | 2.06
193 | JHARGRAM | SM/09915 | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | TSM/008120 | 40004638 | New | MVS | GO2122006627PH | 10/12/2021 | 7538.02 | 2393.39 | 9931.41 | Jhargram Division | Jhargram Mechanical Division | 4247.04 | 1260.48 | 142.21 | 0 | 5649.74 | 4200.05 | 1459.65 | 142.21 | 0 | 5801.91 | 58.42 | 67
194 | JHARGRAM | SM/12528 | SUMITRAPUR AND ADJOINING MOJAS PWSS | TSM/013091 | 40029459 | New | MVS | GO2223007542PH | 13/09/2022 | 495.83 | 38.73 | 534.56 | Jhargram Division | Jhargram Mechanical Division | 270.34 | 8.12 | 0 | 17.41 | 295.87 | 270.34 | 8.12 | 0 | 17.41 | 295.87 | 55.35 | 75
195 | JHARGRAM | SM/12389 | SUSHNI AND ADJOINING MOUJAS PWSS | TSM/013506 | 40027534 | New | MVS | GO2223007547PH | 13/09/2022 | 566.8 | 39.1 | 605.9 | Jhargram Division | Jhargram Mechanical Division | 0 | 3.04 | 0 | 0 | 3.04 | 0 | 3.04 | 0 | 0 | 3.04 | 0.5
196 | JHARGRAM | SM/17932 | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | TSM/015456 | 40032861 | New | MVS | GO2223016664PH | 17/03/2023 | 400.52 | 97.37 | 497.89 | Jhargram Division | Jhargram Mechanical Division | 126.29 | 0 | 0 | 0 | 126.29 | 126.29 | 0 | 0 | 0 | 126.29 | 25.37
197 | JHARGRAM | SM/12341 | TENTULIA AND ADJOINING MOUJAS PWSS | TSM/011773 | 40027160 | New | MVS | GO2223007470PH | 12/09/2022 | 401.21 | 36.98 | 438.2 | Jhargram Division | Jhargram Mechanical Division | 121.65 | 15.19 | 0 | 36.77 | 173.61 | 121.65 | 15.19 | 0 | 36.77 | 173.61 | 39.62 | 80
198 | JHARGRAM | SM/12449 | TENTULIA AND ADJOINING MOUJAS PWSS | TSM/014122 | 40029317 | New | MVS | GO2223007492PH | 13/09/2022 | 379.4 | 36.61 | 416.02 | Jhargram Division | Jhargram Mechanical Division | 0 | 3.93 | 9.23 | 17.86 | 31.02 | 0 | 3.93 | 9.23 | 17.86 | 31.02 | 7.46 | 20
199 | JHARGRAM | SM/12453 | THAKURPARA AND ADJOINING MOUJAS PWSS | TSM/014250 | 40029343 | New | MVS | GO2223007510PH | 13/09/2022 | 623.11 | 65.75 | 688.86 | Jhargram Division | Jhargram Mechanical Division | 263.25 | 18.3 | 37.96 | 40.67 | 360.18 | 263.25 | 18.3 | 37.96 | 40.67 | 360.18 | 52.29 | 60
200 | JHARGRAM | SM/12349 | TIAKITPUR ANAD AJOINING MOUJAS PWSS | TSM/013092 | 40029468 | New | MVS | GO2223007459PH | 12/09/2022 | 378.02 | 37.81 | 415.83 | Jhargram Division | Jhargram Mechanical Division | 105.17 | 9.74 | 0 | 17.44 | 132.35 | 105.17 | 9.74 | 0 | 17.44 | 132.35 | 31.83 | 60
201 | JHARGRAM | SM/12530 | TILABANI AND ADJOINING MOUJAS PWSS | TSM/014285 | 40028796 | New | MVS | GO2223007500PH | 13/09/2022 | 664.18 | 58.82 | 723 | Jhargram Division | Jhargram Mechanical Division | 233.04 | 11.25 | 14.74 | 27.55 | 286.58 | 233.04 | 16.64 | 14.74 | 27.55 | 291.97 | 40.38 | 70
202 | JHARGRAM | SM/17570 | TULIBAR AND ADJOINING MOUZAS PWSS | TSM/013483 | 40033078 | New | MVS | GO2223017041PH | 18/03/2023 | 343.84 | 36.74 | 380.58 | Jhargram Division | Jhargram Mechanical Division | 158.08 | 10.12 | 5.05 | 13.51 | 186.75 | 158.08 | 10.12 | 5.05 | 13.51 | 186.75 | 49.07 | 80
203 | JHARGRAM | SM/12845 | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS | TSM/013075 | 40029432 | New | MVS | GO2223008079PH | 22/09/2022 | 469.64 | 38.46 | 508.1 | Jhargram Division | Jhargram Mechanical Division | 221.02 | 7 | 31.39 | 32.36 | 291.78 | 221.02 | 7 | 31.39 | 32.36 | 291.78 | 57.42 | 60
204 | JHARGRAM | SM/12327 | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | TSM/013123 | 40028719 | New | MVS | GO2223007398PH | 09/09/2022 | 416.91 | 38.52 | 455.43 | Jhargram Division | Jhargram Mechanical Division | 112.03 | 12.22 | 0 | 0 | 124.24 | 112.03 | 12.22 | 0 | 0 | 124.24 | 27.28 | 40
205 | JHARGRAM | SM/12535 | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | TSM/014191 | 40029026 | New | MVS | GO2223007562PH | 13/09/2022 | 613.04 | 38.98 | 652.02 | Jhargram Division | Jhargram Mechanical Division | 351.36 | 24.14 | 60.49 | 0 | 435.99 | 351.36 | 27.66 | 60.49 | 0 | 439.52 | 67.41 | 95
Total | [9 empty] | 87809.23 | 14551.89 | 102361.12 |  |  | 29918.36 | 3907.58 | 2668.89 | 1605.79 | 38100.62 | 29688.3 | 4247.22 | 2668.89 | 1605.79 | 38210.21 | 37.33