## G1- Scheme Physical Progress (R
G1- Scheme Physical Progress (Rs. in Lakh)
Sl. No. | District | Block | Scheme SM Code | Scheme Name | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | Scheme Coverage Type | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | ALIPURDUAR | Alipurduar - II | SM/10668 | AUGMENTATION OF JASHODANGA WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | SVS | 29/04/2022 | 14/03/2023 | 31/05/2025 | 27/01/2026 | 4 | 69.44 | 0.36 | 90 | 1
2 | ALIPURDUAR | Falakata | SM/00016 | DALIMPUR WATER SUPPLY SCHEME | New |  |  |  | MVS | 06/10/1989 | 06/07/2021 |  |  | 3 | 62.67 | 0 | 100 | 0
3 | ALIPURDUAR | Alipurduar - II | SM/10669 | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/04/2022 | 10/08/2022 | 30/06/2025 | 27/01/2026 | 6 | 161.24 | 8.7 | 30 | 5
4 | ALIPURDUAR | Alipurduar - II | SM/00017 | PUTIMARI WATER SUPPLY SCHEME | New |  |  |  | MVS | 28/08/1989 | 24/05/2021 |  |  | 5 | 43.85 | 0 | 100 | 0
5 | ALIPURDUAR | Alipurduar - II | SM/10670 | AUGMENTATION OF SALSALABARI WATER SUPPLY SCHEME. | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 29/04/2022 | 19/09/2022 | 31/07/2025 | 27/01/2026 | 6 | 108.13 | 29.6 | 60 | 27
6 | ALIPURDUAR | Madarihat | SM/00019 | BARA HAUDA & DEBSIMAL AREAS OF BIRPARA TEA GARDEN | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 02/01/1992 | 17/04/2025 |  | 31/07/2019 | 0 | 17.72 | 0 | 100 | 0
7 | ALIPURDUAR | Alipurduar - I | SM/10671 | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 29/04/2022 | 13/05/2022 | 31/05/2025 | 27/01/2026 | 6 | 152.39 | 14.75 | 88 | 10
8 | ALIPURDUAR | Falakata | SM/00023 | JATESWAR WATER SUPPLY SCHEME | New |  |  |  | MVS | 08/11/1966 | 06/07/2021 |  |  | 4 | 5.12 | 0 | 100 | 0
9 | ALIPURDUAR | Madarihat | SM/10672 | AUGMENTATION OF PASCHIM KHAIRBARI WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/04/2022 | 10/08/2022 | 31/07/2025 | 27/01/2026 | 4 | 162.74 | 0 | 75 | 0
10 | ALIPURDUAR | Kalchini | SM/00026 | KALCHINI WATER SUPPLY SCHEME | New |  |  |  | MVS | 16/06/1970 | 27/04/2021 |  |  | 4 | 5.72 | 7.31 | 100 | 128
11 | ALIPURDUAR | Alipurduar - II | SM/10673 | AUGMENTATION OF LOKNATHPUR WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 29/04/2022 | 13/05/2022 | 30/06/2025 | 27/01/2026 | 7 | 252.98 | 16.34 | 85 | 6
12 | ALIPURDUAR | Kumargram | SM/00032 | KAIJALI BASTY WATER SUPPLY SCHEME | New |  |  |  | MVS | 27/02/1979 | 02/11/2020 |  |  | 5 | 10.5 | 0 | 100 | 0
13 | ALIPURDUAR | Alipurduar - I | SM/10674 | AUGMENTATION OF BANCHUKAMARI WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/04/2022 | 10/08/2022 | 31/07/2025 | 27/01/2026 | 6 | 236.97 | 0 | 70 | 0
14 | ALIPURDUAR | Kalchini | SM/00034 | JAYANTI WATER SUPPLY SCHEME | New |  |  |  | MVS | 27/02/1979 | 05/10/2020 |  |  | 5 | 13.3 | 0 | 100 | 0
15 | ALIPURDUAR | Alipurduar - I | SM/10675 | AUGMENTATION OF MUNSHIPARA WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/04/2022 | 16/03/2023 | 31/10/2025 | 27/01/2026 | 2 | 178.64 | 51.29 | 85 | 29
16 | ALIPURDUAR | Madarihat | SM/00035 | BIRPARA WATR SUPPLY SCHEME | New |  |  |  | MVS | 27/02/1979 | 16/09/2020 |  |  | 7 | 12.3 | 0 | 100 | 0
17 | ALIPURDUAR | Alipurduar - I | SM/10676 | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/04/2022 | 13/05/2022 | 31/05/2025 | 27/01/2026 | 6 | 252.39 | 5.02 | 85 | 2
18 | ALIPURDUAR | Madarihat | SM/00039 | NEPANIA WATER SCHEME (NORTH BANDAPARA TEA GARDEN) | New |  |  |  | MVS | 20/03/1982 |  |  |  | 0 | 8.7 | 0 | 100 | 0
19 | ALIPURDUAR | Alipurduar - II | SM/10677 | AUGMENTATION OF CHANDIRJHAR WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/04/2022 | 13/05/2022 | 31/05/2025 | 27/01/2026 | 7 | 192.09 | 8.65 | 85 | 5
20 | ALIPURDUAR | Madarihat | SM/00043 | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | New |  |  |  | MVS | 22/02/1989 | 23/04/2020 |  | 01/01/1996 | 6 | 54.06 | 0 | 100 | 0
21 | ALIPURDUAR | Falakata | SM/10678 | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 29/04/2022 | 01/03/2023 | 31/05/2025 | 27/01/2026 | 6 | 274.45 | 23.86 | 90 | 9
22 | ALIPURDUAR | Kumargram | SM/00044 | KUMARGRAM WATER SUPPLY SCHEME | New |  |  |  | MVS | 22/02/1989 | 04/09/2020 |  |  | 8 | 67.46 | 0 | 100 | 0
23 | ALIPURDUAR | Falakata | SM/00138 | FALAKATA WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 29/01/1979 | 25/03/1979 | 24/03/1982 | 27/01/2026 | 5 | 14.89 | 0 |  | 0
24 | ALIPURDUAR | Madarihat | SM/00139 | UTTAR MADARIHAT WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 28/01/1979 | 28/03/1979 | 02/01/1983 | 27/01/2026 | 4 | 8.15 | 0 |  | 0
25 | ALIPURDUAR | Kalchini | SM/00142 | JOYGAON WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 16/11/1979 | 21/02/1979 | 20/03/1983 | 27/01/2026 | 0 | 25.4 | 0 |  | 0
26 | ALIPURDUAR | Kalchini | SM/00143 | HASIMARA AREAS WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 10/09/1981 | 14/02/1981 | 31/03/1984 | 27/01/2026 | 2 | 28.69 | 0 |  | 0
27 | ALIPURDUAR | Alipurduar - I | SM/00144 | DAKSHIN SONARPUR WATER SUPPLY SCHEME | New | Northern Mechanical Division II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 27/12/1983 | 27/12/1983 | 31/12/2014 | 27/01/2026 | 4 | 48.93 | 0 |  | 0
28 | ALIPURDUAR | Alipurduar - II | SM/00145 | BHATIBARI WATER SUPPLY SCHEME | New |  |  |  | MVS | 13/11/1984 | 01/06/2009 | 31/12/2014 | 27/01/2026 | 5 | 50.07 | 0 |  | 0
29 | ALIPURDUAR | Falakata | SM/10776 | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | MVS | 23/05/2022 | 31/05/2022 | 31/05/2025 | 27/01/2026 | 2 | 167.97 | 97.37 | 91 | 58
30 | ALIPURDUAR | Alipurduar - II | SM/00146 | SAMUKTALA WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 13/11/1984 | 12/02/1985 | 31/12/2014 | 27/01/2026 | 6 | 39.4 | 0 |  | 0
31 | ALIPURDUAR | Kumargram | SM/00147 | BAROBISA AREA WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | MVS | 13/11/1984 | 14/02/1985 | 31/03/1988 | 27/01/2026 | 3 | 53.26 | 0 |  | 0
32 | ALIPURDUAR | Alipurduar - II | SM/00148 | TOTPARA WATER SUPPLY SCHEME | New |  |  |  | MVS | 29/03/1985 | 11/02/1985 | 02/03/1987 | 27/01/2026 | 8 | 8.53 | 0 |  | 0
33 | ALIPURDUAR | Alipurduar - I | SM/00150 | BHOLARDABARI WATER SUPPLY SCHEME | New |  |  |  | MVS | 13/06/1989 | 11/06/1988 | 31/12/2014 | 27/01/2026 | 2 | 28.35 | 0 |  | 0
34 | ALIPURDUAR | Alipurduar - I | SM/11401 | AUGMENTATION OF PATLAKHAWA WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 04/07/2022 | 07/07/2022 | 31/07/2025 | 27/01/2026 | 9 | 140.89 | 126.06 | 75 | 89
35 | ALIPURDUAR | Alipurduar - I | SM/00151 | PATLAKHAWA WATER SUPPLY SCHEME | New |  |  |  | MVS | 14/07/1992 | 10/01/1996 | 31/12/2014 | 27/01/2026 | 2 | 43.56 | 0 |  | 0
36 | ALIPURDUAR | Kalchini | SM/11402 | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 04/07/2022 | 07/07/2022 | 30/06/2025 | 27/01/2026 | 8 | 86.31 | 55.06 | 90 | 64
37 | ALIPURDUAR | Alipurduar - II | SM/00152 | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | New |  |  |  | MVS | 14/07/1992 | 14/02/1996 | 10/01/1998 | 27/01/2026 | 2 | 57.05 | 0 |  | 0
38 | ALIPURDUAR | Alipurduar - I | SM/11459 | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 12/07/2022 | 15/07/2022 | 31/07/2025 | 27/01/2026 | 43 | 1873.61 | 830.13 | 72 | 44
39 | ALIPURDUAR | Alipurduar - I | SM/00153 | PURBA KANTHALBARI WATER SUPPLY SCHEME | New |  |  |  | MVS | 14/07/1992 | 12/11/1995 | 31/12/2014 | 27/01/2026 | 3 | 69.59 | 0 |  | 0
40 | ALIPURDUAR | Kumargram | SM/11482 | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 14/07/2022 | 15/07/2022 | 31/05/2025 | 27/01/2026 | 18 | 395.23 | 153.61 | 90 | 39
41 | ALIPURDUAR | Kumargram | SM/00156 | NARTHALI WATER SUPPLY SCHEME | New |  |  |  | MVS | 26/12/1995 | 21/03/1996 | 31/03/1999 | 27/01/2026 | 3 | 56.73 | 0 |  | 0
42 | ALIPURDUAR | Madarihat | SM/11483 | Bandpani Tea Garden Areas Piped Water Supply Scheme. | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 14/07/2022 | 15/07/2022 | 30/06/2025 | 27/01/2026 | 18 | 528.37 | 183.88 | 80 | 35
43 | ALIPURDUAR | Falakata | SM/00157 | BHUTNIRGHAT WATER SUPPLY SCHEME | New |  |  |  | MVS | 19/01/2005 | 22/03/1996 | 31/12/2014 | 27/01/2026 | 4 | 63.46 | 0 |  | 0
44 | ALIPURDUAR | Kumargram | SM/11484 | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 14/07/2022 | 15/07/2022 | 31/05/2025 | 27/01/2026 | 15 | 455.23 | 200.54 | 90 | 44
45 | ALIPURDUAR | Falakata | SM/00848 | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | New | Northern Mechanical Division II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 1, Northern Mechanical Division-II,PHE Dte. | MVS | 16/11/2005 | 16/11/2005 | 30/11/2013 | 27/01/2026 | 3 | 85.65 | 0 |  | 0
46 | ALIPURDUAR | Kumargram | SM/11485 | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 14/07/2022 | 15/07/2022 | 31/12/2025 | 27/01/2026 | 13 | 389.92 | 174.68 | 90 | 45
47 | ALIPURDUAR | Madarihat | SM/00892 | LANKAPARA WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 19/01/2005 | 08/07/2021 |  | 31/03/2010 | 4 | 86.55 | 0 |  | 0
48 | ALIPURDUAR | Madarihat | SM/00895 | UTTAR SISUBARI WATER SUPPLY SCHEME | New |  |  |  | MVS | 18/02/2003 | 31/03/2007 | 25/02/2010 | 27/01/2026 | 3 | 95.02 | 0 |  | 0
49 | ALIPURDUAR | Madarihat | SM/11696 | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/07/2022 | 10/11/2022 | 31/05/2025 | 27/01/2026 | 9 | 411.35 | 166.74 | 85 | 41
50 | ALIPURDUAR | Kalchini | SM/01021 | UTTAR LATABARI (NM) WATER SUPPLY SCHEME | New |  |  |  | MVS | 25/03/2003 | 28/03/2003 | 05/09/2013 | 27/01/2026 | 1 | 117.79 | 0 |  | 0
51 | ALIPURDUAR | Alipurduar - II | SM/11709 | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 29/07/2022 | 10/11/2022 | 31/05/2025 | 27/01/2026 | 25 | 817.44 | 489.45 | 95 | 60
52 | ALIPURDUAR | Kumargram | SM/01022 | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 29/08/2003 | 23/02/2004 | 03/03/2012 | 27/01/2026 | 7 | 116.58 | 0 |  | 0
53 | ALIPURDUAR | Falakata | SM/01083 | RAICHENGA PIPED WATER SUPPLY SCHEME | New |  |  |  | MVS | 23/02/2004 |  |  | 31/07/2019 | 0 | 2.52 | 0 | 100 | 0
54 | ALIPURDUAR | Madarihat | SM/11765 | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | SVS | 03/08/2022 | 04/04/2023 | 31/05/2025 | 27/01/2026 | 5 | 154.07 | 51.71 | 60 | 34
55 | ALIPURDUAR | Alipurduar - I | SM/01158 | SALKUMARHAT RURAL WATER SUPPLY SCHEME | New |  |  |  | MVS | 16/01/2007 | 25/03/2007 | 15/01/2011 | 27/01/2026 | 0 | 110.19 | 0 |  | 0
56 | ALIPURDUAR | Madarihat | SM/11766 | AUGMENTATION OF NEPANIA PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 03/08/2022 | 13/12/2022 | 31/07/2025 | 27/01/2026 | 4 | 88.14 | 30.66 | 75 | 35
57 | ALIPURDUAR | Alipurduar - II | SM/01378 | Parokata water supply scheme | New |  |  |  | MVS | 06/12/2007 | 06/12/2007 | 31/10/2011 | 27/01/2026 | 1 | 197.32 | 0 |  | 0
58 | ALIPURDUAR | Madarihat | SM/11767 | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | MVS | 03/08/2022 | 13/12/2022 | 31/12/2025 | 27/01/2026 | 14 | 204.15 | 44.96 | 80 | 22
59 | ALIPURDUAR | Madarihat | SM/01416 | Makrapara Water Supply Scheme | New |  |  |  | MVS | 05/10/2007 | 22/07/2025 |  | 31/07/2019 | 0 | 92 | 0 | 100 | 0
60 | ALIPURDUAR | Kumargram | SM/11958 | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 25/08/2022 | 21/11/2022 | 30/11/2025 | 27/01/2026 | 15 | 562.16 | 81.77 | 85 | 15
61 | ALIPURDUAR | Madarihat | SM/11959 | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 25/08/2022 | 19/05/2023 | 30/06/2025 | 27/01/2026 | 8 | 648.63 | 17.13 | 65 | 3
62 | ALIPURDUAR | Madarihat | SM/11960 | AUGMENTATION OF DALMORE & RAMJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 25/08/2022 | 22/12/2022 | 30/06/2025 | 27/01/2026 | 8 | 512.91 | 59.23 | 72 | 12
63 | ALIPURDUAR | Alipurduar - I | SM/11970 | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | Augmentation | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | MVS | 29/08/2022 | 05/09/2022 | 31/12/2025 | 27/01/2026 | 24 | 1275.43 | 227.94 | 70 | 18
64 | ALIPURDUAR | Alipurduar - I | SM/01803 | Water Supply Scheme for Salkumarhat Mouza | New |  |  |  | MVS | 16/01/2007 | 25/03/2007 | 15/01/2011 | 27/01/2026 | 2 | 110.19 | 0 |  | 0
65 | ALIPURDUAR | Madarihat | SM/02173 | Makrapara W/S Scheme | New |  |  |  | MVS | 05/10/2007 | 08/07/2021 |  | 31/03/2011 | 3 | 92 | 0 | 100 | 0
66 | ALIPURDUAR | Kumargram | SM/11985 | AUGMENTATION OF KUMARGRAM PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 01/09/2022 | 05/09/2022 | 30/06/2025 | 27/01/2026 | 26 | 2156.38 | 650.9 | 75 | 30
67 | ALIPURDUAR | Kumargram | SM/11991 | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 01/09/2022 | 21/11/2022 | 31/05/2025 | 27/01/2026 | 12 | 432.05 | 212.38 | 90 | 49
68 | ALIPURDUAR | Kumargram | SM/11992 | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Birpara Sub Division | MVS | 01/09/2022 | 21/11/2022 | 31/05/2025 | 27/01/2026 | 11 | 269.79 | 73.91 | 85 | 27
69 | ALIPURDUAR | Alipurduar - II | SM/12113 | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 02/09/2022 | 21/11/2022 | 31/07/2025 | 27/01/2026 | 17 | 821.35 | 281.54 | 81 | 34
70 | ALIPURDUAR | Kumargram | SM/12114 | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 02/09/2022 | 21/11/2022 | 30/04/2027 | 27/01/2026 | 21 | 588.27 | 133.39 | 90 | 23
71 | ALIPURDUAR | Madarihat | SM/03080 | Totopara Water Supply Scheme | New |  |  |  | MVS |  | 25/07/2025 |  |  | 8 | 6.33 | 0 | 100 | 0
72 | ALIPURDUAR | Madarihat | SM/03081 | Rej. of Totopara Water Supply | Augmentation |  |  |  | MVS |  | 01/03/2008 | 31/03/2010 | 27/01/2026 | 0 | 37.54 | 0 |  | 0
73 | ALIPURDUAR | Falakata | SM/03082 | Bhutnirghat Ghat and Adj. Mouzas Water Supply Scheme | New |  |  |  | MVS |  | 28/03/2005 | 31/12/2007 | 27/01/2026 | 0 | 55.93 | 0 |  | 0
74 | ALIPURDUAR | Kalchini | SM/12361 | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | MVS | 13/09/2022 | 10/01/2023 | 30/06/2025 | 27/01/2026 | 22 | 1269.79 | 49.85 | 35 | 4
75 | ALIPURDUAR | Kalchini | SM/03317 | Augmentation water supply scheme for Jayanty water supply scheme. | Augmentation |  |  |  | MVS | 23/02/2011 |  |  | 31/05/2017 | 0 | 53.69 | 0 | 100 | 0
76 | ALIPURDUAR | Alipurduar - II | SM/12561 | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 14/09/2022 | 19/09/2022 | 30/04/2026 | 27/01/2026 | 44 | 1852.66 | 1010.97 | 85 | 55
77 | ALIPURDUAR | Alipurduar - I | SM/03561 | Alipurduar Municipal Water Supply Scheme | New |  |  |  | MVS | 24/02/1981 | 07/10/2020 |  |  | 5 | 0 | 0 | 100 | NAN
78 | ALIPURDUAR | Alipurduar - I | SM/03602 | Water Supply Scheme for Birpara Mouzas | New |  |  |  | MVS | 02/09/2016 | 21/12/2011 | 31/12/2014 | 27/01/2026 | 0 | 352.92 | 0 |  | 0
79 | ALIPURDUAR | Alipurduar - I | SM/03708 | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | New |  |  |  | MVS | 25/01/2012 | 06/09/2012 | 30/09/2014 | 27/01/2026 | 3 | 373.86 | 0.15 | 5 | 0
80 | ALIPURDUAR | Madarihat | SM/12753 | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 20/09/2022 | 27/03/2023 | 30/06/2025 | 27/01/2026 | 9 | 797.79 | 116.21 | 88 | 15
81 | ALIPURDUAR | Alipurduar - II | SM/03828 | Water Supply Scheme for Purba Chenpani & adj. mouzas | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 27/04/2012 | 17/04/2012 | 31/12/2014 | 27/01/2026 | 5 | 364.81 | 0.92 |  | 0
82 | ALIPURDUAR | Alipurduar - I | SM/12754 | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | MVS | 20/09/2022 | 31/03/2023 | 30/04/2027 | 27/01/2026 | 8 | 415.72 | 11.37 | 68 | 3
83 | ALIPURDUAR | Alipurduar - I | SM/03829 | Water Supply Scheme for Tapashikhata & adj. mouzas | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 27/04/2012 | 17/04/2012 | 31/12/2014 | 27/01/2026 | 5 | 420.23 | 0.58 |  | 0
84 | ALIPURDUAR | Madarihat | SM/03908 | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | New |  |  |  | MVS | 02/09/2016 | 05/02/2013 | 31/12/2017 | 27/01/2026 | 8 | 460.75 | 46.53 | 100 | 10
85 | ALIPURDUAR | Alipurduar - II | SM/04006 | Ground water based water supply scheme for Bakla and adjoining mouzas | New |  |  |  | MVS | 02/09/2016 | 21/05/2013 | 30/06/2017 | 27/01/2026 | 5 | 415.27 | 62.83 | 100 | 15
86 | ALIPURDUAR | Alipurduar - II | SM/04011 | Ground water based water supply scheme for Salsalabari and adjoining mouza | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 02/09/2016 | 15/05/2013 | 31/08/2019 | 27/01/2026 | 8 | 411.33 | 63.78 | 100 | 16
87 | ALIPURDUAR | Falakata | SM/04039 | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | New |  |  |  | MVS | 02/09/2016 | 08/06/2013 | 31/08/2019 | 27/01/2026 | 3 | 344.15 | 8.31 | 100 | 2
88 | ALIPURDUAR | Alipurduar - II | SM/04129 | Water Supply Scheme for Chandijhar & adj. mouzas. | New |  |  |  | MVS | 28/03/2013 | 06/11/2013 | 30/04/2017 | 27/01/2026 | 5 | 375.38 | 2.75 | 100 | 1
89 | ALIPURDUAR | Alipurduar - II | SM/04157 | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | New | Northern Mechanical Division II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 16/05/2013 | 17/08/2013 | 30/04/2017 | 27/01/2026 | 4 | 262.88 | 2.13 | 100 | 1
90 | ALIPURDUAR | Alipurduar - I | SM/04216 | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | New |  |  |  | MVS | 02/09/2016 | 11/04/2017 | 31/08/2019 | 27/01/2026 | 2 | 461.34 | 12.1 | 100 | 3
91 | ALIPURDUAR | Alipurduar - II | SM/04487 | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | New |  |  |  | MVS | 02/09/2016 | 07/01/2014 | 31/08/2019 | 27/01/2026 | 5 | 524.33 | 154.77 | 100 | 30
92 | ALIPURDUAR | Falakata | SM/13239 | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick),RWS Falakata Block | MVS | 14/10/2022 | 17/01/2023 | 31/05/2025 | 27/01/2026 | 15 | 716.98 | 357.99 | 88 | 50
93 | ALIPURDUAR | Madarihat | SM/04770 | Water Supply Scheme for Mujnai Tea Garden Mouza. | New |  |  |  | MVS | 19/05/2014 | 19/07/2014 | 31/05/2025 | 27/01/2026 | 7 | 294.94 | 122.9 | 90 | 42
94 | ALIPURDUAR | Kumargram | SM/13240 | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 14/10/2022 | 17/01/2023 | 30/06/2025 | 27/01/2026 | 7 | 741.26 | 204.24 | 88 | 28
95 | ALIPURDUAR | Kumargram | SM/13241 | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 14/10/2022 | 17/01/2023 | 30/06/2025 | 27/01/2026 | 12 | 780.16 | 186.44 | 50 | 24
96 | ALIPURDUAR | Madarihat | SM/04788 | Dhumchipara Tea Garden Piped Water Supply Scheme | New |  |  |  | MVS | 02/09/2016 | 16/07/2014 | 31/08/2019 | 27/01/2026 | 11 | 485.88 | 284.31 | 100 | 59
97 | ALIPURDUAR | Kumargram | SM/13242 | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 14/10/2022 | 16/03/2023 | 31/05/2025 | 27/01/2026 | 12 | 615.61 | 2.41 | 55 | 0
98 | ALIPURDUAR | Madarihat | SM/04790 | Gargenda Tea Garden Piped Water Supply Scheme | New | Northern Mechanical Division II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 02/09/2016 | 30/07/2014 | 31/08/2019 | 27/01/2026 | 12 | 435.8 | 228.55 | 100 | 52
99 | ALIPURDUAR | Alipurduar - II | SM/13243 | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 14/10/2022 | 27/03/2023 | 30/04/2026 | 27/01/2026 | 11 | 963.61 | 284.79 | 89 | 30
100 | ALIPURDUAR | Alipurduar - I | SM/04810 | Paitkapara Tea Garden Piped Water Supply Scheme | New |  |  |  | MVS | 02/09/2016 | 20/01/2016 | 31/05/2025 | 27/01/2026 | 6 | 310.92 | 170 | 95 | 55
101 | ALIPURDUAR | Kalchini | SM/13244 | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | MVS | 14/10/2022 | 27/03/2023 | 31/05/2025 | 27/01/2026 | 12 | 710.27 | 104.66 | 88 | 15
102 | ALIPURDUAR | Falakata | SM/04848 | Chhota Salkumar Piped Water Supply Scheme | New | Alipurduar Mechanical Sub Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 02/09/2016 | 17/03/2015 | 31/05/2025 | 27/01/2026 | 6 | 524.58 | 363.21 | 90 | 69
103 | ALIPURDUAR | Kalchini | SM/13245 | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | MVS | 14/10/2022 | 17/01/2023 | 30/06/2025 | 27/01/2026 | 8 | 969.65 | 597.02 | 85 | 62
104 | ALIPURDUAR |  | SM/04963 | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | New |  |  |  | MVS | 15/12/2014 |  | 30/06/2021 | 31/05/2021 | 5 | 58.62 | 0.05 | 20 | 0
105 | ALIPURDUAR | Alipurduar - I | SM/13246 | BARIGURI PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | MVS | 14/10/2022 | 16/05/2023 | 31/07/2025 | 27/01/2026 | 10 | 895.77 | 15.83 | 70 | 2
106 | ALIPURDUAR |  | SM/04964 | Construction of 300 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 2014-2015 | New |  |  |  | MVS | 02/09/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 408.96 | 0.47 | 80 | 0
107 | ALIPURDUAR | Alipurduar - I | SM/13247 | PRODHANPARA PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | MVS | 14/10/2022 | 16/03/2023 | 31/05/2025 | 27/01/2026 | 6 | 638.14 | 0 | 85 | 0
108 | ALIPURDUAR | Madarihat | SM/13248 | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | MVS | 14/10/2022 | 27/03/2023 | 31/05/2025 | 27/01/2026 | 12 | 877.17 | 0 | 82 | 0
109 | ALIPURDUAR | Madarihat | SM/05108 | Augmentation of Makrapara Tea Garden Piped Water Supply Scheme | Augmentation |  |  |  | MVS | 12/02/2015 | 26/02/2016 | 31/12/2023 | 27/01/2026 | 1 | 114.22 | 95.01 | 100 | 83
110 | ALIPURDUAR | Kalchini | SM/13249 | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 14/10/2022 | 23/03/2023 | 31/10/2025 | 27/01/2026 | 19 | 860.22 | 12.77 | 20 | 1
111 | ALIPURDUAR | Alipurduar - II | SM/13299 | KAYAKHATA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 17/10/2022 | 16/03/2023 | 31/12/2025 | 27/01/2026 | 10 | 682.41 | 142.96 | 75 | 21
112 | ALIPURDUAR | Kumargram | SM/05155 | Augmentation of Barovisa Water Supply Scheme | Augmentation |  |  |  | MVS | 25/02/2015 | 09/11/2015 | 31/12/2025 | 27/01/2026 | 13 | 706.5 | 219.65 | 98 | 31
113 | ALIPURDUAR | Alipurduar - II | SM/13300 | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 17/10/2022 | 17/01/2023 | 31/05/2025 | 27/01/2026 | 16 | 944.2 | 328.71 | 90 | 35
114 | ALIPURDUAR | Kumargram | SM/05187 | Jayanti Tea Garden Piped Water Supply Scheme | New |  |  |  | MVS | 02/09/2016 | 02/07/2015 | 31/12/2023 | 27/01/2026 | 10 | 311.22 | 246.78 | 100 | 79
115 | ALIPURDUAR | Alipurduar - II | SM/13301 | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 17/10/2022 | 17/01/2023 | 31/07/2025 | 27/01/2026 | 12 | 875.66 | 277.31 | 70 | 32
116 | ALIPURDUAR | Kalchini | SM/05189 | Dima Tea Garden Piped Water Supply Scheme | New |  |  |  | MVS | 02/09/2016 | 09/11/2015 | 30/09/2021 | 27/01/2026 | 5 | 368.23 | 337.72 | 100 | 92
117 | ALIPURDUAR | Alipurduar - I | SM/13302 | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | SVS | 17/10/2022 | 19/01/2023 | 30/11/2025 | 27/01/2026 | 5 | 171.75 | 51.2 | 85 | 30
118 | ALIPURDUAR | Alipurduar - II | SM/05197 | Dhaolajhora Tea Garden Piped Water Supply Scheme | New |  |  |  | MVS | 02/09/2016 | 09/11/2015 | 30/04/2026 | 27/01/2026 | 2 | 295.49 | 245.41 | 80 | 83
119 | ALIPURDUAR | Kumargram | SM/13303 | TELIPARA PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 17/10/2022 | 31/03/2023 | 30/11/2025 | 27/01/2026 | 11 | 488.14 | 77.33 | 90 | 16
120 | ALIPURDUAR | Alipurduar - I | SM/05243 | Improvement of Dakshin Sonapur Water Supply Scheme by construction of Over Head Reservoir. | Augmentation |  |  |  | MVS | 26/08/2015 | 27/04/2015 | 31/12/2017 | 27/01/2026 | 2 | 90 | 135.05 | 100 | 150
121 | ALIPURDUAR | Kumargram | SM/13304 | MARAKHATA PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 17/10/2022 | 17/01/2023 | 31/05/2025 | 27/01/2026 | 11 | 839.09 | 216.9 | 86 | 26
122 | ALIPURDUAR |  | SM/05248 | Construction of 150 nos. Rig Bored Tube Well fitted with India Mark-II hand pump in 2015-2016 | New |  |  |  | MVS | 26/10/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 204.48 | 0.2 |  | 0
123 | ALIPURDUAR | Alipurduar - II | SM/13305 | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 17/10/2022 | 17/01/2023 | 30/04/2027 | 27/01/2026 | 12 | 760.21 | 292.51 | 85 | 38
124 | ALIPURDUAR | Alipurduar - I | SM/13306 | KALABERIA PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | MVS | 17/10/2022 | 27/03/2023 | 30/11/2025 | 27/01/2026 | 7 | 461.28 | 47.11 | 75 | 10
125 | ALIPURDUAR |  | SM/05395 | State Information Education Communication (IEC) Activity for Sustainable Community Development in the Year of 2015-2016 under NRDWP Support Fund | New |  |  |  | MVS | 16/10/2015 |  | 30/04/2018 | 31/03/2018 | 0 | 980.27 | 0 | 100 | 0
126 | ALIPURDUAR | Kumargram | SM/13448 | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 02/11/2022 | 06/06/2023 | 30/11/2025 | 27/01/2026 | 7 | 305.16 | 40 | 65 | 13
127 | ALIPURDUAR |  | SM/05419 | Training/Capacity Development for Engineers/VWSC Members/PRI Members/Grassroot Level Workers/Other Stakeholder for the year 2015-2016 under NRDWP Support Fund | New |  |  |  | MVS | 02/11/2015 |  | 30/04/2018 | 31/03/2018 | 0 | 814.02 | 0 | 100 | 0
128 | ALIPURDUAR | Falakata | SM/13449 | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 02/11/2022 | 17/01/2023 | 31/12/2025 | 27/01/2026 | 12 | 695.45 | 297.5 | 88 | 43
129 | ALIPURDUAR |  | SM/05428 | Computerization and MIS Project under NRDWP Support Fund | New |  |  |  | MVS | 16/11/2015 |  | 30/09/2017 | 30/06/2017 | 0 | 740 | 0 | 100 | 0
130 | ALIPURDUAR |  | SM/05539 | Habitation Survey of 4 Districts of West Bengal (Alipurduar, Purulia, Purba Medinipur & Paschim Medinipur) covering total 79 Blocks | New |  |  |  | MVS | 17/02/2016 |  |  | 31/05/2021 | 0 | 395 | 0 |  | 0
131 | ALIPURDUAR | Kalchini | SM/05647 | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | MVS | 19/07/2016 | 18/11/2016 | 31/07/2025 | 27/01/2026 | 116 | 9372 | 7852.9 | 86 | 84
132 | ALIPURDUAR |  | SM/05658 | Temporary W/S Arrangement at Alipurduar Parade Ground, Mallangi Tourist Lodge & Subhasini Tea Garden during the visit of Hon'ble Chief Minister, Govt. of West Bengal from 24-06-2016 to 29-06-2016 | New |  |  |  | MVS | 02/09/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 2.33 | 0 |  | 0
133 | ALIPURDUAR |  | SM/05670 | Sinking of 25 Nos. Indian Mark-II tubewell at Sourceless Schools under Alipurduar District | New |  |  |  | MVS | 09/09/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 54.41 | 0 | 30 | 0
134 | ALIPURDUAR |  | SM/05684 | Training / Capacity Development for Engineers / VWSC Members / PRI Members / Grassroots Level Workers / Other Stakeholder for the year 2016-17 under NRDWP - Support Fund | New |  |  |  | MVS | 27/09/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 305.36 | 0 |  | 0
135 | ALIPURDUAR |  | SM/05685 | Study of Sanitation, Health and Social Impacts in parts of Western Bengal basin with special reference to the Nirmal Bangla Mission [Submitted by : Indian Institute of Technology (IIT), Kharagpur] | New |  |  |  | MVS | 27/09/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 25.23 | 0 |  | 0
136 | ALIPURDUAR |  | SM/05693 | Temporary w/s and sanitary arrangement for CAPF & Other Police Personnel during the W.B. Legislative Assembly Election, 2016 within Jalpaiguri & Alipurduar District under Jalpaiguri Divn., PHE Dte. | New |  |  |  | MVS | 27/09/2016 |  | 30/06/2017 | 31/05/2017 | 0 | 365.09 | 0 | 100 | 0
137 | ALIPURDUAR | Kalchini | SM/14092 | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 12/12/2022 | 01/03/2023 | 31/05/2025 | 27/01/2026 | 13 | 895.42 | 215 | 88 | 24
138 | ALIPURDUAR |  | SM/05704 | State Information Education Communication (IEC) Activity for Sustainable Community Development for the year 2016-17 under NRDWP - Support Fund | New |  |  |  | MVS | 03/10/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 428.04 | 0 |  | 0
139 | ALIPURDUAR | Kalchini | SM/14093 | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 12/12/2022 | 01/03/2023 | 31/05/2025 | 27/01/2026 | 8 | 528.73 | 123.33 | 90 | 23
140 | ALIPURDUAR |  | SM/05708 | Honorarium & Maintenance charges of PHED & NGO managed Laboratories under NRDWP Water Quality Monitoring & Surveillance for the year 2016-17 | New |  |  |  | MVS | 26/10/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 985.11 | 5.32 |  | 1
141 | ALIPURDUAR | Alipurduar - II | SM/14096 | AUGMENTATION OF BHATIBARI PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 15/12/2022 | 21/12/2022 | 30/04/2026 | 27/01/2026 | 58 | 2031.4 | 756.26 | 86 | 37
142 | ALIPURDUAR |  | SM/05711 | Procurement of Chemicals & Reagents, Annual Service Contract, maintenance of NABL Accreditation status under Water Quality Monitoring & Surveillance for the year 2016-17 | New |  |  |  | MVS | 28/10/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 793.32 | 0 |  | 0
143 | ALIPURDUAR | Alipurduar - I | SM/14209 | PARARPAR PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | SVS | 10/01/2023 | 16/03/2023 | 31/05/2025 | 27/01/2026 | 12 | 561.82 | 29.45 | 70 | 5
144 | ALIPURDUAR |  | SM/05718 | Establishment and Research & Development for the year 2016-17 | New |  |  |  | MVS | 02/11/2016 |  | 30/06/2021 | 31/05/2021 | 0 | 159 | 0 |  | 0
145 | ALIPURDUAR | Alipurduar - I | SM/14210 | FOSKADANGA PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | SVS | 10/01/2023 | 27/03/2023 | 31/07/2025 | 27/01/2026 | 9 | 510.99 | 0 | 65 | 0
146 | ALIPURDUAR |  | SM/05761 | Supply, delivery of Truck Mounted Mobile Water Tanker Unit with GPS Tracking and Smart Filling Station in the different District of West Bengal | New | Northern Mechanical Division II | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, PHE Dte. | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 28/12/2016 |  | 30/06/2021 | 31/05/2021 | 1 | 471.14 | 0 |  | 0
147 | ALIPURDUAR | Kalchini | SM/14211 | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 10/01/2023 | 01/03/2023 | 30/06/2025 | 27/01/2026 | 11 | 530.22 | 109.18 | 78 | 21
148 | ALIPURDUAR |  | SM/05775 | Vertical extension of WTP by incorporating UV Station at proposed Additional MTU | Augmentation |  |  |  | MVS | 17/01/2017 |  | 30/06/2021 | 31/05/2021 | 0 | 36.41 | 0 | 15 | 0
149 | ALIPURDUAR | Kalchini | SM/14212 | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 10/01/2023 | 31/01/2023 | 31/05/2025 | 27/01/2026 | 11 | 570.23 | 128.59 | 90 | 23
150 | ALIPURDUAR | Kalchini | SM/14213 | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 10/01/2023 | 03/08/2023 | 30/06/2025 | 27/01/2026 | 11 | 740.97 | 0 | 50 | 0
151 | ALIPURDUAR | Kalchini | SM/14214 | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 10/01/2023 | 16/03/2023 | 31/05/2025 | 27/01/2026 | 10 | 527.26 | 202.99 | 90 | 38
152 | ALIPURDUAR |  | SM/05815 | Construction of 33 Nos. RBTW fitted with India Mark-II hand pump in 2016-17 under JE / AES | New |  |  |  | MVS | 08/03/2017 |  | 30/06/2021 | 31/05/2021 | 0 | 44.99 | 1.36 |  | 3
153 | ALIPURDUAR | Kalchini | SM/14215 | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 10/01/2023 | 31/03/2023 | 30/04/2027 | 27/01/2026 | 8 | 336.47 | 62.72 | 90 | 19
154 | ALIPURDUAR | Madarihat | SM/05896 | Hantupara Tea Garden Area Piped Water Supply Scheme | New |  |  |  | MVS | 11/07/2017 | 25/01/2021 | 31/12/2020 | 30/11/2020 | 10 | 409.13 | 424.63 | 100 | 104
155 | ALIPURDUAR | Madarihat | SM/14216 | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 10/01/2023 | 19/01/2023 | 31/05/2025 | 27/01/2026 | 4 | 129.41 | 37.08 | 93 | 29
156 | ALIPURDUAR | Kalchini | SM/05897 | Madhu Tea Garden Area Piped Water Supply Scheme | New |  |  |  | MVS | 11/07/2017 | 24/06/2017 | 31/07/2021 | 27/01/2026 | 7 | 283.63 | 447.06 | 100 | 158
157 | ALIPURDUAR | Madarihat | SM/14217 | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 10/01/2023 | 16/03/2023 | 31/05/2025 | 27/01/2026 | 9 | 409.38 | 82.12 | 60 | 20
158 | ALIPURDUAR | Kumargram | SM/05898 | Rahimabad Tea Garden Area Piped Water Supply Scheme | New |  |  |  | MVS | 11/07/2017 | 10/01/2018 | 30/11/2025 | 27/01/2026 | 12 | 260.89 | 396.16 | 90 | 152
159 | ALIPURDUAR | Alipurduar - II | SM/14218 | NURPUR PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 10/01/2023 | 01/03/2023 | 31/05/2025 | 27/01/2026 | 11 | 451.36 | 113.62 | 93 | 25
160 | ALIPURDUAR | Madarihat | SM/05899 | Augmentation of Dalmore Tea Garden Piped Water Supply | Augmentation |  |  |  | MVS | 11/07/2017 | 20/08/2017 | 31/03/2024 | 27/01/2026 | 12 | 430.65 | 374.44 | 10 | 87
161 | ALIPURDUAR | Alipurduar - II | SM/14219 | TURTURI PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 10/01/2023 | 27/03/2023 | 31/07/2025 | 27/01/2026 | 16 | 948.08 | 211.03 | 75 | 22
162 | ALIPURDUAR | Madarihat | SM/05912 | Dekhlapara Tea Garden Area Piped Water Supply Scheme | New | Northern Mechanical Division II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. |  | MVS | 31/08/2017 | 28/04/2021 | 30/09/2020 | 31/10/2020 | 7 | 116.3 | 195.48 | 100 | 168
163 | ALIPURDUAR | Alipurduar - I | SM/14220 | TORSHA FOREST PIPED WATER SUPPLY SCHEME | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | MVS | 10/01/2023 | 19/01/2023 | 31/05/2025 | 27/01/2026 | 5 | 142.14 | 76.4 | 90 | 54
164 | ALIPURDUAR |  | SM/05988 | Construction of RBTW with India Mark-II hand pump under NRDWP 2016-17 [141 Nos.] | New |  |  |  | MVS | 08/11/2017 |  |  | 31/05/2021 | 4 | 194.09 | 281.66 |  | 145
165 | ALIPURDUAR | Madarihat | SM/14221 | BALLALGURI PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | MVS | 10/01/2023 | 01/03/2023 | 31/07/2025 | 27/01/2026 | 6 | 413.54 | 124.05 | 85 | 30
166 | ALIPURDUAR |  | SM/06018 | State Information Education Communication (IEC) Activity for Sustainable Community Development for the year 2017-18. | New |  |  |  | MVS | 01/12/2017 |  |  | 31/08/2019 | 0 | 550 | 0 | 100 | 0
167 | ALIPURDUAR | Madarihat | SM/14222 | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 10/01/2023 | 27/03/2023 | 31/07/2025 | 27/01/2026 | 6 | 429.71 | 10 | 70 | 2
168 | ALIPURDUAR |  | SM/06019 | Training / Capacity Development for Engineers / VWSC Members / PRI Members / Plumber / Machanic / Grassroot Level Workers / Other Stakeholder for the year 2017-18. | New |  |  |  | MVS | 01/12/2017 |  |  | 31/03/2018 | 0 | 510 | 0 | 100 | 0
169 | ALIPURDUAR | Kumargram | SM/14223 | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 10/01/2023 | 31/03/2023 | 31/10/2025 | 27/01/2026 | 15 | 509.75 | 3.62 | 55 | 1
170 | ALIPURDUAR |  | SM/06114 | Establishment & Research & Development for the year 2017-18 | New |  |  |  | MVS | 09/02/2018 |  |  | 30/04/2021 | 0 | 378.56 | 0 |  | 0
171 | ALIPURDUAR | Madarihat | SM/14233 | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 11/01/2023 | 17/01/2023 | 30/06/2025 | 27/01/2026 | 45 | 2288.93 | 289.93 | 65 | 13
172 | ALIPURDUAR |  | SM/06150 | Water Quality Monitoring, Programme Management & its Implementation in the State under Water Quality Monitoring & Surveillance for the year 2017-18 | New |  |  |  | MVS | 27/03/2018 |  |  | 30/04/2021 | 0 | 729.71 | 0 |  | 0
173 | ALIPURDUAR |  | SM/06172 | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | New |  |  |  | MVS | 30/05/2018 | 11/06/2025 |  | 31/05/2021 | 11 | 175.2 | 195.27 |  | 111
174 | ALIPURDUAR | Falakata | SM/15206 | MAIRADANGA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 07/02/2023 | 16/05/2023 | 31/05/2025 | 27/01/2026 | 8 | 963.71 | 0 | 70 | 0
175 | ALIPURDUAR |  | SM/06199 | Sanitary and water supply arrangement to the temporary establishment for CAPF/SF & DCRC Centre in connection with General Panchayet Election, 2018 | New |  |  |  | MVS | 05/09/2018 |  |  | 31/05/2021 | 0 | 48.81 | 59.69 |  | 122
176 | ALIPURDUAR | Falakata | SM/15207 | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 07/02/2023 | 20/07/2023 | 31/12/2025 | 27/01/2026 | 9 | 802.95 | 0 | 65 | 0
177 | ALIPURDUAR |  | SM/06251 | West Bengal Public Health Engineering Department Project Progress Monitoring System (WBPHED-PPMS) | New |  |  |  | MVS | 27/11/2018 |  |  | 30/04/2021 | 0 | 282.9 | 0 |  | 0
178 | ALIPURDUAR | Falakata | SM/15208 | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 07/02/2023 | 31/03/2023 | 30/06/2025 | 27/01/2026 | 8 | 670.33 | 133.71 | 78 | 20
179 | ALIPURDUAR | Falakata | SM/06268 | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | Augmentation |  |  |  | MVS | 10/12/2018 | 14/02/2020 | 31/12/2021 | 30/11/2021 | 22 | 1743.14 | 2271.73 | 100 | 130
180 | ALIPURDUAR | Madarihat | SM/15209 | AUGMENTATION OF HANTUPARA TG PIPED WATER SUPPLY SCHEME. | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 07/02/2023 | 13/03/2023 | 30/06/2025 | 27/01/2026 | 6 | 112.19 | 6.2 | 80 | 6
181 | ALIPURDUAR |  | SM/06366 | Procurement of Chemicals & Reagents & Annual Maintenance Contract of Laboratory instruments under Water Quality Monitoring & Surveillance Programme for 2018-19 | New |  |  |  | MVS | 10/01/2019 |  |  | 30/04/2021 | 0 | 784.19 | 0 |  | 0
182 | ALIPURDUAR | Madarihat | SM/15210 | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 07/02/2023 | 13/03/2023 | 31/07/2025 | 27/01/2026 | 7 | 111.32 | 8.44 | 60 | 8
183 | ALIPURDUAR | Kalchini | SM/15482 | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 13/02/2023 | 01/03/2023 | 31/07/2025 | 27/01/2026 | 21 | 1380.67 | 106.96 | 50 | 8
184 | ALIPURDUAR |  | SM/06381 | Training/Capacity Building Programme for Engineers/VWSC Members/PRI Members/Plumbers/Mechanics/Grass Root level Workers like SHG Members, ASHA Workers etc. and other Stakeholder for the year 2018-19 | New |  |  |  | MVS | 16/01/2019 |  |  | 30/04/2021 | 0 | 649.73 | 0 |  | 0
185 | ALIPURDUAR | Kumargram | SM/15517 | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2023 | 01/03/2023 | 31/05/2025 | 27/01/2026 | 13 | 1067.02 | 371.44 | 83 | 35
186 | ALIPURDUAR |  | SM/06388 | Operational charges of PHED & NGO Managed Laboratories & Capacity Building Laboratory Personnel under State Budget | New |  |  |  | MVS | 29/01/2019 |  |  | 30/04/2021 | 0 | 1257 | 0 |  | 0
187 | ALIPURDUAR | Alipurduar - II | SM/15534 | CHALNIPAK PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | MVS | 16/02/2023 | 01/03/2023 | 30/11/2025 | 27/01/2026 | 14 | 1024.4 | 315.71 | 80 | 31
188 | ALIPURDUAR | Kalchini | SM/06459 | Radharani Tea Garden Area Piped Water Supply Scheme | New |  |  |  | MVS | 08/03/2019 | 20/09/2021 | 31/10/2021 | 30/11/2021 | 13 | 365.07 | 448.83 | 100 | 123
189 | ALIPURDUAR | Falakata | SM/15758 | NARASINGPUR PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 20/02/2023 | 20/07/2023 | 31/07/2025 | 27/01/2026 | 9 | 842.46 | 142.25 | 70 | 17
190 | ALIPURDUAR |  | SM/06473 | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | New |  |  |  | MVS | 25/06/2019 |  |  | 30/04/2021 | 4 | 583.36 | 0 |  | 0
191 | ALIPURDUAR | Kalchini | SM/15914 | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 22/02/2023 | 24/04/2023 | 31/12/2025 | 27/01/2026 | 6 | 358.24 | 15 | 6 | 4
192 | ALIPURDUAR | Madarihat | SM/06549 | Dimdima Tea Garden Area Piped Water Supply Scheme. | New |  |  |  | MVS | 17/10/2019 | 24/06/2021 | 31/05/2021 | 31/05/2021 | 12 | 608.42 | 905.6 | 100 | 149
193 | ALIPURDUAR | Falakata | SM/16114 | UMACHARANPUR PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 22/02/2023 | 02/08/2023 | 02/08/2025 | 27/01/2026 | 10 | 950.07 | 0 | 50 | 0
194 | ALIPURDUAR |  | SM/06574 | Arrangement of drinking water & sanitation facilities for CPMF & SPF accommodation in connection with General Parliamentary Election 2019 under Alipurduar Division. | New |  |  |  | MVS | 26/11/2019 |  |  | 31/05/2021 | 8 | 428.94 | 750.62 |  | 175
195 | ALIPURDUAR | Alipurduar - I | SM/16115 | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | MVS | 22/02/2023 | 31/01/2023 | 30/06/2025 | 27/01/2026 | 1 | 240.25 | 0 | 50 | 0
196 | ALIPURDUAR | Kalchini | SM/16506 | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 03/03/2023 | 23/03/2023 | 31/12/2025 | 27/01/2026 | 23 | 990.41 | 0 | 3 | 0
197 | ALIPURDUAR | Alipurduar - I | SM/06652 | Shifting of pipe line along the flank of Tapshikatha-Shalbari Road with ancillary works infringed due to widening & strengthening of PWD Road for Tapshikatha Water Supply Scheme | Augmentation |  |  |  | MVS | 24/02/2020 |  |  | 30/06/2022 | 0 | 55.44 | 0 |  | 0
198 | ALIPURDUAR | Kalchini | SM/16507 | BUXA PIPE WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 03/03/2023 | 23/03/2023 | 31/12/2025 | 27/01/2026 | 7 | 219.61 | 0 | 2 | 0
199 | ALIPURDUAR | Falakata | SM/07057 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jateswar Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | SVS | 25/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 99.09 | 139.8 | 90 | 141
200 | ALIPURDUAR | Kumargram | SM/16537 | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 10/03/2023 | 27/03/2023 | 31/07/2025 | 27/01/2026 | 16 | 1261.38 | 205.76 | 75 | 16
201 | ALIPURDUAR | Alipurduar - II | SM/07058 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | MVS | 25/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 82.69 | 76.99 | 90 | 93
202 | ALIPURDUAR | Alipurduar - II | SM/16538 | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 10/03/2023 | 17/03/2023 | 31/07/2025 | 27/01/2026 | 11 | 1074.69 | 241.79 | 70 | 22
203 | ALIPURDUAR | Falakata | SM/07059 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | MVS | 25/11/2020 | 17/03/2015 | 31/05/2025 | 27/01/2026 | 2 | 97.58 | 145.8 | 90 | 149
204 | ALIPURDUAR | Kalchini | SM/16539 | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | MVS | 10/03/2023 | 28/07/2023 | 31/07/2025 | 27/01/2026 | 13 | 1121.63 | 0 | 75 | 0
205 | ALIPURDUAR | Alipurduar - I | SM/07060 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | MVS | 25/11/2020 | 01/12/2020 | 31/07/2025 | 27/01/2026 | 3 | 86.77 | 171.88 | 90 | 198
206 | ALIPURDUAR | Falakata | SM/16817 | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 13/03/2023 | 20/07/2023 | 31/07/2026 | 27/01/2026 | 10 | 808.5 | 0 | 65 | 0
207 | ALIPURDUAR | Alipurduar - I | SM/07061 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | MVS | 25/11/2020 | 01/12/2020 | 31/07/2025 | 27/01/2026 | 3 | 93.85 | 119.46 | 55 | 127
208 | ALIPURDUAR | Falakata | SM/16818 | MALSAGAON PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 13/03/2023 | 02/08/2023 | 02/08/2025 | 27/01/2026 | 8 | 777.46 | 0 | 70 | 0
209 | ALIPURDUAR | Kumargram | SM/07062 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Uttar Kamakshyaguri Piped Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 25/11/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 87.86 | 94.91 | 95 | 108
210 | ALIPURDUAR | Falakata | SM/16819 | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 13/03/2023 | 03/08/2023 | 31/05/2025 | 27/01/2026 | 8 | 658.29 | 0 | 60 | 0
211 | ALIPURDUAR | Alipurduar - II | SM/07063 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | SVS | 25/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 5 | 91.9 | 102.2 | 95 | 111
212 | ALIPURDUAR | Falakata | SM/16820 | BENGKANDI PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 13/03/2023 | 28/07/2023 | 31/05/2025 | 27/01/2026 | 9 | 964.09 | 0 | 60 | 0
213 | ALIPURDUAR | Madarihat | SM/07064 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Hantupara Tea Garden Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 25/11/2020 | 11/07/2017 | 31/05/2025 | 27/01/2026 | 5 | 99.04 | 178.48 | 90 | 180
214 | ALIPURDUAR | Falakata | SM/16821 | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 13/03/2023 | 31/03/2023 | 31/07/2025 | 27/01/2026 | 7 | 405.28 | 0 | 25 | 0
215 | ALIPURDUAR | Kumargram | SM/07065 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | SVS | 25/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 7 | 73.85 | 34.11 | 90 | 46
216 | ALIPURDUAR | Falakata | SM/16822 | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | SVS | 13/03/2023 | 12/07/2023 | 31/07/2025 | 27/01/2026 | 10 | 569.65 | 42.36 | 60 | 7
217 | ALIPURDUAR | Madarihat | SM/07066 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | MVS | 25/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 80.75 | 78.08 | 90 | 97
218 | ALIPURDUAR | Falakata | SM/16823 | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | SVS | 13/03/2023 | 31/03/2023 | 31/12/2025 | 27/01/2026 | 10 | 739.67 | 65.7 | 75 | 9
219 | ALIPURDUAR | Kalchini | SM/07067 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | MVS | 25/11/2020 | 05/01/2021 | 31/05/2025 | 27/01/2026 | 5 | 98.86 | 98.86 | 95 | 100
220 | ALIPURDUAR | Madarihat | SM/16824 | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 13/03/2023 | 22/03/2023 | 30/06/2025 | 27/01/2026 | 13 | 273.66 | 0 | 72 | 0
221 | ALIPURDUAR | Madarihat | SM/07068 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Birpara A.E | Alipurduar Sub Division | SVS | 25/11/2020 | 05/01/2021 | 31/05/2025 | 27/01/2026 | 5 | 85.62 | 62.41 | 90 | 73
222 | ALIPURDUAR | Madarihat | SM/07069 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dimdima T.G Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Birpara A.E | Alipurduar Sub Division | SVS | 25/11/2020 | 05/01/2021 | 31/05/2025 | 27/01/2026 | 2 | 61.34 | 61.33 | 90 | 100
223 | ALIPURDUAR | Alipurduar - I | SM/07121 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 26/11/2020 | 07/12/2020 | 31/05/2025 | 27/01/2026 | 4 | 82.27 | 79.34 | 90 | 96
224 | ALIPURDUAR | Kumargram | SM/07122 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | MVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 0 | 98.68 | 98.68 | 95 | 100
225 | ALIPURDUAR | Kumargram | SM/07123 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-III, Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | MVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 5 | 98.96 | 112.42 | 95 | 114
226 | ALIPURDUAR | Alipurduar - II | SM/07124 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 26/11/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 55.28 | 47.81 | 95 | 86
227 | ALIPURDUAR | Kumargram | SM/07125 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 90.17 | 90.17 | 95 | 100
228 | ALIPURDUAR | Kumargram | SM/07126 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 3 | 93 | 171.91 | 95 | 185
229 | ALIPURDUAR | Kumargram | SM/07127 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-I, Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | MVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 66.37 | 71.36 | 95 | 108
230 | ALIPURDUAR | Alipurduar - I | SM/07128 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 26/11/2020 | 25/12/2020 | 31/07/2025 | 27/01/2026 | 2 | 62.07 | 62.07 | 61 | 100
231 | ALIPURDUAR | Falakata | SM/07129 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | SVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 72.16 | 116.02 | 90 | 161
232 | ALIPURDUAR | Madarihat | SM/07130 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 26/11/2020 | 01/12/2020 | 30/06/2025 | 27/01/2026 | 6 | 94.15 | 87.35 | 60 | 93
233 | ALIPURDUAR | Madarihat | SM/07131 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 26/11/2020 | 13/07/2017 | 30/09/2022 | 27/01/2026 | 1 | 73.16 | 107.51 | 10 | 147
234 | ALIPURDUAR | Madarihat | SM/07132 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 26/11/2020 | 01/12/2020 | 30/09/2025 | 27/01/2026 | 6 | 88.7 | 13.76 | 50 | 16
235 | ALIPURDUAR | Madarihat | SM/07133 | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 95.65 | 148.59 | 88 | 155
236 | ALIPURDUAR | Kalchini | SM/18150 | Malangi Tea Garden Area Piped Water Supply Scheme | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 29/03/2023 | 04/05/2023 | 30/06/2026 | 27/01/2026 | 10 | 561.45 | 0 | 50 | 0
237 | ALIPURDUAR | Alipurduar - II | SM/07134 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Purba Chenpani Piped Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 26/11/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 3 | 89.44 | 95.88 | 95 | 107
238 | ALIPURDUAR | Falakata | SM/18151 | Khagenhat Piped Water Supply Scheme | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 29/03/2023 | 04/05/2023 | 31/05/2025 | 27/01/2026 | 11 | 822.98 | 0 | 60 | 0
239 | ALIPURDUAR | Madarihat | SM/07135 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 26/11/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 3 | 87.03 | 109.44 | 95 | 126
240 | ALIPURDUAR | Kumargram | SM/18152 | Chengmari Piped Water Supply Scheme | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 29/03/2023 | 04/05/2023 | 31/07/2025 | 27/01/2026 | 11 | 772.15 | 205.79 | 65 | 27
241 | ALIPURDUAR | Madarihat | SM/07136 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paschim Khairbari Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | MVS | 26/11/2020 | 25/12/2020 | 30/06/2025 | 27/01/2026 | 3 | 80.05 | 67.16 | 80 | 84
242 | ALIPURDUAR | Kumargram | SM/18153 | Dhantali Piped Water Supply Scheme | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 29/03/2023 | 04/05/2023 | 31/07/2025 | 27/01/2026 | 6 | 285.56 | 0 | 70 | 0
243 | ALIPURDUAR | Falakata | SM/07137 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | MVS | 26/11/2020 | 01/12/2020 | 31/07/2025 | 27/01/2026 | 10 | 97.16 | 153.05 | 90 | 158
244 | ALIPURDUAR | Alipurduar - II | SM/18154 | Uttar Dhalkar Piped Water Supply Scheme | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | SVS | 29/03/2023 | 04/05/2023 | 30/06/2025 | 27/01/2026 | 6 | 404.14 | 0 | 70 | 0
245 | ALIPURDUAR | Madarihat | SM/07138 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 26/11/2020 | 01/12/2020 | 31/05/2025 | 27/01/2026 | 3 | 96.46 | 154.63 | 90 | 160
246 | ALIPURDUAR | Kalchini | SM/18156 | Bhutri Forest Piped Water Supply Scheme | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 29/03/2023 | 18/04/2023 | 31/05/2025 | 27/01/2026 | 4 | 59.54 | 0 | 95 | 0
247 | ALIPURDUAR | Alipurduar - II | SM/07174 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Bakla Piped Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | MVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 3 | 76.33 | 108.45 | 90 | 142
248 | ALIPURDUAR | Alipurduar - II | SM/18157 | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | SVS | 29/03/2023 | 22/05/2023 | 31/12/2025 | 27/01/2026 | 6 | 360.16 | 0 | 70 | 0
249 | ALIPURDUAR | Alipurduar - I | SM/07175 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 04/12/2020 | 07/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 91.69 | 94.13 | 90 | 103
250 | ALIPURDUAR | Alipurduar - I | SM/18158 | Parpatla Khawa Piped Water Supply Scheme | New | Alipurduar RWS Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | SVS | 29/03/2023 | 04/05/2023 | 31/07/2025 | 27/01/2026 | 6 | 187.87 | 0 | 68 | 0
251 | ALIPURDUAR | Falakata | SM/07176 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Chotosalkumar Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Falakata Block | SVS | 04/12/2020 | 17/03/2015 | 31/05/2025 | 27/01/2026 | 4 | 70.54 | 56.8 | 90 | 81
252 | ALIPURDUAR | Falakata | SM/18254 | AUGMENTATION OF DALIMPUR PWSS | Augmentation |  |  |  | MVS | 21/06/2023 | 12/07/2023 | 31/10/2025 | 27/01/2026 | 19 | 1020.25 | 43.97 | 70 | 4
253 | ALIPURDUAR | Alipurduar - II | SM/07177 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 5 | 68.96 | 132.18 | 95 | 192
254 | ALIPURDUAR | Alipurduar - I | SM/07178 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 98.08 | 138.02 | 95 | 141
255 | ALIPURDUAR | Alipurduar - I | SM/07179 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 04/12/2020 | 25/12/2020 | 30/06/2025 | 27/01/2026 | 4 | 69.14 | 42.69 | 95 | 62
256 | ALIPURDUAR | Madarihat | SM/07180 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | RWS Madarihat - Birpara Block | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 64.83 | 17.16 | 42 | 26
257 | ALIPURDUAR | Kumargram | SM/07181 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | MVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 89.66 | 91.47 | 90 | 102
258 | ALIPURDUAR | Alipurduar - II | SM/07182 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | MVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 2 | 98.81 | 160.38 | 90 | 162
259 | ALIPURDUAR | Alipurduar - II | SM/07183 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | MVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 1 | 56.02 | 47.7 | 90 | 85
260 | ALIPURDUAR | Alipurduar - II | SM/07184 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 5 | 82.41 | 107.49 | 95 | 130
261 | ALIPURDUAR | Kumargram | SM/07185 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-1,Phase-1) | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | MVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 5 | 82.87 | 146.19 | 95 | 176
262 | ALIPURDUAR | Kalchini | SM/07186 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | SVS | 04/12/2020 | 05/01/2021 | 31/05/2025 | 27/01/2026 | 8 | 99.29 | 79.17 | 95 | 80
263 | ALIPURDUAR | Alipurduar - I | SM/07187 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | MVS | 04/12/2020 | 25/12/2020 | 31/07/2025 | 27/01/2026 | 5 | 73.94 | 137.85 | 72 | 186
264 | ALIPURDUAR | Alipurduar - I | SM/07188 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | MVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 4 | 73.94 | 54.01 | 78 | 73
265 | ALIPURDUAR | Alipurduar - I | SM/07189 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikhata Piped Water Supply Scheme (Phase-1) | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | MVS | 04/12/2020 | 25/12/2020 | 30/06/2025 | 27/01/2026 | 7 | 97.67 | 154.45 | 81 | 158
266 | ALIPURDUAR | Alipurduar - I | SM/07190 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Paitkapara T.G Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 04/12/2020 | 20/01/2016 | 31/05/2025 | 27/01/2026 | 4 | 83.82 | 135.42 | 95 | 162
267 | ALIPURDUAR | Alipurduar - II | SM/07191 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | SVS | 04/12/2020 | 09/11/2015 | 30/04/2026 | 27/01/2026 | 3 | 62.8 | 56.31 | 80 | 90
268 | ALIPURDUAR | Kalchini | SM/07192 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | SVS | 04/12/2020 | 24/06/2017 | 31/07/2021 | 27/01/2026 | 4 | 83.76 | 167.52 | 100 | 200
269 | ALIPURDUAR | Kalchini | SM/07193 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 4 | 60.86 | 71.17 | 95 | 117
270 | ALIPURDUAR | Kalchini | SM/07194 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dima T.G Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | SVS | 04/12/2020 | 09/11/2015 | 30/09/2021 | 27/01/2026 | 3 | 98.15 | 192.92 | 100 | 197
271 | ALIPURDUAR | Kumargram | SM/07195 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti T.G Piped Water Supply Scheme | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 3 | 98.84 | 155.05 | 90 | 157
272 | ALIPURDUAR | Kumargram | SM/07196 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | SVS | 04/12/2020 | 10/01/2018 | 30/11/2025 | 27/01/2026 | 3 | 67.24 | 92.26 | 90 | 137
273 | ALIPURDUAR | Madarihat | SM/07197 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Gargenda T.G Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 84.07 | 65 | 80 | 77
274 | ALIPURDUAR | Madarihat | SM/07198 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Mujnai T.G Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 04/12/2020 | 19/07/2014 | 31/05/2025 | 27/01/2026 | 5 | 69.04 | 68.77 | 90 | 100
275 | ALIPURDUAR | Madarihat | SM/07199 | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | SVS | 04/12/2020 | 25/12/2020 | 31/05/2025 | 27/01/2026 | 6 | 61.63 | 60.56 | 90 | 98
276 | ALIPURDUAR | Alipurduar - I | SM/19197 | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | New |  |  |  | MVS | 22/03/2024 | 24/03/2024 | 31/12/2025 | 03/04/2025 | 48 | 101375 | 0 | 15 | 0
277 | ALIPURDUAR | Kalchini | SM/08080 | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | MVS | 04/02/2021 | 18/11/2016 | 31/07/2025 | 27/01/2026 | 58 | 1224.31 | 1134.6 | 86 | 93
278 | ALIPURDUAR | Madarihat | SM/08580 | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 10/02/2021 | 25/02/2021 | 31/08/2025 | 27/01/2026 | 12 | 295.97 | 143.18 | 90 | 48
279 | ALIPURDUAR | Madarihat | SM/08880 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR MADARIHAT Water Supply Scheme | Retrofitting | Alipurduar Sadar Sub-Division | Birpara A.E | Alipurduar Sub Division | SVS | 27/09/2021 | 04/10/2021 | 31/05/2025 | 27/01/2026 | 6 | 140.24 | 140.24 | 90 | 100
280 | ALIPURDUAR | Madarihat | SM/08881 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of UTTAR SISHUBARI Water Supply Scheme | Retrofitting | Birpara Sub-Division | Birpara A.E | Birpara Sub Division | MVS | 27/09/2021 | 04/10/2021 | 30/06/2025 | 27/01/2026 | 7 | 184.32 | 122.26 | 90 | 66
281 | ALIPURDUAR | Alipurduar - II | SM/08882 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of CHANDIRJHAR Water Supply Scheme | Retrofitting | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division | Alipurduar Sub Division | MVS | 27/09/2021 | 04/10/2021 | 31/05/2025 | 27/01/2026 | 4 | 129.45 | 128.72 | 90 | 99
282 | ALIPURDUAR | Alipurduar - I | SM/08883 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of SALKUMARHAT Water Supply Scheme | Retrofitting | Birpara Sub-Division | Alipurduar RWS | Birpara Sub Division | SVS | 27/09/2021 | 04/10/2021 | 31/05/2025 | 27/01/2026 | 2 | 87.85 | 82.8 | 90 | 94
283 | ALIPURDUAR | Kalchini | SM/08884 | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | Retrofitting | Alipurduar Division | HQ-A.E | RWS Kalchini Block | MVS | 27/09/2021 | 04/10/2021 | 30/06/2025 | 27/01/2026 | 14 | 398.83 | 387.18 | 81 | 97
284 | ALIPURDUAR |  | SM/09333 | Arrangement for supply of safe drinking water after commission of piped water supply schemes | New | Hooghly Division | Assistant Engineer,Assistant Engineer 1,Assistant Engineer 2,Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ),Assistant Engineer-I,Assistant Engineer-II,DIC(D)_MMSD(D) | JE (M),Junior Engineer,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | MVS | 16/11/2021 | 01/06/2023 | 31/03/2025 | 09/12/2024 | 9283 | 24668 | 18384.97 | 80 | 75
285 | ALIPURDUAR | Alipurduar - I | SM/09883 | AUGMENTATION OF BHOLARDABRI PIPE WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 11/01/2022 | 31/07/2025 | 27/01/2026 | 26 | 451.23 | 274.68 | 78 | 61
286 | ALIPURDUAR | Alipurduar - II | SM/09884 | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 08/12/2021 | 11/01/2022 | 30/06/2025 | 27/01/2026 | 23 | 484.93 | 459.11 | 85 | 95
287 | ALIPURDUAR | Falakata | SM/09885 | AUGMENTATION OF BHUTNIRGHAT PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 08/12/2021 | 11/01/2022 | 30/06/2025 | 27/01/2026 | 12 | 449.91 | 433.13 | 90 | 96
288 | ALIPURDUAR | Alipurduar - II | SM/09886 | REJUVENATION OF MADHYA PAROKATA PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 08/12/2021 | 11/01/2022 | 31/05/2025 | 27/01/2026 | 7 | 257.81 | 243.87 | 95 | 95
289 | ALIPURDUAR | Kalchini | SM/09887 | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | MVS | 08/12/2021 | 13/05/2022 | 30/04/2027 | 27/01/2026 | 16 | 92.5 | 32.1 | 98 | 35
290 | ALIPURDUAR | Alipurduar - II | SM/09888 | REJUVINATION OF 'DHAOLAJHORA .T.G WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 14/01/2022 | 31/05/2025 | 27/01/2026 | 3 | 43.87 | 18.35 | 95 | 42
291 | ALIPURDUAR | Alipurduar - II | SM/09890 | REJUVENATION OF 'BAKLA WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 08/12/2021 | 11/01/2022 | 30/06/2025 | 27/01/2026 | 2 | 45.21 | 20.37 | 98 | 45
292 | ALIPURDUAR | Alipurduar - I | SM/09891 | REJUVENATION OF BANCHUKAMARI WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 08/12/2021 | 11/01/2022 | 31/05/2025 | 27/01/2026 | 5 | 47.49 | 17.67 | 82 | 37
293 | ALIPURDUAR | Alipurduar - II | SM/09892 | REJUVINATION OF CHANDIRJHAR WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 08/12/2021 | 11/01/2022 | 31/05/2025 | 27/01/2026 | 7 | 47.49 | 31.03 | 98 | 65
294 | ALIPURDUAR | Alipurduar - II | SM/09893 | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 08/12/2021 | 23/03/2023 | 30/06/2025 | 27/01/2026 | 2 | 45.22 | 30.26 | 90 | 67
295 | ALIPURDUAR | Alipurduar - I | SM/09894 | REJUVENATION OF MUNSHIPARA WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 08/12/2021 | 14/01/2022 | 30/06/2025 | 27/01/2026 | 5 | 44.01 | 4 | 85 | 9
296 | ALIPURDUAR | Madarihat | SM/09895 | Rejuvenation of Makrapara TG WSS. | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 31/01/2022 | 31/05/2025 | 27/01/2026 | 4 | 45.22 | 40.88 | 90 | 90
297 | ALIPURDUAR | Madarihat | SM/09896 | REJUVENATION OF DHUMCHIPARA. T.G. WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 31/01/2022 | 30/06/2025 | 27/01/2026 | 6 | 45.23 | 15.23 | 93 | 34
298 | ALIPURDUAR | Alipurduar - I | SM/09897 | REJUVENATION OF BIRPARA(APD) WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 11/01/2022 | 31/05/2025 | 27/01/2026 | 4 | 45.48 | 27.52 | 98 | 61
299 | ALIPURDUAR | Kalchini | SM/09898 | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 31/01/2022 | 31/05/2025 | 27/01/2026 | 7 | 47.48 | 38.71 | 95 | 82
300 | ALIPURDUAR | Alipurduar - II | SM/09899 | REJUVINATION OF JASHODANGA WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Cooch-Behar Mechanical Sub-Division, PHE Dte. | Alipurduar Sub Division,Junior Engineer 1, Northern Mechanical Division-II,PHE Dte. | SVS | 08/12/2021 | 31/01/2022 | 31/05/2025 | 27/01/2026 | 6 | 45.28 | 34.03 | 97 | 75
301 | ALIPURDUAR | Madarihat | SM/09900 | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 08/12/2021 | 27/12/2021 | 31/07/2025 | 27/01/2026 | 1 | 45.23 | 2.87 | 50 | 6
302 | ALIPURDUAR | Madarihat | SM/09901 | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 23/02/2022 | 30/06/2025 | 27/01/2026 | 6 | 44.25 | 30.95 | 90 | 70
303 | ALIPURDUAR |  | SM/19376 | Augmentation Of Lankapara Chasundari Piped Water Supply Scheme | Augmentation |  |  |  | MVS | 08/10/2025 | 08/10/2025 |  | 08/10/2025 | 1 | 261.31 | 0 |  | 0
304 | ALIPURDUAR | Madarihat | SM/09902 | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 11/01/2022 | 30/06/2025 | 27/01/2026 | 5 | 47.49 | 4.63 | 86 | 10
305 | ALIPURDUAR | Falakata | SM/09903 | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 08/12/2021 | 14/01/2022 | 31/05/2025 | 27/01/2026 | 7 | 45.22 | 26.27 | 93 | 58
306 | ALIPURDUAR | Kalchini | SM/09904 | Rejuvenation Of Dima T.G. W.S.S | Augmentation | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 27/12/2021 | 31/05/2025 | 27/01/2026 | 6 | 44.51 | 13.51 | 70 | 30
307 | ALIPURDUAR | Alipurduar - II | SM/09905 | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 08/12/2021 | 11/01/2022 | 30/06/2025 | 27/01/2026 | 9 | 45.51 | 9.21 | 97 | 20
308 | ALIPURDUAR | Madarihat | SM/09906 | Rejuvenation of Gargenda Tea Garden Water Supply Scheme | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 31/01/2022 | 30/06/2025 | 27/01/2026 | 2 | 45.22 | 14.4 | 94 | 32
309 | ALIPURDUAR | Alipurduar - II | SM/09907 | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 08/12/2021 | 25/02/2022 | 31/05/2025 | 27/01/2026 | 2 | 44.74 | 2.39 | 98 | 5
310 | ALIPURDUAR | Alipurduar - I | SM/09908 | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 08/12/2021 | 11/01/2022 | 31/05/2025 | 27/01/2026 | 4 | 46.31 | 21.68 | 85 | 47
311 | ALIPURDUAR | Kalchini | SM/09909 | REJUVENATION OF MADHU TG WATER SUPPLY SCHEME | Augmentation | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 11/01/2022 | 31/07/2025 | 27/01/2026 | 5 | 45.46 | 28.71 | 72 | 63
312 | ALIPURDUAR | Alipurduar - I | SM/09910 | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 08/12/2021 | 27/12/2021 | 31/05/2025 | 27/01/2026 | 5 | 47.45 | 12.99 | 95 | 27
313 | ALIPURDUAR |  | SM/10027 | Opening Stock | New |  |  |  | MVS |  |  |  |  | 0 | 0 | 0 | 100 | NAN
314 | ALIPURDUAR | Madarihat | SM/10038 | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | SVS | 19/01/2022 | 21/02/2022 | 30/06/2025 | 27/01/2026 | 4 | 247.03 | 66.06 | 90 | 27
315 | ALIPURDUAR | Kalchini | SM/10039 | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | New | Alipurduar Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | SVS | 19/01/2022 | 26/04/2022 | 30/06/2025 | 27/01/2026 | 9 | 284.23 | 255.6 | 90 | 90
316 | ALIPURDUAR | Madarihat | SM/10054 | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | SVS | 25/01/2022 | 11/08/2023 | 30/06/2025 | 27/01/2026 | 11 | 332.16 | 10.44 | 75 | 3
317 | ALIPURDUAR | Kumargram | SM/10154 | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 11/02/2022 | 01/02/2022 | 30/06/2025 | 27/01/2026 | 22 | 632.84 | 576.48 | 90 | 91
318 | ALIPURDUAR | Alipurduar - II | SM/10155 | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 11/02/2022 | 24/02/2022 | 30/06/2025 | 27/01/2026 | 7 | 140.66 | 136.56 | 90 | 97
319 | ALIPURDUAR | Falakata | SM/10156 | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | MVS | 11/02/2022 | 01/02/2022 | 30/06/2025 | 27/01/2026 | 22 | 706.17 | 428.62 | 68 | 61
320 | ALIPURDUAR | Falakata | SM/10169 | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | SVS | 16/02/2022 | 17/02/2022 | 31/05/2025 | 27/01/2026 | 14 | 378.84 | 81.95 | 90 | 22
321 | ALIPURDUAR | Kumargram | SM/10170 | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 16/02/2022 | 01/02/2022 | 31/05/2025 | 27/01/2026 | 17 | 509.72 | 294.58 | 92 | 58
322 | ALIPURDUAR | Alipurduar - II | SM/10171 | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 01/02/2022 | 31/05/2025 | 27/01/2026 | 22 | 750.42 | 576.09 | 92 | 77
323 | ALIPURDUAR | Alipurduar - I | SM/10172 | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 17/02/2022 | 31/05/2025 | 27/01/2026 | 13 | 810.28 | 517.68 | 90 | 64
324 | ALIPURDUAR | Madarihat | SM/10173 | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 17/02/2022 | 31/12/2025 | 27/01/2026 | 19 | 886.25 | 842.97 | 88 | 95
325 | ALIPURDUAR | Alipurduar - I | SM/10174 | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 17/02/2022 | 30/06/2025 | 27/01/2026 | 12 | 732.56 | 640.26 | 90 | 87
326 | ALIPURDUAR | Alipurduar - I | SM/10175 | SIDHABARI PIED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 17/02/2022 | 31/07/2025 | 27/01/2026 | 12 | 360.32 | 273.06 | 65 | 76
327 | ALIPURDUAR | Kalchini | SM/10176 | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 16/02/2022 | 17/02/2022 | 31/07/2025 | 27/01/2026 | 12 | 426.36 | 154.79 | 75 | 36
328 | ALIPURDUAR | Madarihat | SM/10177 | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 17/02/2022 | 31/05/2025 | 27/01/2026 | 7 | 338.59 | 214.19 | 70 | 63
329 | ALIPURDUAR | Madarihat | SM/10178 | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | MVS | 16/02/2022 | 17/02/2022 | 30/06/2025 | 27/01/2026 | 17 | 577.33 | 504.95 | 85 | 87
330 | ALIPURDUAR | Kumargram | SM/10179 | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | New | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 16/02/2022 | 17/02/2022 | 31/12/2025 | 27/01/2026 | 7 | 364.15 | 290.58 | 90 | 80
331 | ALIPURDUAR | Kalchini | SM/10180 | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | New | Birpara Sub-Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 16/02/2022 | 17/02/2022 | 31/05/2025 | 27/01/2026 | 7 | 376.91 | 348.14 | 86 | 92
332 | ALIPURDUAR | Alipurduar - I | SM/10316 | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | Augmentation | Birpara Sub-Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | SVS | 04/03/2022 | 02/05/2022 | 30/06/2025 | 27/01/2026 | 17 | 281.05 | 40.2 | 85 | 14
333 | ALIPURDUAR | Kalchini | SM/10637 | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | Augmentation | Birpara Sub-Division | HQ-A.E | Birpara Sub Division | SVS | 21/04/2022 | 11/05/2022 | 30/06/2025 | 27/01/2026 | 13 | 252.1 | 124.4 | 85 | 49
334 | ALIPURDUAR | Alipurduar - II | SM/10667 | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | Augmentation | Alipurduar Sadar Sub-Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | MVS | 29/04/2022 | 21/11/2022 | 31/07/2025 | 27/01/2026 | 8 | 186.88 | 51.71 | 61 | 28
Total | [13 empty] | 11936 | 254322.06 | 65756.75 |  | 25.86