## G2- NRDWP Ongoing Scheme List (
G2- NRDWP Ongoing Scheme List (ALIPURDUAR)
SL No. | District | Block | Scheme SM Code | Scheme Name | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | Scheme coverage type | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | Physical Progress (in %) | Financial Progress (in %)
1 | ALIPURDUAR | Madarihat | SM/05899 | Augmentation of Dalmore Tea Garden Piped Water Supply(SM/05899) | Augmentation |  |  |  | MVS | 11/07/2017 | 20/08/2017 | 31/03/2024 | 25/03/2024 | 12 | 100 | 90
2 | ALIPURDUAR | Kumargram | SM/05187 | Jayanti Tea Garden Piped Water Supply Scheme (SM/05187) | New |  |  |  | MVS | 02/09/2016 | 07/02/2015 | 31/12/2023 | 25/03/2024 | 9 | 100 | 86
3 | ALIPURDUAR | Kumargram | SM/05155 | Augmentation of Barovisa Water Supply Scheme( SM/05155) | Augmentation |  |  |  | MVS | 25/02/2015 | 11/09/2015 | 31/12/2025 | 25/03/2024 | 15 | 100 | 37
Total | [13 empty] | 36 |  | 63.12