## G2- NRDWP Ongoing Scheme List (
G2- NRDWP Ongoing Scheme List (ALIPURDUAR)
SL No. | District | Block | Scheme SM Code | Scheme Name | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | Scheme coverage type | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | Physical Progress (in %) | Financial Progress (in %)
1 | ALIPURDUAR | Madarihat | SM/05899 | Augmentation of Dalmore Tea Garden Piped Water Supply(SM/05899) | Augmentation |  |  |  | MVS | 11/07/2017 | 08/10/2020 | 30/09/2020 | 31/10/2020 | 12 | 100 | 45
2 | ALIPURDUAR | Kumargram | SM/05187 | Jayanti Tea Garden Piped Water Supply Scheme (SM/05187) | New |  |  |  | MVS | 02/09/2016 | 28/12/2020 | 31/12/2017 | 31/12/2017 | 11 | 100 | 41
3 | ALIPURDUAR | Kumargram | SM/05155 | Augmentation of Barovisa Water Supply Scheme( SM/05155) | Augmentation |  |  |  | MVS | 25/02/2015 | 15/10/2020 | 30/09/2019 | 31/12/2019 | 17 | 100 | 17
Total | [13 empty] | 40 |  | 30.55