## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | DAKSHIN ARIAGAON Pipe Water Supply Scheme (SM/15305) | SM/15305 | 670.23 | 1900 | NEW | 0 | 0% Physical | 3 | 09/02/2023 | 11/07/2025 | 15/12/2025 | 10/08/2023 | 17.81 | 17.81
2 | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12795) | SM/12795 | 423.08 | 1036 | NEW | 0 | 0% Physical | 16 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 68 | 68
3 | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division (SM/18123) | SM/18123 | 231.67 | 0 | SOLARISATION | 0 | 0% Physical | 0 | 29/03/2023 | 11/07/2025 | 15/12/2025 | 07/07/2023 | 0 | 0
4 | Survey and Water Sample Collection from School and Anganwadis at various block in the district, Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/11619) | SM/11619 | 8.64 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 26/07/2022 |  | 28/07/2022 | 22/08/2022 | 0 | 0
5 | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. (SM/10615) | SM/10615 | 2.08 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 20/04/2022 |  | 21/04/2022 | 15/07/2022 | 0 | 0
6 | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs (SM/06641) | SM/06641 | 24.56 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 10/09/2021 | 0 | 0
7 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Uttar Dinajpur District. (SM/08980) | SM/08980 | 208.78 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 29/10/2021 |  | 31/10/2021 | 17/08/2022 | 0 | 0
8 | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. (SM/19073) | SM/19073 | 58.73 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 05/03/2025 | 0 | 0
9 | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. (SM/19074) | SM/19074 | 79.08 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 06/01/2025 | 0 | 0
10 | On-Site assessment with sample collection & testing of Community Water Purification Plants (CWPPs) & Solar Water Plants including supply & delivery of 2 On-site Mobile Analysis System with required consumables in addition to monitoring & processing data o (SM/19280) | SM/19280 | 26.58 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 30/10/2024 |  | 12/11/2024 | 17/01/2025 | 0 | 0
11 | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. (SM/10636) | SM/10636 | 14.25 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 21/04/2022 |  | 22/04/2022 | 31/01/2022 | 0 | 0
12 | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. (SM/08982) | SM/08982 | 14.04 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 |  | 0 | 0
13 | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. (SM/10390) | SM/10390 | 11.88 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 24/03/2022 |  | 24/03/2022 | 28/05/2022 | 0 | 0
14 | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. (SM/11804) | SM/11804 | 102.21 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/08/2022 |  | 08/08/2022 | 10/09/2021 | 0 | 0
15 | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all loaboratory for smooth running of different 5 Nos. Labs under Raiganj Di (SM/19327) | SM/19327 | 51.61 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 26/12/2024 |  | 27/12/2024 | 25/09/2024 | 0 | 0
16 | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div (SM/11803) | SM/11803 | 29.14 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/08/2022 |  | 08/08/2022 | 14/01/2022 | 0 | 0
17 | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). (SM/06640) | SM/06640 | 22.11 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/02/2020 |  | 31/05/2021 | 13/12/2021 | 0 | 0
18 | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen (SM/11226) | SM/11226 | 20.94 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 16/06/2022 |  | 16/06/2022 | 26/08/2021 | 0 | 0
19 | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La (SM/19075) | SM/19075 | 50.75 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 04/04/2024 | 0 | 0
20 | SUPPLY, DELIVERY AND INSTALLATION OF COMPUTER & PERIPHERALS FOR OFFICIAL USE UNRED RAIGANJ DIVISION, P.H.E. DTE. (SM/19115) | SM/19115 | 9.51 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 22/12/2023 |  | 22/12/2023 |  | 0 | 0
21 | Requirement of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. (SM/19342) | SM/19342 | 88.68 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 31/01/2025 |  | 24/02/2025 |  | 0 | 0
22 | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12784) | SM/12784 | 594.32 | 1478 | NEW | 5 | Delayed | 2 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 11.1 | 11.1
23 | FASHIA DIATION PIPED WATER SUPPLY SCHEME (SM/14129) | SM/14129 | 607.1 | 2201 | NEW | 5 | Delayed | 4 | 02/01/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 22.34 | 22.34
24 | MIRJADPUR Piped Water Supply Scheme (SM/14627) | SM/14627 | 626.74 | 2289 | NEW | 5 | Delayed | 2 | 31/01/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 14.1 | 14.1
25 | SARJAPUR Piped Water Supply Scheme (SM/15127) | SM/15127 | 931.52 | 2809 | NEW | 6 | Delayed | 6 | 04/02/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 55.63 | 55.63
26 | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. (SM/16471) | SM/16471 | 393.91 | 1004 | NEW | 6 | Delayed | 2 | 02/03/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 6.18 | 6.18
27 | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16647) | SM/16647 | 651.61 | 2196 | NEW | 6 | Delayed | 4 | 14/03/2023 | 11/07/2025 | 15/12/2025 | 10/08/2023 | 24.35 | 24.35
28 | DAMODARKHURI Piped Water Supply Scheme (SM/13236) | SM/13236 | 602.24 | 1871 | NEW | 10 | Delayed | 8 | 13/10/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 48.41 | 48.41
29 | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block (SM/07072) | SM/07072 | 60.91 | 1139 | RETROFITTING | 10 | Delayed | 100 | 27/11/2020 | 31/12/2020 | 15/12/2025 | 01/11/2020 | 60.91 | 44.42
30 | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14231) | SM/14231 | 49.75 | 50 | AUGMENTATION | 10 | Delayed | 23 | 10/01/2023 | 31/03/2025 | 15/12/2025 | 16/01/2023 | 11.58 | 11.58
31 | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12647) | SM/12647 | 56.37 | 100 | AUGMENTATION | 11 | Delayed | 21 | 19/09/2022 | 31/05/2025 | 15/12/2025 | 28/10/2022 | 11.79 | 11.79
32 | KADERGANJ Pipe Water Supply Scheme (SM/15307) | SM/15307 | 708.54 | 2492 | NEW | 11 | Delayed | 6 | 09/02/2023 | 31/05/2025 | 15/12/2025 | 24/07/2023 | 45.93 | 45.93
33 | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. (SM/18290) | SM/18290 | 1425.54 | 3395 | AUGMENTATION | 14 | Delayed | 9 | 26/06/2023 | 30/06/2025 | 15/12/2025 | 13/07/2023 | 131.85 | 131.85
34 | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12654) | SM/12654 | 58.53 | 150 | AUGMENTATION | 15 | Delayed | 11 | 19/09/2022 | 31/12/2025 | 15/12/2025 | 28/10/2022 | 6.27 | 6.27
35 | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18165) | SM/18165 | 93.53 | 227 | NEW | 15 | Delayed | 3 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 14/08/2023 | 2.52 | 2.52
36 | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18155) | SM/18155 | 65.75 | 116 | NEW | 16 | Delayed | 9 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 29/05/2023 | 5.66 | 5.66
37 | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. (SM/18149) | SM/18149 | 178.3 | 484 | NEW | 16 | Delayed | 10 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 29/05/2023 | 18.04 | 18.04
38 | CHOUKAI Pipe Water Supply Scheme (SM/15304) | SM/15304 | 766.71 | 2030 | NEW | 18 | Delayed | 7 | 09/02/2023 | 11/07/2025 | 15/12/2025 | 11/09/2023 | 57.18 | 57.18
39 | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. (SM/16227) | SM/16227 | 724.68 | 3775 | NEW | 20 | Delayed | 7 | 24/02/2023 | 31/03/2025 | 15/12/2025 | 08/05/2023 | 54.19 | 54.19
40 | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12794) | SM/12794 | 560.31 | 1750 | NEW | 21 | Delayed | 18 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 01/09/2023 | 101.41 | 101.41
41 | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block (SM/12085) | SM/12085 | 762.95 | 2173 | NEW | 21 | Delayed | 3 | 02/09/2022 | 11/07/2025 | 15/12/2025 | 18/07/2023 | 23.31 | 18.56
42 | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17741) | SM/17741 | 169.13 | 482 | AUGMENTATION | 22 | Delayed | 3 | 17/03/2023 | 31/05/2025 | 15/12/2025 | 27/03/2023 | 5.47 | 5.47
43 | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14165) | SM/14165 | 689.32 | 2269 | NEW | 23 | Delayed | 20 | 05/01/2023 | 31/03/2025 | 15/12/2025 | 17/03/2023 | 138.49 | 138.49
44 | BALARAMPUR PIPED WATER SUPPLY SCHEME (SM/13520) | SM/13520 | 432.26 | 1122 | NEW | 23 | Delayed | 43 | 04/11/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 188 | 188
45 | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12649) | SM/12649 | 56.37 | 100 | AUGMENTATION | 23 | Delayed | 21 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 11.73 | 11.73
46 | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13738) | SM/13738 | 819.76 | 2652 | NEW | 24 | Delayed | 24 | 17/11/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 200.56 | 200.56
47 | Sripur Piped Water Supply Scheme (SM/17226) | SM/17226 | 126.21 | 163 | NEW | 25 | Delayed | 18 | 15/03/2023 | 31/03/2025 | 15/12/2025 | 27/03/2023 | 22.42 | 22.42
48 | BARA MIRCHA Piped Water Supply Scheme (SM/12397) | SM/12397 | 328.74 | 737 | NEW | 25 | Delayed | 49 | 13/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 161.64 | 161.64
49 | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. (SM/18828) | SM/18828 | 214.61 | 0 | AUGMENTATION | 25 | Delayed | 3 | 12/09/2023 | 31/03/2025 | 15/12/2025 | 20/09/2023 | 5.4 | 5.4
50 | Source Augmentation for Surun Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12645) | SM/12645 | 56.65 | 100 | AUGMENTATION | 25 | Delayed | 46 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 25.96 | 25.96
51 | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12796) | SM/12796 | 303.76 | 665 | NEW | 25 | Delayed | 26 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 78.26 | 78.26
52 | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. (SM/14239) | SM/14239 | 1369.11 | 3947 | NEW | 26 | Delayed | 7 | 16/01/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 98.16 | 98.16
53 | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14168) | SM/14168 | 726.29 | 1516 | NEW | 26 | Delayed | 21 | 05/01/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 153.69 | 153.69
54 | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. (SM/17631) | SM/17631 | 546 | 2159 | NEW | 26 | Delayed | 8 | 22/03/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 44.67 | 44.67
55 | BHABANIPUR PWSS (SM/18629) | SM/18629 | 1372.82 | 3893 | NEW | 26 | Delayed | 35 | 31/07/2023 | 31/12/2025 | 15/12/2025 | 24/08/2023 | 484.46 | 484.46
56 | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. (SM/18295) | SM/18295 | 1248.45 | 3442 | AUGMENTATION | 27 | Delayed | 26 | 26/06/2023 | 30/06/2025 | 15/12/2025 | 13/07/2023 | 322.62 | 322.62
57 | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. (SM/16228) | SM/16228 | 1042.17 | 2889 | NEW | 27 | Delayed | 33 | 23/02/2023 | 31/03/2025 | 15/12/2025 | 26/05/2023 | 342.69 | 342.69
58 | BARA DOPAHARU Piped Water Supply Scheme (SM/12396) | SM/12396 | 460.65 | 1310 | NEW | 28 | Delayed | 38 | 13/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 176.47 | 176.47
59 | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15214) | SM/15214 | 970.73 | 2916 | NEW | 29 | Delayed | 2 | 07/02/2023 | 31/03/2025 | 15/12/2025 | 23/02/2023 | 18.98 | 18.98
60 | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. (SM/18298) | SM/18298 | 1068.47 | 2297 | NEW | 30 | Delayed | 20 | 26/06/2023 | 31/05/2025 | 15/12/2025 | 13/07/2023 | 209.83 | 209.83
61 | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12106) | SM/12106 | 781.36 | 2691 | NEW | 30 | Delayed | 16 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 124.59 | 124.59
62 | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. (SM/12443) | SM/12443 | 347.81 | 964 | NEW | 30 | Delayed | 40 | 13/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 139.91 | 139.91
63 | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18170) | SM/18170 | 168.56 | 421 | NEW | 30 | Delayed | 38 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 29/05/2023 | 64.59 | 64.59
64 | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14144) | SM/14144 | 690.18 | 2016 | NEW | 31 | Delayed | 31 | 02/01/2023 | 31/03/2025 | 15/12/2025 | 17/03/2023 | 212.65 | 212.65
65 | BELAN Piped Water Supply Scheme (SM/13233) | SM/13233 | 773.92 | 2942 | NEW | 31 | Delayed | 30 | 13/10/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 230.3 | 230.3
66 | MANORA Piped Water Supply Scheme (SM/15126) | SM/15126 | 1000.28 | 3398 | NEW | 32 | Delayed | 12 | 04/02/2023 | 11/07/2025 | 15/12/2025 | 24/07/2023 | 121.82 | 121.82
67 | Gorahar Piped Water Supply Scheme. (SM/14640) | SM/14640 | 594.44 | 1183 | NEW | 32 | Delayed | 28 | 31/01/2023 | 31/12/2025 | 15/12/2025 | 23/02/2023 | 169.07 | 169.07
68 | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12781) | SM/12781 | 417.17 | 1208 | NEW | 32 | Delayed | 32 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 131.92 | 131.92
69 | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18168) | SM/18168 | 268.43 | 1535 | NEW | 32 | Delayed | 35 | 29/03/2023 | 31/01/2026 | 15/12/2025 | 12/05/2023 | 93.37 | 93.37
70 | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16491) | SM/16491 | 538.04 | 1988 | NEW | 33 | Delayed | 28 | 02/03/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 150.35 | 150.35
71 | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. (SM/16226) | SM/16226 | 358.44 | 688 | NEW | 33 | Delayed | 18 | 23/02/2023 | 11/07/2025 | 15/12/2025 | 14/08/2023 | 63.46 | 63.46
72 | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16222) | SM/16222 | 624.52 | 1300 | NEW | 33 | Delayed | 34 | 23/02/2023 | 31/01/2026 | 15/12/2025 | 08/05/2023 | 214.7 | 214.7
73 | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18159) | SM/18159 | 276.37 | 905 | NEW | 33 | Delayed | 38 | 29/03/2023 | 24/03/2025 | 15/12/2025 | 08/05/2023 | 103.98 | 103.98
74 | RAUTARA Pipe Water Supply Scheme (SM/15306) | SM/15306 | 753.03 | 2073 | NEW | 34 | Delayed | 30 | 09/02/2023 | 31/03/2025 | 15/12/2025 | 24/08/2023 | 229.02 | 229.02
75 | TUNIBHITA PWSS (SM/18291) | SM/18291 | 1226.41 | 3213 | NEW | 35 | Delayed | 22 | 26/06/2023 | 31/03/2025 | 15/12/2025 | 24/08/2023 | 271.94 | 271.94
76 | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12638) | SM/12638 | 56.37 | 100 | AUGMENTATION | 35 | Delayed | 17 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 9.62 | 9.62
77 | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12655) | SM/12655 | 56.53 | 100 | AUGMENTATION | 35 | Delayed | 45 | 19/09/2022 | 31/05/2025 | 15/12/2025 | 28/10/2022 | 25.48 | 25.48
78 | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12651) | SM/12651 | 58.53 | 150 | AUGMENTATION | 35 | Delayed | 57 | 19/09/2022 | 31/12/2025 | 15/12/2025 | 28/10/2022 | 33.56 | 33.56
79 | DIGHALGAON PWSS (SM/18292) | SM/18292 | 1056.59 | 3406 | NEW | 35 | Delayed | 10 | 26/06/2023 | 31/01/2026 | 15/12/2025 | 13/07/2023 | 108.98 | 108.98
80 | KUCHILA PWSS (SM/18325) | SM/18325 | 1101.08 | 2923 | NEW | 35 | Delayed | 25 | 27/06/2023 | 31/03/2025 | 15/12/2025 | 13/07/2023 | 271.14 | 271.14
81 | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. (SM/16225) | SM/16225 | 480.89 | 944 | NEW | 35 | Delayed | 20 | 23/02/2023 | 31/03/2026 | 15/12/2025 | 19/05/2023 | 98.07 | 98.07
82 | KATAGAON Piped Water Supply Scheme at Chopra Block (SM/12082) | SM/12082 | 381.86 | 1113 | NEW | 36 | Delayed | 40 | 02/09/2022 | 11/07/2025 | 15/12/2025 | 18/07/2023 | 153.79 | 153.79
83 | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/18341) | SM/18341 | 2257.53 | 5716 | NEW | 36 | Delayed | 18 | 04/07/2023 | 31/05/2025 | 15/12/2025 | 27/07/2023 | 406.4 | 406.4
84 | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12110) | SM/12110 | 814.52 | 2601 | NEW | 36 | Delayed | 8 | 02/09/2022 | 30/06/2025 | 15/12/2025 | 01/11/2022 | 68.7 | 68.7
85 | JAMIRA Piped Water Supply Scheme (SM/14179) | SM/14179 | 789 | 2909 | NEW | 38 | Delayed | 37 | 09/01/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 291.59 | 291.59
86 | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14145) | SM/14145 | 1007.08 | 2612 | NEW | 39 | Delayed | 7 | 02/01/2023 | 31/03/2025 | 15/12/2025 | 22/03/2023 | 69.66 | 46.79
87 | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12780) | SM/12780 | 600.64 | 2533 | NEW | 39 | Delayed | 32 | 20/09/2022 | 31/03/2025 | 15/12/2025 | 04/08/2023 | 194.01 | 194.01
88 | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12787) | SM/12787 | 339.28 | 742 | NEW | 40 | Delayed | 42 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 28/07/2023 | 142.06 | 142.06
89 | Mini Piped Water Supply Scheme for the Blocks of Chopra and Goalpokhar-II in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11520) | SM/11520 | 977.22 | 1632 | NEW | 40 | Delayed | 2 | 19/07/2022 | 31/03/2025 | 15/12/2025 | 08/05/2023 | 15.82 | 15.82
90 | GODASAMAL Piped Water Supply Scheme (SM/15128) | SM/15128 | 1005.02 | 3549 | NEW | 40 | Delayed | 35 | 04/02/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 352 | 352
91 | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. (SM/11517) | SM/11517 | 975.54 | 1442 | NEW | 40 | Delayed | 1 | 19/07/2022 | 31/05/2025 | 15/12/2025 | 08/05/2023 | 9.81 | 9.81
92 | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11519) | SM/11519 | 976.8 | 1627 | NEW | 40 | Delayed | 4 | 19/07/2022 | 31/05/2025 | 15/12/2025 | 08/05/2023 | 40.99 | 40.99
93 | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block (SM/12083) | SM/12083 | 378.6 | 967 | NEW | 40 | Delayed | 42 | 02/09/2022 | 11/07/2025 | 15/12/2025 | 18/07/2023 | 157.19 | 157.19
94 | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12789) | SM/12789 | 536.84 | 1871 | NEW | 40 | Delayed | 42 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 222.98 | 222.98
95 | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11516) | SM/11516 | 969.86 | 1622 | NEW | 40 | Delayed | 1 | 19/07/2022 | 31/01/2026 | 15/12/2025 | 19/05/2023 | 7.38 | 7.38
96 | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block (SM/12089) | SM/12089 | 400.31 | 884 | NEW | 40 | Delayed | 35 | 02/09/2022 | 11/07/2025 | 15/12/2025 | 18/07/2023 | 140.73 | 140.73
97 | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15215) | SM/15215 | 897.34 | 2187 | NEW | 40 | Delayed | 46 | 07/02/2023 | 11/07/2025 | 15/12/2025 | 10/08/2023 | 414.66 | 414.66
98 | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11518) | SM/11518 | 978.29 | 1649 | NEW | 40 | Delayed | 3 | 19/07/2022 | 31/01/2026 | 15/12/2025 | 08/05/2023 | 31.04 | 31.04
99 | Balia Piped Water Supply Scheme. (SM/18493) | SM/18493 | 713.08 | 2372 | NEW | 40 | Delayed | 7 | 24/07/2023 | 31/05/2025 | 15/12/2025 | 04/08/2023 | 50.27 | 50.27
100 | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. (SM/11521) | SM/11521 | 565.81 | 1057 | NEW | 40 | Delayed | 3 | 19/07/2022 | 31/05/2025 | 15/12/2025 | 08/05/2023 | 14.16 | 14.16
101 | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12786) | SM/12786 | 603.43 | 2242 | NEW | 41 | Delayed | 26 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 28/07/2023 | 157.87 | 157.87
102 | AGDIMTI Piped Water Supply Scheme at Islampur Block (SM/12091) | SM/12091 | 741.95 | 2151 | NEW | 41 | Delayed | 47 | 02/09/2022 | 30/06/2025 | 15/12/2025 | 04/04/2023 | 349.53 | 349.53
103 | BASATPUT Piped Water Supply Scheme (SM/15129) | SM/15129 | 933.62 | 3305 | NEW | 41 | Delayed | 31 | 04/02/2023 | 11/07/2025 | 15/12/2025 | 23/02/2023 | 293.92 | 293.92
104 | MALKOT Pipe Water Supply Scheme (SM/15303) | SM/15303 | 764.07 | 2259 | NEW | 41 | Delayed | 24 | 09/02/2023 | 30/06/2025 | 15/12/2025 | 21/07/2023 | 182.38 | 182.38
105 | BAJARGAON PWSS (SM/18626) | SM/18626 | 1290.63 | 3375 | NEW | 41 | Delayed | 11 | 31/07/2023 | 31/03/2025 | 15/12/2025 | 24/08/2023 | 145.32 | 145.32
106 | BILASPUR Piped Water Supply Scheme (SM/16563) | SM/16563 | 642.24 | 1402 | NEW | 42 | Delayed | 6 | 10/03/2023 | 31/03/2025 | 15/12/2025 | 17/08/2023 | 36.68 | 36.68
107 | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18148) | SM/18148 | 377.79 | 1035 | NEW | 42 | Delayed | 24 | 29/03/2023 | 30/06/2025 | 15/12/2025 | 16/08/2023 | 90.95 | 90.95
108 | BALDIABASA Piped Water Supply Scheme (SM/13234) | SM/13234 | 396.51 | 1362 | NEW | 42 | Delayed | 47 | 13/10/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 186.16 | 186.16
109 | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12778) | SM/12778 | 693.47 | 2529 | NEW | 42 | Delayed | 30 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 209.95 | 209.95
110 | BASUDEBPUR Piped Water Supply Scheme (SM/14182) | SM/14182 | 809.69 | 1806 | NEW | 42 | Delayed | 31 | 09/01/2023 | 31/05/2025 | 15/12/2025 | 23/02/2023 | 249.88 | 249.87
111 | BHIKHANPUR PWSS (SM/18628) | SM/18628 | 1156.17 | 3085 | NEW | 42 | Delayed | 36 | 31/07/2023 | 31/03/2025 | 15/12/2025 | 24/08/2023 | 417.66 | 417.66
112 | ILLUABARI PWSS (SM/18449) | SM/18449 | 1911.1 | 3914 | NEW | 42 | Delayed | 29 | 20/07/2023 | 31/12/2025 | 15/12/2025 | 04/08/2023 | 549.18 | 549.18
113 | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17740) | SM/17740 | 181.42 | 509 | AUGMENTATION | 43 | Delayed | 12 | 17/03/2023 | 31/03/2025 | 15/12/2025 | 27/03/2023 | 22.42 | 22.42
114 | BUDHRA PWSS (SM/19012) | SM/19012 | 586.89 | 1680 | NEW | 43 | Delayed | 8 | 27/10/2023 | 31/05/2025 | 15/12/2025 | 30/10/2023 | 44.79 | 44.79
115 | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12791) | SM/12791 | 717.37 | 2369 | NEW | 43 | Delayed | 19 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 133.26 | 133.26
116 | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15213) | SM/15213 | 927.83 | 2660 | NEW | 43 | Delayed | 19 | 07/02/2023 | 31/03/2025 | 15/12/2025 | 24/07/2023 | 179.78 | 179.78
117 | PRATAPPUR PIPED WATER SUPPLY SCHEME (SM/14128) | SM/14128 | 613.01 | 2096 | NEW | 44 | Delayed | 45 | 02/01/2023 | 11/07/2025 | 15/12/2025 | 01/09/2023 | 273.09 | 273.09
118 | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME (SM/15125) | SM/15125 | 602.98 | 2112 | AUGMENTATION | 44 | Delayed | 21 | 04/02/2023 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 128.76 | 128.76
119 | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12782) | SM/12782 | 561.35 | 2030 | NEW | 44 | Delayed | 27 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 28/07/2023 | 154.32 | 154.32
120 | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR (SM/18160) | SM/18160 | 378.98 | 1029 | NEW | 44 | Delayed | 24 | 29/03/2023 | 11/07/2025 | 15/12/2025 | 11/08/2023 | 91.1 | 91.1
121 | BHOMRA PWSS (SM/18627) | SM/18627 | 1301.95 | 4067 | NEW | 44 | Delayed | 20 | 31/07/2023 | 31/05/2025 | 15/12/2025 | 04/08/2023 | 262.42 | 262.42
122 | BARA SINGHANATH Piped Water Supply Scheme (SM/12529) | SM/12529 | 922.51 | 2136 | NEW | 44 | Delayed | 35 | 13/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 320.08 | 320.08
123 | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13739) | SM/13739 | 786.9 | 2128 | NEW | 45 | Delayed | 24 | 17/11/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 185.83 | 185.83
124 | GUNJARIA PWSS (SM/18296) | SM/18296 | 1032.42 | 3298 | NEW | 45 | Delayed | 23 | 26/06/2023 | 31/05/2025 | 15/12/2025 | 04/08/2023 | 235.11 | 235.11
125 | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. (SM/12783) | SM/12783 | 311.92 | 502 | NEW | 45 | Delayed | 36 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 113.35 | 113.35
126 | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. (SM/12707) | SM/12707 | 487.59 | 1384 | NEW | 45 | Delayed | 46 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 28/07/2023 | 221.89 | 221.89
127 | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. (SM/15516) | SM/15516 | 1297.89 | 3922 | NEW | 45 | Delayed | 26 | 16/02/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 341.45 | 341.45
128 | BIRSINGGACHH MINI PIPED WATER SUPPLY SCHEME IN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18166) | SM/18166 | 72.22 | 129 | NEW | 45 | Delayed | 41 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 14/08/2023 | 29.26 | 29.26
129 | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14166) | SM/14166 | 906.05 | 3056 | NEW | 45 | Delayed | 29 | 05/01/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 258.81 | 258.81
130 | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13550) | SM/13550 | 831.68 | 2927 | NEW | 45 | Delayed | 37 | 04/11/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 311.24 | 311.24
131 | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. (SM/14827) | SM/14827 | 122.62 | 193 | NEW | 45 | Delayed | 38 | 03/02/2023 | 31/05/2025 | 15/12/2025 | 22/02/2023 | 46.64 | 46.64
132 | BARAKHANTI Piped Water Supply Scheme at Islampur Block (SM/12093) | SM/12093 | 893.92 | 2310 | NEW | 46 | Delayed | 24 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 212.2 | 212.2
133 | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/12788) | SM/12788 | 736.56 | 1864 | NEW | 46 | Delayed | 20 | 20/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 145.29 | 145.29
134 | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13503) | SM/13503 | 612.92 | 1889 | NEW | 46 | Delayed | 45 | 02/11/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 277.21 | 277.21
135 | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR (SM/11821) | SM/11821 | 605.48 | 1901 | NEW | 46 | Delayed | 44 | 16/08/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 264.22 | 263.94
136 | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/14642) | SM/14642 | 847.33 | 1778 | NEW | 46 | Delayed | 21 | 31/01/2023 | 31/03/2025 | 15/12/2025 | 04/08/2023 | 179.54 | 179.54
137 | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District (SM/18450) | SM/18450 | 1127.27 | 2238 | NEW | 46 | Delayed | 33 | 20/07/2023 | 31/01/2026 | 15/12/2025 | 31/07/2023 | 375.05 | 375.05
138 | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME (SM/11725) | SM/11725 | 883.67 | 2755 | AUGMENTATION | 48 | Delayed | 29 | 03/08/2022 | 31/03/2025 | 15/12/2025 | 26/08/2022 | 260.07 | 260.07
139 | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16490) | SM/16490 | 519.67 | 2042 | NEW | 48 | Delayed | 33 | 02/03/2023 | 11/07/2025 | 15/12/2025 | 11/09/2023 | 173.53 | 173.53
140 | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12793) | SM/12793 | 752.34 | 2764 | NEW | 48 | Delayed | 39 | 20/09/2022 | 11/07/2025 | 15/12/2025 | 03/08/2023 | 294.21 | 294.21
141 | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. (SM/13456) | SM/13456 | 710.31 | 2656 | NEW | 48 | Delayed | 39 | 02/11/2022 | 11/07/2025 | 15/12/2025 | 01/09/2023 | 274.31 | 274.31
142 | DAKSHIN RAMPUR Piped Water Supply Scheme (SM/13232) | SM/13232 | 592.79 | 2380 | NEW | 50 | Delayed | 46 | 13/10/2022 | 11/07/2025 | 15/12/2025 | 11/09/2023 | 275.17 | 275.17
143 | DULEPUR PWSS (SM/18293) | SM/18293 | 1063.92 | 3048 | NEW | 51 | Delayed | 9 | 26/06/2023 | 31/05/2025 | 15/12/2025 | 24/08/2023 | 92.72 | 92.72
144 | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15211) | SM/15211 | 546.12 | 1287 | NEW | 51 | Delayed | 28 | 07/02/2023 | 11/07/2025 | 15/12/2025 | 14/08/2023 | 154.43 | 154.43
145 | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16223) | SM/16223 | 674.95 | 1330 | NEW | 52 | Delayed | 28 | 23/02/2023 | 31/03/2025 | 15/12/2025 | 08/05/2023 | 189.01 | 189.01
146 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11727) | SM/11727 | 1057.12 | 2488 | AUGMENTATION | 52 | Delayed | 20 | 03/08/2022 | 31/01/2026 | 15/12/2025 | 26/08/2022 | 208.4 | 208.4
147 | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. (SM/16219) | SM/16219 | 706.61 | 1475 | NEW | 53 | Delayed | 41 | 23/02/2023 | 31/05/2025 | 15/12/2025 | 08/05/2023 | 292.55 | 292.55
148 | KABUTARKHOPI Piped Water Supply Scheme (SM/13235) | SM/13235 | 627.6 | 2602 | NEW | 53 | Delayed | 46 | 13/10/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 288.51 | 288.51
149 | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17256) | SM/17256 | 185.7 | 457 | NEW | 53 | Delayed | 33 | 15/03/2023 | 31/03/2025 | 15/12/2025 | 29/03/2023 | 60.8 | 60.8
150 | PURBBA GOMAIDIGHI PWSS (SM/18448) | SM/18448 | 1012.28 | 2508 | NEW | 53 | Delayed | 38 | 20/07/2023 | 31/12/2025 | 15/12/2025 | 24/08/2023 | 384.29 | 384.29
151 | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/13012) | SM/13012 | 979.94 | 2805 | NEW | 53 | Delayed | 25 | 28/09/2022 | 31/12/2025 | 15/12/2025 | 23/02/2023 | 243.6 | 243.6
152 | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/15212) | SM/15212 | 700.5 | 2006 | NEW | 55 | Delayed | 34 | 07/02/2023 | 31/01/2026 | 15/12/2025 | 17/03/2023 | 241.23 | 241.23
153 | Retrofitting of Functional household Tap connection (FHTC) under Purba Rampur and adjoining Mouzas water supply scheme (SM/07144) | SM/07144 | 89.5 | 1740 | RETROFITTING | 55 | Delayed | 100 | 27/11/2020 | 31/12/2020 | 15/12/2025 | 11/12/2020 | 89.5 | 84.6
154 | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME (SM/10548) | SM/10548 | 380.61 | 1180 | AUGMENTATION | 55 | Delayed | 35 | 18/04/2022 | 31/03/2025 | 15/12/2025 | 14/07/2022 | 132.14 | 132.14
155 | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14226) | SM/14226 | 49.54 | 50 | AUGMENTATION | 55 | Delayed | 34 | 10/01/2023 | 31/03/2025 | 15/12/2025 | 16/01/2023 | 16.66 | 16.66
156 | KOKRA Piped Water Supply Scheme (SM/14175) | SM/14175 | 476.42 | 1199 | NEW | 55 | Delayed | 30 | 09/01/2023 | 30/04/2025 | 15/12/2025 | 23/02/2023 | 143.48 | 143.48
157 | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13717) | SM/13717 | 1171.44 | 3186 | NEW | 55 | Delayed | 18 | 17/11/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 207.45 | 200.04
158 | JHITKAI PWSS (SM/18476) | SM/18476 | 1183.35 | 3425 | NEW | 55 | Delayed | 34 | 24/07/2023 | 31/03/2025 | 15/12/2025 | 04/08/2023 | 396.46 | 396.46
159 | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18167) | SM/18167 | 133.59 | 279 | NEW | 56 | Delayed | 35 | 29/03/2023 | 31/05/2025 | 15/12/2025 | 29/05/2023 | 46.65 | 46.65
160 | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT (SM/11824) | SM/11824 | 1178.23 | 3169 | NEW | 56 | Delayed | 39 | 16/08/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 463.89 | 463.89
161 | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14163) | SM/14163 | 974.62 | 3112 | NEW | 56 | Delayed | 20 | 05/01/2023 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 192.01 | 192.01
162 | RANIGANJ Piped Water Supply Scheme (SM/14181) | SM/14181 | 833.07 | 3028 | NEW | 56 | Delayed | 31 | 09/01/2023 | 31/12/2025 | 15/12/2025 | 22/02/2023 | 259.56 | 259.56
163 | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16495) | SM/16495 | 607.74 | 1568 | NEW | 56 | Delayed | 41 | 02/03/2023 | 11/07/2025 | 15/12/2025 | 24/07/2023 | 246.35 | 247.21
164 | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/16536) | SM/16536 | 1427.38 | 3752 | NEW | 56 | Delayed | 37 | 10/03/2023 | 31/05/2025 | 15/12/2025 | 11/04/2023 | 529.67 | 529.67
165 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/13115) | SM/13115 | 1519.65 | 5083 | AUGMENTATION | 56 | Delayed | 20 | 10/10/2022 | 31/03/2025 | 15/12/2025 | 12/07/2022 | 303.58 | 303.58
166 | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block (SM/12095) | SM/12095 | 874.21 | 2465 | NEW | 56 | Delayed | 48 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 419.91 | 419.91
167 | TOPAMARI PWSS (SM/18243) | SM/18243 | 1112.55 | 3482 | NEW | 57 | Delayed | 32 | 16/06/2023 | 31/05/2025 | 15/12/2025 | 13/07/2023 | 358.59 | 358.59
168 | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/13502) | SM/13502 | 638.08 | 2490 | NEW | 57 | Delayed | 40 | 02/11/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 254.7 | 254.7
169 | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14227) | SM/14227 | 49.54 | 50 | AUGMENTATION | 57 | Delayed | 53 | 10/01/2023 | 31/12/2025 | 15/12/2025 | 16/01/2023 | 26.38 | 26.38
170 | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. (SM/11897) | SM/11897 | 503.57 | 2458 | NEW | 58 | Delayed | 51 | 18/08/2022 | 31/05/2025 | 15/12/2025 | 12/05/2023 | 258.94 | 258.94
171 | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12650) | SM/12650 | 52.98 | 150 | AUGMENTATION | 58 | Delayed | 37 | 19/09/2022 | 31/01/2026 | 15/12/2025 | 28/10/2022 | 19.35 | 19.35
172 | JAGDISHPUR PWSS (SM/18287) | SM/18287 | 1067.42 | 3803 | NEW | 58 | Delayed | 38 | 23/06/2023 | 31/01/2026 | 15/12/2025 | 13/07/2023 | 403.25 | 403.25
173 | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16505) | SM/16505 | 132.68 | 156 | NEW | 58 | Delayed | 39 | 02/03/2023 | 31/03/2025 | 15/12/2025 | 06/03/2023 | 52.25 | 52.73
174 | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/15148) | SM/15148 | 770.95 | 2412 | NEW | 59 | Delayed | 38 | 07/02/2023 | 31/03/2025 | 15/12/2025 | 23/02/2023 | 289.79 | 289.79
175 | Palaibari Piped Water Supply Scheme. (SM/18181) | SM/18181 | 813.02 | 3420 | NEW | 59 | Delayed | 32 | 31/03/2023 | 31/01/2026 | 15/12/2025 | 24/04/2023 | 257.58 | 257.58
176 | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. (SM/07933) | SM/07933 | 222.19 | 9023 | ANGANWADI | 60 | Delayed | 0 | 19/01/2021 | 31/12/2025 | 15/12/2025 | 24/06/2021 | 0 | 0
177 | Khalsi Piped Water Supply Scheme. (SM/18179) | SM/18179 | 512.31 | 2610 | NEW | 60 | Delayed | 32 | 31/03/2023 | 31/12/2025 | 15/12/2025 | 24/04/2023 | 161.57 | 161.57
178 | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12648) | SM/12648 | 56.37 | 100 | AUGMENTATION | 60 | Delayed | 31 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 17.37 | 17.37
179 | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12105) | SM/12105 | 895.79 | 2789 | NEW | 60 | Delayed | 30 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 18/01/2021 | 269.39 | 269.39
180 | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. (SM/17742) | SM/17742 | 203.43 | 341 | AUGMENTATION | 60 | Delayed | 15 | 17/03/2023 | 31/03/2025 | 15/12/2025 | 27/03/2023 | 29.86 | 29.86
181 | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME (SM/11796) | SM/11796 | 741.87 | 2030 | AUGMENTATION | 60 | Delayed | 35 | 05/08/2022 | 31/05/2025 | 15/12/2025 | 26/08/2022 | 258.18 | 258.18
182 | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12652) | SM/12652 | 56.37 | 100 | AUGMENTATION | 60 | Delayed | 50 | 19/09/2022 | 31/05/2025 | 15/12/2025 | 28/10/2022 | 28.28 | 28.28
183 | DURGAPUR Piped Water Supply Scheme at Islampur Block (SM/12087) | SM/12087 | 558.58 | 1365 | NEW | 60 | Delayed | 29 | 02/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 163.86 | 163.86
184 | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/16221) | SM/16221 | 705.61 | 1373 | NEW | 60 | Delayed | 35 | 23/02/2023 | 31/01/2026 | 15/12/2025 | 08/05/2023 | 249.26 | 249.26
185 | HEMENPUR Piped Water Supply Scheme (SM/14180) | SM/14180 | 564.15 | 1426 | NEW | 60 | Delayed | 40 | 09/01/2023 | 31/12/2025 | 15/12/2025 | 17/03/2023 | 226.97 | 228.57
186 | Dhamdhol Piped Water Supply Scheme. (SM/14639) | SM/14639 | 706.27 | 1314 | NEW | 60 | Delayed | 30 | 31/01/2023 | 31/01/2026 | 15/12/2025 | 23/02/2023 | 214.75 | 214.75
187 | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/11728) | SM/11728 | 707.96 | 1800 | AUGMENTATION | 60 | Delayed | 33 | 03/08/2022 | 31/03/2025 | 15/12/2025 | 26/08/2022 | 234.83 | 234.83
188 | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/12792) | SM/12792 | 870.25 | 2602 | NEW | 60 | Delayed | 51 | 20/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 447.61 | 447.61
189 | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18164) | SM/18164 | 271.95 | 866 | NEW | 60 | Delayed | 21 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 13/07/2023 | 57.87 | 57.87
190 | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14225) | SM/14225 | 49.75 | 50 | AUGMENTATION | 61 | Delayed | 22 | 10/01/2023 | 31/12/2025 | 15/12/2025 | 16/01/2023 | 10.88 | 10.88
191 | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17436) | SM/17436 | 625.89 | 1301 | NEW | 61 | Delayed | 32 | 18/03/2023 | 31/03/2025 | 15/12/2025 | 08/05/2023 | 199.33 | 199.33
192 | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/13014) | SM/13014 | 781.32 | 1880 | NEW | 61 | Delayed | 26 | 28/09/2022 | 31/05/2025 | 15/12/2025 | 20/01/2023 | 202.28 | 202.28
193 | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14167) | SM/14167 | 840.92 | 2762 | NEW | 62 | Delayed | 50 | 05/01/2023 | 11/07/2025 | 15/12/2025 | 11/09/2023 | 418.73 | 418.73
194 | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17437) | SM/17437 | 412.36 | 920 | NEW | 62 | Delayed | 25 | 18/03/2023 | 31/12/2025 | 15/12/2025 | 13/07/2023 | 103.15 | 103.15
195 | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR (SM/11642) | SM/11642 | 898.8 | 3431 | NEW | 62 | Delayed | 49 | 27/07/2022 | 31/05/2025 | 15/12/2025 | 26/08/2022 | 442.36 | 442.36
196 | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18161) | SM/18161 | 91.89 | 250 | NEW | 62 | Delayed | 14 | 29/03/2023 | 24/05/2025 | 15/12/2025 | 29/05/2023 | 13.25 | 13.25
197 | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME (SM/15124) | SM/15124 | 776.11 | 2906 | AUGMENTATION | 62 | Delayed | 37 | 04/02/2023 | 30/04/2025 | 15/12/2025 | 01/11/2022 | 288.25 | 288.25
198 | Kashimpur Piped Water Supply Scheme. (SM/18182) | SM/18182 | 564.01 | 2253 | NEW | 62 | Delayed | 25 | 31/03/2023 | 31/12/2025 | 15/12/2025 | 24/04/2023 | 142.44 | 142.44
199 | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/17199) | SM/17199 | 755.97 | 1496 | NEW | 62 | Delayed | 46 | 15/03/2023 | 31/07/2025 | 15/12/2025 | 08/05/2023 | 344.02 | 344.02
200 | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. (SM/12395) | SM/12395 | 631.31 | 1487 | AUGMENTATION | 63 | Delayed | 30 | 13/09/2022 | 31/01/2026 | 15/12/2025 | 01/11/2022 | 187.1 | 187.1
201 | POTHIA Piped Water Supply Scheme at Islampur Block (SM/12088) | SM/12088 | 731.84 | 2183 | NEW | 63 | Delayed | 46 | 02/09/2022 | 31/12/2025 | 15/12/2025 | 01/11/2022 | 333.74 | 333.74
202 | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18147) | SM/18147 | 100.04 | 250 | NEW | 63 | Delayed | 40 | 29/03/2023 | 31/12/2025 | 15/12/2025 | 29/05/2023 | 40.13 | 40.13
203 | MACHHALI PWSS (SM/18289) | SM/18289 | 1229.16 | 3378 | NEW | 64 | Delayed | 30 | 26/06/2023 | 31/01/2026 | 15/12/2025 | 24/08/2023 | 369.99 | 369.99
204 | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16494) | SM/16494 | 879.93 | 1993 | NEW | 64 | Delayed | 22 | 02/03/2023 | 31/07/2025 | 15/12/2025 | 16/03/2023 | 193.17 | 193.17
205 | PANDITPOTA PIPED WATER SUPPLY SCHEME (SM/13542) | SM/13542 | 540.87 | 1260 | NEW | 65 | Delayed | 26 | 04/11/2022 | 31/01/2026 | 15/12/2025 | 16/01/2023 | 141.39 | 141.39
206 | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. (SM/15147) | SM/15147 | 752.32 | 2122 | NEW | 65 | Delayed | 31 | 07/02/2023 | 31/12/2025 | 15/12/2025 | 16/03/2023 | 229.92 | 233.29
207 | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. (SM/12394) | SM/12394 | 900.04 | 2145 | AUGMENTATION | 65 | Delayed | 32 | 13/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 284.73 | 284.73
208 | Sathaur Piped Water Supply Scheme (SM/13231) | SM/13231 | 445.66 | 1795 | NEW | 65 | Delayed | 44 | 13/10/2022 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 195.8 | 195.8
209 | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12108) | SM/12108 | 580.75 | 1719 | NEW | 66 | Delayed | 49 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 286.77 | 286.77
210 | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. (SM/15146) | SM/15146 | 714.17 | 1910 | NEW | 66 | Delayed | 27 | 07/02/2023 | 31/01/2026 | 15/12/2025 | 23/02/2023 | 192.72 | 192.72
211 | KUNDARGAON Piped Water Supply Scheme at Islampur Block (SM/12086) | SM/12086 | 545.87 | 1299 | NEW | 66 | Delayed | 30 | 02/09/2022 | 30/04/2025 | 15/12/2025 | 01/11/2022 | 163.43 | 163.43
212 | BANIKANER ALISA RAHATPUR PWSS (SM/12522) | SM/12522 | 414.11 | 748 | NEW | 66 | Delayed | 34 | 13/09/2022 | 31/12/2025 | 15/12/2025 | 01/11/2022 | 141.99 | 142.17
213 | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/14164) | SM/14164 | 667.17 | 2116 | NEW | 67 | Delayed | 15 | 05/01/2023 | 31/01/2026 | 15/12/2025 | 17/03/2023 | 102.45 | 102.45
214 | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14232) | SM/14232 | 49.54 | 50 | AUGMENTATION | 67 | Delayed | 81 | 10/01/2023 | 31/12/2025 | 15/12/2025 | 16/01/2023 | 40.07 | 40.07
215 | SADIPUR PWSS (SM/18994) | SM/18994 | 915.05 | 2615 | NEW | 67 | Delayed | 36 | 17/10/2023 | 31/05/2025 | 15/12/2025 | 17/10/2023 | 326.41 | 326.41
216 | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/14641) | SM/14641 | 885.92 | 1740 | NEW | 67 | Delayed | 26 | 31/01/2023 | 31/07/2025 | 15/12/2025 | 23/02/2023 | 226.5 | 226.5
217 | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/15904) | SM/15904 | 913.58 | 1963 | NEW | 67 | Delayed | 41 | 20/02/2023 | 30/04/2025 | 15/12/2025 | 01/11/2022 | 375.74 | 375.74
218 | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11721) | SM/11721 | 1029.67 | 2892 | AUGMENTATION | 68 | Delayed | 35 | 03/08/2022 | 31/12/2025 | 15/12/2025 | 31/08/2022 | 355.86 | 355.86
219 | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12641) | SM/12641 | 49.56 | 60 | AUGMENTATION | 68 | Delayed | 49 | 19/09/2022 | 31/12/2025 | 15/12/2025 | 28/10/2022 | 24.38 | 24.38
220 | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. (SM/12779) | SM/12779 | 557.76 | 1451 | NEW | 68 | Delayed | 29 | 20/09/2022 | 31/03/2025 | 15/12/2025 | 16/03/2022 | 160.66 | 160.66
221 | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/17255) | SM/17255 | 704.46 | 1461 | NEW | 69 | Delayed | 37 | 15/03/2023 | 31/12/2025 | 15/12/2025 | 08/05/2023 | 263.35 | 263.35
222 | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME (SM/10040) | SM/10040 | 381.45 | 950 | AUGMENTATION | 69 | Delayed | 50 | 19/01/2022 | 31/03/2025 | 15/12/2025 | 25/02/2022 | 189.39 | 189.39
223 | GAISAL Piped Water Supply Scheme at Islampur Block (SM/12092) | SM/12092 | 821.68 | 2554 | NEW | 70 | Delayed | 44 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 362.69 | 362.69
224 | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR (SM/11820) | SM/11820 | 751.83 | 2009 | NEW | 70 | Delayed | 53 | 16/08/2022 | 31/05/2025 | 15/12/2025 | 14/11/2022 | 400.37 | 400.37
225 | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME (SM/11795) | SM/11795 | 678.08 | 2632 | AUGMENTATION | 70 | Delayed | 52 | 05/08/2022 | 31/03/2025 | 15/12/2025 | 26/08/2022 | 354.35 | 354.35
226 | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ (SM/11643) | SM/11643 | 425.83 | 1698 | NEW | 70 | Delayed | 54 | 27/07/2022 | 31/12/2025 | 15/12/2025 | 31/08/2022 | 228.33 | 228.33
227 | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11794) | SM/11794 | 767.67 | 1680 | AUGMENTATION | 70 | Delayed | 42 | 05/08/2022 | 30/04/2025 | 15/12/2025 | 21/07/2022 | 324.29 | 324.29
228 | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. (SM/12785) | SM/12785 | 930.19 | 2866 | NEW | 70 | Delayed | 38 | 20/09/2022 | 30/04/2025 | 15/12/2025 | 15/03/2022 | 353.38 | 353.38
229 | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/18451) | SM/18451 | 1352.83 | 2019 | NEW | 71 | Delayed | 29 | 20/07/2023 | 31/01/2026 | 15/12/2025 | 27/07/2023 | 392.81 | 392.81
230 | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12644) | SM/12644 | 54.98 | 200 | AUGMENTATION | 71 | Delayed | 57 | 19/09/2022 | 31/05/2025 | 15/12/2025 | 28/10/2022 | 31.55 | 31.55
231 | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12107) | SM/12107 | 573.51 | 1535 | NEW | 72 | Delayed | 46 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 264.82 | 264.82
232 | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. (SM/16493) | SM/16493 | 496.17 | 1567 | NEW | 72 | Delayed | 48 | 02/03/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 239.38 | 239.38
233 | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT (SM/11825) | SM/11825 | 840.56 | 3083 | NEW | 72 | Delayed | 42 | 16/08/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 355.12 | 355.12
234 | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12099) | SM/12099 | 741.1 | 2423 | NEW | 73 | Delayed | 51 | 02/09/2022 | 31/01/2026 | 15/12/2025 | 01/11/2022 | 379.89 | 379.89
235 | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME (SM/11726) | SM/11726 | 791.06 | 2457 | AUGMENTATION | 73 | Delayed | 51 | 03/08/2022 | 31/03/2025 | 15/12/2025 | 31/08/2022 | 404.92 | 404.92
236 | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12653) | SM/12653 | 54.98 | 200 | AUGMENTATION | 73 | Delayed | 63 | 19/09/2022 | 31/07/2025 | 15/12/2025 | 28/10/2022 | 34.6 | 34.6
237 | Augmentation of Nalbithi Madhabpur Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. (SM/17743) | SM/17743 | 155.24 | 375 | AUGMENTATION | 74 | Delayed | 9 | 17/03/2023 | 30/06/2025 | 15/12/2025 | 27/03/2023 | 13.44 | 13.44
238 | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. (SM/16229) | SM/16229 | 470.99 | 790 | NEW | 74 | Delayed | 33 | 23/02/2023 | 31/12/2025 | 15/12/2025 | 10/08/2023 | 155.07 | 155.07
239 | IKARCHALA PWSS (SM/18294) | SM/18294 | 1200.16 | 3760 | NEW | 75 | Delayed | 41 | 26/06/2023 | 11/07/2025 | 15/12/2025 | 11/08/2023 | 493.91 | 493.91
240 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/11802) | SM/11802 | 894.05 | 2840 | AUGMENTATION | 75 | Delayed | 31 | 05/08/2022 | 31/03/2026 | 15/12/2025 | 26/08/2022 | 279.16 | 278.22
241 | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (SM/13013) | SM/13013 | 747.35 | 2310 | NEW | 75 | Delayed | 30 | 28/09/2022 | 31/12/2025 | 15/12/2025 | 01/11/2022 | 227.26 | 227.26
242 | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. (SM/14146) | SM/14146 | 719.4 | 1416 | NEW | 75 | Delayed | 31 | 02/01/2023 | 31/05/2025 | 15/12/2025 | 23/02/2023 | 221.4 | 221.4
243 | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12100) | SM/12100 | 656.05 | 2107 | NEW | 75 | Delayed | 47 | 02/09/2022 | 31/03/2025 | 15/12/2025 | 03/09/2019 | 309.37 | 309.37
244 | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block (SM/12094) | SM/12094 | 952.55 | 2314 | NEW | 77 | Delayed | 36 | 02/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 340.1 | 340.1
245 | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. (SM/13795) | SM/13795 | 1311.18 | 3098 | NEW | 77 | Delayed | 56 | 22/11/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 728.9 | 728.4
246 | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12639) | SM/12639 | 59.14 | 300 | AUGMENTATION | 78 | Delayed | 55 | 19/09/2022 | 30/04/2025 | 15/12/2025 | 28/10/2022 | 32.71 | 32.71
247 | DOHASO PWSS (SM/18304) | SM/18304 | 1767.14 | 4064 | NEW | 78 | Delayed | 52 | 26/06/2023 | 31/03/2025 | 15/12/2025 | 27/07/2023 | 915.74 | 915.74
248 | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district (SM/12109) | SM/12109 | 732.1 | 2257 | NEW | 78 | Delayed | 33 | 02/09/2022 | 31/05/2025 | 15/12/2025 | 18/01/2021 | 243.63 | 243.63
249 | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12102) | SM/12102 | 458.89 | 887 | NEW | 79 | Delayed | 43 | 02/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 198.36 | 198.36
250 | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12642) | SM/12642 | 63.86 | 425 | AUGMENTATION | 80 | Delayed | 31 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 20.11 | 20.11
251 | MANIKPUR Piped Water Supply Scheme at Islampur Block (SM/12084) | SM/12084 | 733.37 | 1646 | NEW | 80 | Delayed | 61 | 02/09/2022 | 30/04/2025 | 15/12/2025 | 16/01/2023 | 449.6 | 449.6
252 | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14230) | SM/14230 | 49.54 | 50 | AUGMENTATION | 80 | Delayed | 78 | 10/01/2023 | 31/12/2025 | 15/12/2025 | 16/01/2023 | 38.84 | 38.84
253 | Dwipnagar Piped Water Supply Scheme. (SM/18180) | SM/18180 | 531.76 | 2217 | NEW | 80 | Delayed | 42 | 30/03/2023 | 31/12/2025 | 15/12/2025 | 24/04/2023 | 222.85 | 222.85
254 | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. (SM/12393) | SM/12393 | 778.79 | 2114 | AUGMENTATION | 80 | Delayed | 26 | 13/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 198.61 | 198.61
255 | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12101) | SM/12101 | 562.28 | 1484 | NEW | 80 | Delayed | 44 | 02/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 245.83 | 245.83
256 | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12103) | SM/12103 | 733.2 | 2063 | NEW | 80 | Delayed | 43 | 02/09/2022 | 31/12/2025 | 15/12/2025 | 01/11/2022 | 316.49 | 316.49
257 | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/13020) | SM/13020 | 56.37 | 100 | AUGMENTATION | 80 | Delayed | 47 | 28/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 26.55 | 26.55
258 | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK (SM/11863) | SM/11863 | 461.61 | 1373 | NEW | 80 | Delayed | 48 | 17/08/2022 | 30/04/2025 | 15/12/2025 | 31/08/2022 | 221.39 | 221.39
259 | UTTAR SHAHAPUR PWSS (SM/18475) | SM/18475 | 1131 | 3076 | NEW | 80 | Delayed | 40 | 24/07/2023 | 11/07/2025 | 15/12/2025 | 04/08/2023 | 454.65 | 454.65
260 | Augmentation Dilwarpur Piped Water Supply Scheme. (SM/09989) | SM/09989 | 429.52 | 989 | AUGMENTATION | 80 | Delayed | 49 | 16/12/2021 | 31/01/2026 | 15/12/2025 | 07/01/2022 | 212.09 | 212.09
261 | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. (SM/16258) | SM/16258 | 921.63 | 2024 | NEW | 82 | Delayed | 39 | 24/02/2023 | 31/12/2025 | 15/12/2025 | 16/03/2023 | 355.64 | 355.64
262 | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. (SM/11865) | SM/11865 | 750.86 | 1870 | NEW | 82 | Delayed | 49 | 17/08/2022 | 31/05/2025 | 15/12/2025 | 14/11/2022 | 371.27 | 371.27
263 | Solarisation of WBSEDCL energised Pump house with Supply and Installation of Grid Connected Rooftop solar PV systems with Net metering for Sahavita water Supply scheme in the district of Uttar Dinajpur under malda Mechanical Division, PHE Dte. (SM/10232) | SM/10232 | 5.87 | 0 | SOLARISATION | 82 | Delayed | 0 | 24/02/2022 | 31/12/2025 | 15/12/2025 | 28/03/2022 | 0 | 0
264 | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block (SM/12096) | SM/12096 | 484.82 | 1031 | NEW | 84 | On track | 48 | 02/09/2022 | 31/03/2026 | 15/12/2025 | 31/01/2022 | 232.92 | 232.92
265 | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12640) | SM/12640 | 64.44 | 425 | AUGMENTATION | 85 | Delayed | 50 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 32.06 | 32.06
266 | Augmentation of Chopra Water Supply Scheme. (SM/10129) | SM/10129 | 1382.11 | 3136 | AUGMENTATION | 85 | Delayed | 29 | 08/02/2022 | 31/12/2025 | 15/12/2025 | 10/02/2022 | 397.4 | 397.4
267 | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME (SM/11797) | SM/11797 | 723.84 | 3392 | AUGMENTATION | 85 | Delayed | 40 | 05/08/2022 | 31/03/2025 | 15/12/2025 | 26/08/2022 | 290.77 | 290.77
268 | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME (SM/11196) | SM/11196 | 798.69 | 2946 | AUGMENTATION | 85 | Delayed | 41 | 03/06/2022 | 31/12/2025 | 15/12/2025 | 25/07/2022 | 328.24 | 328.24
269 | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12646) | SM/12646 | 49.11 | 50 | AUGMENTATION | 85 | Delayed | 69 | 19/09/2022 | 31/03/2025 | 15/12/2025 | 28/10/2022 | 33.78 | 33.78
270 | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. (SM/16224) | SM/16224 | 812.41 | 1682 | NEW | 85 | Delayed | 42 | 23/02/2023 | 30/04/2025 | 15/12/2025 | 21/03/2023 | 344.11 | 344.09
271 | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME (SM/11724) | SM/11724 | 623.82 | 2535 | AUGMENTATION | 85 | Delayed | 44 | 03/08/2022 | 31/03/2025 | 15/12/2025 | 26/08/2022 | 276.72 | 276.72
272 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11799) | SM/11799 | 1021.76 | 3105 | AUGMENTATION | 85 | Delayed | 37 | 05/08/2022 | 31/10/2025 | 15/12/2025 | 31/08/2022 | 378 | 378
273 | Baje Bindol PWSS in Raiganj Block in North Dinajpur District (SM/11644) | SM/11644 | 654.21 | 2254 | NEW | 85 | Delayed | 48 | 27/07/2022 | 24/05/2025 | 15/12/2025 | 26/08/2022 | 312.93 | 312.93
274 | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. (SM/16220) | SM/16220 | 571.4 | 946 | NEW | 86 | Delayed | 44 | 23/02/2023 | 31/03/2025 | 15/12/2025 | 08/05/2023 | 250.83 | 250.83
275 | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district (SM/12112) | SM/12112 | 650.8 | 1882 | NEW | 86 | Delayed | 62 | 02/09/2022 | 30/04/2025 | 15/12/2025 | 01/11/2022 | 403.2 | 403.2
276 | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. (SM/11801) | SM/11801 | 1037.52 | 3033 | AUGMENTATION | 87 | Delayed | 32 | 05/08/2022 | 30/09/2025 | 15/12/2025 | 07/07/2022 | 334.05 | 334.05
277 | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district (SM/12115) | SM/12115 | 837.26 | 2604 | NEW | 87 | On track | 53 | 02/09/2022 | 31/01/2026 | 15/12/2025 | 01/11/2022 | 441.62 | 441.62
278 | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. (SM/11961) | SM/11961 | 687.72 | 2986 | NEW | 88 | Delayed | 45 | 25/08/2022 | 31/05/2025 | 15/12/2025 | 14/11/2022 | 309 | 310.68
279 | ALIGANJ Piped Water Supply Scheme at Islampur Block (SM/12090) | SM/12090 | 1029.88 | 2409 | NEW | 89 | Delayed | 28 | 02/09/2022 | 31/03/2025 | 15/12/2025 | 01/11/2022 | 288.88 | 288.88
280 | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (SM/11800) | SM/11800 | 866.75 | 3014 | AUGMENTATION | 90 | Delayed | 46 | 05/08/2022 | 30/04/2025 | 15/12/2025 | 26/08/2022 | 396.63 | 396.55
281 | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. (SM/16199) | SM/16199 | 138.64 | 239 | NEW | 90 | On track | 37 | 24/02/2023 | 31/12/2025 | 15/12/2025 | 06/03/2023 | 51.9 | 51.9
282 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. (SM/11798) | SM/11798 | 695.38 | 1806 | AUGMENTATION | 90 | On track | 31 | 05/08/2022 | 31/01/2026 | 15/12/2025 | 31/08/2022 | 217.29 | 217.29
283 | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/13015) | SM/13015 | 53.17 | 150 | AUGMENTATION | 90 | Delayed | 57 | 28/09/2022 | 30/04/2025 | 15/12/2025 | 28/10/2022 | 30.26 | 30.25
284 | Augmentation of Kanki Matiari Piped Water Supply Scheme. (SM/09985) | SM/09985 | 340.27 | 577 | AUGMENTATION | 90 | Delayed | 58 | 16/12/2021 | 31/03/2025 | 15/12/2025 | 07/01/2022 | 196.33 | 196.25
285 | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR (SM/11819) | SM/11819 | 467.12 | 1335 | NEW | 90 | On track | 63 | 16/08/2022 | 31/01/2026 | 15/12/2025 | 14/11/2022 | 296.6 | 298.33
286 | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14229) | SM/14229 | 49.54 | 50 | AUGMENTATION | 90 | On track | 78 | 10/01/2023 | 31/01/2026 | 15/12/2025 | 16/01/2023 | 38.8 | 38.8
287 | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12098) | SM/12098 | 404.9 | 763 | NEW | 91 | Delayed | 48 | 02/09/2022 | 30/04/2025 | 15/12/2025 | 03/09/2019 | 193.96 | 193.96
288 | Augmentation of Sitalgaon Piped Water Supply Scheme. (SM/09990) | SM/09990 | 535.16 | 1165 | AUGMENTATION | 91 | Delayed | 41 | 16/12/2021 | 31/05/2025 | 15/12/2025 | 07/01/2022 | 217.4 | 217.4
289 | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12097) | SM/12097 | 576.88 | 1577 | NEW | 93 | On track | 47 | 02/09/2022 | 31/12/2025 | 15/12/2025 | 18/01/2021 | 273.01 | 274.79
290 | ATGHARA PIPED WATER SUPPLY SCHEME (SM/13796) | SM/13796 | 1298.23 | 3730 | NEW | 94 | Delayed | 59 | 22/11/2022 | 31/05/2025 | 15/12/2025 | 01/11/2022 | 771.45 | 771.45
291 | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. (SM/12790) | SM/12790 | 83.86 | 305 | NEW | 95 | On track | 93 | 20/09/2022 | 31/01/2026 | 15/12/2025 | 22/02/2023 | 77.88 | 77.88
292 | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district (SM/12104) | SM/12104 | 403.41 | 1077 | NEW | 95 | Delayed | 50 | 02/09/2022 | 30/04/2025 | 15/12/2025 | 01/11/2022 | 201.67 | 201.67
293 | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. (SM/18169) | SM/18169 | 96.73 | 236 | NEW | 95 | Delayed | 62 | 29/03/2023 | 31/03/2025 | 15/12/2025 | 29/05/2023 | 60.43 | 60.91
294 | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/12643) | SM/12643 | 54.48 | 200 | AUGMENTATION | 96 | On track | 57 | 19/09/2022 | 31/12/2025 | 15/12/2025 | 28/10/2022 | 30.91 | 30.91
295 | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme (SM/06723) | SM/06723 | 99.83 | 1788 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 99.83 | 49.93
296 | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme (SM/06726) | SM/06726 | 76.53 | 1218 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 76.53 | 69.91
297 | Laying of additional pipe line for retrofitting of Kotar for installation of FHTC. (SM/09169) | SM/09169 | 7.31 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 7.1 | 7.1
298 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. (SM/09172) | SM/09172 | 24.16 | 375 | RETROFITTING | 100 | 100% Physical | 96 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 23.25 | 23.24
299 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. (SM/09182) | SM/09182 | 52.94 | 815 | RETROFITTING | 100 | 100% Physical | 62 | 28/10/2021 | 31/12/2025 | 15/12/2025 | 23/12/2020 | 32.76 | 32.76
300 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. (SM/09193) | SM/09193 | 25.39 | 395 | RETROFITTING | 100 | 100% Physical | 38 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 14/09/2021 | 9.74 | 9.74
301 | Laying of additional pipe line for retrofitting of Poaltair WSS for installation of FHTC. (SM/09144) | SM/09144 | 16.4 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 15.9 | 15.9
302 | Laying of additional pipe line for retrofitting of Choprabari WSS for installation of FHTC. (SM/09134) | SM/09134 | 1.42 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 1.38 | 1.38
303 | Laying of additional pipe line for retrofitting of Baruna WSS for installation of FHTC. (SM/09142) | SM/09142 | 5.32 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 5.15 | 5.15
304 | Laying of additional pipe line for retrofitting of Bamair WSS for installation of FHTC. (SM/09143) | SM/09143 | 9.08 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 8.78 | 8.78
305 | Laying of additional pipe line for retrofitting of Phulatti WSS for installation of FHTC. (SM/09146) | SM/09146 | 6.77 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 6.56 | 6.56
306 | Laying of additional pipe line for retrofitting of Chotparua WSS for installation of FHTC. (SM/09148) | SM/09148 | 9.65 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 9.34 | 9.34
307 | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). (SM/09111) | SM/09111 | 8.11 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 7.8 | 7.8
308 | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. (SM/09121) | SM/09121 | 10.93 | 0 | RETROFITTING | 100 | 100% Physical | 86 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 9.44 | 9.44
309 | Laying of additional pipe line for retrofitting of Gunabari for installation of FHTC. (SM/09124) | SM/09124 | 6.72 | 0 | RETROFITTING | 100 | 100% Physical | 75 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 5.03 | 5.03
310 | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block (SM/07390) | SM/07390 | 2444.58 | 44879 | RETROFITTING | 100 | 100% Physical | 71 | 21/12/2020 | 31/03/2025 | 15/12/2025 | 23/12/2020 | 1726.02 | 1726.02
311 | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block (SM/07071) | SM/07071 | 94.34 | 1847 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/12/2025 | 15/12/2025 | 11/12/2020 | 94.34 | 76.48
312 | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte (SM/07977) | SM/07977 | 502.08 | 9907 | RETROFITTING | 100 | 100% Physical | 75 | 22/01/2021 | 31/03/2025 | 15/12/2025 | 18/06/2021 | 375.3 | 351.61
313 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. (SM/09179) | SM/09179 | 21.4 | 330 | RETROFITTING | 100 | 100% Physical | 98 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 21.07 | 19.81
314 | Laying of additional pipe line for retrofitting of Matikunda (Part-I/II) WSS for installation of FHTC. (SM/09130) | SM/09130 | 11.88 | 0 | RETROFITTING | 100 | 100% Physical | 50 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 24/12/2021 | 5.89 | 5.89
315 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09185) | SM/09185 | 28.92 | 448 | RETROFITTING | 100 | 100% Physical | 78 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 22.57 | 22.57
316 | Laying of additional pipe line for retrofitting of Mahinagar for installation of FHTC. (SM/09156) | SM/09156 | 5.87 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 5.66 | 5.66
317 | Laying of additional pipe line for retrofitting of Maslandapur for installation of FHTC. (SM/09166) | SM/09166 | 19.84 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 19.22 | 19.22
318 | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. (SM/09115) | SM/09115 | 11.97 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 11.61 | 11.61
319 | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). (SM/09127) | SM/09127 | 11.28 | 0 | RETROFITTING | 100 | 100% Physical | 53 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 6 | 5.76
320 | Restoration of Pipe line for providing FHTC for Sahavita Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10443) | SM/10443 | 8.95 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 8.68 | 8.68
321 | Laying of additional pipe line for retrofitting of Kaliganj WSS for installation of FHTC. (SM/09149) | SM/09149 | 7.36 | 0 | RETROFITTING | 100 | 100% Physical | 89 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 6.57 | 6.57
322 | Restoration of Pipe Line for Retrofitting FHTC of Mahadevpur Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10450) | SM/10450 | 9.67 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 11/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 9.37 | 9.37
323 | Restoration of Pipe Line for providing FHTC for Lodhan Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10425) | SM/10425 | 5.68 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 08/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 5.44 | 5.44
324 | Restoration of Pipe line for providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10499) | SM/10499 | 8.06 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 7.73 | 7.73
325 | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. (SM/13021) | SM/13021 | 58.49 | 150 | AUGMENTATION | 100 | 100% Physical | 46 | 28/09/2022 | 30/04/2025 | 15/12/2025 | 28/10/2022 | 26.89 | 26.89
326 | Laying of additional pipe line for retrofitting of Barobilla for installation of FHTC. (SM/09135) | SM/09135 | 2.23 | 0 | RETROFITTING | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 0 | 0
327 | Laying of additional pipe line for retrofitting of Noabari for installation of FHTC. (SM/09159) | SM/09159 | 14.36 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 13.86 | 13.86
328 | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. (SM/14228) | SM/14228 | 49.66 | 50 | AUGMENTATION | 100 | 100% Physical | 79 | 10/01/2023 | 31/12/2025 | 15/12/2025 | 16/01/2023 | 39.26 | 39.26
329 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09174) | SM/09174 | 55.54 | 855 | RETROFITTING | 100 | 100% Physical | 62 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 34.34 | 34.34
330 | Laying of additional pipe line for retrofitting of Nalbithi for installation of FHTC. (SM/09155) | SM/09155 | 8.45 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 8.19 | 8.19
331 | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme (SM/07143) | SM/07143 | 50.55 | 1004 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 50.55 | 56.87
332 | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme (SM/06725) | SM/06725 | 90.72 | 1651 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 90.72 | 82.56
333 | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme (SM/06730) | SM/06730 | 85.81 | 1452 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 85.81 | 81.09
334 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09178) | SM/09178 | 25.46 | 392 | RETROFITTING | 100 | 100% Physical | 100 | 28/10/2021 | 31/12/2023 | 15/12/2025 | 02/11/2021 | 25.46 | 25.46
335 | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. (SM/09131) | SM/09131 | 21.71 | 0 | RETROFITTING | 100 | 100% Physical | 85 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 18.41 | 18.41
336 | Laying of additional pipe line for retrofitting of Sripur for installation of FHTC. (SM/09163) | SM/09163 | 9.78 | 0 | RETROFITTING | 100 | 100% Physical | 94 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 9.24 | 9.24
337 | Laying of additional pipe line for retrofitting of Pakhuriya for installation of FHTC. (SM/09165) | SM/09165 | 33.01 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 31.79 | 31.67
338 | Laying of additional pipe line for retrofitting of Gopalpur for installation of FHTC. (SM/09151) | SM/09151 | 9.49 | 0 | RETROFITTING | 100 | 100% Physical | 90 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 8.59 | 8.46
339 | Laying of additional pipe line for retrofitting of Bindal WSS for installation of FHTC. (SM/09116) | SM/09116 | 13.3 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 12.83 | 12.83
340 | Restoration of Pipe Line for providing FHTC for Barua Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10448) | SM/10448 | 11.31 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 11/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 10.93 | 10.91
341 | Restoration of Damaged Pipe Line for providing FHTC at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10487) | SM/10487 | 16.04 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 15.56 | 15.56
342 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09194) | SM/09194 | 23.34 | 360 | RETROFITTING | 100 | 100% Physical | 52 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 14/09/2021 | 12.17 | 12.17
343 | Restoration of Pipe line for providing FHTC for Kotar Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10495) | SM/10495 | 4.99 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 11/05/2022 | 4.83 | 4.83
344 | Restoration of Pipe line for providing FHTC for Bheur Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10497) | SM/10497 | 6.78 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 6.54 | 6.54
345 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. (SM/09181) | SM/09181 | 25.2 | 388 | RETROFITTING | 100 | 100% Physical | 52 | 28/10/2021 | 31/07/2025 | 15/12/2025 | 02/11/2021 | 13.1 | 13.04
346 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. (SM/09187) | SM/09187 | 80.61 | 1240 | RETROFITTING | 100 | 100% Physical | 32 | 28/10/2021 | 31/05/2025 | 15/12/2025 | 02/11/2021 | 25.53 | 25.53
347 | Laying of additional pipe line for retrofitting of Paharajpur WSS for installation of FHTC. (SM/09145) | SM/09145 | 8.7 | 0 | RETROFITTING | 100 | 100% Physical | 94 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 24/12/2021 | 8.18 | 8.18
348 | Laying of additional pipe line for retrofitting of Siripur for installation of FHTC. (SM/09136) | SM/09136 | 8.46 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 8.21 | 8.21
349 | Laying of additional pipe line for retrofitting of Goagaon for installation of FHTC. (SM/09123) | SM/09123 | 3.47 | 0 | RETROFITTING | 100 | 100% Physical | 78 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 2.69 | 2.69
350 | Restoration of Pipe line for providing FHTC for Maslandpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10463) | SM/10463 | 7.55 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 7.32 | 7.32
351 | Restoration of Pipe Line for providing FHTC of Intia Piped Water Supply Scheme for installation of FHTC under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10447) | SM/10447 | 6.79 | 0 | RETROFITTING | 100 | 100% Physical | 93 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 6.32 | 6.32
352 | Restoration of Pipe line for providing FHTC for Sripur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10441) | SM/10441 | 5.31 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 5.15 | 5.15
353 | Restoration of Pipe Line for providing FHTC at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10424) | SM/10424 | 14.48 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 08/04/2022 | 31/03/2025 | 15/12/2025 | 09/12/2021 | 14.06 | 14.06
354 | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10500) | SM/10500 | 65.12 | 0 | RETROFITTING | 100 | 100% Physical | 20 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 31/03/2023 | 12.72 | 12.72
355 | Restoration of Pipe line for providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10465) | SM/10465 | 5.97 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 5.79 | 5.79
356 | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. (SM/09160) | SM/09160 | 16.43 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 15.95 | 15.93
357 | Restoration of Pipe line for providing FHTC for Bamair Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10493) | SM/10493 | 3.62 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 11/05/2022 | 3.51 | 3.51
358 | Laying of additional pipe line for retrofitting of Dakshin Kundal Pukur for installation of FHTC. (SM/09120) | SM/09120 | 13.59 | 0 | RETROFITTING | 100 | 100% Physical | 76 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 24/12/2021 | 10.37 | 10.37
359 | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme (SM/07141) | SM/07141 | 81.83 | 1578 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 81.83 | 76.5
360 | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block (SM/07389) | SM/07389 | 1512.6 | 26407 | RETROFITTING | 100 | 100% Physical | 73 | 21/12/2020 | 31/03/2025 | 15/12/2025 | 24/12/2020 | 1111.13 | 1092.75
361 | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme (SM/06724) | SM/06724 | 91.76 | 1573 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 91.76 | 84.06
362 | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem (SM/06728) | SM/06728 | 80.84 | 1175 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/12/2023 | 15/12/2025 | 16/10/2020 | 80.84 | 77.01
363 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. (SM/09183) | SM/09183 | 29.49 | 455 | RETROFITTING | 100 | 100% Physical | 47 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 13.89 | 13.89
364 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09186) | SM/09186 | 25.17 | 388 | RETROFITTING | 100 | 100% Physical | 44 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 11.07 | 11.07
365 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09188) | SM/09188 | 46.39 | 715 | RETROFITTING | 100 | 100% Physical | 61 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 14/09/2021 | 28.46 | 28.46
366 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09190) | SM/09190 | 47.07 | 725 | RETROFITTING | 100 | 100% Physical | 53 | 28/10/2021 | 31/01/2026 | 15/12/2025 | 02/11/2021 | 25.01 | 25.01
367 | Laying of additional pipe line for retrofitting of Tungail for installation of FHTC. (SM/09164) | SM/09164 | 4.69 | 0 | RETROFITTING | 100 | 100% Physical | 68 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 3.17 | 3.17
368 | Laying of additional pipe line for retrofitting of Sherpur for installation of FHTC. (SM/09167) | SM/09167 | 4.7 | 0 | RETROFITTING | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 0 | 0
369 | Laying of additional pipe line for retrofitting of Dakshin Jibhokati for installation of FHTC. (SM/09138) | SM/09138 | 1.42 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 1.38 | 1.38
370 | Laying of additional pipe line for retrofitting of Gutin WSS for installation of FHTC. (SM/09141) | SM/09141 | 9.09 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 8.79 | 8.79
371 | Laying of additional pipe line for retrofitting of Bheur WSS for installation of FHTC. (SM/09147) | SM/09147 | 9.09 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 8.81 | 8.81
372 | Laying of additional pipe line for retrofitting of SridharpurWSS for installation of FHTC. (SM/09150) | SM/09150 | 11.73 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 11.28 | 11.28
373 | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). (SM/09109) | SM/09109 | 20.54 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 19.82 | 19.82
374 | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. (SM/09118) | SM/09118 | 21.78 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 21.14 | 21.07
375 | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. (SM/09119) | SM/09119 | 17.05 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 16.45 | 16.45
376 | Laying of additional pipe line for retrofitting of Ghirnigaonfor installation of FHTC. (SM/09122) | SM/09122 | 92.44 | 0 | RETROFITTING | 100 | 100% Physical | 91 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 23/12/2020 | 83.8 | 83.58
377 | Restoration of Pipe line for providing FHTC for Pirojpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10445) | SM/10445 | 101.69 | 0 | RETROFITTING | 100 | 100% Physical | 25 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 24/06/2022 | 25.87 | 25.87
378 | Restoration of Pipe Line for providing FHTC of Gunabari Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10426) | SM/10426 | 10.57 | 0 | RETROFITTING | 100 | 100% Physical | 95 | 08/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 10.07 | 10.07
379 | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block (SM/07385) | SM/07385 | 88.74 | 1481 | RETROFITTING | 100 | 100% Physical | 74 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 09/12/2020 | 65.88 | 55.64
380 | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. (SM/09171) | SM/09171 | 17.94 | 280 | RETROFITTING | 100 | 100% Physical | 91 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 16.28 | 16.28
381 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09180) | SM/09180 | 18.97 | 295 | RETROFITTING | 100 | 100% Physical | 94 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 14/09/2021 | 17.87 | 18.42
382 | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. (SM/09128) | SM/09128 | 12.79 | 0 | RETROFITTING | 100 | 100% Physical | 69 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 8.81 | 8.81
383 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09189) | SM/09189 | 26.54 | 410 | RETROFITTING | 100 | 100% Physical | 86 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 22.75 | 22.75
384 | Laying of additional pipe line for retrofitting of Pirojpur for installation of FHTC. (SM/09157) | SM/09157 | 11.58 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 11.21 | 11.21
385 | Laying of additional pipe line for retrofitting of Udaypur for installation of FHTC. (SM/09158) | SM/09158 | 15.69 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 15.2 | 15.2
386 | Laying of additional pipe line for retrofitting of Piplan for installation of FHTC. (SM/09161) | SM/09161 | 8.07 | 0 | RETROFITTING | 100 | 100% Physical | 95 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 7.69 | 7.69
387 | Laying of additional pipe line for retrofitting of Surun for installation of FHTC. (SM/09168) | SM/09168 | 10.3 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 9.96 | 9.96
388 | Laying of additional pipe line for retrofitting of Pokheria WSS for installation of FHTC. (SM/09132) | SM/09132 | 3.92 | 0 | RETROFITTING | 100 | 100% Physical | 84 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 3.28 | 3.28
389 | Laying of additional pipe line for retrofitting of Biprit WSS for installation of FHTC. (SM/09133) | SM/09133 | 1.42 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 1.37 | 1.37
390 | Laying of additional pipe line for retrofitting of Majlishpur for installation of FHTC. (SM/09140) | SM/09140 | 2.23 | 0 | RETROFITTING | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 0 | 0
391 | Laying of additional pipe line for retrofitting of Intia WSS for installation of FHTC (Part-A & B) . (SM/09125) | SM/09125 | 20.85 | 0 | RETROFITTING | 100 | 100% Physical | 77 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 16.08 | 16.08
392 | Restoration of Pipe line for providing FHTC for Chhotoparua Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10466) | SM/10466 | 8.52 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 8.24 | 8.16
393 | Restoration of Pipe line for providing FHTC for Mahammadpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10444) | SM/10444 | 10.7 | 0 | RETROFITTING | 100 | 100% Physical | 85 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 17/02/2023 | 9.06 | 9.06
394 | Restoration of Pipe line for providing FHTC for Paharajpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10446) | SM/10446 | 6.2 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 6.02 | 6.02
395 | Restoration of Pipe line for providing FHTC for Sherpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10494) | SM/10494 | 5.97 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 5.76 | 5.76
396 | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme (SM/06722) | SM/06722 | 99.82 | 1763 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 99.82 | 76.36
397 | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. (SM/09113) | SM/09113 | 7.24 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 7 | 7
398 | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme (SM/06727) | SM/06727 | 85.49 | 1506 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 85.49 | 77.46
399 | Retrofitting of Functional household Tap connection (FHTC) under Faridpur and adjoining Mouzas water supply scheme (SM/07139) | SM/07139 | 72.77 | 1389 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 72.77 | 69.78
400 | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block (SM/07073) | SM/07073 | 68.13 | 1479 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 26/02/2021 | 68.13 | 62.07
401 | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme (SM/07140) | SM/07140 | 72.75 | 1458 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 72.75 | 55.78
402 | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme (SM/06731) | SM/06731 | 75.13 | 1281 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 75.13 | 40.83
403 | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. (SM/09170) | SM/09170 | 22.39 | 345 | RETROFITTING | 100 | 100% Physical | 100 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 22.28 | 22.28
404 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. (SM/09176) | SM/09176 | 20.04 | 309 | RETROFITTING | 100 | 100% Physical | 92 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 18.5 | 18.5
405 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. (SM/09191) | SM/09191 | 15.8 | 245 | RETROFITTING | 100 | 100% Physical | 78 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 12.25 | 12.25
406 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. (SM/09192) | SM/09192 | 21.06 | 325 | RETROFITTING | 100 | 100% Physical | 87 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 18.24 | 18.24
407 | Laying of additional pipe line for retrofitting of Debiganj for installation of FHTC. (SM/09137) | SM/09137 | 2.64 | 0 | RETROFITTING | 100 | WO no issued | 0 | 29/10/2021 | 31/03/2025 | 15/12/2025 |  | 0 | 0
408 | Laying of additional pipe line for retrofitting of Purba Durlavpur WSS for installation of FHTC. (SM/09112) | SM/09112 | 11.09 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 10.75 | 10.75
409 | Restoration of Pipe line for providing FHTC for Kaliganj Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10464) | SM/10464 | 7.77 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 31/03/2023 | 7.45 | 7.44
410 | Restoration of Pipe Line for Retrofitting FHTC of Deona Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10427) | SM/10427 | 2.08 | 0 | RETROFITTING | 100 | 100% Physical | 94 | 08/04/2022 | 31/03/2025 | 15/12/2025 | 11/05/2022 | 1.96 | 1.96
411 | Restoration of Pipe line for providing FHTC for Shridharpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) (SM/10442) | SM/10442 | 7.8 | 0 | RETROFITTING | 100 | 100% Physical | 55 | 12/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 4.3 | 4.3
412 | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. (SM/09173) | SM/09173 | 24.36 | 375 | RETROFITTING | 100 | 100% Physical | 92 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 22.53 | 22.53
413 | Restoration of Pipe line for providing FHTC for Udaypur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10496) | SM/10496 | 14.63 | 0 | RETROFITTING | 100 | 100% Physical | 72 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 10.6 | 10.6
414 | Restoration of Pipe line for providing FHTC for Mahinagar Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/10498) | SM/10498 | 9.85 | 0 | RETROFITTING | 100 | 100% Physical | 62 | 13/04/2022 | 31/03/2025 | 15/12/2025 | 17/02/2023 | 6.08 | 6.08
415 | Restoration of Pipe Line for providing FHTC at Jaingaon Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10547) | SM/10547 | 14.12 | 0 | RETROFITTING | 100 | 100% Physical | 95 | 18/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 13.36 | 13.36
416 | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme (SM/07142) | SM/07142 | 91.79 | 1788 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 91.79 | 76.88
417 | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme (SM/07145) | SM/07145 | 57.58 | 1291 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 57.58 | 56.72
418 | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme (SM/07146) | SM/07146 | 60.22 | 1125 | RETROFITTING | 100 | 100% Physical | 100 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 11/12/2020 | 60.22 | 58.19
419 | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme (SM/06729) | SM/06729 | 76.33 | 1302 | RETROFITTING | 100 | 100% Physical | 100 | 18/09/2020 | 31/03/2025 | 15/12/2025 | 16/10/2020 | 76.33 | 76.33
420 | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) (SM/07384) | SM/07384 | 51.74 | 841 | RETROFITTING | 100 | 100% Physical | 79 | 27/11/2020 | 31/03/2025 | 15/12/2025 | 04/02/2021 | 40.78 | 40.78
421 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. (SM/09175) | SM/09175 | 50.13 | 775 | RETROFITTING | 100 | 100% Physical | 91 | 28/10/2021 | 31/01/2026 | 15/12/2025 | 02/11/2021 | 45.7 | 45.7
422 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. (SM/09177) | SM/09177 | 16.25 | 250 | RETROFITTING | 100 | 100% Physical | 89 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 14.41 | 14.41
423 | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). (SM/09129) | SM/09129 | 41.15 | 0 | RETROFITTING | 100 | 100% Physical | 87 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 07/07/2021 | 35.8 | 35.8
424 | Laying of additional pipe line for retrofitting of Malgaon for installation of FHTC. (SM/09162) | SM/09162 | 14.14 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 24/12/2021 | 13.63 | 13.63
425 | Laying of additional pipe line for retrofitting of Majhihar WSS for installation of FHTC. (SM/09110) | SM/09110 | 9.77 | 0 | RETROFITTING | 100 | 100% Physical | 97 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 9.45 | 9.45
426 | Laying of additional pipe line for retrofitting of Mahammadpur WSS for installation of FHTC. (SM/09117) | SM/09117 | 18.81 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 17/11/2021 | 18.06 | 18.06
427 | Laying of additional pipe line for retrofitting of Jaingaon WSS for installation of FHTC. (SM/09126) | SM/09126 | 45.99 | 0 | RETROFITTING | 100 | 100% Physical | 96 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 44.16 | 44.16
428 | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. (SM/10545) | SM/10545 | 283.68 | 0 | AUGMENTATION | 100 | 100% Physical | 95 | 18/04/2022 | 31/03/2025 | 15/12/2025 | 03/11/2021 | 269.31 | 269.3
429 | Restoration of Pipe Line for providing FHTC at Pokharia Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) (SM/10449) | SM/10449 | 7.24 | 0 | RETROFITTING | 100 | 100% Physical | 88 | 11/04/2022 | 31/03/2025 | 15/12/2025 | 12/05/2022 | 6.37 | 6.37
430 | Replacement T/W for 4 Nos. water supply scheme. (SM/18227) | SM/18227 | 137.5 | 0 | AUGMENTATION | 100 | 100% Physical | 18 | 16/03/2023 | 31/03/2025 | 15/12/2025 | 16/12/2021 | 24.85 | 24.85
431 | Restoration of Pipe line for providing FHTC for Bindol Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) (SM/18993) | SM/18993 | 10.57 | 1875 | RETROFITTING | 100 | 100% Physical | 80 | 17/10/2023 | 09/04/2025 | 15/12/2025 | 17/10/2023 | 8.41 | 8.41
432 | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. (SM/09184) | SM/09184 | 29.76 | 458 | RETROFITTING | 100 | 100% Physical | 68 | 28/10/2021 | 31/03/2025 | 15/12/2025 | 02/11/2021 | 20.16 | 20.16
433 | Laying of additional pipe line for retrofitting of Bhagabati for installation of FHTC. (SM/09139) | SM/09139 | 2.84 | 0 | RETROFITTING | 100 | 100% Physical | 0 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 0 | 0
434 | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. (SM/09114) | SM/09114 | 13 | 0 | RETROFITTING | 100 | 100% Physical | 84 | 29/10/2021 | 31/03/2025 | 15/12/2025 | 12/11/2021 | 10.86 | 10.17
Total |  |  | 186275.93 | 634782 | [8 empty] | 60742.28 | 60433.99