## Scheme wise Physical Progress (
Scheme wise Physical Progress (Rs. in Lakh)
Sl.No. | Scheme | Scheme Code | Cost | FHTC Involved | Scheme Type | (%) Physical progress | Progress | (%) Financial progress | Date of Sanction | Date of Completion | Date of Updation | Date of 1st WO | Allotment | Expenditure
1 | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani (SM/19225) | SM/19225 | 2769.31 | 0 | AUGMENTATION | 0 | 0% Physical | 0 | 25/07/2024 | 31/12/2026 | 11/12/2025 | 03/12/2024 | 0 | 0
2 | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. (SM/12272) | SM/12272 | 46.86 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 09/09/2022 |  | 12/09/2022 | 31/08/2021 | 0 | 0
3 | Supply, Delivery and Installation of Computer & peripherals through GEMS for official use under office of the Executive Engineer, Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11869) | SM/11869 | 7.18 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 17/08/2022 |  | 18/08/2022 | 20/11/2022 | 0 | 0
4 | Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. (SM/10733) | SM/10733 | 13.14 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 19/05/2022 |  | 19/05/2022 | 03/07/2022 | 0 | 0
5 | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19086) | SM/19086 | 76.24 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 05/12/2023 |  | 05/12/2023 | 15/03/2024 | 0 | 0
6 | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Malda District. (SM/09645) | SM/09645 | 338.24 | 0 | SUPPORT-M&E | 0 | WO no issued | 0 | 23/11/2021 |  | 25/11/2021 | 18/08/2022 | 0 | 0
7 | Drinking water samples collection & testing through Field Test Kit (FTKs) & uploading charges related to Water Quality Monitoring & Surveillance programme under JJM in the district of Malda under Malda Division. (SM/08972) | SM/08972 | 20.92 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 | 03/01/2022 | 0 | 0
8 | Procurement of Computer and peripherals for office use in Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. (SM/10479) | SM/10479 | 7.66 | 0 | SUPPORT - MIS/ COMPUTERIZATION | 0 | 0% Physical | 0 | 13/04/2022 |  | 18/04/2022 | 22/06/2022 | 0 | 0
9 | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Malda District. (SM/08973) | SM/08973 | 11.43 | 0 | SUPPORT-M&E | 0 | 0% Physical | 0 | 29/10/2021 |  | 31/10/2021 | 21/02/2022 | 0 | 0
10 | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission (SM/18275) | SM/18275 | 136.69 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 23/06/2023 |  | 27/06/2023 | 06/12/2023 | 0 | 0
11 | Procurement of chemicals & consumables, glassware etc. required for smooth running of the laboratories under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/06639) | SM/06639 | 7.76 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 05/02/2020 |  | 31/05/2021 | 10/06/2020 | 0 | 0
12 | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission (SM/19339) | SM/19339 | 37.57 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 31/01/2025 |  | 24/02/2025 | 04/06/2025 | 0 | 0
13 | On-site assessment with sample collection & testing of AIRPs & CWPPs installed in Maldah district including supply & delivery of 7956 consumables in compatible with Onsite Mobile Analysis System in addition to monitoring & processing data of AIRPs & CWPPs (SM/19284) | SM/19284 | 88.34 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 | 09/01/2025 | 0 | 0
14 | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. (SM/12119) | SM/12119 | 6.25 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 06/09/2022 |  | 11/09/2022 | 21/01/2022 | 0 | 0
15 | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission (SM/19321) | SM/19321 | 269.66 | 0 | SUPPORT-WQMSP | 0 | 0% Physical | 0 | 26/12/2024 |  | 27/12/2024 | 22/11/2024 | 0 | 0
16 | Procurement of chemicals, Instruments and glassware including Annual Computer Maintenance and peripherals for Dariapur Water Treatment Plant Laboratory under Malda Arsenic Area Water Supply Division, P.H.E.Dte (SM/12843) | SM/12843 | 23.84 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 22/09/2022 |  | 23/09/2022 |  | 0 | 0
17 | Sample Collection & testing charges for drinking water quality quality testing for FHTCs in Malda District related to Water Quality Monitoring & Surveillance Activites under Jal Jeevan Mission (SM/19294) | SM/19294 | 397.07 | 0 | SUPPORT-WQMSP | 0 | WO no issued | 0 | 30/10/2024 |  | 12/11/2024 |  | 0 | 0
18 | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/10430) | SM/10430 | 546.45 | 12750 | RETROFITTING | 6 | Delayed | 1 | 12/04/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 3.9 | 3.9
19 | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit (SM/07971) | SM/07971 | 36.36 | 0 | SUPPORT-WQMSP | 8 | Delayed | 0 | 21/01/2021 | 31/03/2024 | 10/11/2023 | 19/05/2021 | 0 | 0
20 | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. (SM/06637) | SM/06637 | 89.78 | 0 | SUPPORT-WQMSP | 8 | Delayed | 0 | 05/02/2020 | 31/03/2024 | 24/11/2023 | 31/05/2022 | 0 | 0
21 | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/18910) | SM/18910 | 133.47 | 0 | AUGMENTATION | 10 | Delayed | 0 | 09/10/2023 | 30/06/2025 | 11/12/2025 | 30/08/2024 | 0 | 0
22 | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11915) | SM/11915 | 685.6 | 12637 | RETROFITTING | 12 | Delayed | 3 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 22.09 | 22.09
23 | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11914) | SM/11914 | 211.54 | 3749 | RETROFITTING | 12 | Delayed | 2 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 4.63 | 4.63
24 | Providing Functional Household Tap Connection (FHTC) under command area of Panchanadapur and Hamidpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11913) | SM/11913 | 343.66 | 6480 | RETROFITTING | 13 | Delayed | 0 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 0 | 0
25 | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. (SM/12741) | SM/12741 | 197.49 | 0 | SUPPORT-WQMSP | 13 | Delayed | 0 | 20/09/2022 | 31/03/2024 | 15/01/2024 | 26/08/2020 | 0 | 0
26 | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED (SM/15947) | SM/15947 | 875.39 | 2472 | NEW | 15 | Delayed | 9 | 22/02/2023 | 31/12/2025 | 11/12/2025 | 01/08/2023 | 75.59 | 75.59
27 | Providing Functional Household Tap Connection (FHTC) under command area of Paramanandapur, Biswambhar Binodpur, Bishnupur Shrirampara, Kamalpur, Paschim Narayanpur, Enayetpur and Gouripurr Zone Water Supply Scheme at Manikchak Block under Malda Arsenic Ar (SM/11917) | SM/11917 | 521.52 | 7515 | RETROFITTING | 17 | Delayed | 0 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 1.35 | 1.35
28 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl (SM/09656) | SM/09656 | 598.68 | 13790 | RETROFITTING | 18 | Delayed | 11 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 63.15 | 63.15
29 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block (SM/09655) | SM/09655 | 986.55 | 22779 | RETROFITTING | 20 | Delayed | 14 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 136.77 | 136.77
30 | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11912) | SM/11912 | 322.33 | 5765 | RETROFITTING | 20 | Delayed | 15 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 48.47 | 48.47
31 | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. (SM/11911) | SM/11911 | 937.95 | 15538 | RETROFITTING | 22 | Delayed | 0 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 3.94 | 3.94
32 | PERAPUR PWSS (SM/18420) | SM/18420 | 1213.51 | 3213 | NEW | 22 | Delayed | 8 | 18/07/2023 | 30/06/2025 | 11/12/2025 | 08/08/2023 | 94.37 | 94.37
33 | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE (SM/11916) | SM/11916 | 496.83 | 11515 | RETROFITTING | 23 | Delayed | 19 | 22/08/2022 | 31/12/2025 | 11/12/2025 | 10/05/2022 | 91.96 | 91.96
34 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block (SM/09661) | SM/09661 | 883.23 | 20500 | RETROFITTING | 25 | Delayed | 18 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 156.45 | 156.45
35 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha (SM/09658) | SM/09658 | 505.89 | 11500 | RETROFITTING | 25 | Delayed | 18 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 90.82 | 90.82
36 | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED (SM/18418) | SM/18418 | 1309.89 | 3327 | NEW | 28 | Delayed | 20 | 13/07/2023 | 31/12/2025 | 11/12/2025 | 01/08/2023 | 258.72 | 258.72
37 | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte (SM/15521) | SM/15521 | 1310.98 | 4378 | NEW | 30 | Delayed | 10 | 16/02/2023 | 31/12/2025 | 11/12/2025 | 04/05/2023 | 135.07 | 135.07
38 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT (SM/18686) | SM/18686 | 68069.12 | 56048 | NEW | 31 | Delayed | 19 | 04/08/2023 | 31/10/2025 | 11/12/2025 | 16/08/2023 | 13057.36 | 13057.36
39 | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme (SM/13792) | SM/13792 | 2992.8 | 11149 | AUGMENTATION | 32 | Delayed | 12 | 22/11/2022 | 30/06/2025 | 11/12/2025 | 13/03/2023 | 359.5 | 359.5
40 | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division (SM/18124) | SM/18124 | 231.67 | 0 | SOLARISATION | 32 | Delayed | 0 | 29/03/2023 | 31/03/2027 | 11/12/2025 | 07/07/2023 | 0 | 0
41 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc (SM/09657) | SM/09657 | 356.57 | 8012 | RETROFITTING | 34 | Delayed | 29 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 102.56 | 102.56
42 | Augmentation of Samsi PWSS. (SM/18447) | SM/18447 | 2234.04 | 6805 | AUGMENTATION | 35 | Delayed | 12 | 20/07/2023 | 31/12/2025 | 11/12/2025 | 08/08/2023 | 279.13 | 280.86
43 | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block (SM/18685) | SM/18685 | 15363.32 | 12384 | NEW | 35 | Delayed | 27 | 04/08/2023 | 31/07/2025 | 11/12/2025 | 11/08/2023 | 4101.75 | 4044.88
44 | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/18558) | SM/18558 | 3085.32 | 9132 | AUGMENTATION | 38 | Delayed | 17 | 31/07/2023 | 31/10/2025 | 11/12/2025 | 09/08/2023 | 535.86 | 535.86
45 | SOURCE AUGMENTATION TROUGH INTRODUCING ROLLING TYPE BARGE FOR RAW WATER LIFTING FROM RIVER FULHAR AT INTAKE STATION OF BALUPUR WATER SUPPLY SCHEME UNDER RATUA-I BLOCK IN THE DISTRICT OF MALDA UNDER MALDA MECHANICAL DIVISION, PHE DTE. (SM/18911) | SM/18911 | 109.49 | 0 | AUGMENTATION | 39 | Delayed | 38 | 09/10/2023 | 31/03/2027 | 11/12/2025 | 07/03/2024 | 42.04 | 42.04
46 | Uttar Mahinagar Piped Water Supply Scheme (SM/12765) | SM/12765 | 403.76 | 919 | NEW | 39 | Delayed | 41 | 20/09/2022 | 30/06/2025 | 11/12/2025 | 22/03/2023 | 166.45 | 166.45
47 | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED (SM/15949) | SM/15949 | 734.03 | 2088 | NEW | 40 | Delayed | 26 | 22/02/2023 | 31/12/2025 | 11/12/2025 | 06/04/2023 | 188.54 | 188.54
48 | Augmentation of Jatradanga Piped water supply scheme (SM/12734) | SM/12734 | 390.21 | 1133 | AUGMENTATION | 42 | Delayed | 25 | 20/09/2022 | 30/06/2025 | 11/12/2025 | 28/12/2020 | 98.37 | 98.37
49 | HATNAGAR PIPED WATER SUPPLY SCHEME (SM/18496) | SM/18496 | 1232.77 | 2677 | NEW | 42 | Delayed | 34 | 26/07/2023 | 30/06/2025 | 11/12/2025 | 10/08/2023 | 415.71 | 415.71
50 | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme (SM/14190) | SM/14190 | 546.57 | 1245 | AUGMENTATION | 42 | Delayed | 21 | 10/01/2023 | 30/06/2025 | 11/12/2025 | 20/03/2023 | 114.22 | 114.22
51 | DAHIL Piped Water Supply Scheme. (SM/18461) | SM/18461 | 1594.44 | 4422 | NEW | 42 | Delayed | 32 | 20/07/2023 | 31/12/2025 | 11/12/2025 | 08/08/2023 | 517.13 | 517.13
52 | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/16382) | SM/16382 | 1030.99 | 500 | AUGMENTATION | 43 | Delayed | 11 | 28/02/2023 | 30/06/2025 | 11/12/2025 | 11/08/2023 | 118.07 | 118.07
53 | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12323) | SM/12323 | 180.45 | 1906 | AUGMENTATION | 43 | Delayed | 42 | 09/09/2022 | 30/06/2025 | 11/12/2025 | 10/11/2022 | 76.49 | 76.49
54 | Augmentation of Adina Zone-I Piped Water Supply Scheme (SM/15958) | SM/15958 | 543.44 | 972 | AUGMENTATION | 44 | Delayed | 25 | 22/02/2023 | 30/06/2025 | 11/12/2025 | 22/03/2022 | 135.49 | 135.49
55 | JAMALPUR Piped Water Supply Scheme. (SM/12879) | SM/12879 | 1047.18 | 4212 | NEW | 44 | Delayed | 40 | 23/09/2022 | 30/06/2025 | 11/12/2025 | 15/03/2023 | 418.1 | 418.1
56 | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme (SM/14099) | SM/14099 | 2200.14 | 5251 | AUGMENTATION | 45 | Delayed | 6 | 15/12/2022 | 30/06/2025 | 11/12/2025 | 24/07/2023 | 136.36 | 136.36
57 | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) (SM/18660) | SM/18660 | 80427.62 | 0 | AUGMENTATION | 45 | Delayed | 27 | 04/08/2023 | 31/12/2025 | 11/12/2025 | 14/08/2023 | 21474.84 | 21474.84
58 | BISHANPUR PIPED WATER SUPPLY SCHEME (SM/13507) | SM/13507 | 682.77 | 2698 | NEW | 45 | Delayed | 42 | 02/11/2022 | 30/06/2025 | 11/12/2025 | 11/05/2023 | 288.63 | 288.63
59 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik (SM/09663) | SM/09663 | 506.2 | 12315 | RETROFITTING | 45 | Delayed | 36 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 179.94 | 179.94
60 | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/14420) | SM/14420 | 172.98 | 0 | AUGMENTATION | 45 | Delayed | 7 | 20/01/2023 | 30/06/2025 | 11/12/2025 | 02/02/2023 | 12.17 | 12.17
61 | Augmentation of Mahishbathani Piped Water Supply Scheme (SM/16383) | SM/16383 | 328.05 | 1587 | AUGMENTATION | 46 | Delayed | 33 | 28/02/2023 | 30/06/2025 | 11/12/2025 | 17/05/2023 | 108.33 | 108.33
62 | Augmentation of Nasipur Piped Water Supply Scheme (SM/15952) | SM/15952 | 868.83 | 2049 | AUGMENTATION | 46 | Delayed | 39 | 22/02/2023 | 30/06/2025 | 11/12/2025 | 14/07/2023 | 338.98 | 338.98
63 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha (SM/09590) | SM/09590 | 235.98 | 5193 | RETROFITTING | 47 | Delayed | 40 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 14/10/2020 | 95.01 | 95.01
64 | Alal Zone-II Piped Water Supply Scheme (SM/12877) | SM/12877 | 596.19 | 1413 | NEW | 48 | Delayed | 26 | 23/09/2022 | 30/06/2025 | 11/12/2025 | 22/03/2022 | 155.64 | 155.64
65 | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12317) | SM/12317 | 281.18 | 1275 | AUGMENTATION | 49 | Delayed | 38 | 09/09/2022 | 31/12/2025 | 11/12/2025 | 10/11/2022 | 107.71 | 107.71
66 | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15112) | SM/15112 | 84.77 | 0 | AUGMENTATION | 49 | Delayed | 19 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 17/02/2023 | 16.09 | 16.09
67 | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo (SM/08760) | SM/08760 | 183.54 | 2649 | RETROFITTING | 50 | Delayed | 70 | 08/09/2021 | 30/06/2025 | 11/12/2025 | 03/11/2021 | 128.33 | 128.33
68 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III (SM/09650) | SM/09650 | 589.71 | 12985 | RETROFITTING | 50 | Delayed | 37 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 12/05/2022 | 219.54 | 219.54
69 | PARAIL PWSS (SM/18431) | SM/18431 | 1276.14 | 3263 | NEW | 51 | Delayed | 45 | 18/07/2023 | 31/08/2025 | 11/12/2025 | 07/08/2023 | 568.9 | 568.9
70 | Sahapur Piped Water Supply Scheme (SM/11968) | SM/11968 | 1135.04 | 7669 | NEW | 52 | Delayed | 38 | 26/08/2022 | 30/06/2025 | 11/12/2025 | 09/09/2021 | 429.88 | 429.88
71 | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/14098) | SM/14098 | 1578.1 | 4588 | NEW | 52 | Delayed | 30 | 15/12/2022 | 30/06/2025 | 11/12/2025 | 22/03/2022 | 478.46 | 478.46
72 | Augmentation of Alal Zone-III Piped Water Supply Scheme (SM/15951) | SM/15951 | 425.25 | 1052 | AUGMENTATION | 52 | Delayed | 43 | 22/02/2023 | 31/12/2025 | 11/12/2025 | 22/03/2022 | 181.55 | 181.55
73 | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11590) | SM/11590 | 609.28 | 2789 | NEW | 52 | Delayed | 38 | 22/07/2022 | 31/10/2025 | 11/12/2025 | 22/03/2022 | 230.6 | 230.6
74 | BABUPUR PWSS (SM/18433) | SM/18433 | 1697.39 | 5617 | NEW | 52 | Delayed | 41 | 18/07/2023 | 30/06/2025 | 11/12/2025 | 09/08/2023 | 698.44 | 698.44
75 | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15062) | SM/15062 | 93.1 | 0 | AUGMENTATION | 52 | Delayed | 48 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 17/02/2023 | 44.23 | 44.23
76 | Augmentation of Khusida Piped Water Supply Scheme (SM/10397) | SM/10397 | 1222.99 | 426 | AUGMENTATION | 52 | Delayed | 43 | 31/03/2022 | 30/06/2025 | 11/12/2025 | 24/05/2022 | 526.38 | 526.38
77 | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem (SM/07972) | SM/07972 | 2518.77 | 47698 | RETROFITTING | 53 | Delayed | 48 | 26/01/2021 | 30/06/2025 | 11/12/2025 | 30/09/2020 | 1201.68 | 1201.68
78 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme (SM/06862) | SM/06862 | 49.15 | 878 | RETROFITTING | 53 | Delayed | 41 | 07/10/2020 | 31/10/2025 | 11/12/2025 | 13/08/2021 | 20.07 | 20.07
79 | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. (SM/12267) | SM/12267 | 753.45 | 2534 | NEW | 53 | Delayed | 33 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 08/06/2023 | 250.21 | 250.21
80 | Alal Zone-I Piped Water Supply Scheme (SM/12075) | SM/12075 | 732.76 | 1971 | NEW | 53 | Delayed | 35 | 02/09/2022 | 30/06/2025 | 11/12/2025 | 22/03/2022 | 257.15 | 257.15
81 | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME (SM/15155) | SM/15155 | 398.39 | 1413 | AUGMENTATION | 53 | Delayed | 52 | 07/02/2023 | 30/06/2025 | 11/12/2025 | 21/03/2023 | 205.46 | 206.27
82 | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15149) | SM/15149 | 881.16 | 375 | AUGMENTATION | 53 | Delayed | 17 | 06/02/2023 | 30/06/2025 | 11/12/2025 | 14/07/2023 | 150.86 | 150.86
83 | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15057) | SM/15057 | 64.27 | 0 | AUGMENTATION | 54 | Delayed | 23 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 17/02/2023 | 14.56 | 14.56
84 | Hatinda Piped Water Supply Scheme. (SM/12078) | SM/12078 | 1095.36 | 4783 | NEW | 54 | Delayed | 43 | 02/09/2022 | 30/06/2025 | 11/12/2025 | 11/10/2022 | 471.83 | 471.83
85 | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12763) | SM/12763 | 369.49 | 750 | AUGMENTATION | 54 | Delayed | 48 | 20/09/2022 | 31/12/2025 | 11/12/2025 | 07/12/2022 | 176.1 | 176.02
86 | MORGRAM PWSS (SM/18557) | SM/18557 | 1098.97 | 3767 | NEW | 55 | Delayed | 41 | 31/07/2023 | 30/09/2025 | 11/12/2025 | 10/08/2023 | 451.8 | 451.8
87 | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15308) | SM/15308 | 879.54 | 340 | AUGMENTATION | 55 | Delayed | 15 | 10/02/2023 | 30/06/2025 | 11/12/2025 | 03/05/2023 | 134.22 | 134.22
88 | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12313) | SM/12313 | 145.33 | 1008 | AUGMENTATION | 55 | Delayed | 48 | 09/09/2022 | 31/12/2025 | 11/12/2025 | 03/11/2022 | 69.75 | 69.75
89 | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED (SM/17201) | SM/17201 | 714.72 | 8677 | NEW | 55 | Delayed | 22 | 15/03/2023 | 31/07/2025 | 11/12/2025 | 30/03/2023 | 157.77 | 157.77
90 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme (SM/06861) | SM/06861 | 89.31 | 1675 | RETROFITTING | 55 | Delayed | 35 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 10/11/2020 | 31.33 | 31.33
91 | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12760) | SM/12760 | 220.11 | 0 | AUGMENTATION | 56 | Delayed | 3 | 20/09/2022 | 30/06/2025 | 11/12/2025 | 07/12/2022 | 6.67 | 6.67
92 | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15193) | SM/15193 | 988.47 | 420 | AUGMENTATION | 56 | Delayed | 18 | 06/02/2023 | 30/06/2025 | 11/12/2025 | 02/06/2023 | 174.89 | 174.89
93 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B (SM/09662) | SM/09662 | 470.57 | 10136 | RETROFITTING | 56 | Delayed | 52 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 246.8 | 246.8
94 | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12315) | SM/12315 | 174.73 | 0 | AUGMENTATION | 56 | Delayed | 49 | 09/09/2022 | 30/06/2025 | 11/12/2025 | 10/11/2022 | 84.82 | 84.82
95 | KALUARI PWSS (SM/18427) | SM/18427 | 1380.18 | 4894 | NEW | 57 | Delayed | 40 | 18/07/2023 | 31/12/2025 | 11/12/2025 | 08/08/2023 | 549.07 | 549.07
96 | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15093) | SM/15093 | 196.91 | 950 | AUGMENTATION | 58 | Delayed | 29 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 21/03/2023 | 57.77 | 57.77
97 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar (SM/09589) | SM/09589 | 67.89 | 1542 | RETROFITTING | 58 | Delayed | 50 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 33.89 | 33.89
98 | EMAMNAGAR PIPED WATER SUPPLY SCHEME. (SM/13720) | SM/13720 | 1484.54 | 3632 | NEW | 58 | Delayed | 51 | 17/11/2022 | 30/06/2025 | 11/12/2025 | 13/03/2023 | 762.81 | 762.81
99 | Pukuria Piped Water Supply Scheme (SM/14100) | SM/14100 | 1884.19 | 5771 | NEW | 58 | Delayed | 33 | 15/12/2022 | 31/12/2025 | 11/12/2025 | 22/03/2022 | 626 | 626
100 | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15102) | SM/15102 | 104.31 | 0 | AUGMENTATION | 58 | Delayed | 74 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 20/03/2023 | 77.28 | 77.28
101 | PARAHAR PWSS (SM/18432) | SM/18432 | 1356.09 | 2983 | NEW | 58 | Delayed | 51 | 18/07/2023 | 31/08/2025 | 11/12/2025 | 02/08/2023 | 685.3 | 685.3
102 | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15106) | SM/15106 | 149.47 | 1658 | AUGMENTATION | 58 | Delayed | 36 | 04/02/2023 | 31/05/2025 | 11/12/2025 | 17/02/2023 | 53.89 | 53.89
103 | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME (SM/15188) | SM/15188 | 390.5 | 2641 | AUGMENTATION | 58 | Delayed | 43 | 07/02/2023 | 30/06/2025 | 11/12/2025 | 21/03/2023 | 166.58 | 166.58
104 | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/14097) | SM/14097 | 1143.9 | 3524 | NEW | 59 | Delayed | 17 | 15/12/2022 | 30/06/2025 | 11/12/2025 | 22/03/2022 | 197.78 | 197.78
105 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- (SM/09592) | SM/09592 | 464.42 | 9584 | RETROFITTING | 59 | Delayed | 54 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 250.41 | 250.41
106 | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte (SM/12304) | SM/12304 | 602.34 | 1823 | NEW | 59 | Delayed | 54 | 09/09/2022 | 30/06/2025 | 11/12/2025 | 03/05/2023 | 324.76 | 324.76
107 | Augmentation of Uttar Harishandropur piped water supply scheme. (SM/10291) | SM/10291 | 2223.72 | 8400 | AUGMENTATION | 60 | Delayed | 36 | 28/02/2022 | 30/06/2025 | 11/12/2025 | 03/09/2019 | 801.27 | 801.04
108 | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10237) | SM/10237 | 530.47 | 0 | ANGANWADI | 60 | Delayed | 0 | 24/02/2022 | 30/06/2025 | 11/12/2025 | 01/04/2022 | 0 | 0
109 | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED (SM/15275) | SM/15275 | 994.39 | 2458 | NEW | 60 | Delayed | 27 | 04/02/2023 | 31/05/2025 | 11/12/2025 | 31/05/2023 | 264.98 | 264.98
110 | Augmentation of Adina Zone-II Piped Water Supply Scheme (SM/15956) | SM/15956 | 355.78 | 649 | AUGMENTATION | 60 | Delayed | 46 | 22/02/2023 | 30/06/2025 | 11/12/2025 | 02/05/2023 | 164.17 | 164.17
111 | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED (SM/17178) | SM/17178 | 855.71 | 2134 | NEW | 60 | Delayed | 24 | 15/03/2023 | 31/07/2025 | 11/12/2025 | 01/08/2023 | 209.28 | 209.28
112 | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12311) | SM/12311 | 335.27 | 1504 | AUGMENTATION | 60 | Delayed | 52 | 09/09/2022 | 30/06/2025 | 11/12/2025 | 10/11/2022 | 175.72 | 175.72
113 | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/16053) | SM/16053 | 620.93 | 125 | AUGMENTATION | 60 | Delayed | 42 | 22/02/2023 | 31/12/2025 | 11/12/2025 | 26/04/2023 | 263.48 | 263.48
114 | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED (SM/13451) | SM/13451 | 837.04 | 2345 | NEW | 60 | Delayed | 25 | 02/11/2022 | 31/07/2025 | 11/12/2025 | 08/09/2022 | 211.82 | 211.82
115 | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. (SM/17177) | SM/17177 | 967 | 2406 | NEW | 60 | Delayed | 32 | 15/03/2023 | 31/08/2025 | 11/12/2025 | 28/03/2023 | 308.69 | 308.69
116 | JIBJALSAR Piped Water Supply Scheme (SM/12182) | SM/12182 | 73.06 | 146 | NEW | 61 | Delayed | 69 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 01/11/2022 | 50.52 | 50.52
117 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte (SM/07973) | SM/07973 | 5777.65 | 110880 | RETROFITTING | 61 | Delayed | 29 | 26/01/2021 | 30/09/2025 | 11/12/2025 | 16/09/2020 | 1688.47 | 1688.46
118 | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12305) | SM/12305 | 152.39 | 0 | AUGMENTATION | 62 | Delayed | 46 | 09/09/2022 | 31/12/2025 | 11/12/2025 | 20/12/2022 | 70.51 | 70.51
119 | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15080) | SM/15080 | 213.72 | 0 | AUGMENTATION | 62 | Delayed | 59 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 20/03/2023 | 125.04 | 125.04
120 | SUJAPUR PIPED WATER SUPPLY SCHEME (SM/15962) | SM/15962 | 586.08 | 1287 | NEW | 62 | Delayed | 20 | 22/02/2023 | 30/06/2025 | 11/12/2025 | 07/06/2023 | 115.83 | 116.69
121 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme (SM/06870) | SM/06870 | 92.34 | 1735 | RETROFITTING | 62 | Delayed | 54 | 08/10/2020 | 30/06/2025 | 11/12/2025 | 10/11/2020 | 50 | 45.91
122 | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME (SM/10181) | SM/10181 | 2126.39 | 7524 | AUGMENTATION | 62 | Delayed | 49 | 17/02/2022 | 31/07/2025 | 11/12/2025 | 26/08/2021 | 1040.91 | 1040.88
123 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block (SM/09591) | SM/09591 | 145.97 | 3174 | RETROFITTING | 63 | Delayed | 58 | 23/11/2021 | 31/03/2025 | 11/12/2025 | 24/11/2021 | 84.4 | 84.4
124 | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12316) | SM/12316 | 167.81 | 1748 | AUGMENTATION | 63 | Delayed | 53 | 09/09/2022 | 31/12/2025 | 11/12/2025 | 03/11/2022 | 88.63 | 89.29
125 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl (SM/09651) | SM/09651 | 189.35 | 3940 | RETROFITTING | 65 | Delayed | 57 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 107.65 | 107.65
126 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo (SM/09647) | SM/09647 | 363.53 | 8220 | RETROFITTING | 65 | Delayed | 56 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 202.48 | 202.48
127 | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11588) | SM/11588 | 904.9 | 2912 | NEW | 66 | Delayed | 29 | 22/07/2022 | 31/12/2025 | 11/12/2025 | 22/03/2022 | 263.59 | 263.59
128 | KISMAT BAROL Piped Water Supply Scheme (SM/12190) | SM/12190 | 672 | 2326 | NEW | 66 | Delayed | 16 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 06/06/2023 | 109.93 | 109.93
129 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme (SM/06852) | SM/06852 | 102.95 | 1707 | RETROFITTING | 66 | Delayed | 59 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 28/01/2021 | 60.27 | 60.27
130 | Augmentation of Deotala Water Supply Scheme (SM/09986) | SM/09986 | 842.06 | 2446 | AUGMENTATION | 66 | Delayed | 22 | 16/12/2021 | 30/06/2025 | 11/12/2025 | 15/06/2021 | 182.78 | 182.78
131 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl (SM/09652) | SM/09652 | 450.25 | 9700 | RETROFITTING | 66 | Delayed | 60 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 272.23 | 272.23
132 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme (SM/06851) | SM/06851 | 96.17 | 1811 | RETROFITTING | 67 | Delayed | 42 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 10/11/2020 | 40.32 | 40.32
133 | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12312) | SM/12312 | 131.81 | 0 | AUGMENTATION | 67 | Delayed | 49 | 09/09/2022 | 31/12/2025 | 11/12/2025 | 03/11/2022 | 64.5 | 64.5
134 | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. (SM/13721) | SM/13721 | 1128.57 | 2846 | NEW | 67 | Delayed | 5 | 17/11/2022 | 30/06/2025 | 11/12/2025 | 11/08/2023 | 56.19 | 56.19
135 | KRISHNAPUR PIPED WATER SUPPLY SCHEME. (SM/13746) | SM/13746 | 880.68 | 2560 | NEW | 67 | Delayed | 61 | 17/11/2022 | 31/05/2025 | 11/12/2025 | 10/04/2023 | 536.99 | 538.77
136 | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11589) | SM/11589 | 618.45 | 2900 | NEW | 67 | Delayed | 42 | 22/07/2022 | 30/06/2025 | 11/12/2025 | 22/03/2022 | 262.75 | 262.75
137 | FATEPUR Piped Water Supply Scheme (SM/14173) | SM/14173 | 1581.73 | 4277 | NEW | 68 | Delayed | 16 | 09/01/2023 | 30/06/2025 | 11/12/2025 | 13/03/2023 | 256.8 | 256.8
138 | ARAZI JALSA PIPED WATER SUPPLY SCHEME. (SM/13734) | SM/13734 | 1389.03 | 3312 | NEW | 68 | Delayed | 56 | 17/11/2022 | 30/06/2025 | 11/12/2025 | 17/05/2023 | 781.73 | 781.73
139 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme (SM/06850) | SM/06850 | 68.82 | 1268 | RETROFITTING | 69 | Delayed | 50 | 07/10/2020 | 31/12/2025 | 11/12/2025 | 31/12/2021 | 34.1 | 34.1
140 | RAJARAM CHAK PIPED WATER SUPPLY SCHEME (SM/14461) | SM/14461 | 447.97 | 1274 | NEW | 69 | Delayed | 36 | 20/01/2023 | 31/12/2025 | 11/12/2025 | 20/03/2023 | 159.75 | 159.75
141 | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10246) | SM/10246 | 812.74 | 0 | ANGANWADI | 69 | Delayed | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 03/09/2019 | 0 | 0
142 | SULTANNAGAR PWSS (SM/12196) | SM/12196 | 512.75 | 1659 | NEW | 69 | Delayed | 48 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 17/11/2022 | 247.62 | 247.62
143 | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) (SM/10202) | SM/10202 | 609.64 | 0 | ANGANWADI | 70 | Delayed | 0 | 24/02/2022 | 30/06/2025 | 11/12/2025 | 01/04/2022 | 0 | 0
144 | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED (SM/18232) | SM/18232 | 1365.35 | 2545 | NEW | 70 | Delayed | 31 | 12/06/2023 | 31/05/2025 | 11/12/2025 | 13/07/2023 | 424.2 | 424.2
145 | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED (SM/12708) | SM/12708 | 574.74 | 1867 | NEW | 70 | Delayed | 35 | 20/09/2022 | 31/07/2025 | 11/12/2025 | 12/09/2022 | 202.89 | 202.89
146 | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED (SM/15143) | SM/15143 | 270.23 | 0 | AUGMENTATION | 70 | Delayed | 60 | 06/02/2023 | 31/05/2025 | 11/12/2025 | 21/01/2021 | 160.9 | 160.9
147 | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED (SM/15944) | SM/15944 | 571.17 | 833 | NEW | 70 | Delayed | 33 | 22/02/2023 | 31/05/2025 | 11/12/2025 | 01/08/2023 | 189.67 | 189.67
148 | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10380) | SM/10380 | 836.73 | 0 | ANGANWADI | 70 | Delayed | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
149 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme (SM/06857) | SM/06857 | 91.69 | 1722 | RETROFITTING | 70 | Delayed | 52 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 05/05/2021 | 47.4 | 47.4
150 | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12314) | SM/12314 | 135.51 | 0 | AUGMENTATION | 70 | Delayed | 48 | 09/09/2022 | 31/12/2025 | 11/12/2025 | 20/12/2022 | 65.15 | 65.15
151 | Augmentation of Bulbulchandi PWSS. (SM/09422) | SM/09422 | 981.06 | 4929 | AUGMENTATION | 70 | Delayed | 63 | 17/11/2021 | 31/12/2025 | 11/12/2025 | 19/05/2022 | 619.2 | 619.2
152 | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME (SM/15948) | SM/15948 | 254.87 | 733 | AUGMENTATION | 71 | Delayed | 33 | 22/02/2023 | 18/09/2025 | 11/12/2025 | 08/06/2023 | 84.04 | 84.04
153 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl (SM/09593) | SM/09593 | 577.48 | 12090 | RETROFITTING | 71 | Delayed | 48 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 278.49 | 278.49
154 | DAKSHIN BHAKURIA Piped Water Supply Scheme (SM/12186) | SM/12186 | 346.83 | 969 | NEW | 71 | Delayed | 39 | 06/09/2022 | 30/06/2025 | 11/12/2025 | 17/11/2022 | 134.41 | 134.41
155 | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15083) | SM/15083 | 75.97 | 0 | AUGMENTATION | 72 | Delayed | 15 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 11.48 | 11.48
156 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme (SM/07007) | SM/07007 | 86.07 | 1583 | RETROFITTING | 72 | Delayed | 67 | 18/11/2020 | 30/06/2025 | 11/12/2025 | 12/10/2020 | 57.73 | 57.73
157 | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15090) | SM/15090 | 102.52 | 0 | AUGMENTATION | 73 | Delayed | 59 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 60.56 | 60.56
158 | BANGRUA PWSS (SM/12193) | SM/12193 | 300.09 | 900 | NEW | 74 | Delayed | 17 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 17/02/2023 | 52.46 | 53.34
159 | MALIOR PWSS (SM/12192) | SM/12192 | 718.85 | 2789 | NEW | 74 | Delayed | 40 | 07/09/2022 | 31/12/2025 | 11/12/2025 | 17/11/2022 | 284.25 | 284.25
160 | ALINAGAR Piped Water Supply Scheme (SM/13431) | SM/13431 | 724.32 | 2356 | NEW | 74 | Delayed | 57 | 02/11/2022 | 31/05/2025 | 11/12/2025 | 27/02/2023 | 409.47 | 409.47
161 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc (SM/09659) | SM/09659 | 246.4 | 5400 | RETROFITTING | 75 | Delayed | 70 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 172.28 | 172.28
162 | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED (SM/12709) | SM/12709 | 743.66 | 2904 | NEW | 75 | Delayed | 29 | 20/09/2022 | 31/03/2025 | 11/12/2025 | 12/09/2022 | 216.1 | 216.1
163 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme (SM/06853) | SM/06853 | 61.62 | 1125 | RETROFITTING | 75 | Delayed | 14 | 07/10/2020 | 31/12/2025 | 11/12/2025 | 10/11/2020 | 8.75 | 8.75
164 | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED (SM/15946) | SM/15946 | 507.92 | 858 | NEW | 75 | Delayed | 42 | 22/02/2023 | 31/07/2025 | 11/12/2025 | 14/07/2023 | 211.78 | 211.78
165 | PARO PWSS (SM/12195) | SM/12195 | 510.75 | 1995 | NEW | 76 | Delayed | 41 | 07/09/2022 | 31/10/2025 | 11/12/2025 | 18/07/2023 | 208.56 | 208.56
166 | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15113) | SM/15113 | 261.08 | 1251 | AUGMENTATION | 76 | Delayed | 57 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 20/03/2023 | 147.78 | 147.78
167 | MATHURAPUR PIPED WATER SUPPLY SCHEME (SM/15248) | SM/15248 | 576.55 | 2416 | NEW | 76 | Delayed | 33 | 07/02/2023 | 31/12/2025 | 11/12/2025 | 12/05/2023 | 192.38 | 192.59
168 | Sanjail PWSS in Old Malda Block in District Malda (SM/12337) | SM/12337 | 380.75 | 822 | NEW | 76 | Delayed | 75 | 12/09/2022 | 30/06/2025 | 11/12/2025 | 16/09/2022 | 284.03 | 284.03
169 | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10243) | SM/10243 | 503.77 | 0 | ANGANWADI | 76 | Delayed | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
170 | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10242) | SM/10242 | 866.48 | 0 | ANGANWADI | 76 | Delayed | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 07/09/2022 | 0 | 0
171 | SRI CHANDRAPUR Piped Water Supply Scheme (SM/12764) | SM/12764 | 703.14 | 2782 | NEW | 76 | Delayed | 40 | 20/09/2022 | 30/06/2025 | 11/12/2025 | 02/05/2023 | 283.93 | 283.93
172 | SAIDPUR Piped Water Supply Scheme (SM/12766) | SM/12766 | 846.78 | 2570 | NEW | 76 | Delayed | 53 | 20/09/2022 | 31/07/2025 | 11/12/2025 | 08/06/2023 | 445.35 | 445.35
173 | CHAKSUKUR PIPED WATER SUPPLY SCHEME. (SM/13719) | SM/13719 | 1149.66 | 2824 | NEW | 76 | Delayed | 65 | 17/11/2022 | 30/06/2025 | 11/12/2025 | 13/03/2023 | 746.74 | 746.74
174 | AUGMENTATION OF MALATIPUR PWSS (SM/09987) | SM/09987 | 699.42 | 2301 | AUGMENTATION | 77 | Delayed | 50 | 16/12/2021 | 31/12/2025 | 11/12/2025 | 01/08/2022 | 351.63 | 351.63
175 | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10207) | SM/10207 | 535.59 | 0 | SCHOOL | 77 | Delayed | 0 | 24/02/2022 | 31/07/2025 | 11/12/2025 | 01/04/2022 | 0 | 0
176 | Choupaldanga pipe water Supply Scheme (SM/12076) | SM/12076 | 902.87 | 3482 | NEW | 77 | Delayed | 44 | 02/09/2022 | 31/12/2025 | 11/12/2025 | 13/10/2022 | 393.77 | 393.77
177 | Mahil Piped Water Supply Scheme (SM/13733) | SM/13733 | 1895.5 | 4895 | NEW | 78 | Delayed | 37 | 17/11/2022 | 30/06/2025 | 11/12/2025 | 01/11/2022 | 694.78 | 694.78
178 | MATIHARPUR Piped Water Supply Scheme (SM/12769) | SM/12769 | 994.01 | 3531 | NEW | 78 | Delayed | 36 | 20/09/2022 | 31/12/2025 | 11/12/2025 | 10/03/2023 | 356.33 | 356.33
179 | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15074) | SM/15074 | 83.83 | 0 | AUGMENTATION | 78 | Delayed | 44 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 36.7 | 36.7
180 | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15073) | SM/15073 | 96.31 | 0 | AUGMENTATION | 78 | Delayed | 29 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 17/02/2023 | 28.03 | 28.03
181 | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15223) | SM/15223 | 2486.52 | 8288 | NEW | 78 | Delayed | 55 | 07/02/2023 | 31/12/2025 | 11/12/2025 | 15/06/2021 | 1356.57 | 1356.57
182 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme (SM/06867) | SM/06867 | 92.99 | 1748 | RETROFITTING | 78 | Delayed | 77 | 07/10/2020 | 31/12/2025 | 11/12/2025 | 12/10/2020 | 71.55 | 71.55
183 | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15063) | SM/15063 | 124.6 | 250 | AUGMENTATION | 78 | Delayed | 51 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 21/03/2023 | 63.56 | 65.36
184 | MEHERPUR PIPED WATER SUPPLY SCHEME (SM/15222) | SM/15222 | 1264.51 | 4342 | NEW | 78 | Delayed | 48 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 13/03/2023 | 612.38 | 612.38
185 | KHARBA PIPED WATER SUPPLY SCHEME. (SM/13793) | SM/13793 | 1220.74 | 5400 | NEW | 79 | Delayed | 52 | 22/11/2022 | 31/12/2025 | 11/12/2025 | 20/03/2023 | 639.64 | 640.37
186 | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/12761) | SM/12761 | 295.68 | 364 | AUGMENTATION | 79 | Delayed | 76 | 20/09/2022 | 30/06/2025 | 11/12/2025 | 07/12/2022 | 225.74 | 225.74
187 | HORGOA Piped Water Supply Scheme (SM/13432) | SM/13432 | 684.91 | 1714 | NEW | 79 | Delayed | 45 | 02/11/2022 | 30/06/2025 | 11/12/2025 | 08/05/2023 | 308.3 | 308.3
188 | WARI Piped Water Supply Scheme (SM/12077) | SM/12077 | 1077.41 | 3903 | NEW | 79 | Delayed | 54 | 02/09/2022 | 31/12/2025 | 11/12/2025 | 14/10/2022 | 584.73 | 584.73
189 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III (SM/09646) | SM/09646 | 394.52 | 7024 | RETROFITTING | 79 | Delayed | 69 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 27/12/2021 | 272.17 | 272.17
190 | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15091) | SM/15091 | 84.27 | 0 | AUGMENTATION | 79 | Delayed | 47 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 39.54 | 39.54
191 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block (SM/08283) | SM/08283 | 406.26 | 9031 | RETROFITTING | 80 | Delayed | 100 | 01/02/2021 | 31/07/2025 | 11/12/2025 | 15/01/2021 | 404.85 | 404.85
192 | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) (SM/10235) | SM/10235 | 546.3 | 0 | ANGANWADI | 80 | Delayed | 0 | 24/02/2022 | 31/03/2025 | 11/12/2025 | 01/04/2022 | 0 | 0
193 | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED (SM/15950) | SM/15950 | 491.4 | 850 | NEW | 80 | Delayed | 31 | 22/02/2023 | 31/07/2025 | 11/12/2025 | 24/03/2023 | 151.28 | 151.28
194 | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED (SM/15145) | SM/15145 | 31.42 | 0 | AUGMENTATION | 80 | Delayed | 65 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 06/03/2023 | 20.31 | 20.31
195 | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED (SM/15140) | SM/15140 | 768.6 | 2662 | NEW | 80 | Delayed | 32 | 06/02/2023 | 31/05/2025 | 11/12/2025 | 04/05/2023 | 247.86 | 247.86
196 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme (SM/06855) | SM/06855 | 73.75 | 1366 | RETROFITTING | 80 | Delayed | 70 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 12/10/2020 | 51.53 | 40.6
197 | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) (SM/10236) | SM/10236 | 562.14 | 0 | ANGANWADI | 80 | Delayed | 0 | 24/02/2022 | 30/06/2025 | 11/12/2025 | 01/04/2022 | 0 | 0
198 | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. (SM/13237) | SM/13237 | 123.52 | 0 | AUGMENTATION | 81 | On track | 90 | 14/10/2022 | 31/12/2026 | 11/12/2025 | 05/12/2022 | 111.15 | 111.15
199 | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda (SM/12762) | SM/12762 | 149.78 | 736 | AUGMENTATION | 81 | Delayed | 45 | 20/09/2022 | 30/06/2025 | 11/12/2025 | 07/12/2022 | 67.25 | 67.25
200 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme (SM/06869) | SM/06869 | 87.63 | 1642 | RETROFITTING | 81 | Delayed | 76 | 08/10/2020 | 30/06/2025 | 11/12/2025 | 12/10/2020 | 66.83 | 66.83
201 | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10384) | SM/10384 | 565.76 | 0 | SCHOOL | 82 | Delayed | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
202 | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda (SM/12338) | SM/12338 | 710.64 | 1607 | NEW | 82 | Delayed | 15 | 12/09/2022 | 31/12/2025 | 11/12/2025 | 21/09/2022 | 104.15 | 104.15
203 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme (SM/06866) | SM/06866 | 79.87 | 1488 | RETROFITTING | 82 | Delayed | 73 | 07/10/2020 | 31/12/2025 | 11/12/2025 | 10/11/2020 | 58.6 | 58.6
204 | Augmentation of Maheshpur piped water supply scheme (SM/12362) | SM/12362 | 1566.03 | 0 | AUGMENTATION | 82 | Delayed | 45 | 13/09/2022 | 31/12/2025 | 11/12/2025 | 23/12/2022 | 711.07 | 711.07
205 | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED (SM/15141) | SM/15141 | 131.66 | 550 | AUGMENTATION | 82 | Delayed | 70 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 27/09/2022 | 92.18 | 92.18
206 | KHARANGAPUR JABRA Piped Water Supply Scheme (SM/12183) | SM/12183 | 291.47 | 1378 | NEW | 83 | Delayed | 48 | 07/09/2022 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 139.54 | 139.54
207 | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE (SM/10304) | SM/10304 | 597.8 | 0 | ANGANWADI | 83 | Delayed | 0 | 02/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
208 | Augmentation of Bamongram piped water supply scheme. (SM/10138) | SM/10138 | 1038.64 | 3481 | AUGMENTATION | 83 | Delayed | 64 | 08/02/2022 | 30/06/2025 | 11/12/2025 | 15/06/2021 | 667.12 | 667.12
209 | GAURIA Piped Water Supply Scheme. (SM/12079) | SM/12079 | 1006.53 | 4278 | NEW | 83 | Delayed | 50 | 02/09/2022 | 31/12/2025 | 11/12/2025 | 22/09/2022 | 499.5 | 499.5
210 | UTTAR BHAKURIA Piped Water Supply Scheme. (SM/12881) | SM/12881 | 86.24 | 215 | NEW | 83 | Delayed | 51 | 23/09/2022 | 31/12/2025 | 11/12/2025 | 19/01/2023 | 43.59 | 43.59
211 | TALPUKUR Piped Water Supply Scheme (SM/12189) | SM/12189 | 730.06 | 2190 | NEW | 83 | Delayed | 62 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 10/05/2023 | 452.37 | 452.37
212 | Augmentation of Mirzapur Piped Water Supply Scheme (SM/10317) | SM/10317 | 1029.67 | 4880 | AUGMENTATION | 83 | Delayed | 61 | 04/03/2022 | 30/06/2025 | 11/12/2025 | 15/06/2021 | 632.21 | 633.09
213 | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15111) | SM/15111 | 272.73 | 869 | AUGMENTATION | 83 | Delayed | 45 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 20/03/2023 | 121.81 | 121.81
214 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme (SM/06854) | SM/06854 | 84.53 | 1580 | RETROFITTING | 84 | Delayed | 81 | 07/10/2020 | 31/12/2025 | 11/12/2025 | 10/11/2020 | 68.7 | 68.7
215 | BETAHAL Piped Water Supply Scheme (SM/12191) | SM/12191 | 526.99 | 1550 | NEW | 84 | Delayed | 46 | 07/09/2022 | 30/06/2025 | 11/12/2025 | 17/11/2022 | 240.04 | 240.04
216 | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15079) | SM/15079 | 166.09 | 350 | AUGMENTATION | 84 | Delayed | 70 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 23/03/2023 | 116.68 | 116.68
217 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme (SM/06868) | SM/06868 | 61.47 | 1122 | RETROFITTING | 84 | Delayed | 79 | 08/10/2020 | 30/06/2025 | 11/12/2025 | 10/12/2020 | 48.26 | 48.26
218 | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15105) | SM/15105 | 212.37 | 0 | AUGMENTATION | 84 | Delayed | 79 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 166.82 | 166.82
219 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme (SM/06872) | SM/06872 | 87.48 | 1639 | RETROFITTING | 84 | Delayed | 80 | 08/10/2020 | 30/06/2025 | 11/12/2025 | 12/10/2020 | 69.69 | 69.69
220 | PUTIA PWSS (SM/12194) | SM/12194 | 82.16 | 132 | NEW | 84 | Delayed | 67 | 07/09/2022 | 31/12/2025 | 11/12/2025 | 27/02/2023 | 55.3 | 55.3
221 | PASCHIM BHAGABANPUR Piped Water Supply Scheme (SM/12188) | SM/12188 | 867.35 | 2609 | NEW | 84 | On track | 54 | 07/09/2022 | 03/04/2026 | 11/12/2025 | 17/05/2023 | 470.44 | 471.29
222 | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15065) | SM/15065 | 216.09 | 0 | AUGMENTATION | 85 | Delayed | 81 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 17/02/2023 | 174.99 | 174.99
223 | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. (SM/10385) | SM/10385 | 639.24 | 0 | SCHOOL | 85 | Delayed | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
224 | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED (SM/15144) | SM/15144 | 144.97 | 600 | AUGMENTATION | 85 | Delayed | 42 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 13/04/2023 | 60.89 | 60.89
225 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar (SM/09649) | SM/09649 | 213.41 | 4560 | RETROFITTING | 85 | Delayed | 77 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 164.83 | 164.83
226 | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10238) | SM/10238 | 842.66 | 0 | SCHOOL | 85 | Delayed | 0 | 24/02/2022 | 31/07/2025 | 11/12/2025 | 22/04/2022 | 0 | 0
227 | SWARUPGANJ Piped Water Supply Scheme (SM/12185) | SM/12185 | 761.39 | 3192 | NEW | 85 | Delayed | 47 | 07/09/2022 | 31/12/2025 | 11/12/2025 | 28/02/2023 | 361.58 | 361.58
228 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo (SM/09654) | SM/09654 | 63.53 | 1423 | RETROFITTING | 85 | Delayed | 77 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 49 | 49
229 | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15110) | SM/15110 | 119.4 | 130 | AUGMENTATION | 85 | Delayed | 56 | 04/02/2023 | 30/06/2025 | 11/12/2025 | 29/03/2023 | 66.66 | 66.66
230 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block (SM/09587) | SM/09587 | 154.36 | 3660 | RETROFITTING | 86 | Delayed | 81 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 14/09/2021 | 125.39 | 125.34
231 | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. (SM/10379) | SM/10379 | 725.43 | 0 | ANGANWADI | 86 | Delayed | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 27/01/2021 | 0 | 0
232 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block (SM/09660) | SM/09660 | 161.36 | 3600 | RETROFITTING | 87 | Delayed | 60 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 96.86 | 96.86
233 | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15201) | SM/15201 | 196.28 | 450 | AUGMENTATION | 87 | Delayed | 57 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 20/03/2023 | 111.09 | 111.69
234 | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. (SM/15086) | SM/15086 | 116.57 | 0 | AUGMENTATION | 87 | Delayed | 80 | 04/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 93.75 | 93.75
235 | Sharanpur Piped Water Supply Scheme (SM/12631) | SM/12631 | 383.2 | 1080 | NEW | 87 | Delayed | 45 | 19/09/2022 | 31/12/2025 | 11/12/2025 | 17/11/2022 | 171.42 | 171.42
236 | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. (SM/15197) | SM/15197 | 164.65 | 0 | AUGMENTATION | 87 | Delayed | 82 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 21/02/2023 | 134.36 | 134.36
237 | Augmentation of Bhaluka Fatepur Piped water supply scheme (SM/10137) | SM/10137 | 1077.25 | 4734 | AUGMENTATION | 87 | Delayed | 40 | 08/02/2022 | 30/06/2025 | 11/12/2025 | 15/06/2021 | 435.88 | 435.88
238 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc (SM/09588) | SM/09588 | 354.85 | 8954 | RETROFITTING | 88 | Delayed | 83 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 293.09 | 293.09
239 | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. (SM/12632) | SM/12632 | 335.31 | 698 | NEW | 88 | Delayed | 59 | 19/09/2022 | 31/12/2025 | 11/12/2025 | 17/11/2022 | 197.04 | 198.81
240 | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/11587) | SM/11587 | 582.14 | 1523 | NEW | 89 | On track | 31 | 22/07/2022 | 31/12/2025 | 11/12/2025 | 22/03/2022 | 179.17 | 179.17
241 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme (SM/06864) | SM/06864 | 64.66 | 1186 | RETROFITTING | 89 | Delayed | 84 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 31/08/2020 | 54.51 | 54.51
242 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme (SM/06849) | SM/06849 | 73.35 | 1548 | RETROFITTING | 90 | On track | 82 | 08/10/2020 | 31/12/2025 | 11/12/2025 | 09/11/2020 | 60 | 60
243 | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) (SM/10205) | SM/10205 | 492.74 | 0 | SCHOOL | 90 | Delayed | 0 | 24/02/2022 | 31/03/2025 | 11/12/2025 | 24/05/2022 | 0 | 0
244 | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (SM/10206) | SM/10206 | 357.06 | 0 | SCHOOL | 90 | Delayed | 0 | 24/02/2022 | 30/06/2025 | 11/12/2025 | 26/04/2022 | 0 | 0
245 | SAHAPUR Piped Water Supply Scheme (SM/12187) | SM/12187 | 112.27 | 397 | NEW | 90 | On track | 55 | 06/09/2022 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 61.51 | 62.46
246 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme (SM/06986) | SM/06986 | 35.94 | 790 | RETROFITTING | 90 | On track | 97 | 11/11/2020 | 31/12/2025 | 11/12/2025 | 11/11/2020 | 34.96 | 34.96
247 | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Eastern Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (72 nos. AWCs in English Bazar Block (SM/10233) | SM/10233 | 570.05 | 0 | ANGANWADI | 90 | Delayed | 0 | 24/02/2022 | 30/06/2025 | 11/12/2025 | 23/05/2022 | 0 | 0
248 | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. (SM/15960) | SM/15960 | 49.53 | 106 | NEW | 90 | On track | 57 | 22/02/2023 | 31/12/2025 | 11/12/2025 | 30/03/2023 | 28.27 | 28.27
249 | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) (SM/15142) | SM/15142 | 622.76 | 0 | AUGMENTATION | 91 | Delayed | 91 | 06/02/2023 | 30/04/2025 | 11/12/2025 | 15/02/2023 | 566.29 | 540.41
250 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III (SM/09653) | SM/09653 | 445.56 | 9815 | RETROFITTING | 91 | On track | 83 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 368.34 | 368.34
251 | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10306) | SM/10306 | 859.76 | 0 | ANGANWADI | 91 | On track | 0 | 02/03/2022 | 31/12/2025 | 11/12/2025 | 24/06/2020 | 0 | 0
252 | Augmentation of Tilasan Piped water supply scheme (SM/09567) | SM/09567 | 331.85 | 1568 | AUGMENTATION | 92 | On track | 68 | 22/11/2021 | 31/12/2025 | 11/12/2025 | 09/09/2021 | 226.09 | 226.09
253 | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. (SM/10383) | SM/10383 | 760.43 | 0 | SCHOOL | 92 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
254 | JIGIN Piped Water Supply Scheme (SM/13430) | SM/13430 | 234.18 | 459 | NEW | 92 | On track | 61 | 02/11/2022 | 31/12/2025 | 11/12/2025 | 20/03/2023 | 142.67 | 142.67
255 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme (SM/06865) | SM/06865 | 43.73 | 770 | RETROFITTING | 92 | Delayed | 95 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 12/10/2020 | 41.39 | 41.39
256 | SERBABAR BALARAMPUR Piped Water Supply Scheme (SM/12184) | SM/12184 | 834.65 | 2967 | NEW | 92 | On track | 33 | 07/09/2022 | 31/12/2025 | 11/12/2025 | 18/05/2023 | 271.51 | 271.51
257 | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) (SM/10234) | SM/10234 | 514.63 | 0 | ANGANWADI | 92 | Delayed | 0 | 24/02/2022 | 31/03/2025 | 11/12/2025 | 01/04/2022 | 0 | 0
258 | BAIRAT Piped Water Supply Scheme (SM/12743) | SM/12743 | 939.2 | 3235 | NEW | 93 | On track | 72 | 20/09/2022 | 31/12/2025 | 11/12/2025 | 17/11/2022 | 672.82 | 672.82
259 | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. (SM/10386) | SM/10386 | 558.44 | 0 | SCHOOL | 93 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
260 | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10305) | SM/10305 | 503.66 | 0 | ANGANWADI | 93 | On track | 0 | 02/03/2022 | 31/12/2025 | 11/12/2025 | 07/09/2022 | 0 | 0
261 | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10307) | SM/10307 | 570.94 | 0 | ANGANWADI | 94 | On track | 0 | 02/03/2022 | 31/12/2025 | 11/12/2025 | 31/08/2022 | 0 | 0
262 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme (SM/06871) | SM/06871 | 54.06 | 975 | RETROFITTING | 94 | On track | 94 | 08/10/2020 | 31/12/2025 | 11/12/2025 | 12/10/2020 | 50.94 | 50.94
263 | NABAGRAM Piped Water Supply Scheme (SM/12767) | SM/12767 | 876.56 | 3517 | NEW | 95 | On track | 42 | 20/09/2022 | 31/12/2025 | 11/12/2025 | 02/05/2023 | 366.94 | 366.94
264 | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) (SM/10204) | SM/10204 | 742.68 | 0 | SCHOOL | 95 | Delayed | 0 | 24/02/2022 | 31/03/2025 | 11/12/2025 | 28/04/2022 | 0 | 0
265 | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10303) | SM/10303 | 705.27 | 0 | ANGANWADI | 95 | On track | 0 | 02/03/2022 | 31/12/2025 | 11/12/2025 | 03/09/2019 | 0 | 0
266 | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE (SM/10244) | SM/10244 | 792.59 | 0 | ANGANWADI | 96 | On track | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 27/12/2021 | 0 | 0
267 | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE (SM/10215) | SM/10215 | 671.69 | 0 | ANGANWADI | 96 | On track | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 24/06/2020 | 0 | 0
268 | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10382) | SM/10382 | 521.68 | 0 | SCHOOL | 96 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
269 | INSTALLATION OF 18 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT SCHOOLS OF OLD MALDA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10241) | SM/10241 | 106.94 | 0 | SCHOOL | 96 | On track | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 06/04/2022 | 0 | 0
270 | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10216) | SM/10216 | 787.99 | 0 | ANGANWADI | 96 | On track | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 13/06/2022 | 0 | 0
271 | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15108) | SM/15108 | 100.43 | 150 | AUGMENTATION | 97 | On track | 49 | 04/02/2023 | 31/10/2025 | 11/12/2025 | 23/03/2023 | 48.96 | 48.96
272 | OLTARA PIPED WATER SUPPLY SCHEME. (SM/13718) | SM/13718 | 1253.79 | 3535 | NEW | 97 | Delayed | 62 | 17/11/2022 | 30/06/2025 | 11/12/2025 | 22/03/2023 | 772.05 | 772.65
273 | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. (SM/10389) | SM/10389 | 297.04 | 0 | SCHOOL | 97 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 21/07/2022 | 0 | 0
274 | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. (SM/10387) | SM/10387 | 665.38 | 0 | SCHOOL | 98 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 21/07/2022 | 0 | 0
275 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme (SM/06863) | SM/06863 | 54.86 | 991 | RETROFITTING | 98 | On track | 97 | 07/10/2020 | 31/12/2025 | 11/12/2025 | 31/08/2020 | 53 | 52.35
276 | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. (SM/10245) | SM/10245 | 731.13 | 0 | ANGANWADI | 98 | On track | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
277 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme (SM/06858) | SM/06858 | 59.54 | 1084 | RETROFITTING | 98 | Delayed | 97 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 11/12/2020 | 57.78 | 46.32
278 | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. (SM/15190) | SM/15190 | 103.91 | 0 | AUGMENTATION | 99 | On track | 63 | 06/02/2023 | 31/12/2025 | 11/12/2025 | 17/02/2023 | 65.85 | 65.85
279 | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE (SM/10247) | SM/10247 | 644.82 | 0 | ANGANWADI | 99 | On track | 0 | 24/02/2022 | 31/12/2025 | 11/12/2025 | 12/07/2022 | 0 | 0
280 | MABARAKPUR PWSS (SM/12197) | SM/12197 | 704.22 | 2608 | NEW | 99 | On track | 41 | 07/09/2022 | 31/12/2025 | 11/12/2025 | 19/05/2023 | 288.75 | 288.75
281 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme (SM/06856) | SM/06856 | 86.33 | 1616 | RETROFITTING | 99 | Delayed | 98 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 10/11/2020 | 85.02 | 85.02
282 | RAHIMPUR Piped Water Supply Scheme (SM/14174) | SM/14174 | 1077.41 | 2638 | NEW | 99 | On track | 73 | 09/01/2023 | 31/12/2025 | 11/12/2025 | 10/04/2023 | 783.86 | 783.86
283 | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. (SM/10388) | SM/10388 | 594.09 | 0 | SCHOOL | 99 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
284 | DILALBATI Piped Water Supply Scheme. (SM/15903) | SM/15903 | 292.15 | 521 | NEW | 99 | On track | 48 | 20/02/2023 | 31/12/2025 | 11/12/2025 | 20/03/2023 | 139.08 | 139.08
285 | BHADAR Piped Water Supply Scheme (SM/12768) | SM/12768 | 660.39 | 2200 | NEW | 99 | On track | 80 | 20/09/2022 | 31/12/2025 | 11/12/2025 | 17/05/2023 | 530.27 | 530.27
286 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo (SM/09648) | SM/09648 | 242.47 | 4934 | RETROFITTING | 99 | On track | 100 | 23/11/2021 | 31/12/2025 | 11/12/2025 | 24/11/2021 | 242.26 | 242.26
287 | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. (SM/10381) | SM/10381 | 665.38 | 0 | SCHOOL | 99 | On track | 0 | 23/03/2022 | 31/12/2025 | 11/12/2025 | 18/01/2021 | 0 | 0
288 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme (SM/06859) | SM/06859 | 71.47 | 1321 | RETROFITTING | 100 | 100% Physical | 85 | 07/10/2020 | 31/03/2023 | 11/12/2025 | 10/11/2020 | 61.08 | 61.08
289 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme (SM/06860) | SM/06860 | 93.04 | 1749 | RETROFITTING | 100 | 100% Physical | 58 | 07/10/2020 | 30/06/2025 | 11/12/2025 | 29/09/2020 | 54.36 | 54.36
290 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block (SM/06848) | SM/06848 | 85.66 | 1733 | RETROFITTING | 100 | 100% Physical | 100 | 08/10/2020 | 30/06/2025 | 11/12/2025 | 14/10/2020 | 85.66 | 85.66
Total |  |  | 333247.6 | 918158 | [8 empty] | 92423.72 | 92328.55