## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . | SM/06627 | Support-WQMSP | Running of District Laboratory for Physical,Chemical and Bacteiological test of water sample under Scheme, dist Darjeeling under Siliguri W/S division, PHE Dte. 1st sept 2021 to 31st August 2022. |  |  | ORD/000573/2020-2021 | 939/SWSD | 14/08/2020 | 14/08/2020 | TALUKDAR ENTERPRISE | 8.67 | 4.34 | 49.99 | 0
2 | DARJEELING |  | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . | SM/06627 | Support-WQMSP | Supply of Labortory Instruments/Equipments for Darjeeling District Laboratory at Fulbari under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000301/2022-2023 | 2837/SWSD | 17/03/2023 | 01/04/2023 | LAB SOLUTION | 0.95 | 0.95 | 100 | 100
3 | DARJEELING |  | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . | SM/06627 | Support-WQMSP | Continuation order for Supply of Chemical, Consumables for Darjeeling District Laboratories under Siliguri Water Supply Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000191/2024-2025 | 3360/SWSD | 11/12/2024 | 26/12/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.32 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . | SM/06627 | Support-WQMSP | Continuation Order for Supply of Chemicals, Consumables for Darjeeling District Laboratories under Siliguri Water Supply Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000407/2023-2024 | 656/SWSD | 12/03/2024 | 27/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.22 | 0 | 0 | 0
Total | [13 empty] | 13.16 | 5.28 | 40.13