## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme | SM/07030 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Barsadvita habitation Adhikari Barsadvita and village Mayanaguri habitation Moynaguri of Barsadvita piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000058/2020-2021 | 1014/SWSD | 11/12/2020 | 20/01/2021 | VIJAY KUMAR ARORA | 33.45 | 57.9 | 173.1 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme | SM/07030 | Retrofitting | Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission JJM and Jal Swapna under Command area village Maynaguri habitation Pitha bachi Ramchndra village Kelabari habitation Damravita Kalabari and village Alokjhari habitation Surya Mohan of Barsadvita piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000059/2020-2021 | 1015/SWSD | 11/12/2020 | 20/01/2021 | M/S G.C. CONSTRUCTION & CO. | 35.14 | 14.87 | 42.32 | 20
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme | SM/07030 | Retrofitting | Issue of fuel for office vehicles of Executive Engineer Siliguri W/S division PHE Dte. |  |  | BILL/00571/2023-2024 | BP-2023-24-196 | 28/03/2024 | 28/03/2024 | SONA PETROL PUMP | 0.35 | 0 | 0 | 0
Total | [13 empty] | 68.94 | 72.77 | 105.56