## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Matidhar Bijmillini T.E and Pathoria Habitation of Paschim Madati Piped water Supply Scheme (Part - A) | SM/07031 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Motidhar Bijmillini T E Part A of Paschim Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000067/2020-2021 | 1081/SWSD | 18/12/2020 | 27/01/2021 | M/S G.C. CONSTRUCTION & CO. | 33.72 | 25.14 | 74.55 | 85
Total | [13 empty] | 33.72 | 25.14 | 74.55