## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | SM/07032 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Pathoria Ramprasad Sing Rup Sing and Sat of Paschim Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000068/2020-2021 | 1082/SWSD | 18/12/2020 | 17/01/2021 | M/S G.C. CONSTRUCTION & CO. | 28.59 | 4.97 | 17.38 | 89
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | SM/07032 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | SM/07032 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 1671/SWSD | 28/12/2021 |  | Resource Division | 3.17 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | SM/07032 | Retrofitting | Laying distribution system for Paschim Madati piped W/S Scheme at Phansidewa block ( Part-I ) |  |  | ORD/000243/2018-2019 | 1005/SWSD | 20/09/2018 |  | SHRI ANUP BASU | 25.06 | 5 | 19.94 | 0
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | SM/07032 | Retrofitting | Laying distribution system for Paschim Madati w/s scheme at Phansidewa block ( Part-H ) |  |  | ORD/000240/2018-2019 | 1004/SWSD | 20/09/2018 |  | NARENDRA KUMAR | 8.8 | 0 | 0 | 0
Total | [13 empty] | 165.99 | 9.97 | 6