## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeeven Mission & Jal Swapno Programme for Kawakhali Piped Water Supply Scheme at Matigar Block under Siliguri Sub-Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000013/2021-2022 | 707/SWSD | 03/08/2021 | 01/12/2021 | DEBASHIS SINHA | 34.96 | 31.95 | 91.39 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | Retrofitting | Providing Functional House Hold Top Connection under Jal Jeevan Mission & Jal Swapno Programme for AWC¿s , Schools etc. under Kawakhali Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 12 |  |  | ORD/000036/2021-2022 | 996/SWSD | 08/09/2021 | 23/09/2021 | S.G.CONSTRUCTION | 4.71 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | Retrofitting | Providing Functional House Hold Top Connection under Jal Jeevan Mission & Jal Swapno Programme for AWC¿s , Schools etc. under Bairagi Piped Water Supply Scheme at Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 13 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000037/2021-2022 | 1002/SWSD | 09/09/2021 | 24/09/2021 | M/S ROYAL ENTERPRISE | 4.71 | 0 | 0 | 100
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | Retrofitting | Providing functional household tap connection under Jal Jeevan Mission & Jal Swapno programme for Kawakhali Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000087/2021-2022 | 1637/SWSD | 28/12/2021 | 12/01/2022 | KAMAL GHOSH | 4.31 | 4.21 | 97.66 | 100
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | Retrofitting | Minor repairing works in connection with functional household tap connection at Kawakhali piped W/S Scheme at Matigara Blockunder siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000229/2022-2023 | 543/SSD | 19/12/2022 | 03/01/2023 | KAMAL GHOSH | 0.77 | 0.71 | 91.49 | 100
6 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | Retrofitting | Additional work of providing functional household tap connection under Jal jeevan Mission and Jal Swapno for Kawakhali piped water supply scheme at Matigara Block under Siliguri Sub division,P.H.Engineering Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000253/2022-2023 | 508/SSD | 16/11/2022 | 01/12/2022 | DEBASHIS SINHA | 1.1 | 1.09 | 99.11 | 0
Total | [13 empty] | 50.57 | 37.96 | 75.06