## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-I) Piped water Supply Scheme | SM/07034 | Retrofitting | Additional laying of 90mm dia pipeline for FHTC Jal swapno programme of Madhya Bansgaon w/s scheme under Siliguri subdivision, PHE. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000261/2022-2023 | 2064/SWSD | 11/01/2023 | 10/02/2023 | NARENDRA KUMAR | 4.42 | 2.21 | 50 | 100
Total | [13 empty] | 4.42 | 2.21 | 50