## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme | SM/07038 | Retrofitting | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Swapno Programme for Lalman mouza (Part) of Lalman W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000128/2021-2022 | 1009/SWSD | 10/09/2021 | 25/09/2021 | SEBU CHAKRABORTY | 4.84 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme | SM/07038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeeven Mission & Jal SWapno Programme for Lalman Mouza (Part) of Lalman Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub-Division, P.H.E. Dte. (Part-A) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000012/2021-2022 | 706/SWSD | 03/08/2021 | 01/12/2021 | RAJEEV RANJAN OJHA | 32.5 | 13.11 | 40.33 | 43
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme | SM/07038 | Retrofitting | Issue of fuel for Office of the Executive Engineer and Assistant Engineers of Siliguri W/S Division, PHE Dte. from 17th March 2024 to 30th May 2024 |  |  | BILL/00124/2024-2025 | BP-2024-25-41 | 08/07/2024 | 08/07/2024 | SONA PETROL PUMP | 1.87 | 0 | 0 | 0
Total | [13 empty] | 39.2 | 13.11 | 33.44