## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Badang, Pakridhuka, Sapti and Jayantyika 318 Nos house hold) of Purba Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000066/2020-2021 | 1080/SWSD | 18/12/2020 | 22/01/2021 | SUBIR CH. CHOWDHURY | 30.22 | 24.34 | 80.53 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000307/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 0.56 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 1670/SWSD | 28/12/2021 | 28/12/2021 | Resource Division | 1.42 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | Retrofitting | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | Retrofitting | Providing functional house hold tasp connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapno) under command area (Habitation Badang Jayantika Sapti Alim Ganj & Chowdhury Gachh) due to Y.D.U of Purba Madati Piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000080/2021-2022 | 1828/SWSD | 13/01/2022 | 07/02/2022 | BIMAN DUTTA | 10.38 | 0 | 0 | 20
6 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | Retrofitting | Continuation order for Supply of 01 (one) no. Maxi Cab with Engine Capacity less than or equal to 2000 C.C. with Air Condition on hire basis (for monthly hiring) including driver under Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. (With valid Taxi permit and other necessary documents as per norms of Zonal R.T.O) For 03 (three months) with effect from 01.01.2025 to 31.03.2025. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000264/2024-2025 | 3610/SWSD | 31/12/2024 | 31/03/2025 | S S CONSTRUCTIONS | 0.47 | 0 | 0 | 0
Total | [13 empty] | 174.33 | 24.34 | 13.96