## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme | SM/07045 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Churaman Habitation Churaman, village Thuna Habitation Thuna village Thuna Chhat Habitation Thunar Chhat and village Baramala Habitation Baramala of Bhalamanshi Piped Water Supply Scheme and Allied works at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000076/2020-2021 | 1090/SWSD | 18/12/2020 | 01/02/2021 | SHRI ANUP BASU | 37.37 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme | SM/07045 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Fulbar Habitation Fulbar and village Bhalamanshi Habitation Charge more of Bhalamanshi Piped Water Supply Scheme and Allied works at Phansidewa block under Siliguri Sub Division PHE Dte (3rd CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000009/2021-2022 | 695/SWSD | 02/08/2021 | 16/09/2021 | SHRI ANUP BASU | 36.74 | 0 | 0 | 30
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme | SM/07045 | Retrofitting | Acceptance cum work order for installation of the Iron removal filtration plant including platform and drain with necessary connection and blower room 01 No. at Bhalamanshi Piped water supply Scheme H/W Site within Phansidewa Block under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000189/2024-2025 | 3155/SWSD | 25/11/2024 | 25/12/2024 | PALLAB BHOWAL | 26.07 | 0 | 0 | 0
Total | [13 empty] | 100.19 | 0 | 0