## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | SM/07046 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapno under Shyamdhan and adjoining mouas WS Scheme command area at Badra and Balijhora and laying wash out pipeline from 2nd T W IEP upto nearest culvert and also laying HDPE piped at Shyamdhan command area of the Shyamdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000048/2021-2022 | 1219/SWSD | 01/11/2021 | 21/11/2021 | M/S SHIVAJI ROY | 12.99 | 1.05 | 8.07 | 100
2 | DARJEELING |  | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | SM/07046 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 06/01/2023 | DEBRAJ ENTERPRISE | 1.63 | 0 | 0 | 100
3 | DARJEELING |  | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | SM/07046 | Retrofitting | Providing functional household tap connection FHTC and laying 90 mm OD HDPE pipe from house of Dulal Biswas to house of Sunil Sikdar and house of Kalipada Mondal to Zamatulla SSK at village Shyamdhan and habitation Shyamdhan and allied worksw of the Shyamdhan piped WS scheme under Siliguri Sub Division PHE Dte Kharibari block. SL. NO. 08. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000082/2021-2022 | 1830/SWSD | 13/01/2022 | 28/01/2022 | BUDDHADEV NAG | 6.5 | 5.34 | 82.22 | 100
4 | DARJEELING |  | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | SM/07046 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 1672/SWSD | 28/12/2021 |  | Resource Division | 0.05 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | SM/07046 | Retrofitting | Acceptance cum work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000376/2023-2024 | 646/SWSD | 11/03/2024 | 25/04/2024 | ARUN KUMAR SHRIVASTAVA | 81.01 | 0 | 0 | 0
Total | [13 empty] | 102.18 | 6.39 | 6.25