## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) | SM/07047 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Uttar Ramdhan habitation Projote of Uttar Ramdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000057/2020-2021 | 1013/SWSD | 11/12/2020 | 15/01/2021 | NARENDRA KUMAR | 32.96 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) | SM/07047 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Antaram village habitation Vulka Bajarur Chhat village habitation Bazarir chat Bhulka and Gandagal village habitation Barodil Saram and Chhoto Dil saran of Uttar Ramdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000053/2020-2021 | 1009/SWSD | 11/12/2020 | 10/01/2021 | M/S DEBRAJ ENTERPRISE | 24.49 | 10.85 | 44.29 | 100
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) | SM/07047 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 06/01/2023 | DEBRAJ ENTERPRISE | 1.63 | 0.39 | 24.22 | 100
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) | SM/07047 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Gandagal village habitation Dil saram Dulal Gandogle and village Jibansing habitation Babuchhan Dilsaram and Jiban sing of Uttar Ramdhan and adjoining mouzas Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2020-2021 | 1011/SWSD | 11/12/2020 | 20/01/2021 | M/S DEBRAJ ENTERPRISE | 37.92 | 44.01 | 116.05 | 100
Total | [13 empty] | 97 | 55.25 | 56.96