## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Gandagal village habitation Dil saram Dulal Gandogle and village Jibansing habitation Babuchhan Dilsaram and Jiban sing of Uttar Ramdhan and adjoining mouzas Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2020-2021 | 1011/SWSD | 11/12/2020 | 20/01/2021 | M/S DEBRAJ ENTERPRISE | 37.92 | 4.51 | 11.91 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area village Madan habitation Madan and village Uttar Ramdhan habitation Goursing and Wairish of Uttar Ramdhan and adjoining Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000054/2020-2021 | 1010/SWSD | 11/12/2020 | 15/01/2021 | M/S DEBRAJ ENTERPRISE | 37.87 | 42.26 | 111.61 | 100
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 06/01/2023 | DEBRAJ ENTERPRISE | 1.63 | 0.07 | 4.14 | 100
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | Retrofitting | Work order for construction of 2 nos. of boundary wall, IEP (45 cu.3m/Hr. for Zone-I & 40 cu.m for Zone-II) including blower rooms Uttar Ramdhan PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000287/2023-2024 | 336/SWSD | 09/02/2024 | 09/04/2024 | BISWADEEP CONSTRUCTION | 46.36 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | Retrofitting | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2022 TO 31.08.2022. (FOR EXECUIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) (i.e. SIX MONTHS) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000162/2021-2022 | 2301/SWSD | 28/02/2022 | 31/08/2022 | SUBIR CH. CHOWDHURY | 0.88 | 1.69 | 191.5 | 100
6 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | Retrofitting | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF UTTAR RAMDHAN PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000053/2023-2024 | 246/SSD | 05/06/2023 | 15/06/2023 | ENVIROTECH SOLUTIONS | 3.58 | 3.55 | 99.16 | 100
Total | [13 empty] | 128.24 | 52.08 | 40.61