## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Pelku (JL No-71) & Thiknikata (JL No.-74) Mouzas of Kawakhali Pipe water Supply Scheme | SM/07213 | Retrofitting | Acceptance cum work order for Providing Functional House Hold Tap Connection under Jal Jeevan Mission Programme for PELKU (JL No. 71) and TIKNIKATA (JL No. 74) mouzas of KAWAKHALI Piped Water Supply Scheme at Matigara block under Siliguri W/S Division, P.H.E. Dte.(1st CALL) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000117/2023-2024 | 1196/SWSD | 10/08/2023 | 24/10/2023 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 74.02 | 0 | 0 | 0
Total | [13 empty] | 74.02 | 0 | 0