## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Providing functional house hold tap connection under Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 03 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000077/2021-2022 | 1825/SWSD | 13/01/2022 | 22/02/2022 | AKASH ENTERPRISE | 25.43 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 | 18/02/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Providing Functional Household Tap Connection under Jal Swapna Programme for Purba Bansgaon Village of PURBA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART A | Assistant Engineer(Civil) |  | ORD/000002/2021-2022 | 696/SWSD | 02/08/2021 | 06/09/2021 | AKASH ENTERPRISE | 30.21 | 46.15 | 152.79 | 100
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Laying of new PVC line at along with other repairing works at Matigara Habitation, Purba Bansgaon water supply scheme Phansidewa Block, Siliguri W/S Division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000233/2022-2023 | 512/SSD | 16/11/2022 | 26/11/2022 | SHIVNATH DEY | 0.36 | 0.35 | 97.67 | 100
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 1667/SWSD | 28/12/2021 | 28/12/2021 | Resource Division | 2.13 | 0 | 0 | 0
Total | [13 empty] | 158.49 | 46.51 | 29.34