## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 | 18/02/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Providing Functional Household Tap Connection under Jal Swapna Programme for Purba Bansgaon Village of PURBA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART A | Assistant Engineer(Civil) |  | ORD/000002/2021-2022 | 696/SWSD | 02/08/2021 | 06/09/2021 | AKASH ENTERPRISE | 30.21 | 46.15 | 152.79 | 100
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Laying of new PVC line at along with other repairing works at Matigara Habitation, Purba Bansgaon water supply scheme Phansidewa Block, Siliguri W/S Division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000233/2022-2023 | 512/SSD | 16/11/2022 | 26/11/2022 | SHIVNATH DEY | 0.36 | 0.35 | 97.67 | 100
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 1667/SWSD | 28/12/2021 | 28/12/2021 | Resource Division | 2.13 | 0 | 0 | 0
Total | [13 empty] | 133.06 | 46.51 | 34.95