## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission & Jal Swapno Programme for bharatsing & Putimari of Lalman Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub-Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000014/2021-2022 | 708/SWSD | 03/08/2021 | 01/11/2021 | M/S UTPAL CHAKRABORTY & CO. | 21.03 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | Additional work in connection with Providing FHTC under Jal Jeevan Mission and Jal Swapno Programme for Bharatsing and Putimari of Lalman Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000121/2021-2022 | 2362/SWSD | 08/03/2022 | 23/03/2022 | M/S UTPAL CHAKRABORTY & CO. | 6.9 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | Hiring of I (one) nos Disel Motor CAB on monthly besis for the Assistant Engineer II ,Office of Executive Engineer under Siligui W/S Division, P.H.E Dte..With effect from 25.08.2023 to 24.02.2024 .Total 184 days. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000195/2023-2024 | 1427/SWSD | 24/08/2023 | 24/02/2024 | BUDDHADEV NAG | 0.88 | 0 | 0 | 100
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | Further continuation order for hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of the Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.01.2024 to 31.07.2024 for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte. i.e. 07 (seven) months. |  |  | ORD/000325/2023-2024 | 2398/SWSD | 16/12/2023 | 16/07/2024 | HIMADRI DAM | 1.03 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | ISSUE OF FULE FOR OFFICE VEHICLES OF EXECUTIVWE ENGINEER SILIGURI W/S DIVISION PHE DTE |  |  | BILL/00539/2023-2024 | BP-2023-24-184 | 13/03/2024 | 13/03/2024 | SONA PETROL PUMP | 1.4 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | Continuation order of Hiring of I (one) nos Diesel Motor CAB on monthly basis for the Assistant Engineer II ,Office of Executive Engineer under Siligui W/S Division, P.H.E Dte..for the month of 25/02/2024 to 22/08/2024 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000400/2023-2024 | 225/SWSD | 30/01/2024 | 28/07/2024 | BUDDHADEV NAG | 0.88 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | Retrofitting | Continuation order of Hiring of 01 (one) nos Disel Motor CAB on monthly basis for the Assistant Engineer-II, Office of the Executive Engineer under Siliguri W/S Division, P.H.E. Dte. for the month of 01.09.2024 to 28.02.2025. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000184/2024-2025 | 2161/SWSD | 21/08/2024 | 17/02/2025 | BUDDHADEV NAG | 0.88 | 0 | 0 | 0
Total | [13 empty] | 32.99 | 0 | 0